## Table 1
METRIC NUMBER | UTILITY ID | SUBMISSION DATE | ACTIVITY CLASSIFICATION | PROJECT START DATE | PROJECT END DATE | WMP ACTIVITY NAME | ACTIVITY DESCRIPTION | ACTIVITY OBJECTIVE | WMP CATEGORY | WMP INITIATIVE | WMP INITIATIVE NAME IF OTHER | WMP SECTION | UTILITY MITIGATION ACTIVITY TRACKING ID | WMP ACTIVITY CODE | WMP PAGE NUMBER | RISK TARGET REDUCTION | MIDYEAR TARGET (YES / NO) | QUANT TARGET UNITS | COMMENTS | REPORTING YEAR | REPORTING QUARTER | QUANTITATIVE ACTUAL PROGRESS Q1 | QUANTITATIVE ACTUAL PROGRESS Q1-2 | QUANTITATIVE ACTUAL PROGRESS Q1-3 | QUANTITATIVE ACTUAL PROGRESS Q1-4 | QUALITATIVE ACTUAL PROGRESS Q1 | QUALITATIVE ACTUAL PROGRESS Q1-2 | QUALITATIVE ACTUAL PROGRESS Q1-3 | QUALITATIVE ACTUAL PROGRESS Q1-4 | STATUS | CORRECTIVE ACTIONS IF DELAYED
1010000000 | SCE | 2026-02-01 | Program |  |  | Wildfire Safety Community Meetings | Community meetings, primarily in SCE's HFRA, to share information about SCE’s WMP efforts | Share grid hardening, PSPS, and emergency preparedness updates, and highlight SCE's various programs, services, and resources. Also, receive direct feedback from meeting participants | Community Outreach and Engagement | Public Outreach and Education Awareness Program |  | 8.5.2.1 | DEP-1 | Community Outreach and Engagement_Public Outreach and Education Awareness Program_DEP-1_2023 | 585 |  | No | # of meetings | Risk Target Reduction not applicable. | 2025 | 4 | 0 | 2 | 11 | 14 |  |  |  |  | Completed
1010000001 | SCE | 2026-02-01 | Program |  |  | SCE Emergency Response Training | Technical training programs that prepare employees to perform their jobs safely, comply with regulatory requirements and laws, maintain system reliability, and leverage new technology | Provide effective emergency response and restore service during and after a major event. | Emergency Preparedness | Emergency Preparedness Plan |  | 8.4.2.2.1 | DEP-2 | Emergency Preparedness_Emergency Preparedness Plan_DEP-2_2023 | 540 |  | No |  | Risk Target Reduction not applicable. | 2025 | 4 |  |  |  |  | In Q1,100% of customers enrolled received their battery within 30 calendar days | As of Q2, 2025 PSPS Training and Exercise Requalification Series is complete.​ | SCE met target. 2025 PSPS Training and Exercise Requalification Series is complete. ​ | SCE met target. 2025 PSPS Training and Exercise Requalification Series is complete. | Completed
1010000002 | SCE | 2026-02-01 | Program |  |  | Customer Research and Education | SCE develops surveys to capture customer feedback on SCE’s wildfire mitigation initiatives with a special emphasis on PSPS activities | Improve its understanding of how to reduce impacts of wildfires, PSPS, and wildfire mitigation work for its customers | Community Outreach and Engagement | Public Outreach and Education Awareness Program |  | 8.5.2.3 | DEP-4 | Community Outreach and Engagement_Public Outreach and Education Awareness Program_DEP-4_2023 | 586 |  | No | # of surveys | Risk Target Reduction not applicable. | 2025 | 4 | 0 | 1 | 1 | 3 |  |  |  |  | Completed
1010000003 | SCE | 2026-02-01 | Project | 2026-01-01 | 2026-12-31 | Aerial Suppression | SCE funds up to four aerial firefighting helicopters, support personnel and equipment to bolster firefighting capabilities | Fire suppression within SCE’s service area | Emergency Preparedness | External Collaboration and Coordination |  | 8.4.3.3.1 | DEP-5 | Emergency Preparedness_External Collaboration and Coordination_DEP-5_2023 | 556 | Wildfire vulnerability | No |  |  | 2025 | 4 |  |  |  |  | SCE met target in Q1. Contracts were issued at the end of 2024, and final payment was provided to the agencies in January 2025. | SCE met target. Contracts were issued at the end of 2024, and final payment was provided to the agencies in January 2025.​ | SCE met target. Contracts were issued at the end of 2024, and final payment was provided to the agencies in January 2025. | SCE met target. Contracts were issued at the end of 2024, and final payment was provided to the agencies in January 2025. | Completed
1010000004 | SCE | 2026-02-01 | Program |  |  | Distribution High Fire Risk‐Informed (HFRI) Inspections and Remediations (Ground and Aerial) | Detailed inspections of distribution electric lines and equipment | Detect equipment anomalies and mitigate ignition risks that cannot be detected during compliance ‐ driven programs alone | Grid Design, Operations, and Maintenance | Asset Inspections |  | 8.1.3.1 | IN-1.1 | Grid Design, Operations, and Maintenance_Asset Inspections_IN-1.1_2023 | 282 | Equipment ignition likelihood, Contact from vegetation ignition likelihood, Contact by object ignition | Yes | # of structures in HFRA | Aerial: 229101.0 Ground: 230783.0 | 2025 | 4 | 54846 | 116076 | 195693 | 230783 |  |  |  |  | Completed
1010000005 | SCE | 2026-02-01 | Program |  |  | Transmission High Fire Risk‐Informed (HFRI) Inspections and Remediations (Ground and Aerial) | Transmission HFRI Inspections and Remediations | Detect equipment anomalies and mitigate ignition risks that cannot be detected during compliance ‐ driven programs alone | Grid Design, Operations, and Maintenance | Asset Inspections |  | 8.1.3.2 | IN-1.2 | Grid Design, Operations, and Maintenance_Asset Inspections_IN-1.2_2023 | 289 | Equipment ignition likelihood, Contact from vegetation ignition likelihood, Contact by object ignition | Yes | # of structures in HFRA | Aerial: 33529.0 Ground: 33886.0 | 2025 | 4 | 6195 | 20124 | 31924 | 33886 |  |  |  |  | Completed
1010000006 | SCE | 2026-02-01 | Program |  |  | Infrared Inspection of Energized Overhead Distribution Facilities and Equipment | Infrared inspections of distribution electric lines and equipment | Detect deteriorated connection points on electrical equipment such as conductors, insulators, splices or connectors that over time can lead to failures if left unmitigated and pose ignition risks | Grid Design, Operations, and Maintenance | Asset Inspections |  | 8.1.3.5 | IN-3 | Grid Design, Operations, and Maintenance_Asset Inspections_IN-3_2023 | 297 | Equipment ignition likelihood | Yes | # of distribution circuit miles in HFRA |  | 2025 | 4 | 0 | 4765.37 | 5551.42 | 5636.34 |  |  |  |  | Completed
1010000007 | SCE | 2026-02-01 | Program |  |  | Infrared Inspection, Corona Scanning, and High-Definition Imagery of Energized Overhead Transmission Facilities and Equipment | Infrared inspections of transmission electric lines and equipment | Detect deteriorated connection points on electrical equipment such as conductors, insulators, splices or connectors that over time can lead to failures if left unmitigated and pose ignition risks | Grid Design, Operations, and Maintenance | Asset Inspections |  | 8.1.3.6 | IN-4 | Grid Design, Operations, and Maintenance_Asset Inspections_IN-4_2023 | 300 | Equipment ignition likelihood | Yes | # of transmission circuit miles in HFRA |  | 2025 | 4 | 159 | 648.9 | 1029.8 | 1051.7 |  |  |  |  | Completed
1010000008 | SCE | 2026-02-01 | Program |  |  | Generation High Fire Risk-Informed Inspections and Remediations in HFRA | Generation High Fire Risk-Informed Inspections and Remediations in HFRA | Identify potential ignition risks on generation-related assets and mitigate the ignition driver risks through system hardening | Grid Design, Operations, and Maintenance | Asset Inspections |  | 8.1.3.7 | IN-5 | Grid Design, Operations, and Maintenance_Asset Inspections_IN-5_2023 | 303 | Equipment ignition likelihood, Contact from vegetation ignition likelihood, Contact by object ignition | Yes | # of structures in HFRA |  | 2025 | 4 | 0 | 68 | 238 | 238 |  |  |  |  | Completed
1010000009 | SCE | 2026-02-01 | Project | 2026-01-01 | 2026-12-31 | Inspection and Maintenance Tools | InspectForce is the centralized asset inspection product used for planning and executing inspections | Improves the effectiveness and speed of inspections, data quality and record accuracy, and helps ensure that information is available, accessible, and timely to support wildfire mitigation activities. | Grid Design, Operations, and Maintenance | Asset Management and Inspection Enterprise System(s) |  | 8.1.5 | IN-8 | Grid Design, Operations, and Maintenance_Asset Management and Inspection Enterprise System(s)_IN-8_2023 | 323 |  | Yes |  | Risk Target Reduction not applicable. | 2025 | 4 |  |  |  |  | Activity is off track due to continued work on the system development plan and system engineering specifications. Activity is expected to be on track by end of Q3. | Activity is off track due to extended work on system development plan, system engineering specifications, and additional quality verifications.​ The schedule has been re-baselined with an expedited Go-Live date of December 2025.​ Over the past two months, alignment has been achieved, and teams are more integrated. | Activity year-end target will not be met due to extended work on system execution plan, system engineering specifications, and additional quality verifications The schedule has been re-baselined with an expedited Go-Live date of December 2025 Given the amount of development and testing still pending, it is possible the December Go-Live date may not be met | SCE target not met. SCE continues to optimize execution in support of January go-live date. Monitoring and reporting is anticipated to begin in January through the end of March. | Delayed | Detailed project plan has been developed to monitor the work management tool post-implementation Monitoring to complete the 2025 target is expected to run concurrently with the 2026 plan to execute and train users on the software solution Routine check-ins scheduled with partners to address challenges, review schedules and monitor resources to ensure completion of work The get-well plan is to continue to proactively identify opportunities to optimize execution and track mitigation activities
1010000010 | SCE | 2026-02-01 | Project | 2026-01-01 | 2026-12-31 | Transmission Conductor and Splice Assessment | Transmission Conductor and Splice Assessment | Reduce transmission conductor wire down events | Grid Design, Operations, and Maintenance | Asset Inspections |  | 8.1.3.8 | IN-9 | Grid Design, Operations, and Maintenance_Asset Inspections_IN-9_2023 | 305 |  | Yes | # Spans/splices | Risk Target Reduction not applicable. | 2025 | 4 | 0 | 0 | 0 | 0 |  |  |  |  | Completed
1010000011 | SCE | 2026-02-01 | Program |  |  | Customer Care Programs (Critical Care Backup Battery (CCBB) Program) | Supports all customers enrolled in Medical Baseline (MBL) that reside in a HFRA to provide a battery-powered portable backup solution | Allows eligible customers to operate critical medical equipment during power outages due to PSPS events or other emergencies | Emergency Preparedness | Customer Support in Wildfire and PSPS Emergencies |  | 8.4.6.2 | PSPS-2 | Emergency Preparedness_Customer Support in Wildfire and PSPS Emergencies_PSPS-2_2023 | 572 | PSPS vulnerability | No |  |  | 2025 | 4 |  |  |  |  | In Q1,100% of customers enrolled received their battery within 30 calendar days. | As of Q2, SCE met targets. Both the WMP 85% and 90% targets were achieved, with 1,772 batteries deployed to customers year-to-date.​ | As of Q3, SCE met target. 100% of the eligible customers who enrolled in the CCBB program received their batteries within 30 days exceeding the 85% and 90% stive targets. 1,772 batteries deployed to customers year-to-date. | SCE met target. 100% of the eligible customers who enrolled in the CCBB program received their batteries within 30 days. | Completed
1010000012 | SCE | 2026-02-01 | Program |  |  | Customer Care Programs (Portable Power Station and Generator Rebates) | Provides up to five $75 rebates to customers for purchasing a portable power station for their home or small business resiliency needs | Provide additional opportunities to increase customer resiliency | Emergency Preparedness | Customer Support in Wildfire and PSPS Emergencies |  | 8.4.6.3 | PSPS-3 | Emergency Preparedness_Customer Support in Wildfire and PSPS Emergencies_PSPS-3_2023 | 572 | PSPS vulnerability | No |  |  | 2025 | 4 |  |  |  |  | In Q1, 100% of rebate claims submitted were processed and distributed within 30 business day | As of Q2, SCE met targets. 100% success rate was achieved in paying all claims within the target of 30 days. Total number of claims paid out year-to-date is 5,059.​ | As of Q3, SCE met targets. 100% success rate was achieved in paying all claims within the target of 30 days. Both 85% and 90% strive targets were achieved. Total number of claims paid out year-to-date is 6,490. | SCE met targets. 100% success rate was achieved in paying all claims within the target of 30 days. | Completed
1010000013 | SCE | 2026-02-01 | Program |  |  | Weather Stations | Validate real-time conditions in the field during elevated fire conditions and are used to provide critical situational awareness for PSPS decision-making and help improve weather models. | Help SCE make decisions during potential fire conditions, including PSPS de-energization and re-energizations | Situational Awareness and Forecasting | Environmental Monitoring Systems |  | 8.3.2.1.1 | SA-1 | Situational Awareness and Forecasting_Environmental Monitoring Systems_SA-1_2023 | 454 | PSPS vulnerability | No | # of weather stations installed |  | 2025 | 4 | 28 | 88 | 162 | 202 |  |  |  |  | Completed
1010000014 | SCE | 2026-02-01 | Project | 2026-01-01 | 2026-12-31 | High Definition (HD) Cameras | HD camera installations resolves gaps in SCE’s spatial data and provides improved fire confirmation capabilities | Helps IMTs and first responders more quickly assess and respond to reported fires | Situational Awareness and Forecasting | Ignition Detection Systems |  | 8.3.4.1.1 | SA-10 | Situational Awareness and Forecasting_Ignition Detection Systems_SA-10_2023 | 492 | Wildfire vulnerability, PSPS vulnerability | No | # of HD cameras installed |  | 2025 | 4 | 0 | 2 | 2 | 2 |  |  |  |  | Completed
1010000015 | SCE | 2026-02-01 | Pilot |  |  | Early Fault Detection (EFD) | Radio Frequency Monitors: Early Fault Detection (EFD) (SA-11) | EFD could potentially be used to monitor the overall health of the electric system which may inform operational decisions during high‐risk conditions. | Situational Awareness and Forecasting | Situational awareness and forecasting |  | 8.3.3.1.1 | SA-11 | Situational Awareness and Forecasting_Situational awareness and forecasting_SA-11_2023 | 469 | Equipment ignition likelihood, Contact from vegetation ignition likelihood, Contact by object ignition | No | # of locations |  | 2025 | 4 | 2 | 18 | 42 | 204 |  |  |  |  | Completed
1010000016 | SCE | 2026-02-01 | Program |  |  | Weather and Fuels Modeling | Weather and fuels modeling including weather forecasts and historic weather data spanning the entire SCE service area | Maintain and enhance operational weather and fuel forecasting capabilities | Situational Awareness and Forecasting | Weather Forecasting |  | 8.3.5 | SA-3 | Situational Awareness and Forecasting_Weather Forecasting_SA-3_2023 | 499 | PSPS vulnerability | No |  |  | 2025 | 4 |  |  |  |  | In Q1, SCE delivered a list of all installed weather stations and vendor provided a list of weather station locations that are capable of supporting new machine learning models.​ | SCE delivered a list of all installed weather stations and vendor provided a list of weather station locations that can support new machine learning models.​ | As of Q3, SCE operationalized machine learning at selected locations by sending the forecast output daily with other weather model outputs.​ | SCE met target to operationalize machine learning at selected locations by sending the forecast output daily with other weather model outputs. | Completed
1010000017 | SCE | 2026-02-01 | Program |  |  | Fire Science Enhancements | Various modeling tools to predict fire ignition and consequence outputs such as fire perimeter size, structures impacted, populations affected, and injury and death | Expand data analysis, emphasize fire potential forecasting, and improve modeling efforts as it relates to fire science | Situational Awareness and Forecasting | Environmental Monitoring Systems |  | 8.3.2.3.2 | SA-8 | Situational Awareness and Forecasting_Environmental Monitoring Systems_SA-8_2023 | 466 | PSPS vulnerability | No |  |  | 2025 | 4 |  |  |  |  | In Q1, SCE benchmarked consequence metrics against past extreme fire weather events.​ | As of Q2, SCE benchmarked consequence metrics against past extreme fire weather events.​ | As of Q3, SCE benchmarked consequence metrics against real time events. ​ | SCE met target. SCE benchmarked consequence metrics against real-time events. SCE will continue to use model for the In-Event Risk Calculator and be used as an additional data point. | Completed
1010000018 | SCE | 2026-02-01 | Program |  |  | Covered Conductor (WCCP and Non WCCP) | Replacing bare wire with conductor / components (fire-resistant poles, composite crossarms, FR3 transformers, wildlife covers, surge arresters, polymer insulators and vibration dampers) to protect against the arcing, faults, or energy release that can come from incidental contact. | Reduce CFO, EFF and Wire-to-Wire Risk | Grid Design, Operations, and Maintenance | Covered Conductor Installation |  | 8.1.2.1.1 | SH-1 | Grid Design, Operations, and Maintenance_Covered Conductor Installation_SH-1_2023 | 251 | Equipment ignition likelihood, Contact from vegetation ignition likelihood, Contact by object ignition, PSPS Likelihood | No | # of circuit miles in HFRA |  | 2025 | 4 | 62.17 | 216.35 | 404.65 | 710.42 |  |  |  |  | Completed
1010000019 | SCE | 2026-02-01 | Program |  |  | Tree Attachment Remediation | Tree Attachment Remediations | Reduce EFF Risk | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 8.1.2.3.1 | SH-10 | Grid Design, Operations, and Maintenance_Grid Design and System Hardening_SH-10_2023 | 258 | Equipment ignition likelihood, Contact from vegetation ignition likelihood, Contact by object ignition | No | # of tree attachment remediations |  | 2025 | 4 | 0 | 0 | 8 | 0 |  |  |  |  | Delayed | Expediting field checks to be scheduled one week after cost estimates complete; then submission for an MSUP to Sequioa National Forest can occur (impacts 16 structures) Expedite requests pending Design Standard Decision Document (DSDD or Caltrans design deviations); Environmental will also review requests proactively (impacts 18 structures) Connect with Caltrans District 6 to prioritize work Partner with Sequoia National Park on undergrounding options versus overhead pole placement
1010000020 | SCE | 2026-02-01 | Program |  |  | Long Span Initiative (LSI) | Long Span initiative remediation | Reduce Wire to Wire Risk | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 8.1.2.5.2 | SH-14 | Grid Design, Operations, and Maintenance_Grid Design and System Hardening_SH-14_2023 | 263 | Equipment ignition likelihood, Contact from vegetation ignition likelihood, Contact by object ignition | No | # of remediations |  | 2025 | 4 | 71 | 350 | 920 | 1102 |  |  |  |  | Completed
1010000021 | SCE | 2026-02-01 | Program |  |  | Vibration Damper Retrofit | Vibration Damper Retrofit | Reduce Wire to Wire Risk | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 8.1.2.1.2 | SH-16 | Grid Design, Operations, and Maintenance_Grid Design and System Hardening_SH-16_2023 | 254 | Equipment ignition likelihood, Contact from vegetation ignition likelihood, Contact by object ignition | No | # structures |  | 2025 | 4 | 74 | 572 | 666 | 731 |  |  |  |  | Completed
1010000022 | SCE | 2026-02-01 | Program |  |  | Rapid Earth Fault Current Limiter (REFCL) Ground Fault Neutralizer | REFCL Ground Fault Neutralizer | Reduce CFO and EFF Risk | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 8.1.2.6.1 | SH-17 | Grid Design, Operations, and Maintenance_Grid Design and System Hardening_SH-17_2023 | 266 | Equipment ignition likelihood, Contact from vegetation ignition likelihood, Contact by object ignition | No |  |  | 2025 | 4 |  |  |  |  | In Q1, construction is in progress for 2 substations. | As of Q2, SCE completed construction of GFN at two substations.​ | SCE met target. Program exceeded its target and completed construction of GFN at 4 substations. | SCE met target. SCE completed construction of GFN at 4 substations. | Completed
1010000023 | SCE | 2026-02-01 | Program |  |  | Rapid Earth Fault Current Limiter (REFCL) Grounding Conversion | REFCL Grounding Conversion | Reduce CFO and EFF Risk | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 8.1.2.6.2 | SH-18 | Grid Design, Operations, and Maintenance_Grid Design and System Hardening_SH-18_2023 | 268 | Equipment ignition likelihood, Contact from vegetation ignition likelihood, Contact by object ignition | No |  |  | 2025 | 4 |  |  |  |  | In Q1, SCE provided selected installation locations. | As of Q2, SCE has one work order completed and routed for construction. 3 work order designs are in progress.​ | As of Q3, 0 grounding conversions completed YTD. Activity is at risk due to resource constraints, specialty resource needs, and competing priorities. The team is working to alleviate risks, obtain clearances, and secure resources. | SCE target not met. SCE completed 3 of 4 grounding conversions; the outstanding grounding conversion is awaiting a field assessment by the city of Banning. | Delayed | Continue work with City of Banning in 2026 to obtain the necessary approvals to proceed with the project
1010000024 | SCE | 2026-02-01 | Program |  |  | Undergrounding Overhead Conductor | Targeted Undergrounding | Reduce CFO, EFF and Wire-to-Wire Risk | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 8.1.2.2.1 | SH-2 | Grid Design, Operations, and Maintenance_Grid Design and System Hardening_SH-2_2023 | 256 | Equipment ignition likelihood, Contact from vegetation ignition likelihood, Contact by object ignition, PSPS Likelihood | No | # of circuit miles in HFRA |  | 2025 | 4 | 1.05 | 10.18 | 14.75 | 45.37 |  |  |  |  | Completed
1010000025 | SCE | 2026-02-01 | Program |  |  | Remote Controlled Automatic Reclosers Settings Update | Remote Controlled Automatic Reclosers | Reduce CFO and Wire-to-Wire Risk | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 8.1.2.8.1 | SH-5 | Grid Design, Operations, and Maintenance_Grid Design and System Hardening_SH-5_2023 | 271 | Equipment ignition likelihood, Contact from vegetation ignition likelihood, Contact by object ignition | No | # of RARs / RCSs installed and operationalized |  | 2025 | 4 | 0 | 2 | 6 | 13 |  |  |  |  | Completed
1010000026 | SCE | 2026-02-01 | Program |  |  | Transmission Open Phase Detection | Protective Relay - Transmission Open Phase Detection (TOPD) | Refine circuit protection strategies to further reduce wildfire risk while balancing system reliability | Grid Design, Operations, and Maintenance | Grid Design and System Hardening |  | 8.3.3.1.2.1 | SH-8 | Grid Design, Operations, and Maintenance_Grid Design and System Hardening_SH-8_2023 | 470 | Equipment ignition likelihood | No |  |  | 2025 | 4 |  |  |  |  | Activity is scheduled to begin in Q2. | As of Q2, SCE has drafted the evaluation report, which is currently in progress. The scope of work is being finalized, and project design have been initiated to support construction and deployment of TOPD logic at 4 locations serving HFRA circuitry. ​ ​ | As of Q3, SCE has drafted the evaluation report, which is currently in progress. The scope of work is being finalized, and project design have been initiated to support construction and deployment of TOPD logic at 4 locations serving HFRA circuitry. ​ | SCE met target. SCE completed the final evaluation report; and deployed TOPD logic at 7 locations. | Completed
1010000027 | SCE | 2026-02-01 | Program |  |  | Hazard Tree Management Program (Distribution) | Identifies trees that pose a risk to electric facilities based on the tree’s observed structural integrity and site conditions. | Reduce Contact From Vegetation Risk | Vegetation Management and Inspections | Vegetation Inspections |  | 8.2.3.4.1 | VM-1 | Vegetation Management and Inspections_Vegetation Inspections_VM-1_2023 | 418 | Contact from vegetation ignition likelihood | Yes | # grids/circuits |  | 2025 | 4 | 178 | 311 | 439 | 526 |  |  |  |  | Completed
1010000028 | SCE | 2026-02-01 | Program |  |  | LiDAR Vegetation Inspections - Transmission | LiDAR as an inspection and measurement tool acquired via air patrol to identify clearances between high-voltage transmission lines and vegetation. | Make substantial progress on evaluation of incorporation of remote sensing technology into vegetation inspections | Vegetation Management and Inspections | Vegetation Inspections |  | 8.2.2.4.1 | VM-10 | Vegetation Management and Inspections_Vegetation Inspections_VM-10_2023 | 398 |  | Yes | # circuit miles | Risk Target Reduction not applicable. | 2025 | 4 | 183.26 | 1440.81 | 1952.01 | 2182.39 |  |  |  |  | Completed
1010000029 | SCE | 2026-02-01 | Program |  |  | Projects Structure Brushing | Structure Brushing | Reduce EFF Risk | Vegetation Management and Inspections | Pole Clearing |  | 8.2.3.1.1 | VM-2 | Vegetation Management and Inspections_Pole Clearing_VM-2_2023 | 408 | Equipment ignition likelihood, Contact from vegetation ignition likelihood | Yes | # structures brushed |  | 2025 | 4 | 46120 | 88238 | 140858 | 157691 |  |  |  |  | Completed
1010000030 | SCE | 2026-02-01 | Program |  |  | Projects Expanded Clearances for Legacy Facilities (Polygon) | Remove / clear additional vegetation using the standard remediation methods of trims, removals, and/or weed abatement to render the defensible space around a generation facility even more vegetation free | Reduce Contact From Vegetation and EFF Risk | Vegetation Management and Inspections | Clearance |  | 8.2.3.3.2 | VM-3 | Vegetation Management and Inspections_Clearance_VM-3_2023 | 416 | Equipment ignition likelihood, Contact from vegetation ignition likelihood | No | # of sites treated |  | 2025 | 4 | 0 | 24 | 41 | 63 |  |  |  |  | Completed
1010000031 | SCE | 2026-02-01 | Program |  |  | Dead and Dying Tree Removal (Distribution) | Patrols in HFRA to identify and remove dead, dying, or diseased trees affected by drought conditions and/or insect infestation. | Reduce Contact From Vegetation Risk | Vegetation Management and Inspections | Clearance |  | 8.2.3.4.2 | VM-4 | Vegetation Management and Inspections_Clearance_VM-4_2023 | 419 | Contact from vegetation ignition likelihood | Yes | # of grids/circuits |  | 2025 | 4 | 200 | 353 | 507 | 600 |  |  |  |  | Completed
1010000032 | SCE | 2026-02-01 | Project | 2026-01-01 | 2026-12-31 | VM Work Management Tool | Data Warehouse used for Routine Vegetation Management inspections and resulting mitigations | Consolidated work tracking and reporting to optimize operations and improve data accuracy | Vegetation Management and Inspections | Vegetation Management Enterprise System |  | 8.2.4 | VM-6 | Vegetation Management and Inspections_Vegetation Management Enterprise System_VM-6_2023 | 426 |  | Yes |  | Risk Target Reduction not applicable. | 2025 | 4 |  |  |  |  | In Q1, SCE completed the design documents for the transition to SF Mobile. | As of Q2, SCE completed the design documents for the transition to SF Mobile.​ | As of Q3, the SES (System Engineering Specification) for Salesforce Mobile was designed and approved. Full deployment of SF Mobile is in progress. ​ | SCE met target. Arbora has monitored stabilization and continued execution of plan to enable additional VM maintenance programs. | Completed
1010000033 | SCE | 2026-02-01 | Program |  |  | Detailed Inspections for the Prescription, Where Necessary and Feasible, of Expanded Vegetation Clearances from Distribution Lines in HFRA | Distribution Expanded Clearing | Reduce Contact From Vegetation Risk | Vegetation Management and Inspections | Vegetation management and inspections |  | 8.2.3.3.1 | VM-7 | Vegetation Management and Inspections_Vegetation management and inspections_VM-7_2023 | 412 | Contact from vegetation ignition likelihood | Yes | # of grids |  | 2025 | 4 | 237 | 441 | 670 | 789 |  |  |  |  | Completed
1010000034 | SCE | 2026-02-01 | Program |  |  | Detailed Inspections for the Prescription, Where Necessary and Feasible, of Expanded Vegetation Clearances from Transmission Lines in HFRA | Transmission expanded line clearances to mitigate the risk of vegetation contact with energized conductors | Reduce Contact From Vegetation Risk | Vegetation Management and Inspections | Clearance |  | 8.2.3.3.1 | VM-8 | Vegetation Management and Inspections_Clearance_VM-8_2023 | 412 | Contact from vegetation ignition likelihood | Yes | # of grids |  | 2025 | 4 | 79 | 279 | 405 | 448 |  |  |  |  | Completed
1010000035 | SCE | 2026-02-01 | Program |  |  | LiDAR Vegetation Inspections - Distribution | LiDAR as an inspection and measurement tool acquired via air patrol to identify clearances between high-voltage distribution lines and vegetation. | Make substantial progress on evaluation of incorporation of remote sensing technology into vegetation inspections | Vegetation Management and Inspections | Vegetation Inspections |  | 8.2.2.4.1 | VM-9 | Vegetation Management and Inspections_Vegetation Inspections_VM-9_2023 | 398 |  | Yes | # circuit miles | Risk Target Reduction not applicable. | 2025 | 4 | 181.41 | 1424.19 | 2705.25 | 4031.75 |  |  |  |  | Completed

## Table 2
METRIC NUMBER | METRIC TYPE | METRIC NAME | WIND WARNING STATUS | HFTD TIER | LINE TYPE | INSPECTION TYPE | INSPECTION METHOD | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1020000000 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | HFTD Tier 2 |  |  |  | Number of events | SCE notes tha the aggregate sum of all risk events is for those with ignition risk only and that these sums should not be expected to align with table 5 and 6 for total risk events. |  | SCE | 2025 | 4 | 0
1020000001 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | HFTD Tier 2 |  |  |  | Number of events | SCE notes tha the aggregate sum of all risk events is for those with ignition risk only and that these sums should not be expected to align with table 5 and 6 for total risk events. |  | SCE | 2025 | 4 | 8
1020000002 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events | SCE notes tha the aggregate sum of all risk events is for those with ignition risk only and that these sums should not be expected to align with table 5 and 6 for total risk events. |  | SCE | 2025 | 4 | 0
1020000003 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | HFTD Tier 2 |  |  |  | Number of events | SCE notes tha the aggregate sum of all risk events is for those with ignition risk only and that these sums should not be expected to align with table 5 and 6 for total risk events. |  | SCE | 2025 | 4 | 272
1020000004 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | HFTD Tier 3 |  |  |  | Number of events | SCE notes tha the aggregate sum of all risk events is for those with ignition risk only and that these sums should not be expected to align with table 5 and 6 for total risk events. |  | SCE | 2025 | 4 | 4
1020000005 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | HFTD Tier 3 |  |  |  | Number of events | SCE notes tha the aggregate sum of all risk events is for those with ignition risk only and that these sums should not be expected to align with table 5 and 6 for total risk events. |  | SCE | 2025 | 4 | 36
1020000006 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events | SCE notes tha the aggregate sum of all risk events is for those with ignition risk only and that these sums should not be expected to align with table 5 and 6 for total risk events. |  | SCE | 2025 | 4 | 0
1020000007 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | HFTD Tier 3 |  |  |  | Number of events | SCE notes tha the aggregate sum of all risk events is for those with ignition risk only and that these sums should not be expected to align with table 5 and 6 for total risk events. |  | SCE | 2025 | 4 | 484
1020000008 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | Non-HFTD |  |  |  | Number of events | SCE notes tha the aggregate sum of all risk events is for those with ignition risk only and that these sums should not be expected to align with table 5 and 6 for total risk events. |  | SCE | 2025 | 4 | 0
1020000009 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | Non-HFTD |  |  |  | Number of events | SCE notes tha the aggregate sum of all risk events is for those with ignition risk only and that these sums should not be expected to align with table 5 and 6 for total risk events. |  | SCE | 2025 | 4 | 31
1020000010 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | Non-HFTD |  |  |  | Number of events | SCE notes tha the aggregate sum of all risk events is for those with ignition risk only and that these sums should not be expected to align with table 5 and 6 for total risk events. |  | SCE | 2025 | 4 | 0
1020000011 | 1. Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | Non-HFTD |  |  |  | Number of events | SCE notes tha the aggregate sum of all risk events is for those with ignition risk only and that these sums should not be expected to align with table 5 and 6 for total risk events. |  | SCE | 2025 | 4 | 2783
1020000012 | 1. Risk Events | Number of wires down | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | SCE | 2025 | 4 | 0
1020000013 | 1. Risk Events | Number of wires down | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | SCE | 2025 | 4 | 1
1020000014 | 1. Risk Events | Number of wires down | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | SCE | 2025 | 4 | 0
1020000015 | 1. Risk Events | Number of wires down | Neither | HFTD Tier 2 |  |  |  | Number of events | Note: A portion of this data includes "Unknown" HWW/RFW. |  | SCE | 2025 | 4 | 28
1020000016 | 1. Risk Events | Number of wires down | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | SCE | 2025 | 4 | 0
1020000017 | 1. Risk Events | Number of wires down | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | SCE | 2025 | 4 | 9
1020000018 | 1. Risk Events | Number of wires down | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | SCE | 2025 | 4 | 0
1020000019 | 1. Risk Events | Number of wires down | Neither | HFTD Tier 3 |  |  |  | Number of events | Note: A portion of this data includes "Unknown" HWW/RFW. |  | SCE | 2025 | 4 | 73
1020000020 | 1. Risk Events | Number of wires down | RFW only | Non-HFTD |  |  |  | Number of events |  |  | SCE | 2025 | 4 | 0
1020000021 | 1. Risk Events | Number of wires down | HWW only | Non-HFTD |  |  |  | Number of events |  |  | SCE | 2025 | 4 | 7
1020000022 | 1. Risk Events | Number of wires down | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | SCE | 2025 | 4 | 0
1020000023 | 1. Risk Events | Number of wires down | Neither | Non-HFTD |  |  |  | Number of events | Note: A portion of this data includes "Unknown" HFTD & "Unknown" HWW/RFW. |  | SCE | 2025 | 4 | 305
1020000024 | 1. Risk Events | Number of outage events not caused by contact with vegetation | RFW only | HFTD Tier 2 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2025 | 4 | 0
1020000025 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW only | HFTD Tier 2 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2025 | 4 | 5
1020000026 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2025 | 4 | 0
1020000027 | 1. Risk Events | Number of outage events not caused by contact with vegetation | Neither | HFTD Tier 2 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2025 | 4 | 216
1020000028 | 1. Risk Events | Number of outage events not caused by contact with vegetation | RFW only | HFTD Tier 3 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2025 | 4 | 4
1020000029 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW only | HFTD Tier 3 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2025 | 4 | 15
1020000030 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2025 | 4 | 0
1020000031 | 1. Risk Events | Number of outage events not caused by contact with vegetation | Neither | HFTD Tier 3 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2025 | 4 | 378
1020000032 | 1. Risk Events | Number of outage events not caused by contact with vegetation | RFW only | Non-HFTD |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2025 | 4 | 0
1020000033 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW only | Non-HFTD |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2025 | 4 | 22
1020000034 | 1. Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | Non-HFTD |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2025 | 4 | 0
1020000035 | 1. Risk Events | Number of outage events not caused by contact with vegetation | Neither | Non-HFTD |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2025 | 4 | 2252
1020000036 | 1. Risk Events | Number of outage events caused by contact with vegetation | RFW only | HFTD Tier 2 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2025 | 4 | 0
1020000037 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW only | HFTD Tier 2 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2025 | 4 | 1
1020000038 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2025 | 4 | 0
1020000039 | 1. Risk Events | Number of outage events caused by contact with vegetation | Neither | HFTD Tier 2 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2025 | 4 | 9
1020000040 | 1. Risk Events | Number of outage events caused by contact with vegetation | RFW only | HFTD Tier 3 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2025 | 4 | 0
1020000041 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW only | HFTD Tier 3 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2025 | 4 | 8
1020000042 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2025 | 4 | 0
1020000043 | 1. Risk Events | Number of outage events caused by contact with vegetation | Neither | HFTD Tier 3 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2025 | 4 | 14
1020000044 | 1. Risk Events | Number of outage events caused by contact with vegetation | RFW only | Non-HFTD |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2025 | 4 | 0
1020000045 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW only | Non-HFTD |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2025 | 4 | 0
1020000046 | 1. Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | Non-HFTD |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2025 | 4 | 0
1020000047 | 1. Risk Events | Number of outage events caused by contact with vegetation | Neither | Non-HFTD |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2025 | 4 | 90
1020000048 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | HFTD Tier 2 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2025 | 4 | 0
1020000049 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | HFTD Tier 2 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2025 | 4 | 1
1020000050 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2025 | 4 | 0
1020000051 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | HFTD Tier 2 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2025 | 4 | 19
1020000052 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | HFTD Tier 3 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2025 | 4 | 0
1020000053 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | HFTD Tier 3 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2025 | 4 | 4
1020000054 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2025 | 4 | 0
1020000055 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | HFTD Tier 3 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2025 | 4 | 18
1020000056 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | Non-HFTD |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2025 | 4 | 0
1020000057 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | Non-HFTD |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2025 | 4 | 2
1020000058 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | Non-HFTD |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2025 | 4 | 0
1020000059 | 1. Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | Non-HFTD |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2025 | 4 | 129
1020000060 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 2 | Distribution |  |  | days |  |  | SCE | 2025 | 4 | 54
1020000061 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | days |  |  | SCE | 2025 | 4 | 386
1020000062 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 3 | Distribution |  |  | days |  |  | SCE | 2025 | 4 | 59
1020000063 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | days |  |  | SCE | 2025 | 4 | 233
1020000064 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | Non-HFTD | Distribution |  |  | days |  |  | SCE | 2025 | 4 | 51
1020000065 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | days |  |  | SCE | 2025 | 4 | 124
1020000066 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 2 | Transmission |  |  | days |  |  | SCE | 2025 | 4 | 90
1020000067 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | days |  |  | SCE | 2025 | 4 | 798
1020000068 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 3 | Transmission |  |  | days |  |  | SCE | 2025 | 4 | 91
1020000069 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | days |  |  | SCE | 2025 | 4 | 682
1020000070 | 2. Time between vegetation inspection finding and resulting trimming activity | Median time |  | Non-HFTD | Transmission |  |  | days |  |  | SCE | 2025 | 4 | 97
1020000071 | 2. Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | days |  |  | SCE | 2025 | 4 | 260
1020000072 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours | Notifications created 1/1/20 and later |  | SCE | 2025 | 4 | 1
1020000073 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours |  |  | SCE | 2025 | 4 | 13
1020000074 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours |  |  | SCE | 2025 | 4 | 1
1020000075 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours |  |  | SCE | 2025 | 4 | 15
1020000076 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000077 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000078 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours |  |  | SCE | 2025 | 4 | 0
1020000079 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours |  |  | SCE | 2025 | 4 | 0
1020000080 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours |  |  | SCE | 2025 | 4 | 0
1020000081 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours |  |  | SCE | 2025 | 4 | 0
1020000082 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000083 | 3. Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000084 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours |  |  | SCE | 2025 | 4 | 45
1020000085 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours |  |  | SCE | 2025 | 4 | 677
1020000086 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours |  |  | SCE | 2025 | 4 | 120
1020000087 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours |  |  | SCE | 2025 | 4 | 568
1020000088 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000089 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000090 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours |  |  | SCE | 2025 | 4 | 469
1020000091 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours |  |  | SCE | 2025 | 4 | 1980
1020000092 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours |  |  | SCE | 2025 | 4 | 146
1020000093 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours |  |  | SCE | 2025 | 4 | 1858
1020000094 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000095 | 4. Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000096 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours |  |  | SCE | 2025 | 4 | 1342
1020000097 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours |  |  | SCE | 2025 | 4 | 7263
1020000098 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours |  |  | SCE | 2025 | 4 | 824
1020000099 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours |  |  | SCE | 2025 | 4 | 7504
1020000100 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000101 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000102 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours |  |  | SCE | 2025 | 4 | 854
1020000103 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours |  |  | SCE | 2025 | 4 | 2504
1020000104 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours |  |  | SCE | 2025 | 4 | 877
1020000105 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours |  |  | SCE | 2025 | 4 | 1977
1020000106 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000107 | 5. Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000108 | 6. Vegetation management work orders | Number of vegetation management open work orders (total) | [5 empty] | Number of orders | Routine |  | SCE | 2025 | 4 | 74592
1020000109 | 6. Vegetation management work orders | Number of vegetation management past due work orders (total) | [5 empty] | Number of orders | Routine - For Veg Past Due WOs, SCE reports the number of open work points in 6a that have exceeded internal targets of 30 days <Regulatory Clearance Distance (RCD) and 90 days between RCD and Trigger Clearance Distance (TCD). |  | SCE | 2025 | 4 | 25217
1020000110 | 7. Asset management work orders | Number of asset management open work orders (total) | [5 empty] | Number of orders |  |  | SCE | 2025 | 4 | 140195
1020000111 | 7. Asset management work orders | Number of asset management past due work orders (total) | [5 empty] | Number of orders |  |  | SCE | 2025 | 4 | 5700
1020000112 | 8. Response Time | Response time to locked open circuit breaker | [5 empty] | Hours | For metric 8a, data for crew response time to a locked circuit breaker incident is not readily availableis not currently available as SCE does not make it mandatory to track arrival time of the crew for instances not involving hazard conditions such as 911 or wire down calls. Documentation takes time away from restoring customers and therefore not tracked for other purposesSCE will continue to review the available information in its outage systems to provide this information in a future filing. Currently, aAny average on a quarterly basisquarterly data would not reflect only 911 and wire down events and is not a good representation of our overall true response time. | Metric Not Available at this Time. | SCE | 2025 | 4
1020000113 | 9. Fatalities and injuries due to utility-related ignitions | Fatalities due to utility-related ignitions (total) | [5 empty] | Number of fatalities | The information provided in conjunction with all of the “utility-ignited” wildfire statistics in tables 1-13 should not be construed as an admission of any wrongdoing or liability by SCE or concession that the wildfire was actually caused by SCE equipment. SCE is required to submit an Electric Safety Incident Report when certain criteria are met, including any allegation that an incident is attributed to SCE equipment, even if there is no evidence supporting such allegation. SCE further notes that the damages metrics provided may be tracked by other agencies and thus, SCE does not guarantee the accuracy of such information. Additionally, in many instances the cause of wildfires are still under investigation and even where an Authority Having Jurisdiction (AHJ) has issued a report on the cause, SCE may dispute the conclusions of such report. |  | SCE | 2025 | 4 | 0
1020000114 | 9. Fatalities and injuries due to utility-related ignitions | Injuries due to utility-related ignitions (total) | [5 empty] | Number of injuries | The information provided in conjunction with all of the “utility-ignited” wildfire statistics in tables 1-13 should not be construed as an admission of any wrongdoing or liability by SCE or concession that the wildfire was actually caused by SCE equipment. SCE is required to submit an Electric Safety Incident Report when certain criteria are met, including any allegation that an incident is attributed to SCE equipment, even if there is no evidence supporting such allegation. SCE further notes that the damages metrics provided may be tracked by other agencies and thus, SCE does not guarantee the accuracy of such information. Additionally, in many instances the cause of wildfires are still under investigation and even where an Authority Having Jurisdiction (AHJ) has issued a report on the cause, SCE may dispute the conclusions of such report. |  | SCE | 2025 | 4 | 0
1020000115 | 10. Value of assets destroyed by utility-related ignitions, listed by asset type | Value of assets destroyed by utility-related ignitions (total) | [5 empty] | Dollars | The information provided in conjunction with all of the “utility-ignited” wildfire statistics in tables 1-13 should not be construed as an admission of any wrongdoing or liability by SCE or concession that the wildfire was actually caused by SCE equipment. SCE is required to submit an Electric Safety Incident Report when certain criteria are met, including any allegation that an incident is attributed to SCE equipment, even if there is no evidence supporting such allegation. SCE further notes that the damages metrics provided may be tracked by other agencies and thus, SCE does not guarantee the accuracy of such information. Additionally, in many instances the cause of wildfires are still under investigation and even where an Authority Having Jurisdiction (AHJ) has issued a report on the cause, SCE may dispute the conclusions of such report. Ignition costs include only those repair WOs that have been closed by time of report out. Additional costs may still be pending. Updated estimates of these costs may be provided in SCE/EIX quarterly financial statements, where applicable. |  | SCE | 2025 | 4 | 11612.79
1020000116 | 11. Structures damaged or destroyed by utility-related ignitions | Number of structures destroyed by utility-related ignitions (total) | [5 empty] | Number of structures | The information provided in conjunction with all of the “utility-ignited” wildfire statistics in tables 1-13 should not be construed as an admission of any wrongdoing or liability by SCE or concession that the wildfire was actually caused by SCE equipment. SCE is required to submit an Electric Safety Incident Report when certain criteria are met, including any allegation that an incident is attributed to SCE equipment, even if there is no evidence supporting such allegation. SCE further notes that the damages metrics provided may be tracked by other agencies and thus, SCE does not guarantee the accuracy of such information. Additionally, in many instances the cause of wildfires are still under investigation and even where an Authority Having Jurisdiction (AHJ) has issued a report on the cause, SCE may dispute the conclusions of such report. |  | SCE | 2025 | 4 | 0
1020000117 | 11. Structures damaged or destroyed by utility-related ignitions | Critical infrastructure damaged/destroyed by utility-related ignitions (total) | [5 empty] | Number of structures |  | Data point is not currently tracked. | SCE | 2025 | 4
1020000118 | 12. Acreage burned by utility-ignited wildfires | Acreage burned by utility-ignited wildfires | [5 empty] | Acres | The information provided in conjunction with all of the “utility-ignited” wildfire statistics in tables 1-13 should not be construed as an admission of any wrongdoing or liability by SCE or concession that the wildfire was actually caused by SCE equipment. SCE is required to submit an Electric Safety Incident Report when certain criteria are met, including any allegation that an incident is attributed to SCE equipment, even if there is no evidence supporting such allegation. SCE further notes that the damages metrics provided may be tracked by other agencies and thus, SCE does not guarantee the accuracy of such information. Additionally, in many instances the cause of wildfires are still under investigation and even where an Authority Having Jurisdiction (AHJ) has issued a report on the cause, SCE may dispute the conclusions of such report. |  | SCE | 2025 | 4 | 2
1020000119 | 13. Number of utility-related ignitions | Number of ignitions | RFW only | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | SCE | 2025 | 4 | 0
1020000120 | 13. Number of utility-related ignitions | Number of ignitions | HWW only | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | SCE | 2025 | 4 | 0
1020000121 | 13. Number of utility-related ignitions | Number of ignitions | HWW & RFW | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | SCE | 2025 | 4 | 0
1020000122 | 13. Number of utility-related ignitions | Number of ignitions | Neither | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | SCE | 2025 | 4 | 0
1020000123 | 13. Number of utility-related ignitions | Number of ignitions | RFW only | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | SCE | 2025 | 4 | 0
1020000124 | 13. Number of utility-related ignitions | Number of ignitions | HWW only | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | SCE | 2025 | 4 | 0
1020000125 | 13. Number of utility-related ignitions | Number of ignitions | HWW & RFW | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | SCE | 2025 | 4 | 0
1020000126 | 13. Number of utility-related ignitions | Number of ignitions | Neither | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | SCE | 2025 | 4 | 1
1020000127 | 13. Number of utility-related ignitions | Number of ignitions | RFW only | Non-HFTD |  |  |  | Number of ignitions |  |  | SCE | 2025 | 4 | 0
1020000128 | 13. Number of utility-related ignitions | Number of ignitions | HWW only | Non-HFTD |  |  |  | Number of ignitions |  |  | SCE | 2025 | 4 | 0
1020000129 | 13. Number of utility-related ignitions | Number of ignitions | HWW & RFW | Non-HFTD |  |  |  | Number of ignitions |  |  | SCE | 2025 | 4 | 0
1020000130 | 13. Number of utility-related ignitions | Number of ignitions | Neither | Non-HFTD |  |  |  | Number of ignitions |  |  | SCE | 2025 | 4 | 7
1020000131 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000132 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000133 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000134 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000135 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SCE | 2025 | 4 | 16776
1020000136 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | SCE Dist Aerial inspections completed using drone. Aerial only used for "Hard To Access" structures. |  | SCE | 2025 | 4 | 0
1020000137 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000138 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SCE | 2025 | 4 | 16820
1020000139 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000140 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | SCE's Dist IR Scan uses Aerial (helicopter) for HFTD "Hard to Access" structures only. |  | SCE | 2025 | 4 | 0
1020000141 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000142 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SCE | 2025 | 4 | 0
1020000143 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000144 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000145 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000146 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000147 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. |  | SCE | 2025 | 4 | 568.7035
1020000148 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility | SCE Dist Aerial inspections completed using drone. Aerial only used for "Hard To Access" structures. SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. |  | SCE | 2025 | 4 | 0
1020000149 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000150 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. |  | SCE | 2025 | 4 | 570.1951
1020000151 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000152 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility | SCE's Dist IR Scan uses Aerial (helicopter) for HFTD "Hard to Access" structures only. SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. |  | SCE | 2025 | 4 | 0
1020000153 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000154 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. |  | SCE | 2025 | 4 | 0
1020000155 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000156 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000157 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000158 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000159 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000160 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000161 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000162 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 44
1020000163 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000164 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000165 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000166 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 1
1020000167 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000168 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000169 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000170 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000171 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 38
1020000172 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000173 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000174 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 3724
1020000175 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000176 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000177 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000178 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 2
1020000179 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000180 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000181 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000182 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000183 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000184 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000185 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000186 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 2603
1020000187 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000188 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000189 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000190 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000191 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000192 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000193 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000194 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000195 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SCE | 2025 | 4 | 17364
1020000196 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | SCE Dist Aerial inspections completed using drone. Aerial only used for "Hard To Access" structures. |  | SCE | 2025 | 4 | 0
1020000197 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000198 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SCE | 2025 | 4 | 17320
1020000199 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000200 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | SCE's Dist IR Scan uses Aerial (helicopter) for HFTD "Hard to Access" structures only. |  | SCE | 2025 | 4 | 0
1020000201 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000202 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SCE | 2025 | 4 | 0
1020000203 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000204 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000205 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000206 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000207 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. |  | SCE | 2025 | 4 | 588.6366
1020000208 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility | SCE Dist Aerial inspections completed using drone. Aerial only used for "Hard To Access" structures. SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspection |  | SCE | 2025 | 4 | 0
1020000209 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000210 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. |  | SCE | 2025 | 4 | 587.145
1020000211 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000212 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility | SCE's Dist IR Scan uses Aerial (helicopter) for HFTD "Hard to Access" structures only. SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requ |  | SCE | 2025 | 4 | 0
1020000213 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000214 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. |  | SCE | 2025 | 4 | 0
1020000215 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000216 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000217 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000218 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000219 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000220 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000221 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000222 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 76
1020000223 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000224 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000225 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000226 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 1
1020000227 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000228 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000229 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000230 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000231 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 62
1020000232 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000233 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000234 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 4107
1020000235 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000236 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000237 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000238 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 1
1020000239 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000240 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000241 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000242 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000243 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000244 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000245 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000246 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 2803
1020000247 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000248 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 1
1020000249 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000250 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000251 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000252 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000253 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000254 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000255 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE Dist Aerial completed in HFRA only | SCE | 2025 | 4
1020000256 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | SCE Dist Aerial inspections completed using drone. Aerial only used for "Hard To Access" structures. | SCE Dist Aerial inspections completed using drone. Aerial only used for "Hard To Access" structures. | SCE | 2025 | 4
1020000257 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000258 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000259 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000260 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE's Dist IR Scan uses Aerial (helicopter) for HFTD "Hard to Access" structures only. | SCE | 2025 | 4
1020000261 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000262 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000263 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000264 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000265 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000266 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000267 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | SCE Dist Aerial completed in HFRA only | SCE | 2025 | 4
1020000268 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  | SCE Dist Aerial inspections completed using drone. Aerial only used for "Hard To Access" structures. | SCE | 2025 | 4
1020000269 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000270 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000271 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000272 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000273 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000274 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000275 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000276 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000277 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000278 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000279 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000280 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000281 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000282 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000283 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000284 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000285 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000286 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000287 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000288 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000289 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000290 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000291 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000292 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000293 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000294 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000295 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000296 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000297 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000298 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000299 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000300 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000301 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000302 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000303 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000304 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000305 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000306 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000307 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000308 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000309 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000310 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000311 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000312 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000313 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000314 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000315 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SCE | 2025 | 4 | 7304
1020000316 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | SCE Trans Detailed inspections use Aerial (helicopter) for "Hard to Access" structures only. |  | SCE | 2025 | 4 | 0
1020000317 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000318 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SCE | 2025 | 4 | 495
1020000319 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000320 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SCE | 2025 | 4 | 66
1020000321 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000322 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000323 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000324 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000325 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000326 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000327 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. |  | SCE | 2025 | 4 | 867.1688
1020000328 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility | SCE Trans Detailed inspections use Aerial (helicopter) for "Hard to Access" structures only. SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. |  | SCE | 2025 | 4 | 0
1020000329 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000330 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. |  | SCE | 2025 | 4 | 58.769
1020000331 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000332 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. |  | SCE | 2025 | 4 | 4
1020000333 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000334 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000335 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000336 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000337 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000338 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000339 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000340 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000341 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000342 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000343 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000344 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000345 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000346 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000347 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000348 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000349 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000350 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000351 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 41
1020000352 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000353 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000354 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 10
1020000355 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000356 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000357 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000358 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000359 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000360 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000361 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000362 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000363 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000364 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000365 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000366 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 39
1020000367 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000368 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000369 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000370 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000371 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000372 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000373 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000374 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000375 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SCE | 2025 | 4 | 6635
1020000376 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | SCE Trans Detailed inspections use Aerial (helicopter) for "Hard to Access" structures only. |  | SCE | 2025 | 4 | 0
1020000377 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000378 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SCE | 2025 | 4 | 982
1020000379 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000380 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SCE | 2025 | 4 | 287
1020000381 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000382 | 14. Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000383 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000384 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000385 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000386 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000387 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. |  | SCE | 2025 | 4 | 787.7416
1020000388 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility | SCE Trans Detailed inspections use Aerial (helicopter) for "Hard to Access" structures only. SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in th |  | SCE | 2025 | 4 | 0
1020000389 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000390 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. |  | SCE | 2025 | 4 | 116.5881
1020000391 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000392 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. |  | SCE | 2025 | 4 | 18
1020000393 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000394 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000395 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000396 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000397 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000398 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000399 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000400 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000401 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000402 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000403 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000404 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000405 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000406 | 14. Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000407 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000408 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000409 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000410 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000411 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 46
1020000412 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000413 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000414 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 21
1020000415 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000416 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000417 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000418 | 14. Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 1
1020000419 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000420 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000421 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000422 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000423 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000424 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000425 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000426 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 45
1020000427 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000428 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000429 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000430 | 14. Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2025 | 4 | 0
1020000431 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000432 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000433 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000434 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000435 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE Trans Aerial inspection is HFTD only | SCE | 2025 | 4
1020000436 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE Trans Aerial inspection is HFTD only | SCE | 2025 | 4
1020000437 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000438 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000439 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000440 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE Trans IR scan is HFTD only | SCE | 2025 | 4
1020000441 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000442 | 14. Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000443 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000444 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000445 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000446 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000447 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | SCE Trans Aerial inspection is HFTD only | SCE | 2025 | 4
1020000448 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  | SCE Trans Aerial inspection is HFTD only | SCE | 2025 | 4
1020000449 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000450 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000451 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000452 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | SCE Trans IR scan is HFTD only | SCE | 2025 | 4
1020000453 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000454 | 14. Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000455 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000456 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000457 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000458 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000459 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000460 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000461 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000462 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000463 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000464 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000465 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000466 | 14. Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000467 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000468 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000469 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000470 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000471 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000472 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000473 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000474 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000475 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000476 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000477 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000478 | 14. Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000479 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000480 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000481 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000482 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000483 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000484 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000485 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000486 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000487 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000488 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000489 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2025 | 4
1020000490 | 14. Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000491 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000492 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000493 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000494 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000495 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000496 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000497 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000498 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 45
1020000499 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000500 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000501 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000502 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 1
1020000503 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000504 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000505 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000506 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000507 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 27
1020000508 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000509 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000510 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 3098
1020000511 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000512 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000513 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000514 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 4
1020000515 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000516 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000517 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000518 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000519 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000520 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000521 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000522 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 2174
1020000523 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000524 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000525 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000526 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000527 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000528 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000529 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000530 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000531 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000532 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000533 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000534 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 65
1020000535 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000536 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000537 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000538 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 1
1020000539 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000540 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000541 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000542 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000543 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 182
1020000544 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000545 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000546 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 6946
1020000547 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000548 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000549 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000550 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 11
1020000551 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000552 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000553 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000554 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000555 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000556 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000557 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000558 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 3772
1020000559 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000560 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000561 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000562 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000563 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000564 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000565 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000566 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000567 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000568 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000569 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000570 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000571 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000572 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000573 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000574 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000575 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000576 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000577 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000578 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000579 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000580 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000581 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000582 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000583 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000584 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000585 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000586 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000587 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000588 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000589 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000590 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000591 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000592 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000593 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000594 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000595 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000596 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000597 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000598 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000599 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000600 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000601 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000602 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000603 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000604 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000605 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000606 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000607 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000608 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000609 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000610 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000611 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000612 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000613 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000614 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000615 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 88
1020000616 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000617 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000618 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 100
1020000619 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000620 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000621 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000622 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000623 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000624 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000625 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000626 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000627 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 14
1020000628 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000629 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000630 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 64
1020000631 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000632 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000633 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000634 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000635 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000636 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000637 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000638 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000639 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000640 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000641 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000642 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000643 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000644 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000645 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000646 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000647 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000648 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000649 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000650 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000651 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 97
1020000652 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000653 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000654 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 89
1020000655 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000656 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000657 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000658 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000659 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000660 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000661 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000662 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000663 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 28
1020000664 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000665 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000666 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 83
1020000667 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000668 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000669 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000670 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2025 | 4 | 0
1020000671 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000672 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000673 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000674 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000675 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000676 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000677 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000678 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000679 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000680 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000681 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000682 | 15. Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000683 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000684 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000685 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000686 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000687 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000688 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000689 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000690 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000691 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000692 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000693 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000694 | 15. Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000695 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000696 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000697 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000698 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000699 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000700 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000701 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000702 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000703 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000704 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000705 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2025 | 4
1020000706 | 15. Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2025 | 4
1020000707 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000708 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000709 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000710 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SCE | 2025 | 4 | 38347
1020000711 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000712 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000713 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000714 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SCE | 2025 | 4 | 785
1020000715 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000716 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000717 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000718 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SCE | 2025 | 4 | 1
1020000719 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000720 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000721 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000722 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SCE | 2025 | 4 | 899
1020000723 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000724 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000725 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000726 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SCE | 2025 | 4 | 105156
1020000727 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000728 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000729 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000730 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SCE | 2025 | 4 | 1100
1020000731 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000732 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000733 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000734 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SCE | 2025 | 4 | 2
1020000735 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000736 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000737 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000738 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SCE | 2025 | 4 | 1383
1020000739 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000740 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000741 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000742 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SCE | 2025 | 4 | 186222
1020000743 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000744 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000745 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000746 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SCE | 2025 | 4 | 5163
1020000747 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000748 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000749 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000750 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SCE | 2025 | 4 | 11
1020000751 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000752 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000753 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000754 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SCE | 2025 | 4 | 3486
1020000755 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000756 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000757 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000758 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SCE | 2025 | 4 | 863
1020000759 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000760 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000761 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000762 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SCE | 2025 | 4 | 2
1020000763 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000764 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000765 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000766 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SCE | 2025 | 4 | 0
1020000767 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000768 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000769 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000770 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SCE | 2025 | 4 | 0
1020000771 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000772 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000773 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000774 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SCE | 2025 | 4 | 81
1020000775 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000776 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000777 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000778 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SCE | 2025 | 4 | 4
1020000779 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000780 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000781 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000782 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SCE | 2025 | 4 | 0
1020000783 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000784 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000785 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000786 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SCE | 2025 | 4 | 0
1020000787 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000788 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000789 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000790 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SCE | 2025 | 4 | 935
1020000791 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000792 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000793 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000794 | 16. Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SCE | 2025 | 4 | 23
1020000795 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000796 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000797 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000798 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SCE | 2025 | 4 | 0
1020000799 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000800 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000801 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2025 | 4
1020000802 | 16. Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SCE | 2025 | 4 | 12
1020000803 | 17. Community outreach metrics | % of customers notified of evacuation in evacuation zone of a utility-ignited wildfire | [5 empty] | Percentage of customers notified of evacuation | SCE has no jurisdiction over evacuation orders. SCE diligently requested and followed up with local governments and law enforcement, and was only able to obtain information from one county. Even then, the information provided included high-level estimations of evacuation counts estimated by the local government and law enforcement entity for a limited amount of fires. Because of this, SCE is unable to obtain the requested data, analyze it, and report on evacuation related requirements in this table. SCE anticipates this to be a recurring challenge going forward. | SCE does not track this metric. | SCE | 2025 | 4

## Table 3
METRIC NUMBER | METRIC | DEFINITION | PURPOSE | ASSUMPTIONS MADE TO CONNECT METRIC TO PURPOSE | THIRD-PARTY VALIDATION (IF ANY) | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1030000000 | 1. Number of CPUC reportable ignitions in HFRA | Count of the number of CPUC reportable ignitions in HFRA | To measure changes in rate of ignitions between years | Factors outside of SCE's control (e.g., wind, live fuel moisture) have a significant effect on CPUC reportable ignition counts in HFRA. | Annual submission of CPUC reportable ignition totals to CPUC | # of ignitions |  |  | SCE | 2025 | 4 | 1
1030000001 | 2. Number of wire downs in HFRA | Count of the number of wire downs in HFRA | To measure changes in rate of fault events which are a pre-cursor both ignition and safety events | Number of wire down incidents in HFRA based on cause. These metrics may help to provide insight on controllable and uncontrollable risks or help plan future activities to focus on a particular type of fault or outage that may be of wildfire risk. | Deep-dive audits of select portions of utility grid | # of wiredowns |  |  | SCE | 2025 | 4 | 111
1030000002 | 3. Number of outages in HFRA | Count of the number of outages in HFRA | To measure changes in rate of wire down events which are a pre-cursor both ignition and safety events | Number of faults in HFRA based on cause. These metrics may help to provide insight on controllable and uncontrollable risks or help plan future activities to focus on a particular type of fault or outage that may be of wildfire risk. | Deep-dive audits of select portions of utility grid | # of outages |  |  | SCE | 2025 | 4 | 650
1030000003 | 4. # of asset management ignition risk-related work orders that are past due (excluding GO95 exceptions) | Count of the total past due T&D ignition risk work orders, excluding GO95 exceptions | To meaure the past due asset-related work orders that have ignition risk and are not subject to GO95 exceptions | This metric will help track past due work order that are related to wildfire risk mitigation and that are largely within the utility's control for addressing. |  | # of work orders |  |  | SCE | 2025 | 4 | 2412
1030000004 | 5. Number of Tree-Caused Circuit Interruptions (TCCIs) in HFRA (ODRM data) | Count of TCCIs in HFRA | To measure trends in how vegetation is causing risk events when contacting overhead circuitry in HFRA | Vegetation that comes into contact with energized circuits can cause a circuit interruption (e.g., fault), however there may be cases with vegetation comes into contact with SCE infrastructure and no fault occurs. |  | # of interruptions |  |  | SCE | 2025 | 4 | 42
1030000005 | 6. Number of trees inspected where at least some vegetation was found in a non-compliant condition in HFRA - Routine | Count of instances in HFRA where vegetation found in non-compliant condition through Routine Line Clearing programs | To meaure the extent to which vegetation exists in non-compliant condition | Routine Line Clearing activities will identify instances in which vegetation exists in a non-compliant condition |  | # of trees |  |  | SCE | 2025 | 4 | 2282
1030000006 | 7. Frequency of PSPS events (total) | Count of PSPS events in which de-energization has occurred | To measure trends in how many de-energization events occur each year | Metric does not account for the normalization of weather, fuel conditions, etc., year over year. Actual performance in each year will be driven by weather and fuel conditions experienced in those years and may vary from prior year and future year projected figures. | CPUC compliance reporting (e.g., PSPS Post-Event Reports, Post Season Reports) | # of events | SCE uses a 2020-2022 PSPS event average to forecast 2023-2025 events. SCE does not forecast a reduction in events from the 2020-2022 average as overall circuit scope reduction may not reduce event count |  | SCE | 2025 | 4 | 6
1030000007 | 8. Scope of PSPS events (total) | Count of circuit de-energized | To meaure trends in how may circuits are de-energized due to PSPS events | Metric does not account for the normalization of weather, fuel conditions, etc., year over year. Actual performance in each year will be driven by weather and fuel conditions experienced in those years and may vary from prior year and future year projected figures. | CPUC compliance reporting (e.g., PSPS Post-Event Reports, Post Season Reports) | # of circuits | Forecast reductions are derived from applying SCE's 2023 reduction forecast to 2020-2022 averages across each future year. |  | SCE | 2025 | 4 | 29
1030000008 | 9. Duration of PSPS (total) | Customer hours de-energized due to PSPS | To measure trends in the amount of customer hours de-energized due to PSPS | Metric does not account for the normalization of weather, fuel conditions, etc., year over year. Actual performance in each year will be driven by weather and fuel conditions experienced in those years and may vary from prior year and future year projected figures. | CPUC compliance reporting (e.g., PSPS Post-Event Reports, Post Season Reports) | # of hours | Forecast reductions are derived from applying SCE's 2023 reduction forecast to 2020-2022 averages across each future year. |  | SCE | 2025 | 4 | 156876.38
1030000009 | 10. # of customers impacted by PSPS | Count of customers de-enrgized due to PSPS | To measure trends in the number of customers de-energized due to PSPS | Metric does not account for the normalization of weather, fuel conditions, etc., year over year. Actual performance in each year will be driven by weather and fuel conditions experienced in those years and may vary from prior year and future year projected figures. | CPUC compliance reporting (e.g., PSPS Post-Event Reports, Post Season Reports) | # of customers | Forecast reductions are derived from applying SCE's 2023 reduction forecast to 2020-2022 averages across each future year. |  | SCE | 2025 | 4 | 5909
1030000010 | 11a. Customer recall of SCE wildfire and preparedness communications - System Wide | The percentage of surveyed customers across SCE's service area who responded that they recalled communications from SCE about the threat of wildfire and how they can prepare for them. | To help measure the effectiveness of its community outreach and engagement activities by measuring customer awareness of SCE’s wildfire messaging and customer wildfire and PSPS programs and services. | Results can be impacted by volume of PSPS events experienced per year, level of marketing and outreach to customers, severity of fire season, and other factors. | In-Language Wildfire Mitigation / PSPS Communications Effectiveness Survey | % | The survey that generates these results is performed twice annually, once once toward the start of Q3 and once toward the end of Q4. Therefore, figures are not provided for Q1 or Q2. |  | SCE | 2025 | 4 | 46
1030000011 | 11b. Customer recall of SCE wildfire and preparedness communications - HFRA only | The percentage of surveyed customers across SCE's HFRA who responded that they recalled communications from SCE about the threat of wildfire and how they can prepare for them. | To help measure the effectiveness of its community outreach and engagement activities by measuring customer awareness of SCE’s wildfire messaging and customer wildfire and PSPS programs and services. | Results can be impacted by volume of PSPS events experienced per year, level of marketing and outreach to customers, severity of fire season, and other factors. | In-Language Wildfire Mitigation / PSPS Communications Effectiveness Survey | % | The survey that generates these results is performed twice annually, once once toward the start of Q3 and once toward the end of Q4. Therefore, figures are not provided for Q1 or Q2. |  | SCE | 2025 | 4 | 56

## Table 4
METRIC NUMBER | METRIC TYPE | METRIC NAME | LINE TYPE | HFTD TIER | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1040000000 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | HFTD Tier 2 | Red flag warning overhead circuit mile days |  |  | SCE | 2025 | 4 | 0.68811
1040000001 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | HFTD Tier 3 | Red flag warning overhead circuit mile days |  |  | SCE | 2025 | 4 | 1262.5317
1040000002 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | Non-HFTD | Red flag warning overhead circuit mile days |  |  | SCE | 2025 | 4 | 296.5713
1040000003 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | HFTD Tier 2 | Red flag warning overhead circuit mile days |  |  | SCE | 2025 | 4 | 44.7177
1040000004 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | HFTD Tier 3 | Red flag warning overhead circuit mile days |  |  | SCE | 2025 | 4 | 820.6981
1040000005 | 1. Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | Non-HFTD | Red flag warning overhead circuit mile days |  |  | SCE | 2025 | 4 | 185.0145
1040000006 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | HFTD Tier 2 | High Wind Warning overhead circuit mile days |  |  | SCE | 2025 | 4 | 2405.1514
1040000007 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | HFTD Tier 3 | High Wind Warning overhead circuit mile days |  |  | SCE | 2025 | 4 | 5418.7019
1040000008 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | Non-HFTD | High Wind Warning overhead circuit mile days |  |  | SCE | 2025 | 4 | 13647.8902
1040000009 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | HFTD Tier 2 | High Wind Warning overhead circuit mile days |  |  | SCE | 2025 | 4 | 1363.0274
1040000010 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | HFTD Tier 3 | High Wind Warning overhead circuit mile days |  |  | SCE | 2025 | 4 | 2246.8432
1040000011 | 2. Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | Non-HFTD | High Wind Warning overhead circuit mile days |  |  | SCE | 2025 | 4 | 4341.4878
1040000012 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | HFTD Tier 2 | High wind warning and red flag warning overhead circuit mile days |  |  | SCE | 2025 | 4 | 0
1040000013 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | HFTD Tier 3 | High wind warning and red flag warning overhead circuit mile days |  |  | SCE | 2025 | 4 | 0
1040000014 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | Non-HFTD | High wind warning and red flag warning overhead circuit mile days |  |  | SCE | 2025 | 4 | 0
1040000015 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | HFTD Tier 2 | High wind warning and red flag warning overhead circuit mile days |  |  | SCE | 2025 | 4 | 0
1040000016 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | HFTD Tier 3 | High wind warning and red flag warning overhead circuit mile days |  |  | SCE | 2025 | 4 | 0
1040000017 | 3. Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | Non-HFTD | High wind warning and red flag warning overhead circuit mile days |  |  | SCE | 2025 | 4 | 0
1040000018 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | HFTD Tier 2 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | SCE | 2025 | 4 | 0
1040000019 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | HFTD Tier 3 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | SCE | 2025 | 4 | 0
1040000020 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | Non-HFTD | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | SCE | 2025 | 4 | 0
1040000021 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | HFTD Tier 2 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | SCE | 2025 | 4 | 0
1040000022 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | HFTD Tier 3 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | SCE | 2025 | 4 | 0
1040000023 | 4. Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | Non-HFTD | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | SCE | 2025 | 4 | 0

## Table 5
METRIC NUMBER | METRIC TYPE | METRIC NAME | RISK EVENT DRIVER | LINE TYPE | HFTD TIER | UNIT(S) | RISK EVENT DRIVER TRACKED | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1050000000 | 1. Fire | Wire down event | Fire | Distribution | Non-HFTD | # risk events | No |  |  | SCE | 2025 | 4 | 9
1050000001 | 1. Fire | Wire down event | Fire | Distribution | HFTD Tier 2 | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000002 | 1. Fire | Wire down event | Fire | Distribution | HFTD Tier 3 | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000003 | 1. Fire | Wire down event | Fire | Transmission | Non-HFTD | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000004 | 1. Fire | Wire down event | Fire | Transmission | HFTD Tier 2 | # risk events | No |  |  | SCE | 2025 | 4 | 1
1050000005 | 1. Fire | Wire down event | Fire | Transmission | HFTD Tier 3 | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000006 | 2. Contact from object | Wire down event | Animal contact | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 10
1050000007 | 2. Contact from object | Wire down event | Animal contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000008 | 2. Contact from object | Wire down event | Animal contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000009 | 2. Contact from object | Wire down event | Animal contact | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000010 | 2. Contact from object | Wire down event | Animal contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000011 | 2. Contact from object | Wire down event | Animal contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000012 | 2. Contact from object | Wire down event | Balloon contact | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 12
1050000013 | 2. Contact from object | Wire down event | Balloon contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000014 | 2. Contact from object | Wire down event | Balloon contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000015 | 2. Contact from object | Wire down event | Balloon contact | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000016 | 2. Contact from object | Wire down event | Balloon contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000017 | 2. Contact from object | Wire down event | Balloon contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000018 | 2. Contact from object | Wire down event | Land vehicle contact | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 78
1050000019 | 2. Contact from object | Wire down event | Land vehicle contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 3
1050000020 | 2. Contact from object | Wire down event | Land vehicle contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 14
1050000021 | 2. Contact from object | Wire down event | Land vehicle contact | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000022 | 2. Contact from object | Wire down event | Land vehicle contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000023 | 2. Contact from object | Wire down event | Land vehicle contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000024 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000025 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000026 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000027 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000028 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000029 | 2. Contact from object | Wire down event | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000030 | 2. Contact from object | Wire down event | 3rd party contact | Distribution | Non-HFTD | # risk events | No |  |  | SCE | 2025 | 4 | 2
1050000031 | 2. Contact from object | Wire down event | 3rd party contact | Distribution | HFTD Tier 2 | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000032 | 2. Contact from object | Wire down event | 3rd party contact | Distribution | HFTD Tier 3 | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000033 | 2. Contact from object | Wire down event | 3rd party contact | Transmission | Non-HFTD | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000034 | 2. Contact from object | Wire down event | 3rd party contact | Transmission | HFTD Tier 2 | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000035 | 2. Contact from object | Wire down event | 3rd party contact | Transmission | HFTD Tier 3 | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000036 | 2. Contact from object | Wire down event | Other (contact from object) | Distribution | Non-HFTD | # risk events | No |  |  | SCE | 2025 | 4 | 6
1050000037 | 2. Contact from object | Wire down event | Other (contact from object) | Distribution | HFTD Tier 2 | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000038 | 2. Contact from object | Wire down event | Other (contact from object) | Distribution | HFTD Tier 3 | # risk events | No |  |  | SCE | 2025 | 4 | 1
1050000039 | 2. Contact from object | Wire down event | Other (contact from object) | Transmission | Non-HFTD | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000040 | 2. Contact from object | Wire down event | Other (contact from object) | Transmission | HFTD Tier 2 | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000041 | 2. Contact from object | Wire down event | Other (contact from object) | Transmission | HFTD Tier 3 | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000042 | 2. Contact from object | Wire down event | Unknown (contact from object) | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000043 | 2. Contact from object | Wire down event | Unknown (contact from object) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000044 | 2. Contact from object | Wire down event | Unknown (contact from object) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000045 | 2. Contact from object | Wire down event | Unknown (contact from object) | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000046 | 2. Contact from object | Wire down event | Unknown (contact from object) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000047 | 2. Contact from object | Wire down event | Unknown (contact from object) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000048 | 3. Vegetation contact | Wire down event | Vegetation contact | Distribution | Non-HFTD | # risk events | Yes | Note: A portion of this data includes "Unknown" HFTD. |  | SCE | 2025 | 4 | 60
1050000049 | 3. Vegetation contact | Wire down event | Vegetation contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 18
1050000050 | 3. Vegetation contact | Wire down event | Vegetation contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 56
1050000051 | 3. Vegetation contact | Wire down event | Vegetation contact | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 1
1050000052 | 3. Vegetation contact | Wire down event | Vegetation contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 1
1050000053 | 3. Vegetation contact | Wire down event | Vegetation contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000054 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000055 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000056 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000057 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000058 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000059 | 4. Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000060 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000061 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000062 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000063 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000064 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000065 | 4. Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000066 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 55
1050000067 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 3
1050000068 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 3
1050000069 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Transmission | Non-HFTD | # risk events | Yes | Note: A portion of this data includes "Unknown" HFTD. |  | SCE | 2025 | 4 | 0
1050000070 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000071 | 4. Equipment / facility failure or damage | Wire down event | Conductor | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000072 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Distribution | Non-HFTD | # risk events | No |  |  | SCE | 2025 | 4 | 14
1050000073 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Distribution | HFTD Tier 2 | # risk events | No |  |  | SCE | 2025 | 4 | 2
1050000074 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Distribution | HFTD Tier 3 | # risk events | No |  |  | SCE | 2025 | 4 | 1
1050000075 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Transmission | Non-HFTD | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000076 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Transmission | HFTD Tier 2 | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000077 | 4. Equipment / facility failure or damage | Wire down event | Connection device | Transmission | HFTD Tier 3 | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000078 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 3
1050000079 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000080 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000081 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000082 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000083 | 4. Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000084 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000085 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000086 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000087 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000088 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000089 | 4. Equipment / facility failure or damage | Wire down event | Fuse | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000090 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000091 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000092 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000093 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000094 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000095 | 4. Equipment / facility failure or damage | Wire down event | Cutout | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000096 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | Non-HFTD | # risk events | No |  |  | SCE | 2025 | 4 | 15
1050000097 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | HFTD Tier 2 | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000098 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | HFTD Tier 3 | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000099 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | Non-HFTD | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000100 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | HFTD Tier 2 | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000101 | 4. Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | HFTD Tier 3 | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000102 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | Non-HFTD | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000103 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | HFTD Tier 2 | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000104 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | HFTD Tier 3 | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000105 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | Non-HFTD | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000106 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | HFTD Tier 2 | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000107 | 4. Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | HFTD Tier 3 | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000108 | 4. Equipment / facility failure or damage | Wire down event | Pole | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 9
1050000109 | 4. Equipment / facility failure or damage | Wire down event | Pole | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000110 | 4. Equipment / facility failure or damage | Wire down event | Pole | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 3
1050000111 | 4. Equipment / facility failure or damage | Wire down event | Pole | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000112 | 4. Equipment / facility failure or damage | Wire down event | Pole | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000113 | 4. Equipment / facility failure or damage | Wire down event | Pole | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000114 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000115 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000116 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000117 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000118 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000119 | 4. Equipment / facility failure or damage | Wire down event | Recloser | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000120 | 4. Equipment / facility failure or damage | Wire down event | Relay | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000121 | 4. Equipment / facility failure or damage | Wire down event | Relay | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000122 | 4. Equipment / facility failure or damage | Wire down event | Relay | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000123 | 4. Equipment / facility failure or damage | Wire down event | Relay | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000124 | 4. Equipment / facility failure or damage | Wire down event | Relay | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000125 | 4. Equipment / facility failure or damage | Wire down event | Relay | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000126 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000127 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000128 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000129 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000130 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000131 | 4. Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000132 | 4. Equipment / facility failure or damage | Wire down event | Splice | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 6
1050000133 | 4. Equipment / facility failure or damage | Wire down event | Splice | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 1
1050000134 | 4. Equipment / facility failure or damage | Wire down event | Splice | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000135 | 4. Equipment / facility failure or damage | Wire down event | Splice | Transmission | Non-HFTD | # risk events | Yes | Note: A portion of this data includes "Unknown" HFTD. |  | SCE | 2025 | 4 | 0
1050000136 | 4. Equipment / facility failure or damage | Wire down event | Splice | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000137 | 4. Equipment / facility failure or damage | Wire down event | Splice | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000138 | 4. Equipment / facility failure or damage | Wire down event | Switch | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000139 | 4. Equipment / facility failure or damage | Wire down event | Switch | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000140 | 4. Equipment / facility failure or damage | Wire down event | Switch | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000141 | 4. Equipment / facility failure or damage | Wire down event | Switch | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000142 | 4. Equipment / facility failure or damage | Wire down event | Switch | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000143 | 4. Equipment / facility failure or damage | Wire down event | Switch | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000144 | 4. Equipment / facility failure or damage | Wire down event | Tap | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000145 | 4. Equipment / facility failure or damage | Wire down event | Tap | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000146 | 4. Equipment / facility failure or damage | Wire down event | Tap | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000147 | 4. Equipment / facility failure or damage | Wire down event | Tap | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000148 | 4. Equipment / facility failure or damage | Wire down event | Tap | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000149 | 4. Equipment / facility failure or damage | Wire down event | Tap | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000150 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000151 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000152 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000153 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000154 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000155 | 4. Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000156 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000157 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000158 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000159 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000160 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000161 | 4. Equipment / facility failure or damage | Wire down event | Transformer | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000162 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000163 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000164 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000165 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000166 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000167 | 4. Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000168 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000169 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000170 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000171 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000172 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000173 | 4. Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000174 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 5
1050000175 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000176 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 1
1050000177 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000178 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000179 | 4. Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000180 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 7
1050000181 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000182 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000183 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000184 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000185 | 5. Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000186 | 6. Contamination | Wire down event | Contamination | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000187 | 6. Contamination | Wire down event | Contamination | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000188 | 6. Contamination | Wire down event | Contamination | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000189 | 6. Contamination | Wire down event | Contamination | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000190 | 6. Contamination | Wire down event | Contamination | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000191 | 6. Contamination | Wire down event | Contamination | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000192 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 7
1050000193 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000194 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 1
1050000195 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000196 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000197 | 7. Vandalism / theft | Wire down event | Vandalism / theft | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000198 | 8. Lightning | Wire down event | Lightning | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 7
1050000199 | 8. Lightning | Wire down event | Lightning | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000200 | 8. Lightning | Wire down event | Lightning | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000201 | 8. Lightning | Wire down event | Lightning | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000202 | 8. Lightning | Wire down event | Lightning | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000203 | 8. Lightning | Wire down event | Lightning | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000204 | 9. Unknown | Wire down event | Unknown (unknown) | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 6
1050000205 | 9. Unknown | Wire down event | Unknown (unknown) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000206 | 9. Unknown | Wire down event | Unknown (unknown) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 1
1050000207 | 9. Unknown | Wire down event | Unknown (unknown) | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000208 | 9. Unknown | Wire down event | Unknown (unknown) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000209 | 9. Unknown | Wire down event | Unknown (unknown) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000210 | 10. Other | Wire down event | Other (other) | Distribution | Non-HFTD | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000211 | 10. Other | Wire down event | Other (other) | Distribution | HFTD Tier 2 | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000212 | 10. Other | Wire down event | Other (other) | Distribution | HFTD Tier 3 | # risk events | No |  |  | SCE | 2025 | 4 | 1
1050000213 | 10. Other | Wire down event | Other (other) | Transmission | Non-HFTD | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000214 | 10. Other | Wire down event | Other (other) | Transmission | HFTD Tier 2 | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000215 | 10. Other | Wire down event | Other (other) | Transmission | HFTD Tier 3 | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000216 | 11. Dig-in | Unplanned Outage | Dig-in | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 12
1050000217 | 11. Dig-in | Unplanned Outage | Dig-in | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 1
1050000218 | 11. Dig-in | Unplanned Outage | Dig-in | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 3
1050000219 | 11. Dig-in | Unplanned Outage | Dig-in | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000220 | 11. Dig-in | Unplanned Outage | Dig-in | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000221 | 11. Dig-in | Unplanned Outage | Dig-in | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000222 | 12. Fire | Unplanned Outage | Fire | Distribution | Non-HFTD | # risk events | No |  |  | SCE | 2025 | 4 | 10
1050000223 | 12. Fire | Unplanned Outage | Fire | Distribution | HFTD Tier 2 | # risk events | No |  |  | SCE | 2025 | 4 | 3
1050000224 | 12. Fire | Unplanned Outage | Fire | Distribution | HFTD Tier 3 | # risk events | No |  |  | SCE | 2025 | 4 | 1
1050000225 | 12. Fire | Unplanned Outage | Fire | Transmission | Non-HFTD | # risk events | No |  |  | SCE | 2025 | 4 | 1
1050000226 | 12. Fire | Unplanned Outage | Fire | Transmission | HFTD Tier 2 | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000227 | 12. Fire | Unplanned Outage | Fire | Transmission | HFTD Tier 3 | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000228 | 13. Contact from object | Unplanned Outage | Animal contact | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 126
1050000229 | 13. Contact from object | Unplanned Outage | Animal contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 8
1050000230 | 13. Contact from object | Unplanned Outage | Animal contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 20
1050000231 | 13. Contact from object | Unplanned Outage | Animal contact | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 3
1050000232 | 13. Contact from object | Unplanned Outage | Animal contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000233 | 13. Contact from object | Unplanned Outage | Animal contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 1
1050000234 | 13. Contact from object | Unplanned Outage | Balloon contact | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 96
1050000235 | 13. Contact from object | Unplanned Outage | Balloon contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 3
1050000236 | 13. Contact from object | Unplanned Outage | Balloon contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 1
1050000237 | 13. Contact from object | Unplanned Outage | Balloon contact | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 2
1050000238 | 13. Contact from object | Unplanned Outage | Balloon contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000239 | 13. Contact from object | Unplanned Outage | Balloon contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 1
1050000240 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 126
1050000241 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 6
1050000242 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 23
1050000243 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 3
1050000244 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 1
1050000245 | 13. Contact from object | Unplanned Outage | Land vehicle contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000246 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | Non-HFTD | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000247 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000248 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000249 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | Non-HFTD | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000250 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000251 | 13. Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000252 | 13. Contact from object | Unplanned Outage | 3rd party contact | Distribution | Non-HFTD | # risk events | No |  |  | SCE | 2025 | 4 | 12
1050000253 | 13. Contact from object | Unplanned Outage | 3rd party contact | Distribution | HFTD Tier 2 | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000254 | 13. Contact from object | Unplanned Outage | 3rd party contact | Distribution | HFTD Tier 3 | # risk events | No |  |  | SCE | 2025 | 4 | 3
1050000255 | 13. Contact from object | Unplanned Outage | 3rd party contact | Transmission | Non-HFTD | # risk events | No |  |  | SCE | 2025 | 4 | 2
1050000256 | 13. Contact from object | Unplanned Outage | 3rd party contact | Transmission | HFTD Tier 2 | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000257 | 13. Contact from object | Unplanned Outage | 3rd party contact | Transmission | HFTD Tier 3 | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000258 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 11
1050000259 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 1
1050000260 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 7
1050000261 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000262 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000263 | 13. Contact from object | Unplanned Outage | Other (contact from object) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000264 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000265 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000266 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000267 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000268 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000269 | 13. Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000270 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 86
1050000271 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 10
1050000272 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 21
1050000273 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 4
1050000274 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000275 | 14. Vegetation contact | Unplanned Outage | Vegetation contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 1
1050000276 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 1
1050000277 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000278 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000279 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000280 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000281 | 15. Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000282 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 7
1050000283 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 1
1050000284 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000285 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000286 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000287 | 15. Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000288 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 123
1050000289 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 12
1050000290 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 41
1050000291 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 5
1050000292 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 3
1050000293 | 15. Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000294 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 163
1050000295 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 27
1050000296 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 34
1050000297 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000298 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 1
1050000299 | 15. Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000300 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 89
1050000301 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 4
1050000302 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 8
1050000303 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 1
1050000304 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000305 | 15. Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000306 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 139
1050000307 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 16
1050000308 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 20
1050000309 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000310 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 1
1050000311 | 15. Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000312 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000313 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000314 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000315 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000316 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000317 | 15. Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000318 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | Non-HFTD | # risk events | No |  |  | SCE | 2025 | 4 | 44
1050000319 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | HFTD Tier 2 | # risk events | No |  |  | SCE | 2025 | 4 | 4
1050000320 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | HFTD Tier 3 | # risk events | No |  |  | SCE | 2025 | 4 | 5
1050000321 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | Non-HFTD | # risk events | No |  |  | SCE | 2025 | 4 | 2
1050000322 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | HFTD Tier 2 | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000323 | 15. Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | HFTD Tier 3 | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000324 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 19
1050000325 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 2
1050000326 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 7
1050000327 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000328 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000329 | 15. Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000330 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 42
1050000331 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000332 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 18
1050000333 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 1
1050000334 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000335 | 15. Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000336 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000337 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000338 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000339 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000340 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000341 | 15. Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000342 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000343 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000344 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000345 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000346 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000347 | 15. Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000348 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000349 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000350 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000351 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000352 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000353 | 15. Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000354 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000355 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000356 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000357 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000358 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000359 | 15. Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000360 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 17
1050000361 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000362 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 3
1050000363 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 1
1050000364 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000365 | 15. Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000366 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000367 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000368 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000369 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000370 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000371 | 15. Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000372 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000373 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000374 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000375 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000376 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000377 | 15. Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000378 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 320
1050000379 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 26
1050000380 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 48
1050000381 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000382 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000383 | 15. Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000384 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000385 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000386 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000387 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000388 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000389 | 15. Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000390 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000391 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000392 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000393 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000394 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000395 | 15. Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000396 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 15
1050000397 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 5
1050000398 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 14
1050000399 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 7
1050000400 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 1
1050000401 | 15. Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000402 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 1
1050000403 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000404 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000405 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 1
1050000406 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000407 | 16. Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000408 | 17. Contamination | Unplanned Outage | Contamination | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000409 | 17. Contamination | Unplanned Outage | Contamination | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000410 | 17. Contamination | Unplanned Outage | Contamination | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000411 | 17. Contamination | Unplanned Outage | Contamination | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 3
1050000412 | 17. Contamination | Unplanned Outage | Contamination | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 1
1050000413 | 17. Contamination | Unplanned Outage | Contamination | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000414 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 6
1050000415 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 1
1050000416 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000417 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000418 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000419 | 18. Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000420 | 19. Lightning | Unplanned Outage | Lightning | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 24
1050000421 | 19. Lightning | Unplanned Outage | Lightning | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 2
1050000422 | 19. Lightning | Unplanned Outage | Lightning | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 2
1050000423 | 19. Lightning | Unplanned Outage | Lightning | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000424 | 19. Lightning | Unplanned Outage | Lightning | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000425 | 19. Lightning | Unplanned Outage | Lightning | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 0
1050000426 | 20. Government agency request | Unplanned Outage | Government agency request | Distribution | Non-HFTD | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000427 | 20. Government agency request | Unplanned Outage | Government agency request | Distribution | HFTD Tier 2 | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000428 | 20. Government agency request | Unplanned Outage | Government agency request | Distribution | HFTD Tier 3 | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000429 | 20. Government agency request | Unplanned Outage | Government agency request | Transmission | Non-HFTD | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000430 | 20. Government agency request | Unplanned Outage | Government agency request | Transmission | HFTD Tier 2 | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000431 | 20. Government agency request | Unplanned Outage | Government agency request | Transmission | HFTD Tier 3 | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000432 | 21. Customer request | Unplanned Outage | Customer request | Distribution | Non-HFTD | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000433 | 21. Customer request | Unplanned Outage | Customer request | Distribution | HFTD Tier 2 | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000434 | 21. Customer request | Unplanned Outage | Customer request | Distribution | HFTD Tier 3 | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000435 | 21. Customer request | Unplanned Outage | Customer request | Transmission | Non-HFTD | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000436 | 21. Customer request | Unplanned Outage | Customer request | Transmission | HFTD Tier 2 | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000437 | 21. Customer request | Unplanned Outage | Customer request | Transmission | HFTD Tier 3 | # risk events | No |  |  | SCE | 2025 | 4 | 0
1050000438 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | Non-HFTD | # risk events | No |  |  | SCE | 2025 | 4 | 675
1050000439 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | HFTD Tier 2 | # risk events | No |  |  | SCE | 2025 | 4 | 95
1050000440 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | HFTD Tier 3 | # risk events | No |  |  | SCE | 2025 | 4 | 204
1050000441 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | Non-HFTD | # risk events | No |  |  | SCE | 2025 | 4 | 16
1050000442 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | HFTD Tier 2 | # risk events | No |  |  | SCE | 2025 | 4 | 1
1050000443 | 22. Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | HFTD Tier 3 | # risk events | No |  |  | SCE | 2025 | 4 | 1
1050000444 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Distribution | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 191
1050000445 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Distribution | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 33
1050000446 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Distribution | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 29
1050000447 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Transmission | Non-HFTD | # risk events | Yes |  |  | SCE | 2025 | 4 | 36
1050000448 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Transmission | HFTD Tier 2 | # risk events | Yes |  |  | SCE | 2025 | 4 | 2
1050000449 | 23. Unknown | Unplanned Outage | Unknown (unknown) | Transmission | HFTD Tier 3 | # risk events | Yes |  |  | SCE | 2025 | 4 | 4
1050000450 | 24. Other | Unplanned Outage | Other (other) | Distribution | Non-HFTD | # risk events | No |  |  | SCE | 2025 | 4 | 566
1050000451 | 24. Other | Unplanned Outage | Other (other) | Distribution | HFTD Tier 2 | # risk events | No |  |  | SCE | 2025 | 4 | 52
1050000452 | 24. Other | Unplanned Outage | Other (other) | Distribution | HFTD Tier 3 | # risk events | No |  |  | SCE | 2025 | 4 | 98
1050000453 | 24. Other | Unplanned Outage | Other (other) | Transmission | Non-HFTD | # risk events | No |  |  | SCE | 2025 | 4 | 46
1050000454 | 24. Other | Unplanned Outage | Other (other) | Transmission | HFTD Tier 2 | # risk events | No |  |  | SCE | 2025 | 4 | 4
1050000455 | 24. Other | Unplanned Outage | Other (other) | Transmission | HFTD Tier 3 | # risk events | No |  |  | SCE | 2025 | 4 | 6

## Table 6
METRIC NUMBER | METRIC TYPE | IGNITION DRIVER | LINE TYPE | HFTD TIER | UNIT(S) | IGNITION DRIVER TRACKED | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1060000000 | 1. Dig-in | Dig-in | Distribution | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000001 | 1. Dig-in | Dig-in | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000002 | 1. Dig-in | Dig-in | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000003 | 1. Dig-in | Dig-in | Transmission | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000004 | 1. Dig-in | Dig-in | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000005 | 1. Dig-in | Dig-in | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000006 | 2. Contact from object | Animal contact | Distribution | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000007 | 2. Contact from object | Animal contact | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000008 | 2. Contact from object | Animal contact | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000009 | 2. Contact from object | Animal contact | Transmission | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000010 | 2. Contact from object | Animal contact | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000011 | 2. Contact from object | Animal contact | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000012 | 2. Contact from object | Balloon contact | Distribution | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000013 | 2. Contact from object | Balloon contact | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000014 | 2. Contact from object | Balloon contact | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000015 | 2. Contact from object | Balloon contact | Transmission | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000016 | 2. Contact from object | Balloon contact | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000017 | 2. Contact from object | Balloon contact | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000018 | 2. Contact from object | Land vehicle contact | Distribution | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 1
1060000019 | 2. Contact from object | Land vehicle contact | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000020 | 2. Contact from object | Land vehicle contact | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 1
1060000021 | 2. Contact from object | Land vehicle contact | Transmission | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000022 | 2. Contact from object | Land vehicle contact | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000023 | 2. Contact from object | Land vehicle contact | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000024 | 2. Contact from object | Aircraft vehicle contact | Distribution | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000025 | 2. Contact from object | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000026 | 2. Contact from object | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000027 | 2. Contact from object | Aircraft vehicle contact | Transmission | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000028 | 2. Contact from object | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000029 | 2. Contact from object | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000030 | 2. Contact from object | 3rd party facility | Distribution | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000031 | 2. Contact from object | 3rd party facility | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000032 | 2. Contact from object | 3rd party facility | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000033 | 2. Contact from object | 3rd party facility | Transmission | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000034 | 2. Contact from object | 3rd party facility | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000035 | 2. Contact from object | 3rd party facility | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000036 | 2. Contact from object | Unknown (contact from object) | Distribution | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000037 | 2. Contact from object | Unknown (contact from object) | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000038 | 2. Contact from object | Unknown (contact from object) | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000039 | 2. Contact from object | Unknown (contact from object) | Transmission | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000040 | 2. Contact from object | Unknown (contact from object) | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000041 | 2. Contact from object | Unknown (contact from object) | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000042 | 2. Contact from object | Other (contact from object) | Distribution | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000043 | 2. Contact from object | Other (contact from object) | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000044 | 2. Contact from object | Other (contact from object) | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000045 | 2. Contact from object | Other (contact from object) | Transmission | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000046 | 2. Contact from object | Other (contact from object) | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000047 | 2. Contact from object | Other (contact from object) | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000048 | 3. Vegetation contact | Vegetation contact | Distribution | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000049 | 3. Vegetation contact | Vegetation contact | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000050 | 3. Vegetation contact | Vegetation contact | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000051 | 3. Vegetation contact | Vegetation contact | Transmission | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000052 | 3. Vegetation contact | Vegetation contact | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000053 | 3. Vegetation contact | Vegetation contact | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000054 | 4. Equipment / facility failure or damage | Anchor / guy | Distribution | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000055 | 4. Equipment / facility failure or damage | Anchor / guy | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000056 | 4. Equipment / facility failure or damage | Anchor / guy | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000057 | 4. Equipment / facility failure or damage | Anchor / guy | Transmission | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000058 | 4. Equipment / facility failure or damage | Anchor / guy | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000059 | 4. Equipment / facility failure or damage | Anchor / guy | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000060 | 4. Equipment / facility failure or damage | Capacitor bank | Distribution | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000061 | 4. Equipment / facility failure or damage | Capacitor bank | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000062 | 4. Equipment / facility failure or damage | Capacitor bank | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000063 | 4. Equipment / facility failure or damage | Capacitor bank | Transmission | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000064 | 4. Equipment / facility failure or damage | Capacitor bank | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000065 | 4. Equipment / facility failure or damage | Capacitor bank | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000066 | 4. Equipment / facility failure or damage | Conductor | Distribution | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 2
1060000067 | 4. Equipment / facility failure or damage | Conductor | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000068 | 4. Equipment / facility failure or damage | Conductor | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000069 | 4. Equipment / facility failure or damage | Conductor | Transmission | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000070 | 4. Equipment / facility failure or damage | Conductor | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000071 | 4. Equipment / facility failure or damage | Conductor | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000072 | 4. Equipment / facility failure or damage | Connection device | Distribution | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 2
1060000073 | 4. Equipment / facility failure or damage | Connection device | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000074 | 4. Equipment / facility failure or damage | Connection device | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000075 | 4. Equipment / facility failure or damage | Connection device | Transmission | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000076 | 4. Equipment / facility failure or damage | Connection device | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000077 | 4. Equipment / facility failure or damage | Connection device | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000078 | 4. Equipment / facility failure or damage | Crossarm | Distribution | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000079 | 4. Equipment / facility failure or damage | Crossarm | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000080 | 4. Equipment / facility failure or damage | Crossarm | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000081 | 4. Equipment / facility failure or damage | Crossarm | Transmission | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000082 | 4. Equipment / facility failure or damage | Crossarm | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000083 | 4. Equipment / facility failure or damage | Crossarm | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000084 | 4. Equipment / facility failure or damage | Fuse | Distribution | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000085 | 4. Equipment / facility failure or damage | Fuse | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000086 | 4. Equipment / facility failure or damage | Fuse | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000087 | 4. Equipment / facility failure or damage | Fuse | Transmission | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000088 | 4. Equipment / facility failure or damage | Fuse | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000089 | 4. Equipment / facility failure or damage | Fuse | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000090 | 4. Equipment / facility failure or damage | Cutout | Distribution | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000091 | 4. Equipment / facility failure or damage | Cutout | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000092 | 4. Equipment / facility failure or damage | Cutout | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000093 | 4. Equipment / facility failure or damage | Cutout | Transmission | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000094 | 4. Equipment / facility failure or damage | Cutout | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000095 | 4. Equipment / facility failure or damage | Cutout | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000096 | 4. Equipment / facility failure or damage | Insulator and bushing | Distribution | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000097 | 4. Equipment / facility failure or damage | Insulator and bushing | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000098 | 4. Equipment / facility failure or damage | Insulator and bushing | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000099 | 4. Equipment / facility failure or damage | Insulator and bushing | Transmission | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000100 | 4. Equipment / facility failure or damage | Insulator and bushing | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000101 | 4. Equipment / facility failure or damage | Insulator and bushing | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000102 | 4. Equipment / facility failure or damage | Lightning arrester | Distribution | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000103 | 4. Equipment / facility failure or damage | Lightning arrester | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000104 | 4. Equipment / facility failure or damage | Lightning arrester | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000105 | 4. Equipment / facility failure or damage | Lightning arrester | Transmission | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000106 | 4. Equipment / facility failure or damage | Lightning arrester | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000107 | 4. Equipment / facility failure or damage | Lightning arrester | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000108 | 4. Equipment / facility failure or damage | Pole | Distribution | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000109 | 4. Equipment / facility failure or damage | Pole | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000110 | 4. Equipment / facility failure or damage | Pole | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000111 | 4. Equipment / facility failure or damage | Pole | Transmission | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000112 | 4. Equipment / facility failure or damage | Pole | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000113 | 4. Equipment / facility failure or damage | Pole | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000114 | 4. Equipment / facility failure or damage | Recloser | Distribution | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000115 | 4. Equipment / facility failure or damage | Recloser | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000116 | 4. Equipment / facility failure or damage | Recloser | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000117 | 4. Equipment / facility failure or damage | Recloser | Transmission | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000118 | 4. Equipment / facility failure or damage | Recloser | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000119 | 4. Equipment / facility failure or damage | Recloser | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000120 | 4. Equipment / facility failure or damage | Relay | Distribution | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000121 | 4. Equipment / facility failure or damage | Relay | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000122 | 4. Equipment / facility failure or damage | Relay | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000123 | 4. Equipment / facility failure or damage | Relay | Transmission | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000124 | 4. Equipment / facility failure or damage | Relay | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000125 | 4. Equipment / facility failure or damage | Relay | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000126 | 4. Equipment / facility failure or damage | Sectionalizer | Distribution | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000127 | 4. Equipment / facility failure or damage | Sectionalizer | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000128 | 4. Equipment / facility failure or damage | Sectionalizer | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000129 | 4. Equipment / facility failure or damage | Sectionalizer | Transmission | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000130 | 4. Equipment / facility failure or damage | Sectionalizer | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000131 | 4. Equipment / facility failure or damage | Sectionalizer | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000132 | 4. Equipment / facility failure or damage | Splice | Distribution | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000133 | 4. Equipment / facility failure or damage | Splice | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000134 | 4. Equipment / facility failure or damage | Splice | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000135 | 4. Equipment / facility failure or damage | Splice | Transmission | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000136 | 4. Equipment / facility failure or damage | Splice | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000137 | 4. Equipment / facility failure or damage | Splice | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000138 | 4. Equipment / facility failure or damage | Switch | Distribution | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000139 | 4. Equipment / facility failure or damage | Switch | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000140 | 4. Equipment / facility failure or damage | Switch | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000141 | 4. Equipment / facility failure or damage | Switch | Transmission | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000142 | 4. Equipment / facility failure or damage | Switch | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000143 | 4. Equipment / facility failure or damage | Switch | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000144 | 4. Equipment / facility failure or damage | Tap | Distribution | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000145 | 4. Equipment / facility failure or damage | Tap | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000146 | 4. Equipment / facility failure or damage | Tap | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000147 | 4. Equipment / facility failure or damage | Tap | Transmission | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000148 | 4. Equipment / facility failure or damage | Tap | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000149 | 4. Equipment / facility failure or damage | Tap | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000150 | 4. Equipment / facility failure or damage | Tie wire | Distribution | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000151 | 4. Equipment / facility failure or damage | Tie wire | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000152 | 4. Equipment / facility failure or damage | Tie wire | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000153 | 4. Equipment / facility failure or damage | Tie wire | Transmission | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000154 | 4. Equipment / facility failure or damage | Tie wire | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000155 | 4. Equipment / facility failure or damage | Tie wire | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000156 | 4. Equipment / facility failure or damage | Transformer | Distribution | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 1
1060000157 | 4. Equipment / facility failure or damage | Transformer | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000158 | 4. Equipment / facility failure or damage | Transformer | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000159 | 4. Equipment / facility failure or damage | Transformer | Transmission | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000160 | 4. Equipment / facility failure or damage | Transformer | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000161 | 4. Equipment / facility failure or damage | Transformer | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000162 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Distribution | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000163 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000164 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000165 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Transmission | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000166 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000167 | 4. Equipment / facility failure or damage | Voltage regulator / booster | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000168 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000169 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000170 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000171 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000172 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000173 | 4. Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000174 | 4. Equipment / facility failure or damage | Other (equipment failure) | Distribution | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000175 | 4. Equipment / facility failure or damage | Other (equipment failure) | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000176 | 4. Equipment / facility failure or damage | Other (equipment failure) | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000177 | 4. Equipment / facility failure or damage | Other (equipment failure) | Transmission | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000178 | 4. Equipment / facility failure or damage | Other (equipment failure) | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000179 | 4. Equipment / facility failure or damage | Other (equipment failure) | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000180 | 5. Wire-to-wire contact | Wire-to-wire contact | Distribution | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000181 | 5. Wire-to-wire contact | Wire-to-wire contact | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000182 | 5. Wire-to-wire contact | Wire-to-wire contact | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000183 | 5. Wire-to-wire contact | Wire-to-wire contact | Transmission | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000184 | 5. Wire-to-wire contact | Wire-to-wire contact | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000185 | 5. Wire-to-wire contact | Wire-to-wire contact | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000186 | 6. Contamination | Contamination | Distribution | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000187 | 6. Contamination | Contamination | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000188 | 6. Contamination | Contamination | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000189 | 6. Contamination | Contamination | Transmission | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000190 | 6. Contamination | Contamination | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000191 | 6. Contamination | Contamination | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000192 | 7. Protective device operation | Protective device operation | Distribution | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000193 | 7. Protective device operation | Protective device operation | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000194 | 7. Protective device operation | Protective device operation | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000195 | 7. Protective device operation | Protective device operation | Transmission | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000196 | 7. Protective device operation | Protective device operation | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000197 | 7. Protective device operation | Protective device operation | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000198 | 8. Vandalism / theft | Vandalism / theft | Distribution | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 1
1060000199 | 8. Vandalism / theft | Vandalism / theft | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000200 | 8. Vandalism / theft | Vandalism / theft | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000201 | 8. Vandalism / theft | Vandalism / theft | Transmission | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000202 | 8. Vandalism / theft | Vandalism / theft | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000203 | 8. Vandalism / theft | Vandalism / theft | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000204 | 9. Lightning | Lightning | Distribution | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000205 | 9. Lightning | Lightning | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000206 | 9. Lightning | Lightning | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000207 | 9. Lightning | Lightning | Transmission | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000208 | 9. Lightning | Lightning | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000209 | 9. Lightning | Lightning | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000210 | 10. Unknown | Unknown (unknown) | Distribution | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000211 | 10. Unknown | Unknown (unknown) | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000212 | 10. Unknown | Unknown (unknown) | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000213 | 10. Unknown | Unknown (unknown) | Transmission | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000214 | 10. Unknown | Unknown (unknown) | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000215 | 10. Unknown | Unknown (unknown) | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000216 | 11. Other | Other (other) | Distribution | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000217 | 11. Other | Other (other) | Distribution | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000218 | 11. Other | Other (other) | Distribution | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000219 | 11. Other | Other (other) | Transmission | Non-HFTD | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000220 | 11. Other | Other (other) | Transmission | HFTD Tier 2 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0
1060000221 | 11. Other | Other (other) | Transmission | HFTD Tier 3 | # ignitions | Yes |  |  | SCE | 2025 | 4 | 0

## Table 7
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1070000000 | 1. Overhead circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 3395
1070000001 | 1. Overhead circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 12794
1070000002 | 1. Overhead circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 2760
1070000003 | 1. Overhead circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 6402
1070000004 | 1. Overhead circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 468
1070000005 | 1. Overhead circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 2307
1070000006 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 568
1070000007 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 387
1070000008 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 1025
1070000009 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 801
1070000010 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 221
1070000011 | 1. Overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 788
1070000012 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 746
1070000013 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 159
1070000014 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 2560
1070000015 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 1535
1070000016 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 150
1070000017 | 1. Overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 349
1070000018 | 1. Overhead circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 478
1070000019 | 1. Overhead circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 2685
1070000020 | 1. Overhead circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 268
1070000021 | 1. Overhead circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 2323
1070000022 | 1. Overhead circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 37
1070000023 | 1. Overhead circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 2008
1070000024 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 190
1070000025 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 217
1070000026 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 255
1070000027 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 727
1070000028 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 32
1070000029 | 1. Overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 555
1070000030 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 238
1070000031 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 201
1070000032 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 424
1070000033 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 1268
1070000034 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 22
1070000035 | 1. Overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 249
1070000036 | 2. Underground circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 6130
1070000037 | 2. Underground circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 13390
1070000038 | 2. Underground circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 1618
1070000039 | 2. Underground circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 2375
1070000040 | 2. Underground circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 57
1070000041 | 2. Underground circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 241
1070000042 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 1182
1070000043 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 648
1070000044 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 799
1070000045 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 361
1070000046 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 36
1070000047 | 2. Underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 108
1070000048 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 1908
1070000049 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 290
1070000050 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 1639
1070000051 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 460
1070000052 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 15
1070000053 | 2. Underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 62
1070000054 | 2. Underground circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 15
1070000055 | 2. Underground circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 232
1070000056 | 2. Underground circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 1
1070000057 | 2. Underground circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 47
1070000058 | 2. Underground circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 0
1070000059 | 2. Underground circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 17
1070000060 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 7
1070000061 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 6
1070000062 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 1
1070000063 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 5
1070000064 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 0
1070000065 | 2. Underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 0
1070000066 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 16
1070000067 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 11
1070000068 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 7
1070000069 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 10
1070000070 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 0
1070000071 | 2. Underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 0
1070000072 | 3. Critical facilities |  | Non-HFTD | Urban | WUI | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 11392
1070000073 | 3. Critical facilities |  | Non-HFTD | Urban | Non-WUI | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 49177
1070000074 | 3. Critical facilities |  | Non-HFTD | Rural | WUI | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 3152
1070000075 | 3. Critical facilities |  | Non-HFTD | Rural | Non-WUI | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 6914
1070000076 | 3. Critical facilities |  | Non-HFTD | Highly rural | WUI | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 230
1070000077 | 3. Critical facilities |  | Non-HFTD | Highly rural | Non-WUI | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 983
1070000078 | 3. Critical facilities |  | HFTD Tier 2 | Urban | WUI | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 1851
1070000079 | 3. Critical facilities |  | HFTD Tier 2 | Urban | Non-WUI | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 1519
1070000080 | 3. Critical facilities |  | HFTD Tier 2 | Rural | WUI | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 1228
1070000081 | 3. Critical facilities |  | HFTD Tier 2 | Rural | Non-WUI | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 869
1070000082 | 3. Critical facilities |  | HFTD Tier 2 | Highly rural | WUI | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 157
1070000083 | 3. Critical facilities |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 419
1070000084 | 3. Critical facilities |  | HFTD Tier 3 | Urban | WUI | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 3298
1070000085 | 3. Critical facilities |  | HFTD Tier 3 | Urban | Non-WUI | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 862
1070000086 | 3. Critical facilities |  | HFTD Tier 3 | Rural | WUI | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 3330
1070000087 | 3. Critical facilities |  | HFTD Tier 3 | Rural | Non-WUI | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 1550
1070000088 | 3. Critical facilities |  | HFTD Tier 3 | Highly rural | WUI | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 168
1070000089 | 3. Critical facilities |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 199
1070000090 | 4. Residential customers |  | Non-HFTD | Urban | WUI | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 860013
1070000091 | 4. Residential customers |  | Non-HFTD | Urban | Non-WUI | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 2717976
1070000092 | 4. Residential customers |  | Non-HFTD | Rural | WUI | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 176115
1070000093 | 4. Residential customers |  | Non-HFTD | Rural | Non-WUI | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 90035
1070000094 | 4. Residential customers |  | Non-HFTD | Highly rural | WUI | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 8617
1070000095 | 4. Residential customers |  | Non-HFTD | Highly rural | Non-WUI | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 3737
1070000096 | 4. Residential customers |  | HFTD Tier 2 | Urban | WUI | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 111235
1070000097 | 4. Residential customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 53186
1070000098 | 4. Residential customers |  | HFTD Tier 2 | Rural | WUI | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 72069
1070000099 | 4. Residential customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 11974
1070000100 | 4. Residential customers |  | HFTD Tier 2 | Highly rural | WUI | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 5663
1070000101 | 4. Residential customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 2248
1070000102 | 4. Residential customers |  | HFTD Tier 3 | Urban | WUI | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 228769
1070000103 | 4. Residential customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 8497
1070000104 | 4. Residential customers |  | HFTD Tier 3 | Rural | WUI | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 145465
1070000105 | 4. Residential customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 9241
1070000106 | 4. Residential customers |  | HFTD Tier 3 | Highly rural | WUI | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 6070
1070000107 | 4. Residential customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 853
1070000108 | 5. Commercial customers |  | Non-HFTD | Urban | WUI | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 67053
1070000109 | 5. Commercial customers |  | Non-HFTD | Urban | Non-WUI | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 395898
1070000110 | 5. Commercial customers |  | Non-HFTD | Rural | WUI | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 14473
1070000111 | 5. Commercial customers |  | Non-HFTD | Rural | Non-WUI | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 45254
1070000112 | 5. Commercial customers |  | Non-HFTD | Highly rural | WUI | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 790
1070000113 | 5. Commercial customers |  | Non-HFTD | Highly rural | Non-WUI | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 2454
1070000114 | 5. Commercial customers |  | HFTD Tier 2 | Urban | WUI | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 7160
1070000115 | 5. Commercial customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 6041
1070000116 | 5. Commercial customers |  | HFTD Tier 2 | Rural | WUI | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 4745
1070000117 | 5. Commercial customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 2524
1070000118 | 5. Commercial customers |  | HFTD Tier 2 | Highly rural | WUI | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 602
1070000119 | 5. Commercial customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 1011
1070000120 | 5. Commercial customers |  | HFTD Tier 3 | Urban | WUI | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 20749
1070000121 | 5. Commercial customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 8509
1070000122 | 5. Commercial customers |  | HFTD Tier 3 | Rural | WUI | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 12977
1070000123 | 5. Commercial customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 6527
1070000124 | 5. Commercial customers |  | HFTD Tier 3 | Highly rural | WUI | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 573
1070000125 | 5. Commercial customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 532
1070000126 | 6. AFN customers |  | Non-HFTD | Urban | WUI | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 336046
1070000127 | 6. AFN customers |  | Non-HFTD | Urban | Non-WUI | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 1095982
1070000128 | 6. AFN customers |  | Non-HFTD | Rural | WUI | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 69074
1070000129 | 6. AFN customers |  | Non-HFTD | Rural | Non-WUI | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 37283
1070000130 | 6. AFN customers |  | Non-HFTD | Highly rural | WUI | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 2966
1070000131 | 6. AFN customers |  | Non-HFTD | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 1195
1070000132 | 6. AFN customers |  | HFTD Tier 2 | Urban | WUI | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 33506
1070000133 | 6. AFN customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 13819
1070000134 | 6. AFN customers |  | HFTD Tier 2 | Rural | WUI | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 22729
1070000135 | 6. AFN customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 3472
1070000136 | 6. AFN customers |  | HFTD Tier 2 | Highly rural | WUI | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 1464
1070000137 | 6. AFN customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 740
1070000138 | 6. AFN customers |  | HFTD Tier 3 | Urban | WUI | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 62025
1070000139 | 6. AFN customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 2174
1070000140 | 6. AFN customers |  | HFTD Tier 3 | Rural | WUI | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 38706
1070000141 | 6. AFN customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 2567
1070000142 | 6. AFN customers |  | HFTD Tier 3 | Highly rural | WUI | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 2067
1070000143 | 6. AFN customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 264
1070000144 | 7. Substations |  | Non-HFTD | Urban | WUI | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 66
1070000145 | 7. Substations |  | Non-HFTD | Urban | Non-WUI | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 392
1070000146 | 7. Substations |  | Non-HFTD | Rural | WUI | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 24
1070000147 | 7. Substations |  | Non-HFTD | Rural | Non-WUI | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 242
1070000148 | 7. Substations |  | Non-HFTD | Highly rural | WUI | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 6
1070000149 | 7. Substations |  | Non-HFTD | Highly rural | Non-WUI | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 124
1070000150 | 7. Substations |  | HFTD Tier 2 | Urban | WUI | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 11
1070000151 | 7. Substations |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 17
1070000152 | 7. Substations |  | HFTD Tier 2 | Rural | WUI | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 12
1070000153 | 7. Substations |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 38
1070000154 | 7. Substations |  | HFTD Tier 2 | Highly rural | WUI | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 5
1070000155 | 7. Substations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 33
1070000156 | 7. Substations |  | HFTD Tier 3 | Urban | WUI | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 17
1070000157 | 7. Substations |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 9
1070000158 | 7. Substations |  | HFTD Tier 3 | Rural | WUI | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 22
1070000159 | 7. Substations |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 41
1070000160 | 7. Substations |  | HFTD Tier 3 | Highly rural | WUI | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 1
1070000161 | 7. Substations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 5
1070000162 | 8. Weather stations |  | Non-HFTD | Urban | WUI | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 78
1070000163 | 8. Weather stations |  | Non-HFTD | Urban | Non-WUI | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 50
1070000164 | 8. Weather stations |  | Non-HFTD | Rural | WUI | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 46
1070000165 | 8. Weather stations |  | Non-HFTD | Rural | Non-WUI | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 34
1070000166 | 8. Weather stations |  | Non-HFTD | Highly rural | WUI | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 0
1070000167 | 8. Weather stations |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 19
1070000168 | 8. Weather stations |  | HFTD Tier 2 | Urban | WUI | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 130
1070000169 | 8. Weather stations |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 99
1070000170 | 8. Weather stations |  | HFTD Tier 2 | Rural | WUI | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 136
1070000171 | 8. Weather stations |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 192
1070000172 | 8. Weather stations |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 25
1070000173 | 8. Weather stations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 143
1070000174 | 8. Weather stations |  | HFTD Tier 3 | Urban | WUI | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 129
1070000175 | 8. Weather stations |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 59
1070000176 | 8. Weather stations |  | HFTD Tier 3 | Rural | WUI | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 372
1070000177 | 8. Weather stations |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 400
1070000178 | 8. Weather stations |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 15
1070000179 | 8. Weather stations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2025 | 4 | 75

## Table 8
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1080000000 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | -13
1080000001 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | -25
1080000002 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | -5
1080000003 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 1
1080000004 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | -1
1080000005 | 1. Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 9
1080000006 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | -3
1080000007 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | -1
1080000008 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | -3
1080000009 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | -1
1080000010 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | -1
1080000011 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 2
1080000012 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000013 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | -1
1080000014 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | -5
1080000015 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | -5
1080000016 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000017 | 1. Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000018 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | -1
1080000019 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000020 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000021 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000022 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000023 | 1. Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000024 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000025 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | -1
1080000026 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000027 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000028 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000029 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | -1
1080000030 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000031 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000032 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000033 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000034 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000035 | 1. Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000036 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | -1
1080000037 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 34
1080000038 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | -2
1080000039 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 16
1080000040 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000041 | 2. Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 4
1080000042 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 6
1080000043 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 3
1080000044 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 9
1080000045 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 9
1080000046 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000047 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 1
1080000048 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 5
1080000049 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 2
1080000050 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 6
1080000051 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 1
1080000052 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000053 | 2. Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000054 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000055 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000056 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000057 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000058 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000059 | 2. Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000060 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000061 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000062 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000063 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000064 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000065 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000066 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000067 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000068 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000069 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000070 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000071 | 2. Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000072 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Urban | WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | -2
1080000073 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Urban | Non-WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000074 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Rural | WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000075 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Rural | Non-WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 1
1080000076 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Highly rural | WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000077 | 3. Net addition (or removal) - Substations |  | Non-HFTD | Highly rural | Non-WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 2
1080000078 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Urban | WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000079 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000080 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Rural | WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 1
1080000081 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000082 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Highly rural | WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000083 | 3. Net addition (or removal) - Substations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000084 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Urban | WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000085 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000086 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Rural | WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000087 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000088 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Highly rural | WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000089 | 3. Net addition (or removal) - Substations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000090 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Urban | WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 15
1080000091 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Urban | Non-WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 11
1080000092 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Rural | WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 4
1080000093 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Rural | Non-WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 4
1080000094 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Highly rural | WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000095 | 4. Net addition (or removal) - Weather stations |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000096 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Urban | WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000097 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000098 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Rural | WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000099 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000100 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000101 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 2
1080000102 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Urban | WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000103 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000104 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Rural | WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 1
1080000105 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 2
1080000106 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1080000107 | 4. Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0

## Table 9
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1090000000 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Urban | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 16
1090000001 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 2
1090000002 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 2
1090000003 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 12
1090000004 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1090000005 | 1. Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1090000006 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 2
1090000007 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1090000008 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 2
1090000009 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 15
1090000010 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1090000011 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1090000012 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 12
1090000013 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 9
1090000014 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 1
1090000015 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 20
1090000016 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1090000017 | 1. Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1090000018 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Urban | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. | Metric Not tracked/available at this Time. | SCE | 2025 | 4
1090000019 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. | Metric Not tracked/available at this Time. | SCE | 2025 | 4
1090000020 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. | Metric Not tracked/available at this Time. | SCE | 2025 | 4
1090000021 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. | Metric Not tracked/available at this Time. | SCE | 2025 | 4
1090000022 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. | Metric Not tracked/available at this Time. | SCE | 2025 | 4
1090000023 | 1. Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. | Metric Not tracked/available at this Time. | SCE | 2025 | 4
1090000024 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. | Metric Not tracked/available at this Time. | SCE | 2025 | 4
1090000025 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. | Metric Not tracked/available at this Time. | SCE | 2025 | 4
1090000026 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. | Metric Not tracked/available at this Time. | SCE | 2025 | 4
1090000027 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. | Metric Not tracked/available at this Time. | SCE | 2025 | 4
1090000028 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. | Metric Not tracked/available at this Time. | SCE | 2025 | 4
1090000029 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. | Metric Not tracked/available at this Time. | SCE | 2025 | 4
1090000030 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. | Metric Not tracked/available at this Time. | SCE | 2025 | 4
1090000031 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. | Metric Not tracked/available at this Time. | SCE | 2025 | 4
1090000032 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. | Metric Not tracked/available at this Time. | SCE | 2025 | 4
1090000033 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. | Metric Not tracked/available at this Time. | SCE | 2025 | 4
1090000034 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. | Metric Not tracked/available at this Time. | SCE | 2025 | 4
1090000035 | 1. Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. | Metric Not tracked/available at this Time. | SCE | 2025 | 4
1090000036 | 2. Number of substations upgraded |  | Non-HFTD | Urban | WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 3
1090000037 | 2. Number of substations upgraded |  | Non-HFTD | Urban | Non-WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 7
1090000038 | 2. Number of substations upgraded |  | Non-HFTD | Rural | WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1090000039 | 2. Number of substations upgraded |  | Non-HFTD | Rural | Non-WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 1
1090000040 | 2. Number of substations upgraded |  | Non-HFTD | Highly rural | WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1090000041 | 2. Number of substations upgraded |  | Non-HFTD | Highly rural | Non-WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 1
1090000042 | 2. Number of substations upgraded |  | HFTD Tier 2 | Urban | WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1090000043 | 2. Number of substations upgraded |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1090000044 | 2. Number of substations upgraded |  | HFTD Tier 2 | Rural | WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1090000045 | 2. Number of substations upgraded |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1090000046 | 2. Number of substations upgraded |  | HFTD Tier 2 | Highly rural | WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1090000047 | 2. Number of substations upgraded |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1090000048 | 2. Number of substations upgraded |  | HFTD Tier 3 | Urban | WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1090000049 | 2. Number of substations upgraded |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 1
1090000050 | 2. Number of substations upgraded |  | HFTD Tier 3 | Rural | WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1090000051 | 2. Number of substations upgraded |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1090000052 | 2. Number of substations upgraded |  | HFTD Tier 3 | Highly rural | WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1090000053 | 2. Number of substations upgraded |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1090000054 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Urban | WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1090000055 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Urban | Non-WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1090000056 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Rural | WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1090000057 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Rural | Non-WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 1
1090000058 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Highly rural | WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1090000059 | 3. Number of weather stations with hardware upgraded |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1090000060 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Urban | WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 1
1090000061 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 2
1090000062 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Rural | WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 3
1090000063 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 3
1090000064 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1090000065 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 3
1090000066 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Urban | WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 1
1090000067 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1090000068 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Rural | WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 3
1090000069 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 3
1090000070 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 0
1090000071 | 3. Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2025 | 4 | 2

## Table 10
METRIC NUMBER | METRIC TYPE | METRIC NAME | WIND WARNING STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1100000000 | 1. Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | RFW only | Number of events |  |  | SCE | 2025 | 4 | 1
1100000001 | 1. Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | HWW only | Number of events |  |  | SCE | 2025 | 4 | 1
1100000002 | 1. Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | HWW & RFW | Number of events |  |  | SCE | 2025 | 4 | 0
1100000003 | 1. Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | Neither | Number of events |  |  | SCE | 2025 | 4 | 4
1100000004 | 1. Recent use of PSPS and fast-trip | Scope of PSPS events (total) | RFW only | Circuit-events, measured in number of events multiplied by number of circuits de-energized | SCE interprets this line item as de-energized circuit count. If one circuit is de-energized in subsequent events, the circuit count would be two. |  | SCE | 2025 | 4 | 2
1100000005 | 1. Recent use of PSPS and fast-trip | Scope of PSPS events (total) | HWW only | Circuit-events, measured in number of events multiplied by number of circuits de-energized | SCE interprets this line item as de-energized circuit count. If one circuit is de-energized in subsequent events, the circuit count would be two. |  | SCE | 2025 | 4 | 1
1100000006 | 1. Recent use of PSPS and fast-trip | Scope of PSPS events (total) | HWW & RFW | Circuit-events, measured in number of events multiplied by number of circuits de-energized | SCE interprets this line item as de-energized circuit count. If one circuit is de-energized in subsequent events, the circuit count would be two. |  | SCE | 2025 | 4 | 0
1100000007 | 1. Recent use of PSPS and fast-trip | Scope of PSPS events (total) | Neither | Circuit-events, measured in number of events multiplied by number of circuits de-energized | SCE interprets this line item as de-energized circuit count. If one circuit is de-energized in subsequent events, the circuit count would be two. |  | SCE | 2025 | 4 | 26
1100000008 | 1. Recent use of PSPS and fast-trip | Duration of PSPS events (total) | RFW only | Customer hours |  |  | SCE | 2025 | 4 | 439.35
1100000009 | 1. Recent use of PSPS and fast-trip | Duration of PSPS events (total) | HWW only | Customer hours |  |  | SCE | 2025 | 4 | 5971.73
1100000010 | 1. Recent use of PSPS and fast-trip | Duration of PSPS events (total) | HWW & RFW | Customer hours |  |  | SCE | 2025 | 4 | 0
1100000011 | 1. Recent use of PSPS and fast-trip | Duration of PSPS events (total) | Neither | Customer hours |  |  | SCE | 2025 | 4 | 150465.3
1100000012 | 1. Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | RFW only | Number of events | Fast curve (FC) events are outages where FC settings were enabled on HFRA circuits and not solely where outages were due to FC. |  | SCE | 2025 | 4 | 0
1100000013 | 1. Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | HWW only | Number of events | Fast curve (FC) events are outages where FC settings were enabled on HFRA circuits and not solely where outages were due to FC. |  | SCE | 2025 | 4 | 0
1100000014 | 1. Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | HWW & RFW | Number of events | Fast curve (FC) events are outages where FC settings were enabled on HFRA circuits and not solely where outages were due to FC. |  | SCE | 2025 | 4 | 0
1100000015 | 1. Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | Neither | Number of events | Fast curve (FC) events are outages where FC settings were enabled on HFRA circuits and not solely where outages were due to FC. |  | SCE | 2025 | 4 | 7
1100000016 | 1. Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | RFW only | Circuit mile days | Data for fast curve is a mix of on and off signals. While the matching of outages to Fast curve enablement was consistent, the switching caused issues with days being counted as a Fast curve day. Code has been adjusted to accurately capture the day as a fast curve day |  | SCE | 2025 | 4 | 5286
1100000017 | 1. Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | HWW only | Circuit mile days | Data for fast curve is a mix of on and off signals. While the matching of outages to Fast curve enablement was consistent, the switching caused issues with days being counted as a Fast curve day. Code has been adjusted to accurately capture the day as a fast curve day |  | SCE | 2025 | 4 | 627
1100000018 | 1. Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | HWW & RFW | Circuit mile days | Data for fast curve is a mix of on and off signals. While the matching of outages to Fast curve enablement was consistent, the switching caused issues with days being counted as a Fast curve day. Code has been adjusted to accurately capture the day as a fast curve day |  | SCE | 2025 | 4 | 0
1100000019 | 1. Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | Neither | Circuit mile days | Data for fast curve is a mix of on and off signals. While the matching of outages to Fast curve enablement was consistent, the switching caused issues with days being counted as a Fast curve day. Code has been adjusted to accurately capture the day as a fast curve day |  | SCE | 2025 | 4 | 925766
1100000020 | 2. Customer hours of PSPS and other outages | Customer hours of planned outages including PSPS (total) |  | Customer hours | Customer Hours of Interruption for Planned Outages (Customers interrupted multiplied by Hours of Interruption). Antcipate data related to planned outages will change as SCE finishes an enhancement project to improve planned outage reporting. |  | SCE | 2025 | 4 | 1846456.9103
1100000021 | 2. Customer hours of PSPS and other outages | Customer hours of unplanned outages, not including PSPS or fast-trip (total) |  | Customer hours |  |  | SCE | 2025 | 4 | 3218433.87
1100000022 | 2. Customer hours of PSPS and other outages | Customer hours of unplanned outages resulting from fast-trip |  | Customer hours | Fast curve (FC) events are outages where FC settings were enabled on HFRA circuits and not solely where outages were due to FC. Customer hours are customer hours of interruption (customers multiplied by their duration) |  | SCE | 2025 | 4 | 16707
1100000023 | 2. Customer hours of PSPS and other outages | System Average Interruption Duration Index (SAIDI) (including PSPS) |  | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served | Includes both planned and unplanned outages. Data is subject to change. |  | SCE | 2025 | 4 | 37.9015
1100000024 | 2. Customer hours of PSPS and other outages | System Average Interruption Duration Index (SAIDI) (excluding PSPS) |  | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served | Includes both planned and unplanned outages. Data is subject to change. |  | SCE | 2025 | 4 | 36.1408
1100000025 | 2. Customer hours of PSPS and other outages | System Average Interruption Frequency Index (SAIFI) (including PSPS) |  | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) | Includes both planned and unplanned outages. Data is subject to change. |  | SCE | 2025 | 4 | 0.26696
1100000026 | 2. Customer hours of PSPS and other outages | System Average Interruption Frequency Index (SAIFI) (excluding PSPS) |  | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) | Includes both planned and unplanned outages. Data is subject to change. |  | SCE | 2025 | 4 | 0.26542
1100000027 | 3. Critical infrastructure impacted by PSPS | Critical infrastructure impacted by PSPS |  | Number of critical infrastructure (in accordance with D.19-05-042) locations impacted multiplied by hours offline | This number is the total number of Critical Infrastructure customers impacted (de-energized) by a PSPS event |  | SCE | 2025 | 4 | 414
1100000028 | 4. Community outreach of PSPS metrics | # of customers impacted by PSPS |  | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | SCE | 2025 | 4 | 5909
1100000029 | 4. Community outreach of PSPS metrics | # of medical baseline customers impacted by PSPS |  | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | SCE | 2025 | 4 | 191
1100000030 | 4. Community outreach of PSPS metrics | # of customers notified prior to initiation of PSPS event |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) | This number is the total number of customers sent pre-event notification (adv Int, Int, Update, Expected) for a potential PSPS de-energization. |  | SCE | 2025 | 4 | 124086
1100000031 | 4. Community outreach of PSPS metrics | # of medical baseline customers notified prior to initiation of PSPS event |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) | This number is the total number of MBL customers sent pre-event notification (adv Int, Int, Update, Expected) for a potential PSPS de-energization. |  | SCE | 2025 | 4 | 2701
1100000032 | 4. Community outreach of PSPS metrics | # of customers notified prior to a PSPS event impacting them |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) | This number is the total number of customers impacted (de-energized) by a PSPS event. NOTE: This is a subset number of K40. De-energized customers who were notified pre-event (adv int, int, update, expected) |  | SCE | 2025 | 4 | 5888
1100000033 | 4. Community outreach of PSPS metrics | # of medical baseline customers notified prior to a PSPS event impacting them |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) | This number is the total number of MBL customers impacted (de-energized) by a PSPS event. NOTE: This is a subset number of K41. De-energized MBL customers who were notified pre-event (adv int, int, update, expected) |  | SCE | 2025 | 4 | 173
1100000034 | 5. Other PSPS metrics | Number of PSPS events in which a notification was sent but no de-energization occurred |  | Number of events |  |  | SCE | 2025 | 4 | 0
1100000035 | 5. Other PSPS metrics | Average number of customers located on de-energized circuit |  | Number of customers | Sum total of all de-energized customers / total number of de-energized circuits. |  | SCE | 2025 | 4 | 227.27
1100000036 | 5. Other PSPS metrics | Customer hours of PSPS per RFW OH circuit mile day |  | Customer hours per RFW OH circuit mile day in time period |  |  | SCE | 2025 | 4 | 7.92
1100000037 | 5. Other PSPS metrics | Customer hours of PSPS per HWW OH circuit mile day |  | Customer hours per HWW OH circuit mile day in time period |  |  | SCE | 2025 | 4 | 13.36
1100000038 | 5. Other PSPS metrics | Customer hours of PSPS per high FPIOH circuit mile day |  | Customer hours per FPI OH circuit mile day in time period |  |  | SCE | 2025 | 4 | 0
1100000039 | 5. Other PSPS metrics | Median time between de-energization, due to PSPS, and inspection of a circuit segment |  | hours | De-en to prep-to-restore time (=MEDIAN,[ARRAY]) |  | SCE | 2025 | 4 | 32.18
1100000040 | 5. Other PSPS metrics | 95 percentile of time between de-energization, due to PSPS, and inspection of a circuit segment |  | hours | De-en to prep-to-restore time (0.95) (=PERCENTILE.INC,[ARRAY]) |  | SCE | 2025 | 4 | 130.52
1100000041 | 5. Other PSPS metrics | Median time between de-energization, due to fast-trip, and inspection of a circuit segment |  | hours | Fast curve (FC) events are outages where FC settings were enabled on HFRA circuits and not solely where outages were due to FC. Median time of entire outage durations instead of inspection on circuit-segment |  | SCE | 2025 | 4 | 3
1100000042 | 5. Other PSPS metrics | 95 percentile of time between de-energization, due to fast-trip, and inspection of a circuit segment |  | hours | Fast curve (FC) events are outages where FC settings were enabled on HFRA circuits and not solely where outages were due to FC. 95th percentile of entire outage durations instead of inspection on circuit-segment. 5% of durations are above value |  | SCE | 2025 | 4 | 15.8
1100000043 | 5. Other PSPS metrics | Number of risk events occurring on a de-energized circuit |  | Number of risk events |  |  | SCE | 2025 | 4 | 0

## Table 13
METRIC NUMBER | WORK ORDER NUMBER | EQUIPMENT TYPE | HFTD TIER | LINE TYPE | DATE OPENED | DUE DATE | GO 95 RULE 18 PRIORITY | UTILITY SPECIFIC REPAIR PRIORITY | DATE REINSPECTED OR MODIFIED | DUE DATE AFTER REINSPECTED OR MODIFIED | GO 95 RULE 18 PRIORITY AFTER REINSPECTED OR MODIFIED | REASON FOR REINSPECTION | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER
1130000000 | 400000734 | Insulator | HFTD Tier 2 | Transmission | 2005-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000001 | 400005640 | High Sign | HFTD Tier 3 | Distribution | 2004-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000002 | 400005656 | High Sign | HFTD Tier 3 | Distribution | 2004-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000003 | 400005887 | High Sign | HFTD Tier 3 | Distribution | 2004-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000004 | 400006050 | Guy | HFTD Tier 2 | Distribution | 2004-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000005 | 400006534 | Insulator | HFTD Tier 3 | Distribution | 2004-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000006 | 400006536 | High Sign | HFTD Tier 3 | Distribution | 2004-11-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000007 | 400006683 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000008 | 400006775 | Hardware/Framing | HFTD Tier 2 | Distribution | 2005-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000009 | 400006923 | Molding | HFTD Tier 2 | Distribution | 2005-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000010 | 400007350 | Ground | HFTD Tier 3 | Distribution | 2004-11-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000011 | 400007388 | Molding | HFTD Tier 3 | Distribution | 2010-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000012 | 400007482 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000013 | 400007483 | High Sign | HFTD Tier 3 | Distribution | 2004-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000014 | 400007566 | High Sign | HFTD Tier 3 | Distribution | 2004-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000015 | 400007687 | Molding | HFTD Tier 3 | Distribution | 2004-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000016 | 400008013 | High Sign | HFTD Tier 3 | Distribution | 2004-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000017 | 400008216 | Molding | HFTD Tier 3 | Distribution | 2004-11-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000018 | 400008348 | High Sign | HFTD Tier 2 | Distribution | 2004-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000019 | 400008453 | High Sign | HFTD Tier 2 | Distribution | 2005-01-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000020 | 400008504 | Molding | HFTD Tier 3 | Distribution | 2010-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000021 | 400008551 | Molding | HFTD Tier 2 | Distribution | 2010-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000022 | 400008583 | High Sign | HFTD Tier 3 | Distribution | 2010-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000023 | 400008910 | Molding | HFTD Tier 3 | Distribution | 2010-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000024 | 400009059 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000025 | 400009285 | High Sign | HFTD Tier 2 | Distribution | 2004-11-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000026 | 400009411 | Guy | HFTD Tier 3 | Distribution | 2008-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000027 | 400009643 | Molding | HFTD Tier 2 | Distribution | 2003-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000028 | 400009717 | High Sign | HFTD Tier 3 | Distribution | 2008-01-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000029 | 400009810 | Molding | HFTD Tier 2 | Distribution | 2003-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000030 | 400009881 | Molding | HFTD Tier 2 | Distribution | 2008-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000031 | 400010119 | Molding | HFTD Tier 2 | Distribution | 2003-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000032 | 400010465 | Molding | HFTD Tier 2 | Distribution | 2003-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000033 | 400010580 | High Sign | HFTD Tier 3 | Distribution | 2003-09-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000034 | 400010618 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-03-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000035 | 400010656 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-11-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000036 | 400010692 | High Sign | HFTD Tier 3 | Distribution | 2001-09-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000037 | 400010888 | High Sign | HFTD Tier 3 | Distribution | 2004-12-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000038 | 400010946 | Crossarm | HFTD Tier 3 | Distribution | 2001-09-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000039 | 400011075 | Molding | HFTD Tier 3 | Distribution | 2005-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000040 | 400011159 | High Sign | HFTD Tier 3 | Distribution | 2001-09-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000041 | 400011169 | Molding | HFTD Tier 2 | Distribution | 2005-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000042 | 400011311 | High Sign | HFTD Tier 3 | Distribution | 2004-12-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000043 | 400011371 | High Sign | HFTD Tier 3 | Distribution | 2003-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000044 | 400011377 | Hardware/Framing | HFTD Tier 2 | Distribution | 2005-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000045 | 400011438 | Molding | HFTD Tier 2 | Distribution | 2003-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000046 | 400011439 | High Sign | HFTD Tier 3 | Distribution | 2001-09-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000047 | 400011500 | High Sign | HFTD Tier 3 | Distribution | 2001-11-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000048 | 400011643 | Molding | HFTD Tier 2 | Distribution | 2003-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000049 | 400011664 | High Sign | HFTD Tier 2 | Distribution | 2008-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000050 | 400011731 | High Sign | HFTD Tier 3 | Distribution | 2006-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000051 | 400011787 | Bond | HFTD Tier 3 | Distribution | 2008-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000052 | 400011873 | Molding | HFTD Tier 3 | Distribution | 2010-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000053 | 400011928 | High Sign | HFTD Tier 2 | Distribution | 2003-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000054 | 400011978 | High Sign | HFTD Tier 2 | Distribution | 2008-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000055 | 400012051 | Guy | HFTD Tier 3 | Distribution | 2004-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000056 | 400012108 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000057 | 400012341 | High Sign | HFTD Tier 2 | Distribution | 2008-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000058 | 400012538 | Molding | HFTD Tier 2 | Distribution | 2003-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000059 | 400012626 | Molding | HFTD Tier 3 | Distribution | 2009-11-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000060 | 400012688 | High Sign | HFTD Tier 3 | Distribution | 2008-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000061 | 400012841 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000062 | 400012884 | Molding | HFTD Tier 3 | Distribution | 2006-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000063 | 400012947 | High Sign | HFTD Tier 3 | Distribution | 2004-10-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000064 | 400012970 | High Sign | HFTD Tier 3 | Distribution | 2004-09-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000065 | 400013010 | Molding | HFTD Tier 3 | Distribution | 2004-08-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000066 | 400013056 | Guy | HFTD Tier 3 | Distribution | 2009-12-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000067 | 400013256 | Molding | HFTD Tier 2 | Distribution | 2008-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000068 | 400013695 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000069 | 400013835 | High Sign | HFTD Tier 3 | Distribution | 2008-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000070 | 400013859 | High Sign | HFTD Tier 2 | Distribution | 2008-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000071 | 400013888 | High Sign | HFTD Tier 3 | Distribution | 2004-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000072 | 400014056 | High Sign | HFTD Tier 3 | Distribution | 2008-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000073 | 400014133 | Molding | HFTD Tier 2 | Distribution | 2008-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000074 | 400014234 | Molding | HFTD Tier 3 | Distribution | 2008-04-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000075 | 400014273 | Molding | HFTD Tier 3 | Distribution | 2008-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000076 | 400014646 | Molding | HFTD Tier 2 | Distribution | 2008-04-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000077 | 400014732 | Molding | HFTD Tier 3 | Distribution | 2008-04-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000078 | 400014896 | Molding | HFTD Tier 3 | Distribution | 2009-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000079 | 400014939 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-12-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000080 | 400014950 | Molding | HFTD Tier 3 | Distribution | 2010-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000081 | 400015028 | Molding | HFTD Tier 3 | Distribution | 2004-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000082 | 400015087 | High Sign | HFTD Tier 2 | Distribution | 2008-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000083 | 400015103 | Molding | HFTD Tier 3 | Distribution | 2003-11-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000084 | 400015150 | High Sign | HFTD Tier 2 | Distribution | 2008-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000085 | 400015232 | High Sign | HFTD Tier 3 | Distribution | 2009-10-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000086 | 400015358 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2008-04-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000087 | 400015389 | Molding | HFTD Tier 2 | Distribution | 2010-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000088 | 400015522 | Molding | HFTD Tier 3 | Distribution | 2006-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000089 | 400015628 | Riser/Conduit | HFTD Tier 3 | Distribution | 2003-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000090 | 400015734 | Riser/Conduit | HFTD Tier 3 | Distribution | 2004-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000091 | 400015767 | High Sign | HFTD Tier 2 | Distribution | 2006-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000092 | 400016093 | Molding | HFTD Tier 3 | Distribution | 2001-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000093 | 400016252 | Crossarm | HFTD Tier 2 | Distribution | 2008-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000094 | 400016288 | High Sign | HFTD Tier 3 | Distribution | 2004-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000095 | 400016318 | High Sign | HFTD Tier 3 | Distribution | 2009-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000096 | 400016417 | High Sign | HFTD Tier 3 | Distribution | 2004-09-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000097 | 400016482 | Molding | HFTD Tier 2 | Distribution | 2003-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000098 | 400016624 | High Sign | HFTD Tier 3 | Distribution | 2004-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000099 | 400016859 | Molding | HFTD Tier 2 | Distribution | 2008-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000100 | 400016872 | Molding | HFTD Tier 3 | Distribution | 2006-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000101 | 400017029 | Molding | HFTD Tier 2 | Distribution | 2001-11-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000102 | 400017286 | Molding | HFTD Tier 2 | Distribution | 2008-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000103 | 400017400 | Guy | HFTD Tier 3 | Distribution | 2005-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000104 | 400017527 | Guy | HFTD Tier 3 | Distribution | 2004-10-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000105 | 400017594 | High Sign | HFTD Tier 3 | Distribution | 2010-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000106 | 400017673 | High Sign | HFTD Tier 3 | Distribution | 2004-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000107 | 400017846 | High Sign | HFTD Tier 2 | Distribution | 2008-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000108 | 400018008 | High Sign | HFTD Tier 2 | Distribution | 2008-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000109 | 400018114 | High Sign | HFTD Tier 2 | Distribution | 2006-04-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000110 | 400018477 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2004-09-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000111 | 400018496 | High Sign | HFTD Tier 3 | Distribution | 2004-11-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000112 | 400018527 | High Sign | HFTD Tier 2 | Distribution | 2004-10-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000113 | 400018572 | High Sign | HFTD Tier 3 | Distribution | 2004-11-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000114 | 400018655 | High Sign | HFTD Tier 3 | Distribution | 2004-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000115 | 400018771 | High Sign | HFTD Tier 2 | Distribution | 2004-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000116 | 400018784 | Molding | HFTD Tier 3 | Distribution | 2010-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000117 | 400018890 | Molding | HFTD Tier 2 | Distribution | 2004-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000118 | 400018968 | Molding | HFTD Tier 3 | Distribution | 2005-02-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000119 | 400019014 | Molding | HFTD Tier 2 | Distribution | 2008-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000120 | 400019053 | High Sign | HFTD Tier 2 | Distribution | 2009-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000121 | 400019302 | High Sign | HFTD Tier 3 | Distribution | 2010-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000122 | 400019575 | Hardware/Framing | HFTD Tier 3 | Distribution | 2003-11-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000123 | 400019625 | Molding | HFTD Tier 3 | Distribution | 2003-12-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000124 | 400019789 | Molding | HFTD Tier 3 | Distribution | 2008-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000125 | 400019897 | High Sign | HFTD Tier 3 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000126 | 400019907 | High Sign | HFTD Tier 3 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000127 | 400019926 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000128 | 400019945 | Molding | HFTD Tier 2 | Distribution | 2004-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000129 | 400019968 | Molding | HFTD Tier 2 | Distribution | 2008-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000130 | 400020069 | High Sign | HFTD Tier 3 | Distribution | 2003-11-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000131 | 400020118 | Molding | HFTD Tier 3 | Distribution | 2003-11-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000132 | 400020280 | Guy | HFTD Tier 2 | Distribution | 2004-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000133 | 400020679 | Molding | HFTD Tier 2 | Distribution | 2004-11-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000134 | 400020716 | High Sign | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000135 | 400020804 | Insulator | HFTD Tier 2 | Distribution | 2004-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000136 | 400020821 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000137 | 400020862 | High Sign | HFTD Tier 3 | Distribution | 2004-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000138 | 400020901 | Molding | HFTD Tier 2 | Distribution | 2004-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000139 | 400020978 | Molding | HFTD Tier 3 | Distribution | 2004-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000140 | 400021371 | Molding | HFTD Tier 2 | Distribution | 2004-07-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000141 | 400021384 | High Sign | HFTD Tier 3 | Distribution | 2005-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000142 | 400021550 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000143 | 400021552 | Molding | HFTD Tier 2 | Distribution | 2008-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000144 | 400021605 | Molding | HFTD Tier 3 | Distribution | 2005-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000145 | 400021618 | High Sign | HFTD Tier 3 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000146 | 400021703 | High Sign | HFTD Tier 2 | Distribution | 2008-05-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000147 | 400021724 | Molding | HFTD Tier 2 | Distribution | 2009-09-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000148 | 400021980 | Bond | HFTD Tier 3 | Distribution | 2008-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000149 | 400022014 | High Sign | HFTD Tier 2 | Distribution | 2003-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000150 | 400022053 | Molding | HFTD Tier 3 | Distribution | 2004-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000151 | 400022221 | Guy | HFTD Tier 2 | Distribution | 2009-10-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000152 | 400022326 | High Sign | HFTD Tier 3 | Distribution | 2004-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000153 | 400022580 | Molding | HFTD Tier 2 | Distribution | 2005-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000154 | 400022704 | Molding | HFTD Tier 2 | Distribution | 2004-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000155 | 400022889 | High Sign | HFTD Tier 3 | Distribution | 2005-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000156 | 400023061 | Insulator | HFTD Tier 3 | Distribution | 2009-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000157 | 400023110 | High Sign | HFTD Tier 3 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000158 | 400023112 | Guy | HFTD Tier 2 | Distribution | 2004-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000159 | 400023118 | Hardware/Framing | HFTD Tier 2 | Distribution | 2003-11-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000160 | 400023251 | High Sign | HFTD Tier 3 | Distribution | 2005-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000161 | 400023404 | High Sign | HFTD Tier 3 | Distribution | 2005-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000162 | 400023413 | Molding | HFTD Tier 3 | Distribution | 2008-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000163 | 400023604 | High Sign | HFTD Tier 3 | Distribution | 2004-09-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000164 | 400023607 | Molding | HFTD Tier 3 | Distribution | 2004-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000165 | 400023866 | Guy | HFTD Tier 3 | Distribution | 2004-07-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000166 | 400023886 | Guy | HFTD Tier 2 | Distribution | 2004-11-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000167 | 400023974 | Molding | HFTD Tier 3 | Distribution | 2001-01-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000168 | 400024023 | Molding | HFTD Tier 3 | Distribution | 2006-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000169 | 400024110 | High Sign | HFTD Tier 3 | Distribution | 2004-11-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000170 | 400024126 | High Sign | HFTD Tier 2 | Distribution | 2010-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000171 | 400024137 | High Sign | HFTD Tier 2 | Distribution | 2009-10-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000172 | 400024219 | High Sign | HFTD Tier 2 | Distribution | 2001-11-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000173 | 400024220 | Crossarm | HFTD Tier 3 | Distribution | 2004-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000174 | 400024246 | High Sign | HFTD Tier 3 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000175 | 400024252 | High Sign | HFTD Tier 3 | Distribution | 2004-10-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000176 | 400024253 | High Sign | HFTD Tier 3 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000177 | 400024293 | High Sign | HFTD Tier 2 | Distribution | 2001-09-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000178 | 400024440 | Molding | HFTD Tier 3 | Distribution | 2004-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000179 | 400024878 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000180 | 400024907 | Molding | HFTD Tier 3 | Distribution | 2001-12-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000181 | 400025102 | Molding | HFTD Tier 2 | Distribution | 2008-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000182 | 400025226 | Molding | HFTD Tier 3 | Distribution | 2006-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000183 | 400025357 | High Sign | HFTD Tier 2 | Distribution | 2008-05-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000184 | 400025499 | High Sign | HFTD Tier 3 | Distribution | 2009-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000185 | 400025560 | High Sign | HFTD Tier 2 | Distribution | 2001-12-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000186 | 400025581 | High Sign | HFTD Tier 3 | Distribution | 2005-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000187 | 400026025 | High Sign | HFTD Tier 3 | Distribution | 2004-11-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000188 | 400026149 | High Sign | HFTD Tier 3 | Distribution | 2004-09-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000189 | 400026249 | Molding | HFTD Tier 2 | Distribution | 2001-12-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000190 | 400026308 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000191 | 400026329 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000192 | 400026339 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000193 | 400026521 | High Sign | HFTD Tier 2 | Distribution | 2004-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000194 | 400026540 | Insulator | HFTD Tier 3 | Distribution | 2004-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000195 | 400026548 | High Sign | HFTD Tier 3 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000196 | 400026560 | High Sign | HFTD Tier 2 | Distribution | 2004-11-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000197 | 400026732 | High Sign | HFTD Tier 3 | Distribution | 2005-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000198 | 400026959 | Molding | HFTD Tier 3 | Distribution | 2005-09-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000199 | 400027192 | High Sign | HFTD Tier 3 | Distribution | 2000-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000200 | 400027318 | Molding | HFTD Tier 3 | Distribution | 2004-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000201 | 400027530 | High Sign | HFTD Tier 3 | Distribution | 2010-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000202 | 400027534 | Molding | HFTD Tier 3 | Distribution | 2009-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000203 | 400027600 | High Sign | HFTD Tier 3 | Distribution | 2005-09-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000204 | 400027724 | High Sign | HFTD Tier 2 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000205 | 400027776 | Molding | HFTD Tier 2 | Distribution | 2005-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000206 | 400027955 | Molding | HFTD Tier 2 | Distribution | 2001-12-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000207 | 400028202 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000208 | 400028304 | High Sign | HFTD Tier 3 | Distribution | 2004-12-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000209 | 400028330 | High Sign | HFTD Tier 2 | Distribution | 2004-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000210 | 400028409 | Molding | HFTD Tier 3 | Distribution | 2004-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000211 | 400028568 | High Sign | HFTD Tier 2 | Distribution | 2004-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000212 | 400028598 | Riser/Conduit | HFTD Tier 2 | Distribution | 2005-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000213 | 400028730 | Hardware/Framing | HFTD Tier 2 | Distribution | 2009-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000214 | 400028860 | Insulator | HFTD Tier 2 | Distribution | 2004-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000215 | 400028939 | High Sign | HFTD Tier 3 | Distribution | 2005-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000216 | 400029117 | High Sign | HFTD Tier 3 | Distribution | 2004-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000217 | 400029263 | Molding | HFTD Tier 2 | Distribution | 2004-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000218 | 400029634 | High Sign | HFTD Tier 2 | Distribution | 2004-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000219 | 400029666 | Molding | HFTD Tier 3 | Distribution | 2004-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000220 | 400029776 | Molding | HFTD Tier 3 | Distribution | 2004-09-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000221 | 400029874 | Molding | HFTD Tier 3 | Distribution | 2003-11-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000222 | 400029939 | Molding | HFTD Tier 3 | Distribution | 2005-08-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000223 | 400029942 | Molding | HFTD Tier 3 | Distribution | 2008-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000224 | 400030245 | Guy | HFTD Tier 3 | Distribution | 2009-12-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000225 | 400030613 | Molding | HFTD Tier 3 | Distribution | 2004-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000226 | 400030696 | High Sign | HFTD Tier 3 | Distribution | 2009-10-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000227 | 400030776 | Molding | HFTD Tier 2 | Distribution | 2004-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000228 | 400030781 | High Sign | HFTD Tier 2 | Distribution | 2009-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000229 | 400030784 | Molding | HFTD Tier 3 | Distribution | 2006-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000230 | 400030878 | Molding | HFTD Tier 3 | Distribution | 2001-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000231 | 400031631 | High Sign | HFTD Tier 3 | Distribution | 2004-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000232 | 400031726 | High Sign | HFTD Tier 2 | Distribution | 2004-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000233 | 400031752 | High Sign | HFTD Tier 2 | Distribution | 2004-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000234 | 400031909 | High Sign | HFTD Tier 2 | Distribution | 2004-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000235 | 400032020 | High Sign | HFTD Tier 2 | Distribution | 2010-01-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000236 | 400032162 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000237 | 400032232 | Guy | HFTD Tier 3 | Distribution | 2005-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000238 | 400032573 | Molding | HFTD Tier 2 | Distribution | 2010-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000239 | 400032601 | High Sign | HFTD Tier 3 | Distribution | 2009-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000240 | 400032649 | High Sign | HFTD Tier 3 | Distribution | 2010-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000241 | 400032759 | Guy | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000242 | 400032813 | Ground | HFTD Tier 2 | Distribution | 2008-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000243 | 400032823 | Molding | HFTD Tier 3 | Distribution | 2005-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000244 | 400033212 | Molding | HFTD Tier 3 | Distribution | 2004-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000245 | 400033294 | Molding | HFTD Tier 3 | Distribution | 2009-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000246 | 400033327 | Molding | HFTD Tier 3 | Distribution | 2004-11-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000247 | 400033627 | High Sign | HFTD Tier 3 | Distribution | 2004-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000248 | 400033731 | Hardware/Framing | HFTD Tier 2 | Distribution | 2009-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000249 | 400033888 | Molding | HFTD Tier 2 | Distribution | 2003-12-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000250 | 400034003 | High Sign | HFTD Tier 2 | Distribution | 2006-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000251 | 400034047 | Molding | HFTD Tier 2 | Distribution | 2003-11-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000252 | 400034090 | High Sign | HFTD Tier 3 | Distribution | 2005-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000253 | 400034121 | High Sign | HFTD Tier 3 | Distribution | 2005-07-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000254 | 400034137 | Molding | HFTD Tier 3 | Distribution | 2008-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000255 | 400034268 | High Sign | HFTD Tier 3 | Distribution | 2004-08-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000256 | 400034315 | High Sign | HFTD Tier 3 | Distribution | 2005-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000257 | 400034354 | High Sign | HFTD Tier 3 | Distribution | 2004-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000258 | 400034367 | Hardware/Framing | HFTD Tier 2 | Distribution | 2009-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000259 | 400034482 | Molding | HFTD Tier 3 | Distribution | 2005-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000260 | 400034777 | High Sign | HFTD Tier 3 | Distribution | 2005-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000261 | 400034855 | High Sign | HFTD Tier 2 | Distribution | 2003-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000262 | 400034860 | High Sign | HFTD Tier 3 | Distribution | 2008-10-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000263 | 400035000 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000264 | 400035016 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000265 | 400035178 | High Sign | HFTD Tier 3 | Distribution | 2009-01-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000266 | 400035192 | High Sign | HFTD Tier 2 | Distribution | 2005-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000267 | 400035391 | Molding | HFTD Tier 2 | Distribution | 2005-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000268 | 400035497 | Molding | HFTD Tier 2 | Distribution | 2008-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000269 | 400035680 | Molding | HFTD Tier 3 | Distribution | 2001-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000270 | 400036094 | Molding | HFTD Tier 3 | Distribution | 2004-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000271 | 400036414 | High Sign | HFTD Tier 2 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000272 | 400036458 | High Sign | HFTD Tier 3 | Distribution | 2004-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000273 | 400036662 | High Sign | HFTD Tier 3 | Distribution | 2009-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000274 | 400036786 | Termination | HFTD Tier 3 | Distribution | 2008-12-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000275 | 400036803 | Molding | HFTD Tier 3 | Distribution | 2009-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000276 | 400036849 | High Sign | HFTD Tier 3 | Distribution | 2004-11-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000277 | 400036965 | Guy | HFTD Tier 3 | Distribution | 2004-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000278 | 400037022 | Molding | HFTD Tier 2 | Distribution | 2009-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000279 | 400037185 | Molding | HFTD Tier 2 | Distribution | 2004-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000280 | 400037328 | High Sign | HFTD Tier 3 | Distribution | 2004-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000281 | 400037343 | Molding | HFTD Tier 2 | Distribution | 2005-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000282 | 400037652 | High Sign | HFTD Tier 3 | Distribution | 2004-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000283 | 400037782 | Guy | HFTD Tier 3 | Distribution | 2008-12-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000284 | 400037819 | Molding | HFTD Tier 3 | Distribution | 2009-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000285 | 400037905 | Molding | HFTD Tier 2 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000286 | 400037979 | Molding | HFTD Tier 3 | Distribution | 2001-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000287 | 400038237 | High Sign | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000288 | 400038425 | High Sign | HFTD Tier 3 | Distribution | 2004-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000289 | 400038489 | High Sign | HFTD Tier 3 | Distribution | 2004-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000290 | 400038528 | Guy | HFTD Tier 2 | Distribution | 2009-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000291 | 400038629 | High Sign | HFTD Tier 2 | Distribution | 2005-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000292 | 400038734 | Molding | HFTD Tier 2 | Distribution | 2004-11-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000293 | 400038921 | Riser/Conduit | HFTD Tier 3 | Distribution | 2003-11-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000294 | 400039138 | Molding | HFTD Tier 3 | Distribution | 2003-12-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000295 | 400039373 | Molding | HFTD Tier 2 | Distribution | 2004-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000296 | 400039460 | Guy | HFTD Tier 3 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000297 | 400039502 | High Sign | HFTD Tier 2 | Distribution | 2004-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000298 | 400039626 | High Sign | HFTD Tier 2 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000299 | 400039681 | High Sign | HFTD Tier 2 | Distribution | 2004-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000300 | 400040141 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000301 | 400040194 | High Sign | HFTD Tier 2 | Distribution | 2000-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000302 | 400040345 | Guy | HFTD Tier 2 | Distribution | 2004-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000303 | 400040370 | High Sign | HFTD Tier 3 | Distribution | 2004-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000304 | 400040391 | Molding | HFTD Tier 3 | Distribution | 2005-09-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000305 | 400040403 | High Sign | HFTD Tier 3 | Distribution | 2004-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000306 | 400040545 | Molding | HFTD Tier 3 | Distribution | 2005-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000307 | 400040636 | High Sign | HFTD Tier 2 | Distribution | 2004-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000308 | 400040831 | High Sign | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000309 | 400040875 | High Sign | HFTD Tier 3 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000310 | 400041106 | High Sign | HFTD Tier 2 | Distribution | 2009-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000311 | 400041232 | High Sign | HFTD Tier 3 | Distribution | 2004-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000312 | 400041483 | High Sign | HFTD Tier 3 | Distribution | 2004-08-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000313 | 400041487 | High Sign | HFTD Tier 2 | Distribution | 2004-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000314 | 400041520 | Molding | HFTD Tier 2 | Distribution | 2004-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000315 | 400042326 | High Sign | HFTD Tier 2 | Distribution | 2009-08-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000316 | 400042327 | Molding | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000317 | 400042405 | High Sign | HFTD Tier 2 | Distribution | 2004-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000318 | 400042515 | Molding | HFTD Tier 3 | Distribution | 2005-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000319 | 400042663 | High Sign | HFTD Tier 2 | Distribution | 2004-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000320 | 400042796 | High Sign | HFTD Tier 3 | Distribution | 2005-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000321 | 400042893 | Riser/Conduit | HFTD Tier 2 | Distribution | 2005-01-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000322 | 400043047 | High Sign | HFTD Tier 2 | Distribution | 2004-09-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000323 | 400043068 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000324 | 400043103 | Molding | HFTD Tier 2 | Distribution | 2005-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000325 | 400043237 | Molding | HFTD Tier 2 | Distribution | 2004-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000326 | 400043275 | High Sign | HFTD Tier 2 | Distribution | 2004-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000327 | 400043332 | High Sign | HFTD Tier 2 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000328 | 400043466 | High Sign | HFTD Tier 3 | Distribution | 2005-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000329 | 400043576 | Molding | HFTD Tier 2 | Distribution | 2004-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000330 | 400043787 | High Sign | HFTD Tier 2 | Distribution | 2001-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000331 | 400043863 | Molding | HFTD Tier 3 | Distribution | 2001-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000332 | 400043936 | Molding | HFTD Tier 2 | Distribution | 2005-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000333 | 400044439 | High Sign | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000334 | 400044534 | Molding | HFTD Tier 2 | Distribution | 2000-10-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000335 | 400044552 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000336 | 400044691 | High Sign | HFTD Tier 3 | Distribution | 2005-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000337 | 400044795 | High Sign | HFTD Tier 2 | Distribution | 2004-10-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000338 | 400044854 | Hardware/Framing | HFTD Tier 2 | Distribution | 2009-08-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000339 | 400045261 | High Sign | HFTD Tier 2 | Distribution | 2004-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000340 | 400045285 | High Sign | HFTD Tier 2 | Distribution | 2004-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000341 | 400045292 | High Sign | HFTD Tier 3 | Distribution | 2009-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000342 | 400045303 | High Sign | HFTD Tier 3 | Distribution | 2005-08-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000343 | 400045326 | High Sign | HFTD Tier 3 | Distribution | 2009-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000344 | 400045385 | High Sign | HFTD Tier 3 | Distribution | 2004-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000345 | 400045386 | Molding | HFTD Tier 3 | Distribution | 2003-12-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000346 | 400045474 | Guy | HFTD Tier 3 | Distribution | 2004-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000347 | 400045631 | High Sign | HFTD Tier 2 | Distribution | 2003-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000348 | 400045638 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000349 | 400045671 | Riser/Conduit | HFTD Tier 2 | Distribution | 2009-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000350 | 400045899 | Molding | HFTD Tier 2 | Distribution | 2004-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000351 | 400046010 | Molding | HFTD Tier 3 | Distribution | 2003-12-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000352 | 400046071 | Insulator | HFTD Tier 2 | Distribution | 2009-10-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000353 | 400046130 | High Sign | HFTD Tier 3 | Distribution | 2003-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000354 | 400046171 | High Sign | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000355 | 400046268 | High Sign | HFTD Tier 3 | Distribution | 2000-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000356 | 400046347 | High Sign | HFTD Tier 3 | Distribution | 2005-08-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000357 | 400046497 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000358 | 400046527 | High Sign | HFTD Tier 2 | Distribution | 2004-09-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000359 | 400046599 | Guy | HFTD Tier 2 | Distribution | 2004-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000360 | 400046609 | High Sign | HFTD Tier 2 | Distribution | 2004-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000361 | 400046635 | Molding | HFTD Tier 3 | Distribution | 2009-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000362 | 400047158 | High Sign | HFTD Tier 3 | Distribution | 2004-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000363 | 400047201 | Guy | HFTD Tier 3 | Distribution | 2004-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000364 | 400047296 | Molding | HFTD Tier 3 | Distribution | 2004-10-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000365 | 400047306 | Molding | HFTD Tier 2 | Distribution | 2001-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000366 | 400047360 | High Sign | HFTD Tier 2 | Distribution | 2009-08-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000367 | 400047406 | Molding | HFTD Tier 2 | Distribution | 2004-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000368 | 400047555 | Molding | HFTD Tier 2 | Distribution | 2006-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000369 | 400047589 | Molding | HFTD Tier 3 | Distribution | 2009-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000370 | 400047761 | High Sign | HFTD Tier 2 | Distribution | 2009-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000371 | 400048054 | High Sign | HFTD Tier 2 | Distribution | 2008-11-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000372 | 400048119 | Molding | HFTD Tier 2 | Distribution | 2001-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000373 | 400048246 | Guy | HFTD Tier 3 | Distribution | 2005-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000374 | 400048432 | High Sign | HFTD Tier 2 | Distribution | 2004-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000375 | 400048645 | High Sign | HFTD Tier 2 | Distribution | 2004-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000376 | 400048768 | High Sign | HFTD Tier 2 | Distribution | 2004-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000377 | 400048801 | High Sign | HFTD Tier 2 | Distribution | 2004-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000378 | 400048894 | Hardware/Framing | HFTD Tier 2 | Distribution | 2009-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000379 | 400048895 | Molding | HFTD Tier 2 | Distribution | 2003-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000380 | 400048943 | High Sign | HFTD Tier 3 | Distribution | 2009-10-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000381 | 400048963 | Molding | HFTD Tier 3 | Distribution | 2005-08-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000382 | 400048973 | High Sign | HFTD Tier 3 | Distribution | 2004-09-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000383 | 400049190 | Molding | HFTD Tier 3 | Distribution | 2005-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000384 | 400049255 | Molding | HFTD Tier 2 | Distribution | 2003-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000385 | 400049635 | Molding | HFTD Tier 2 | Distribution | 2005-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000386 | 400049717 | High Sign | HFTD Tier 3 | Distribution | 2009-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000387 | 400049777 | Guy | HFTD Tier 3 | Distribution | 2009-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000388 | 400049800 | Molding | HFTD Tier 3 | Distribution | 2004-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000389 | 400049970 | High Sign | HFTD Tier 3 | Distribution | 2003-11-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000390 | 400050188 | High Sign | HFTD Tier 2 | Distribution | 2005-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000391 | 400050208 | High Sign | HFTD Tier 2 | Distribution | 2004-02-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000392 | 400050384 | Molding | HFTD Tier 3 | Distribution | 2004-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000393 | 400050433 | High Sign | HFTD Tier 2 | Distribution | 2004-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000394 | 400050444 | High Sign | HFTD Tier 3 | Distribution | 2009-07-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000395 | 400050897 | Molding | HFTD Tier 2 | Distribution | 2003-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000396 | 400050955 | Molding | HFTD Tier 2 | Distribution | 2005-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000397 | 400051099 | High Sign | HFTD Tier 2 | Distribution | 2004-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000398 | 400051112 | Hardware/Framing | HFTD Tier 2 | Distribution | 2009-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000399 | 400051154 | Molding | HFTD Tier 2 | Distribution | 2008-11-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000400 | 400051476 | Molding | HFTD Tier 3 | Distribution | 2004-08-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000401 | 400051489 | High Sign | HFTD Tier 2 | Distribution | 2005-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000402 | 400051578 | Guy | HFTD Tier 3 | Distribution | 2005-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000403 | 400051736 | Molding | HFTD Tier 2 | Distribution | 2003-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000404 | 400052015 | High Sign | HFTD Tier 2 | Distribution | 2003-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000405 | 400052050 | High Sign | HFTD Tier 3 | Distribution | 2004-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000406 | 400052116 | High Sign | HFTD Tier 2 | Distribution | 2005-01-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000407 | 400052133 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000408 | 400052157 | Molding | HFTD Tier 3 | Distribution | 2005-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000409 | 400052280 | High Sign | HFTD Tier 2 | Distribution | 2004-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000410 | 400052297 | High Sign | HFTD Tier 3 | Distribution | 2006-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000411 | 400052344 | Guy | HFTD Tier 3 | Distribution | 2004-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000412 | 400052550 | High Sign | HFTD Tier 3 | Distribution | 2009-10-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000413 | 400052579 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-10-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000414 | 400052745 | High Sign | HFTD Tier 3 | Distribution | 2004-09-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000415 | 400053094 | High Sign | HFTD Tier 2 | Distribution | 2004-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000416 | 400053176 | Molding | HFTD Tier 3 | Distribution | 2005-08-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000417 | 400053181 | Molding | HFTD Tier 2 | Distribution | 2004-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000418 | 400053198 | High Sign | HFTD Tier 2 | Distribution | 2004-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000419 | 400053297 | High Sign | HFTD Tier 2 | Distribution | 2004-10-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000420 | 400053576 | High Sign | HFTD Tier 2 | Distribution | 2008-11-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000421 | 400053658 | High Sign | HFTD Tier 2 | Distribution | 2009-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000422 | 400053851 | Molding | HFTD Tier 2 | Distribution | 2004-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000423 | 400053858 | Molding | HFTD Tier 2 | Distribution | 2004-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000424 | 400053971 | High Sign | HFTD Tier 3 | Distribution | 2004-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000425 | 400054045 | High Sign | HFTD Tier 2 | Distribution | 2004-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000426 | 400054118 | High Sign | HFTD Tier 2 | Distribution | 2005-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000427 | 400054139 | Molding | HFTD Tier 2 | Distribution | 2004-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000428 | 400054304 | High Sign | HFTD Tier 2 | Distribution | 2009-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000429 | 400054337 | High Sign | HFTD Tier 3 | Distribution | 2005-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000430 | 400054448 | High Sign | HFTD Tier 3 | Distribution | 2004-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000431 | 400054531 | Guy | HFTD Tier 2 | Distribution | 2005-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000432 | 400054606 | Molding | HFTD Tier 2 | Distribution | 2009-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000433 | 400054840 | High Sign | HFTD Tier 3 | Distribution | 2004-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000434 | 400055150 | High Sign | HFTD Tier 3 | Distribution | 2004-12-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000435 | 400055202 | Molding | HFTD Tier 2 | Distribution | 2003-11-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000436 | 400055333 | High Sign | HFTD Tier 2 | Distribution | 2005-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000437 | 400055402 | Molding | HFTD Tier 2 | Distribution | 2005-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000438 | 400055440 | Molding | HFTD Tier 3 | Distribution | 2008-12-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000439 | 400055455 | Guy | HFTD Tier 3 | Distribution | 2004-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000440 | 400055487 | High Sign | HFTD Tier 2 | Distribution | 2004-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000441 | 400055523 | Hardware/Framing | HFTD Tier 2 | Distribution | 2005-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000442 | 400055533 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2009-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000443 | 400055639 | Molding | HFTD Tier 2 | Distribution | 2010-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000444 | 400055699 | High Sign | HFTD Tier 2 | Distribution | 2004-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000445 | 400055896 | High Sign | HFTD Tier 2 | Distribution | 2004-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000446 | 400055897 | High Sign | HFTD Tier 3 | Distribution | 2009-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000447 | 400055899 | Molding | HFTD Tier 2 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000448 | 400056039 | Molding | HFTD Tier 2 | Distribution | 2001-01-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000449 | 400056106 | High Sign | HFTD Tier 2 | Distribution | 2004-10-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000450 | 400056232 | High Sign | HFTD Tier 3 | Distribution | 2003-11-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000451 | 400056277 | High Sign | HFTD Tier 2 | Distribution | 2004-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000452 | 400056319 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000453 | 400056430 | Molding | HFTD Tier 2 | Distribution | 2008-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000454 | 400056470 | Molding | HFTD Tier 3 | Distribution | 2004-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000455 | 400056603 | High Sign | HFTD Tier 2 | Distribution | 2001-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000456 | 400056711 | Molding | HFTD Tier 3 | Distribution | 2005-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000457 | 400057206 | High Sign | HFTD Tier 2 | Distribution | 2001-12-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000458 | 400057329 | Molding | HFTD Tier 2 | Distribution | 2004-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000459 | 400057339 | Guy | HFTD Tier 3 | Distribution | 2005-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000460 | 400057390 | High Sign | HFTD Tier 2 | Distribution | 2005-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000461 | 400057428 | High Sign | HFTD Tier 2 | Distribution | 2004-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000462 | 400057437 | High Sign | HFTD Tier 3 | Distribution | 2004-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000463 | 400057573 | Molding | HFTD Tier 2 | Distribution | 2004-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000464 | 400057845 | High Sign | HFTD Tier 3 | Distribution | 2004-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000465 | 400057909 | High Sign | HFTD Tier 3 | Distribution | 2003-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000466 | 400058089 | Molding | HFTD Tier 3 | Distribution | 2004-12-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000467 | 400058141 | Molding | HFTD Tier 2 | Distribution | 2008-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000468 | 400058289 | Molding | HFTD Tier 3 | Distribution | 2009-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000469 | 400058376 | High Sign | HFTD Tier 2 | Distribution | 2004-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000470 | 400058485 | High Sign | HFTD Tier 3 | Distribution | 2005-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000471 | 400058623 | Molding | HFTD Tier 3 | Distribution | 2005-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000472 | 400058635 | High Sign | HFTD Tier 2 | Distribution | 2004-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000473 | 400058655 | Molding | HFTD Tier 3 | Distribution | 2004-11-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000474 | 400058680 | Molding | HFTD Tier 3 | Distribution | 2005-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000475 | 400058685 | Molding | HFTD Tier 2 | Distribution | 2005-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000476 | 400058703 | High Sign | HFTD Tier 2 | Distribution | 2003-11-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000477 | 400058722 | Ground | HFTD Tier 3 | Distribution | 2004-11-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000478 | 400058923 | High Sign | HFTD Tier 2 | Distribution | 2005-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000479 | 400059019 | High Sign | HFTD Tier 3 | Distribution | 2004-08-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000480 | 400059027 | High Sign | HFTD Tier 3 | Distribution | 2004-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000481 | 400059034 | High Sign | HFTD Tier 2 | Distribution | 2005-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000482 | 400059088 | High Sign | HFTD Tier 3 | Distribution | 2004-08-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000483 | 400059184 | High Sign | HFTD Tier 3 | Distribution | 2009-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000484 | 400059297 | Molding | HFTD Tier 2 | Distribution | 2001-01-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000485 | 400059412 | High Sign | HFTD Tier 3 | Distribution | 2009-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000486 | 400059414 | High Sign | HFTD Tier 2 | Distribution | 2003-11-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000487 | 400059448 | Molding | HFTD Tier 2 | Distribution | 2004-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000488 | 400059502 | Molding | HFTD Tier 3 | Distribution | 2008-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000489 | 400059636 | High Sign | HFTD Tier 2 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000490 | 400059703 | Molding | HFTD Tier 3 | Distribution | 2004-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000491 | 400059752 | High Sign | HFTD Tier 2 | Distribution | 2004-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000492 | 400060000 | Bond | HFTD Tier 2 | Distribution | 2005-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000493 | 400060110 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000494 | 400060220 | Molding | HFTD Tier 3 | Distribution | 2005-08-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000495 | 400060497 | High Sign | HFTD Tier 2 | Distribution | 2008-11-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000496 | 400060894 | Molding | HFTD Tier 3 | Distribution | 2004-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000497 | 400060974 | Molding | HFTD Tier 3 | Distribution | 2004-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000498 | 400060987 | Molding | HFTD Tier 3 | Distribution | 2004-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000499 | 400061176 | Molding | HFTD Tier 2 | Distribution | 2004-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000500 | 400061215 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000501 | 400061255 | High Sign | HFTD Tier 3 | Distribution | 2004-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000502 | 400061410 | Molding | HFTD Tier 2 | Distribution | 2004-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000503 | 400061731 | Molding | HFTD Tier 2 | Distribution | 2005-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000504 | 400061877 | Molding | HFTD Tier 2 | Distribution | 2005-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000505 | 400061915 | High Sign | HFTD Tier 2 | Distribution | 2009-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000506 | 400061939 | High Sign | HFTD Tier 2 | Distribution | 2005-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000507 | 400062029 | High Sign | HFTD Tier 2 | Distribution | 2005-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000508 | 400062395 | High Sign | HFTD Tier 2 | Distribution | 2004-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000509 | 400062498 | High Sign | HFTD Tier 3 | Distribution | 2000-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000510 | 400062635 | Guy | HFTD Tier 3 | Distribution | 2005-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000511 | 400062699 | Molding | HFTD Tier 2 | Distribution | 2006-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000512 | 400062979 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000513 | 400062984 | Hardware/Framing | HFTD Tier 3 | Distribution | 2005-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000514 | 400062995 | Molding | HFTD Tier 3 | Distribution | 2004-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000515 | 400063063 | Molding | HFTD Tier 2 | Distribution | 2004-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000516 | 400063136 | Guy | HFTD Tier 2 | Distribution | 2004-11-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000517 | 400063452 | Molding | HFTD Tier 2 | Distribution | 2004-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000518 | 400063509 | Molding | HFTD Tier 3 | Distribution | 2005-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000519 | 400063873 | Molding | HFTD Tier 3 | Distribution | 2009-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000520 | 400064004 | High Sign | HFTD Tier 2 | Distribution | 2001-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000521 | 400064048 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2005-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000522 | 400064160 | Ground | HFTD Tier 2 | Distribution | 2006-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000523 | 400064339 | Molding | HFTD Tier 3 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000524 | 400064354 | Molding | HFTD Tier 3 | Distribution | 2004-11-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000525 | 400064688 | High Sign | HFTD Tier 2 | Distribution | 2005-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000526 | 400064707 | High Sign | HFTD Tier 3 | Distribution | 2004-06-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000527 | 400065080 | Cable/Conductor | HFTD Tier 2 | Distribution | 2002-01-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000528 | 400065180 | High Sign | HFTD Tier 2 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000529 | 400065314 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000530 | 400065476 | High Sign | HFTD Tier 2 | Distribution | 2005-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000531 | 400065621 | Molding | HFTD Tier 3 | Distribution | 2000-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000532 | 400065666 | High Sign | HFTD Tier 3 | Distribution | 2005-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000533 | 400065697 | High Sign | HFTD Tier 3 | Distribution | 2005-09-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000534 | 400065897 | High Sign | HFTD Tier 3 | Distribution | 2005-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000535 | 400065992 | Molding | HFTD Tier 2 | Distribution | 2005-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000536 | 400066061 | Molding | HFTD Tier 2 | Distribution | 2005-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000537 | 400066371 | Molding | HFTD Tier 2 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000538 | 400066433 | Molding | HFTD Tier 2 | Distribution | 2004-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000539 | 400066511 | Molding | HFTD Tier 3 | Distribution | 2004-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000540 | 400066527 | Molding | HFTD Tier 2 | Distribution | 2004-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000541 | 400066573 | High Sign | HFTD Tier 3 | Distribution | 2004-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000542 | 400066589 | Molding | HFTD Tier 3 | Distribution | 2004-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000543 | 400066621 | High Sign | HFTD Tier 2 | Distribution | 2004-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000544 | 400066870 | Molding | HFTD Tier 2 | Distribution | 2001-01-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000545 | 400066904 | High Sign | HFTD Tier 2 | Distribution | 2005-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000546 | 400066967 | High Sign | HFTD Tier 2 | Distribution | 2005-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000547 | 400067062 | High Sign | HFTD Tier 2 | Distribution | 2009-09-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000548 | 400067142 | High Sign | HFTD Tier 3 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000549 | 400067188 | High Sign | HFTD Tier 2 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000550 | 400067209 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-12-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000551 | 400067223 | High Sign | HFTD Tier 3 | Distribution | 2005-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000552 | 400067358 | High Sign | HFTD Tier 3 | Distribution | 2005-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000553 | 400067367 | High Sign | HFTD Tier 2 | Distribution | 2008-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000554 | 400067368 | High Sign | HFTD Tier 2 | Distribution | 2009-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000555 | 400067412 | High Sign | HFTD Tier 2 | Distribution | 2004-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000556 | 400067636 | Molding | HFTD Tier 3 | Distribution | 2008-11-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000557 | 400067695 | Molding | HFTD Tier 3 | Distribution | 2004-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000558 | 400067806 | Molding | HFTD Tier 2 | Distribution | 2005-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000559 | 400067853 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000560 | 400067870 | High Sign | HFTD Tier 2 | Distribution | 2005-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000561 | 400067941 | Molding | HFTD Tier 2 | Distribution | 2009-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000562 | 400068034 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-06-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000563 | 400068408 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000564 | 400068534 | High Sign | HFTD Tier 3 | Distribution | 2009-09-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000565 | 400068642 | High Sign | HFTD Tier 2 | Distribution | 2005-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000566 | 400068978 | High Sign | HFTD Tier 2 | Distribution | 2005-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000567 | 400069056 | High Sign | HFTD Tier 3 | Distribution | 2004-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000568 | 400069143 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000569 | 400069249 | Molding | HFTD Tier 3 | Distribution | 2005-08-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000570 | 400069253 | Molding | HFTD Tier 3 | Distribution | 2004-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000571 | 400069444 | High Sign | HFTD Tier 3 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000572 | 400069680 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000573 | 400069765 | Molding | HFTD Tier 2 | Distribution | 2005-02-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000574 | 400069807 | Molding | HFTD Tier 2 | Distribution | 2005-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000575 | 400069934 | High Sign | HFTD Tier 3 | Distribution | 2004-11-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000576 | 400070051 | High Sign | HFTD Tier 3 | Distribution | 2005-09-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000577 | 400070396 | Molding | HFTD Tier 3 | Distribution | 2003-11-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000578 | 400070444 | High Sign | HFTD Tier 2 | Distribution | 2005-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000579 | 400070454 | High Sign | HFTD Tier 3 | Distribution | 2009-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000580 | 400070511 | Molding | HFTD Tier 3 | Distribution | 2005-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000581 | 400070514 | High Sign | HFTD Tier 2 | Distribution | 2005-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000582 | 400070544 | Molding | HFTD Tier 2 | Distribution | 2005-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000583 | 400070580 | Molding | HFTD Tier 2 | Distribution | 2004-02-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000584 | 400070737 | Guy | HFTD Tier 2 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000585 | 400070787 | High Sign | HFTD Tier 2 | Distribution | 2009-09-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000586 | 400070876 | Molding | HFTD Tier 2 | Distribution | 2009-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000587 | 400071283 | Molding | HFTD Tier 3 | Distribution | 2004-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000588 | 400071390 | Guy | HFTD Tier 3 | Distribution | 2005-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000589 | 400071476 | Molding | HFTD Tier 3 | Distribution | 2005-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000590 | 400071529 | Molding | HFTD Tier 2 | Distribution | 2009-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000591 | 400071927 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-10-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000592 | 400071949 | High Sign | HFTD Tier 3 | Distribution | 2004-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000593 | 400072045 | High Sign | HFTD Tier 2 | Distribution | 2004-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000594 | 400072089 | High Sign | HFTD Tier 2 | Distribution | 2004-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000595 | 400072147 | Molding | HFTD Tier 2 | Distribution | 2010-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000596 | 400072611 | Molding | HFTD Tier 3 | Distribution | 2010-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000597 | 400072973 | Guy | HFTD Tier 2 | Distribution | 2005-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000598 | 400073009 | Guy | HFTD Tier 3 | Distribution | 2009-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000599 | 400073128 | Molding | HFTD Tier 3 | Distribution | 2005-02-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000600 | 400073403 | Molding | HFTD Tier 2 | Distribution | 2005-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000601 | 400073578 | High Sign | HFTD Tier 3 | Distribution | 2005-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000602 | 400073721 | High Sign | HFTD Tier 2 | Distribution | 2004-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000603 | 400074197 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000604 | 400074563 | Molding | HFTD Tier 2 | Distribution | 2004-09-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000605 | 400074680 | Molding | HFTD Tier 3 | Distribution | 2005-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000606 | 400074764 | Cable/Conductor | HFTD Tier 3 | Distribution | 2008-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000607 | 400074891 | High Sign | HFTD Tier 2 | Distribution | 2004-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000608 | 400074893 | Molding | HFTD Tier 2 | Distribution | 2009-09-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000609 | 400074933 | High Sign | HFTD Tier 3 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000610 | 400075025 | Molding | HFTD Tier 2 | Distribution | 2009-10-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000611 | 400075230 | Guy | HFTD Tier 2 | Distribution | 2005-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000612 | 400075276 | High Sign | HFTD Tier 3 | Distribution | 2004-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000613 | 400075567 | Molding | HFTD Tier 3 | Distribution | 2004-12-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000614 | 400075704 | High Sign | HFTD Tier 3 | Distribution | 2001-11-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000615 | 400075807 | Cable/Conductor | HFTD Tier 3 | Distribution | 2003-12-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000616 | 400075899 | High Sign | HFTD Tier 3 | Distribution | 2005-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000617 | 400075903 | High Sign | HFTD Tier 2 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000618 | 400075991 | High Sign | HFTD Tier 3 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000619 | 400076022 | High Sign | HFTD Tier 3 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000620 | 400076054 | High Sign | HFTD Tier 3 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000621 | 400076156 | Molding | HFTD Tier 2 | Distribution | 2005-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000622 | 400076161 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000623 | 400076497 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000624 | 400076522 | High Sign | HFTD Tier 3 | Distribution | 2005-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000625 | 400076527 | High Sign | HFTD Tier 2 | Distribution | 2005-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000626 | 400076536 | Molding | HFTD Tier 2 | Distribution | 2004-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000627 | 400077078 | High Sign | HFTD Tier 3 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000628 | 400077201 | High Sign | HFTD Tier 2 | Distribution | 2003-12-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000629 | 400077267 | Molding | HFTD Tier 3 | Distribution | 2004-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000630 | 400077315 | High Sign | HFTD Tier 2 | Distribution | 2005-09-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000631 | 400077341 | High Sign | HFTD Tier 3 | Distribution | 2005-09-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000632 | 400077754 | Molding | HFTD Tier 2 | Distribution | 2004-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000633 | 400077755 | High Sign | HFTD Tier 3 | Distribution | 2004-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000634 | 400077842 | High Sign | HFTD Tier 3 | Distribution | 2005-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000635 | 400077920 | Hardware/Framing | HFTD Tier 3 | Distribution | 2004-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000636 | 400077958 | High Sign | HFTD Tier 3 | Distribution | 2005-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000637 | 400077964 | Molding | HFTD Tier 3 | Distribution | 2009-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000638 | 400078011 | High Sign | HFTD Tier 2 | Distribution | 2005-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000639 | 400078111 | High Sign | HFTD Tier 3 | Distribution | 2004-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000640 | 400078304 | Riser/Conduit | HFTD Tier 3 | Distribution | 2004-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000641 | 400078310 | Molding | HFTD Tier 3 | Distribution | 2001-01-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000642 | 400078390 | High Sign | HFTD Tier 3 | Distribution | 2004-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000643 | 400078425 | Molding | HFTD Tier 2 | Distribution | 2004-05-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000644 | 400078430 | High Sign | HFTD Tier 2 | Distribution | 2004-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000645 | 400078484 | High Sign | HFTD Tier 2 | Distribution | 2004-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000646 | 400078675 | Molding | HFTD Tier 3 | Distribution | 2009-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000647 | 400078888 | High Sign | HFTD Tier 2 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000648 | 400078933 | Guy | HFTD Tier 2 | Distribution | 2004-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000649 | 400078942 | High Sign | HFTD Tier 2 | Distribution | 2005-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000650 | 400079053 | High Sign | HFTD Tier 3 | Distribution | 2005-05-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000651 | 400079130 | Riser/Conduit | HFTD Tier 2 | Distribution | 2009-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000652 | 400079297 | High Sign | HFTD Tier 3 | Distribution | 2001-11-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000653 | 400079339 | High Sign | HFTD Tier 3 | Distribution | 2009-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000654 | 400079347 | High Sign | HFTD Tier 3 | Distribution | 2005-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000655 | 400079436 | High Sign | HFTD Tier 2 | Distribution | 2004-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000656 | 400079448 | High Sign | HFTD Tier 2 | Distribution | 2005-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000657 | 400079557 | Guy | HFTD Tier 2 | Distribution | 2009-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000658 | 400079604 | High Sign | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000659 | 400079631 | Molding | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000660 | 400079671 | Guy | HFTD Tier 2 | Distribution | 2003-12-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000661 | 400079700 | High Sign | HFTD Tier 2 | Distribution | 2003-12-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000662 | 400079831 | Hardware/Framing | HFTD Tier 2 | Distribution | 2004-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000663 | 400080158 | High Sign | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000664 | 400080253 | Molding | HFTD Tier 3 | Distribution | 2004-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000665 | 400080677 | High Sign | HFTD Tier 2 | Distribution | 2008-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000666 | 400080747 | High Sign | HFTD Tier 2 | Distribution | 2003-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000667 | 400080773 | High Sign | HFTD Tier 2 | Distribution | 2009-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000668 | 400080909 | Molding | HFTD Tier 3 | Distribution | 2005-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000669 | 400080927 | Molding | HFTD Tier 3 | Distribution | 2004-12-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000670 | 400080971 | High Sign | HFTD Tier 2 | Distribution | 2004-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000671 | 400080988 | Molding | HFTD Tier 3 | Distribution | 2004-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000672 | 400081026 | High Sign | HFTD Tier 2 | Distribution | 2005-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000673 | 400081101 | High Sign | HFTD Tier 3 | Distribution | 2009-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000674 | 400081184 | Guy | HFTD Tier 2 | Distribution | 2003-11-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000675 | 400081214 | Molding | HFTD Tier 3 | Distribution | 2003-12-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000676 | 400081389 | High Sign | HFTD Tier 3 | Distribution | 2004-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000677 | 400081418 | High Sign | HFTD Tier 2 | Distribution | 2009-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000678 | 400081530 | High Sign | HFTD Tier 3 | Distribution | 2008-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000679 | 400081578 | Molding | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000680 | 400081780 | Molding | HFTD Tier 2 | Distribution | 2009-10-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000681 | 400082065 | Molding | HFTD Tier 2 | Distribution | 2009-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000682 | 400082170 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000683 | 400082177 | Molding | HFTD Tier 2 | Distribution | 2004-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000684 | 400082226 | Molding | HFTD Tier 2 | Distribution | 2005-02-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000685 | 400082279 | High Sign | HFTD Tier 2 | Distribution | 2004-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000686 | 400082328 | Molding | HFTD Tier 3 | Distribution | 2010-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000687 | 400082425 | Molding | HFTD Tier 3 | Distribution | 2004-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000688 | 400082429 | High Sign | HFTD Tier 3 | Distribution | 2004-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000689 | 400082529 | High Sign | HFTD Tier 2 | Distribution | 2005-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000690 | 400082535 | Molding | HFTD Tier 2 | Distribution | 2004-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000691 | 400082563 | Hardware/Framing | HFTD Tier 2 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000692 | 400082599 | High Sign | HFTD Tier 2 | Distribution | 2009-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000693 | 400082632 | Guy | HFTD Tier 3 | Distribution | 2009-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000694 | 400082649 | High Sign | HFTD Tier 2 | Distribution | 2004-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000695 | 400082670 | High Sign | HFTD Tier 2 | Distribution | 2004-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000696 | 400082697 | Molding | HFTD Tier 2 | Distribution | 2004-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000697 | 400082724 | High Sign | HFTD Tier 3 | Distribution | 2004-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000698 | 400082776 | Guy | HFTD Tier 2 | Distribution | 2004-05-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000699 | 400082825 | Molding | HFTD Tier 3 | Distribution | 2004-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000700 | 400083009 | Molding | HFTD Tier 2 | Distribution | 2006-07-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000701 | 400083053 | Molding | HFTD Tier 3 | Distribution | 2004-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000702 | 400083332 | High Sign | HFTD Tier 3 | Distribution | 2005-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000703 | 400083694 | Guy | HFTD Tier 3 | Distribution | 2004-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000704 | 400083932 | High Sign | HFTD Tier 2 | Distribution | 2004-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000705 | 400084111 | High Sign | HFTD Tier 3 | Distribution | 2008-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000706 | 400084126 | High Sign | HFTD Tier 2 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000707 | 400084203 | Guy | HFTD Tier 3 | Distribution | 2009-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000708 | 400084218 | Guy | HFTD Tier 3 | Distribution | 2010-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000709 | 400084232 | Molding | HFTD Tier 3 | Distribution | 2009-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000710 | 400084288 | High Sign | HFTD Tier 2 | Distribution | 2001-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000711 | 400084409 | High Sign | HFTD Tier 3 | Distribution | 2003-11-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000712 | 400084428 | Molding | HFTD Tier 3 | Distribution | 2005-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000713 | 400084490 | Molding | HFTD Tier 2 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000714 | 400084788 | Riser/Conduit | HFTD Tier 3 | Distribution | 2009-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000715 | 400084820 | Molding | HFTD Tier 2 | Distribution | 2005-01-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000716 | 400084857 | High Sign | HFTD Tier 2 | Distribution | 2005-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000717 | 400084964 | High Sign | HFTD Tier 2 | Distribution | 2004-05-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000718 | 400085001 | High Sign | HFTD Tier 3 | Distribution | 2004-10-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000719 | 400085008 | High Sign | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000720 | 400085253 | Molding | HFTD Tier 3 | Distribution | 2005-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000721 | 400085476 | Molding | HFTD Tier 2 | Distribution | 2005-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000722 | 400085523 | High Sign | HFTD Tier 2 | Distribution | 2004-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000723 | 400085699 | Molding | HFTD Tier 2 | Distribution | 2009-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000724 | 400085706 | Guy | HFTD Tier 2 | Distribution | 2009-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000725 | 400086201 | Molding | HFTD Tier 3 | Distribution | 2009-09-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000726 | 400086366 | Molding | HFTD Tier 2 | Distribution | 2003-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000727 | 400086381 | High Sign | HFTD Tier 2 | Distribution | 2010-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000728 | 400086506 | Molding | HFTD Tier 2 | Distribution | 2004-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000729 | 400086572 | Molding | HFTD Tier 2 | Distribution | 2004-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000730 | 400086670 | Molding | HFTD Tier 3 | Distribution | 2005-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000731 | 400086698 | Ground | HFTD Tier 3 | Distribution | 2009-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000732 | 400086811 | High Sign | HFTD Tier 2 | Distribution | 2008-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000733 | 400087061 | High Sign | HFTD Tier 2 | Distribution | 2004-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000734 | 400087436 | Molding | HFTD Tier 3 | Distribution | 2004-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000735 | 400087852 | Ground | HFTD Tier 2 | Distribution | 2004-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000736 | 400087913 | High Sign | HFTD Tier 3 | Distribution | 2004-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000737 | 400087969 | High Sign | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000738 | 400088016 | High Sign | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000739 | 400088058 | Guy | HFTD Tier 3 | Distribution | 2004-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000740 | 400088294 | High Sign | HFTD Tier 2 | Distribution | 2004-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000741 | 400088312 | High Sign | HFTD Tier 3 | Distribution | 2004-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000742 | 400088395 | Molding | HFTD Tier 2 | Distribution | 2004-05-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000743 | 400088458 | High Sign | HFTD Tier 2 | Distribution | 2009-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000744 | 400088593 | Insulator | HFTD Tier 3 | Distribution | 2004-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000745 | 400088661 | High Sign | HFTD Tier 2 | Distribution | 2004-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000746 | 400088730 | Molding | HFTD Tier 2 | Distribution | 2005-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000747 | 400088915 | Riser/Conduit | HFTD Tier 2 | Distribution | 2006-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000748 | 400089097 | Insulator | HFTD Tier 3 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000749 | 400089173 | Molding | HFTD Tier 3 | Distribution | 2005-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000750 | 400089235 | High Sign | HFTD Tier 3 | Distribution | 2005-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000751 | 400089240 | Molding | HFTD Tier 3 | Distribution | 2005-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000752 | 400089324 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000753 | 400089437 | Molding | HFTD Tier 3 | Distribution | 2004-10-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000754 | 400089622 | Molding | HFTD Tier 2 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000755 | 400089687 | High Sign | HFTD Tier 3 | Distribution | 2010-01-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000756 | 400089750 | High Sign | HFTD Tier 3 | Distribution | 2009-11-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000757 | 400089849 | Molding | HFTD Tier 3 | Distribution | 2004-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000758 | 400089857 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000759 | 400089905 | High Sign | HFTD Tier 3 | Distribution | 2004-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000760 | 400089965 | Molding | HFTD Tier 3 | Distribution | 2005-08-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000761 | 400090010 | High Sign | HFTD Tier 3 | Distribution | 2005-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000762 | 400090032 | Molding | HFTD Tier 3 | Distribution | 2005-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000763 | 400090221 | High Sign | HFTD Tier 3 | Distribution | 2010-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000764 | 400090493 | Molding | HFTD Tier 2 | Distribution | 2005-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000765 | 400090622 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000766 | 400090759 | Riser/Conduit | HFTD Tier 3 | Distribution | 2010-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000767 | 400090940 | Molding | HFTD Tier 3 | Distribution | 2005-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000768 | 400091211 | High Sign | HFTD Tier 2 | Distribution | 2004-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000769 | 400091242 | High Sign | HFTD Tier 3 | Distribution | 2003-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000770 | 400091686 | Molding | HFTD Tier 3 | Distribution | 2004-12-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000771 | 400092784 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000772 | 400092842 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000773 | 400093109 | High Sign | HFTD Tier 3 | Distribution | 2005-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000774 | 400093118 | Molding | HFTD Tier 2 | Distribution | 2006-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000775 | 400093212 | High Sign | HFTD Tier 2 | Distribution | 2008-12-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000776 | 400093418 | Molding | HFTD Tier 3 | Distribution | 2004-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000777 | 400093548 | Molding | HFTD Tier 3 | Distribution | 2009-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000778 | 400093624 | High Sign | HFTD Tier 2 | Distribution | 2001-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000779 | 400093766 | High Sign | HFTD Tier 2 | Distribution | 2003-12-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000780 | 400093835 | High Sign | HFTD Tier 2 | Distribution | 2004-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000781 | 400093840 | Hardware/Framing | HFTD Tier 2 | Distribution | 2004-12-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000782 | 400093861 | High Sign | HFTD Tier 2 | Distribution | 2004-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000783 | 400094087 | Insulator | HFTD Tier 2 | Distribution | 2009-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000784 | 400094410 | High Sign | HFTD Tier 2 | Distribution | 2005-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000785 | 400094731 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000786 | 400094883 | High Sign | HFTD Tier 2 | Distribution | 2004-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000787 | 400095012 | High Sign | HFTD Tier 2 | Distribution | 2009-10-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000788 | 400095040 | Molding | HFTD Tier 3 | Distribution | 2009-08-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000789 | 400095578 | Molding | HFTD Tier 3 | Distribution | 2004-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000790 | 400095754 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000791 | 400095868 | High Sign | HFTD Tier 2 | Distribution | 2004-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000792 | 400095880 | High Sign | HFTD Tier 2 | Distribution | 2009-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000793 | 400095893 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000794 | 400096013 | Molding | HFTD Tier 3 | Distribution | 2001-11-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000795 | 400096165 | Molding | HFTD Tier 2 | Distribution | 2009-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000796 | 400096169 | High Sign | HFTD Tier 3 | Distribution | 2004-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000797 | 400096210 | Molding | HFTD Tier 2 | Distribution | 2004-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000798 | 400096283 | Molding | HFTD Tier 3 | Distribution | 2008-12-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000799 | 400096352 | Molding | HFTD Tier 3 | Distribution | 2004-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000800 | 400096379 | Molding | HFTD Tier 3 | Distribution | 2004-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000801 | 400096441 | Molding | HFTD Tier 3 | Distribution | 2004-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000802 | 400096674 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000803 | 400096696 | High Sign | HFTD Tier 2 | Distribution | 2004-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000804 | 400096713 | High Sign | HFTD Tier 3 | Distribution | 2009-05-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000805 | 400096732 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000806 | 400096746 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000807 | 400096805 | High Sign | HFTD Tier 2 | Distribution | 2004-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000808 | 400096894 | Guy | HFTD Tier 2 | Distribution | 2003-12-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000809 | 400097303 | Riser/Conduit | HFTD Tier 3 | Distribution | 2009-12-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000810 | 400097670 | High Sign | HFTD Tier 3 | Distribution | 2009-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000811 | 400097709 | Guy | HFTD Tier 3 | Distribution | 2005-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000812 | 400097816 | High Sign | HFTD Tier 2 | Distribution | 2003-12-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000813 | 400098009 | High Sign | HFTD Tier 2 | Distribution | 2001-12-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000814 | 400098053 | High Sign | HFTD Tier 2 | Distribution | 2008-12-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000815 | 400098203 | Molding | HFTD Tier 3 | Distribution | 2004-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000816 | 400098306 | Molding | HFTD Tier 3 | Distribution | 2008-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000817 | 400098559 | Molding | HFTD Tier 2 | Distribution | 2009-11-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000818 | 400098636 | High Sign | HFTD Tier 3 | Distribution | 2001-11-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000819 | 400098640 | Molding | HFTD Tier 3 | Distribution | 2008-07-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000820 | 400098694 | Molding | HFTD Tier 3 | Distribution | 2005-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000821 | 400098740 | Molding | HFTD Tier 2 | Distribution | 2004-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000822 | 400098741 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000823 | 400098859 | Molding | HFTD Tier 2 | Distribution | 2009-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000824 | 400099055 | Molding | HFTD Tier 2 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000825 | 400099421 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000826 | 400099475 | Molding | HFTD Tier 3 | Distribution | 2009-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000827 | 400099516 | High Sign | HFTD Tier 3 | Distribution | 2004-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000828 | 400099600 | High Sign | HFTD Tier 2 | Distribution | 2004-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000829 | 400099626 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000830 | 400099673 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000831 | 400099689 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000832 | 400099738 | High Sign | HFTD Tier 3 | Distribution | 2004-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000833 | 400099760 | High Sign | HFTD Tier 3 | Distribution | 2009-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000834 | 400099817 | Molding | HFTD Tier 2 | Distribution | 2009-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000835 | 400100168 | High Sign | HFTD Tier 2 | Distribution | 2009-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000836 | 400100180 | High Sign | HFTD Tier 3 | Distribution | 2004-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000837 | 400100201 | High Sign | HFTD Tier 2 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000838 | 400100358 | Riser/Conduit | HFTD Tier 3 | Distribution | 2010-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000839 | 400100925 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000840 | 400100970 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000841 | 400100996 | Guy | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000842 | 400100997 | Molding | HFTD Tier 3 | Distribution | 2004-02-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000843 | 400101059 | High Sign | HFTD Tier 2 | Distribution | 2005-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000844 | 400101234 | Molding | HFTD Tier 3 | Distribution | 2004-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000845 | 400101398 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000846 | 400101472 | Guy | HFTD Tier 2 | Distribution | 2009-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000847 | 400101543 | High Sign | HFTD Tier 2 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000848 | 400101639 | High Sign | HFTD Tier 2 | Distribution | 2004-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000849 | 400101750 | High Sign | HFTD Tier 2 | Distribution | 2009-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000850 | 400101779 | Molding | HFTD Tier 3 | Distribution | 2005-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000851 | 400102008 | Molding | HFTD Tier 3 | Distribution | 2004-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000852 | 400102308 | Molding | HFTD Tier 2 | Distribution | 2004-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000853 | 400102663 | High Sign | HFTD Tier 2 | Distribution | 2004-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000854 | 400102856 | Molding | HFTD Tier 2 | Distribution | 2008-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000855 | 400102890 | High Sign | HFTD Tier 3 | Distribution | 2004-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000856 | 400103256 | Guy | HFTD Tier 3 | Distribution | 2005-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000857 | 400103320 | High Sign | HFTD Tier 3 | Distribution | 2004-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000858 | 400103409 | Molding | HFTD Tier 2 | Distribution | 2006-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000859 | 400103438 | High Sign | HFTD Tier 2 | Distribution | 2005-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000860 | 400103450 | High Sign | HFTD Tier 2 | Distribution | 2005-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000861 | 400103808 | Molding | HFTD Tier 3 | Distribution | 2004-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000862 | 400103830 | Molding | HFTD Tier 3 | Distribution | 2008-07-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000863 | 400103832 | Molding | HFTD Tier 2 | Distribution | 2006-06-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000864 | 400103905 | Molding | HFTD Tier 3 | Distribution | 2004-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000865 | 400103999 | Molding | HFTD Tier 2 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000866 | 400104004 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000867 | 400104048 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000868 | 400104071 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000869 | 400104091 | High Sign | HFTD Tier 2 | Distribution | 2009-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000870 | 400104157 | Guy | HFTD Tier 2 | Distribution | 2009-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000871 | 400104395 | High Sign | HFTD Tier 3 | Distribution | 2009-09-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000872 | 400104401 | High Sign | HFTD Tier 3 | Distribution | 2001-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000873 | 400104526 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000874 | 400104549 | High Sign | HFTD Tier 2 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000875 | 400104568 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2009-09-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000876 | 400104602 | Molding | HFTD Tier 2 | Distribution | 2009-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000877 | 400105123 | Guy | HFTD Tier 2 | Distribution | 2005-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000878 | 400105203 | Molding | HFTD Tier 2 | Distribution | 2009-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000879 | 400105216 | High Sign | HFTD Tier 3 | Distribution | 2004-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000880 | 400105313 | Molding | HFTD Tier 2 | Distribution | 2006-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000881 | 400105314 | High Sign | HFTD Tier 3 | Distribution | 2009-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000882 | 400105320 | Molding | HFTD Tier 3 | Distribution | 2001-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000883 | 400105476 | High Sign | HFTD Tier 3 | Distribution | 2001-08-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000884 | 400105743 | High Sign | HFTD Tier 3 | Distribution | 2006-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000885 | 400105799 | Molding | HFTD Tier 3 | Distribution | 2010-02-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000886 | 400105959 | High Sign | HFTD Tier 2 | Distribution | 2004-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000887 | 400105970 | High Sign | HFTD Tier 2 | Distribution | 2004-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000888 | 400106015 | High Sign | HFTD Tier 2 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000889 | 400106023 | Molding | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000890 | 400106072 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-12-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000891 | 400106458 | Guy | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000892 | 400106509 | High Sign | HFTD Tier 3 | Distribution | 2010-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000893 | 400106545 | High Sign | HFTD Tier 3 | Distribution | 2004-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000894 | 400106549 | Molding | HFTD Tier 2 | Distribution | 2008-11-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000895 | 400106561 | High Sign | HFTD Tier 2 | Distribution | 2004-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000896 | 400106618 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000897 | 400106620 | Molding | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000898 | 400106640 | Molding | HFTD Tier 3 | Distribution | 2004-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000899 | 400106642 | High Sign | HFTD Tier 3 | Distribution | 2004-09-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000900 | 400106726 | High Sign | HFTD Tier 3 | Distribution | 2005-09-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000901 | 400106939 | High Sign | HFTD Tier 3 | Distribution | 2009-09-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000902 | 400106941 | High Sign | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000903 | 400107009 | High Sign | HFTD Tier 3 | Distribution | 2009-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000904 | 400107252 | Insulator | HFTD Tier 2 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000905 | 400107256 | Cable/Conductor | HFTD Tier 3 | Distribution | 2008-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000906 | 400107411 | Cable/Conductor | HFTD Tier 3 | Distribution | 2005-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000907 | 400107429 | Molding | HFTD Tier 3 | Distribution | 2004-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000908 | 400107491 | High Sign | HFTD Tier 3 | Distribution | 2009-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000909 | 400108242 | Guy | HFTD Tier 3 | Distribution | 2004-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000910 | 400108321 | Riser/Conduit | HFTD Tier 3 | Distribution | 2005-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000911 | 400108475 | High Sign | HFTD Tier 2 | Distribution | 2004-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000912 | 400108664 | Ground | HFTD Tier 3 | Distribution | 2004-09-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000913 | 400109125 | Molding | HFTD Tier 3 | Distribution | 2005-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000914 | 400109239 | Guy | HFTD Tier 2 | Distribution | 2009-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000915 | 400109384 | Molding | HFTD Tier 2 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000916 | 400109389 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000917 | 400109682 | Molding | HFTD Tier 3 | Distribution | 2008-11-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000918 | 400109710 | High Sign | HFTD Tier 2 | Distribution | 2009-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000919 | 400109748 | Molding | HFTD Tier 3 | Distribution | 2004-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000920 | 400109774 | Molding | HFTD Tier 3 | Distribution | 2005-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000921 | 400109861 | Molding | HFTD Tier 2 | Distribution | 2004-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000922 | 400109986 | Molding | HFTD Tier 3 | Distribution | 2009-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000923 | 400110017 | High Sign | HFTD Tier 3 | Distribution | 2009-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000924 | 400110207 | High Sign | HFTD Tier 2 | Distribution | 2004-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000925 | 400110402 | Hardware/Framing | HFTD Tier 2 | Distribution | 2005-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000926 | 400110431 | Molding | HFTD Tier 2 | Distribution | 2005-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000927 | 400110457 | High Sign | HFTD Tier 3 | Distribution | 2009-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000928 | 400110483 | Molding | HFTD Tier 2 | Distribution | 2009-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000929 | 400110503 | Hardware/Framing | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000930 | 400110593 | High Sign | HFTD Tier 2 | Distribution | 2001-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000931 | 400110638 | High Sign | HFTD Tier 3 | Distribution | 2005-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000932 | 400110718 | Guy | HFTD Tier 2 | Distribution | 2006-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000933 | 400110790 | Molding | HFTD Tier 3 | Distribution | 2004-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000934 | 400110808 | High Sign | HFTD Tier 2 | Distribution | 2003-11-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000935 | 400110893 | High Sign | HFTD Tier 3 | Distribution | 2001-08-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000936 | 400111330 | High Sign | HFTD Tier 2 | Distribution | 2008-12-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000937 | 400111407 | High Sign | HFTD Tier 3 | Distribution | 2004-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000938 | 400111447 | High Sign | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000939 | 400111486 | Guy | HFTD Tier 2 | Distribution | 2009-12-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000940 | 400111567 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000941 | 400111615 | Molding | HFTD Tier 2 | Distribution | 2005-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000942 | 400111630 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000943 | 400111652 | Guy | HFTD Tier 2 | Distribution | 2004-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000944 | 400111751 | Hardware/Framing | HFTD Tier 3 | Distribution | 2004-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000945 | 400111952 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000946 | 400112009 | Molding | HFTD Tier 2 | Distribution | 2006-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000947 | 400112085 | Molding | HFTD Tier 2 | Distribution | 2005-02-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000948 | 400112101 | Guy | HFTD Tier 3 | Distribution | 2004-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000949 | 400112153 | High Sign | HFTD Tier 3 | Distribution | 2005-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000950 | 400112176 | Molding | HFTD Tier 2 | Distribution | 2009-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000951 | 400112487 | Molding | HFTD Tier 2 | Distribution | 2006-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000952 | 400112886 | High Sign | HFTD Tier 3 | Distribution | 2005-08-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000953 | 400112989 | Molding | HFTD Tier 3 | Distribution | 2005-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000954 | 400113069 | High Sign | HFTD Tier 3 | Distribution | 2010-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000955 | 400113309 | Molding | HFTD Tier 2 | Distribution | 2005-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000956 | 400113511 | Molding | HFTD Tier 2 | Distribution | 2005-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000957 | 400113544 | High Sign | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000958 | 400113839 | Molding | HFTD Tier 3 | Distribution | 2004-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000959 | 400113871 | High Sign | HFTD Tier 2 | Distribution | 2005-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000960 | 400113881 | High Sign | HFTD Tier 2 | Distribution | 2004-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000961 | 400113934 | Riser/Conduit | HFTD Tier 3 | Distribution | 2008-07-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000962 | 400114045 | Riser/Conduit | HFTD Tier 3 | Distribution | 2004-08-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000963 | 400114197 | Molding | HFTD Tier 3 | Distribution | 2004-09-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000964 | 400114225 | High Sign | HFTD Tier 2 | Distribution | 2009-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000965 | 400114234 | High Sign | HFTD Tier 3 | Distribution | 2003-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000966 | 400114267 | Molding | HFTD Tier 3 | Distribution | 2004-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000967 | 400114341 | High Sign | HFTD Tier 3 | Distribution | 2003-11-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000968 | 400114511 | Guy | HFTD Tier 2 | Distribution | 2004-08-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000969 | 400114549 | Molding | HFTD Tier 2 | Distribution | 2004-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000970 | 400114553 | High Sign | HFTD Tier 3 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000971 | 400114567 | Molding | HFTD Tier 2 | Distribution | 2004-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000972 | 400114879 | Molding | HFTD Tier 3 | Distribution | 2005-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000973 | 400114962 | Molding | HFTD Tier 3 | Distribution | 2004-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000974 | 400115088 | High Sign | HFTD Tier 3 | Distribution | 2009-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000975 | 400115149 | Molding | HFTD Tier 2 | Distribution | 2001-12-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000976 | 400115227 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000977 | 400115229 | Molding | HFTD Tier 2 | Distribution | 2009-12-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000978 | 400115238 | Molding | HFTD Tier 3 | Distribution | 2004-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000979 | 400115249 | High Sign | HFTD Tier 2 | Distribution | 2004-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000980 | 400115333 | Molding | HFTD Tier 3 | Distribution | 2005-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000981 | 400115349 | High Sign | HFTD Tier 3 | Distribution | 2005-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000982 | 400115440 | High Sign | HFTD Tier 2 | Distribution | 2005-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000983 | 400115851 | Hardware/Framing | HFTD Tier 3 | Distribution | 2005-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000984 | 400116033 | Hardware/Framing | HFTD Tier 2 | Distribution | 2004-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000985 | 400116114 | Molding | HFTD Tier 2 | Distribution | 2004-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000986 | 400116321 | High Sign | HFTD Tier 3 | Distribution | 2004-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000987 | 400116474 | High Sign | HFTD Tier 2 | Distribution | 2004-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000988 | 400116564 | High Sign | HFTD Tier 3 | Distribution | 2004-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000989 | 400116791 | Insulator | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000990 | 400116858 | Guy | HFTD Tier 3 | Distribution | 2005-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000991 | 400116919 | Molding | HFTD Tier 2 | Distribution | 2004-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000992 | 400116975 | High Sign | HFTD Tier 3 | Distribution | 2004-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000993 | 400117003 | Molding | HFTD Tier 3 | Distribution | 2004-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000994 | 400117157 | Insulator | HFTD Tier 2 | Distribution | 2005-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000995 | 400117232 | Guy | HFTD Tier 3 | Distribution | 2009-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000996 | 400117308 | High Sign | HFTD Tier 3 | Distribution | 2009-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000997 | 400117311 | High Sign | HFTD Tier 2 | Distribution | 2005-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000998 | 400117335 | High Sign | HFTD Tier 2 | Distribution | 2004-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130000999 | 400117437 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2003-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001000 | 400117442 | Molding | HFTD Tier 3 | Distribution | 2000-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001001 | 400117696 | High Sign | HFTD Tier 2 | Distribution | 2009-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001002 | 400117870 | High Sign | HFTD Tier 3 | Distribution | 2009-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001003 | 400117925 | Molding | HFTD Tier 2 | Distribution | 2005-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001004 | 400118078 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-12-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001005 | 400118253 | Insulator | HFTD Tier 2 | Distribution | 2004-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001006 | 400118375 | High Sign | HFTD Tier 2 | Distribution | 2004-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001007 | 400118536 | Guy | HFTD Tier 3 | Distribution | 2005-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001008 | 400118717 | High Sign | HFTD Tier 3 | Distribution | 2004-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001009 | 400118963 | High Sign | HFTD Tier 3 | Distribution | 2010-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001010 | 400119061 | High Sign | HFTD Tier 2 | Distribution | 2004-05-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001011 | 400119159 | High Sign | HFTD Tier 2 | Distribution | 2004-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001012 | 400119246 | High Sign | HFTD Tier 2 | Distribution | 2001-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001013 | 400119473 | Molding | HFTD Tier 2 | Distribution | 2009-12-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001014 | 400119509 | Molding | HFTD Tier 3 | Distribution | 2005-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001015 | 400119617 | Molding | HFTD Tier 3 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001016 | 400119749 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001017 | 400119786 | High Sign | HFTD Tier 2 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001018 | 400119908 | Molding | HFTD Tier 2 | Distribution | 2005-02-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001019 | 400120032 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001020 | 400120049 | Molding | HFTD Tier 2 | Distribution | 2004-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001021 | 400120071 | Guy | HFTD Tier 3 | Distribution | 2004-07-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001022 | 400120124 | Molding | HFTD Tier 3 | Distribution | 2005-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001023 | 400120395 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2009-08-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001024 | 400120501 | Guy | HFTD Tier 2 | Distribution | 2005-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001025 | 400120682 | Molding | HFTD Tier 2 | Distribution | 2004-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001026 | 400120909 | Molding | HFTD Tier 2 | Distribution | 2009-01-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001027 | 400120956 | High Sign | HFTD Tier 2 | Distribution | 2010-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001028 | 400120996 | High Sign | HFTD Tier 3 | Distribution | 2004-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001029 | 400121042 | Molding | HFTD Tier 2 | Distribution | 2005-01-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001030 | 400121130 | Molding | HFTD Tier 3 | Distribution | 2004-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001031 | 400121335 | Molding | HFTD Tier 2 | Distribution | 2009-12-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001032 | 400121462 | High Sign | HFTD Tier 2 | Distribution | 2004-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001033 | 400121507 | Molding | HFTD Tier 3 | Distribution | 2005-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001034 | 400121591 | Molding | HFTD Tier 3 | Distribution | 2004-01-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001035 | 400121854 | High Sign | HFTD Tier 3 | Distribution | 2009-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001036 | 400121864 | Molding | HFTD Tier 2 | Distribution | 2004-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001037 | 400121921 | Molding | HFTD Tier 3 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001038 | 400121960 | Molding | HFTD Tier 3 | Distribution | 2009-10-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001039 | 400122076 | Molding | HFTD Tier 3 | Distribution | 2004-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001040 | 400122082 | Molding | HFTD Tier 2 | Distribution | 2009-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001041 | 400122130 | High Sign | HFTD Tier 2 | Distribution | 2005-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001042 | 400122315 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001043 | 400122427 | Molding | HFTD Tier 2 | Distribution | 2005-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001044 | 400122438 | Hardware/Framing | HFTD Tier 3 | Distribution | 2004-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001045 | 400122464 | High Sign | HFTD Tier 2 | Distribution | 2004-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001046 | 400122488 | Riser/Conduit | HFTD Tier 3 | Distribution | 2005-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001047 | 400122491 | High Sign | HFTD Tier 2 | Distribution | 2004-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001048 | 400122540 | Riser/Conduit | HFTD Tier 3 | Distribution | 2004-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001049 | 400122659 | Riser/Conduit | HFTD Tier 3 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001050 | 400122715 | Guy | HFTD Tier 3 | Distribution | 2008-11-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001051 | 400122804 | Molding | HFTD Tier 2 | Distribution | 2004-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001052 | 400123021 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001053 | 400123156 | High Sign | HFTD Tier 2 | Distribution | 2003-11-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001054 | 400123299 | Molding | HFTD Tier 2 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001055 | 400123380 | Molding | HFTD Tier 3 | Distribution | 2005-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001056 | 400123385 | High Sign | HFTD Tier 2 | Distribution | 2009-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001057 | 400123537 | Molding | HFTD Tier 3 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001058 | 400123592 | High Sign | HFTD Tier 2 | Distribution | 2004-05-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001059 | 400123642 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001060 | 400123646 | Molding | HFTD Tier 3 | Distribution | 2004-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001061 | 400123672 | High Sign | HFTD Tier 2 | Distribution | 2004-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001062 | 400123830 | High Sign | HFTD Tier 2 | Distribution | 2004-12-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001063 | 400123906 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001064 | 400123935 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001065 | 400123983 | High Sign | HFTD Tier 2 | Distribution | 2010-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001066 | 400124057 | High Sign | HFTD Tier 2 | Distribution | 2003-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001067 | 400124162 | Molding | HFTD Tier 2 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001068 | 400124212 | High Sign | HFTD Tier 3 | Distribution | 2001-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001069 | 400124235 | Molding | HFTD Tier 2 | Distribution | 2004-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001070 | 400124377 | High Sign | HFTD Tier 3 | Distribution | 2009-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001071 | 400124459 | Insulator | HFTD Tier 3 | Distribution | 2005-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001072 | 400124476 | Molding | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001073 | 400124503 | Molding | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001074 | 400124597 | Guy | HFTD Tier 2 | Distribution | 2009-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001075 | 400124677 | High Sign | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001076 | 400124692 | High Sign | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001077 | 400124754 | Molding | HFTD Tier 2 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001078 | 400124788 | Insulator | HFTD Tier 3 | Distribution | 2009-12-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001079 | 400124823 | Molding | HFTD Tier 3 | Distribution | 2005-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001080 | 400124871 | High Sign | HFTD Tier 2 | Distribution | 2003-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001081 | 400125002 | High Sign | HFTD Tier 3 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001082 | 400125054 | High Sign | HFTD Tier 3 | Distribution | 2004-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001083 | 400125087 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001084 | 400125127 | Hardware/Framing | HFTD Tier 2 | Distribution | 2004-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001085 | 400125139 | Cable/Conductor | HFTD Tier 3 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001086 | 400125233 | Molding | HFTD Tier 3 | Distribution | 2004-01-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001087 | 400125264 | High Sign | HFTD Tier 3 | Distribution | 2006-08-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001088 | 400125357 | Hardware/Framing | HFTD Tier 3 | Distribution | 2004-08-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001089 | 400125363 | High Sign | HFTD Tier 2 | Distribution | 2004-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001090 | 400125437 | Molding | HFTD Tier 2 | Distribution | 2005-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001091 | 400125470 | Molding | HFTD Tier 3 | Distribution | 2005-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001092 | 400125507 | Molding | HFTD Tier 3 | Distribution | 2001-08-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001093 | 400125599 | High Sign | HFTD Tier 2 | Distribution | 2004-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001094 | 400125668 | Molding | HFTD Tier 3 | Distribution | 2003-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001095 | 400125821 | Guy | HFTD Tier 3 | Distribution | 2004-04-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001096 | 400125827 | Molding | HFTD Tier 3 | Distribution | 2010-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001097 | 400125854 | Molding | HFTD Tier 3 | Distribution | 2008-11-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001098 | 400125881 | High Sign | HFTD Tier 3 | Distribution | 2004-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001099 | 400126120 | High Sign | HFTD Tier 3 | Distribution | 2004-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001100 | 400126178 | High Sign | HFTD Tier 2 | Distribution | 2005-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001101 | 400126217 | Guy | HFTD Tier 3 | Distribution | 2004-01-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001102 | 400126403 | Molding | HFTD Tier 3 | Distribution | 2004-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001103 | 400126471 | High Sign | HFTD Tier 3 | Distribution | 2004-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001104 | 400126475 | High Sign | HFTD Tier 2 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001105 | 400126504 | High Sign | HFTD Tier 2 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001106 | 400126568 | Crossarm | HFTD Tier 2 | Distribution | 2004-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001107 | 400126686 | High Sign | HFTD Tier 3 | Distribution | 2005-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001108 | 400126781 | Molding | HFTD Tier 3 | Distribution | 2005-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001109 | 400127223 | High Sign | HFTD Tier 3 | Distribution | 2004-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001110 | 400127489 | Molding | HFTD Tier 3 | Distribution | 2006-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001111 | 400127536 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001112 | 400127538 | High Sign | HFTD Tier 2 | Distribution | 2009-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001113 | 400127572 | Hardware/Framing | HFTD Tier 2 | Distribution | 2009-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001114 | 400127608 | High Sign | HFTD Tier 3 | Distribution | 2009-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001115 | 400127702 | Molding | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001116 | 400127744 | Molding | HFTD Tier 2 | Distribution | 2003-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001117 | 400127896 | High Sign | HFTD Tier 2 | Distribution | 2009-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001118 | 400127961 | Molding | HFTD Tier 3 | Distribution | 2008-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001119 | 400127967 | High Sign | HFTD Tier 3 | Distribution | 2004-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001120 | 400127998 | High Sign | HFTD Tier 3 | Distribution | 2004-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001121 | 400128031 | Insulator | HFTD Tier 2 | Distribution | 2004-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001122 | 400128074 | Molding | HFTD Tier 2 | Distribution | 2004-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001123 | 400128089 | Insulator | HFTD Tier 2 | Distribution | 2004-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001124 | 400128231 | High Sign | HFTD Tier 2 | Distribution | 2009-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001125 | 400128489 | Riser/Conduit | HFTD Tier 2 | Distribution | 2003-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001126 | 400128957 | Guy | HFTD Tier 2 | Distribution | 2006-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001127 | 400129471 | Cable/Conductor | HFTD Tier 3 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001128 | 400129675 | High Sign | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001129 | 400129717 | Molding | HFTD Tier 2 | Distribution | 2005-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001130 | 400129818 | Molding | HFTD Tier 3 | Distribution | 2004-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001131 | 400129853 | Molding | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001132 | 400129912 | High Sign | HFTD Tier 3 | Distribution | 2004-10-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001133 | 400130018 | Molding | HFTD Tier 3 | Distribution | 2009-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001134 | 400130055 | High Sign | HFTD Tier 3 | Distribution | 2001-12-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001135 | 400130082 | Hardware/Framing | HFTD Tier 2 | Distribution | 2009-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001136 | 400130313 | High Sign | HFTD Tier 2 | Distribution | 2009-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001137 | 400130402 | High Sign | HFTD Tier 2 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001138 | 400130486 | High Sign | HFTD Tier 3 | Distribution | 2004-01-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001139 | 400130591 | Insulator | HFTD Tier 2 | Distribution | 2004-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001140 | 400130595 | Molding | HFTD Tier 3 | Distribution | 2005-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001141 | 400130634 | Guy | HFTD Tier 3 | Distribution | 2004-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001142 | 400130658 | Molding | HFTD Tier 2 | Distribution | 2004-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001143 | 400130749 | High Sign | HFTD Tier 3 | Distribution | 2001-12-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001144 | 400130891 | High Sign | HFTD Tier 2 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001145 | 400131215 | Molding | HFTD Tier 2 | Distribution | 2004-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001146 | 400131216 | Molding | HFTD Tier 3 | Distribution | 2004-06-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001147 | 400131260 | Molding | HFTD Tier 3 | Distribution | 2009-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001148 | 400131278 | High Sign | HFTD Tier 2 | Distribution | 2005-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001149 | 400131479 | Molding | HFTD Tier 2 | Distribution | 2004-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001150 | 400131519 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-01-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001151 | 400131575 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001152 | 400131606 | High Sign | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001153 | 400131662 | Molding | HFTD Tier 3 | Distribution | 2010-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001154 | 400131689 | High Sign | HFTD Tier 3 | Distribution | 2004-04-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001155 | 400131826 | Molding | HFTD Tier 2 | Distribution | 2004-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001156 | 400132009 | High Sign | HFTD Tier 2 | Distribution | 2004-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001157 | 400132077 | High Sign | HFTD Tier 3 | Distribution | 2005-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001158 | 400132182 | Molding | HFTD Tier 3 | Distribution | 2000-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001159 | 400132276 | High Sign | HFTD Tier 2 | Distribution | 2004-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001160 | 400132278 | Guy | HFTD Tier 3 | Distribution | 2004-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001161 | 400132351 | High Sign | HFTD Tier 2 | Distribution | 2003-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001162 | 400132511 | Molding | HFTD Tier 3 | Distribution | 2010-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001163 | 400132517 | High Sign | HFTD Tier 3 | Distribution | 2004-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001164 | 400132707 | High Sign | HFTD Tier 3 | Distribution | 2009-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001165 | 400132767 | High Sign | HFTD Tier 3 | Distribution | 2005-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001166 | 400132770 | Molding | HFTD Tier 3 | Distribution | 2010-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001167 | 400132960 | Anchor | HFTD Tier 3 | Distribution | 2009-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001168 | 400132995 | Molding | HFTD Tier 2 | Distribution | 2009-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001169 | 400133266 | Molding | HFTD Tier 2 | Distribution | 1999-09-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001170 | 400133286 | Molding | HFTD Tier 3 | Distribution | 2004-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001171 | 400133330 | Molding | HFTD Tier 3 | Distribution | 2003-12-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001172 | 400133369 | High Sign | HFTD Tier 3 | Distribution | 2005-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001173 | 400133469 | Molding | HFTD Tier 3 | Distribution | 2005-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001174 | 400133472 | Molding | HFTD Tier 3 | Distribution | 2004-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001175 | 400133618 | High Sign | HFTD Tier 3 | Distribution | 2009-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001176 | 400133774 | Hardware/Framing | HFTD Tier 3 | Distribution | 2005-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001177 | 400133991 | Hardware/Framing | HFTD Tier 3 | Distribution | 2001-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001178 | 400134032 | Molding | HFTD Tier 2 | Distribution | 2004-01-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001179 | 400134231 | High Sign | HFTD Tier 3 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001180 | 400134341 | High Sign | HFTD Tier 3 | Distribution | 2004-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001181 | 400134410 | Molding | HFTD Tier 2 | Distribution | 2005-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001182 | 400134437 | Molding | HFTD Tier 2 | Distribution | 2005-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001183 | 400134442 | High Sign | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001184 | 400134641 | Molding | HFTD Tier 3 | Distribution | 2005-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001185 | 400134911 | Molding | HFTD Tier 2 | Distribution | 2005-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001186 | 400134984 | Molding | HFTD Tier 2 | Distribution | 2004-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001187 | 400135034 | High Sign | HFTD Tier 3 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001188 | 400135046 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001189 | 400135249 | Molding | HFTD Tier 3 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001190 | 400135312 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001191 | 400135444 | High Sign | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001192 | 400135480 | Molding | HFTD Tier 3 | Distribution | 2004-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001193 | 400135502 | High Sign | HFTD Tier 2 | Distribution | 2004-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001194 | 400135575 | Molding | HFTD Tier 3 | Distribution | 2005-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001195 | 400135618 | High Sign | HFTD Tier 3 | Distribution | 2004-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001196 | 400135848 | Molding | HFTD Tier 2 | Distribution | 2005-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001197 | 400136111 | Molding | HFTD Tier 2 | Distribution | 2004-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001198 | 400136158 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001199 | 400136197 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001200 | 400136269 | High Sign | HFTD Tier 3 | Distribution | 2004-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001201 | 400136465 | High Sign | HFTD Tier 2 | Distribution | 2006-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001202 | 400136501 | Guy | HFTD Tier 3 | Distribution | 2004-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001203 | 400136520 | Molding | HFTD Tier 2 | Distribution | 2005-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001204 | 400136887 | Molding | HFTD Tier 3 | Distribution | 2004-04-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001205 | 400136890 | Molding | HFTD Tier 3 | Distribution | 2004-01-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001206 | 400137020 | Riser/Conduit | HFTD Tier 2 | Distribution | 2004-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001207 | 400137241 | Molding | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001208 | 400137295 | High Sign | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001209 | 400137603 | High Sign | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001210 | 400138089 | High Sign | HFTD Tier 2 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001211 | 400138115 | High Sign | HFTD Tier 2 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001212 | 400138193 | High Sign | HFTD Tier 3 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001213 | 400138194 | High Sign | HFTD Tier 2 | Distribution | 2009-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001214 | 400138203 | High Sign | HFTD Tier 3 | Distribution | 2004-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001215 | 400138410 | Molding | HFTD Tier 2 | Distribution | 2009-12-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001216 | 400138716 | High Sign | HFTD Tier 2 | Distribution | 2001-12-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001217 | 400139040 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001218 | 400139120 | Molding | HFTD Tier 2 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001219 | 400139297 | Molding | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001220 | 400139325 | Molding | HFTD Tier 3 | Distribution | 2005-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001221 | 400139369 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001222 | 400139471 | High Sign | HFTD Tier 2 | Distribution | 2009-09-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001223 | 400139494 | Hardware/Framing | HFTD Tier 2 | Distribution | 2009-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001224 | 400139527 | Molding | HFTD Tier 3 | Distribution | 2005-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001225 | 400139572 | High Sign | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001226 | 400139579 | High Sign | HFTD Tier 3 | Distribution | 2004-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001227 | 400139602 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001228 | 400139631 | Molding | HFTD Tier 2 | Distribution | 2005-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001229 | 400139675 | High Sign | HFTD Tier 2 | Distribution | 2001-08-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001230 | 400139682 | Molding | HFTD Tier 3 | Distribution | 2005-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001231 | 400139719 | High Sign | HFTD Tier 3 | Distribution | 2003-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001232 | 400139812 | Hardware/Framing | HFTD Tier 2 | Distribution | 2004-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001233 | 400139845 | Molding | HFTD Tier 3 | Distribution | 2010-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001234 | 400139939 | Molding | HFTD Tier 3 | Distribution | 2004-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001235 | 400140135 | Molding | HFTD Tier 3 | Distribution | 2004-07-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001236 | 400140157 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001237 | 400140161 | Hardware/Framing | HFTD Tier 2 | Distribution | 2004-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001238 | 400140211 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2009-10-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001239 | 400140217 | Riser/Conduit | HFTD Tier 3 | Distribution | 2009-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001240 | 400140495 | High Sign | HFTD Tier 2 | Distribution | 2005-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001241 | 400140528 | Molding | HFTD Tier 3 | Distribution | 2005-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001242 | 400140557 | High Sign | HFTD Tier 2 | Distribution | 2004-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001243 | 400140692 | High Sign | HFTD Tier 2 | Distribution | 2004-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001244 | 400140843 | Molding | HFTD Tier 2 | Distribution | 2009-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001245 | 400140846 | High Sign | HFTD Tier 3 | Distribution | 2009-10-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001246 | 400140967 | Molding | HFTD Tier 3 | Distribution | 2009-11-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001247 | 400140984 | Molding | HFTD Tier 2 | Distribution | 2009-12-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001248 | 400140994 | Molding | HFTD Tier 2 | Distribution | 2004-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001249 | 400141098 | High Sign | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001250 | 400141377 | High Sign | HFTD Tier 3 | Distribution | 2009-10-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001251 | 400141461 | High Sign | HFTD Tier 2 | Distribution | 2005-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001252 | 400141571 | Molding | HFTD Tier 3 | Distribution | 2004-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001253 | 400141601 | High Sign | HFTD Tier 3 | Distribution | 2004-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001254 | 400141610 | Molding | HFTD Tier 3 | Distribution | 2009-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001255 | 400141674 | Molding | HFTD Tier 3 | Distribution | 2004-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001256 | 400141706 | Guy | HFTD Tier 3 | Distribution | 2005-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001257 | 400141714 | Hardware/Framing | HFTD Tier 3 | Distribution | 2004-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001258 | 400141810 | Molding | HFTD Tier 3 | Distribution | 2005-11-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001259 | 400141828 | Molding | HFTD Tier 3 | Distribution | 2005-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001260 | 400141908 | Molding | HFTD Tier 3 | Distribution | 2005-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001261 | 400141913 | High Sign | HFTD Tier 2 | Distribution | 2004-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001262 | 400141949 | High Sign | HFTD Tier 2 | Distribution | 2004-08-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001263 | 400142008 | Guy | HFTD Tier 2 | Distribution | 2005-11-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001264 | 400142172 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-11-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001265 | 400142323 | High Sign | HFTD Tier 2 | Distribution | 2004-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001266 | 400142342 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001267 | 400142497 | Molding | HFTD Tier 3 | Distribution | 2005-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001268 | 400142553 | High Sign | HFTD Tier 2 | Distribution | 2009-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001269 | 400142643 | Molding | HFTD Tier 3 | Distribution | 2004-08-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001270 | 400143223 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001271 | 400143252 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001272 | 400143318 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001273 | 400143342 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001274 | 400143397 | Guy | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001275 | 400143555 | Guy | HFTD Tier 3 | Distribution | 2004-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001276 | 400143560 | Molding | HFTD Tier 3 | Distribution | 2004-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001277 | 400143566 | Molding | HFTD Tier 3 | Distribution | 2005-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001278 | 400143625 | High Sign | HFTD Tier 2 | Distribution | 2010-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001279 | 400143683 | High Sign | HFTD Tier 2 | Distribution | 2003-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001280 | 400143697 | High Sign | HFTD Tier 3 | Distribution | 2009-11-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001281 | 400143899 | Molding | HFTD Tier 2 | Distribution | 2003-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001282 | 400144080 | High Sign | HFTD Tier 2 | Distribution | 2005-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001283 | 400144193 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-06-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001284 | 400144241 | High Sign | HFTD Tier 3 | Distribution | 2004-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001285 | 400144253 | Hardware/Framing | HFTD Tier 3 | Distribution | 2005-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001286 | 400144429 | High Sign | HFTD Tier 3 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001287 | 400144545 | Hardware/Framing | HFTD Tier 3 | Distribution | 2005-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001288 | 400144549 | Molding | HFTD Tier 2 | Distribution | 2004-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001289 | 400144662 | Guy | HFTD Tier 2 | Distribution | 2004-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001290 | 400144754 | Molding | HFTD Tier 3 | Distribution | 2004-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001291 | 400144767 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001292 | 400144817 | Molding | HFTD Tier 3 | Distribution | 2005-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001293 | 400144875 | Molding | HFTD Tier 3 | Distribution | 2009-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001294 | 400145233 | Molding | HFTD Tier 3 | Distribution | 2009-09-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001295 | 400145408 | High Sign | HFTD Tier 2 | Distribution | 2005-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001296 | 400145421 | High Sign | HFTD Tier 3 | Distribution | 2004-11-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001297 | 400145552 | Molding | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001298 | 400145612 | High Sign | HFTD Tier 3 | Distribution | 2004-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001299 | 400145631 | Molding | HFTD Tier 3 | Distribution | 2004-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001300 | 400145649 | Riser/Conduit | HFTD Tier 3 | Distribution | 2005-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001301 | 400145696 | Molding | HFTD Tier 3 | Distribution | 2005-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001302 | 400145699 | Molding | HFTD Tier 3 | Distribution | 2004-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001303 | 400145700 | Molding | HFTD Tier 2 | Distribution | 2005-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001304 | 400145725 | High Sign | HFTD Tier 3 | Distribution | 2004-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001305 | 400145855 | High Sign | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001306 | 400145961 | Molding | HFTD Tier 3 | Distribution | 2008-11-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001307 | 400146058 | Molding | HFTD Tier 3 | Distribution | 2004-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001308 | 400146102 | Molding | HFTD Tier 2 | Distribution | 2005-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001309 | 400146209 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001310 | 400146372 | Molding | HFTD Tier 2 | Distribution | 2004-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001311 | 400146392 | Cable/Conductor | HFTD Tier 3 | Distribution | 2008-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001312 | 400146464 | Molding | HFTD Tier 3 | Distribution | 2004-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001313 | 400146486 | Guy | HFTD Tier 3 | Distribution | 2004-08-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001314 | 400146580 | High Sign | HFTD Tier 3 | Distribution | 2004-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001315 | 400146595 | Molding | HFTD Tier 3 | Distribution | 2004-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001316 | 400146775 | High Sign | HFTD Tier 2 | Distribution | 2009-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001317 | 400146800 | High Sign | HFTD Tier 3 | Distribution | 2009-10-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001318 | 400146803 | Molding | HFTD Tier 2 | Distribution | 2006-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001319 | 400146828 | High Sign | HFTD Tier 3 | Distribution | 2004-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001320 | 400146929 | High Sign | HFTD Tier 3 | Distribution | 2004-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001321 | 400147042 | High Sign | HFTD Tier 2 | Distribution | 2006-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001322 | 400147086 | Molding | HFTD Tier 2 | Distribution | 2010-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001323 | 400147199 | Molding | HFTD Tier 3 | Distribution | 2004-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001324 | 400147334 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001325 | 400147349 | High Sign | HFTD Tier 2 | Distribution | 2003-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001326 | 400147423 | High Sign | HFTD Tier 3 | Distribution | 2001-08-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001327 | 400147428 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001328 | 400147435 | High Sign | HFTD Tier 2 | Distribution | 2004-08-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001329 | 400147465 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001330 | 400147490 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001331 | 400147536 | Molding | HFTD Tier 2 | Distribution | 2004-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001332 | 400147552 | High Sign | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001333 | 400147577 | Molding | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001334 | 400147982 | Molding | HFTD Tier 3 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001335 | 400148040 | High Sign | HFTD Tier 3 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001336 | 400148137 | Hardware/Framing | HFTD Tier 2 | Distribution | 2002-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001337 | 400148252 | Guy | HFTD Tier 3 | Distribution | 2004-08-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001338 | 400148369 | Molding | HFTD Tier 2 | Distribution | 2004-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001339 | 400148559 | High Sign | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001340 | 400148789 | High Sign | HFTD Tier 2 | Distribution | 2009-06-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001341 | 400148790 | Molding | HFTD Tier 2 | Distribution | 2009-09-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001342 | 400148981 | High Sign | HFTD Tier 3 | Distribution | 2006-08-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001343 | 400149113 | Guy | HFTD Tier 3 | Distribution | 2005-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001344 | 400149459 | Hardware/Framing | HFTD Tier 3 | Distribution | 2004-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001345 | 400149503 | Molding | HFTD Tier 3 | Distribution | 2004-12-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001346 | 400149678 | High Sign | HFTD Tier 2 | Distribution | 2006-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001347 | 400149815 | High Sign | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001348 | 400149816 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001349 | 400149823 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-11-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001350 | 400149941 | Molding | HFTD Tier 3 | Distribution | 2010-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001351 | 400149962 | Molding | HFTD Tier 3 | Distribution | 2004-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001352 | 400150002 | High Sign | HFTD Tier 2 | Distribution | 2006-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001353 | 400150256 | Molding | HFTD Tier 3 | Distribution | 2009-06-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001354 | 400150391 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2004-07-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001355 | 400150402 | High Sign | HFTD Tier 2 | Distribution | 2003-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001356 | 400150426 | High Sign | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001357 | 400150612 | High Sign | HFTD Tier 3 | Distribution | 2001-12-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001358 | 400150803 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-10-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001359 | 400150871 | High Sign | HFTD Tier 3 | Distribution | 2003-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001360 | 400150958 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-09-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001361 | 400151236 | Molding | HFTD Tier 3 | Distribution | 2009-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001362 | 400151239 | Guy | HFTD Tier 3 | Distribution | 2010-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001363 | 400151264 | Molding | HFTD Tier 2 | Distribution | 2004-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001364 | 400151267 | Molding | HFTD Tier 2 | Distribution | 2004-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001365 | 400151268 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001366 | 400151336 | Molding | HFTD Tier 2 | Distribution | 2006-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001367 | 400151351 | Molding | HFTD Tier 2 | Distribution | 2004-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001368 | 400151408 | Molding | HFTD Tier 3 | Distribution | 2004-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001369 | 400151421 | High Sign | HFTD Tier 3 | Distribution | 2001-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001370 | 400151448 | High Sign | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001371 | 400151771 | High Sign | HFTD Tier 3 | Distribution | 2005-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001372 | 400151882 | High Sign | HFTD Tier 3 | Distribution | 2001-12-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001373 | 400151962 | Molding | HFTD Tier 2 | Distribution | 2008-10-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001374 | 400151973 | Molding | HFTD Tier 3 | Distribution | 2004-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001375 | 400152060 | High Sign | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001376 | 400152173 | High Sign | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001377 | 400152178 | High Sign | HFTD Tier 2 | Distribution | 2004-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001378 | 400152304 | Guy | HFTD Tier 2 | Distribution | 2004-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001379 | 400152361 | Molding | HFTD Tier 2 | Distribution | 2004-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001380 | 400152401 | High Sign | HFTD Tier 3 | Distribution | 2001-12-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001381 | 400152437 | High Sign | HFTD Tier 3 | Distribution | 2006-08-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001382 | 400152596 | High Sign | HFTD Tier 3 | Distribution | 2004-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001383 | 400152623 | High Sign | HFTD Tier 2 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001384 | 400152650 | High Sign | HFTD Tier 2 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001385 | 400152774 | Molding | HFTD Tier 3 | Distribution | 2004-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001386 | 400153016 | Molding | HFTD Tier 3 | Distribution | 2004-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001387 | 400153221 | Guy | HFTD Tier 3 | Distribution | 2004-09-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001388 | 400153286 | Molding | HFTD Tier 3 | Distribution | 2005-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001389 | 400153366 | Molding | HFTD Tier 3 | Distribution | 2005-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001390 | 400153490 | Molding | HFTD Tier 3 | Distribution | 2005-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001391 | 400153527 | Riser/Conduit | HFTD Tier 3 | Distribution | 2009-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001392 | 400153570 | Molding | HFTD Tier 3 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001393 | 400153675 | High Sign | HFTD Tier 3 | Distribution | 2004-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001394 | 400153846 | Molding | HFTD Tier 2 | Distribution | 2004-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001395 | 400153928 | Molding | HFTD Tier 3 | Distribution | 2004-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001396 | 400154343 | High Sign | HFTD Tier 3 | Distribution | 2005-11-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001397 | 400154413 | High Sign | HFTD Tier 3 | Distribution | 2006-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001398 | 400154568 | High Sign | HFTD Tier 3 | Distribution | 2010-02-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001399 | 400154692 | Molding | HFTD Tier 3 | Distribution | 2005-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001400 | 400154767 | High Sign | HFTD Tier 3 | Distribution | 2004-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001401 | 400154807 | Cable/Conductor | HFTD Tier 2 | Distribution | 2005-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001402 | 400154963 | High Sign | HFTD Tier 2 | Distribution | 2005-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001403 | 400154982 | High Sign | HFTD Tier 2 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001404 | 400155202 | High Sign | HFTD Tier 2 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001405 | 400155333 | Molding | HFTD Tier 2 | Distribution | 2010-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001406 | 400155364 | High Sign | HFTD Tier 3 | Distribution | 2007-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001407 | 400155592 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001408 | 400155819 | High Sign | HFTD Tier 3 | Distribution | 2006-08-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001409 | 400156054 | High Sign | HFTD Tier 3 | Distribution | 2001-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001410 | 400156058 | High Sign | HFTD Tier 3 | Distribution | 2001-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001411 | 400156068 | Molding | HFTD Tier 3 | Distribution | 2005-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001412 | 400156084 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001413 | 400156200 | High Sign | HFTD Tier 3 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001414 | 400156384 | Molding | HFTD Tier 3 | Distribution | 2004-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001415 | 400156617 | Molding | HFTD Tier 3 | Distribution | 2005-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001416 | 400156702 | High Sign | HFTD Tier 2 | Distribution | 2004-08-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001417 | 400157103 | High Sign | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001418 | 400157205 | Molding | HFTD Tier 3 | Distribution | 2010-01-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001419 | 400157325 | High Sign | HFTD Tier 2 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001420 | 400157392 | Molding | HFTD Tier 3 | Distribution | 2005-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001421 | 400157432 | Molding | HFTD Tier 2 | Distribution | 2004-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001422 | 400157618 | Molding | HFTD Tier 3 | Distribution | 2004-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001423 | 400157660 | High Sign | HFTD Tier 3 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001424 | 400157671 | Molding | HFTD Tier 3 | Distribution | 2004-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001425 | 400157674 | Molding | HFTD Tier 3 | Distribution | 2006-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001426 | 400157688 | Molding | HFTD Tier 3 | Distribution | 2004-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001427 | 400157701 | Molding | HFTD Tier 3 | Distribution | 2008-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001428 | 400157750 | High Sign | HFTD Tier 3 | Distribution | 2006-08-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001429 | 400158001 | Molding | HFTD Tier 2 | Distribution | 2004-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001430 | 400158196 | High Sign | HFTD Tier 3 | Distribution | 2004-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001431 | 400158213 | Molding | HFTD Tier 3 | Distribution | 2005-02-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001432 | 400158347 | Molding | HFTD Tier 3 | Distribution | 2005-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001433 | 400158391 | High Sign | HFTD Tier 3 | Distribution | 2004-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001434 | 400158440 | Hardware/Framing | HFTD Tier 2 | Distribution | 2009-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001435 | 400159172 | High Sign | HFTD Tier 2 | Distribution | 2005-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001436 | 400159280 | High Sign | HFTD Tier 3 | Distribution | 2010-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001437 | 400159378 | High Sign | HFTD Tier 3 | Distribution | 2004-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001438 | 400159386 | High Sign | HFTD Tier 3 | Distribution | 2004-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001439 | 400159387 | High Sign | HFTD Tier 2 | Distribution | 2008-10-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001440 | 400159409 | Molding | HFTD Tier 2 | Distribution | 2004-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001441 | 400159431 | High Sign | HFTD Tier 2 | Distribution | 2004-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001442 | 400159467 | Molding | HFTD Tier 3 | Distribution | 2005-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001443 | 400159703 | High Sign | HFTD Tier 3 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001444 | 400159841 | Molding | HFTD Tier 3 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001445 | 400159923 | Molding | HFTD Tier 2 | Distribution | 2004-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001446 | 400160229 | High Sign | HFTD Tier 3 | Distribution | 2003-11-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001447 | 400160274 | High Sign | HFTD Tier 3 | Distribution | 2008-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001448 | 400160366 | Molding | HFTD Tier 3 | Distribution | 2009-10-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001449 | 400160449 | High Sign | HFTD Tier 3 | Distribution | 2004-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001450 | 400160686 | High Sign | HFTD Tier 3 | Distribution | 2004-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001451 | 400160935 | Molding | HFTD Tier 2 | Distribution | 2005-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001452 | 400160980 | High Sign | HFTD Tier 3 | Distribution | 2005-11-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001453 | 400161009 | High Sign | HFTD Tier 2 | Distribution | 2004-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001454 | 400161342 | Hardware/Framing | HFTD Tier 2 | Distribution | 2009-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001455 | 400161407 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001456 | 400161452 | High Sign | HFTD Tier 3 | Distribution | 2001-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001457 | 400161543 | Molding | HFTD Tier 3 | Distribution | 2009-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001458 | 400161665 | High Sign | HFTD Tier 3 | Distribution | 2004-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001459 | 400161699 | Molding | HFTD Tier 3 | Distribution | 2005-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001460 | 400161835 | High Sign | HFTD Tier 3 | Distribution | 2004-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001461 | 400161909 | Molding | HFTD Tier 2 | Distribution | 2009-06-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001462 | 400162099 | Molding | HFTD Tier 3 | Distribution | 2004-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001463 | 400162107 | Riser/Conduit | HFTD Tier 2 | Distribution | 2005-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001464 | 400162118 | High Sign | HFTD Tier 2 | Distribution | 2004-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001465 | 400162155 | Hardware/Framing | HFTD Tier 2 | Distribution | 2004-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001466 | 400162204 | High Sign | HFTD Tier 2 | Distribution | 2006-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001467 | 400162341 | High Sign | HFTD Tier 2 | Distribution | 2004-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001468 | 400162419 | High Sign | HFTD Tier 3 | Distribution | 2004-11-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001469 | 400162449 | Molding | HFTD Tier 2 | Distribution | 2004-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001470 | 400162450 | Molding | HFTD Tier 2 | Distribution | 2004-08-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001471 | 400162537 | Molding | HFTD Tier 3 | Distribution | 2004-09-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001472 | 400162538 | Molding | HFTD Tier 3 | Distribution | 2009-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001473 | 400162678 | Molding | HFTD Tier 3 | Distribution | 2004-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001474 | 400162752 | Guy | HFTD Tier 3 | Distribution | 2003-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001475 | 400162814 | Guy | HFTD Tier 3 | Distribution | 2004-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001476 | 400162875 | Molding | HFTD Tier 2 | Distribution | 2004-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001477 | 400163114 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-10-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001478 | 400163123 | High Sign | HFTD Tier 3 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001479 | 400163243 | High Sign | HFTD Tier 3 | Distribution | 2005-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001480 | 400163458 | Molding | HFTD Tier 3 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001481 | 400163491 | Molding | HFTD Tier 2 | Distribution | 2005-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001482 | 400163567 | High Sign | HFTD Tier 2 | Distribution | 2004-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001483 | 400163776 | Molding | HFTD Tier 3 | Distribution | 2009-12-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001484 | 400163905 | High Sign | HFTD Tier 2 | Distribution | 2003-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001485 | 400163943 | Molding | HFTD Tier 2 | Distribution | 2008-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001486 | 400164076 | Guy | HFTD Tier 3 | Distribution | 2002-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001487 | 400164273 | Molding | HFTD Tier 3 | Distribution | 2009-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001488 | 400164403 | High Sign | HFTD Tier 3 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001489 | 400164609 | Molding | HFTD Tier 2 | Distribution | 2009-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001490 | 400164715 | High Sign | HFTD Tier 3 | Distribution | 2009-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001491 | 400164813 | Molding | HFTD Tier 2 | Distribution | 2004-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001492 | 400165063 | High Sign | HFTD Tier 3 | Distribution | 2009-10-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001493 | 400165263 | High Sign | HFTD Tier 3 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001494 | 400165287 | High Sign | HFTD Tier 2 | Distribution | 2001-12-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001495 | 400165366 | Molding | HFTD Tier 2 | Distribution | 2005-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001496 | 400165547 | High Sign | HFTD Tier 3 | Distribution | 2002-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001497 | 400165720 | High Sign | HFTD Tier 3 | Distribution | 2009-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001498 | 400165744 | High Sign | HFTD Tier 3 | Distribution | 2009-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001499 | 400165778 | High Sign | HFTD Tier 2 | Distribution | 2004-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001500 | 400165780 | Molding | HFTD Tier 2 | Distribution | 2006-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001501 | 400166027 | High Sign | HFTD Tier 2 | Distribution | 2009-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001502 | 400166140 | Hardware/Framing | HFTD Tier 2 | Distribution | 2002-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001503 | 400166168 | High Sign | HFTD Tier 3 | Distribution | 2002-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001504 | 400166303 | Guy | HFTD Tier 2 | Distribution | 2006-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001505 | 400166361 | High Sign | HFTD Tier 2 | Distribution | 2004-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001506 | 400166366 | Molding | HFTD Tier 3 | Distribution | 2004-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001507 | 400166521 | Molding | HFTD Tier 3 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001508 | 400166548 | High Sign | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001509 | 400166740 | Molding | HFTD Tier 3 | Distribution | 2004-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001510 | 400166814 | Molding | HFTD Tier 3 | Distribution | 2001-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001511 | 400166882 | High Sign | HFTD Tier 2 | Distribution | 2005-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001512 | 400166960 | High Sign | HFTD Tier 3 | Distribution | 2009-11-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001513 | 400167073 | High Sign | HFTD Tier 2 | Distribution | 2009-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001514 | 400167107 | High Sign | HFTD Tier 3 | Distribution | 2010-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001515 | 400167183 | High Sign | HFTD Tier 3 | Distribution | 2010-02-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001516 | 400167226 | Molding | HFTD Tier 3 | Distribution | 2005-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001517 | 400167277 | Molding | HFTD Tier 3 | Distribution | 2003-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001518 | 400167299 | High Sign | HFTD Tier 2 | Distribution | 2009-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001519 | 400167325 | Molding | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001520 | 400167515 | Molding | HFTD Tier 3 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001521 | 400167534 | Molding | HFTD Tier 2 | Distribution | 2008-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001522 | 400167611 | Molding | HFTD Tier 2 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001523 | 400167650 | Guy | HFTD Tier 3 | Distribution | 2010-04-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001524 | 400167841 | Molding | HFTD Tier 2 | Distribution | 2004-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001525 | 400167862 | High Sign | HFTD Tier 2 | Distribution | 2005-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001526 | 400167913 | High Sign | HFTD Tier 3 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001527 | 400167936 | High Sign | HFTD Tier 3 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001528 | 400168074 | Molding | HFTD Tier 3 | Distribution | 2004-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001529 | 400168144 | High Sign | HFTD Tier 3 | Distribution | 2004-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001530 | 400168190 | Guy | HFTD Tier 2 | Distribution | 2002-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001531 | 400168206 | High Sign | HFTD Tier 2 | Distribution | 2009-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001532 | 400168387 | Molding | HFTD Tier 2 | Distribution | 2004-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001533 | 400168388 | Molding | HFTD Tier 2 | Distribution | 2004-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001534 | 400168583 | Pole Tag | HFTD Tier 2 | Distribution | 2009-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001535 | 400168691 | Molding | HFTD Tier 2 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001536 | 400169034 | Molding | HFTD Tier 2 | Distribution | 2004-07-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001537 | 400169332 | Molding | HFTD Tier 3 | Distribution | 2004-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001538 | 400169340 | Molding | HFTD Tier 2 | Distribution | 2004-10-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001539 | 400169393 | High Sign | HFTD Tier 2 | Distribution | 2004-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001540 | 400169496 | High Sign | HFTD Tier 2 | Distribution | 2004-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001541 | 400169655 | High Sign | HFTD Tier 2 | Distribution | 2002-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001542 | 400169837 | Molding | HFTD Tier 3 | Distribution | 2005-11-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001543 | 400169918 | High Sign | HFTD Tier 3 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001544 | 400170044 | High Sign | HFTD Tier 2 | Distribution | 2001-09-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001545 | 400170068 | High Sign | HFTD Tier 3 | Distribution | 2004-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001546 | 400170252 | High Sign | HFTD Tier 3 | Distribution | 2001-08-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001547 | 400170510 | Molding | HFTD Tier 2 | Distribution | 2009-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001548 | 400170700 | Molding | HFTD Tier 2 | Distribution | 2004-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001549 | 400170719 | Molding | HFTD Tier 3 | Distribution | 2009-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001550 | 400170764 | Molding | HFTD Tier 3 | Distribution | 2006-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001551 | 400170782 | Molding | HFTD Tier 2 | Distribution | 2005-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001552 | 400170819 | High Sign | HFTD Tier 3 | Distribution | 2005-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001553 | 400170844 | High Sign | HFTD Tier 2 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001554 | 400171011 | Molding | HFTD Tier 2 | Distribution | 2004-07-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001555 | 400171090 | Molding | HFTD Tier 2 | Distribution | 2004-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001556 | 400171094 | High Sign | HFTD Tier 3 | Distribution | 2004-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001557 | 400171394 | High Sign | HFTD Tier 3 | Distribution | 2001-08-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001558 | 400171468 | Riser/Conduit | HFTD Tier 2 | Distribution | 2004-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001559 | 400171562 | Molding | HFTD Tier 2 | Distribution | 2009-12-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001560 | 400171741 | High Sign | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001561 | 400171849 | High Sign | HFTD Tier 3 | Distribution | 2009-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001562 | 400172156 | Molding | HFTD Tier 3 | Distribution | 2009-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001563 | 400172245 | High Sign | HFTD Tier 3 | Distribution | 2009-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001564 | 400172497 | High Sign | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001565 | 400172526 | Molding | HFTD Tier 2 | Distribution | 2004-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001566 | 400172570 | Molding | HFTD Tier 2 | Distribution | 2005-11-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001567 | 400172599 | Molding | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001568 | 400172868 | Molding | HFTD Tier 2 | Distribution | 2006-10-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001569 | 400172891 | High Sign | HFTD Tier 3 | Distribution | 2006-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001570 | 400173033 | Molding | HFTD Tier 2 | Distribution | 2009-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001571 | 400173084 | Molding | HFTD Tier 3 | Distribution | 2004-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001572 | 400173113 | Ground | HFTD Tier 2 | Distribution | 2009-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001573 | 400173349 | High Sign | HFTD Tier 2 | Distribution | 2010-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001574 | 400173360 | Guy | HFTD Tier 3 | Distribution | 2008-11-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001575 | 400173365 | Molding | HFTD Tier 2 | Distribution | 2004-07-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001576 | 400173495 | High Sign | HFTD Tier 2 | Distribution | 2004-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001577 | 400173513 | Molding | HFTD Tier 2 | Distribution | 2004-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001578 | 400173596 | High Sign | HFTD Tier 2 | Distribution | 2004-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001579 | 400173686 | Guy | HFTD Tier 2 | Distribution | 2005-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001580 | 400174098 | High Sign | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001581 | 400174129 | Guy | HFTD Tier 3 | Distribution | 2008-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001582 | 400174269 | Molding | HFTD Tier 2 | Distribution | 2001-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001583 | 400174319 | Guy | HFTD Tier 3 | Distribution | 2004-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001584 | 400174364 | High Sign | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001585 | 400174608 | Molding | HFTD Tier 3 | Distribution | 2009-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001586 | 400174714 | Molding | HFTD Tier 2 | Distribution | 2005-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001587 | 400174735 | High Sign | HFTD Tier 2 | Distribution | 2009-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001588 | 400174780 | High Sign | HFTD Tier 2 | Distribution | 2008-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001589 | 400174788 | Guy | HFTD Tier 3 | Distribution | 2010-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001590 | 400174795 | Guy | HFTD Tier 2 | Distribution | 2009-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001591 | 400174816 | Molding | HFTD Tier 3 | Distribution | 2010-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001592 | 400175010 | High Sign | HFTD Tier 3 | Distribution | 2009-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001593 | 400175156 | Guy | HFTD Tier 2 | Distribution | 2009-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001594 | 400175223 | Molding | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001595 | 400175250 | Molding | HFTD Tier 3 | Distribution | 2006-11-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001596 | 400175503 | High Sign | HFTD Tier 3 | Distribution | 2006-09-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001597 | 400175575 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2008-11-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001598 | 400176022 | High Sign | HFTD Tier 3 | Distribution | 2003-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001599 | 400176095 | High Sign | HFTD Tier 3 | Distribution | 2005-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001600 | 400176232 | Molding | HFTD Tier 3 | Distribution | 2009-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001601 | 400176259 | High Sign | HFTD Tier 3 | Distribution | 2005-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001602 | 400176308 | Molding | HFTD Tier 3 | Distribution | 2004-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001603 | 400176778 | Molding | HFTD Tier 3 | Distribution | 2005-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001604 | 400176817 | High Sign | HFTD Tier 3 | Distribution | 2010-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001605 | 400176947 | High Sign | HFTD Tier 2 | Distribution | 2004-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001606 | 400176983 | High Sign | HFTD Tier 3 | Distribution | 2003-11-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001607 | 400177030 | High Sign | HFTD Tier 2 | Distribution | 2004-05-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001608 | 400177033 | High Sign | HFTD Tier 2 | Distribution | 2004-04-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001609 | 400177056 | High Sign | HFTD Tier 3 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001610 | 400177057 | Hardware/Framing | HFTD Tier 2 | Distribution | 2001-09-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001611 | 400177586 | Molding | HFTD Tier 3 | Distribution | 2009-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001612 | 400177681 | High Sign | HFTD Tier 3 | Distribution | 2009-12-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001613 | 400178040 | Ground | HFTD Tier 3 | Distribution | 2010-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001614 | 400178144 | High Sign | HFTD Tier 2 | Distribution | 2004-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001615 | 400178193 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-11-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001616 | 400178210 | High Sign | HFTD Tier 3 | Distribution | 2003-12-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001617 | 400178533 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001618 | 400178643 | Molding | HFTD Tier 2 | Distribution | 2008-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001619 | 400178734 | Molding | HFTD Tier 3 | Distribution | 2009-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001620 | 400178756 | Molding | HFTD Tier 3 | Distribution | 2004-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001621 | 400178784 | Molding | HFTD Tier 3 | Distribution | 2004-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001622 | 400178803 | Cable/Conductor | HFTD Tier 3 | Distribution | 2005-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001623 | 400179186 | High Sign | HFTD Tier 3 | Distribution | 2004-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001624 | 400179233 | High Sign | HFTD Tier 2 | Distribution | 2005-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001625 | 400179349 | High Sign | HFTD Tier 3 | Distribution | 2009-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001626 | 400179592 | High Sign | HFTD Tier 2 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001627 | 400179691 | Guy | HFTD Tier 3 | Distribution | 2009-11-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001628 | 400179766 | Molding | HFTD Tier 2 | Distribution | 2004-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001629 | 400179774 | High Sign | HFTD Tier 2 | Distribution | 2005-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001630 | 400179977 | High Sign | HFTD Tier 2 | Distribution | 2005-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001631 | 400179988 | High Sign | HFTD Tier 2 | Distribution | 2004-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001632 | 400180134 | Molding | HFTD Tier 3 | Distribution | 2004-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001633 | 400180157 | High Sign | HFTD Tier 2 | Distribution | 2009-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001634 | 400180390 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2008-11-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001635 | 400180638 | Molding | HFTD Tier 2 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001636 | 400180705 | Molding | HFTD Tier 2 | Distribution | 2004-04-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001637 | 400180733 | Molding | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001638 | 400181176 | Molding | HFTD Tier 2 | Distribution | 2003-11-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001639 | 400181353 | High Sign | HFTD Tier 3 | Distribution | 2004-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001640 | 400181886 | Insulator | HFTD Tier 2 | Distribution | 2004-11-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001641 | 400181936 | High Sign | HFTD Tier 3 | Distribution | 2005-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001642 | 400181997 | Molding | HFTD Tier 3 | Distribution | 2004-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001643 | 400182039 | High Sign | HFTD Tier 2 | Distribution | 2004-05-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001644 | 400182066 | Molding | HFTD Tier 3 | Distribution | 2004-05-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001645 | 400182161 | Molding | HFTD Tier 2 | Distribution | 2005-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001646 | 400182198 | Molding | HFTD Tier 2 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001647 | 400182199 | Molding | HFTD Tier 2 | Distribution | 2010-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001648 | 400182389 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001649 | 400182553 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001650 | 400182596 | High Sign | HFTD Tier 2 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001651 | 400182627 | Molding | HFTD Tier 2 | Distribution | 2009-09-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001652 | 400182694 | High Sign | HFTD Tier 2 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001653 | 400182724 | Molding | HFTD Tier 2 | Distribution | 2008-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001654 | 400183037 | Molding | HFTD Tier 2 | Distribution | 2005-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001655 | 400183121 | High Sign | HFTD Tier 3 | Distribution | 2009-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001656 | 400183193 | High Sign | HFTD Tier 2 | Distribution | 2009-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001657 | 400183281 | Molding | HFTD Tier 3 | Distribution | 2009-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001658 | 400183318 | Molding | HFTD Tier 2 | Distribution | 2009-08-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001659 | 400183350 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001660 | 400183481 | High Sign | HFTD Tier 2 | Distribution | 2004-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001661 | 400183604 | Insulator | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001662 | 400183635 | High Sign | HFTD Tier 2 | Distribution | 2004-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001663 | 400183656 | High Sign | HFTD Tier 2 | Distribution | 2005-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001664 | 400183698 | Molding | HFTD Tier 2 | Distribution | 2004-09-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001665 | 400183704 | High Sign | HFTD Tier 2 | Distribution | 2004-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001666 | 400183726 | High Sign | HFTD Tier 2 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001667 | 400183727 | High Sign | HFTD Tier 2 | Distribution | 2004-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001668 | 400183729 | Molding | HFTD Tier 2 | Distribution | 2004-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001669 | 400183817 | High Sign | HFTD Tier 2 | Distribution | 2004-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001670 | 400183839 | High Sign | HFTD Tier 3 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001671 | 400183962 | Guy | HFTD Tier 2 | Distribution | 2003-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001672 | 400184095 | High Sign | HFTD Tier 2 | Distribution | 2005-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001673 | 400184552 | High Sign | HFTD Tier 2 | Distribution | 2005-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001674 | 400184583 | High Sign | HFTD Tier 2 | Distribution | 2005-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001675 | 400184656 | High Sign | HFTD Tier 3 | Distribution | 2008-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001676 | 400184665 | High Sign | HFTD Tier 2 | Distribution | 2005-05-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001677 | 400184720 | High Sign | HFTD Tier 2 | Distribution | 2004-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001678 | 400184753 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001679 | 400184767 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001680 | 400184904 | High Sign | HFTD Tier 3 | Distribution | 2003-12-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001681 | 400185011 | Guy | HFTD Tier 3 | Distribution | 2005-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001682 | 400185052 | Molding | HFTD Tier 2 | Distribution | 2004-08-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001683 | 400185064 | Molding | HFTD Tier 2 | Distribution | 2001-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001684 | 400185163 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2009-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001685 | 400185224 | High Sign | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001686 | 400185260 | High Sign | HFTD Tier 2 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001687 | 400185288 | High Sign | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001688 | 400185373 | High Sign | HFTD Tier 2 | Distribution | 2005-11-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001689 | 400185413 | Molding | HFTD Tier 2 | Distribution | 2006-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001690 | 400185442 | High Sign | HFTD Tier 2 | Distribution | 2009-12-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001691 | 400185453 | Ground | HFTD Tier 2 | Distribution | 2004-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001692 | 400185508 | Molding | HFTD Tier 2 | Distribution | 2003-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001693 | 400185553 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001694 | 400185570 | Molding | HFTD Tier 2 | Distribution | 2004-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001695 | 400185598 | High Sign | HFTD Tier 2 | Distribution | 2009-09-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001696 | 400185665 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001697 | 400185690 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001698 | 400185864 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001699 | 400185928 | High Sign | HFTD Tier 2 | Distribution | 2005-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001700 | 400185961 | High Sign | HFTD Tier 2 | Distribution | 2005-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001701 | 400185988 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001702 | 400186087 | Hardware/Framing | HFTD Tier 3 | Distribution | 2005-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001703 | 400186238 | Guy | HFTD Tier 3 | Distribution | 2004-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001704 | 400186337 | Guy | HFTD Tier 3 | Distribution | 2005-02-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001705 | 400186582 | Molding | HFTD Tier 3 | Distribution | 2010-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001706 | 400186715 | Guy | HFTD Tier 2 | Distribution | 2002-02-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001707 | 400186879 | High Sign | HFTD Tier 3 | Distribution | 2008-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001708 | 400186901 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001709 | 400186933 | Guy | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001710 | 400186971 | Molding | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001711 | 400187077 | Molding | HFTD Tier 3 | Distribution | 2009-12-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001712 | 400187292 | High Sign | HFTD Tier 2 | Distribution | 2005-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001713 | 400187434 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2008-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001714 | 400187474 | Molding | HFTD Tier 3 | Distribution | 2005-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001715 | 400187530 | High Sign | HFTD Tier 2 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001716 | 400187570 | High Sign | HFTD Tier 3 | Distribution | 2004-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001717 | 400187588 | High Sign | HFTD Tier 3 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001718 | 400187590 | Molding | HFTD Tier 2 | Distribution | 2005-11-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001719 | 400187768 | High Sign | HFTD Tier 2 | Distribution | 2004-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001720 | 400188043 | Molding | HFTD Tier 3 | Distribution | 2003-12-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001721 | 400188099 | High Sign | HFTD Tier 2 | Distribution | 2004-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001722 | 400188188 | High Sign | HFTD Tier 3 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001723 | 400188211 | Molding | HFTD Tier 3 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001724 | 400188257 | High Sign | HFTD Tier 2 | Distribution | 2004-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001725 | 400188489 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-11-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001726 | 400188560 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-05-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001727 | 400188682 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2008-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001728 | 400188699 | Hardware/Framing | HFTD Tier 2 | Distribution | 2004-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001729 | 400188779 | High Sign | HFTD Tier 3 | Distribution | 2008-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001730 | 400188811 | High Sign | HFTD Tier 2 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001731 | 400188814 | Molding | HFTD Tier 2 | Distribution | 2005-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001732 | 400188826 | High Sign | HFTD Tier 2 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001733 | 400189133 | High Sign | HFTD Tier 2 | Distribution | 2008-11-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001734 | 400189193 | High Sign | HFTD Tier 2 | Distribution | 2004-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001735 | 400189235 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001736 | 400189265 | Molding | HFTD Tier 3 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001737 | 400189297 | High Sign | HFTD Tier 2 | Distribution | 2004-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001738 | 400189311 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001739 | 400189377 | High Sign | HFTD Tier 2 | Distribution | 2004-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001740 | 400189464 | Molding | HFTD Tier 2 | Distribution | 2004-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001741 | 400189670 | Molding | HFTD Tier 3 | Distribution | 2004-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001742 | 400189686 | High Sign | HFTD Tier 3 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001743 | 400189710 | Molding | HFTD Tier 2 | Distribution | 2010-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001744 | 400189806 | High Sign | HFTD Tier 3 | Distribution | 2006-08-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001745 | 400189859 | Molding | HFTD Tier 3 | Distribution | 2005-08-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001746 | 400189874 | Molding | HFTD Tier 3 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001747 | 400189900 | Molding | HFTD Tier 3 | Distribution | 2008-08-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001748 | 400190135 | Molding | HFTD Tier 2 | Distribution | 2005-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001749 | 400190263 | Molding | HFTD Tier 3 | Distribution | 2005-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001750 | 400190282 | Guy | HFTD Tier 2 | Distribution | 2003-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001751 | 400190304 | High Sign | HFTD Tier 2 | Distribution | 2004-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001752 | 400190397 | Molding | HFTD Tier 3 | Distribution | 2010-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001753 | 400190583 | High Sign | HFTD Tier 3 | Distribution | 2004-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001754 | 400190687 | High Sign | HFTD Tier 2 | Distribution | 2005-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001755 | 400190820 | High Sign | HFTD Tier 3 | Distribution | 2008-05-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001756 | 400190897 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2008-11-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001757 | 400190963 | Guy | HFTD Tier 2 | Distribution | 2002-02-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001758 | 400190994 | Molding | HFTD Tier 2 | Distribution | 2004-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001759 | 400191116 | Molding | HFTD Tier 2 | Distribution | 2006-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001760 | 400191189 | High Sign | HFTD Tier 3 | Distribution | 2004-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001761 | 400191222 | High Sign | HFTD Tier 2 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001762 | 400191239 | Molding | HFTD Tier 3 | Distribution | 2004-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001763 | 400191307 | Hardware/Framing | HFTD Tier 2 | Distribution | 2009-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001764 | 400191339 | High Sign | HFTD Tier 2 | Distribution | 2010-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001765 | 400191341 | Molding | HFTD Tier 2 | Distribution | 2005-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001766 | 400191379 | Molding | HFTD Tier 3 | Distribution | 2004-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001767 | 400191446 | Guy | HFTD Tier 2 | Distribution | 2002-02-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001768 | 400191571 | Guy | HFTD Tier 2 | Distribution | 2003-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001769 | 400191572 | High Sign | HFTD Tier 2 | Distribution | 2004-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001770 | 400191601 | High Sign | HFTD Tier 3 | Distribution | 2009-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001771 | 400191681 | Guy | HFTD Tier 2 | Distribution | 2005-11-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001772 | 400191821 | Molding | HFTD Tier 3 | Distribution | 2004-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001773 | 400192000 | Molding | HFTD Tier 2 | Distribution | 2005-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001774 | 400192363 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001775 | 400192444 | Hardware/Framing | HFTD Tier 2 | Distribution | 2004-11-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001776 | 400192477 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-10-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001777 | 400192532 | Molding | HFTD Tier 2 | Distribution | 2006-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001778 | 400192721 | High Sign | HFTD Tier 2 | Distribution | 2005-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001779 | 400192826 | Molding | HFTD Tier 3 | Distribution | 2009-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001780 | 400192827 | Molding | HFTD Tier 2 | Distribution | 2005-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001781 | 400192839 | High Sign | HFTD Tier 2 | Distribution | 2004-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001782 | 400192957 | Molding | HFTD Tier 2 | Distribution | 2004-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001783 | 400193238 | High Sign | HFTD Tier 3 | Distribution | 2006-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001784 | 400193261 | Molding | HFTD Tier 3 | Distribution | 2006-10-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001785 | 400193292 | Molding | HFTD Tier 3 | Distribution | 2003-12-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001786 | 400193311 | Molding | HFTD Tier 2 | Distribution | 2006-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001787 | 400193480 | High Sign | HFTD Tier 3 | Distribution | 2005-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001788 | 400193573 | Molding | HFTD Tier 2 | Distribution | 2004-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001789 | 400193714 | Molding | HFTD Tier 2 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001790 | 400193780 | Molding | HFTD Tier 3 | Distribution | 2009-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001791 | 400193852 | High Sign | HFTD Tier 2 | Distribution | 2009-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001792 | 400193888 | Molding | HFTD Tier 3 | Distribution | 2004-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001793 | 400194156 | High Sign | HFTD Tier 3 | Distribution | 2005-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001794 | 400194296 | Molding | HFTD Tier 2 | Distribution | 2004-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001795 | 400194332 | High Sign | HFTD Tier 2 | Distribution | 2001-09-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001796 | 400194429 | Molding | HFTD Tier 2 | Distribution | 2005-09-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001797 | 400194453 | Molding | HFTD Tier 2 | Distribution | 2005-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001798 | 400194467 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001799 | 400194531 | Molding | HFTD Tier 3 | Distribution | 2004-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001800 | 400194580 | High Sign | HFTD Tier 2 | Distribution | 2001-09-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001801 | 400194980 | High Sign | HFTD Tier 3 | Distribution | 2005-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001802 | 400195033 | High Sign | HFTD Tier 2 | Distribution | 2009-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001803 | 400195168 | Molding | HFTD Tier 3 | Distribution | 2003-12-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001804 | 400195217 | High Sign | HFTD Tier 2 | Distribution | 2010-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001805 | 400195262 | High Sign | HFTD Tier 3 | Distribution | 2010-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001806 | 400195332 | Molding | HFTD Tier 3 | Distribution | 2002-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001807 | 400195482 | Molding | HFTD Tier 3 | Distribution | 2010-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001808 | 400195592 | Molding | HFTD Tier 2 | Distribution | 2005-11-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001809 | 400195617 | Insulator | HFTD Tier 3 | Distribution | 2004-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001810 | 400195853 | High Sign | HFTD Tier 2 | Distribution | 2003-12-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001811 | 400195948 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2009-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001812 | 400196001 | Molding | HFTD Tier 3 | Distribution | 2006-10-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001813 | 400196068 | Molding | HFTD Tier 3 | Distribution | 2003-12-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001814 | 400196100 | Molding | HFTD Tier 3 | Distribution | 2004-01-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001815 | 400196125 | Hardware/Framing | HFTD Tier 2 | Distribution | 2004-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001816 | 400196359 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001817 | 400196692 | High Sign | HFTD Tier 3 | Distribution | 2004-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001818 | 400196978 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-10-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001819 | 400197006 | High Sign | HFTD Tier 3 | Distribution | 2004-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001820 | 400197042 | High Sign | HFTD Tier 2 | Distribution | 2009-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001821 | 400197116 | High Sign | HFTD Tier 3 | Distribution | 2005-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001822 | 400197352 | Ground | HFTD Tier 2 | Distribution | 2009-10-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001823 | 400197384 | Molding | HFTD Tier 3 | Distribution | 2003-12-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001824 | 400197393 | High Sign | HFTD Tier 3 | Distribution | 2005-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001825 | 400197449 | Molding | HFTD Tier 2 | Distribution | 2009-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001826 | 400197491 | High Sign | HFTD Tier 3 | Distribution | 2008-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001827 | 400197544 | Molding | HFTD Tier 3 | Distribution | 2009-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001828 | 400197568 | Molding | HFTD Tier 2 | Distribution | 2009-12-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001829 | 400197610 | Molding | HFTD Tier 2 | Distribution | 2005-09-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001830 | 400197632 | Molding | HFTD Tier 2 | Distribution | 2004-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001831 | 400197689 | Molding | HFTD Tier 2 | Distribution | 2004-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001832 | 400197747 | High Sign | HFTD Tier 3 | Distribution | 2004-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001833 | 400197772 | Guy | HFTD Tier 3 | Distribution | 2004-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001834 | 400197894 | Molding | HFTD Tier 3 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001835 | 400197925 | Molding | HFTD Tier 2 | Distribution | 2004-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001836 | 400197957 | High Sign | HFTD Tier 3 | Distribution | 2009-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001837 | 400197965 | High Sign | HFTD Tier 2 | Distribution | 2004-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001838 | 400198046 | High Sign | HFTD Tier 2 | Distribution | 2003-12-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001839 | 400198079 | Molding | HFTD Tier 2 | Distribution | 2006-12-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001840 | 400198133 | High Sign | HFTD Tier 2 | Distribution | 2005-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001841 | 400198171 | Molding | HFTD Tier 2 | Distribution | 2009-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001842 | 400198209 | High Sign | HFTD Tier 3 | Distribution | 2009-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001843 | 400198212 | High Sign | HFTD Tier 2 | Distribution | 2009-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001844 | 400198246 | High Sign | HFTD Tier 3 | Distribution | 2009-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001845 | 400198339 | Molding | HFTD Tier 3 | Distribution | 2009-09-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001846 | 400198544 | High Sign | HFTD Tier 2 | Distribution | 2004-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001847 | 400198597 | High Sign | HFTD Tier 3 | Distribution | 2001-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001848 | 400198648 | High Sign | HFTD Tier 3 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001849 | 400198753 | Molding | HFTD Tier 3 | Distribution | 2005-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001850 | 400198969 | Insulator | HFTD Tier 2 | Distribution | 2004-07-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001851 | 400199047 | Molding | HFTD Tier 2 | Distribution | 2002-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001852 | 400199071 | Molding | HFTD Tier 2 | Distribution | 2002-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001853 | 400199120 | High Sign | HFTD Tier 2 | Distribution | 1999-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001854 | 400199303 | High Sign | HFTD Tier 2 | Distribution | 2005-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001855 | 400199351 | Molding | HFTD Tier 3 | Distribution | 2006-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001856 | 400199519 | High Sign | HFTD Tier 3 | Distribution | 2009-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001857 | 400199619 | High Sign | HFTD Tier 2 | Distribution | 2005-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001858 | 400199745 | High Sign | HFTD Tier 2 | Distribution | 2003-11-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001859 | 400199881 | High Sign | HFTD Tier 2 | Distribution | 2004-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001860 | 400199938 | Molding | HFTD Tier 2 | Distribution | 2002-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001861 | 400200109 | Guy | HFTD Tier 2 | Distribution | 2005-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001862 | 400200198 | Molding | HFTD Tier 2 | Distribution | 2005-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001863 | 400200235 | High Sign | HFTD Tier 2 | Distribution | 2008-09-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001864 | 400200248 | High Sign | HFTD Tier 3 | Distribution | 2003-11-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001865 | 400200330 | Molding | HFTD Tier 2 | Distribution | 2004-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001866 | 400200353 | Molding | HFTD Tier 3 | Distribution | 2009-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001867 | 400200539 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001868 | 400200586 | Molding | HFTD Tier 2 | Distribution | 2009-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001869 | 400200601 | High Sign | HFTD Tier 2 | Distribution | 2005-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001870 | 400200658 | Molding | HFTD Tier 2 | Distribution | 2005-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001871 | 400200769 | High Sign | HFTD Tier 3 | Distribution | 2009-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001872 | 400200870 | Molding | HFTD Tier 2 | Distribution | 2009-11-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001873 | 400201139 | Molding | HFTD Tier 2 | Distribution | 2009-09-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001874 | 400201207 | High Sign | HFTD Tier 3 | Distribution | 2004-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001875 | 400201359 | Molding | HFTD Tier 2 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001876 | 400201474 | Molding | HFTD Tier 2 | Distribution | 2004-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001877 | 400201551 | High Sign | HFTD Tier 2 | Distribution | 2009-09-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001878 | 400201558 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001879 | 400201686 | High Sign | HFTD Tier 3 | Distribution | 2004-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001880 | 400201701 | Molding | HFTD Tier 2 | Distribution | 2004-07-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001881 | 400201703 | High Sign | HFTD Tier 3 | Distribution | 2010-02-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001882 | 400201756 | High Sign | HFTD Tier 3 | Distribution | 2010-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001883 | 400201772 | Molding | HFTD Tier 3 | Distribution | 2004-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001884 | 400201844 | Molding | HFTD Tier 2 | Distribution | 2004-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001885 | 400201893 | Hardware/Framing | HFTD Tier 2 | Distribution | 2004-06-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001886 | 400201976 | High Sign | HFTD Tier 2 | Distribution | 2004-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001887 | 400202009 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001888 | 400202035 | Molding | HFTD Tier 3 | Distribution | 2007-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001889 | 400202158 | Molding | HFTD Tier 3 | Distribution | 2010-04-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001890 | 400202252 | Molding | HFTD Tier 3 | Distribution | 2005-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001891 | 400202278 | High Sign | HFTD Tier 3 | Distribution | 2009-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001892 | 400202320 | Riser/Conduit | HFTD Tier 3 | Distribution | 2004-12-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001893 | 400202438 | Guy | HFTD Tier 3 | Distribution | 2007-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001894 | 400202608 | High Sign | HFTD Tier 3 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001895 | 400202965 | Molding | HFTD Tier 2 | Distribution | 2003-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001896 | 400203016 | High Sign | HFTD Tier 2 | Distribution | 2003-11-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001897 | 400203113 | Molding | HFTD Tier 2 | Distribution | 2009-11-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001898 | 400203138 | Molding | HFTD Tier 3 | Distribution | 2009-10-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001899 | 400203141 | High Sign | HFTD Tier 3 | Distribution | 2007-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001900 | 400203242 | Molding | HFTD Tier 3 | Distribution | 2009-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001901 | 400203343 | High Sign | HFTD Tier 2 | Distribution | 2005-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001902 | 400203393 | High Sign | HFTD Tier 2 | Distribution | 2004-07-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001903 | 400203447 | Molding | HFTD Tier 2 | Distribution | 2004-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001904 | 400203490 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001905 | 400203502 | Guy | HFTD Tier 3 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001906 | 400203561 | Molding | HFTD Tier 3 | Distribution | 2008-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001907 | 400203628 | Molding | HFTD Tier 3 | Distribution | 2004-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001908 | 400203827 | High Sign | HFTD Tier 3 | Distribution | 2004-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001909 | 400203850 | Molding | HFTD Tier 3 | Distribution | 2004-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001910 | 400204073 | Molding | HFTD Tier 2 | Distribution | 2005-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001911 | 400204150 | Molding | HFTD Tier 3 | Distribution | 2004-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001912 | 400204208 | Molding | HFTD Tier 3 | Distribution | 2004-01-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001913 | 400204390 | High Sign | HFTD Tier 2 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001914 | 400204400 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001915 | 400204425 | Molding | HFTD Tier 2 | Distribution | 2003-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001916 | 400204480 | Molding | HFTD Tier 3 | Distribution | 2004-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001917 | 400204490 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2008-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001918 | 400204572 | Molding | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001919 | 400204593 | Molding | HFTD Tier 3 | Distribution | 2005-09-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001920 | 400204664 | Guy | HFTD Tier 3 | Distribution | 2010-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001921 | 400204835 | High Sign | HFTD Tier 3 | Distribution | 2001-11-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001922 | 400205021 | High Sign | HFTD Tier 3 | Distribution | 2008-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001923 | 400205047 | High Sign | HFTD Tier 2 | Distribution | 2004-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001924 | 400205053 | Guy | HFTD Tier 3 | Distribution | 2004-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001925 | 400205159 | High Sign | HFTD Tier 2 | Distribution | 2001-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001926 | 400205170 | Molding | HFTD Tier 2 | Distribution | 2004-10-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001927 | 400205185 | High Sign | HFTD Tier 3 | Distribution | 2004-12-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001928 | 400205197 | Molding | HFTD Tier 3 | Distribution | 2004-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001929 | 400205224 | High Sign | HFTD Tier 2 | Distribution | 2009-11-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001930 | 400205265 | High Sign | HFTD Tier 2 | Distribution | 2006-11-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001931 | 400205301 | High Sign | HFTD Tier 3 | Distribution | 2008-10-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001932 | 400205302 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001933 | 400205409 | Molding | HFTD Tier 3 | Distribution | 2010-02-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001934 | 400205566 | High Sign | HFTD Tier 3 | Distribution | 2006-11-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001935 | 400205631 | High Sign | HFTD Tier 3 | Distribution | 2005-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001936 | 400205832 | High Sign | HFTD Tier 3 | Distribution | 2010-01-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001937 | 400205854 | Molding | HFTD Tier 2 | Distribution | 2002-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001938 | 400205894 | High Sign | HFTD Tier 2 | Distribution | 2004-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001939 | 400205933 | Guy | HFTD Tier 3 | Distribution | 2006-11-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001940 | 400206049 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001941 | 400206148 | Molding | HFTD Tier 2 | Distribution | 2010-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001942 | 400206384 | Molding | HFTD Tier 3 | Distribution | 2010-04-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001943 | 400206553 | High Sign | HFTD Tier 2 | Distribution | 2001-01-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001944 | 400206577 | High Sign | HFTD Tier 3 | Distribution | 2004-10-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001945 | 400206636 | Molding | HFTD Tier 2 | Distribution | 2004-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001946 | 400206739 | Crossarm | HFTD Tier 3 | Distribution | 2008-09-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001947 | 400206803 | Molding | HFTD Tier 2 | Distribution | 2001-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001948 | 400206809 | Molding | HFTD Tier 2 | Distribution | 2005-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001949 | 400206837 | Molding | HFTD Tier 3 | Distribution | 2005-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001950 | 400206858 | High Sign | HFTD Tier 3 | Distribution | 2004-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001951 | 400206886 | Molding | HFTD Tier 2 | Distribution | 2009-11-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001952 | 400206931 | Guy | HFTD Tier 3 | Distribution | 2005-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001953 | 400206963 | High Sign | HFTD Tier 2 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001954 | 400206983 | High Sign | HFTD Tier 3 | Distribution | 2004-07-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001955 | 400207004 | Molding | HFTD Tier 3 | Distribution | 2004-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001956 | 400207146 | Molding | HFTD Tier 2 | Distribution | 2005-08-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001957 | 400207297 | High Sign | HFTD Tier 3 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001958 | 400207313 | High Sign | HFTD Tier 3 | Distribution | 2004-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001959 | 400207611 | Molding | HFTD Tier 3 | Distribution | 2005-08-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001960 | 400207709 | High Sign | HFTD Tier 3 | Distribution | 2005-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001961 | 400207920 | Molding | HFTD Tier 2 | Distribution | 2009-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001962 | 400208295 | High Sign | HFTD Tier 3 | Distribution | 2002-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001963 | 400208449 | High Sign | HFTD Tier 2 | Distribution | 2009-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001964 | 400208504 | High Sign | HFTD Tier 3 | Distribution | 2001-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001965 | 400208758 | Riser/Conduit | HFTD Tier 3 | Distribution | 2010-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001966 | 400208776 | High Sign | HFTD Tier 3 | Distribution | 2008-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001967 | 400208809 | Molding | HFTD Tier 3 | Distribution | 2009-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001968 | 400208868 | High Sign | HFTD Tier 3 | Distribution | 2004-01-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001969 | 400208958 | Riser/Conduit | HFTD Tier 3 | Distribution | 2010-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001970 | 400209323 | Molding | HFTD Tier 2 | Distribution | 2003-11-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001971 | 400209347 | High Sign | HFTD Tier 2 | Distribution | 2003-11-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001972 | 400209431 | Molding | HFTD Tier 3 | Distribution | 2009-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001973 | 400209470 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001974 | 400209751 | Molding | HFTD Tier 2 | Distribution | 2005-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001975 | 400209989 | Molding | HFTD Tier 2 | Distribution | 2005-01-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001976 | 400210149 | High Sign | HFTD Tier 3 | Distribution | 2004-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001977 | 400210337 | High Sign | HFTD Tier 3 | Distribution | 2002-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001978 | 400210379 | Molding | HFTD Tier 3 | Distribution | 2005-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001979 | 400210447 | Molding | HFTD Tier 3 | Distribution | 2005-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001980 | 400210701 | High Sign | HFTD Tier 2 | Distribution | 2004-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001981 | 400210711 | High Sign | HFTD Tier 2 | Distribution | 2004-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001982 | 400210736 | Molding | HFTD Tier 3 | Distribution | 2004-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001983 | 400210756 | Molding | HFTD Tier 3 | Distribution | 2005-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001984 | 400210811 | High Sign | HFTD Tier 3 | Distribution | 2005-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001985 | 400210858 | Guy | HFTD Tier 3 | Distribution | 2010-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001986 | 400210890 | High Sign | HFTD Tier 3 | Distribution | 2004-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001987 | 400210926 | Molding | HFTD Tier 2 | Distribution | 2004-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001988 | 400211081 | Molding | HFTD Tier 2 | Distribution | 2009-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001989 | 400211201 | High Sign | HFTD Tier 2 | Distribution | 2003-12-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001990 | 400211247 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2008-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001991 | 400211253 | Molding | HFTD Tier 3 | Distribution | 2005-11-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001992 | 400211411 | Cable/Conductor | HFTD Tier 3 | Distribution | 2008-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001993 | 400211465 | High Sign | HFTD Tier 2 | Distribution | 2001-01-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001994 | 400211515 | High Sign | HFTD Tier 3 | Distribution | 2009-10-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001995 | 400211545 | High Sign | HFTD Tier 3 | Distribution | 2008-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001996 | 400211576 | Molding | HFTD Tier 3 | Distribution | 2009-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001997 | 400211623 | Guy | HFTD Tier 3 | Distribution | 2006-09-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001998 | 400211657 | High Sign | HFTD Tier 3 | Distribution | 2009-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130001999 | 400211751 | High Sign | HFTD Tier 2 | Distribution | 2004-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002000 | 400211822 | Guy | HFTD Tier 3 | Distribution | 2004-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002001 | 400212005 | Molding | HFTD Tier 3 | Distribution | 2010-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002002 | 400212030 | High Sign | HFTD Tier 3 | Distribution | 2010-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002003 | 400212505 | High Sign | HFTD Tier 2 | Distribution | 2004-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002004 | 400212541 | Molding | HFTD Tier 3 | Distribution | 2004-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002005 | 400212555 | Molding | HFTD Tier 3 | Distribution | 2005-08-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002006 | 400212624 | Molding | HFTD Tier 2 | Distribution | 2004-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002007 | 400212676 | Molding | HFTD Tier 2 | Distribution | 2004-11-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002008 | 400212728 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002009 | 400213020 | Molding | HFTD Tier 3 | Distribution | 2005-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002010 | 400213479 | High Sign | HFTD Tier 2 | Distribution | 2001-09-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002011 | 400213508 | Molding | HFTD Tier 3 | Distribution | 2004-07-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002012 | 400213577 | Guy | HFTD Tier 3 | Distribution | 2004-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002013 | 400213591 | Guy | HFTD Tier 2 | Distribution | 2004-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002014 | 400213628 | High Sign | HFTD Tier 2 | Distribution | 2004-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002015 | 400213666 | Molding | HFTD Tier 2 | Distribution | 2009-11-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002016 | 400213744 | High Sign | HFTD Tier 3 | Distribution | 2005-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002017 | 400213966 | High Sign | HFTD Tier 2 | Distribution | 2004-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002018 | 400214002 | High Sign | HFTD Tier 3 | Distribution | 2008-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002019 | 400214040 | High Sign | HFTD Tier 3 | Distribution | 2005-08-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002020 | 400214090 | Molding | HFTD Tier 2 | Distribution | 2008-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002021 | 400214512 | Molding | HFTD Tier 3 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002022 | 400214517 | Ground | HFTD Tier 2 | Distribution | 2009-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002023 | 400214549 | High Sign | HFTD Tier 2 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002024 | 400214629 | Guy | HFTD Tier 2 | Distribution | 2004-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002025 | 400214880 | Molding | HFTD Tier 2 | Distribution | 2004-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002026 | 400215074 | Molding | HFTD Tier 2 | Distribution | 2005-01-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002027 | 400215108 | High Sign | HFTD Tier 2 | Distribution | 2005-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002028 | 400215118 | Riser/Conduit | HFTD Tier 3 | Distribution | 2010-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002029 | 400215580 | High Sign | HFTD Tier 2 | Distribution | 2005-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002030 | 400215842 | Molding | HFTD Tier 3 | Distribution | 2005-08-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002031 | 400215850 | Guy | HFTD Tier 3 | Distribution | 2009-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002032 | 400215885 | Molding | HFTD Tier 3 | Distribution | 2004-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002033 | 400215910 | High Sign | HFTD Tier 3 | Distribution | 2004-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002034 | 400216092 | Molding | HFTD Tier 3 | Distribution | 2009-07-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002035 | 400216114 | High Sign | HFTD Tier 2 | Distribution | 2010-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002036 | 400216140 | High Sign | HFTD Tier 2 | Distribution | 2010-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002037 | 400216148 | Ground | HFTD Tier 2 | Distribution | 2010-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002038 | 400216367 | High Sign | HFTD Tier 2 | Distribution | 2009-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002039 | 400216415 | Guy | HFTD Tier 3 | Distribution | 2010-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002040 | 400216770 | High Sign | HFTD Tier 3 | Distribution | 2004-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002041 | 400216785 | Molding | HFTD Tier 3 | Distribution | 2004-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002042 | 400216883 | High Sign | HFTD Tier 3 | Distribution | 2005-11-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002043 | 400216901 | Molding | HFTD Tier 3 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002044 | 400216926 | High Sign | HFTD Tier 3 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002045 | 400216938 | Molding | HFTD Tier 2 | Distribution | 2004-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002046 | 400216980 | Molding | HFTD Tier 2 | Distribution | 2009-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002047 | 400216984 | High Sign | HFTD Tier 2 | Distribution | 2010-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002048 | 400217094 | Guy | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002049 | 400217118 | Molding | HFTD Tier 2 | Distribution | 2005-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002050 | 400217205 | Ground | HFTD Tier 2 | Distribution | 2009-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002051 | 400217354 | Riser/Conduit | HFTD Tier 3 | Distribution | 2009-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002052 | 400217413 | High Sign | HFTD Tier 3 | Distribution | 2008-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002053 | 400217418 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002054 | 400217473 | Molding | HFTD Tier 3 | Distribution | 2003-12-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002055 | 400217614 | Riser/Conduit | HFTD Tier 2 | Distribution | 2005-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002056 | 400217736 | High Sign | HFTD Tier 3 | Distribution | 2004-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002057 | 400217838 | High Sign | HFTD Tier 2 | Distribution | 2005-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002058 | 400217885 | High Sign | HFTD Tier 3 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002059 | 400217959 | High Sign | HFTD Tier 2 | Distribution | 2009-06-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002060 | 400218043 | Molding | HFTD Tier 2 | Distribution | 2005-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002061 | 400218249 | High Sign | HFTD Tier 2 | Distribution | 2004-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002062 | 400218274 | High Sign | HFTD Tier 2 | Distribution | 2004-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002063 | 400218330 | Crossarm | HFTD Tier 2 | Distribution | 2009-10-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002064 | 400218364 | Molding | HFTD Tier 3 | Distribution | 2008-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002065 | 400218504 | High Sign | HFTD Tier 2 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002066 | 400218603 | Molding | HFTD Tier 3 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002067 | 400218634 | Molding | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002068 | 400218850 | High Sign | HFTD Tier 3 | Distribution | 2004-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002069 | 400218978 | Molding | HFTD Tier 3 | Distribution | 2004-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002070 | 400219149 | Molding | HFTD Tier 2 | Distribution | 2004-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002071 | 400219194 | Molding | HFTD Tier 3 | Distribution | 2006-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002072 | 400219640 | Molding | HFTD Tier 3 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002073 | 400219768 | Molding | HFTD Tier 3 | Distribution | 2004-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002074 | 400219801 | Riser/Conduit | HFTD Tier 3 | Distribution | 2008-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002075 | 400219836 | High Sign | HFTD Tier 2 | Distribution | 2005-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002076 | 400220262 | Molding | HFTD Tier 3 | Distribution | 2004-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002077 | 400220326 | Molding | HFTD Tier 3 | Distribution | 2004-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002078 | 400220349 | High Sign | HFTD Tier 2 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002079 | 400220373 | High Sign | HFTD Tier 3 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002080 | 400220454 | Riser/Conduit | HFTD Tier 2 | Distribution | 2004-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002081 | 400220475 | Molding | HFTD Tier 2 | Distribution | 2009-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002082 | 400220494 | Molding | HFTD Tier 2 | Distribution | 2005-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002083 | 400220696 | High Sign | HFTD Tier 3 | Distribution | 2009-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002084 | 400220750 | Guy | HFTD Tier 2 | Distribution | 2005-11-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002085 | 400220772 | Molding | HFTD Tier 3 | Distribution | 2008-11-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002086 | 400220826 | Molding | HFTD Tier 3 | Distribution | 2008-12-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002087 | 400220922 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-01-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002088 | 400220972 | Molding | HFTD Tier 3 | Distribution | 2004-08-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002089 | 400221021 | High Sign | HFTD Tier 2 | Distribution | 2001-09-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002090 | 400221223 | High Sign | HFTD Tier 2 | Distribution | 2004-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002091 | 400221515 | High Sign | HFTD Tier 2 | Distribution | 2004-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002092 | 400221539 | Hardware/Framing | HFTD Tier 3 | Distribution | 2004-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002093 | 400221563 | High Sign | HFTD Tier 3 | Distribution | 2009-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002094 | 400221895 | Molding | HFTD Tier 2 | Distribution | 2004-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002095 | 400221984 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002096 | 400222014 | High Sign | HFTD Tier 3 | Distribution | 2001-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002097 | 400222064 | Molding | HFTD Tier 3 | Distribution | 2008-11-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002098 | 400222249 | Hardware/Framing | HFTD Tier 2 | Distribution | 2009-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002099 | 400222452 | High Sign | HFTD Tier 3 | Distribution | 2004-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002100 | 400222630 | High Sign | HFTD Tier 3 | Distribution | 2004-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002101 | 400222870 | Molding | HFTD Tier 3 | Distribution | 2008-11-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002102 | 400222872 | Guy | HFTD Tier 2 | Distribution | 2004-08-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002103 | 400222887 | Guy | HFTD Tier 3 | Distribution | 2004-08-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002104 | 400222891 | High Sign | HFTD Tier 3 | Distribution | 2005-09-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002105 | 400222900 | High Sign | HFTD Tier 2 | Distribution | 2004-08-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002106 | 400222962 | Molding | HFTD Tier 2 | Distribution | 2005-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002107 | 400223159 | Molding | HFTD Tier 3 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002108 | 400223226 | High Sign | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002109 | 400223305 | High Sign | HFTD Tier 3 | Distribution | 2005-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002110 | 400223457 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-12-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002111 | 400223459 | High Sign | HFTD Tier 2 | Distribution | 2004-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002112 | 400223498 | Molding | HFTD Tier 2 | Distribution | 2004-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002113 | 400223528 | Molding | HFTD Tier 2 | Distribution | 2004-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002114 | 400223703 | Molding | HFTD Tier 3 | Distribution | 2010-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002115 | 400223735 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002116 | 400223761 | High Sign | HFTD Tier 3 | Distribution | 2004-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002117 | 400223799 | Molding | HFTD Tier 3 | Distribution | 2003-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002118 | 400223872 | Molding | HFTD Tier 3 | Distribution | 2003-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002119 | 400224053 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002120 | 400224063 | Molding | HFTD Tier 3 | Distribution | 2009-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002121 | 400224085 | Molding | HFTD Tier 3 | Distribution | 2004-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002122 | 400224122 | High Sign | HFTD Tier 2 | Distribution | 2009-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002123 | 400224126 | High Sign | HFTD Tier 3 | Distribution | 2004-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002124 | 400224348 | Molding | HFTD Tier 2 | Distribution | 2006-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002125 | 400224349 | High Sign | HFTD Tier 3 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002126 | 400224465 | Molding | HFTD Tier 3 | Distribution | 2005-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002127 | 400224502 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-09-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002128 | 400224721 | High Sign | HFTD Tier 3 | Distribution | 2009-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002129 | 400224813 | Molding | HFTD Tier 2 | Distribution | 2004-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002130 | 400224822 | High Sign | HFTD Tier 2 | Distribution | 2005-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002131 | 400224848 | High Sign | HFTD Tier 2 | Distribution | 2004-10-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002132 | 400225207 | Molding | HFTD Tier 3 | Distribution | 2009-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002133 | 400225219 | Molding | HFTD Tier 2 | Distribution | 2005-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002134 | 400225229 | Molding | HFTD Tier 2 | Distribution | 2003-11-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002135 | 400225322 | Molding | HFTD Tier 2 | Distribution | 2009-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002136 | 400225367 | High Sign | HFTD Tier 2 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002137 | 400225472 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2008-12-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002138 | 400225503 | High Sign | HFTD Tier 3 | Distribution | 2001-01-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002139 | 400225616 | High Sign | HFTD Tier 3 | Distribution | 2004-09-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002140 | 400226130 | Insulator | HFTD Tier 2 | Distribution | 2003-11-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002141 | 400226184 | Molding | HFTD Tier 2 | Distribution | 2004-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002142 | 400226377 | Guy | HFTD Tier 3 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002143 | 400226426 | High Sign | HFTD Tier 3 | Distribution | 2004-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002144 | 400226912 | High Sign | HFTD Tier 3 | Distribution | 2004-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002145 | 400226915 | High Sign | HFTD Tier 2 | Distribution | 2004-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002146 | 400226937 | High Sign | HFTD Tier 3 | Distribution | 2004-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002147 | 400226999 | High Sign | HFTD Tier 3 | Distribution | 2004-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002148 | 400227061 | Molding | HFTD Tier 2 | Distribution | 2006-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002149 | 400227093 | Molding | HFTD Tier 2 | Distribution | 2005-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002150 | 400227268 | Molding | HFTD Tier 2 | Distribution | 2005-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002151 | 400227408 | High Sign | HFTD Tier 3 | Distribution | 2004-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002152 | 400227428 | Molding | HFTD Tier 2 | Distribution | 2004-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002153 | 400227453 | Guy | HFTD Tier 3 | Distribution | 2004-08-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002154 | 400227458 | Molding | HFTD Tier 2 | Distribution | 2004-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002155 | 400227476 | Guy | HFTD Tier 3 | Distribution | 2005-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002156 | 400227617 | Guy | HFTD Tier 3 | Distribution | 2004-09-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002157 | 400227847 | Molding | HFTD Tier 2 | Distribution | 2006-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002158 | 400228193 | High Sign | HFTD Tier 2 | Distribution | 2004-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002159 | 400228199 | High Sign | HFTD Tier 2 | Distribution | 2004-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002160 | 400228202 | Molding | HFTD Tier 3 | Distribution | 2009-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002161 | 400228206 | High Sign | HFTD Tier 3 | Distribution | 2004-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002162 | 400228684 | High Sign | HFTD Tier 3 | Distribution | 2004-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002163 | 400228685 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002164 | 400228938 | Molding | HFTD Tier 3 | Distribution | 2009-10-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002165 | 400228955 | Molding | HFTD Tier 2 | Distribution | 2006-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002166 | 400228968 | Molding | HFTD Tier 2 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002167 | 400229138 | Molding | HFTD Tier 2 | Distribution | 2009-06-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002168 | 400229343 | Molding | HFTD Tier 3 | Distribution | 2005-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002169 | 400229589 | High Sign | HFTD Tier 3 | Distribution | 2001-08-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002170 | 400229677 | High Sign | HFTD Tier 2 | Distribution | 2001-08-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002171 | 400229839 | High Sign | HFTD Tier 3 | Distribution | 2004-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002172 | 400229852 | High Sign | HFTD Tier 3 | Distribution | 2004-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002173 | 400229875 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002174 | 400229914 | Molding | HFTD Tier 2 | Distribution | 2005-08-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002175 | 400229970 | High Sign | HFTD Tier 2 | Distribution | 2005-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002176 | 400230131 | Molding | HFTD Tier 2 | Distribution | 2004-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002177 | 400230142 | Molding | HFTD Tier 3 | Distribution | 2009-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002178 | 400230341 | Guy | HFTD Tier 3 | Distribution | 2009-12-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002179 | 400230429 | Guy | HFTD Tier 3 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002180 | 400230584 | High Sign | HFTD Tier 3 | Distribution | 2004-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002181 | 400230623 | High Sign | HFTD Tier 3 | Distribution | 2004-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002182 | 400230641 | Molding | HFTD Tier 2 | Distribution | 2004-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002183 | 400230679 | Insulator | HFTD Tier 2 | Distribution | 2004-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002184 | 400230681 | Molding | HFTD Tier 2 | Distribution | 2004-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002185 | 400230682 | High Sign | HFTD Tier 3 | Distribution | 2004-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002186 | 400230714 | Molding | HFTD Tier 2 | Distribution | 2004-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002187 | 400230928 | High Sign | HFTD Tier 3 | Distribution | 2004-06-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002188 | 400230981 | High Sign | HFTD Tier 3 | Distribution | 2006-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002189 | 400230986 | Molding | HFTD Tier 3 | Distribution | 2009-10-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002190 | 400231034 | Molding | HFTD Tier 2 | Distribution | 2004-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002191 | 400231295 | Hardware/Framing | HFTD Tier 2 | Distribution | 2004-09-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002192 | 400231318 | High Sign | HFTD Tier 3 | Distribution | 2008-11-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002193 | 400231350 | High Sign | HFTD Tier 2 | Distribution | 2004-08-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002194 | 400231713 | Insulator | HFTD Tier 2 | Distribution | 2005-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002195 | 400231755 | High Sign | HFTD Tier 3 | Distribution | 2004-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002196 | 400231794 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002197 | 400231925 | Molding | HFTD Tier 3 | Distribution | 2004-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002198 | 400231970 | High Sign | HFTD Tier 3 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002199 | 400231986 | High Sign | HFTD Tier 3 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002200 | 400232084 | High Sign | HFTD Tier 2 | Distribution | 2009-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002201 | 400232171 | Molding | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002202 | 400232423 | Molding | HFTD Tier 3 | Distribution | 2003-12-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002203 | 400232608 | High Sign | HFTD Tier 2 | Distribution | 2005-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002204 | 400232676 | Guy | HFTD Tier 2 | Distribution | 2005-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002205 | 400232739 | Molding | HFTD Tier 3 | Distribution | 2004-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002206 | 400232807 | Molding | HFTD Tier 3 | Distribution | 2003-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002207 | 400232833 | Guy | HFTD Tier 2 | Distribution | 2005-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002208 | 400233023 | Molding | HFTD Tier 3 | Distribution | 2006-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002209 | 400233031 | Molding | HFTD Tier 3 | Distribution | 2004-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002210 | 400233103 | Molding | HFTD Tier 3 | Distribution | 2005-04-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002211 | 400233117 | Molding | HFTD Tier 3 | Distribution | 2009-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002212 | 400233459 | High Sign | HFTD Tier 2 | Distribution | 2005-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002213 | 400233507 | High Sign | HFTD Tier 2 | Distribution | 2001-08-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002214 | 400233799 | High Sign | HFTD Tier 2 | Distribution | 2004-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002215 | 400233824 | High Sign | HFTD Tier 3 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002216 | 400234063 | High Sign | HFTD Tier 2 | Distribution | 2005-08-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002217 | 400234091 | Molding | HFTD Tier 3 | Distribution | 2009-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002218 | 400234108 | Molding | HFTD Tier 3 | Distribution | 2007-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002219 | 400234291 | Riser/Conduit | HFTD Tier 2 | Distribution | 2004-10-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002220 | 400234460 | Molding | HFTD Tier 2 | Distribution | 2009-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002221 | 400234594 | High Sign | HFTD Tier 3 | Distribution | 2004-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002222 | 400234625 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002223 | 400234657 | Molding | HFTD Tier 3 | Distribution | 2006-10-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002224 | 400234661 | High Sign | HFTD Tier 3 | Distribution | 2005-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002225 | 400234704 | Guy | HFTD Tier 2 | Distribution | 2005-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002226 | 400234720 | Molding | HFTD Tier 3 | Distribution | 2005-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002227 | 400234890 | Guy | HFTD Tier 2 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002228 | 400235034 | High Sign | HFTD Tier 2 | Distribution | 2005-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002229 | 400235074 | High Sign | HFTD Tier 2 | Distribution | 2005-08-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002230 | 400235107 | High Sign | HFTD Tier 2 | Distribution | 2005-09-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002231 | 400235124 | High Sign | HFTD Tier 3 | Distribution | 2009-12-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002232 | 400235189 | Molding | HFTD Tier 2 | Distribution | 2001-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002233 | 400235323 | High Sign | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002234 | 400235409 | High Sign | HFTD Tier 3 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002235 | 400235434 | High Sign | HFTD Tier 3 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002236 | 400235462 | Molding | HFTD Tier 3 | Distribution | 2006-10-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002237 | 400235505 | High Sign | HFTD Tier 2 | Distribution | 2005-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002238 | 400235705 | Molding | HFTD Tier 2 | Distribution | 2001-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002239 | 400235831 | Molding | HFTD Tier 2 | Distribution | 2001-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002240 | 400235886 | High Sign | HFTD Tier 3 | Distribution | 2004-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002241 | 400236130 | Guy | HFTD Tier 3 | Distribution | 2009-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002242 | 400236173 | High Sign | HFTD Tier 2 | Distribution | 2005-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002243 | 400236262 | High Sign | HFTD Tier 2 | Distribution | 2001-09-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002244 | 400236418 | High Sign | HFTD Tier 3 | Distribution | 2005-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002245 | 400236427 | High Sign | HFTD Tier 3 | Distribution | 2004-09-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002246 | 400236639 | Molding | HFTD Tier 2 | Distribution | 2004-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002247 | 400236671 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002248 | 400236674 | High Sign | HFTD Tier 2 | Distribution | 2004-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002249 | 400236823 | High Sign | HFTD Tier 3 | Distribution | 2009-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002250 | 400236864 | Molding | HFTD Tier 2 | Distribution | 2001-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002251 | 400236875 | Guy | HFTD Tier 3 | Distribution | 2005-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002252 | 400236909 | High Sign | HFTD Tier 2 | Distribution | 2005-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002253 | 400236939 | High Sign | HFTD Tier 3 | Distribution | 2004-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002254 | 400237017 | Molding | HFTD Tier 2 | Distribution | 2001-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002255 | 400237047 | Molding | HFTD Tier 2 | Distribution | 2004-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002256 | 400237058 | High Sign | HFTD Tier 2 | Distribution | 2004-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002257 | 400237127 | Molding | HFTD Tier 3 | Distribution | 2001-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002258 | 400237221 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002259 | 400237389 | High Sign | HFTD Tier 3 | Distribution | 2005-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002260 | 400237618 | Molding | HFTD Tier 3 | Distribution | 2004-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002261 | 400237838 | Molding | HFTD Tier 3 | Distribution | 2009-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002262 | 400237871 | High Sign | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002263 | 400237882 | High Sign | HFTD Tier 2 | Distribution | 2001-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002264 | 400237964 | Molding | HFTD Tier 3 | Distribution | 2008-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002265 | 400238016 | High Sign | HFTD Tier 3 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002266 | 400238027 | Molding | HFTD Tier 3 | Distribution | 2008-11-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002267 | 400238071 | Molding | HFTD Tier 2 | Distribution | 2001-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002268 | 400238269 | Molding | HFTD Tier 2 | Distribution | 2004-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002269 | 400238326 | Molding | HFTD Tier 3 | Distribution | 2006-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002270 | 400238357 | Molding | HFTD Tier 3 | Distribution | 2008-12-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002271 | 400238751 | Molding | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002272 | 400239158 | High Sign | HFTD Tier 2 | Distribution | 2009-08-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002273 | 400239233 | Molding | HFTD Tier 2 | Distribution | 2001-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002274 | 400239442 | Molding | HFTD Tier 3 | Distribution | 2009-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002275 | 400239452 | High Sign | HFTD Tier 2 | Distribution | 2004-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002276 | 400239503 | Molding | HFTD Tier 2 | Distribution | 2001-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002277 | 400239584 | Molding | HFTD Tier 2 | Distribution | 2005-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002278 | 400239605 | Molding | HFTD Tier 3 | Distribution | 2004-10-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002279 | 400239631 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002280 | 400239659 | High Sign | HFTD Tier 3 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002281 | 400239683 | High Sign | HFTD Tier 3 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002282 | 400239844 | Molding | HFTD Tier 2 | Distribution | 2001-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002283 | 400239891 | Molding | HFTD Tier 3 | Distribution | 2004-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002284 | 400239898 | High Sign | HFTD Tier 3 | Distribution | 2004-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002285 | 400239995 | Molding | HFTD Tier 3 | Distribution | 2008-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002286 | 400240060 | Molding | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002287 | 400240063 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002288 | 400240493 | Molding | HFTD Tier 3 | Distribution | 2004-01-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002289 | 400240689 | Molding | HFTD Tier 2 | Distribution | 2004-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002290 | 400240721 | High Sign | HFTD Tier 2 | Distribution | 2005-08-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002291 | 400240823 | Molding | HFTD Tier 3 | Distribution | 2004-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002292 | 400240830 | High Sign | HFTD Tier 3 | Distribution | 2004-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002293 | 400240885 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002294 | 400240889 | High Sign | HFTD Tier 3 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002295 | 400240920 | High Sign | HFTD Tier 3 | Distribution | 2001-08-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002296 | 400241075 | Hardware/Framing | HFTD Tier 3 | Distribution | 2004-10-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002297 | 400241106 | Molding | HFTD Tier 3 | Distribution | 2005-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002298 | 400241108 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2008-12-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002299 | 400241118 | High Sign | HFTD Tier 2 | Distribution | 2005-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002300 | 400241614 | High Sign | HFTD Tier 2 | Distribution | 2004-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002301 | 400241704 | Molding | HFTD Tier 3 | Distribution | 2004-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002302 | 400241810 | Molding | HFTD Tier 2 | Distribution | 2001-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002303 | 400241825 | Molding | HFTD Tier 2 | Distribution | 2001-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002304 | 400241873 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002305 | 400241922 | Molding | HFTD Tier 2 | Distribution | 2007-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002306 | 400241941 | Guy | HFTD Tier 2 | Distribution | 2005-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002307 | 400242105 | High Sign | HFTD Tier 2 | Distribution | 2005-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002308 | 400242289 | High Sign | HFTD Tier 2 | Distribution | 2004-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002309 | 400242290 | Molding | HFTD Tier 2 | Distribution | 2002-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002310 | 400242322 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-12-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002311 | 400242428 | Molding | HFTD Tier 3 | Distribution | 2008-10-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002312 | 400242544 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002313 | 400242575 | High Sign | HFTD Tier 2 | Distribution | 2005-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002314 | 400242830 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002315 | 400243046 | Molding | HFTD Tier 2 | Distribution | 2005-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002316 | 400243179 | High Sign | HFTD Tier 2 | Distribution | 2008-11-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002317 | 400243239 | Molding | HFTD Tier 3 | Distribution | 2009-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002318 | 400243320 | Molding | HFTD Tier 2 | Distribution | 2004-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002319 | 400243432 | High Sign | HFTD Tier 2 | Distribution | 2005-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002320 | 400243520 | High Sign | HFTD Tier 2 | Distribution | 2001-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002321 | 400243524 | High Sign | HFTD Tier 3 | Distribution | 2001-08-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002322 | 400243595 | Molding | HFTD Tier 2 | Distribution | 2002-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002323 | 400243596 | Molding | HFTD Tier 2 | Distribution | 2005-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002324 | 400243676 | High Sign | HFTD Tier 3 | Distribution | 2005-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002325 | 400243758 | Molding | HFTD Tier 2 | Distribution | 2004-10-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002326 | 400243773 | Molding | HFTD Tier 3 | Distribution | 2003-12-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002327 | 400243849 | Molding | HFTD Tier 3 | Distribution | 2010-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002328 | 400243900 | High Sign | HFTD Tier 3 | Distribution | 2004-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002329 | 400243905 | High Sign | HFTD Tier 2 | Distribution | 2004-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002330 | 400244265 | Molding | HFTD Tier 2 | Distribution | 2002-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002331 | 400244313 | High Sign | HFTD Tier 3 | Distribution | 2010-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002332 | 400244441 | High Sign | HFTD Tier 2 | Distribution | 2005-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002333 | 400244471 | Molding | HFTD Tier 3 | Distribution | 2009-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002334 | 400244494 | Molding | HFTD Tier 3 | Distribution | 2005-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002335 | 400244535 | Guy | HFTD Tier 2 | Distribution | 2009-11-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002336 | 400244548 | Structure/Equip Itself | HFTD Tier 3 | Transmission | 2007-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002337 | 400244677 | Guy | HFTD Tier 2 | Distribution | 2005-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002338 | 400244906 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002339 | 400244930 | Molding | HFTD Tier 3 | Distribution | 2010-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002340 | 400244973 | High Sign | HFTD Tier 3 | Distribution | 2002-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002341 | 400245200 | Molding | HFTD Tier 2 | Distribution | 2009-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002342 | 400245217 | High Sign | HFTD Tier 2 | Distribution | 2003-11-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002343 | 400245290 | Molding | HFTD Tier 3 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002344 | 400245428 | High Sign | HFTD Tier 2 | Distribution | 2004-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002345 | 400245595 | Molding | HFTD Tier 2 | Distribution | 2010-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002346 | 400245664 | Molding | HFTD Tier 3 | Distribution | 2004-09-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002347 | 400246209 | High Sign | HFTD Tier 3 | Distribution | 2004-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002348 | 400246229 | High Sign | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002349 | 400246379 | Molding | HFTD Tier 3 | Distribution | 2004-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002350 | 400246453 | High Sign | HFTD Tier 3 | Distribution | 2005-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002351 | 400246515 | High Sign | HFTD Tier 2 | Distribution | 2001-08-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002352 | 400246608 | High Sign | HFTD Tier 2 | Distribution | 2010-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002353 | 400246609 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-12-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002354 | 400246667 | High Sign | HFTD Tier 3 | Distribution | 2005-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002355 | 400246890 | Molding | HFTD Tier 2 | Distribution | 2004-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002356 | 400246900 | High Sign | HFTD Tier 2 | Distribution | 2004-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002357 | 400246927 | High Sign | HFTD Tier 3 | Distribution | 2008-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002358 | 400247047 | High Sign | HFTD Tier 2 | Distribution | 2004-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002359 | 400247083 | High Sign | HFTD Tier 2 | Distribution | 2005-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002360 | 400247133 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002361 | 400247392 | High Sign | HFTD Tier 2 | Distribution | 2004-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002362 | 400247398 | Molding | HFTD Tier 3 | Distribution | 2010-01-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002363 | 400247416 | High Sign | HFTD Tier 2 | Distribution | 2004-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002364 | 400247518 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002365 | 400247552 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002366 | 400247558 | High Sign | HFTD Tier 3 | Distribution | 2004-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002367 | 400247566 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002368 | 400247625 | High Sign | HFTD Tier 2 | Distribution | 2003-11-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002369 | 400247664 | High Sign | HFTD Tier 3 | Distribution | 2005-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002370 | 400247706 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002371 | 400247718 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002372 | 400247761 | Molding | HFTD Tier 3 | Distribution | 2003-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002373 | 400247770 | High Sign | HFTD Tier 3 | Distribution | 2004-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002374 | 400247819 | High Sign | HFTD Tier 3 | Distribution | 2004-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002375 | 400247900 | High Sign | HFTD Tier 3 | Distribution | 2005-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002376 | 400247964 | Guy | HFTD Tier 3 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002377 | 400247969 | High Sign | HFTD Tier 3 | Distribution | 2004-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002378 | 400248060 | High Sign | HFTD Tier 3 | Distribution | 2006-12-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002379 | 400248197 | High Sign | HFTD Tier 2 | Distribution | 2005-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002380 | 400248398 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002381 | 400248411 | High Sign | HFTD Tier 3 | Distribution | 2010-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002382 | 400248427 | High Sign | HFTD Tier 3 | Distribution | 2004-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002383 | 400248793 | Molding | HFTD Tier 3 | Distribution | 2003-12-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002384 | 400248868 | High Sign | HFTD Tier 2 | Distribution | 2004-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002385 | 400249002 | High Sign | HFTD Tier 3 | Distribution | 2009-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002386 | 400249111 | Molding | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002387 | 400249245 | High Sign | HFTD Tier 2 | Distribution | 2004-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002388 | 400249373 | High Sign | HFTD Tier 2 | Distribution | 2001-09-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002389 | 400249455 | Molding | HFTD Tier 2 | Distribution | 2005-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002390 | 400249488 | High Sign | HFTD Tier 2 | Distribution | 2004-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002391 | 400249565 | Molding | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002392 | 400249639 | Molding | HFTD Tier 3 | Distribution | 2003-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002393 | 400249659 | Molding | HFTD Tier 2 | Distribution | 2007-03-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002394 | 400249875 | Molding | HFTD Tier 3 | Distribution | 2005-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002395 | 400249904 | Guy | HFTD Tier 3 | Distribution | 2005-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002396 | 400249914 | Guy | HFTD Tier 2 | Distribution | 2002-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002397 | 400249950 | Molding | HFTD Tier 3 | Distribution | 2009-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002398 | 400250128 | Molding | HFTD Tier 3 | Distribution | 2004-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002399 | 400250183 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002400 | 400250231 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002401 | 400250274 | High Sign | HFTD Tier 2 | Distribution | 2004-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002402 | 400250283 | High Sign | HFTD Tier 3 | Distribution | 2005-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002403 | 400250288 | Molding | HFTD Tier 3 | Distribution | 2005-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002404 | 400250316 | High Sign | HFTD Tier 2 | Distribution | 2004-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002405 | 400250354 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002406 | 400250355 | High Sign | HFTD Tier 2 | Distribution | 2004-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002407 | 400250375 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002408 | 400250517 | High Sign | HFTD Tier 3 | Distribution | 2004-10-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002409 | 400250542 | Molding | HFTD Tier 3 | Distribution | 2004-10-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002410 | 400250685 | High Sign | HFTD Tier 2 | Distribution | 2007-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002411 | 400250838 | Molding | HFTD Tier 3 | Distribution | 2008-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002412 | 400251062 | High Sign | HFTD Tier 2 | Distribution | 2010-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002413 | 400251190 | Riser/Conduit | HFTD Tier 3 | Distribution | 2004-01-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002414 | 400251294 | High Sign | HFTD Tier 3 | Distribution | 2009-12-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002415 | 400251314 | High Sign | HFTD Tier 2 | Distribution | 2004-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002416 | 400251333 | High Sign | HFTD Tier 3 | Distribution | 2004-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002417 | 400251612 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002418 | 400251615 | High Sign | HFTD Tier 3 | Distribution | 2008-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002419 | 400251633 | Guy | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002420 | 400251722 | Molding | HFTD Tier 3 | Distribution | 2004-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002421 | 400251796 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002422 | 400251810 | Molding | HFTD Tier 2 | Distribution | 2003-11-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002423 | 400251847 | Molding | HFTD Tier 3 | Distribution | 2006-11-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002424 | 400251929 | Molding | HFTD Tier 3 | Distribution | 2004-10-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002425 | 400252141 | High Sign | HFTD Tier 2 | Distribution | 2001-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002426 | 400252164 | Molding | HFTD Tier 2 | Distribution | 2005-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002427 | 400252213 | High Sign | HFTD Tier 2 | Distribution | 2001-09-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002428 | 400252378 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-04-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002429 | 400252430 | High Sign | HFTD Tier 3 | Distribution | 2008-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002430 | 400252464 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-12-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002431 | 400252685 | High Sign | HFTD Tier 2 | Distribution | 2004-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002432 | 400252811 | High Sign | HFTD Tier 3 | Distribution | 2003-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002433 | 400252841 | High Sign | HFTD Tier 2 | Distribution | 2001-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002434 | 400252876 | High Sign | HFTD Tier 3 | Distribution | 2006-11-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002435 | 400252952 | Molding | HFTD Tier 2 | Distribution | 2005-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002436 | 400252963 | High Sign | HFTD Tier 3 | Distribution | 2004-09-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002437 | 400253021 | High Sign | HFTD Tier 2 | Distribution | 2005-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002438 | 400253124 | High Sign | HFTD Tier 3 | Distribution | 2008-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002439 | 400253127 | High Sign | HFTD Tier 2 | Distribution | 2001-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002440 | 400253212 | Molding | HFTD Tier 3 | Distribution | 2009-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002441 | 400253429 | Molding | HFTD Tier 3 | Distribution | 2005-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002442 | 400253492 | Molding | HFTD Tier 2 | Distribution | 2004-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002443 | 400253502 | Molding | HFTD Tier 3 | Distribution | 2009-12-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002444 | 400253530 | Cable/Conductor | HFTD Tier 3 | Distribution | 2008-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002445 | 400253559 | High Sign | HFTD Tier 2 | Distribution | 2004-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002446 | 400253582 | Molding | HFTD Tier 3 | Distribution | 2008-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002447 | 400253629 | High Sign | HFTD Tier 2 | Distribution | 2004-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002448 | 400253726 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002449 | 400253750 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002450 | 400253760 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002451 | 400253799 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002452 | 400253843 | Molding | HFTD Tier 3 | Distribution | 2009-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002453 | 400253967 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002454 | 400254116 | High Sign | HFTD Tier 2 | Distribution | 2001-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002455 | 400254256 | High Sign | HFTD Tier 3 | Distribution | 2004-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002456 | 400254280 | Molding | HFTD Tier 2 | Distribution | 2007-03-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002457 | 400254330 | High Sign | HFTD Tier 3 | Distribution | 2004-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002458 | 400254339 | Molding | HFTD Tier 3 | Distribution | 2004-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002459 | 400254346 | High Sign | HFTD Tier 2 | Distribution | 2009-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002460 | 400254433 | Molding | HFTD Tier 3 | Distribution | 2004-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002461 | 400254499 | Molding | HFTD Tier 3 | Distribution | 2008-12-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002462 | 400254691 | High Sign | HFTD Tier 2 | Distribution | 2001-09-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002463 | 400254828 | Molding | HFTD Tier 2 | Distribution | 2010-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002464 | 400254831 | Molding | HFTD Tier 2 | Distribution | 2004-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002465 | 400254965 | High Sign | HFTD Tier 2 | Distribution | 2004-12-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002466 | 400254974 | Molding | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002467 | 400254976 | High Sign | HFTD Tier 2 | Distribution | 2004-12-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002468 | 400255033 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2003-12-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002469 | 400255286 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002470 | 400255351 | High Sign | HFTD Tier 2 | Distribution | 2004-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002471 | 400255413 | High Sign | HFTD Tier 2 | Distribution | 2004-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002472 | 400255415 | Molding | HFTD Tier 2 | Distribution | 2004-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002473 | 400255673 | High Sign | HFTD Tier 3 | Distribution | 2004-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002474 | 400256003 | Molding | HFTD Tier 2 | Distribution | 2010-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002475 | 400256156 | Molding | HFTD Tier 2 | Distribution | 2010-01-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002476 | 400256180 | High Sign | HFTD Tier 2 | Distribution | 2004-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002477 | 400256194 | Molding | HFTD Tier 3 | Distribution | 2005-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002478 | 400256216 | Molding | HFTD Tier 3 | Distribution | 2005-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002479 | 400256462 | Molding | HFTD Tier 3 | Distribution | 2010-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002480 | 400256475 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002481 | 400256612 | Molding | HFTD Tier 3 | Distribution | 2004-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002482 | 400256777 | Molding | HFTD Tier 3 | Distribution | 2010-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002483 | 400256805 | Molding | HFTD Tier 2 | Distribution | 2004-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002484 | 400256843 | High Sign | HFTD Tier 2 | Distribution | 2004-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002485 | 400257039 | Molding | HFTD Tier 3 | Distribution | 2007-02-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002486 | 400257099 | High Sign | HFTD Tier 3 | Distribution | 2004-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002487 | 400257148 | Guy | HFTD Tier 3 | Distribution | 2005-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002488 | 400257157 | Molding | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002489 | 400257194 | Molding | HFTD Tier 2 | Distribution | 2004-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002490 | 400257242 | Molding | HFTD Tier 2 | Distribution | 2004-09-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002491 | 400257264 | High Sign | HFTD Tier 2 | Distribution | 2005-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002492 | 400257334 | High Sign | HFTD Tier 2 | Distribution | 2004-05-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002493 | 400257418 | Molding | HFTD Tier 2 | Distribution | 2002-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002494 | 400257725 | Molding | HFTD Tier 2 | Distribution | 2005-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002495 | 400257813 | Molding | HFTD Tier 3 | Distribution | 2009-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002496 | 400257906 | High Sign | HFTD Tier 3 | Distribution | 2010-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002497 | 400257922 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002498 | 400257945 | Molding | HFTD Tier 2 | Distribution | 2004-12-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002499 | 400258219 | Molding | HFTD Tier 3 | Distribution | 2008-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002500 | 400258232 | High Sign | HFTD Tier 2 | Distribution | 2005-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002501 | 400258270 | High Sign | HFTD Tier 3 | Distribution | 2004-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002502 | 400258452 | High Sign | HFTD Tier 3 | Distribution | 2004-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002503 | 400258550 | High Sign | HFTD Tier 2 | Distribution | 2003-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002504 | 400258557 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002505 | 400258712 | High Sign | HFTD Tier 2 | Distribution | 2001-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002506 | 400258864 | High Sign | HFTD Tier 3 | Distribution | 2004-09-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002507 | 400258888 | High Sign | HFTD Tier 3 | Distribution | 2004-09-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002508 | 400258953 | High Sign | HFTD Tier 3 | Distribution | 2005-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002509 | 400259126 | Molding | HFTD Tier 3 | Distribution | 2004-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002510 | 400259143 | High Sign | HFTD Tier 3 | Distribution | 2004-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002511 | 400259183 | Molding | HFTD Tier 2 | Distribution | 2004-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002512 | 400259186 | Molding | HFTD Tier 3 | Distribution | 2005-10-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002513 | 400259197 | High Sign | HFTD Tier 2 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002514 | 400259219 | High Sign | HFTD Tier 2 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002515 | 400259227 | Molding | HFTD Tier 2 | Distribution | 2004-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002516 | 400259242 | High Sign | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002517 | 400259322 | Hardware/Framing | HFTD Tier 3 | Distribution | 2004-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002518 | 400259463 | Riser/Conduit | HFTD Tier 3 | Distribution | 2004-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002519 | 400259568 | Guy | HFTD Tier 2 | Distribution | 2003-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002520 | 400259589 | High Sign | HFTD Tier 2 | Distribution | 2005-08-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002521 | 400259663 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002522 | 400259802 | Molding | HFTD Tier 2 | Distribution | 2009-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002523 | 400260110 | High Sign | HFTD Tier 2 | Distribution | 2005-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002524 | 400260118 | High Sign | HFTD Tier 2 | Distribution | 2005-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002525 | 400260430 | Molding | HFTD Tier 2 | Distribution | 2002-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002526 | 400260443 | High Sign | HFTD Tier 2 | Distribution | 2002-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002527 | 400260552 | Molding | HFTD Tier 3 | Distribution | 2004-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002528 | 400260649 | High Sign | HFTD Tier 3 | Distribution | 2004-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002529 | 400260783 | Molding | HFTD Tier 3 | Distribution | 2004-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002530 | 400260849 | Molding | HFTD Tier 3 | Distribution | 2009-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002531 | 400261091 | High Sign | HFTD Tier 3 | Distribution | 2004-09-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002532 | 400261193 | Hardware/Framing | HFTD Tier 2 | Distribution | 2001-01-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002533 | 400261243 | High Sign | HFTD Tier 2 | Distribution | 2007-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002534 | 400261296 | Molding | HFTD Tier 2 | Distribution | 2004-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002535 | 400261350 | Molding | HFTD Tier 3 | Distribution | 2004-09-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002536 | 400261476 | Molding | HFTD Tier 3 | Distribution | 2004-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002537 | 400261526 | High Sign | HFTD Tier 3 | Distribution | 2004-09-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002538 | 400261768 | High Sign | HFTD Tier 3 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002539 | 400261893 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002540 | 400261965 | High Sign | HFTD Tier 2 | Distribution | 2009-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002541 | 400262029 | High Sign | HFTD Tier 3 | Distribution | 2009-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002542 | 400262054 | High Sign | HFTD Tier 3 | Distribution | 2009-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002543 | 400262223 | Molding | HFTD Tier 2 | Distribution | 2002-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002544 | 400262338 | High Sign | HFTD Tier 3 | Distribution | 2009-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002545 | 400262348 | High Sign | HFTD Tier 2 | Distribution | 2003-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002546 | 400262389 | High Sign | HFTD Tier 3 | Distribution | 2009-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002547 | 400262617 | Molding | HFTD Tier 3 | Distribution | 2009-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002548 | 400262693 | High Sign | HFTD Tier 3 | Distribution | 2005-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002549 | 400262725 | Molding | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002550 | 400262772 | Molding | HFTD Tier 3 | Distribution | 2004-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002551 | 400262780 | High Sign | HFTD Tier 3 | Distribution | 2001-09-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002552 | 400262817 | Molding | HFTD Tier 3 | Distribution | 2009-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002553 | 400263172 | Molding | HFTD Tier 3 | Distribution | 2005-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002554 | 400263296 | Molding | HFTD Tier 2 | Distribution | 2005-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002555 | 400263396 | Guy | HFTD Tier 2 | Distribution | 2003-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002556 | 400263491 | High Sign | HFTD Tier 2 | Distribution | 2003-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002557 | 400263649 | High Sign | HFTD Tier 3 | Distribution | 2004-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002558 | 400263694 | High Sign | HFTD Tier 3 | Distribution | 2009-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002559 | 400263789 | High Sign | HFTD Tier 2 | Distribution | 2003-11-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002560 | 400264049 | Guy | HFTD Tier 3 | Distribution | 2008-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002561 | 400264090 | Molding | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002562 | 400264094 | High Sign | HFTD Tier 2 | Distribution | 2004-05-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002563 | 400264357 | Molding | HFTD Tier 2 | Distribution | 2010-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002564 | 400264462 | Guy | HFTD Tier 2 | Distribution | 2003-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002565 | 400264578 | Molding | HFTD Tier 3 | Distribution | 2010-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002566 | 400264703 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002567 | 400264736 | Molding | HFTD Tier 2 | Distribution | 2006-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002568 | 400264874 | High Sign | HFTD Tier 3 | Distribution | 2009-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002569 | 400265023 | High Sign | HFTD Tier 2 | Distribution | 2006-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002570 | 400265163 | High Sign | HFTD Tier 3 | Distribution | 2004-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002571 | 400265180 | High Sign | HFTD Tier 3 | Distribution | 2004-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002572 | 400265200 | Molding | HFTD Tier 2 | Distribution | 2004-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002573 | 400265331 | Molding | HFTD Tier 3 | Distribution | 2010-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002574 | 400265450 | High Sign | HFTD Tier 3 | Distribution | 2009-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002575 | 400265516 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002576 | 400265556 | High Sign | HFTD Tier 2 | Distribution | 2005-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002577 | 400265707 | High Sign | HFTD Tier 2 | Distribution | 2001-09-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002578 | 400265915 | Molding | HFTD Tier 2 | Distribution | 2005-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002579 | 400265924 | Hardware/Framing | HFTD Tier 3 | Distribution | 2004-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002580 | 400266041 | High Sign | HFTD Tier 2 | Distribution | 2004-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002581 | 400266330 | High Sign | HFTD Tier 2 | Distribution | 2009-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002582 | 400266451 | Molding | HFTD Tier 2 | Distribution | 2005-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002583 | 400266497 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2005-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002584 | 400266509 | High Sign | HFTD Tier 3 | Distribution | 2004-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002585 | 400266563 | Molding | HFTD Tier 3 | Distribution | 2010-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002586 | 400266630 | High Sign | HFTD Tier 3 | Distribution | 2005-09-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002587 | 400266734 | Molding | HFTD Tier 2 | Distribution | 2009-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002588 | 400266748 | High Sign | HFTD Tier 3 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002589 | 400266882 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002590 | 400266911 | Molding | HFTD Tier 3 | Distribution | 2009-10-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002591 | 400266914 | Molding | HFTD Tier 3 | Distribution | 2003-12-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002592 | 400266942 | Molding | HFTD Tier 2 | Distribution | 2009-04-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002593 | 400266957 | High Sign | HFTD Tier 2 | Distribution | 2005-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002594 | 400267159 | High Sign | HFTD Tier 2 | Distribution | 2001-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002595 | 400267374 | Molding | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002596 | 400267378 | High Sign | HFTD Tier 3 | Distribution | 2009-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002597 | 400267474 | High Sign | HFTD Tier 2 | Distribution | 2005-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002598 | 400267809 | Riser/Conduit | HFTD Tier 3 | Distribution | 2004-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002599 | 400267934 | Molding | HFTD Tier 2 | Distribution | 2002-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002600 | 400267993 | Molding | HFTD Tier 3 | Distribution | 2005-09-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002601 | 400268129 | Molding | HFTD Tier 3 | Distribution | 2008-12-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002602 | 400268195 | High Sign | HFTD Tier 3 | Distribution | 2006-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002603 | 400268197 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002604 | 400268279 | Molding | HFTD Tier 2 | Distribution | 2010-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002605 | 400268395 | Molding | HFTD Tier 3 | Distribution | 2004-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002606 | 400268666 | High Sign | HFTD Tier 3 | Distribution | 2008-08-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002607 | 400268836 | Molding | HFTD Tier 2 | Distribution | 2004-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002608 | 400268841 | Molding | HFTD Tier 2 | Distribution | 2004-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002609 | 400268891 | Molding | HFTD Tier 2 | Distribution | 2010-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002610 | 400268934 | Molding | HFTD Tier 3 | Distribution | 2005-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002611 | 400268951 | High Sign | HFTD Tier 2 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002612 | 400269021 | High Sign | HFTD Tier 2 | Distribution | 2005-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002613 | 400269464 | High Sign | HFTD Tier 2 | Distribution | 2009-10-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002614 | 400269597 | High Sign | HFTD Tier 3 | Distribution | 2005-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002615 | 400269603 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2008-11-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002616 | 400269680 | High Sign | HFTD Tier 2 | Distribution | 2005-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002617 | 400269914 | Molding | HFTD Tier 3 | Distribution | 2004-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002618 | 400269917 | Molding | HFTD Tier 2 | Distribution | 2006-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002619 | 400269975 | Guy | HFTD Tier 3 | Distribution | 2010-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002620 | 400270033 | Molding | HFTD Tier 3 | Distribution | 2007-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002621 | 400270110 | Hardware/Framing | HFTD Tier 2 | Distribution | 2009-12-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002622 | 400270140 | High Sign | HFTD Tier 2 | Distribution | 2004-05-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002623 | 400270285 | Molding | HFTD Tier 3 | Distribution | 2004-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002624 | 400270299 | Cable/Conductor | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002625 | 400270333 | Guy | HFTD Tier 3 | Distribution | 2005-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002626 | 400270430 | Molding | HFTD Tier 2 | Distribution | 2009-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002627 | 400270482 | High Sign | HFTD Tier 3 | Distribution | 2006-12-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002628 | 400270541 | Molding | HFTD Tier 2 | Distribution | 2004-09-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002629 | 400270604 | High Sign | HFTD Tier 3 | Distribution | 2004-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002630 | 400270635 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-08-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002631 | 400270643 | High Sign | HFTD Tier 3 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002632 | 400270653 | High Sign | HFTD Tier 3 | Distribution | 2009-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002633 | 400270921 | High Sign | HFTD Tier 2 | Distribution | 2004-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002634 | 400271067 | High Sign | HFTD Tier 2 | Distribution | 2003-11-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002635 | 400271163 | Molding | HFTD Tier 3 | Distribution | 2003-11-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002636 | 400271185 | High Sign | HFTD Tier 2 | Distribution | 2004-05-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002637 | 400271213 | Molding | HFTD Tier 2 | Distribution | 2006-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002638 | 400271247 | Molding | HFTD Tier 3 | Distribution | 2004-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002639 | 400271313 | Molding | HFTD Tier 3 | Distribution | 2010-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002640 | 400271769 | High Sign | HFTD Tier 3 | Distribution | 2004-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002641 | 400271948 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-11-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002642 | 400271997 | High Sign | HFTD Tier 3 | Distribution | 2009-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002643 | 400272027 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002644 | 400272162 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002645 | 400272424 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002646 | 400272469 | Guy | HFTD Tier 2 | Distribution | 2004-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002647 | 400272548 | Molding | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002648 | 400272573 | High Sign | HFTD Tier 3 | Distribution | 2009-10-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002649 | 400272758 | High Sign | HFTD Tier 3 | Distribution | 2004-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002650 | 400272883 | High Sign | HFTD Tier 3 | Distribution | 2006-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002651 | 400272898 | Molding | HFTD Tier 2 | Distribution | 2010-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002652 | 400272913 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002653 | 400272925 | Molding | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002654 | 400273023 | Molding | HFTD Tier 3 | Distribution | 2007-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002655 | 400273053 | Guy | HFTD Tier 3 | Distribution | 2004-12-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002656 | 400273393 | Molding | HFTD Tier 3 | Distribution | 2009-11-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002657 | 400273718 | High Sign | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002658 | 400273745 | Molding | HFTD Tier 2 | Distribution | 2004-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002659 | 400273748 | High Sign | HFTD Tier 2 | Distribution | 2004-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002660 | 400273886 | Molding | HFTD Tier 3 | Distribution | 2004-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002661 | 400274085 | High Sign | HFTD Tier 2 | Distribution | 2004-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002662 | 400274162 | Molding | HFTD Tier 3 | Distribution | 2009-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002663 | 400274211 | High Sign | HFTD Tier 2 | Distribution | 2005-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002664 | 400274229 | High Sign | HFTD Tier 3 | Distribution | 2004-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002665 | 400274314 | Ground | HFTD Tier 3 | Distribution | 2004-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002666 | 400274419 | Guy | HFTD Tier 2 | Distribution | 2005-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002667 | 400274563 | High Sign | HFTD Tier 3 | Distribution | 2005-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002668 | 400274651 | High Sign | HFTD Tier 3 | Distribution | 2005-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002669 | 400275004 | High Sign | HFTD Tier 3 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002670 | 400275035 | High Sign | HFTD Tier 3 | Distribution | 2005-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002671 | 400275056 | Molding | HFTD Tier 3 | Distribution | 2004-07-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002672 | 400275175 | High Sign | HFTD Tier 2 | Distribution | 2001-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002673 | 400275532 | Molding | HFTD Tier 3 | Distribution | 2004-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002674 | 400275860 | High Sign | HFTD Tier 2 | Distribution | 2005-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002675 | 400275866 | Guy | HFTD Tier 3 | Distribution | 2005-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002676 | 400275920 | Molding | HFTD Tier 3 | Distribution | 2008-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002677 | 400276088 | High Sign | HFTD Tier 2 | Distribution | 2007-03-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002678 | 400276180 | Molding | HFTD Tier 3 | Distribution | 2004-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002679 | 400276552 | Molding | HFTD Tier 2 | Distribution | 2009-04-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002680 | 400276585 | High Sign | HFTD Tier 2 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002681 | 400276669 | High Sign | HFTD Tier 3 | Distribution | 2006-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002682 | 400276699 | Molding | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002683 | 400276716 | Molding | HFTD Tier 3 | Distribution | 2008-11-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002684 | 400276731 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-11-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002685 | 400276810 | High Sign | HFTD Tier 2 | Distribution | 2004-04-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002686 | 400277063 | Molding | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002687 | 400277149 | Molding | HFTD Tier 2 | Distribution | 2005-08-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002688 | 400277197 | High Sign | HFTD Tier 2 | Distribution | 2005-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002689 | 400277232 | Molding | HFTD Tier 3 | Distribution | 2004-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002690 | 400277329 | Molding | HFTD Tier 3 | Distribution | 2004-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002691 | 400277374 | High Sign | HFTD Tier 2 | Distribution | 2005-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002692 | 400277430 | Molding | HFTD Tier 3 | Distribution | 2004-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002693 | 400277486 | High Sign | HFTD Tier 2 | Distribution | 2004-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002694 | 400277556 | Molding | HFTD Tier 2 | Distribution | 2007-05-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002695 | 400277824 | Molding | HFTD Tier 3 | Distribution | 2003-12-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002696 | 400278002 | Molding | HFTD Tier 2 | Distribution | 2001-10-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002697 | 400278214 | High Sign | HFTD Tier 2 | Distribution | 2005-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002698 | 400278282 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002699 | 400278296 | High Sign | HFTD Tier 3 | Distribution | 2010-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002700 | 400278390 | Molding | HFTD Tier 3 | Distribution | 2002-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002701 | 400278393 | Molding | HFTD Tier 2 | Distribution | 2005-10-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002702 | 400278474 | High Sign | HFTD Tier 2 | Distribution | 2005-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002703 | 400278488 | Molding | HFTD Tier 3 | Distribution | 2005-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002704 | 400278600 | Molding | HFTD Tier 2 | Distribution | 2007-05-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002705 | 400278638 | High Sign | HFTD Tier 2 | Distribution | 2002-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002706 | 400278851 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-01-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002707 | 400278965 | Molding | HFTD Tier 3 | Distribution | 2010-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002708 | 400279116 | High Sign | HFTD Tier 2 | Distribution | 2003-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002709 | 400279171 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002710 | 400279211 | High Sign | HFTD Tier 2 | Distribution | 2001-01-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002711 | 400279224 | High Sign | HFTD Tier 2 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002712 | 400279393 | High Sign | HFTD Tier 2 | Distribution | 2004-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002713 | 400279542 | High Sign | HFTD Tier 2 | Distribution | 2009-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002714 | 400279611 | Molding | HFTD Tier 2 | Distribution | 2005-08-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002715 | 400279704 | Molding | HFTD Tier 3 | Distribution | 2005-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002716 | 400279925 | High Sign | HFTD Tier 2 | Distribution | 2003-11-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002717 | 400279985 | Molding | HFTD Tier 3 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002718 | 400280118 | High Sign | HFTD Tier 2 | Distribution | 2004-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002719 | 400280182 | High Sign | HFTD Tier 2 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002720 | 400280206 | High Sign | HFTD Tier 2 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002721 | 400280281 | High Sign | HFTD Tier 3 | Distribution | 2004-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002722 | 400280306 | High Sign | HFTD Tier 3 | Distribution | 2004-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002723 | 400280460 | High Sign | HFTD Tier 3 | Distribution | 2005-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002724 | 400280488 | Guy | HFTD Tier 2 | Distribution | 2007-03-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002725 | 400280535 | High Sign | HFTD Tier 2 | Distribution | 2004-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002726 | 400280575 | High Sign | HFTD Tier 2 | Distribution | 2005-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002727 | 400280837 | Molding | HFTD Tier 3 | Distribution | 2007-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002728 | 400280864 | Molding | HFTD Tier 3 | Distribution | 2004-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002729 | 400280959 | Guy | HFTD Tier 3 | Distribution | 2005-09-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002730 | 400281280 | Molding | HFTD Tier 2 | Distribution | 2004-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002731 | 400281290 | Molding | HFTD Tier 3 | Distribution | 2007-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002732 | 400281329 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2005-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002733 | 400281370 | Molding | HFTD Tier 3 | Distribution | 2009-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002734 | 400281386 | High Sign | HFTD Tier 3 | Distribution | 2004-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002735 | 400281453 | High Sign | HFTD Tier 2 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002736 | 400281471 | High Sign | HFTD Tier 3 | Distribution | 2005-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002737 | 400281505 | High Sign | HFTD Tier 2 | Distribution | 2004-05-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002738 | 400281524 | High Sign | HFTD Tier 2 | Distribution | 2005-08-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002739 | 400281539 | Molding | HFTD Tier 3 | Distribution | 2004-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002740 | 400281746 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-11-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002741 | 400281902 | High Sign | HFTD Tier 2 | Distribution | 2005-09-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002742 | 400282033 | Molding | HFTD Tier 3 | Distribution | 2010-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002743 | 400282064 | High Sign | HFTD Tier 3 | Distribution | 2003-12-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002744 | 400282360 | High Sign | HFTD Tier 3 | Distribution | 2004-10-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002745 | 400282422 | High Sign | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002746 | 400282441 | High Sign | HFTD Tier 2 | Distribution | 2008-09-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002747 | 400282502 | High Sign | HFTD Tier 2 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002748 | 400282549 | Molding | HFTD Tier 2 | Distribution | 2005-08-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002749 | 400282598 | Molding | HFTD Tier 3 | Distribution | 2007-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002750 | 400282676 | High Sign | HFTD Tier 2 | Distribution | 2004-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002751 | 400282737 | Guy | HFTD Tier 3 | Distribution | 2009-10-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002752 | 400282862 | High Sign | HFTD Tier 2 | Distribution | 2004-10-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002753 | 400283010 | Molding | HFTD Tier 3 | Distribution | 2009-11-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002754 | 400283270 | High Sign | HFTD Tier 2 | Distribution | 2009-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002755 | 400283444 | High Sign | HFTD Tier 3 | Distribution | 2007-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002756 | 400283495 | High Sign | HFTD Tier 3 | Distribution | 2008-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002757 | 400283505 | Molding | HFTD Tier 3 | Distribution | 2006-12-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002758 | 400283639 | Molding | HFTD Tier 2 | Distribution | 2004-12-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002759 | 400283771 | Molding | HFTD Tier 3 | Distribution | 2009-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002760 | 400283775 | High Sign | HFTD Tier 2 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002761 | 400283800 | High Sign | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002762 | 400283822 | High Sign | HFTD Tier 2 | Distribution | 2005-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002763 | 400283836 | High Sign | HFTD Tier 3 | Distribution | 2003-12-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002764 | 400283870 | High Sign | HFTD Tier 2 | Distribution | 2005-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002765 | 400283916 | High Sign | HFTD Tier 3 | Distribution | 2009-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002766 | 400283941 | High Sign | HFTD Tier 2 | Distribution | 2004-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002767 | 400284004 | Guy | HFTD Tier 3 | Distribution | 2005-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002768 | 400284011 | Molding | HFTD Tier 2 | Distribution | 2009-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002769 | 400284151 | High Sign | HFTD Tier 2 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002770 | 400284164 | Molding | HFTD Tier 2 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002771 | 400284200 | Riser/Conduit | HFTD Tier 3 | Distribution | 2005-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002772 | 400284350 | Molding | HFTD Tier 2 | Distribution | 2009-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002773 | 400284553 | Molding | HFTD Tier 3 | Distribution | 2007-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002774 | 400284622 | High Sign | HFTD Tier 2 | Distribution | 2004-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002775 | 400284681 | Molding | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002776 | 400284773 | High Sign | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002777 | 400284886 | Molding | HFTD Tier 3 | Distribution | 2003-12-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002778 | 400285149 | High Sign | HFTD Tier 2 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002779 | 400285260 | Hardware/Framing | HFTD Tier 3 | Distribution | 2004-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002780 | 400285329 | High Sign | HFTD Tier 2 | Distribution | 2004-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002781 | 400285507 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002782 | 400285656 | Molding | HFTD Tier 3 | Distribution | 2004-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002783 | 400285667 | High Sign | HFTD Tier 3 | Distribution | 2009-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002784 | 400285912 | High Sign | HFTD Tier 2 | Distribution | 2004-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002785 | 400285937 | High Sign | HFTD Tier 2 | Distribution | 2004-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002786 | 400286006 | Molding | HFTD Tier 3 | Distribution | 2005-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002787 | 400286036 | Molding | HFTD Tier 3 | Distribution | 2009-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002788 | 400286092 | High Sign | HFTD Tier 2 | Distribution | 2004-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002789 | 400286188 | High Sign | HFTD Tier 2 | Distribution | 2008-09-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002790 | 400286204 | Molding | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002791 | 400286426 | Molding | HFTD Tier 2 | Distribution | 2004-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002792 | 400286570 | High Sign | HFTD Tier 3 | Distribution | 2005-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002793 | 400286626 | Insulator | HFTD Tier 2 | Distribution | 2004-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002794 | 400286695 | Molding | HFTD Tier 3 | Distribution | 2004-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002795 | 400286730 | Molding | HFTD Tier 2 | Distribution | 2009-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002796 | 400286790 | Hardware/Framing | HFTD Tier 3 | Distribution | 2004-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002797 | 400286920 | Hardware/Framing | HFTD Tier 2 | Distribution | 2009-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002798 | 400286981 | High Sign | HFTD Tier 2 | Distribution | 2007-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002799 | 400287010 | High Sign | HFTD Tier 2 | Distribution | 2004-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002800 | 400287018 | High Sign | HFTD Tier 2 | Distribution | 2004-10-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002801 | 400287191 | Molding | HFTD Tier 2 | Distribution | 2004-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002802 | 400287380 | Molding | HFTD Tier 2 | Distribution | 2004-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002803 | 400287435 | High Sign | HFTD Tier 3 | Distribution | 2005-09-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002804 | 400287438 | High Sign | HFTD Tier 2 | Distribution | 2007-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002805 | 400287642 | High Sign | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002806 | 400287666 | High Sign | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002807 | 400287736 | High Sign | HFTD Tier 2 | Distribution | 2005-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002808 | 400287824 | Molding | HFTD Tier 2 | Distribution | 2004-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002809 | 400287873 | Molding | HFTD Tier 3 | Distribution | 2005-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002810 | 400287913 | Molding | HFTD Tier 2 | Distribution | 2008-12-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002811 | 400288239 | High Sign | HFTD Tier 2 | Distribution | 2004-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002812 | 400288529 | High Sign | HFTD Tier 3 | Distribution | 2004-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002813 | 400288619 | High Sign | HFTD Tier 2 | Distribution | 2007-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002814 | 400288970 | High Sign | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002815 | 400288988 | High Sign | HFTD Tier 2 | Distribution | 2004-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002816 | 400289128 | Molding | HFTD Tier 3 | Distribution | 2007-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002817 | 400289289 | Guy | HFTD Tier 3 | Distribution | 2009-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002818 | 400289294 | Molding | HFTD Tier 3 | Distribution | 2010-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002819 | 400289367 | Molding | HFTD Tier 3 | Distribution | 2008-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002820 | 400289573 | High Sign | HFTD Tier 2 | Distribution | 2004-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002821 | 400289648 | High Sign | HFTD Tier 3 | Distribution | 2005-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002822 | 400289667 | Molding | HFTD Tier 2 | Distribution | 2004-07-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002823 | 400289758 | Molding | HFTD Tier 3 | Distribution | 2008-11-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002824 | 400290072 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002825 | 400290178 | High Sign | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002826 | 400290228 | Molding | HFTD Tier 3 | Distribution | 2004-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002827 | 400290234 | Insulator | HFTD Tier 3 | Distribution | 2004-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002828 | 400290256 | High Sign | HFTD Tier 3 | Distribution | 2004-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002829 | 400290409 | High Sign | HFTD Tier 3 | Distribution | 2009-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002830 | 400290542 | High Sign | HFTD Tier 3 | Distribution | 2004-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002831 | 400290884 | Guy | HFTD Tier 3 | Distribution | 2003-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002832 | 400291137 | Molding | HFTD Tier 3 | Distribution | 2009-10-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002833 | 400291333 | Molding | HFTD Tier 2 | Distribution | 2009-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002834 | 400291383 | Guy | HFTD Tier 2 | Distribution | 2005-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002835 | 400291391 | Molding | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002836 | 400291415 | Molding | HFTD Tier 2 | Distribution | 2005-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002837 | 400291424 | High Sign | HFTD Tier 2 | Distribution | 2009-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002838 | 400291517 | High Sign | HFTD Tier 3 | Distribution | 2008-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002839 | 400291624 | High Sign | HFTD Tier 3 | Distribution | 2004-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002840 | 400291719 | High Sign | HFTD Tier 2 | Distribution | 2009-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002841 | 400291770 | High Sign | HFTD Tier 2 | Distribution | 2010-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002842 | 400291821 | Molding | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002843 | 400291918 | Molding | HFTD Tier 3 | Distribution | 2007-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002844 | 400291953 | High Sign | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002845 | 400292087 | Guy | HFTD Tier 2 | Distribution | 2005-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002846 | 400292088 | High Sign | HFTD Tier 2 | Distribution | 2005-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002847 | 400292095 | Molding | HFTD Tier 3 | Distribution | 2009-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002848 | 400292100 | Molding | HFTD Tier 3 | Distribution | 2008-12-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002849 | 400292208 | Molding | HFTD Tier 2 | Distribution | 2005-09-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002850 | 400292258 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2008-12-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002851 | 400292661 | Molding | HFTD Tier 2 | Distribution | 2005-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002852 | 400292861 | Molding | HFTD Tier 2 | Distribution | 2007-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002853 | 400293080 | Molding | HFTD Tier 3 | Distribution | 2005-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002854 | 400293304 | High Sign | HFTD Tier 3 | Distribution | 2004-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002855 | 400293327 | Molding | HFTD Tier 2 | Distribution | 2004-05-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002856 | 400294068 | High Sign | HFTD Tier 3 | Distribution | 2004-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002857 | 400294153 | High Sign | HFTD Tier 2 | Distribution | 2004-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002858 | 400294217 | KV Cable Tags | HFTD Tier 2 | Distribution | 2008-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002859 | 400294419 | High Sign | HFTD Tier 3 | Distribution | 2003-10-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002860 | 400294718 | High Sign | HFTD Tier 2 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002861 | 400294832 | High Sign | HFTD Tier 2 | Distribution | 2005-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002862 | 400294858 | High Sign | HFTD Tier 3 | Distribution | 2004-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002863 | 400294870 | High Sign | HFTD Tier 2 | Distribution | 2004-10-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002864 | 400295054 | Molding | HFTD Tier 3 | Distribution | 2005-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002865 | 400295181 | High Sign | HFTD Tier 2 | Distribution | 2003-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002866 | 400295344 | Molding | HFTD Tier 3 | Distribution | 2005-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002867 | 400295374 | High Sign | HFTD Tier 3 | Distribution | 2004-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002868 | 400295375 | Molding | HFTD Tier 2 | Distribution | 2005-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002869 | 400295538 | High Sign | HFTD Tier 2 | Distribution | 2003-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002870 | 400295911 | High Sign | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002871 | 400295984 | High Sign | HFTD Tier 2 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002872 | 400296010 | Molding | HFTD Tier 3 | Distribution | 2004-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002873 | 400296162 | High Sign | HFTD Tier 3 | Distribution | 2008-04-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002874 | 400296389 | Riser/Conduit | HFTD Tier 3 | Distribution | 2008-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002875 | 400296396 | Hardware/Framing | HFTD Tier 3 | Distribution | 2005-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002876 | 400296409 | High Sign | HFTD Tier 2 | Distribution | 2005-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002877 | 400296538 | High Sign | HFTD Tier 2 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002878 | 400296542 | Molding | HFTD Tier 3 | Distribution | 2004-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002879 | 400296573 | Molding | HFTD Tier 3 | Distribution | 2009-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002880 | 400296611 | Molding | HFTD Tier 2 | Distribution | 2003-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002881 | 400296826 | Ground | HFTD Tier 2 | Distribution | 2003-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002882 | 400296852 | High Sign | HFTD Tier 2 | Distribution | 2003-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002883 | 400296938 | High Sign | HFTD Tier 3 | Distribution | 2005-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002884 | 400297163 | Molding | HFTD Tier 3 | Distribution | 2009-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002885 | 400297176 | High Sign | HFTD Tier 3 | Distribution | 2005-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002886 | 400297260 | High Sign | HFTD Tier 2 | Distribution | 2001-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002887 | 400297386 | Hardware/Framing | HFTD Tier 3 | Distribution | 2003-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002888 | 400297463 | High Sign | HFTD Tier 2 | Distribution | 2004-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002889 | 400297538 | High Sign | HFTD Tier 3 | Distribution | 2010-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002890 | 400297729 | Riser/Conduit | HFTD Tier 3 | Distribution | 2004-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002891 | 400297783 | High Sign | HFTD Tier 3 | Distribution | 2004-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002892 | 400297872 | Molding | HFTD Tier 2 | Distribution | 2003-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002893 | 400297941 | Molding | HFTD Tier 2 | Distribution | 2003-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002894 | 400297995 | Molding | HFTD Tier 3 | Distribution | 2004-07-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002895 | 400298005 | High Sign | HFTD Tier 2 | Distribution | 2005-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002896 | 400298019 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002897 | 400298313 | High Sign | HFTD Tier 2 | Distribution | 2005-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002898 | 400298333 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002899 | 400298416 | High Sign | HFTD Tier 3 | Distribution | 2007-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002900 | 400298480 | High Sign | HFTD Tier 2 | Distribution | 2009-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002901 | 400298503 | Molding | HFTD Tier 3 | Distribution | 2007-02-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002902 | 400298563 | Molding | HFTD Tier 2 | Distribution | 2005-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002903 | 400298891 | Molding | HFTD Tier 2 | Distribution | 2005-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002904 | 400299003 | High Sign | HFTD Tier 3 | Distribution | 2004-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002905 | 400299156 | Guy | HFTD Tier 2 | Distribution | 2005-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002906 | 400299249 | High Sign | HFTD Tier 3 | Distribution | 2009-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002907 | 400299318 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-05-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002908 | 400299335 | Molding | HFTD Tier 2 | Distribution | 2004-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002909 | 400299563 | Molding | HFTD Tier 3 | Distribution | 2004-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002910 | 400299570 | High Sign | HFTD Tier 3 | Distribution | 2001-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002911 | 400299635 | Molding | HFTD Tier 3 | Distribution | 2005-02-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002912 | 400299697 | Molding | HFTD Tier 3 | Distribution | 2004-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002913 | 400299839 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2004-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002914 | 400299940 | High Sign | HFTD Tier 3 | Distribution | 2007-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002915 | 400299943 | Molding | HFTD Tier 2 | Distribution | 2003-10-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002916 | 400300100 | Molding | HFTD Tier 2 | Distribution | 2005-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002917 | 400300228 | High Sign | HFTD Tier 2 | Distribution | 2004-07-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002918 | 400300311 | High Sign | HFTD Tier 3 | Distribution | 2003-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002919 | 400300446 | High Sign | HFTD Tier 3 | Distribution | 2005-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002920 | 400301061 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2008-11-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002921 | 400301131 | High Sign | HFTD Tier 3 | Distribution | 2004-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002922 | 400301166 | KV Cable Tags | HFTD Tier 2 | Distribution | 2008-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002923 | 400301195 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002924 | 400301639 | High Sign | HFTD Tier 2 | Distribution | 2010-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002925 | 400301645 | High Sign | HFTD Tier 2 | Distribution | 2005-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002926 | 400301695 | High Sign | HFTD Tier 3 | Distribution | 2004-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002927 | 400301748 | Hardware/Framing | HFTD Tier 2 | Distribution | 2004-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002928 | 400301800 | High Sign | HFTD Tier 2 | Distribution | 2005-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002929 | 400301867 | High Sign | HFTD Tier 2 | Distribution | 2001-09-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002930 | 400301876 | Hardware/Framing | HFTD Tier 2 | Distribution | 2009-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002931 | 400302131 | High Sign | HFTD Tier 3 | Distribution | 2005-09-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002932 | 400302246 | High Sign | HFTD Tier 2 | Distribution | 2004-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002933 | 400302359 | Molding | HFTD Tier 3 | Distribution | 2004-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002934 | 400302400 | Ground | HFTD Tier 2 | Distribution | 2010-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002935 | 400302513 | Guy | HFTD Tier 3 | Distribution | 2008-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002936 | 400302525 | High Sign | HFTD Tier 2 | Distribution | 2004-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002937 | 400302703 | High Sign | HFTD Tier 2 | Distribution | 2003-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002938 | 400302712 | High Sign | HFTD Tier 2 | Distribution | 2005-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002939 | 400302827 | High Sign | HFTD Tier 3 | Distribution | 2002-01-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002940 | 400303230 | Molding | HFTD Tier 3 | Distribution | 2009-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002941 | 400303463 | KV Cable Tags | HFTD Tier 3 | Distribution | 2008-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002942 | 400303534 | Ground | HFTD Tier 2 | Distribution | 2010-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002943 | 400303829 | High Sign | HFTD Tier 2 | Distribution | 2004-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002944 | 400303917 | High Sign | HFTD Tier 3 | Distribution | 2009-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002945 | 400304082 | High Sign | HFTD Tier 3 | Distribution | 2009-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002946 | 400304212 | Molding | HFTD Tier 3 | Distribution | 2009-07-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002947 | 400304249 | High Sign | HFTD Tier 2 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002948 | 400304311 | Insulator | HFTD Tier 2 | Distribution | 2003-11-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002949 | 400304338 | High Sign | HFTD Tier 2 | Distribution | 2003-11-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002950 | 400304910 | High Sign | HFTD Tier 3 | Distribution | 2003-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002951 | 400304948 | Guy | HFTD Tier 3 | Distribution | 2003-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002952 | 400305043 | Molding | HFTD Tier 2 | Distribution | 2007-05-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002953 | 400305185 | Molding | HFTD Tier 2 | Distribution | 2010-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002954 | 400305208 | Molding | HFTD Tier 3 | Distribution | 2008-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002955 | 400305356 | High Sign | HFTD Tier 3 | Distribution | 2003-11-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002956 | 400305447 | Molding | HFTD Tier 3 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002957 | 400305524 | Guy | HFTD Tier 3 | Distribution | 2004-11-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002958 | 400305737 | Molding | HFTD Tier 2 | Distribution | 2004-12-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002959 | 400305840 | Molding | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002960 | 400305843 | High Sign | HFTD Tier 2 | Distribution | 2004-02-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002961 | 400305870 | High Sign | HFTD Tier 3 | Distribution | 2004-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002962 | 400306084 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002963 | 400306086 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002964 | 400306115 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002965 | 400306162 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2005-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002966 | 400306594 | High Sign | HFTD Tier 3 | Distribution | 2009-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002967 | 400306761 | Cable/Conductor | HFTD Tier 3 | Distribution | 2008-04-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002968 | 400306793 | Molding | HFTD Tier 3 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002969 | 400306802 | High Sign | HFTD Tier 2 | Distribution | 2005-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002970 | 400306874 | High Sign | HFTD Tier 3 | Distribution | 2005-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002971 | 400306924 | Molding | HFTD Tier 3 | Distribution | 2009-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002972 | 400306955 | Molding | HFTD Tier 2 | Distribution | 2005-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002973 | 400307063 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002974 | 400307210 | Molding | HFTD Tier 3 | Distribution | 2007-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002975 | 400307266 | High Sign | HFTD Tier 3 | Distribution | 2004-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002976 | 400307491 | High Sign | HFTD Tier 3 | Distribution | 2008-05-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002977 | 400307503 | High Sign | HFTD Tier 3 | Distribution | 2008-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002978 | 400307612 | High Sign | HFTD Tier 3 | Distribution | 2008-08-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002979 | 400307648 | Molding | HFTD Tier 3 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002980 | 400307737 | High Sign | HFTD Tier 2 | Distribution | 2003-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002981 | 400308060 | High Sign | HFTD Tier 3 | Distribution | 2004-12-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002982 | 400308113 | High Sign | HFTD Tier 3 | Distribution | 2003-11-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002983 | 400308131 | High Sign | HFTD Tier 3 | Distribution | 2004-09-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002984 | 400308330 | High Sign | HFTD Tier 2 | Distribution | 2001-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002985 | 400308351 | Riser/Conduit | HFTD Tier 3 | Distribution | 2004-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002986 | 400308481 | High Sign | HFTD Tier 2 | Distribution | 2005-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002987 | 400308528 | Molding | HFTD Tier 3 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002988 | 400308560 | Molding | HFTD Tier 2 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002989 | 400308685 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002990 | 400308743 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2008-12-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002991 | 400308805 | High Sign | HFTD Tier 2 | Distribution | 2004-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002992 | 400309072 | High Sign | HFTD Tier 3 | Distribution | 2004-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002993 | 400309159 | Guy | HFTD Tier 3 | Distribution | 2005-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002994 | 400309189 | Molding | HFTD Tier 3 | Distribution | 2005-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002995 | 400309196 | High Sign | HFTD Tier 2 | Distribution | 2004-04-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002996 | 400309229 | Riser/Conduit | HFTD Tier 2 | Distribution | 2005-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002997 | 400309289 | Molding | HFTD Tier 2 | Distribution | 2009-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002998 | 400309296 | High Sign | HFTD Tier 2 | Distribution | 2008-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130002999 | 400309411 | Guy | HFTD Tier 2 | Distribution | 2005-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003000 | 400309488 | High Sign | HFTD Tier 3 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003001 | 400309517 | Molding | HFTD Tier 2 | Distribution | 2004-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003002 | 400309613 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003003 | 400309629 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003004 | 400309658 | Molding | HFTD Tier 2 | Distribution | 2003-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003005 | 400309877 | Guy | HFTD Tier 3 | Distribution | 2004-02-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003006 | 400309897 | Hardware/Framing | HFTD Tier 3 | Distribution | 2005-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003007 | 400309933 | High Sign | HFTD Tier 3 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003008 | 400310028 | Molding | HFTD Tier 2 | Distribution | 2004-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003009 | 400310072 | Molding | HFTD Tier 2 | Distribution | 2005-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003010 | 400310102 | High Sign | HFTD Tier 3 | Distribution | 2005-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003011 | 400310264 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003012 | 400310285 | Molding | HFTD Tier 3 | Distribution | 2010-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003013 | 400310371 | Molding | HFTD Tier 3 | Distribution | 2003-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003014 | 400310414 | High Sign | HFTD Tier 3 | Distribution | 2004-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003015 | 400310544 | High Sign | HFTD Tier 2 | Distribution | 2005-08-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003016 | 400310567 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003017 | 400310670 | Molding | HFTD Tier 2 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003018 | 400310769 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003019 | 400310846 | Molding | HFTD Tier 2 | Distribution | 1999-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003020 | 400310871 | High Sign | HFTD Tier 2 | Distribution | 2005-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003021 | 400311379 | Guy | HFTD Tier 3 | Distribution | 2004-12-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003022 | 400311442 | Molding | HFTD Tier 2 | Distribution | 2003-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003023 | 400311457 | Molding | HFTD Tier 3 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003024 | 400311582 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003025 | 400311715 | Guy | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003026 | 400311768 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003027 | 400311887 | Molding | HFTD Tier 2 | Distribution | 2009-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003028 | 400311946 | High Sign | HFTD Tier 3 | Distribution | 2004-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003029 | 400312041 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003030 | 400312231 | Molding | HFTD Tier 3 | Distribution | 2009-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003031 | 400312269 | High Sign | HFTD Tier 3 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003032 | 400312281 | High Sign | HFTD Tier 2 | Distribution | 2005-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003033 | 400312283 | High Sign | HFTD Tier 2 | Distribution | 2001-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003034 | 400312342 | Guy | HFTD Tier 3 | Distribution | 2005-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003035 | 400312350 | Molding | HFTD Tier 3 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003036 | 400312353 | High Sign | HFTD Tier 3 | Distribution | 2004-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003037 | 400312550 | Molding | HFTD Tier 3 | Distribution | 2004-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003038 | 400312622 | Guy | HFTD Tier 2 | Distribution | 2008-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003039 | 400312641 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003040 | 400312656 | Molding | HFTD Tier 2 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003041 | 400312682 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003042 | 400312708 | High Sign | HFTD Tier 2 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003043 | 400312717 | High Sign | HFTD Tier 3 | Distribution | 2004-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003044 | 400312807 | Molding | HFTD Tier 2 | Distribution | 2004-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003045 | 400313038 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003046 | 400313141 | Molding | HFTD Tier 3 | Distribution | 2010-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003047 | 400313552 | Molding | HFTD Tier 3 | Distribution | 2003-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003048 | 400313566 | High Sign | HFTD Tier 2 | Distribution | 2005-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003049 | 400313582 | High Sign | HFTD Tier 2 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003050 | 400313640 | Molding | HFTD Tier 2 | Distribution | 2004-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003051 | 400313708 | Molding | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003052 | 400313943 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003053 | 400313969 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-04-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003054 | 400313970 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003055 | 400314338 | High Sign | HFTD Tier 3 | Distribution | 2004-09-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003056 | 400314481 | Molding | HFTD Tier 2 | Distribution | 2004-12-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003057 | 400314522 | Molding | HFTD Tier 3 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003058 | 400314637 | Molding | HFTD Tier 3 | Distribution | 2008-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003059 | 400314907 | High Sign | HFTD Tier 2 | Distribution | 2009-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003060 | 400314962 | Guy | HFTD Tier 2 | Distribution | 2004-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003061 | 400314995 | High Sign | HFTD Tier 3 | Distribution | 2004-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003062 | 400315173 | Molding | HFTD Tier 3 | Distribution | 2004-02-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003063 | 400315180 | Molding | HFTD Tier 2 | Distribution | 2004-08-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003064 | 400315198 | High Sign | HFTD Tier 2 | Distribution | 2001-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003065 | 400315245 | Guy | HFTD Tier 3 | Distribution | 2004-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003066 | 400315266 | High Sign | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003067 | 400315324 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003068 | 400315336 | Molding | HFTD Tier 2 | Distribution | 2004-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003069 | 400315351 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003070 | 400315392 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003071 | 400315400 | Molding | HFTD Tier 2 | Distribution | 2005-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003072 | 400315751 | High Sign | HFTD Tier 3 | Distribution | 2005-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003073 | 400315876 | High Sign | HFTD Tier 2 | Distribution | 2004-02-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003074 | 400315906 | Molding | HFTD Tier 2 | Distribution | 2003-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003075 | 400315963 | Guy | HFTD Tier 2 | Distribution | 2004-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003076 | 400316112 | Molding | HFTD Tier 2 | Distribution | 2004-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003077 | 400316142 | Guy | HFTD Tier 3 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003078 | 400316326 | High Sign | HFTD Tier 2 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003079 | 400316352 | Molding | HFTD Tier 2 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003080 | 400316395 | High Sign | HFTD Tier 2 | Distribution | 2005-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003081 | 400316441 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003082 | 400316511 | Molding | HFTD Tier 2 | Distribution | 1999-09-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003083 | 400316646 | High Sign | HFTD Tier 3 | Distribution | 2009-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003084 | 400316801 | High Sign | HFTD Tier 3 | Distribution | 2008-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003085 | 400316895 | Guy | HFTD Tier 3 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003086 | 400317210 | High Sign | HFTD Tier 2 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003087 | 400317393 | Guy | HFTD Tier 3 | Distribution | 2005-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003088 | 400317589 | High Sign | HFTD Tier 2 | Distribution | 2004-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003089 | 400317680 | Guy | HFTD Tier 3 | Distribution | 2009-11-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003090 | 400318030 | High Sign | HFTD Tier 3 | Distribution | 2003-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003091 | 400318181 | High Sign | HFTD Tier 2 | Distribution | 2004-12-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003092 | 400318201 | High Sign | HFTD Tier 2 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003093 | 400318385 | High Sign | HFTD Tier 2 | Distribution | 2003-11-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003094 | 400318466 | High Sign | HFTD Tier 3 | Distribution | 2005-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003095 | 400318487 | High Sign | HFTD Tier 3 | Distribution | 2004-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003096 | 400318504 | High Sign | HFTD Tier 2 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003097 | 400318677 | High Sign | HFTD Tier 2 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003098 | 400318857 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003099 | 400318905 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003100 | 400318919 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003101 | 400318933 | High Sign | HFTD Tier 2 | Distribution | 2004-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003102 | 400319088 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003103 | 400319159 | Molding | HFTD Tier 2 | Distribution | 2007-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003104 | 400319322 | High Sign | HFTD Tier 2 | Distribution | 2003-11-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003105 | 400319439 | High Sign | HFTD Tier 2 | Distribution | 2004-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003106 | 400319449 | Molding | HFTD Tier 3 | Distribution | 2007-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003107 | 400319515 | Molding | HFTD Tier 2 | Distribution | 2008-12-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003108 | 400319517 | Molding | HFTD Tier 3 | Distribution | 2008-12-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003109 | 400319669 | Molding | HFTD Tier 3 | Distribution | 2004-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003110 | 400319818 | High Sign | HFTD Tier 2 | Distribution | 2004-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003111 | 400319875 | Molding | HFTD Tier 3 | Distribution | 2004-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003112 | 400320231 | High Sign | HFTD Tier 2 | Distribution | 2004-12-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003113 | 400320239 | High Sign | HFTD Tier 2 | Distribution | 2005-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003114 | 400320244 | High Sign | HFTD Tier 3 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003115 | 400320270 | Molding | HFTD Tier 3 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003116 | 400320273 | Molding | HFTD Tier 3 | Distribution | 2008-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003117 | 400320305 | Molding | HFTD Tier 2 | Distribution | 2005-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003118 | 400320422 | High Sign | HFTD Tier 2 | Distribution | 2003-11-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003119 | 400320636 | High Sign | HFTD Tier 3 | Distribution | 2004-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003120 | 400320646 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-12-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003121 | 400320662 | High Sign | HFTD Tier 3 | Distribution | 2004-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003122 | 400320669 | High Sign | HFTD Tier 2 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003123 | 400320716 | High Sign | HFTD Tier 2 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003124 | 400320840 | Molding | HFTD Tier 3 | Distribution | 2005-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003125 | 400320878 | Molding | HFTD Tier 3 | Distribution | 2009-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003126 | 400320907 | High Sign | HFTD Tier 3 | Distribution | 2009-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003127 | 400320974 | Molding | HFTD Tier 2 | Distribution | 2005-10-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003128 | 400321046 | Ground | HFTD Tier 2 | Distribution | 2008-09-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003129 | 400321058 | Molding | HFTD Tier 3 | Distribution | 2004-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003130 | 400321375 | High Sign | HFTD Tier 2 | Distribution | 2003-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003131 | 400321397 | Guy | HFTD Tier 3 | Distribution | 2004-04-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003132 | 400321489 | Molding | HFTD Tier 2 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003133 | 400321527 | Molding | HFTD Tier 3 | Distribution | 2004-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003134 | 400321595 | High Sign | HFTD Tier 3 | Distribution | 2001-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003135 | 400321806 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003136 | 400321837 | High Sign | HFTD Tier 2 | Distribution | 2008-07-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003137 | 400322089 | Molding | HFTD Tier 2 | Distribution | 2008-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003138 | 400322114 | High Sign | HFTD Tier 2 | Distribution | 2008-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003139 | 400322444 | High Sign | HFTD Tier 2 | Distribution | 2009-08-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003140 | 400322467 | High Sign | HFTD Tier 2 | Distribution | 2008-05-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003141 | 400322596 | High Sign | HFTD Tier 2 | Distribution | 2004-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003142 | 400323418 | Molding | HFTD Tier 3 | Distribution | 2004-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003143 | 400323865 | High Sign | HFTD Tier 3 | Distribution | 2004-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003144 | 400323874 | High Sign | HFTD Tier 2 | Distribution | 2003-11-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003145 | 400324360 | Molding | HFTD Tier 3 | Distribution | 2004-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003146 | 400324435 | High Sign | HFTD Tier 2 | Distribution | 2007-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003147 | 400324445 | Molding | HFTD Tier 3 | Distribution | 2005-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003148 | 400324678 | Molding | HFTD Tier 2 | Distribution | 2005-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003149 | 400324694 | Molding | HFTD Tier 3 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003150 | 400324866 | High Sign | HFTD Tier 2 | Distribution | 2008-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003151 | 400324869 | Molding | HFTD Tier 2 | Distribution | 2003-11-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003152 | 400325102 | Insulator | HFTD Tier 2 | Distribution | 2004-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003153 | 400325307 | High Sign | HFTD Tier 3 | Distribution | 2005-09-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003154 | 400325337 | Molding | HFTD Tier 2 | Distribution | 2005-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003155 | 400325356 | Molding | HFTD Tier 2 | Distribution | 2009-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003156 | 400325386 | High Sign | HFTD Tier 2 | Distribution | 2008-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003157 | 400325446 | Insulator | HFTD Tier 2 | Distribution | 2004-04-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003158 | 400325499 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003159 | 400325578 | High Sign | HFTD Tier 3 | Distribution | 2008-09-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003160 | 400325638 | Molding | HFTD Tier 2 | Distribution | 1999-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003161 | 400325643 | High Sign | HFTD Tier 2 | Distribution | 2004-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003162 | 400325955 | Riser/Conduit | HFTD Tier 2 | Distribution | 2003-11-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003163 | 400326038 | Molding | HFTD Tier 3 | Distribution | 2004-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003164 | 400326127 | High Sign | HFTD Tier 3 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003165 | 400326146 | High Sign | HFTD Tier 2 | Distribution | 2009-08-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003166 | 400326185 | Molding | HFTD Tier 2 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003167 | 400326207 | Molding | HFTD Tier 2 | Distribution | 2003-11-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003168 | 400326209 | High Sign | HFTD Tier 2 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003169 | 400326233 | High Sign | HFTD Tier 2 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003170 | 400326438 | High Sign | HFTD Tier 3 | Distribution | 2004-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003171 | 400326466 | High Sign | HFTD Tier 2 | Distribution | 2004-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003172 | 400326511 | Molding | HFTD Tier 3 | Distribution | 2007-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003173 | 400326685 | Guy | HFTD Tier 3 | Distribution | 2004-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003174 | 400326997 | Molding | HFTD Tier 3 | Distribution | 2004-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003175 | 400327046 | Molding | HFTD Tier 3 | Distribution | 2004-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003176 | 400327207 | High Sign | HFTD Tier 3 | Distribution | 2004-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003177 | 400327216 | High Sign | HFTD Tier 2 | Distribution | 2001-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003178 | 400327329 | Guy | HFTD Tier 3 | Distribution | 2005-09-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003179 | 400327659 | Molding | HFTD Tier 2 | Distribution | 2004-02-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003180 | 400327923 | High Sign | HFTD Tier 3 | Distribution | 2004-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003181 | 400327942 | High Sign | HFTD Tier 3 | Distribution | 2008-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003182 | 400328411 | High Sign | HFTD Tier 3 | Distribution | 2001-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003183 | 400328432 | High Sign | HFTD Tier 2 | Distribution | 2003-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003184 | 400328542 | Molding | HFTD Tier 2 | Distribution | 2005-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003185 | 400328626 | High Sign | HFTD Tier 3 | Distribution | 2008-01-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003186 | 400328796 | High Sign | HFTD Tier 2 | Distribution | 2004-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003187 | 400328889 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003188 | 400328998 | Molding | HFTD Tier 3 | Distribution | 2007-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003189 | 400329024 | High Sign | HFTD Tier 2 | Distribution | 2004-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003190 | 400329072 | High Sign | HFTD Tier 3 | Distribution | 2005-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003191 | 400329090 | High Sign | HFTD Tier 2 | Distribution | 2009-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003192 | 400329114 | High Sign | HFTD Tier 2 | Distribution | 2009-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003193 | 400329251 | High Sign | HFTD Tier 3 | Distribution | 2009-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003194 | 400329381 | Molding | HFTD Tier 2 | Distribution | 2004-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003195 | 400329412 | Molding | HFTD Tier 2 | Distribution | 2003-11-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003196 | 400329440 | High Sign | HFTD Tier 2 | Distribution | 2003-11-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003197 | 400329468 | Molding | HFTD Tier 2 | Distribution | 2003-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003198 | 400329768 | High Sign | HFTD Tier 3 | Distribution | 2008-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003199 | 400329861 | High Sign | HFTD Tier 3 | Distribution | 2008-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003200 | 400329941 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003201 | 400329953 | Molding | HFTD Tier 2 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003202 | 400330014 | Molding | HFTD Tier 2 | Distribution | 2001-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003203 | 400330343 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-11-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003204 | 400330372 | High Sign | HFTD Tier 3 | Distribution | 2009-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003205 | 400330378 | Insulator | HFTD Tier 2 | Distribution | 2004-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003206 | 400330996 | High Sign | HFTD Tier 2 | Distribution | 2001-09-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003207 | 400331037 | Molding | HFTD Tier 2 | Distribution | 2003-10-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003208 | 400331188 | High Sign | HFTD Tier 3 | Distribution | 2005-12-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003209 | 400331352 | High Sign | HFTD Tier 3 | Distribution | 2008-12-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003210 | 400331550 | Guy | HFTD Tier 2 | Distribution | 2005-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003211 | 400331560 | Molding | HFTD Tier 3 | Distribution | 2004-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003212 | 400331794 | Molding | HFTD Tier 3 | Distribution | 2008-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003213 | 400331852 | High Sign | HFTD Tier 2 | Distribution | 2005-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003214 | 400332017 | Molding | HFTD Tier 3 | Distribution | 2004-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003215 | 400332157 | High Sign | HFTD Tier 3 | Distribution | 2009-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003216 | 400332187 | High Sign | HFTD Tier 3 | Distribution | 2009-07-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003217 | 400332303 | High Sign | HFTD Tier 3 | Distribution | 2004-11-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003218 | 400332449 | High Sign | HFTD Tier 2 | Distribution | 2004-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003219 | 400332519 | Molding | HFTD Tier 3 | Distribution | 2005-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003220 | 400332541 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003221 | 400332614 | High Sign | HFTD Tier 2 | Distribution | 2004-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003222 | 400332629 | High Sign | HFTD Tier 2 | Distribution | 2003-11-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003223 | 400332668 | Riser/Conduit | HFTD Tier 3 | Distribution | 2005-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003224 | 400332930 | High Sign | HFTD Tier 3 | Distribution | 2009-11-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003225 | 400333039 | Molding | HFTD Tier 2 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003226 | 400333087 | Molding | HFTD Tier 3 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003227 | 400333102 | High Sign | HFTD Tier 2 | Distribution | 2004-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003228 | 400333220 | High Sign | HFTD Tier 2 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003229 | 400333255 | Insulator | HFTD Tier 2 | Distribution | 2004-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003230 | 400333325 | High Sign | HFTD Tier 2 | Distribution | 2004-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003231 | 400333432 | Molding | HFTD Tier 3 | Distribution | 2005-10-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003232 | 400333438 | High Sign | HFTD Tier 2 | Distribution | 2004-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003233 | 400333463 | Molding | HFTD Tier 3 | Distribution | 2004-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003234 | 400333494 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-05-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003235 | 400333546 | High Sign | HFTD Tier 2 | Distribution | 2005-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003236 | 400333684 | High Sign | HFTD Tier 2 | Distribution | 2005-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003237 | 400333818 | Molding | HFTD Tier 3 | Distribution | 2008-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003238 | 400333952 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-11-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003239 | 400334118 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003240 | 400334191 | Crossarm | HFTD Tier 3 | Distribution | 2004-01-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003241 | 400334228 | Molding | HFTD Tier 3 | Distribution | 2003-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003242 | 400334236 | Molding | HFTD Tier 3 | Distribution | 2007-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003243 | 400334286 | High Sign | HFTD Tier 2 | Distribution | 2004-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003244 | 400334351 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2004-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003245 | 400334673 | Ground | HFTD Tier 2 | Distribution | 2008-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003246 | 400334730 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003247 | 400334905 | Insulator | HFTD Tier 2 | Distribution | 2009-12-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003248 | 400335010 | High Sign | HFTD Tier 2 | Distribution | 2004-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003249 | 400335052 | Molding | HFTD Tier 2 | Distribution | 2003-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003250 | 400335175 | Molding | HFTD Tier 2 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003251 | 400335194 | High Sign | HFTD Tier 2 | Distribution | 2004-10-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003252 | 400335331 | High Sign | HFTD Tier 3 | Distribution | 2005-12-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003253 | 400335422 | Molding | HFTD Tier 3 | Distribution | 2004-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003254 | 400335502 | Molding | HFTD Tier 3 | Distribution | 2005-12-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003255 | 400335560 | High Sign | HFTD Tier 3 | Distribution | 2008-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003256 | 400335574 | Molding | HFTD Tier 2 | Distribution | 2008-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003257 | 400335576 | Molding | HFTD Tier 3 | Distribution | 2009-09-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003258 | 400335694 | Insulator | HFTD Tier 2 | Distribution | 2004-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003259 | 400335802 | Molding | HFTD Tier 3 | Distribution | 2004-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003260 | 400335890 | High Sign | HFTD Tier 3 | Distribution | 2009-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003261 | 400336076 | Molding | HFTD Tier 3 | Distribution | 2005-09-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003262 | 400336255 | High Sign | HFTD Tier 2 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003263 | 400336438 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2008-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003264 | 400336531 | Molding | HFTD Tier 2 | Distribution | 2005-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003265 | 400336644 | Guy | HFTD Tier 3 | Distribution | 2003-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003266 | 400336698 | Molding | HFTD Tier 3 | Distribution | 2004-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003267 | 400336737 | High Sign | HFTD Tier 2 | Distribution | 2009-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003268 | 400336903 | Molding | HFTD Tier 3 | Distribution | 2001-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003269 | 400336954 | Molding | HFTD Tier 3 | Distribution | 2009-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003270 | 400336969 | Molding | HFTD Tier 3 | Distribution | 2005-10-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003271 | 400337124 | Molding | HFTD Tier 2 | Distribution | 2001-01-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003272 | 400337329 | High Sign | HFTD Tier 2 | Distribution | 2005-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003273 | 400337396 | High Sign | HFTD Tier 3 | Distribution | 2004-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003274 | 400337423 | High Sign | HFTD Tier 2 | Distribution | 2004-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003275 | 400337478 | High Sign | HFTD Tier 2 | Distribution | 2004-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003276 | 400337498 | Molding | HFTD Tier 2 | Distribution | 2001-01-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003277 | 400337627 | High Sign | HFTD Tier 2 | Distribution | 2004-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003278 | 400337937 | Molding | HFTD Tier 2 | Distribution | 2004-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003279 | 400338039 | High Sign | HFTD Tier 3 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003280 | 400338086 | High Sign | HFTD Tier 3 | Distribution | 2008-11-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003281 | 400338608 | High Sign | HFTD Tier 3 | Distribution | 2009-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003282 | 400338629 | High Sign | HFTD Tier 3 | Distribution | 2000-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003283 | 400338952 | High Sign | HFTD Tier 2 | Distribution | 2004-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003284 | 400338992 | Molding | HFTD Tier 2 | Distribution | 2003-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003285 | 400339155 | Molding | HFTD Tier 2 | Distribution | 2007-08-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003286 | 400339215 | Molding | HFTD Tier 3 | Distribution | 2004-12-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003287 | 400339421 | Molding | HFTD Tier 2 | Distribution | 2008-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003288 | 400339570 | High Sign | HFTD Tier 3 | Distribution | 2009-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003289 | 400339609 | Molding | HFTD Tier 3 | Distribution | 2007-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003290 | 400339617 | Guy | HFTD Tier 2 | Distribution | 2005-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003291 | 400339633 | Molding | HFTD Tier 2 | Distribution | 2009-12-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003292 | 400339912 | High Sign | HFTD Tier 2 | Distribution | 2005-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003293 | 400339960 | Molding | HFTD Tier 3 | Distribution | 2004-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003294 | 400340058 | Molding | HFTD Tier 2 | Distribution | 2005-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003295 | 400340092 | High Sign | HFTD Tier 2 | Distribution | 2005-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003296 | 400340213 | Molding | HFTD Tier 2 | Distribution | 2004-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003297 | 400340252 | Molding | HFTD Tier 3 | Distribution | 2005-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003298 | 400340305 | Molding | HFTD Tier 2 | Distribution | 2004-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003299 | 400340676 | High Sign | HFTD Tier 3 | Distribution | 2009-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003300 | 400340914 | High Sign | HFTD Tier 3 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003301 | 400340960 | Molding | HFTD Tier 3 | Distribution | 2004-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003302 | 400340976 | Guy | HFTD Tier 3 | Distribution | 2003-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003303 | 400341031 | High Sign | HFTD Tier 3 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003304 | 400341049 | Molding | HFTD Tier 3 | Distribution | 2004-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003305 | 400341103 | High Sign | HFTD Tier 2 | Distribution | 2014-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003306 | 400341194 | High Sign | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003307 | 400341227 | High Sign | HFTD Tier 3 | Distribution | 2009-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003308 | 400341239 | High Sign | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003309 | 400341316 | High Sign | HFTD Tier 3 | Distribution | 2005-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003310 | 400341317 | Molding | HFTD Tier 3 | Distribution | 2004-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003311 | 400341392 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-11-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003312 | 400341513 | High Sign | HFTD Tier 2 | Distribution | 2004-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003313 | 400341931 | High Sign | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003314 | 400342170 | Molding | HFTD Tier 2 | Distribution | 2003-10-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003315 | 400342254 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003316 | 400342284 | High Sign | HFTD Tier 2 | Distribution | 2004-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003317 | 400342349 | High Sign | HFTD Tier 3 | Distribution | 2004-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003318 | 400342451 | Molding | HFTD Tier 2 | Distribution | 2005-12-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003319 | 400342454 | Guy | HFTD Tier 2 | Distribution | 2009-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003320 | 400342477 | Molding | HFTD Tier 2 | Distribution | 2005-12-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003321 | 400342620 | Guy | HFTD Tier 3 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003322 | 400342700 | Guy | HFTD Tier 3 | Distribution | 2004-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003323 | 400342765 | Molding | HFTD Tier 3 | Distribution | 2004-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003324 | 400342799 | Molding | HFTD Tier 2 | Distribution | 2004-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003325 | 400342954 | Molding | HFTD Tier 3 | Distribution | 2007-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003326 | 400342986 | High Sign | HFTD Tier 3 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003327 | 400343179 | Molding | HFTD Tier 3 | Distribution | 2003-11-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003328 | 400343208 | Guy | HFTD Tier 3 | Distribution | 2003-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003329 | 400343300 | High Sign | HFTD Tier 3 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003330 | 400343344 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003331 | 400343372 | Molding | HFTD Tier 2 | Distribution | 2004-07-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003332 | 400343529 | High Sign | HFTD Tier 3 | Distribution | 2004-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003333 | 400343561 | Cable/Conductor | HFTD Tier 3 | Distribution | 2005-09-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003334 | 400343574 | High Sign | HFTD Tier 3 | Distribution | 2004-08-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003335 | 400343723 | Hardware/Framing | HFTD Tier 2 | Distribution | 2009-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003336 | 400343794 | High Sign | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003337 | 400343796 | Molding | HFTD Tier 3 | Distribution | 2004-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003338 | 400343844 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003339 | 400343866 | Molding | HFTD Tier 3 | Distribution | 2004-10-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003340 | 400343939 | Molding | HFTD Tier 2 | Distribution | 2002-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003341 | 400344100 | Molding | HFTD Tier 2 | Distribution | 2007-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003342 | 400344225 | High Sign | HFTD Tier 2 | Distribution | 2005-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003343 | 400344378 | Molding | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003344 | 400344386 | High Sign | HFTD Tier 2 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003345 | 400344433 | Insulator | HFTD Tier 2 | Distribution | 2004-04-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003346 | 400344485 | High Sign | HFTD Tier 2 | Distribution | 2005-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003347 | 400344521 | High Sign | HFTD Tier 2 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003348 | 400344651 | High Sign | HFTD Tier 3 | Distribution | 2004-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003349 | 400344753 | Molding | HFTD Tier 2 | Distribution | 2004-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003350 | 400344840 | High Sign | HFTD Tier 2 | Distribution | 2003-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003351 | 400344888 | Molding | HFTD Tier 3 | Distribution | 2004-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003352 | 400344906 | Molding | HFTD Tier 3 | Distribution | 2007-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003353 | 400345009 | High Sign | HFTD Tier 2 | Distribution | 2004-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003354 | 400345160 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-11-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003355 | 400345202 | Guy | HFTD Tier 3 | Distribution | 2003-07-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003356 | 400345238 | High Sign | HFTD Tier 3 | Distribution | 2003-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003357 | 400345295 | Crossarm | HFTD Tier 3 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003358 | 400345693 | Molding | HFTD Tier 2 | Distribution | 2004-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003359 | 400345911 | Insulator | HFTD Tier 2 | Distribution | 2004-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003360 | 400346057 | Molding | HFTD Tier 3 | Distribution | 2008-12-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003361 | 400346209 | High Sign | HFTD Tier 3 | Distribution | 2004-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003362 | 400346230 | Guy | HFTD Tier 3 | Distribution | 2004-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003363 | 400346331 | Molding | HFTD Tier 2 | Distribution | 2009-05-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003364 | 400346591 | High Sign | HFTD Tier 3 | Distribution | 2007-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003365 | 400346615 | High Sign | HFTD Tier 2 | Distribution | 2003-09-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003366 | 400346659 | Molding | HFTD Tier 2 | Distribution | 2007-05-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003367 | 400346672 | Molding | HFTD Tier 3 | Distribution | 2004-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003368 | 400346771 | Hardware/Framing | HFTD Tier 3 | Distribution | 2003-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003369 | 400346919 | Guy | HFTD Tier 2 | Distribution | 2009-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003370 | 400347043 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003371 | 400347051 | Guy | HFTD Tier 3 | Distribution | 2003-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003372 | 400347056 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003373 | 400347128 | Riser/Conduit | HFTD Tier 2 | Distribution | 2004-08-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003374 | 400347251 | High Sign | HFTD Tier 3 | Distribution | 2005-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003375 | 400347293 | High Sign | HFTD Tier 2 | Distribution | 2004-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003376 | 400347601 | Molding | HFTD Tier 2 | Distribution | 2001-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003377 | 400347679 | Guy | HFTD Tier 3 | Distribution | 2004-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003378 | 400347864 | High Sign | HFTD Tier 2 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003379 | 400347872 | Molding | HFTD Tier 2 | Distribution | 2004-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003380 | 400347963 | Molding | HFTD Tier 2 | Distribution | 2005-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003381 | 400348018 | Hardware/Framing | HFTD Tier 2 | Distribution | 2009-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003382 | 400348036 | High Sign | HFTD Tier 2 | Distribution | 2005-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003383 | 400348165 | Molding | HFTD Tier 2 | Distribution | 2002-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003384 | 400348303 | High Sign | HFTD Tier 2 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003385 | 400348319 | Molding | HFTD Tier 2 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003386 | 400348338 | High Sign | HFTD Tier 3 | Distribution | 2009-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003387 | 400348403 | Guy | HFTD Tier 3 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003388 | 400348492 | Molding | HFTD Tier 2 | Distribution | 2005-09-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003389 | 400348600 | Molding | HFTD Tier 3 | Distribution | 2005-06-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003390 | 400348679 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003391 | 400348694 | Molding | HFTD Tier 2 | Distribution | 2005-11-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003392 | 400348701 | High Sign | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003393 | 400348739 | Molding | HFTD Tier 3 | Distribution | 2008-04-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003394 | 400348811 | High Sign | HFTD Tier 3 | Distribution | 2008-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003395 | 400348860 | High Sign | HFTD Tier 2 | Distribution | 2003-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003396 | 400348983 | Riser/Conduit | HFTD Tier 3 | Distribution | 2010-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003397 | 400349013 | Guy | HFTD Tier 3 | Distribution | 2003-07-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003398 | 400349077 | Molding | HFTD Tier 3 | Distribution | 2005-09-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003399 | 400349381 | High Sign | HFTD Tier 3 | Distribution | 2004-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003400 | 400349419 | Hardware/Framing | HFTD Tier 3 | Distribution | 2004-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003401 | 400349692 | High Sign | HFTD Tier 3 | Distribution | 2009-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003402 | 400349744 | Guy | HFTD Tier 2 | Distribution | 2005-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003403 | 400349774 | High Sign | HFTD Tier 3 | Distribution | 2005-06-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003404 | 400350156 | Hardware/Framing | HFTD Tier 3 | Distribution | 2004-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003405 | 400350285 | High Sign | HFTD Tier 2 | Distribution | 2005-09-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003406 | 400350304 | Molding | HFTD Tier 2 | Distribution | 2004-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003407 | 400350356 | Guy | HFTD Tier 3 | Distribution | 2004-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003408 | 400350494 | Riser/Conduit | HFTD Tier 3 | Distribution | 2005-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003409 | 400350544 | High Sign | HFTD Tier 3 | Distribution | 2005-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003410 | 400350591 | High Sign | HFTD Tier 2 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003411 | 400350711 | High Sign | HFTD Tier 2 | Distribution | 2004-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003412 | 400350858 | Molding | HFTD Tier 3 | Distribution | 2005-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003413 | 400350961 | High Sign | HFTD Tier 2 | Distribution | 2003-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003414 | 400350984 | High Sign | HFTD Tier 2 | Distribution | 2003-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003415 | 400351075 | High Sign | HFTD Tier 2 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003416 | 400351127 | High Sign | HFTD Tier 3 | Distribution | 2004-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003417 | 400351158 | High Sign | HFTD Tier 2 | Distribution | 2009-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003418 | 400351218 | Molding | HFTD Tier 2 | Distribution | 2004-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003419 | 400351370 | Cable/Conductor | HFTD Tier 3 | Distribution | 2005-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003420 | 400351392 | Guy | HFTD Tier 3 | Distribution | 2005-11-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003421 | 400351747 | Molding | HFTD Tier 2 | Distribution | 2009-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003422 | 400351772 | High Sign | HFTD Tier 2 | Distribution | 2004-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003423 | 400351790 | High Sign | HFTD Tier 3 | Distribution | 2004-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003424 | 400351827 | Guy | HFTD Tier 2 | Distribution | 2003-11-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003425 | 400352042 | High Sign | HFTD Tier 3 | Distribution | 2000-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003426 | 400352071 | High Sign | HFTD Tier 2 | Distribution | 2005-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003427 | 400352239 | Molding | HFTD Tier 3 | Distribution | 2008-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003428 | 400352282 | Molding | HFTD Tier 3 | Distribution | 2005-08-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003429 | 400352305 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003430 | 400352397 | High Sign | HFTD Tier 2 | Distribution | 2003-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003431 | 400352419 | High Sign | HFTD Tier 2 | Distribution | 2003-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003432 | 400352521 | Molding | HFTD Tier 2 | Distribution | 2003-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003433 | 400352783 | Molding | HFTD Tier 3 | Distribution | 2009-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003434 | 400352852 | High Sign | HFTD Tier 3 | Distribution | 2009-01-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003435 | 400352857 | Riser/Conduit | HFTD Tier 2 | Distribution | 2009-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003436 | 400353016 | High Sign | HFTD Tier 3 | Distribution | 2004-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003437 | 400353019 | Hardware/Framing | HFTD Tier 2 | Distribution | 2009-01-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003438 | 400353029 | Molding | HFTD Tier 3 | Distribution | 2009-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003439 | 400353174 | Molding | HFTD Tier 2 | Distribution | 2004-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003440 | 400353220 | High Sign | HFTD Tier 2 | Distribution | 2004-07-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003441 | 400353258 | High Sign | HFTD Tier 2 | Distribution | 2004-07-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003442 | 400353432 | Molding | HFTD Tier 2 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003443 | 400353450 | Molding | HFTD Tier 3 | Distribution | 2003-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003444 | 400353485 | High Sign | HFTD Tier 2 | Distribution | 2003-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003445 | 400353585 | High Sign | HFTD Tier 2 | Distribution | 2005-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003446 | 400353800 | High Sign | HFTD Tier 3 | Distribution | 2004-09-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003447 | 400353946 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003448 | 400354019 | Molding | HFTD Tier 3 | Distribution | 2005-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003449 | 400354091 | High Sign | HFTD Tier 3 | Distribution | 2005-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003450 | 400354100 | High Sign | HFTD Tier 3 | Distribution | 2004-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003451 | 400354167 | High Sign | HFTD Tier 2 | Distribution | 2004-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003452 | 400354174 | Cable/Conductor | HFTD Tier 3 | Distribution | 2003-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003453 | 400354274 | High Sign | HFTD Tier 2 | Distribution | 2003-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003454 | 400354618 | Molding | HFTD Tier 2 | Distribution | 2004-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003455 | 400354693 | High Sign | HFTD Tier 3 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003456 | 400354871 | High Sign | HFTD Tier 2 | Distribution | 2003-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003457 | 400354881 | High Sign | HFTD Tier 2 | Distribution | 2005-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003458 | 400355052 | High Sign | HFTD Tier 2 | Distribution | 2009-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003459 | 400355127 | Guy | HFTD Tier 3 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003460 | 400355128 | Molding | HFTD Tier 3 | Distribution | 2005-02-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003461 | 400355248 | Molding | HFTD Tier 2 | Distribution | 2004-11-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003462 | 400355360 | High Sign | HFTD Tier 3 | Distribution | 2005-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003463 | 400355373 | Molding | HFTD Tier 3 | Distribution | 2009-07-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003464 | 400355409 | Molding | HFTD Tier 2 | Distribution | 2004-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003465 | 400355855 | Molding | HFTD Tier 2 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003466 | 400355890 | High Sign | HFTD Tier 3 | Distribution | 2005-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003467 | 400356031 | Molding | HFTD Tier 2 | Distribution | 2004-07-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003468 | 400356095 | Guy | HFTD Tier 2 | Distribution | 2002-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003469 | 400356140 | High Sign | HFTD Tier 2 | Distribution | 2003-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003470 | 400356186 | Guy | HFTD Tier 3 | Distribution | 2003-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003471 | 400356613 | Molding | HFTD Tier 2 | Distribution | 2004-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003472 | 400356763 | High Sign | HFTD Tier 2 | Distribution | 2004-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003473 | 400357023 | High Sign | HFTD Tier 3 | Distribution | 2003-09-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003474 | 400357121 | Molding | HFTD Tier 3 | Distribution | 2000-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003475 | 400357182 | High Sign | HFTD Tier 2 | Distribution | 2001-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003476 | 400357230 | Molding | HFTD Tier 2 | Distribution | 2005-01-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003477 | 400357283 | Hardware/Framing | HFTD Tier 3 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003478 | 400357313 | High Sign | HFTD Tier 2 | Distribution | 2003-10-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003479 | 400357376 | High Sign | HFTD Tier 3 | Distribution | 2004-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003480 | 400357433 | Molding | HFTD Tier 2 | Distribution | 2002-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003481 | 400357458 | High Sign | HFTD Tier 2 | Distribution | 2005-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003482 | 400357546 | High Sign | HFTD Tier 3 | Distribution | 2003-11-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003483 | 400357741 | High Sign | HFTD Tier 2 | Distribution | 2004-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003484 | 400357750 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003485 | 400357873 | Molding | HFTD Tier 2 | Distribution | 2005-12-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003486 | 400357948 | Riser/Conduit | HFTD Tier 3 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003487 | 400357963 | High Sign | HFTD Tier 3 | Distribution | 2003-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003488 | 400358132 | Molding | HFTD Tier 2 | Distribution | 2003-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003489 | 400358315 | High Sign | HFTD Tier 3 | Distribution | 2004-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003490 | 400358422 | Molding | HFTD Tier 3 | Distribution | 2008-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003491 | 400358535 | Molding | HFTD Tier 2 | Distribution | 2003-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003492 | 400358537 | High Sign | HFTD Tier 3 | Distribution | 2008-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003493 | 400358572 | High Sign | HFTD Tier 3 | Distribution | 2008-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003494 | 400358578 | High Sign | HFTD Tier 2 | Distribution | 2004-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003495 | 400358663 | Molding | HFTD Tier 2 | Distribution | 2008-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003496 | 400358706 | Guy | HFTD Tier 3 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003497 | 400358708 | Molding | HFTD Tier 2 | Distribution | 2002-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003498 | 400358765 | Insulator | HFTD Tier 2 | Distribution | 2004-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003499 | 400358892 | High Sign | HFTD Tier 2 | Distribution | 2004-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003500 | 400358949 | High Sign | HFTD Tier 2 | Distribution | 2008-09-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003501 | 400358991 | Molding | HFTD Tier 2 | Distribution | 2005-10-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003502 | 400359240 | High Sign | HFTD Tier 2 | Distribution | 2003-09-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003503 | 400359449 | High Sign | HFTD Tier 3 | Distribution | 2003-11-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003504 | 400359458 | Molding | HFTD Tier 2 | Distribution | 2009-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003505 | 400359734 | Guy | HFTD Tier 2 | Distribution | 2004-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003506 | 400359889 | Guy | HFTD Tier 3 | Distribution | 2003-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003507 | 400359915 | High Sign | HFTD Tier 3 | Distribution | 2008-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003508 | 400359966 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-02-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003509 | 400360027 | High Sign | HFTD Tier 3 | Distribution | 2005-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003510 | 400360085 | High Sign | HFTD Tier 2 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003511 | 400360216 | Molding | HFTD Tier 2 | Distribution | 2003-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003512 | 400360288 | Guy | HFTD Tier 3 | Distribution | 2005-08-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003513 | 400360656 | High Sign | HFTD Tier 3 | Distribution | 2008-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003514 | 400360720 | High Sign | HFTD Tier 2 | Distribution | 2001-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003515 | 400360770 | High Sign | HFTD Tier 3 | Distribution | 2008-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003516 | 400360942 | Guy | HFTD Tier 3 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003517 | 400361061 | Hardware/Framing | HFTD Tier 3 | Distribution | 2004-04-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003518 | 400361134 | Molding | HFTD Tier 2 | Distribution | 2004-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003519 | 400361204 | High Sign | HFTD Tier 3 | Distribution | 2003-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003520 | 400361410 | High Sign | HFTD Tier 3 | Distribution | 2010-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003521 | 400361535 | High Sign | HFTD Tier 3 | Distribution | 2005-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003522 | 400361540 | Guy | HFTD Tier 3 | Distribution | 2003-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003523 | 400361696 | Molding | HFTD Tier 2 | Distribution | 2007-10-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003524 | 400361766 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2008-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003525 | 400361799 | Molding | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003526 | 400361837 | High Sign | HFTD Tier 3 | Distribution | 2005-02-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003527 | 400361871 | Molding | HFTD Tier 2 | Distribution | 2004-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003528 | 400361878 | High Sign | HFTD Tier 3 | Distribution | 2004-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003529 | 400361907 | High Sign | HFTD Tier 2 | Distribution | 2004-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003530 | 400361963 | High Sign | HFTD Tier 2 | Distribution | 2005-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003531 | 400362232 | Molding | HFTD Tier 2 | Distribution | 2005-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003532 | 400362677 | High Sign | HFTD Tier 2 | Distribution | 2009-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003533 | 400362873 | High Sign | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003534 | 400362962 | Molding | HFTD Tier 3 | Distribution | 2009-11-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003535 | 400363068 | High Sign | HFTD Tier 3 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003536 | 400363107 | High Sign | HFTD Tier 3 | Distribution | 2007-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003537 | 400363243 | Molding | HFTD Tier 3 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003538 | 400363587 | High Sign | HFTD Tier 3 | Distribution | 2004-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003539 | 400363589 | Molding | HFTD Tier 2 | Distribution | 2007-10-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003540 | 400363611 | High Sign | HFTD Tier 2 | Distribution | 2004-01-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003541 | 400363612 | Guy | HFTD Tier 3 | Distribution | 2009-12-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003542 | 400363792 | Molding | HFTD Tier 3 | Distribution | 2003-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003543 | 400363883 | Riser/Conduit | HFTD Tier 3 | Distribution | 2003-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003544 | 400363996 | Molding | HFTD Tier 2 | Distribution | 2002-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003545 | 400364164 | Molding | HFTD Tier 3 | Distribution | 2004-09-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003546 | 400364356 | High Sign | HFTD Tier 3 | Distribution | 2005-10-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003547 | 400364467 | High Sign | HFTD Tier 3 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003548 | 400364521 | High Sign | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003549 | 400364541 | Guy | HFTD Tier 3 | Distribution | 2004-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003550 | 400364599 | Molding | HFTD Tier 3 | Distribution | 2008-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003551 | 400364877 | Molding | HFTD Tier 3 | Distribution | 2004-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003552 | 400365011 | Molding | HFTD Tier 3 | Distribution | 2005-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003553 | 400365040 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003554 | 400365045 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003555 | 400365128 | High Sign | HFTD Tier 2 | Distribution | 2003-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003556 | 400365202 | Molding | HFTD Tier 3 | Distribution | 2004-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003557 | 400365314 | High Sign | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003558 | 400365384 | High Sign | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003559 | 400365474 | Molding | HFTD Tier 3 | Distribution | 2008-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003560 | 400365686 | Guy | HFTD Tier 3 | Distribution | 2005-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003561 | 400365693 | High Sign | HFTD Tier 2 | Distribution | 2004-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003562 | 400365798 | High Sign | HFTD Tier 3 | Distribution | 2008-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003563 | 400365891 | Molding | HFTD Tier 3 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003564 | 400365967 | Guy | HFTD Tier 3 | Distribution | 2004-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003565 | 400366101 | Molding | HFTD Tier 2 | Distribution | 2009-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003566 | 400366202 | High Sign | HFTD Tier 2 | Distribution | 2004-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003567 | 400366263 | High Sign | HFTD Tier 2 | Distribution | 2005-10-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003568 | 400366577 | High Sign | HFTD Tier 2 | Distribution | 2004-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003569 | 400366594 | Molding | HFTD Tier 3 | Distribution | 2004-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003570 | 400366742 | High Sign | HFTD Tier 2 | Distribution | 2004-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003571 | 400366964 | High Sign | HFTD Tier 2 | Distribution | 2005-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003572 | 400366975 | High Sign | HFTD Tier 3 | Distribution | 2003-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003573 | 400366985 | Molding | HFTD Tier 2 | Distribution | 2007-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003574 | 400367095 | High Sign | HFTD Tier 2 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003575 | 400367343 | Molding | HFTD Tier 3 | Distribution | 2008-12-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003576 | 400367379 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003577 | 400367545 | Molding | HFTD Tier 2 | Distribution | 2004-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003578 | 400367582 | High Sign | HFTD Tier 3 | Distribution | 2004-11-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003579 | 400367786 | High Sign | HFTD Tier 3 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003580 | 400367826 | High Sign | HFTD Tier 3 | Distribution | 2004-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003581 | 400367885 | High Sign | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003582 | 400367938 | High Sign | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003583 | 400367991 | High Sign | HFTD Tier 3 | Distribution | 2004-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003584 | 400368606 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003585 | 400368706 | Ground | HFTD Tier 3 | Distribution | 2005-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003586 | 400368763 | High Sign | HFTD Tier 3 | Distribution | 2005-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003587 | 400368839 | Molding | HFTD Tier 2 | Distribution | 2004-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003588 | 400368891 | High Sign | HFTD Tier 2 | Distribution | 2004-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003589 | 400368908 | Guy | HFTD Tier 2 | Distribution | 2004-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003590 | 400368921 | High Sign | HFTD Tier 3 | Distribution | 2003-10-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003591 | 400369076 | Molding | HFTD Tier 2 | Distribution | 2004-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003592 | 400369173 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003593 | 400369229 | High Sign | HFTD Tier 3 | Distribution | 2004-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003594 | 400369477 | Molding | HFTD Tier 3 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003595 | 400369547 | High Sign | HFTD Tier 3 | Distribution | 2008-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003596 | 400369899 | High Sign | HFTD Tier 2 | Distribution | 2004-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003597 | 400369921 | Riser/Conduit | HFTD Tier 2 | Distribution | 2009-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003598 | 400370083 | High Sign | HFTD Tier 3 | Distribution | 2003-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003599 | 400370214 | High Sign | HFTD Tier 2 | Distribution | 2001-01-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003600 | 400370250 | High Sign | HFTD Tier 3 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003601 | 400370374 | Insulator | HFTD Tier 2 | Distribution | 2004-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003602 | 400370919 | High Sign | HFTD Tier 2 | Distribution | 2003-10-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003603 | 400370983 | High Sign | HFTD Tier 3 | Distribution | 2006-01-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003604 | 400371342 | Cable/Conductor | HFTD Tier 3 | Distribution | 2005-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003605 | 400371370 | Molding | HFTD Tier 2 | Distribution | 2009-10-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003606 | 400371393 | High Sign | HFTD Tier 3 | Distribution | 2009-05-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003607 | 400371467 | Molding | HFTD Tier 2 | Distribution | 2006-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003608 | 400371599 | High Sign | HFTD Tier 3 | Distribution | 2003-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003609 | 400371637 | High Sign | HFTD Tier 3 | Distribution | 2003-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003610 | 400371750 | High Sign | HFTD Tier 3 | Distribution | 2005-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003611 | 400371945 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003612 | 400372100 | Molding | HFTD Tier 2 | Distribution | 2007-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003613 | 400372138 | High Sign | HFTD Tier 2 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003614 | 400372146 | High Sign | HFTD Tier 2 | Distribution | 2004-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003615 | 400372407 | High Sign | HFTD Tier 3 | Distribution | 2004-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003616 | 400372422 | Cable/Conductor | HFTD Tier 3 | Distribution | 2005-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003617 | 400372439 | Insulator | HFTD Tier 2 | Distribution | 2004-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003618 | 400372944 | High Sign | HFTD Tier 2 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003619 | 400372951 | High Sign | HFTD Tier 2 | Distribution | 2005-07-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003620 | 400373064 | High Sign | HFTD Tier 2 | Distribution | 2009-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003621 | 400373194 | High Sign | HFTD Tier 3 | Distribution | 2004-09-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003622 | 400373210 | Guy | HFTD Tier 3 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003623 | 400373232 | High Sign | HFTD Tier 3 | Distribution | 2004-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003624 | 400373308 | High Sign | HFTD Tier 3 | Distribution | 2004-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003625 | 400373465 | Molding | HFTD Tier 2 | Distribution | 2009-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003626 | 400373510 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003627 | 400373512 | High Sign | HFTD Tier 3 | Distribution | 2003-11-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003628 | 400373563 | High Sign | HFTD Tier 2 | Distribution | 2005-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003629 | 400373588 | High Sign | HFTD Tier 3 | Distribution | 2009-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003630 | 400373668 | High Sign | HFTD Tier 3 | Distribution | 2004-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003631 | 400373798 | Guy | HFTD Tier 3 | Distribution | 2005-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003632 | 400373874 | Molding | HFTD Tier 3 | Distribution | 2003-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003633 | 400374014 | High Sign | HFTD Tier 2 | Distribution | 2003-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003634 | 400374057 | High Sign | HFTD Tier 3 | Distribution | 2005-09-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003635 | 400374125 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-09-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003636 | 400374155 | Guy | HFTD Tier 3 | Distribution | 2004-12-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003637 | 400374274 | High Sign | HFTD Tier 2 | Distribution | 2010-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003638 | 400374323 | High Sign | HFTD Tier 2 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003639 | 400374383 | Molding | HFTD Tier 3 | Distribution | 2009-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003640 | 400374416 | High Sign | HFTD Tier 2 | Distribution | 2009-08-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003641 | 400374618 | Molding | HFTD Tier 3 | Distribution | 2004-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003642 | 400374719 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003643 | 400374942 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003644 | 400375161 | Molding | HFTD Tier 3 | Distribution | 2003-11-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003645 | 400375181 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2008-12-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003646 | 400375233 | High Sign | HFTD Tier 3 | Distribution | 2009-11-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003647 | 400375367 | Guy | HFTD Tier 2 | Distribution | 2009-09-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003648 | 400375549 | Molding | HFTD Tier 2 | Distribution | 2004-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003649 | 400375797 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003650 | 400375815 | Molding | HFTD Tier 2 | Distribution | 2007-10-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003651 | 400376028 | High Sign | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003652 | 400376168 | High Sign | HFTD Tier 2 | Distribution | 2009-09-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003653 | 400376271 | Molding | HFTD Tier 2 | Distribution | 2005-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003654 | 400376308 | High Sign | HFTD Tier 2 | Distribution | 2009-08-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003655 | 400376349 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003656 | 400376432 | High Sign | HFTD Tier 3 | Distribution | 2005-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003657 | 400376480 | High Sign | HFTD Tier 3 | Distribution | 2009-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003658 | 400376601 | High Sign | HFTD Tier 3 | Distribution | 2003-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003659 | 400376865 | Molding | HFTD Tier 2 | Distribution | 2004-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003660 | 400376948 | High Sign | HFTD Tier 2 | Distribution | 2000-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003661 | 400377078 | High Sign | HFTD Tier 2 | Distribution | 2004-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003662 | 400377139 | High Sign | HFTD Tier 2 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003663 | 400377143 | Molding | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003664 | 400377198 | Molding | HFTD Tier 2 | Distribution | 2004-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003665 | 400377728 | Molding | HFTD Tier 3 | Distribution | 2003-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003666 | 400377737 | Molding | HFTD Tier 3 | Distribution | 2000-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003667 | 400377776 | High Sign | HFTD Tier 3 | Distribution | 2004-10-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003668 | 400377791 | Cable/Conductor | HFTD Tier 2 | Distribution | 2005-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003669 | 400377863 | High Sign | HFTD Tier 2 | Distribution | 2003-09-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003670 | 400377878 | High Sign | HFTD Tier 2 | Distribution | 2005-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003671 | 400378075 | High Sign | HFTD Tier 2 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003672 | 400378215 | High Sign | HFTD Tier 2 | Distribution | 2004-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003673 | 400378294 | Molding | HFTD Tier 2 | Distribution | 2004-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003674 | 400378472 | High Sign | HFTD Tier 2 | Distribution | 2004-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003675 | 400378561 | High Sign | HFTD Tier 3 | Distribution | 2003-08-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003676 | 400378682 | Molding | HFTD Tier 3 | Distribution | 2003-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003677 | 400378811 | High Sign | HFTD Tier 2 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003678 | 400378847 | Molding | HFTD Tier 2 | Distribution | 2007-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003679 | 400378946 | High Sign | HFTD Tier 2 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003680 | 400378971 | High Sign | HFTD Tier 2 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003681 | 400379033 | High Sign | HFTD Tier 2 | Distribution | 2003-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003682 | 400379180 | High Sign | HFTD Tier 3 | Distribution | 2009-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003683 | 400379203 | Molding | HFTD Tier 3 | Distribution | 2004-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003684 | 400379223 | Molding | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003685 | 400379391 | Insulator | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003686 | 400379408 | High Sign | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003687 | 400379427 | Guy | HFTD Tier 3 | Distribution | 2010-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003688 | 400379453 | Molding | HFTD Tier 2 | Distribution | 2008-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003689 | 400379523 | Molding | HFTD Tier 3 | Distribution | 2004-12-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003690 | 400379614 | High Sign | HFTD Tier 2 | Distribution | 2005-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003691 | 400379632 | High Sign | HFTD Tier 3 | Distribution | 2004-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003692 | 400379906 | High Sign | HFTD Tier 3 | Distribution | 2003-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003693 | 400379921 | Molding | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003694 | 400380304 | Molding | HFTD Tier 3 | Distribution | 2004-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003695 | 400380332 | Molding | HFTD Tier 2 | Distribution | 2004-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003696 | 400380404 | Molding | HFTD Tier 3 | Distribution | 2004-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003697 | 400380454 | High Sign | HFTD Tier 2 | Distribution | 2006-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003698 | 400380529 | High Sign | HFTD Tier 3 | Distribution | 2003-08-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003699 | 400380557 | High Sign | HFTD Tier 3 | Distribution | 2001-09-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003700 | 400380669 | High Sign | HFTD Tier 2 | Distribution | 2004-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003701 | 400380696 | High Sign | HFTD Tier 2 | Distribution | 2004-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003702 | 400380850 | High Sign | HFTD Tier 3 | Distribution | 2005-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003703 | 400380860 | High Sign | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003704 | 400380871 | High Sign | HFTD Tier 3 | Distribution | 2005-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003705 | 400381183 | Molding | HFTD Tier 2 | Distribution | 2003-11-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003706 | 400381378 | High Sign | HFTD Tier 3 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003707 | 400381401 | Molding | HFTD Tier 2 | Distribution | 2005-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003708 | 400381594 | Molding | HFTD Tier 3 | Distribution | 2004-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003709 | 400381622 | High Sign | HFTD Tier 2 | Distribution | 2008-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003710 | 400381703 | Guy | HFTD Tier 3 | Distribution | 2005-12-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003711 | 400381822 | Molding | HFTD Tier 2 | Distribution | 2004-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003712 | 400381875 | Molding | HFTD Tier 2 | Distribution | 2003-11-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003713 | 400381958 | Molding | HFTD Tier 2 | Distribution | 2009-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003714 | 400382253 | High Sign | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003715 | 400382270 | Guy | HFTD Tier 2 | Distribution | 2006-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003716 | 400382284 | High Sign | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003717 | 400382569 | High Sign | HFTD Tier 2 | Distribution | 2004-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003718 | 400382591 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003719 | 400382642 | High Sign | HFTD Tier 2 | Distribution | 2005-07-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003720 | 400382765 | Molding | HFTD Tier 3 | Distribution | 2004-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003721 | 400382834 | High Sign | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003722 | 400382837 | High Sign | HFTD Tier 3 | Distribution | 2010-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003723 | 400383237 | High Sign | HFTD Tier 3 | Distribution | 2003-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003724 | 400383273 | High Sign | HFTD Tier 3 | Distribution | 2005-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003725 | 400383284 | Molding | HFTD Tier 3 | Distribution | 2003-11-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003726 | 400383304 | High Sign | HFTD Tier 3 | Distribution | 2005-05-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003727 | 400383323 | Molding | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003728 | 400383398 | High Sign | HFTD Tier 3 | Distribution | 2005-09-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003729 | 400383411 | High Sign | HFTD Tier 3 | Distribution | 2004-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003730 | 400383600 | Molding | HFTD Tier 3 | Distribution | 2005-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003731 | 400383619 | Hardware/Framing | HFTD Tier 3 | Distribution | 2003-11-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003732 | 400383763 | Molding | HFTD Tier 2 | Distribution | 2009-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003733 | 400383861 | Molding | HFTD Tier 3 | Distribution | 2003-10-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003734 | 400383914 | High Sign | HFTD Tier 2 | Distribution | 2005-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003735 | 400384178 | High Sign | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003736 | 400384227 | High Sign | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003737 | 400384361 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003738 | 400384376 | High Sign | HFTD Tier 3 | Distribution | 2004-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003739 | 400384469 | High Sign | HFTD Tier 3 | Distribution | 2009-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003740 | 400384542 | Molding | HFTD Tier 3 | Distribution | 2005-10-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003741 | 400384992 | High Sign | HFTD Tier 3 | Distribution | 2004-08-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003742 | 400385175 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2008-05-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003743 | 400385230 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-12-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003744 | 400385535 | Guy | HFTD Tier 3 | Distribution | 2005-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003745 | 400385573 | High Sign | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003746 | 400385745 | Hardware/Framing | HFTD Tier 2 | Distribution | 2009-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003747 | 400385757 | Molding | HFTD Tier 3 | Distribution | 2009-08-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003748 | 400385789 | High Sign | HFTD Tier 2 | Distribution | 2004-08-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003749 | 400385911 | Molding | HFTD Tier 3 | Distribution | 2010-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003750 | 400385971 | Molding | HFTD Tier 2 | Distribution | 2004-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003751 | 400386095 | Molding | HFTD Tier 2 | Distribution | 2001-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003752 | 400386181 | Cable/Conductor | HFTD Tier 3 | Distribution | 2008-11-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003753 | 400386231 | High Sign | HFTD Tier 2 | Distribution | 2004-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003754 | 400386308 | Molding | HFTD Tier 2 | Distribution | 2004-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003755 | 400386338 | High Sign | HFTD Tier 2 | Distribution | 2004-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003756 | 400386358 | Molding | HFTD Tier 3 | Distribution | 2005-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003757 | 400386363 | High Sign | HFTD Tier 2 | Distribution | 2004-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003758 | 400386636 | High Sign | HFTD Tier 2 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003759 | 400386908 | High Sign | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003760 | 400386984 | High Sign | HFTD Tier 3 | Distribution | 2005-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003761 | 400387035 | Molding | HFTD Tier 3 | Distribution | 2009-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003762 | 400387043 | Molding | HFTD Tier 3 | Distribution | 2005-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003763 | 400387222 | Molding | HFTD Tier 3 | Distribution | 2005-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003764 | 400387265 | Molding | HFTD Tier 2 | Distribution | 2004-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003765 | 400387306 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003766 | 400387363 | High Sign | HFTD Tier 2 | Distribution | 2005-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003767 | 400387367 | High Sign | HFTD Tier 3 | Distribution | 2005-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003768 | 400387398 | Molding | HFTD Tier 3 | Distribution | 2005-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003769 | 400387448 | Molding | HFTD Tier 3 | Distribution | 2005-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003770 | 400387455 | Molding | HFTD Tier 2 | Distribution | 2004-06-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003771 | 400387604 | High Sign | HFTD Tier 2 | Distribution | 2007-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003772 | 400387607 | High Sign | HFTD Tier 3 | Distribution | 2009-09-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003773 | 400387632 | High Sign | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003774 | 400387706 | Molding | HFTD Tier 2 | Distribution | 2003-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003775 | 400387849 | High Sign | HFTD Tier 3 | Distribution | 2004-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003776 | 400387935 | Molding | HFTD Tier 2 | Distribution | 2009-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003777 | 400388070 | Molding | HFTD Tier 2 | Distribution | 2009-11-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003778 | 400388273 | Molding | HFTD Tier 2 | Distribution | 2004-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003779 | 400388370 | High Sign | HFTD Tier 2 | Distribution | 2004-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003780 | 400388379 | Molding | HFTD Tier 3 | Distribution | 2004-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003781 | 400388434 | High Sign | HFTD Tier 3 | Distribution | 2010-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003782 | 400388613 | Molding | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003783 | 400388671 | High Sign | HFTD Tier 2 | Distribution | 2002-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003784 | 400388742 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-05-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003785 | 400388815 | Molding | HFTD Tier 2 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003786 | 400388889 | High Sign | HFTD Tier 3 | Distribution | 2008-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003787 | 400388964 | Molding | HFTD Tier 2 | Distribution | 2009-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003788 | 400388991 | Molding | HFTD Tier 3 | Distribution | 2004-09-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003789 | 400389086 | High Sign | HFTD Tier 2 | Distribution | 2004-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003790 | 400389112 | High Sign | HFTD Tier 2 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003791 | 400389143 | Molding | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003792 | 400389198 | High Sign | HFTD Tier 2 | Distribution | 2009-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003793 | 400389225 | High Sign | HFTD Tier 3 | Distribution | 2009-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003794 | 400389420 | High Sign | HFTD Tier 2 | Distribution | 2004-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003795 | 400389464 | High Sign | HFTD Tier 3 | Distribution | 2005-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003796 | 400389480 | Molding | HFTD Tier 3 | Distribution | 2007-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003797 | 400389663 | Molding | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003798 | 400389913 | High Sign | HFTD Tier 2 | Distribution | 2004-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003799 | 400390004 | Crossarm | HFTD Tier 3 | Distribution | 2004-11-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003800 | 400390033 | Cable/Conductor | HFTD Tier 3 | Distribution | 2008-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003801 | 400390091 | High Sign | HFTD Tier 2 | Distribution | 2004-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003802 | 400390207 | Molding | HFTD Tier 2 | Distribution | 2009-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003803 | 400390247 | High Sign | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003804 | 400390403 | High Sign | HFTD Tier 2 | Distribution | 2001-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003805 | 400390409 | High Sign | HFTD Tier 2 | Distribution | 2003-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003806 | 400390506 | Molding | HFTD Tier 3 | Distribution | 2004-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003807 | 400390677 | Ground | HFTD Tier 3 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003808 | 400390736 | High Sign | HFTD Tier 2 | Distribution | 2004-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003809 | 400390771 | Molding | HFTD Tier 3 | Distribution | 2005-05-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003810 | 400390923 | High Sign | HFTD Tier 3 | Distribution | 2009-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003811 | 400390934 | High Sign | HFTD Tier 3 | Distribution | 2004-06-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003812 | 400391091 | High Sign | HFTD Tier 2 | Distribution | 2005-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003813 | 400391260 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003814 | 400391354 | Molding | HFTD Tier 3 | Distribution | 2004-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003815 | 400391458 | High Sign | HFTD Tier 2 | Distribution | 2005-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003816 | 400391529 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003817 | 400391579 | Guy | HFTD Tier 3 | Distribution | 2005-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003818 | 400391609 | High Sign | HFTD Tier 3 | Distribution | 2005-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003819 | 400391639 | High Sign | HFTD Tier 3 | Distribution | 2005-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003820 | 400391709 | Molding | HFTD Tier 3 | Distribution | 2005-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003821 | 400391720 | Molding | HFTD Tier 3 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003822 | 400391832 | High Sign | HFTD Tier 3 | Distribution | 2001-12-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003823 | 400391837 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2008-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003824 | 400391850 | Molding | HFTD Tier 3 | Distribution | 2005-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003825 | 400391866 | High Sign | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003826 | 400391921 | Molding | HFTD Tier 2 | Distribution | 2005-02-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003827 | 400392028 | High Sign | HFTD Tier 2 | Distribution | 2003-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003828 | 400392372 | High Sign | HFTD Tier 2 | Distribution | 2003-09-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003829 | 400392434 | Molding | HFTD Tier 2 | Distribution | 2005-12-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003830 | 400392438 | High Sign | HFTD Tier 3 | Distribution | 2009-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003831 | 400392640 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-02-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003832 | 400392682 | Guy | HFTD Tier 2 | Distribution | 2005-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003833 | 400392756 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003834 | 400392758 | High Sign | HFTD Tier 2 | Distribution | 2003-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003835 | 400392811 | High Sign | HFTD Tier 2 | Distribution | 2005-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003836 | 400392838 | Molding | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003837 | 400392879 | Molding | HFTD Tier 2 | Distribution | 2001-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003838 | 400392890 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-11-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003839 | 400392986 | High Sign | HFTD Tier 3 | Distribution | 2004-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003840 | 400393031 | Molding | HFTD Tier 3 | Distribution | 2004-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003841 | 400393092 | Molding | HFTD Tier 2 | Distribution | 2007-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003842 | 400393243 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003843 | 400393270 | Guy | HFTD Tier 3 | Distribution | 2004-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003844 | 400393393 | Molding | HFTD Tier 3 | Distribution | 2005-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003845 | 400393414 | Molding | HFTD Tier 2 | Distribution | 2009-11-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003846 | 400393535 | Molding | HFTD Tier 3 | Distribution | 2004-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003847 | 400393771 | Cable/Conductor | HFTD Tier 3 | Distribution | 2005-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003848 | 400393829 | High Sign | HFTD Tier 3 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003849 | 400393881 | Molding | HFTD Tier 2 | Distribution | 2009-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003850 | 400393941 | Molding | HFTD Tier 2 | Distribution | 2003-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003851 | 400394010 | Molding | HFTD Tier 3 | Distribution | 2005-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003852 | 400394017 | High Sign | HFTD Tier 2 | Distribution | 2005-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003853 | 400394056 | Molding | HFTD Tier 2 | Distribution | 2006-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003854 | 400394084 | High Sign | HFTD Tier 3 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003855 | 400394112 | High Sign | HFTD Tier 3 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003856 | 400394177 | Molding | HFTD Tier 3 | Distribution | 2008-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003857 | 400394259 | High Sign | HFTD Tier 3 | Distribution | 2008-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003858 | 400394345 | High Sign | HFTD Tier 2 | Distribution | 2005-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003859 | 400394358 | Crossarm | HFTD Tier 3 | Distribution | 2005-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003860 | 400394485 | Molding | HFTD Tier 2 | Distribution | 2005-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003861 | 400394503 | Molding | HFTD Tier 3 | Distribution | 2003-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003862 | 400394543 | High Sign | HFTD Tier 2 | Distribution | 2004-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003863 | 400394630 | Molding | HFTD Tier 2 | Distribution | 2004-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003864 | 400394700 | High Sign | HFTD Tier 2 | Distribution | 2009-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003865 | 400394781 | High Sign | HFTD Tier 2 | Distribution | 2007-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003866 | 400394856 | Molding | HFTD Tier 3 | Distribution | 2009-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003867 | 400394904 | Molding | HFTD Tier 3 | Distribution | 2009-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003868 | 400394974 | High Sign | HFTD Tier 2 | Distribution | 2005-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003869 | 400395034 | High Sign | HFTD Tier 2 | Distribution | 2005-07-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003870 | 400395086 | High Sign | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003871 | 400395340 | High Sign | HFTD Tier 3 | Distribution | 2010-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003872 | 400395631 | High Sign | HFTD Tier 2 | Distribution | 2008-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003873 | 400395919 | Molding | HFTD Tier 2 | Distribution | 2004-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003874 | 400395926 | Molding | HFTD Tier 3 | Distribution | 2009-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003875 | 400395970 | Molding | HFTD Tier 3 | Distribution | 2003-12-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003876 | 400396156 | High Sign | HFTD Tier 3 | Distribution | 2009-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003877 | 400396183 | Molding | HFTD Tier 2 | Distribution | 2001-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003878 | 400396215 | High Sign | HFTD Tier 2 | Distribution | 2004-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003879 | 400396234 | High Sign | HFTD Tier 2 | Distribution | 2004-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003880 | 400396307 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003881 | 400396712 | Molding | HFTD Tier 2 | Distribution | 2009-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003882 | 400396923 | High Sign | HFTD Tier 3 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003883 | 400396946 | High Sign | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003884 | 400396973 | Molding | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003885 | 400396975 | Molding | HFTD Tier 3 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003886 | 400397142 | Guy | HFTD Tier 2 | Distribution | 2004-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003887 | 400397177 | High Sign | HFTD Tier 3 | Distribution | 2010-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003888 | 400397232 | High Sign | HFTD Tier 2 | Distribution | 2010-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003889 | 400397323 | Molding | HFTD Tier 3 | Distribution | 2004-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003890 | 400397334 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003891 | 400397358 | Molding | HFTD Tier 3 | Distribution | 2008-11-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003892 | 400397519 | Molding | HFTD Tier 2 | Distribution | 2003-10-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003893 | 400397556 | High Sign | HFTD Tier 3 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003894 | 400397831 | High Sign | HFTD Tier 2 | Distribution | 2005-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003895 | 400397949 | High Sign | HFTD Tier 2 | Distribution | 2008-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003896 | 400398141 | High Sign | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003897 | 400398148 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003898 | 400398165 | Guy | HFTD Tier 2 | Distribution | 2005-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003899 | 400398186 | Molding | HFTD Tier 2 | Distribution | 2009-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003900 | 400398313 | High Sign | HFTD Tier 2 | Distribution | 2001-01-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003901 | 400398329 | Molding | HFTD Tier 2 | Distribution | 2004-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003902 | 400398371 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003903 | 400398401 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003904 | 400398452 | High Sign | HFTD Tier 2 | Distribution | 2004-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003905 | 400398487 | Molding | HFTD Tier 3 | Distribution | 2005-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003906 | 400398496 | High Sign | HFTD Tier 3 | Distribution | 2004-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003907 | 400398715 | High Sign | HFTD Tier 3 | Distribution | 2004-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003908 | 400398991 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003909 | 400399182 | Guy | HFTD Tier 3 | Distribution | 2005-10-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003910 | 400399218 | High Sign | HFTD Tier 3 | Distribution | 2005-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003911 | 400399274 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003912 | 400399465 | Molding | HFTD Tier 2 | Distribution | 2009-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003913 | 400399610 | High Sign | HFTD Tier 2 | Distribution | 2007-10-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003914 | 400399780 | High Sign | HFTD Tier 2 | Distribution | 2004-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003915 | 400399954 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003916 | 400399978 | Molding | HFTD Tier 3 | Distribution | 2008-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003917 | 400399984 | High Sign | HFTD Tier 2 | Distribution | 2001-01-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003918 | 400400395 | High Sign | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003919 | 400400491 | Guy | HFTD Tier 3 | Distribution | 2005-09-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003920 | 400400564 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003921 | 400401020 | High Sign | HFTD Tier 2 | Distribution | 2004-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003922 | 400401122 | Molding | HFTD Tier 3 | Distribution | 2004-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003923 | 400401334 | High Sign | HFTD Tier 2 | Distribution | 2004-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003924 | 400401500 | Guy | HFTD Tier 3 | Distribution | 2003-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003925 | 400401503 | High Sign | HFTD Tier 2 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003926 | 400401535 | High Sign | HFTD Tier 3 | Distribution | 2008-12-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003927 | 400401542 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003928 | 400401732 | High Sign | HFTD Tier 3 | Distribution | 2008-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003929 | 400401760 | High Sign | HFTD Tier 2 | Distribution | 2009-09-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003930 | 400401910 | High Sign | HFTD Tier 2 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003931 | 400402055 | High Sign | HFTD Tier 2 | Distribution | 2005-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003932 | 400402151 | Molding | HFTD Tier 2 | Distribution | 2004-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003933 | 400402413 | Riser/Conduit | HFTD Tier 2 | Distribution | 2004-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003934 | 400402437 | High Sign | HFTD Tier 3 | Distribution | 2005-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003935 | 400402503 | Molding | HFTD Tier 3 | Distribution | 2006-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003936 | 400402531 | Molding | HFTD Tier 2 | Distribution | 2004-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003937 | 400402603 | High Sign | HFTD Tier 2 | Distribution | 2005-08-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003938 | 400402809 | Molding | HFTD Tier 2 | Distribution | 2006-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003939 | 400402869 | Molding | HFTD Tier 3 | Distribution | 2008-01-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003940 | 400403178 | High Sign | HFTD Tier 2 | Distribution | 2003-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003941 | 400403194 | Molding | HFTD Tier 2 | Distribution | 2007-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003942 | 400403391 | High Sign | HFTD Tier 3 | Distribution | 2004-03-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003943 | 400403520 | Guy | HFTD Tier 3 | Distribution | 2003-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003944 | 400403652 | Molding | HFTD Tier 3 | Distribution | 2005-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003945 | 400403681 | Molding | HFTD Tier 3 | Distribution | 2005-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003946 | 400403744 | Molding | HFTD Tier 3 | Distribution | 2005-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003947 | 400403927 | Molding | HFTD Tier 2 | Distribution | 2004-06-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003948 | 400404650 | High Sign | HFTD Tier 2 | Distribution | 2009-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003949 | 400404938 | High Sign | HFTD Tier 3 | Distribution | 2004-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003950 | 400404945 | High Sign | HFTD Tier 2 | Distribution | 2003-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003951 | 400405172 | High Sign | HFTD Tier 3 | Distribution | 2004-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003952 | 400405276 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003953 | 400405294 | Molding | HFTD Tier 3 | Distribution | 2004-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003954 | 400405313 | High Sign | HFTD Tier 3 | Distribution | 2004-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003955 | 400405374 | Molding | HFTD Tier 2 | Distribution | 2004-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003956 | 400405429 | High Sign | HFTD Tier 3 | Distribution | 2004-03-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003957 | 400405453 | High Sign | HFTD Tier 3 | Distribution | 2004-03-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003958 | 400405468 | High Sign | HFTD Tier 3 | Distribution | 2004-03-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003959 | 400405483 | High Sign | HFTD Tier 2 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003960 | 400405714 | Molding | HFTD Tier 2 | Distribution | 2005-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003961 | 400405881 | Molding | HFTD Tier 2 | Distribution | 2004-07-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003962 | 400405986 | High Sign | HFTD Tier 3 | Distribution | 2009-04-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003963 | 400406054 | High Sign | HFTD Tier 2 | Distribution | 2009-09-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003964 | 400406308 | High Sign | HFTD Tier 2 | Distribution | 2004-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003965 | 400406314 | Molding | HFTD Tier 3 | Distribution | 2004-12-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003966 | 400406344 | High Sign | HFTD Tier 2 | Distribution | 2003-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003967 | 400406370 | Molding | HFTD Tier 3 | Distribution | 2004-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003968 | 400406372 | Hardware/Framing | HFTD Tier 2 | Distribution | 2004-06-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003969 | 400406390 | High Sign | HFTD Tier 3 | Distribution | 2004-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003970 | 400406403 | Riser/Conduit | HFTD Tier 3 | Distribution | 2005-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003971 | 400406416 | Molding | HFTD Tier 2 | Distribution | 2004-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003972 | 400406513 | High Sign | HFTD Tier 3 | Distribution | 2004-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003973 | 400406517 | Guy | HFTD Tier 3 | Distribution | 2004-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003974 | 400406521 | Molding | HFTD Tier 2 | Distribution | 2004-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003975 | 400406551 | High Sign | HFTD Tier 2 | Distribution | 2005-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003976 | 400406674 | High Sign | HFTD Tier 2 | Distribution | 2003-09-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003977 | 400406685 | High Sign | HFTD Tier 3 | Distribution | 2005-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003978 | 400406794 | Molding | HFTD Tier 2 | Distribution | 2003-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003979 | 400407240 | High Sign | HFTD Tier 3 | Distribution | 2004-03-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003980 | 400407521 | Molding | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003981 | 400407799 | High Sign | HFTD Tier 2 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003982 | 400407967 | High Sign | HFTD Tier 2 | Distribution | 2004-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003983 | 400408207 | Molding | HFTD Tier 2 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003984 | 400408387 | Guy | HFTD Tier 3 | Distribution | 2005-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003985 | 400408403 | Molding | HFTD Tier 3 | Distribution | 2008-02-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003986 | 400408409 | Molding | HFTD Tier 3 | Distribution | 2010-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003987 | 400409087 | Molding | HFTD Tier 3 | Distribution | 2005-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003988 | 400409337 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003989 | 400409342 | Molding | HFTD Tier 3 | Distribution | 2005-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003990 | 400409436 | Molding | HFTD Tier 2 | Distribution | 2005-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003991 | 400409516 | Molding | HFTD Tier 2 | Distribution | 2005-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003992 | 400409627 | High Sign | HFTD Tier 2 | Distribution | 2004-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003993 | 400409768 | High Sign | HFTD Tier 2 | Distribution | 2004-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003994 | 400409817 | Molding | HFTD Tier 3 | Distribution | 2005-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003995 | 400409829 | High Sign | HFTD Tier 3 | Distribution | 2007-10-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003996 | 400410064 | Molding | HFTD Tier 2 | Distribution | 2004-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003997 | 400410141 | High Sign | HFTD Tier 3 | Distribution | 2004-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003998 | 400410144 | High Sign | HFTD Tier 3 | Distribution | 2003-11-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130003999 | 400410360 | High Sign | HFTD Tier 2 | Distribution | 2004-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004000 | 400410476 | Molding | HFTD Tier 2 | Distribution | 2009-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004001 | 400410691 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004002 | 400410766 | High Sign | HFTD Tier 2 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004003 | 400410823 | High Sign | HFTD Tier 3 | Distribution | 2000-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004004 | 400410947 | Insulator | HFTD Tier 3 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004005 | 400411046 | High Sign | HFTD Tier 3 | Distribution | 2004-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004006 | 400411071 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004007 | 400411121 | Molding | HFTD Tier 3 | Distribution | 2005-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004008 | 400411496 | Molding | HFTD Tier 2 | Distribution | 2005-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004009 | 400411551 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004010 | 400411857 | Molding | HFTD Tier 3 | Distribution | 2005-12-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004011 | 400411878 | High Sign | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004012 | 400412397 | Molding | HFTD Tier 2 | Distribution | 2008-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004013 | 400412457 | High Sign | HFTD Tier 2 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004014 | 400412712 | Guy | HFTD Tier 2 | Distribution | 2004-10-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004015 | 400413055 | Guy | HFTD Tier 2 | Distribution | 2002-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004016 | 400413314 | High Sign | HFTD Tier 2 | Distribution | 2004-08-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004017 | 400413666 | High Sign | HFTD Tier 3 | Distribution | 2004-12-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004018 | 400413946 | Molding | HFTD Tier 3 | Distribution | 2005-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004019 | 400414065 | High Sign | HFTD Tier 2 | Distribution | 2005-08-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004020 | 400414088 | Molding | HFTD Tier 3 | Distribution | 2005-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004021 | 400414105 | Hardware/Framing | HFTD Tier 2 | Distribution | 2004-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004022 | 400414164 | High Sign | HFTD Tier 3 | Distribution | 2003-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004023 | 400414346 | High Sign | HFTD Tier 2 | Distribution | 2004-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004024 | 400414419 | High Sign | HFTD Tier 2 | Distribution | 2004-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004025 | 400414441 | High Sign | HFTD Tier 2 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004026 | 400414510 | High Sign | HFTD Tier 2 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004027 | 400414550 | High Sign | HFTD Tier 2 | Distribution | 2005-08-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004028 | 400414681 | Molding | HFTD Tier 3 | Distribution | 2005-12-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004029 | 400414732 | High Sign | HFTD Tier 2 | Distribution | 2004-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004030 | 400415002 | Insulator | HFTD Tier 2 | Distribution | 2009-11-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004031 | 400415099 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004032 | 400415224 | High Sign | HFTD Tier 2 | Distribution | 2004-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004033 | 400415440 | Molding | HFTD Tier 3 | Distribution | 2004-09-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004034 | 400415493 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004035 | 400415555 | High Sign | HFTD Tier 2 | Distribution | 2005-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004036 | 400415627 | Riser/Conduit | HFTD Tier 3 | Distribution | 2008-12-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004037 | 400415662 | High Sign | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004038 | 400415678 | Molding | HFTD Tier 3 | Distribution | 2005-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004039 | 400415770 | Molding | HFTD Tier 2 | Distribution | 2003-11-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004040 | 400415892 | High Sign | HFTD Tier 3 | Distribution | 2004-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004041 | 400415909 | Molding | HFTD Tier 2 | Distribution | 2010-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004042 | 400416073 | Molding | HFTD Tier 3 | Distribution | 2004-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004043 | 400416277 | High Sign | HFTD Tier 3 | Distribution | 2004-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004044 | 400416485 | Molding | HFTD Tier 2 | Distribution | 2009-01-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004045 | 400416513 | Molding | HFTD Tier 2 | Distribution | 2004-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004046 | 400417050 | High Sign | HFTD Tier 2 | Distribution | 2005-08-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004047 | 400417252 | High Sign | HFTD Tier 3 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004048 | 400417310 | Molding | HFTD Tier 2 | Distribution | 2004-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004049 | 400417332 | High Sign | HFTD Tier 2 | Distribution | 2004-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004050 | 400417580 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004051 | 400417599 | Insulator | HFTD Tier 2 | Distribution | 2004-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004052 | 400417617 | High Sign | HFTD Tier 2 | Distribution | 2004-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004053 | 400417647 | High Sign | HFTD Tier 2 | Distribution | 2004-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004054 | 400417728 | Molding | HFTD Tier 2 | Distribution | 2008-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004055 | 400417903 | High Sign | HFTD Tier 3 | Distribution | 2004-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004056 | 400417905 | High Sign | HFTD Tier 3 | Distribution | 2004-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004057 | 400418021 | Molding | HFTD Tier 3 | Distribution | 2001-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004058 | 400418028 | High Sign | HFTD Tier 2 | Distribution | 2004-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004059 | 400418065 | High Sign | HFTD Tier 2 | Distribution | 2004-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004060 | 400418376 | High Sign | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004061 | 400418472 | Cable/Conductor | HFTD Tier 2 | Distribution | 2005-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004062 | 400418475 | Molding | HFTD Tier 3 | Distribution | 2005-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004063 | 400418641 | Molding | HFTD Tier 3 | Distribution | 2005-09-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004064 | 400418646 | Molding | HFTD Tier 3 | Distribution | 2005-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004065 | 400419244 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004066 | 400419553 | Molding | HFTD Tier 3 | Distribution | 2004-04-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004067 | 400419561 | Molding | HFTD Tier 2 | Distribution | 2005-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004068 | 400419807 | High Sign | HFTD Tier 3 | Distribution | 2004-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004069 | 400419948 | High Sign | HFTD Tier 3 | Distribution | 2004-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004070 | 400420087 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004071 | 400420146 | High Sign | HFTD Tier 2 | Distribution | 2004-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004072 | 400420163 | High Sign | HFTD Tier 3 | Distribution | 2008-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004073 | 400420172 | High Sign | HFTD Tier 2 | Distribution | 2004-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004074 | 400420212 | High Sign | HFTD Tier 3 | Distribution | 2004-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004075 | 400420225 | Molding | HFTD Tier 2 | Distribution | 2003-10-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004076 | 400420310 | Molding | HFTD Tier 3 | Distribution | 2001-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004077 | 400420344 | High Sign | HFTD Tier 2 | Distribution | 2004-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004078 | 400420349 | High Sign | HFTD Tier 3 | Distribution | 2009-07-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004079 | 400420805 | High Sign | HFTD Tier 2 | Distribution | 2004-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004080 | 400420823 | Guy | HFTD Tier 2 | Distribution | 2003-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004081 | 400420915 | High Sign | HFTD Tier 2 | Distribution | 2004-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004082 | 400421197 | Molding | HFTD Tier 2 | Distribution | 2004-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004083 | 400421259 | High Sign | HFTD Tier 2 | Distribution | 2004-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004084 | 400421286 | High Sign | HFTD Tier 3 | Distribution | 2008-08-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004085 | 400421357 | High Sign | HFTD Tier 2 | Distribution | 2005-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004086 | 400421456 | High Sign | HFTD Tier 3 | Distribution | 2003-12-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004087 | 400421773 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004088 | 400421787 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004089 | 400421860 | High Sign | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004090 | 400421963 | Guy | HFTD Tier 3 | Distribution | 2009-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004091 | 400422099 | High Sign | HFTD Tier 2 | Distribution | 2005-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004092 | 400422708 | Guy | HFTD Tier 3 | Distribution | 2004-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004093 | 400422826 | High Sign | HFTD Tier 2 | Distribution | 2009-10-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004094 | 400422883 | Molding | HFTD Tier 3 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004095 | 400422922 | High Sign | HFTD Tier 2 | Distribution | 2005-02-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004096 | 400423159 | High Sign | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004097 | 400423221 | High Sign | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004098 | 400423252 | Molding | HFTD Tier 2 | Distribution | 2004-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004099 | 400423654 | High Sign | HFTD Tier 3 | Distribution | 2009-08-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004100 | 400423668 | High Sign | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004101 | 400423823 | Guy | HFTD Tier 3 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004102 | 400423833 | Molding | HFTD Tier 3 | Distribution | 2004-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004103 | 400424363 | Molding | HFTD Tier 3 | Distribution | 2009-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004104 | 400424414 | Molding | HFTD Tier 3 | Distribution | 2008-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004105 | 400424745 | Molding | HFTD Tier 2 | Distribution | 2005-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004106 | 400424838 | Molding | HFTD Tier 3 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004107 | 400424904 | High Sign | HFTD Tier 3 | Distribution | 2001-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004108 | 400424990 | Guy | HFTD Tier 2 | Distribution | 2004-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004109 | 400425138 | Guy | HFTD Tier 3 | Distribution | 2004-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004110 | 400425236 | Molding | HFTD Tier 2 | Distribution | 2004-07-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004111 | 400425335 | High Sign | HFTD Tier 3 | Distribution | 2009-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004112 | 400425450 | Guy | HFTD Tier 3 | Distribution | 2008-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004113 | 400425464 | High Sign | HFTD Tier 3 | Distribution | 2004-09-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004114 | 400425580 | High Sign | HFTD Tier 2 | Distribution | 2009-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004115 | 400425717 | Molding | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004116 | 400425930 | High Sign | HFTD Tier 2 | Distribution | 2009-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004117 | 400426014 | High Sign | HFTD Tier 2 | Distribution | 2003-10-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004118 | 400426016 | High Sign | HFTD Tier 3 | Distribution | 2008-02-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004119 | 400426101 | High Sign | HFTD Tier 2 | Distribution | 2003-11-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004120 | 400426246 | High Sign | HFTD Tier 3 | Distribution | 2009-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004121 | 400426326 | Molding | HFTD Tier 2 | Distribution | 2008-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004122 | 400426435 | High Sign | HFTD Tier 2 | Distribution | 2004-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004123 | 400426463 | Molding | HFTD Tier 3 | Distribution | 2006-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004124 | 400426539 | High Sign | HFTD Tier 3 | Distribution | 2008-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004125 | 400426933 | High Sign | HFTD Tier 2 | Distribution | 2004-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004126 | 400427191 | High Sign | HFTD Tier 3 | Distribution | 2004-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004127 | 400427207 | Molding | HFTD Tier 3 | Distribution | 2003-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004128 | 400427261 | Molding | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004129 | 400427332 | Molding | HFTD Tier 2 | Distribution | 2007-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004130 | 400427345 | High Sign | HFTD Tier 3 | Distribution | 2009-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004131 | 400427366 | High Sign | HFTD Tier 2 | Distribution | 2003-10-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004132 | 400427377 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004133 | 400427408 | Molding | HFTD Tier 3 | Distribution | 2004-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004134 | 400427472 | High Sign | HFTD Tier 2 | Distribution | 2005-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004135 | 400427532 | Molding | HFTD Tier 2 | Distribution | 2005-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004136 | 400427563 | High Sign | HFTD Tier 3 | Distribution | 2005-05-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004137 | 400427635 | Molding | HFTD Tier 3 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004138 | 400427810 | Molding | HFTD Tier 3 | Distribution | 2003-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004139 | 400427826 | Molding | HFTD Tier 3 | Distribution | 2005-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004140 | 400427831 | Molding | HFTD Tier 3 | Distribution | 2004-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004141 | 400427928 | High Sign | HFTD Tier 2 | Distribution | 2009-11-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004142 | 400427957 | KV Cable Tags | HFTD Tier 3 | Distribution | 2008-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004143 | 400428049 | High Sign | HFTD Tier 2 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004144 | 400428197 | Molding | HFTD Tier 3 | Distribution | 2005-08-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004145 | 400428213 | Molding | HFTD Tier 3 | Distribution | 2008-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004146 | 400428233 | Guy | HFTD Tier 3 | Distribution | 2004-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004147 | 400428357 | High Sign | HFTD Tier 3 | Distribution | 2004-08-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004148 | 400428429 | Molding | HFTD Tier 2 | Distribution | 2005-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004149 | 400428491 | High Sign | HFTD Tier 3 | Distribution | 2004-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004150 | 400428514 | Guy | HFTD Tier 3 | Distribution | 2005-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004151 | 400428559 | Molding | HFTD Tier 3 | Distribution | 2004-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004152 | 400428673 | High Sign | HFTD Tier 2 | Distribution | 2009-11-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004153 | 400428815 | High Sign | HFTD Tier 2 | Distribution | 2003-11-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004154 | 400428854 | Molding | HFTD Tier 3 | Distribution | 2005-10-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004155 | 400428871 | High Sign | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004156 | 400428941 | Molding | HFTD Tier 3 | Distribution | 2005-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004157 | 400428944 | High Sign | HFTD Tier 2 | Distribution | 2005-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004158 | 400428995 | Molding | HFTD Tier 2 | Distribution | 2008-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004159 | 400429072 | High Sign | HFTD Tier 3 | Distribution | 2008-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004160 | 400429510 | High Sign | HFTD Tier 3 | Distribution | 2009-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004161 | 400429798 | Molding | HFTD Tier 2 | Distribution | 2004-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004162 | 400429925 | Molding | HFTD Tier 2 | Distribution | 2005-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004163 | 400429951 | High Sign | HFTD Tier 2 | Distribution | 2005-08-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004164 | 400429955 | High Sign | HFTD Tier 2 | Distribution | 2005-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004165 | 400430168 | Molding | HFTD Tier 2 | Distribution | 2004-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004166 | 400430202 | High Sign | HFTD Tier 2 | Distribution | 2009-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004167 | 400430230 | High Sign | HFTD Tier 2 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004168 | 400430260 | High Sign | HFTD Tier 2 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004169 | 400430341 | Molding | HFTD Tier 3 | Distribution | 2004-10-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004170 | 400430418 | KV Cable Tags | HFTD Tier 3 | Distribution | 2008-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004171 | 400430484 | Anchor | HFTD Tier 3 | Distribution | 2009-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004172 | 400430499 | High Sign | HFTD Tier 2 | Distribution | 2009-10-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004173 | 400430525 | High Sign | HFTD Tier 2 | Distribution | 2009-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004174 | 400430552 | Molding | HFTD Tier 2 | Distribution | 2009-09-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004175 | 400430826 | Guy | HFTD Tier 3 | Distribution | 2005-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004176 | 400430899 | High Sign | HFTD Tier 2 | Distribution | 2003-11-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004177 | 400430970 | Molding | HFTD Tier 3 | Distribution | 2005-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004178 | 400430980 | Riser/Conduit | HFTD Tier 3 | Distribution | 2009-12-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004179 | 400431019 | High Sign | HFTD Tier 2 | Distribution | 2009-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004180 | 400431187 | Molding | HFTD Tier 2 | Distribution | 2010-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004181 | 400431204 | Molding | HFTD Tier 3 | Distribution | 2001-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004182 | 400431353 | Molding | HFTD Tier 3 | Distribution | 2001-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004183 | 400431417 | High Sign | HFTD Tier 3 | Distribution | 2004-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004184 | 400431586 | Molding | HFTD Tier 3 | Distribution | 2004-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004185 | 400431830 | High Sign | HFTD Tier 3 | Distribution | 2001-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004186 | 400432105 | High Sign | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004187 | 400432241 | Molding | HFTD Tier 2 | Distribution | 2005-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004188 | 400432387 | Guy | HFTD Tier 3 | Distribution | 2005-08-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004189 | 400432478 | Molding | HFTD Tier 3 | Distribution | 2009-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004190 | 400432602 | High Sign | HFTD Tier 2 | Distribution | 2003-10-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004191 | 400432747 | High Sign | HFTD Tier 3 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004192 | 400432849 | Molding | HFTD Tier 3 | Distribution | 2008-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004193 | 400432853 | High Sign | HFTD Tier 2 | Distribution | 2004-08-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004194 | 400432982 | High Sign | HFTD Tier 3 | Distribution | 2009-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004195 | 400433099 | Riser/Conduit | HFTD Tier 2 | Distribution | 2009-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004196 | 400433108 | Molding | HFTD Tier 3 | Distribution | 2005-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004197 | 400433109 | High Sign | HFTD Tier 2 | Distribution | 2005-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004198 | 400433208 | High Sign | HFTD Tier 2 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004199 | 400433236 | Guy | HFTD Tier 3 | Distribution | 2004-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004200 | 400433244 | Molding | HFTD Tier 2 | Distribution | 2007-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004201 | 400433251 | Molding | HFTD Tier 3 | Distribution | 2005-08-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004202 | 400433315 | Molding | HFTD Tier 3 | Distribution | 2009-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004203 | 400433326 | Cable/Conductor | HFTD Tier 3 | Distribution | 2008-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004204 | 400433571 | Insulator | HFTD Tier 2 | Distribution | 2004-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004205 | 400433572 | High Sign | HFTD Tier 3 | Distribution | 2004-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004206 | 400433666 | Molding | HFTD Tier 3 | Distribution | 2009-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004207 | 400433708 | Molding | HFTD Tier 3 | Distribution | 2009-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004208 | 400433900 | High Sign | HFTD Tier 3 | Distribution | 2003-10-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004209 | 400433922 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004210 | 400433932 | Molding | HFTD Tier 3 | Distribution | 2009-09-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004211 | 400433966 | High Sign | HFTD Tier 3 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004212 | 400434164 | High Sign | HFTD Tier 3 | Distribution | 2004-04-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004213 | 400434187 | High Sign | HFTD Tier 2 | Distribution | 2005-10-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004214 | 400434195 | High Sign | HFTD Tier 2 | Distribution | 2004-07-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004215 | 400434220 | High Sign | HFTD Tier 3 | Distribution | 2008-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004216 | 400434344 | High Sign | HFTD Tier 2 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004217 | 400434572 | Molding | HFTD Tier 2 | Distribution | 2009-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004218 | 400434613 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2005-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004219 | 400434629 | High Sign | HFTD Tier 3 | Distribution | 2009-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004220 | 400434655 | High Sign | HFTD Tier 3 | Distribution | 2009-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004221 | 400434695 | High Sign | HFTD Tier 2 | Distribution | 2004-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004222 | 400434712 | Molding | HFTD Tier 2 | Distribution | 2003-09-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004223 | 400435090 | Guy | HFTD Tier 3 | Distribution | 2004-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004224 | 400435255 | Guy | HFTD Tier 2 | Distribution | 2005-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004225 | 400435480 | High Sign | HFTD Tier 3 | Distribution | 2005-08-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004226 | 400435697 | Molding | HFTD Tier 3 | Distribution | 2003-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004227 | 400435763 | High Sign | HFTD Tier 3 | Distribution | 2009-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004228 | 400435995 | Molding | HFTD Tier 3 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004229 | 400436014 | High Sign | HFTD Tier 3 | Distribution | 2009-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004230 | 400436017 | High Sign | HFTD Tier 2 | Distribution | 2004-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004231 | 400436090 | High Sign | HFTD Tier 3 | Distribution | 2000-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004232 | 400436092 | High Sign | HFTD Tier 3 | Distribution | 2005-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004233 | 400436329 | Molding | HFTD Tier 3 | Distribution | 2005-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004234 | 400436429 | Molding | HFTD Tier 3 | Distribution | 2009-09-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004235 | 400436502 | High Sign | HFTD Tier 2 | Distribution | 2009-11-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004236 | 400436843 | High Sign | HFTD Tier 3 | Distribution | 2005-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004237 | 400436851 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-05-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004238 | 400437128 | High Sign | HFTD Tier 3 | Distribution | 2005-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004239 | 400437207 | High Sign | HFTD Tier 2 | Distribution | 2005-08-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004240 | 400437319 | High Sign | HFTD Tier 2 | Distribution | 2003-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004241 | 400437407 | Molding | HFTD Tier 2 | Distribution | 2008-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004242 | 400437487 | Molding | HFTD Tier 3 | Distribution | 2008-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004243 | 400437582 | Guy | HFTD Tier 3 | Distribution | 2005-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004244 | 400437744 | High Sign | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004245 | 400437786 | Riser/Conduit | HFTD Tier 2 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004246 | 400437864 | Guy | HFTD Tier 3 | Distribution | 2004-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004247 | 400438157 | Molding | HFTD Tier 3 | Distribution | 2004-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004248 | 400438219 | High Sign | HFTD Tier 3 | Distribution | 2010-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004249 | 400438258 | High Sign | HFTD Tier 3 | Distribution | 2004-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004250 | 400438827 | Molding | HFTD Tier 2 | Distribution | 2008-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004251 | 400439170 | High Sign | HFTD Tier 3 | Distribution | 2004-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004252 | 400439270 | Molding | HFTD Tier 2 | Distribution | 2007-10-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004253 | 400439334 | Molding | HFTD Tier 3 | Distribution | 2010-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004254 | 400439427 | Guy | HFTD Tier 3 | Distribution | 2009-11-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004255 | 400439592 | Molding | HFTD Tier 2 | Distribution | 2008-07-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004256 | 400439627 | Molding | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004257 | 400439660 | High Sign | HFTD Tier 3 | Distribution | 2005-05-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004258 | 400439680 | High Sign | HFTD Tier 3 | Distribution | 2004-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004259 | 400439752 | Molding | HFTD Tier 3 | Distribution | 2004-09-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004260 | 400440044 | Riser/Conduit | HFTD Tier 2 | Distribution | 2005-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004261 | 400440149 | Molding | HFTD Tier 3 | Distribution | 2001-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004262 | 400440209 | Molding | HFTD Tier 3 | Distribution | 2008-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004263 | 400440233 | High Sign | HFTD Tier 3 | Distribution | 2004-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004264 | 400440297 | Riser/Conduit | HFTD Tier 3 | Distribution | 2004-08-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004265 | 400440499 | High Sign | HFTD Tier 2 | Distribution | 2003-09-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004266 | 400440522 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004267 | 400440702 | Molding | HFTD Tier 3 | Distribution | 2009-09-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004268 | 400440916 | High Sign | HFTD Tier 3 | Distribution | 2010-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004269 | 400441166 | KV Cable Tags | HFTD Tier 2 | Distribution | 2008-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004270 | 400441284 | Molding | HFTD Tier 2 | Distribution | 2004-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004271 | 400441309 | Molding | HFTD Tier 3 | Distribution | 2004-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004272 | 400441385 | High Sign | HFTD Tier 3 | Distribution | 2005-08-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004273 | 400441439 | Riser/Conduit | HFTD Tier 3 | Distribution | 2009-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004274 | 400441608 | High Sign | HFTD Tier 2 | Distribution | 2004-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004275 | 400441822 | High Sign | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004276 | 400441975 | High Sign | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004277 | 400442075 | High Sign | HFTD Tier 2 | Distribution | 2003-09-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004278 | 400442104 | Molding | HFTD Tier 2 | Distribution | 2005-08-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004279 | 400442329 | High Sign | HFTD Tier 3 | Distribution | 2004-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004280 | 400442422 | Molding | HFTD Tier 2 | Distribution | 2004-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004281 | 400442447 | Molding | HFTD Tier 3 | Distribution | 2004-09-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004282 | 400442546 | Guy | HFTD Tier 3 | Distribution | 2005-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004283 | 400442907 | Termination | HFTD Tier 3 | Distribution | 2008-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004284 | 400443032 | Molding | HFTD Tier 2 | Distribution | 2003-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004285 | 400443052 | High Sign | HFTD Tier 2 | Distribution | 2004-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004286 | 400443143 | Molding | HFTD Tier 3 | Distribution | 2009-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004287 | 400443200 | High Sign | HFTD Tier 2 | Distribution | 2009-08-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004288 | 400443358 | High Sign | HFTD Tier 2 | Distribution | 2005-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004289 | 400443405 | Insulator | HFTD Tier 2 | Distribution | 2004-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004290 | 400443814 | Molding | HFTD Tier 3 | Distribution | 2004-01-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004291 | 400443874 | High Sign | HFTD Tier 3 | Distribution | 2001-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004292 | 400443953 | Molding | HFTD Tier 2 | Distribution | 2008-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004293 | 400444132 | High Sign | HFTD Tier 2 | Distribution | 2009-10-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004294 | 400444216 | High Sign | HFTD Tier 3 | Distribution | 2008-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004295 | 400444324 | Molding | HFTD Tier 3 | Distribution | 2009-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004296 | 400444328 | High Sign | HFTD Tier 2 | Distribution | 2004-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004297 | 400444370 | Riser/Conduit | HFTD Tier 3 | Distribution | 2005-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004298 | 400444428 | High Sign | HFTD Tier 2 | Distribution | 2000-12-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004299 | 400444728 | High Sign | HFTD Tier 2 | Distribution | 2009-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004300 | 400444737 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2004-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004301 | 400444782 | Molding | HFTD Tier 3 | Distribution | 2003-11-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004302 | 400444973 | High Sign | HFTD Tier 3 | Distribution | 2004-09-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004303 | 400445082 | Molding | HFTD Tier 3 | Distribution | 2001-09-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004304 | 400445346 | Molding | HFTD Tier 3 | Distribution | 2005-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004305 | 400445467 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004306 | 400445563 | Molding | HFTD Tier 3 | Distribution | 2004-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004307 | 400445565 | Molding | HFTD Tier 2 | Distribution | 2003-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004308 | 400445799 | Molding | HFTD Tier 3 | Distribution | 2005-10-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004309 | 400445921 | High Sign | HFTD Tier 3 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004310 | 400445946 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2008-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004311 | 400446072 | High Sign | HFTD Tier 3 | Distribution | 2001-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004312 | 400446419 | High Sign | HFTD Tier 3 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004313 | 400446479 | Molding | HFTD Tier 2 | Distribution | 2009-10-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004314 | 400446576 | Molding | HFTD Tier 3 | Distribution | 2006-04-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004315 | 400446652 | Molding | HFTD Tier 3 | Distribution | 2001-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004316 | 400446657 | High Sign | HFTD Tier 3 | Distribution | 2004-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004317 | 400446893 | Hardware/Framing | HFTD Tier 3 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004318 | 400447145 | High Sign | HFTD Tier 3 | Distribution | 2010-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004319 | 400447305 | High Sign | HFTD Tier 3 | Distribution | 2009-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004320 | 400447308 | Molding | HFTD Tier 3 | Distribution | 2008-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004321 | 400447383 | High Sign | HFTD Tier 3 | Distribution | 2004-09-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004322 | 400447414 | Molding | HFTD Tier 3 | Distribution | 2001-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004323 | 400447545 | Riser/Conduit | HFTD Tier 3 | Distribution | 2010-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004324 | 400447662 | High Sign | HFTD Tier 2 | Distribution | 2003-09-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004325 | 400447750 | Molding | HFTD Tier 3 | Distribution | 2003-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004326 | 400447809 | High Sign | HFTD Tier 3 | Distribution | 2008-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004327 | 400447882 | Guy | HFTD Tier 3 | Distribution | 2004-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004328 | 400448259 | Guy | HFTD Tier 3 | Distribution | 2005-05-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004329 | 400448912 | High Sign | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004330 | 400449016 | Molding | HFTD Tier 2 | Distribution | 2009-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004331 | 400449043 | High Sign | HFTD Tier 3 | Distribution | 2004-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004332 | 400449322 | High Sign | HFTD Tier 3 | Distribution | 2001-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004333 | 400450122 | Molding | HFTD Tier 3 | Distribution | 2004-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004334 | 400450130 | Molding | HFTD Tier 3 | Distribution | 2004-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004335 | 400450216 | High Sign | HFTD Tier 2 | Distribution | 2004-09-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004336 | 400450322 | High Sign | HFTD Tier 2 | Distribution | 2008-02-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004337 | 400450381 | High Sign | HFTD Tier 3 | Distribution | 2004-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004338 | 400450393 | Molding | HFTD Tier 2 | Distribution | 2004-12-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004339 | 400450406 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004340 | 400450466 | Molding | HFTD Tier 2 | Distribution | 2004-04-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004341 | 400450607 | High Sign | HFTD Tier 3 | Distribution | 2008-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004342 | 400450795 | High Sign | HFTD Tier 3 | Distribution | 2006-02-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004343 | 400450947 | High Sign | HFTD Tier 2 | Distribution | 2005-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004344 | 400451015 | High Sign | HFTD Tier 2 | Distribution | 2003-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004345 | 400451203 | High Sign | HFTD Tier 2 | Distribution | 2003-11-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004346 | 400451228 | High Sign | HFTD Tier 2 | Distribution | 2003-11-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004347 | 400451237 | High Sign | HFTD Tier 3 | Distribution | 2001-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004348 | 400451288 | High Sign | HFTD Tier 2 | Distribution | 2004-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004349 | 400451311 | High Sign | HFTD Tier 2 | Distribution | 2004-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004350 | 400451615 | High Sign | HFTD Tier 2 | Distribution | 2005-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004351 | 400451706 | Hardware/Framing | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004352 | 400451714 | Guy | HFTD Tier 3 | Distribution | 2009-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004353 | 400451807 | Molding | HFTD Tier 2 | Distribution | 2008-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004354 | 400451868 | High Sign | HFTD Tier 2 | Distribution | 2005-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004355 | 400451970 | High Sign | HFTD Tier 2 | Distribution | 2005-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004356 | 400452180 | High Sign | HFTD Tier 2 | Distribution | 2010-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004357 | 400452271 | Molding | HFTD Tier 3 | Distribution | 2005-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004358 | 400452303 | Molding | HFTD Tier 2 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004359 | 400452309 | Molding | HFTD Tier 2 | Distribution | 2005-08-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004360 | 400452432 | Molding | HFTD Tier 3 | Distribution | 2005-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004361 | 400452629 | Guy | HFTD Tier 3 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004362 | 400452667 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004363 | 400452693 | Molding | HFTD Tier 2 | Distribution | 2006-02-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004364 | 400452917 | Molding | HFTD Tier 2 | Distribution | 2009-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004365 | 400453060 | Molding | HFTD Tier 2 | Distribution | 2003-11-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004366 | 400453338 | Molding | HFTD Tier 3 | Distribution | 2004-06-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004367 | 400453370 | High Sign | HFTD Tier 2 | Distribution | 2004-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004368 | 400453488 | Molding | HFTD Tier 2 | Distribution | 2005-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004369 | 400453494 | Molding | HFTD Tier 3 | Distribution | 2001-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004370 | 400453540 | Molding | HFTD Tier 3 | Distribution | 2005-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004371 | 400453585 | High Sign | HFTD Tier 2 | Distribution | 2004-04-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004372 | 400453636 | Insulator | HFTD Tier 2 | Distribution | 2004-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004373 | 400453680 | High Sign | HFTD Tier 3 | Distribution | 2008-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004374 | 400453735 | High Sign | HFTD Tier 3 | Distribution | 2005-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004375 | 400453762 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2004-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004376 | 400453910 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004377 | 400454107 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004378 | 400454263 | Molding | HFTD Tier 3 | Distribution | 2004-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004379 | 400454335 | Molding | HFTD Tier 2 | Distribution | 2005-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004380 | 400454359 | Molding | HFTD Tier 2 | Distribution | 2004-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004381 | 400454428 | Guy | HFTD Tier 2 | Distribution | 2008-07-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004382 | 400454450 | High Sign | HFTD Tier 2 | Distribution | 2004-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004383 | 400454456 | Molding | HFTD Tier 3 | Distribution | 2003-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004384 | 400454596 | High Sign | HFTD Tier 3 | Distribution | 2004-07-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004385 | 400454651 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004386 | 400454755 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004387 | 400454945 | High Sign | HFTD Tier 3 | Distribution | 2005-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004388 | 400455027 | Molding | HFTD Tier 2 | Distribution | 2009-10-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004389 | 400455154 | Molding | HFTD Tier 3 | Distribution | 2008-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004390 | 400455184 | High Sign | HFTD Tier 2 | Distribution | 2010-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004391 | 400455210 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004392 | 400455325 | High Sign | HFTD Tier 2 | Distribution | 2004-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004393 | 400455384 | High Sign | HFTD Tier 2 | Distribution | 2004-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004394 | 400455445 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004395 | 400455459 | High Sign | HFTD Tier 2 | Distribution | 2004-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004396 | 400455699 | Molding | HFTD Tier 3 | Distribution | 2005-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004397 | 400456102 | High Sign | HFTD Tier 3 | Distribution | 2004-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004398 | 400456231 | High Sign | HFTD Tier 3 | Distribution | 2008-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004399 | 400456251 | Molding | HFTD Tier 3 | Distribution | 2005-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004400 | 400456683 | Molding | HFTD Tier 3 | Distribution | 2009-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004401 | 400456776 | High Sign | HFTD Tier 3 | Distribution | 2001-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004402 | 400456793 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2003-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004403 | 400457023 | High Sign | HFTD Tier 2 | Distribution | 2009-10-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004404 | 400457098 | High Sign | HFTD Tier 3 | Distribution | 2005-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004405 | 400457395 | High Sign | HFTD Tier 3 | Distribution | 2004-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004406 | 400457472 | High Sign | HFTD Tier 3 | Distribution | 2004-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004407 | 400457912 | Molding | HFTD Tier 3 | Distribution | 2005-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004408 | 400458026 | High Sign | HFTD Tier 2 | Distribution | 2005-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004409 | 400458056 | Molding | HFTD Tier 3 | Distribution | 2005-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004410 | 400458060 | Insulator | HFTD Tier 2 | Distribution | 2004-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004411 | 400458098 | Molding | HFTD Tier 2 | Distribution | 2004-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004412 | 400458100 | High Sign | HFTD Tier 3 | Distribution | 2005-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004413 | 400458115 | High Sign | HFTD Tier 3 | Distribution | 2004-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004414 | 400458273 | Crossarm | HFTD Tier 3 | Distribution | 2004-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004415 | 400458564 | Molding | HFTD Tier 2 | Distribution | 2004-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004416 | 400458618 | Molding | HFTD Tier 2 | Distribution | 2004-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004417 | 400458624 | Guy | HFTD Tier 3 | Distribution | 2010-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004418 | 400458652 | High Sign | HFTD Tier 2 | Distribution | 2005-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004419 | 400458748 | Molding | HFTD Tier 3 | Distribution | 2005-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004420 | 400458877 | High Sign | HFTD Tier 3 | Distribution | 2005-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004421 | 400458886 | High Sign | HFTD Tier 3 | Distribution | 2004-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004422 | 400458977 | Molding | HFTD Tier 3 | Distribution | 2004-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004423 | 400459015 | Molding | HFTD Tier 3 | Distribution | 2004-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004424 | 400459065 | High Sign | HFTD Tier 3 | Distribution | 2008-07-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004425 | 400459068 | Riser/Conduit | HFTD Tier 3 | Distribution | 2008-12-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004426 | 400459107 | High Sign | HFTD Tier 2 | Distribution | 2009-09-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004427 | 400459132 | High Sign | HFTD Tier 3 | Distribution | 2009-09-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004428 | 400459212 | Ground | HFTD Tier 2 | Distribution | 2004-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004429 | 400459308 | Molding | HFTD Tier 3 | Distribution | 2009-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004430 | 400459378 | Molding | HFTD Tier 2 | Distribution | 2005-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004431 | 400459530 | Molding | HFTD Tier 2 | Distribution | 2004-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004432 | 400459648 | High Sign | HFTD Tier 2 | Distribution | 2004-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004433 | 400459656 | High Sign | HFTD Tier 2 | Distribution | 2005-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004434 | 400459853 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004435 | 400460043 | High Sign | HFTD Tier 3 | Distribution | 2005-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004436 | 400460100 | Molding | HFTD Tier 3 | Distribution | 2001-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004437 | 400460149 | Molding | HFTD Tier 3 | Distribution | 2005-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004438 | 400460257 | Insulator | HFTD Tier 2 | Distribution | 2004-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004439 | 400460336 | High Sign | HFTD Tier 3 | Distribution | 2006-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004440 | 400460437 | Guy | HFTD Tier 3 | Distribution | 2003-10-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004441 | 400460482 | High Sign | HFTD Tier 2 | Distribution | 2003-10-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004442 | 400460574 | Molding | HFTD Tier 3 | Distribution | 2009-02-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004443 | 400460629 | Guy | HFTD Tier 3 | Distribution | 2003-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004444 | 400460868 | Hardware/Framing | HFTD Tier 3 | Distribution | 2004-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004445 | 400461162 | High Sign | HFTD Tier 3 | Distribution | 2001-11-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004446 | 400461234 | High Sign | HFTD Tier 2 | Distribution | 2004-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004447 | 400461290 | Molding | HFTD Tier 2 | Distribution | 2004-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004448 | 400461456 | High Sign | HFTD Tier 2 | Distribution | 2004-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004449 | 400461658 | High Sign | HFTD Tier 3 | Distribution | 2004-09-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004450 | 400461679 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004451 | 400461714 | Hardware/Framing | HFTD Tier 2 | Distribution | 2004-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004452 | 400461735 | High Sign | HFTD Tier 2 | Distribution | 2009-10-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004453 | 400461817 | High Sign | HFTD Tier 2 | Distribution | 2005-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004454 | 400462015 | High Sign | HFTD Tier 3 | Distribution | 2009-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004455 | 400462137 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004456 | 400462139 | Insulator | HFTD Tier 2 | Distribution | 2008-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004457 | 400462345 | Riser/Conduit | HFTD Tier 3 | Distribution | 2005-09-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004458 | 400462384 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004459 | 400462503 | High Sign | HFTD Tier 3 | Distribution | 2004-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004460 | 400462567 | High Sign | HFTD Tier 3 | Distribution | 2004-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004461 | 400462601 | High Sign | HFTD Tier 3 | Distribution | 2004-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004462 | 400462886 | Guy | HFTD Tier 3 | Distribution | 2003-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004463 | 400462911 | High Sign | HFTD Tier 3 | Distribution | 2004-01-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004464 | 400462976 | High Sign | HFTD Tier 3 | Distribution | 2005-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004465 | 400463059 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004466 | 400463184 | Molding | HFTD Tier 2 | Distribution | 2004-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004467 | 400463298 | High Sign | HFTD Tier 3 | Distribution | 2004-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004468 | 400463344 | Guy | HFTD Tier 3 | Distribution | 2005-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004469 | 400463369 | High Sign | HFTD Tier 3 | Distribution | 2001-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004470 | 400463415 | Guy | HFTD Tier 2 | Distribution | 2003-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004471 | 400463522 | High Sign | HFTD Tier 2 | Distribution | 2009-11-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004472 | 400463540 | Cable/Conductor | HFTD Tier 3 | Distribution | 2008-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004473 | 400463573 | Guy | HFTD Tier 3 | Distribution | 2009-11-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004474 | 400463716 | High Sign | HFTD Tier 3 | Distribution | 2001-09-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004475 | 400463779 | Molding | HFTD Tier 3 | Distribution | 2003-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004476 | 400463909 | Molding | HFTD Tier 3 | Distribution | 2004-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004477 | 400463926 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2009-05-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004478 | 400463933 | Cable/Conductor | HFTD Tier 3 | Distribution | 2008-12-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004479 | 400463952 | High Sign | HFTD Tier 2 | Distribution | 2003-11-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004480 | 400464011 | Molding | HFTD Tier 2 | Distribution | 2004-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004481 | 400464116 | High Sign | HFTD Tier 3 | Distribution | 2005-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004482 | 400464305 | High Sign | HFTD Tier 2 | Distribution | 2004-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004483 | 400464307 | Molding | HFTD Tier 2 | Distribution | 2009-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004484 | 400464327 | High Sign | HFTD Tier 2 | Distribution | 2010-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004485 | 400464336 | Molding | HFTD Tier 3 | Distribution | 2008-12-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004486 | 400464581 | Molding | HFTD Tier 3 | Distribution | 2004-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004487 | 400464921 | Molding | HFTD Tier 3 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004488 | 400464971 | Molding | HFTD Tier 2 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004489 | 400465005 | Guy | HFTD Tier 2 | Distribution | 2004-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004490 | 400465090 | High Sign | HFTD Tier 2 | Distribution | 2008-05-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004491 | 400465098 | High Sign | HFTD Tier 2 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004492 | 400465119 | High Sign | HFTD Tier 3 | Distribution | 2004-09-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004493 | 400465123 | Molding | HFTD Tier 2 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004494 | 400465230 | High Sign | HFTD Tier 3 | Distribution | 2005-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004495 | 400465425 | Molding | HFTD Tier 3 | Distribution | 2005-02-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004496 | 400465534 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004497 | 400465639 | High Sign | HFTD Tier 3 | Distribution | 2005-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004498 | 400465696 | Molding | HFTD Tier 3 | Distribution | 2004-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004499 | 400465709 | High Sign | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004500 | 400465752 | Molding | HFTD Tier 2 | Distribution | 2009-11-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004501 | 400465850 | High Sign | HFTD Tier 2 | Distribution | 2004-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004502 | 400465865 | High Sign | HFTD Tier 3 | Distribution | 2005-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004503 | 400466033 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2009-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004504 | 400466249 | Guy | HFTD Tier 2 | Distribution | 2003-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004505 | 400466964 | High Sign | HFTD Tier 2 | Distribution | 2005-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004506 | 400467070 | Molding | HFTD Tier 3 | Distribution | 2003-11-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004507 | 400467145 | Molding | HFTD Tier 3 | Distribution | 2005-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004508 | 400467214 | Molding | HFTD Tier 2 | Distribution | 2009-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004509 | 400467317 | High Sign | HFTD Tier 3 | Distribution | 2004-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004510 | 400467362 | Hardware/Framing | HFTD Tier 3 | Distribution | 2005-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004511 | 400467422 | Molding | HFTD Tier 3 | Distribution | 2004-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004512 | 400467443 | Molding | HFTD Tier 2 | Distribution | 2009-11-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004513 | 400467542 | High Sign | HFTD Tier 3 | Distribution | 2001-11-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004514 | 400467739 | High Sign | HFTD Tier 2 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004515 | 400467778 | High Sign | HFTD Tier 2 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004516 | 400467819 | Molding | HFTD Tier 2 | Distribution | 2005-10-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004517 | 400467988 | High Sign | HFTD Tier 2 | Distribution | 2009-11-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004518 | 400467998 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004519 | 400468058 | Guy | HFTD Tier 2 | Distribution | 2005-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004520 | 400468096 | Riser/Conduit | HFTD Tier 2 | Distribution | 2009-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004521 | 400468124 | High Sign | HFTD Tier 3 | Distribution | 2005-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004522 | 400468160 | Molding | HFTD Tier 2 | Distribution | 2006-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004523 | 400468174 | Molding | HFTD Tier 3 | Distribution | 2005-02-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004524 | 400468188 | High Sign | HFTD Tier 3 | Distribution | 2009-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004525 | 400468242 | High Sign | HFTD Tier 3 | Distribution | 2009-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004526 | 400468372 | Guy | HFTD Tier 2 | Distribution | 2004-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004527 | 400468537 | Molding | HFTD Tier 3 | Distribution | 2003-12-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004528 | 400468575 | Molding | HFTD Tier 3 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004529 | 400468586 | Molding | HFTD Tier 3 | Distribution | 2004-11-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004530 | 400468616 | Guy | HFTD Tier 3 | Distribution | 2009-11-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004531 | 400468812 | Molding | HFTD Tier 3 | Distribution | 2009-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004532 | 400468830 | High Sign | HFTD Tier 2 | Distribution | 2004-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004533 | 400468954 | Molding | HFTD Tier 3 | Distribution | 2005-02-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004534 | 400468984 | High Sign | HFTD Tier 2 | Distribution | 2003-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004535 | 400469593 | Cable/Conductor | HFTD Tier 3 | Distribution | 2008-04-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004536 | 400469596 | High Sign | HFTD Tier 3 | Distribution | 2009-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004537 | 400469622 | High Sign | HFTD Tier 2 | Distribution | 2009-11-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004538 | 400470024 | Molding | HFTD Tier 2 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004539 | 400470038 | Molding | HFTD Tier 2 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004540 | 400470049 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004541 | 400470086 | High Sign | HFTD Tier 2 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004542 | 400470240 | High Sign | HFTD Tier 2 | Distribution | 2003-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004543 | 400470489 | Molding | HFTD Tier 3 | Distribution | 2005-09-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004544 | 400470575 | High Sign | HFTD Tier 3 | Distribution | 2005-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004545 | 400470615 | High Sign | HFTD Tier 3 | Distribution | 2004-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004546 | 400470625 | High Sign | HFTD Tier 2 | Distribution | 2005-10-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004547 | 400470635 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-07-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004548 | 400470658 | High Sign | HFTD Tier 3 | Distribution | 2008-07-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004549 | 400470669 | Molding | HFTD Tier 3 | Distribution | 2009-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004550 | 400470808 | Molding | HFTD Tier 3 | Distribution | 2004-07-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004551 | 400470990 | High Sign | HFTD Tier 2 | Distribution | 2005-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004552 | 400471143 | Guy | HFTD Tier 2 | Distribution | 2004-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004553 | 400471152 | High Sign | HFTD Tier 2 | Distribution | 2005-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004554 | 400471220 | High Sign | HFTD Tier 2 | Distribution | 2003-10-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004555 | 400471568 | Molding | HFTD Tier 3 | Distribution | 2003-12-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004556 | 400471588 | High Sign | HFTD Tier 2 | Distribution | 2008-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004557 | 400471691 | Molding | HFTD Tier 3 | Distribution | 2010-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004558 | 400472098 | Molding | HFTD Tier 3 | Distribution | 2009-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004559 | 400472121 | Molding | HFTD Tier 2 | Distribution | 2009-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004560 | 400472179 | High Sign | HFTD Tier 3 | Distribution | 2004-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004561 | 400472207 | High Sign | HFTD Tier 2 | Distribution | 2003-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004562 | 400472554 | High Sign | HFTD Tier 3 | Distribution | 2004-09-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004563 | 400472682 | High Sign | HFTD Tier 3 | Distribution | 2004-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004564 | 400472698 | High Sign | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004565 | 400472720 | Molding | HFTD Tier 3 | Distribution | 2009-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004566 | 400472742 | Riser/Conduit | HFTD Tier 2 | Distribution | 2003-10-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004567 | 400473058 | Molding | HFTD Tier 3 | Distribution | 2005-02-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004568 | 400473073 | High Sign | HFTD Tier 3 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004569 | 400473225 | Molding | HFTD Tier 3 | Distribution | 2009-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004570 | 400473436 | Molding | HFTD Tier 3 | Distribution | 2004-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004571 | 400473592 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2004-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004572 | 400473696 | High Sign | HFTD Tier 3 | Distribution | 2004-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004573 | 400473813 | High Sign | HFTD Tier 2 | Distribution | 2005-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004574 | 400473822 | High Sign | HFTD Tier 2 | Distribution | 2006-10-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004575 | 400474135 | High Sign | HFTD Tier 2 | Distribution | 2005-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004576 | 400474276 | High Sign | HFTD Tier 3 | Distribution | 2004-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004577 | 400474887 | High Sign | HFTD Tier 3 | Distribution | 2004-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004578 | 400475206 | High Sign | HFTD Tier 3 | Distribution | 2009-10-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004579 | 400475494 | Molding | HFTD Tier 2 | Distribution | 2008-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004580 | 400475599 | High Sign | HFTD Tier 3 | Distribution | 2005-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004581 | 400475906 | High Sign | HFTD Tier 3 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004582 | 400476077 | Molding | HFTD Tier 2 | Distribution | 2009-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004583 | 400476111 | High Sign | HFTD Tier 3 | Distribution | 2004-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004584 | 400476338 | Molding | HFTD Tier 2 | Distribution | 2005-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004585 | 400476491 | Molding | HFTD Tier 3 | Distribution | 2008-12-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004586 | 400476708 | Molding | HFTD Tier 2 | Distribution | 2001-01-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004587 | 400476822 | High Sign | HFTD Tier 3 | Distribution | 2008-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004588 | 400476868 | High Sign | HFTD Tier 3 | Distribution | 2005-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004589 | 400476941 | High Sign | HFTD Tier 3 | Distribution | 2004-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004590 | 400477015 | High Sign | HFTD Tier 2 | Distribution | 2005-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004591 | 400477095 | High Sign | HFTD Tier 2 | Distribution | 2000-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004592 | 400477100 | High Sign | HFTD Tier 2 | Distribution | 2008-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004593 | 400477102 | Molding | HFTD Tier 2 | Distribution | 2004-03-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004594 | 400477186 | Molding | HFTD Tier 2 | Distribution | 2004-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004595 | 400477485 | High Sign | HFTD Tier 3 | Distribution | 2004-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004596 | 400477495 | High Sign | HFTD Tier 3 | Distribution | 2004-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004597 | 400477710 | High Sign | HFTD Tier 3 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004598 | 400477721 | Molding | HFTD Tier 3 | Distribution | 2001-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004599 | 400477923 | Molding | HFTD Tier 3 | Distribution | 2005-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004600 | 400477930 | Bond | HFTD Tier 3 | Distribution | 2008-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004601 | 400478002 | High Sign | HFTD Tier 2 | Distribution | 2005-08-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004602 | 400478116 | Guy | HFTD Tier 3 | Distribution | 2004-01-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004603 | 400478356 | Molding | HFTD Tier 3 | Distribution | 2004-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004604 | 400478367 | Guy | HFTD Tier 3 | Distribution | 2005-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004605 | 400478375 | High Sign | HFTD Tier 2 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004606 | 400478493 | Molding | HFTD Tier 3 | Distribution | 2004-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004607 | 400478514 | Molding | HFTD Tier 3 | Distribution | 2003-11-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004608 | 400478547 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004609 | 400478562 | Hardware/Framing | HFTD Tier 3 | Distribution | 2001-01-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004610 | 400478624 | Molding | HFTD Tier 2 | Distribution | 2004-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004611 | 400478794 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004612 | 400478798 | High Sign | HFTD Tier 2 | Distribution | 2004-02-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004613 | 400478867 | High Sign | HFTD Tier 2 | Distribution | 2009-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004614 | 400479016 | Molding | HFTD Tier 2 | Distribution | 2009-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004615 | 400479201 | Molding | HFTD Tier 3 | Distribution | 2005-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004616 | 400479398 | Guy | HFTD Tier 2 | Distribution | 2004-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004617 | 400479419 | Molding | HFTD Tier 2 | Distribution | 2004-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004618 | 400479590 | Guy | HFTD Tier 2 | Distribution | 2009-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004619 | 400479644 | Molding | HFTD Tier 3 | Distribution | 2004-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004620 | 400479664 | High Sign | HFTD Tier 3 | Distribution | 2004-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004621 | 400479699 | High Sign | HFTD Tier 3 | Distribution | 2009-09-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004622 | 400479748 | Molding | HFTD Tier 3 | Distribution | 2004-12-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004623 | 400480041 | High Sign | HFTD Tier 3 | Distribution | 2009-09-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004624 | 400480248 | High Sign | HFTD Tier 3 | Distribution | 2004-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004625 | 400480344 | High Sign | HFTD Tier 2 | Distribution | 2004-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004626 | 400480438 | Molding | HFTD Tier 2 | Distribution | 2005-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004627 | 400480578 | High Sign | HFTD Tier 2 | Distribution | 2004-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004628 | 400480738 | High Sign | HFTD Tier 2 | Distribution | 2009-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004629 | 400480809 | High Sign | HFTD Tier 3 | Distribution | 2003-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004630 | 400480998 | High Sign | HFTD Tier 3 | Distribution | 2001-11-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004631 | 400481073 | High Sign | HFTD Tier 2 | Distribution | 2004-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004632 | 400481164 | Guy | HFTD Tier 3 | Distribution | 2004-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004633 | 400481188 | High Sign | HFTD Tier 3 | Distribution | 2008-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004634 | 400481300 | High Sign | HFTD Tier 2 | Distribution | 2001-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004635 | 400481353 | Molding | HFTD Tier 2 | Distribution | 2003-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004636 | 400481559 | High Sign | HFTD Tier 3 | Distribution | 2005-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004637 | 400481601 | Molding | HFTD Tier 2 | Distribution | 2004-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004638 | 400481615 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004639 | 400481648 | High Sign | HFTD Tier 3 | Distribution | 2009-05-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004640 | 400481656 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004641 | 400481664 | Molding | HFTD Tier 2 | Distribution | 2004-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004642 | 400481838 | Guy | HFTD Tier 3 | Distribution | 2005-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004643 | 400481863 | High Sign | HFTD Tier 2 | Distribution | 2004-02-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004644 | 400482083 | High Sign | HFTD Tier 3 | Distribution | 2004-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004645 | 400482102 | Crossarm | HFTD Tier 3 | Distribution | 2004-01-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004646 | 400482164 | High Sign | HFTD Tier 2 | Distribution | 2005-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004647 | 400482190 | High Sign | HFTD Tier 3 | Distribution | 2004-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004648 | 400482276 | Guy | HFTD Tier 3 | Distribution | 2005-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004649 | 400482286 | Molding | HFTD Tier 2 | Distribution | 2003-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004650 | 400482294 | High Sign | HFTD Tier 3 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004651 | 400482394 | High Sign | HFTD Tier 2 | Distribution | 2008-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004652 | 400482486 | High Sign | HFTD Tier 2 | Distribution | 2004-02-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004653 | 400482583 | High Sign | HFTD Tier 2 | Distribution | 2009-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004654 | 400482588 | High Sign | HFTD Tier 3 | Distribution | 2004-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004655 | 400482685 | Molding | HFTD Tier 3 | Distribution | 2003-11-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004656 | 400482845 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-12-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004657 | 400482880 | High Sign | HFTD Tier 3 | Distribution | 2008-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004658 | 400482944 | Molding | HFTD Tier 2 | Distribution | 2005-05-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004659 | 400482965 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004660 | 400483016 | Molding | HFTD Tier 2 | Distribution | 2005-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004661 | 400483023 | Hardware/Framing | HFTD Tier 2 | Distribution | 2004-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004662 | 400483066 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004663 | 400483470 | High Sign | HFTD Tier 2 | Distribution | 2009-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004664 | 400483759 | Molding | HFTD Tier 3 | Distribution | 2004-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004665 | 400483802 | Molding | HFTD Tier 2 | Distribution | 2004-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004666 | 400483824 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-02-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004667 | 400483825 | Molding | HFTD Tier 2 | Distribution | 2004-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004668 | 400483853 | Molding | HFTD Tier 2 | Distribution | 2005-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004669 | 400483937 | High Sign | HFTD Tier 3 | Distribution | 2003-12-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004670 | 400484004 | High Sign | HFTD Tier 3 | Distribution | 2004-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004671 | 400484103 | High Sign | HFTD Tier 3 | Distribution | 2004-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004672 | 400484139 | Insulator | HFTD Tier 2 | Distribution | 2004-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004673 | 400484175 | Molding | HFTD Tier 3 | Distribution | 2004-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004674 | 400484361 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004675 | 400484480 | Molding | HFTD Tier 3 | Distribution | 2003-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004676 | 400484531 | Molding | HFTD Tier 2 | Distribution | 2009-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004677 | 400484543 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004678 | 400484674 | High Sign | HFTD Tier 2 | Distribution | 2004-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004679 | 400484773 | Guy | HFTD Tier 3 | Distribution | 2004-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004680 | 400484791 | Molding | HFTD Tier 2 | Distribution | 2008-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004681 | 400484857 | Guy | HFTD Tier 3 | Distribution | 2006-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004682 | 400485233 | High Sign | HFTD Tier 2 | Distribution | 2009-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004683 | 400485235 | Guy | HFTD Tier 2 | Distribution | 2009-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004684 | 400485292 | Molding | HFTD Tier 2 | Distribution | 2004-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004685 | 400485320 | Molding | HFTD Tier 2 | Distribution | 2004-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004686 | 400485502 | Molding | HFTD Tier 3 | Distribution | 2003-12-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004687 | 400485746 | Molding | HFTD Tier 2 | Distribution | 2004-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004688 | 400485853 | High Sign | HFTD Tier 3 | Distribution | 2009-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004689 | 400486106 | Guy | HFTD Tier 2 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004690 | 400486172 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004691 | 400486204 | Molding | HFTD Tier 2 | Distribution | 2005-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004692 | 400486329 | Ground | HFTD Tier 3 | Distribution | 2004-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004693 | 400486392 | Insulator | HFTD Tier 2 | Distribution | 2009-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004694 | 400486455 | High Sign | HFTD Tier 2 | Distribution | 2004-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004695 | 400486702 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004696 | 400486731 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004697 | 400486785 | High Sign | HFTD Tier 2 | Distribution | 2004-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004698 | 400486965 | Molding | HFTD Tier 3 | Distribution | 2004-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004699 | 400486968 | High Sign | HFTD Tier 3 | Distribution | 2009-05-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004700 | 400487195 | Molding | HFTD Tier 3 | Distribution | 2008-04-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004701 | 400487206 | High Sign | HFTD Tier 2 | Distribution | 2003-11-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004702 | 400487285 | High Sign | HFTD Tier 3 | Distribution | 2009-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004703 | 400487503 | High Sign | HFTD Tier 3 | Distribution | 2004-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004704 | 400487557 | High Sign | HFTD Tier 3 | Distribution | 2003-12-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004705 | 400487727 | Molding | HFTD Tier 3 | Distribution | 2005-10-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004706 | 400487801 | High Sign | HFTD Tier 3 | Distribution | 2003-09-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004707 | 400487947 | Molding | HFTD Tier 2 | Distribution | 2008-10-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004708 | 400487973 | High Sign | HFTD Tier 3 | Distribution | 2004-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004709 | 400487989 | Molding | HFTD Tier 3 | Distribution | 2005-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004710 | 400488133 | High Sign | HFTD Tier 3 | Distribution | 2005-08-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004711 | 400488196 | High Sign | HFTD Tier 3 | Distribution | 2005-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004712 | 400488206 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004713 | 400488239 | Guy | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004714 | 400488414 | Molding | HFTD Tier 2 | Distribution | 2004-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004715 | 400488430 | Molding | HFTD Tier 2 | Distribution | 2004-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004716 | 400488688 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004717 | 400488896 | High Sign | HFTD Tier 3 | Distribution | 2008-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004718 | 400488953 | High Sign | HFTD Tier 2 | Distribution | 2007-01-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004719 | 400488988 | Molding | HFTD Tier 3 | Distribution | 2005-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004720 | 400488991 | High Sign | HFTD Tier 3 | Distribution | 2004-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004721 | 400489026 | High Sign | HFTD Tier 2 | Distribution | 2004-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004722 | 400489050 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004723 | 400489070 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004724 | 400489430 | Molding | HFTD Tier 3 | Distribution | 2005-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004725 | 400489617 | Molding | HFTD Tier 2 | Distribution | 2009-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004726 | 400489655 | High Sign | HFTD Tier 3 | Distribution | 2009-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004727 | 400489736 | High Sign | HFTD Tier 3 | Distribution | 2004-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004728 | 400489856 | Molding | HFTD Tier 2 | Distribution | 2004-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004729 | 400490086 | Molding | HFTD Tier 2 | Distribution | 2005-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004730 | 400490178 | Molding | HFTD Tier 3 | Distribution | 2003-11-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004731 | 400490241 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004732 | 400490337 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004733 | 400490372 | High Sign | HFTD Tier 2 | Distribution | 2005-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004734 | 400490860 | High Sign | HFTD Tier 2 | Distribution | 2003-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004735 | 400491241 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-02-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004736 | 400491310 | High Sign | HFTD Tier 3 | Distribution | 2004-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004737 | 400491766 | High Sign | HFTD Tier 2 | Distribution | 2005-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004738 | 400491784 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004739 | 400491826 | High Sign | HFTD Tier 2 | Distribution | 2005-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004740 | 400491889 | High Sign | HFTD Tier 2 | Distribution | 2005-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004741 | 400492182 | High Sign | HFTD Tier 2 | Distribution | 2005-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004742 | 400492186 | Molding | HFTD Tier 3 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004743 | 400492320 | High Sign | HFTD Tier 3 | Distribution | 2003-10-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004744 | 400492456 | Molding | HFTD Tier 3 | Distribution | 2005-02-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004745 | 400492471 | Guy | HFTD Tier 3 | Distribution | 2004-02-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004746 | 400492513 | High Sign | HFTD Tier 3 | Distribution | 2009-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004747 | 400492610 | High Sign | HFTD Tier 3 | Distribution | 2009-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004748 | 400492698 | Molding | HFTD Tier 2 | Distribution | 2005-09-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004749 | 400492758 | Molding | HFTD Tier 2 | Distribution | 2005-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004750 | 400492830 | Molding | HFTD Tier 3 | Distribution | 2009-01-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004751 | 400492944 | Cable/Conductor | HFTD Tier 3 | Distribution | 2005-08-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004752 | 400492953 | High Sign | HFTD Tier 2 | Distribution | 2003-11-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004753 | 400493018 | High Sign | HFTD Tier 2 | Distribution | 2004-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004754 | 400493037 | High Sign | HFTD Tier 3 | Distribution | 2008-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004755 | 400493115 | Molding | HFTD Tier 2 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004756 | 400493267 | Molding | HFTD Tier 3 | Distribution | 2004-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004757 | 400493323 | High Sign | HFTD Tier 3 | Distribution | 2005-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004758 | 400493467 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004759 | 400493737 | High Sign | HFTD Tier 2 | Distribution | 2009-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004760 | 400493787 | Molding | HFTD Tier 2 | Distribution | 2004-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004761 | 400493923 | Molding | HFTD Tier 2 | Distribution | 2004-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004762 | 400493953 | Molding | HFTD Tier 2 | Distribution | 2004-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004763 | 400494021 | Molding | HFTD Tier 3 | Distribution | 2005-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004764 | 400494025 | Molding | HFTD Tier 3 | Distribution | 2005-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004765 | 400494035 | Molding | HFTD Tier 2 | Distribution | 2003-10-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004766 | 400494198 | High Sign | HFTD Tier 3 | Distribution | 2005-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004767 | 400494277 | High Sign | HFTD Tier 3 | Distribution | 2004-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004768 | 400494390 | High Sign | HFTD Tier 2 | Distribution | 2009-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004769 | 400494473 | High Sign | HFTD Tier 2 | Distribution | 2004-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004770 | 400494544 | High Sign | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004771 | 400494601 | Molding | HFTD Tier 2 | Distribution | 2008-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004772 | 400494726 | High Sign | HFTD Tier 2 | Distribution | 2004-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004773 | 400494741 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004774 | 400494854 | High Sign | HFTD Tier 3 | Distribution | 2004-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004775 | 400494902 | Guy | HFTD Tier 3 | Distribution | 2005-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004776 | 400494938 | High Sign | HFTD Tier 3 | Distribution | 2005-08-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004777 | 400494990 | High Sign | HFTD Tier 2 | Distribution | 2005-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004778 | 400495230 | Guy | HFTD Tier 3 | Distribution | 2009-05-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004779 | 400495267 | High Sign | HFTD Tier 3 | Distribution | 2005-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004780 | 400495332 | High Sign | HFTD Tier 3 | Distribution | 2008-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004781 | 400495619 | Molding | HFTD Tier 2 | Distribution | 2004-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004782 | 400495634 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004783 | 400495763 | High Sign | HFTD Tier 3 | Distribution | 2005-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004784 | 400495853 | Ground | HFTD Tier 3 | Distribution | 2005-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004785 | 400496254 | Guy | HFTD Tier 3 | Distribution | 2005-08-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004786 | 400496289 | High Sign | HFTD Tier 2 | Distribution | 2004-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004787 | 400496292 | High Sign | HFTD Tier 3 | Distribution | 2005-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004788 | 400496625 | Molding | HFTD Tier 3 | Distribution | 2009-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004789 | 400496714 | High Sign | HFTD Tier 3 | Distribution | 2005-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004790 | 400496813 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004791 | 400496860 | Molding | HFTD Tier 3 | Distribution | 2005-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004792 | 400496927 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004793 | 400497027 | Molding | HFTD Tier 2 | Distribution | 2008-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004794 | 400497032 | High Sign | HFTD Tier 3 | Distribution | 2005-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004795 | 400497096 | Molding | HFTD Tier 2 | Distribution | 2004-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004796 | 400497373 | Molding | HFTD Tier 2 | Distribution | 2009-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004797 | 400497392 | Guy | HFTD Tier 2 | Distribution | 2003-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004798 | 400497628 | Molding | HFTD Tier 2 | Distribution | 2005-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004799 | 400497746 | Molding | HFTD Tier 2 | Distribution | 2001-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004800 | 400497822 | Guy | HFTD Tier 2 | Distribution | 2004-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004801 | 400497834 | Molding | HFTD Tier 3 | Distribution | 2005-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004802 | 400497851 | Molding | HFTD Tier 3 | Distribution | 2003-10-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004803 | 400497871 | Molding | HFTD Tier 3 | Distribution | 2004-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004804 | 400497900 | Molding | HFTD Tier 2 | Distribution | 2003-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004805 | 400497930 | Molding | HFTD Tier 3 | Distribution | 2001-11-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004806 | 400497985 | Riser/Conduit | HFTD Tier 3 | Distribution | 2005-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004807 | 400498003 | High Sign | HFTD Tier 2 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004808 | 400498067 | Molding | HFTD Tier 3 | Distribution | 2008-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004809 | 400498090 | High Sign | HFTD Tier 3 | Distribution | 2008-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004810 | 400498104 | Riser/Conduit | HFTD Tier 3 | Distribution | 2005-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004811 | 400498358 | Molding | HFTD Tier 3 | Distribution | 2009-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004812 | 400498359 | High Sign | HFTD Tier 2 | Distribution | 2003-10-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004813 | 400498380 | High Sign | HFTD Tier 2 | Distribution | 2003-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004814 | 400498386 | High Sign | HFTD Tier 2 | Distribution | 2003-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004815 | 400498389 | High Sign | HFTD Tier 2 | Distribution | 2004-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004816 | 400498419 | Guy | HFTD Tier 2 | Distribution | 2005-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004817 | 400498493 | High Sign | HFTD Tier 2 | Distribution | 2004-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004818 | 400499052 | High Sign | HFTD Tier 2 | Distribution | 2004-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004819 | 400499087 | High Sign | HFTD Tier 3 | Distribution | 2004-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004820 | 400499646 | Guy | HFTD Tier 2 | Distribution | 2005-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004821 | 400499745 | Molding | HFTD Tier 2 | Distribution | 2001-11-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004822 | 400499748 | Molding | HFTD Tier 3 | Distribution | 2005-06-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004823 | 400499804 | Molding | HFTD Tier 2 | Distribution | 2005-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004824 | 400500146 | Molding | HFTD Tier 3 | Distribution | 2005-09-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004825 | 400500150 | High Sign | HFTD Tier 2 | Distribution | 2003-10-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004826 | 400500237 | Molding | HFTD Tier 2 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004827 | 400500540 | Molding | HFTD Tier 2 | Distribution | 2005-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004828 | 400500590 | Guy | HFTD Tier 3 | Distribution | 2005-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004829 | 400500615 | High Sign | HFTD Tier 3 | Distribution | 2005-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004830 | 400500846 | Guy | HFTD Tier 3 | Distribution | 2005-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004831 | 400500852 | High Sign | HFTD Tier 2 | Distribution | 2005-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004832 | 400501368 | Molding | HFTD Tier 2 | Distribution | 2008-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004833 | 400501606 | Molding | HFTD Tier 3 | Distribution | 2005-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004834 | 400501818 | Molding | HFTD Tier 2 | Distribution | 2003-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004835 | 400501841 | Molding | HFTD Tier 2 | Distribution | 2003-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004836 | 400501990 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004837 | 400502135 | High Sign | HFTD Tier 3 | Distribution | 2008-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004838 | 400502190 | High Sign | HFTD Tier 3 | Distribution | 2005-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004839 | 400502231 | Molding | HFTD Tier 3 | Distribution | 2005-08-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004840 | 400502469 | Molding | HFTD Tier 3 | Distribution | 2003-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004841 | 400502524 | High Sign | HFTD Tier 2 | Distribution | 2001-12-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004842 | 400502714 | High Sign | HFTD Tier 3 | Distribution | 2008-03-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004843 | 400502903 | KV Cable Tags | HFTD Tier 3 | Distribution | 2008-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004844 | 400502956 | Molding | HFTD Tier 2 | Distribution | 2005-08-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004845 | 400503002 | High Sign | HFTD Tier 3 | Distribution | 2003-10-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004846 | 400503093 | High Sign | HFTD Tier 2 | Distribution | 2005-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004847 | 400503118 | High Sign | HFTD Tier 3 | Distribution | 2007-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004848 | 400503143 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004849 | 400503622 | High Sign | HFTD Tier 2 | Distribution | 2005-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004850 | 400503633 | High Sign | HFTD Tier 3 | Distribution | 2003-11-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004851 | 400503839 | High Sign | HFTD Tier 2 | Distribution | 2005-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004852 | 400503917 | Molding | HFTD Tier 3 | Distribution | 2008-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004853 | 400504131 | Molding | HFTD Tier 3 | Distribution | 2001-10-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004854 | 400504315 | Molding | HFTD Tier 3 | Distribution | 2001-10-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004855 | 400504568 | Hardware/Framing | HFTD Tier 2 | Distribution | 2005-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004856 | 400504582 | Molding | HFTD Tier 3 | Distribution | 2008-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004857 | 400504625 | Molding | HFTD Tier 3 | Distribution | 2001-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004858 | 400504682 | Molding | HFTD Tier 3 | Distribution | 2003-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004859 | 400504689 | High Sign | HFTD Tier 2 | Distribution | 2004-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004860 | 400504740 | Crossarm | HFTD Tier 3 | Distribution | 2001-09-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004861 | 400504822 | Molding | HFTD Tier 2 | Distribution | 2003-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004862 | 400505375 | Hardware/Framing | HFTD Tier 3 | Distribution | 2004-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004863 | 400505518 | High Sign | HFTD Tier 2 | Distribution | 2008-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004864 | 400505555 | Crossarm | HFTD Tier 2 | Distribution | 2009-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004865 | 400505765 | Molding | HFTD Tier 2 | Distribution | 2001-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004866 | 400505817 | High Sign | HFTD Tier 3 | Distribution | 2008-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004867 | 400506032 | Molding | HFTD Tier 2 | Distribution | 2003-10-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004868 | 400506297 | Molding | HFTD Tier 2 | Distribution | 2005-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004869 | 400506325 | Molding | HFTD Tier 2 | Distribution | 2003-09-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004870 | 400506434 | High Sign | HFTD Tier 2 | Distribution | 2003-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004871 | 400506671 | Guy | HFTD Tier 2 | Distribution | 2005-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004872 | 400506916 | Molding | HFTD Tier 2 | Distribution | 2005-11-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004873 | 400507008 | Guy | HFTD Tier 3 | Distribution | 2005-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004874 | 400507068 | High Sign | HFTD Tier 3 | Distribution | 2005-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004875 | 400507127 | High Sign | HFTD Tier 3 | Distribution | 2004-12-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004876 | 400507402 | Cable/Conductor | HFTD Tier 3 | Distribution | 2003-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004877 | 400507428 | Molding | HFTD Tier 2 | Distribution | 2008-07-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004878 | 400507463 | Riser/Conduit | HFTD Tier 3 | Distribution | 2005-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004879 | 400507746 | Guy | HFTD Tier 2 | Distribution | 2004-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004880 | 400507901 | Hardware/Framing | HFTD Tier 2 | Distribution | 2009-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004881 | 400508220 | Molding | HFTD Tier 2 | Distribution | 2003-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004882 | 400508229 | Molding | HFTD Tier 2 | Distribution | 2003-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004883 | 400508270 | Molding | HFTD Tier 2 | Distribution | 2005-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004884 | 400508542 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004885 | 400508584 | Molding | HFTD Tier 2 | Distribution | 2004-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004886 | 400508837 | High Sign | HFTD Tier 3 | Distribution | 2001-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004887 | 400509071 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004888 | 400509224 | High Sign | HFTD Tier 2 | Distribution | 2004-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004889 | 400509366 | High Sign | HFTD Tier 3 | Distribution | 2005-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004890 | 400509409 | High Sign | HFTD Tier 3 | Distribution | 2003-10-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004891 | 400509428 | Hardware/Framing | HFTD Tier 2 | Distribution | 2004-12-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004892 | 400509448 | Molding | HFTD Tier 2 | Distribution | 2003-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004893 | 400509590 | Molding | HFTD Tier 3 | Distribution | 2005-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004894 | 400509611 | High Sign | HFTD Tier 2 | Distribution | 2005-10-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004895 | 400509660 | High Sign | HFTD Tier 2 | Distribution | 2005-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004896 | 400509854 | Molding | HFTD Tier 2 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004897 | 400509915 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2008-05-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004898 | 400509970 | Molding | HFTD Tier 3 | Distribution | 2005-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004899 | 400510008 | High Sign | HFTD Tier 2 | Distribution | 2005-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004900 | 400510058 | High Sign | HFTD Tier 3 | Distribution | 2003-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004901 | 400510126 | High Sign | HFTD Tier 2 | Distribution | 2002-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004902 | 400510142 | Riser/Conduit | HFTD Tier 3 | Distribution | 2005-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004903 | 400510228 | Hardware/Framing | HFTD Tier 3 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004904 | 400510233 | High Sign | HFTD Tier 3 | Distribution | 2004-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004905 | 400510307 | Molding | HFTD Tier 3 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004906 | 400510324 | Molding | HFTD Tier 3 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004907 | 400510494 | Molding | HFTD Tier 3 | Distribution | 2009-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004908 | 400510635 | High Sign | HFTD Tier 2 | Distribution | 2001-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004909 | 400510678 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004910 | 400510698 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004911 | 400510827 | High Sign | HFTD Tier 3 | Distribution | 2008-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004912 | 400511185 | High Sign | HFTD Tier 2 | Distribution | 2003-11-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004913 | 400511228 | High Sign | HFTD Tier 2 | Distribution | 2005-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004914 | 400511241 | High Sign | HFTD Tier 3 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004915 | 400512008 | Molding | HFTD Tier 3 | Distribution | 2005-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004916 | 400512034 | High Sign | HFTD Tier 2 | Distribution | 2003-11-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004917 | 400512083 | High Sign | HFTD Tier 2 | Distribution | 2005-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004918 | 400512366 | High Sign | HFTD Tier 2 | Distribution | 2008-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004919 | 400512452 | High Sign | HFTD Tier 2 | Distribution | 2001-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004920 | 400512656 | Molding | HFTD Tier 3 | Distribution | 2004-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004921 | 400512933 | High Sign | HFTD Tier 2 | Distribution | 2009-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004922 | 400513581 | High Sign | HFTD Tier 2 | Distribution | 2003-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004923 | 400513887 | Molding | HFTD Tier 3 | Distribution | 2005-08-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004924 | 400514116 | High Sign | HFTD Tier 3 | Distribution | 2004-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004925 | 400514269 | Molding | HFTD Tier 3 | Distribution | 2003-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004926 | 400514885 | High Sign | HFTD Tier 2 | Distribution | 2003-10-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004927 | 400515086 | Guy | HFTD Tier 3 | Distribution | 2005-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004928 | 400515120 | High Sign | HFTD Tier 3 | Distribution | 2005-08-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004929 | 400515198 | High Sign | HFTD Tier 3 | Distribution | 2005-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004930 | 400515207 | Molding | HFTD Tier 3 | Distribution | 2008-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004931 | 400515564 | High Sign | HFTD Tier 2 | Distribution | 2003-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004932 | 400515679 | High Sign | HFTD Tier 2 | Distribution | 2003-10-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004933 | 400515708 | High Sign | HFTD Tier 2 | Distribution | 2005-11-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004934 | 400515746 | Cable/Conductor | HFTD Tier 2 | Distribution | 2003-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004935 | 400515762 | High Sign | HFTD Tier 2 | Distribution | 2005-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004936 | 400515882 | High Sign | HFTD Tier 2 | Distribution | 2005-03-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004937 | 400515993 | Molding | HFTD Tier 2 | Distribution | 2004-03-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004938 | 400516107 | Molding | HFTD Tier 3 | Distribution | 2005-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004939 | 400516305 | High Sign | HFTD Tier 2 | Distribution | 2005-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004940 | 400516342 | Molding | HFTD Tier 3 | Distribution | 2005-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004941 | 400516361 | Molding | HFTD Tier 3 | Distribution | 2004-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004942 | 400516400 | Molding | HFTD Tier 2 | Distribution | 2004-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004943 | 400516963 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004944 | 400517023 | Molding | HFTD Tier 2 | Distribution | 2004-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004945 | 400517053 | Hardware/Framing | HFTD Tier 3 | Distribution | 2005-01-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004946 | 400517067 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004947 | 400517073 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004948 | 400517113 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004949 | 400517124 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004950 | 400517315 | Molding | HFTD Tier 2 | Distribution | 2003-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004951 | 400517452 | Molding | HFTD Tier 2 | Distribution | 2003-10-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004952 | 400517473 | Molding | HFTD Tier 3 | Distribution | 2005-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004953 | 400517481 | Molding | HFTD Tier 2 | Distribution | 2004-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004954 | 400517536 | High Sign | HFTD Tier 3 | Distribution | 2008-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004955 | 400517599 | High Sign | HFTD Tier 2 | Distribution | 2005-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004956 | 400517887 | High Sign | HFTD Tier 3 | Distribution | 2005-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004957 | 400517963 | Molding | HFTD Tier 2 | Distribution | 2008-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004958 | 400517995 | High Sign | HFTD Tier 3 | Distribution | 2008-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004959 | 400518111 | Guy | HFTD Tier 3 | Distribution | 2005-08-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004960 | 400518233 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004961 | 400518236 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004962 | 400518253 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004963 | 400518262 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004964 | 400518388 | Vis Strips | HFTD Tier 2 | Distribution | 2008-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004965 | 400518429 | High Sign | HFTD Tier 2 | Distribution | 2003-10-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004966 | 400518536 | High Sign | HFTD Tier 3 | Distribution | 2008-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004967 | 400518572 | High Sign | HFTD Tier 3 | Distribution | 2008-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004968 | 400518953 | Molding | HFTD Tier 3 | Distribution | 2005-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004969 | 400519128 | High Sign | HFTD Tier 3 | Distribution | 2005-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004970 | 400519175 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004971 | 400519481 | Molding | HFTD Tier 2 | Distribution | 2008-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004972 | 400519482 | Riser/Conduit | HFTD Tier 3 | Distribution | 2008-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004973 | 400519515 | KV Cable Tags | HFTD Tier 2 | Distribution | 2008-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004974 | 400519586 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004975 | 400520103 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004976 | 400520114 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004977 | 400520124 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004978 | 400520281 | Guy | HFTD Tier 3 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004979 | 400520330 | High Sign | HFTD Tier 2 | Distribution | 2005-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004980 | 400520441 | Molding | HFTD Tier 3 | Distribution | 2005-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004981 | 400520482 | High Sign | HFTD Tier 3 | Distribution | 2001-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004982 | 400520604 | High Sign | HFTD Tier 2 | Distribution | 2008-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004983 | 400520660 | Molding | HFTD Tier 3 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004984 | 400520690 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004985 | 400520850 | High Sign | HFTD Tier 2 | Distribution | 2003-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004986 | 400521001 | Molding | HFTD Tier 2 | Distribution | 2003-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004987 | 400521111 | High Sign | HFTD Tier 3 | Distribution | 2005-09-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004988 | 400521327 | KV Cable Tags | HFTD Tier 2 | Distribution | 2008-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004989 | 400521370 | High Sign | HFTD Tier 3 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004990 | 400521436 | High Sign | HFTD Tier 2 | Distribution | 2005-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004991 | 400521911 | Molding | HFTD Tier 3 | Distribution | 2005-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004992 | 400522003 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004993 | 400522031 | Molding | HFTD Tier 2 | Distribution | 2005-03-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004994 | 400522089 | Molding | HFTD Tier 3 | Distribution | 2003-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004995 | 400522091 | Molding | HFTD Tier 2 | Distribution | 2005-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004996 | 400522113 | High Sign | HFTD Tier 2 | Distribution | 2005-02-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004997 | 400522310 | High Sign | HFTD Tier 3 | Distribution | 2005-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004998 | 400522597 | Molding | HFTD Tier 3 | Distribution | 2008-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130004999 | 400522969 | Molding | HFTD Tier 3 | Distribution | 2005-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005000 | 400522999 | High Sign | HFTD Tier 3 | Distribution | 2005-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005001 | 400523296 | High Sign | HFTD Tier 3 | Distribution | 2003-11-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005002 | 400523316 | Hardware/Framing | HFTD Tier 3 | Distribution | 2005-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005003 | 400523342 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005004 | 400523388 | Molding | HFTD Tier 2 | Distribution | 2005-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005005 | 400523417 | Molding | HFTD Tier 3 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005006 | 400523447 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005007 | 400523678 | High Sign | HFTD Tier 2 | Distribution | 2003-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005008 | 400523699 | High Sign | HFTD Tier 2 | Distribution | 2005-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005009 | 400523713 | High Sign | HFTD Tier 3 | Distribution | 2008-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005010 | 400523761 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005011 | 400523771 | Cable/Conductor | HFTD Tier 3 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005012 | 400524001 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2008-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005013 | 400524010 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005014 | 400524290 | Molding | HFTD Tier 3 | Distribution | 2005-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005015 | 400524404 | High Sign | HFTD Tier 3 | Distribution | 2003-12-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005016 | 400524599 | Molding | HFTD Tier 3 | Distribution | 2005-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005017 | 400524673 | Molding | HFTD Tier 2 | Distribution | 2005-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005018 | 400524746 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005019 | 400524881 | Molding | HFTD Tier 3 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005020 | 400524914 | High Sign | HFTD Tier 2 | Distribution | 1999-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005021 | 400525127 | Molding | HFTD Tier 2 | Distribution | 2005-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005022 | 400525190 | High Sign | HFTD Tier 3 | Distribution | 2004-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005023 | 400525373 | Molding | HFTD Tier 2 | Distribution | 2003-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005024 | 400525427 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005025 | 400525578 | Riser/Conduit | HFTD Tier 3 | Distribution | 2005-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005026 | 400525738 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005027 | 400526003 | High Sign | HFTD Tier 3 | Distribution | 2005-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005028 | 400526011 | Molding | HFTD Tier 3 | Distribution | 2003-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005029 | 400526045 | High Sign | HFTD Tier 3 | Distribution | 2004-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005030 | 400526047 | Guy | HFTD Tier 3 | Distribution | 2003-10-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005031 | 400526055 | Molding | HFTD Tier 2 | Distribution | 2005-02-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005032 | 400526080 | Cable/Conductor | HFTD Tier 3 | Distribution | 2003-10-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005033 | 400526150 | Molding | HFTD Tier 2 | Distribution | 2003-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005034 | 400526209 | Molding | HFTD Tier 3 | Distribution | 2005-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005035 | 400526306 | High Sign | HFTD Tier 3 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005036 | 400526313 | Molding | HFTD Tier 2 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005037 | 400526329 | High Sign | HFTD Tier 3 | Distribution | 2001-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005038 | 400526558 | Molding | HFTD Tier 2 | Distribution | 2003-10-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005039 | 400526626 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005040 | 400526639 | Molding | HFTD Tier 3 | Distribution | 2005-02-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005041 | 400527227 | Molding | HFTD Tier 2 | Distribution | 2003-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005042 | 400527250 | Molding | HFTD Tier 2 | Distribution | 2003-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005043 | 400527346 | Molding | HFTD Tier 3 | Distribution | 2005-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005044 | 400527519 | High Sign | HFTD Tier 2 | Distribution | 2009-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005045 | 400528011 | High Sign | HFTD Tier 3 | Distribution | 2001-11-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005046 | 400528035 | Riser/Conduit | HFTD Tier 3 | Distribution | 2007-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005047 | 400528055 | Guy | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005048 | 400528104 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005049 | 400528229 | High Sign | HFTD Tier 2 | Distribution | 2008-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005050 | 400528713 | High Sign | HFTD Tier 2 | Distribution | 2003-09-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005051 | 400528748 | Molding | HFTD Tier 3 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005052 | 400529042 | High Sign | HFTD Tier 3 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005053 | 400529093 | Molding | HFTD Tier 3 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005054 | 400529156 | Molding | HFTD Tier 3 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005055 | 400529170 | High Sign | HFTD Tier 2 | Distribution | 2003-03-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005056 | 400529337 | High Sign | HFTD Tier 3 | Distribution | 2003-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005057 | 400529571 | Molding | HFTD Tier 2 | Distribution | 2003-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005058 | 400529587 | Guy | HFTD Tier 3 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005059 | 400529608 | Guy | HFTD Tier 3 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005060 | 400529648 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005061 | 400530153 | Molding | HFTD Tier 2 | Distribution | 2003-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005062 | 400530472 | Molding | HFTD Tier 2 | Distribution | 2005-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005063 | 400530622 | High Sign | HFTD Tier 2 | Distribution | 2002-04-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005064 | 400530858 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005065 | 400530954 | High Sign | HFTD Tier 3 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005066 | 400531012 | High Sign | HFTD Tier 3 | Distribution | 2004-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005067 | 400531099 | Molding | HFTD Tier 2 | Distribution | 2005-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005068 | 400531111 | Molding | HFTD Tier 2 | Distribution | 2005-08-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005069 | 400531184 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005070 | 400531418 | High Sign | HFTD Tier 3 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005071 | 400531462 | High Sign | HFTD Tier 2 | Distribution | 2004-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005072 | 400531476 | Guy | HFTD Tier 3 | Distribution | 2005-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005073 | 400531507 | High Sign | HFTD Tier 3 | Distribution | 2005-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005074 | 400531582 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005075 | 400531605 | Guy | HFTD Tier 3 | Distribution | 2005-08-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005076 | 400531649 | High Sign | HFTD Tier 3 | Distribution | 2004-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005077 | 400531859 | High Sign | HFTD Tier 2 | Distribution | 2005-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005078 | 400531925 | High Sign | HFTD Tier 3 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005079 | 400532075 | Molding | HFTD Tier 3 | Distribution | 2007-03-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005080 | 400532077 | High Sign | HFTD Tier 3 | Distribution | 2007-06-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005081 | 400532526 | Molding | HFTD Tier 2 | Distribution | 2005-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005082 | 400532551 | Molding | HFTD Tier 3 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005083 | 400532826 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005084 | 400532855 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005085 | 400532866 | Molding | HFTD Tier 3 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005086 | 400532907 | High Sign | HFTD Tier 2 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005087 | 400532942 | High Sign | HFTD Tier 3 | Distribution | 2005-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005088 | 400532963 | High Sign | HFTD Tier 3 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005089 | 400533081 | High Sign | HFTD Tier 2 | Distribution | 2003-10-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005090 | 400533634 | Molding | HFTD Tier 3 | Distribution | 2005-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005091 | 400533723 | High Sign | HFTD Tier 2 | Distribution | 2003-10-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005092 | 400533902 | High Sign | HFTD Tier 2 | Distribution | 2003-10-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005093 | 400533924 | Molding | HFTD Tier 3 | Distribution | 2007-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005094 | 400534271 | High Sign | HFTD Tier 2 | Distribution | 2003-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005095 | 400534284 | High Sign | HFTD Tier 2 | Distribution | 2003-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005096 | 400534527 | High Sign | HFTD Tier 3 | Distribution | 2007-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005097 | 400534604 | Guy | HFTD Tier 3 | Distribution | 2004-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005098 | 400534639 | Molding | HFTD Tier 2 | Distribution | 2007-07-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005099 | 400534816 | Molding | HFTD Tier 2 | Distribution | 2005-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005100 | 400534841 | High Sign | HFTD Tier 3 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005101 | 400534844 | High Sign | HFTD Tier 2 | Distribution | 2005-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005102 | 400534856 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005103 | 400534930 | High Sign | HFTD Tier 3 | Distribution | 2005-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005104 | 400534939 | Riser/Conduit | HFTD Tier 2 | Distribution | 2005-09-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005105 | 400535000 | High Sign | HFTD Tier 2 | Distribution | 2008-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005106 | 400535012 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005107 | 400535048 | Riser/Conduit | HFTD Tier 2 | Distribution | 2005-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005108 | 400535061 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005109 | 400535067 | Molding | HFTD Tier 3 | Distribution | 2005-09-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005110 | 400535092 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005111 | 400535122 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005112 | 400535327 | High Sign | HFTD Tier 3 | Distribution | 2003-10-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005113 | 400535378 | Guy | HFTD Tier 2 | Distribution | 2007-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005114 | 400535453 | Molding | HFTD Tier 2 | Distribution | 2003-08-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005115 | 400535569 | High Sign | HFTD Tier 3 | Distribution | 2007-06-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005116 | 400535611 | High Sign | HFTD Tier 2 | Distribution | 2005-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005117 | 400535635 | High Sign | HFTD Tier 2 | Distribution | 2006-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005118 | 400535663 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005119 | 400535671 | High Sign | HFTD Tier 2 | Distribution | 2005-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005120 | 400535692 | Guy | HFTD Tier 2 | Distribution | 2007-10-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005121 | 400535798 | Molding | HFTD Tier 3 | Distribution | 2007-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005122 | 400535809 | Molding | HFTD Tier 2 | Distribution | 2003-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005123 | 400535824 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-10-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005124 | 400536036 | Molding | HFTD Tier 3 | Distribution | 2005-09-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005125 | 400536051 | Molding | HFTD Tier 3 | Distribution | 2003-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005126 | 400536222 | High Sign | HFTD Tier 2 | Distribution | 2003-11-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005127 | 400536254 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005128 | 400536286 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005129 | 400536367 | Hardware/Framing | HFTD Tier 3 | Distribution | 2002-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005130 | 400536465 | Riser/Conduit | HFTD Tier 3 | Distribution | 2005-02-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005131 | 400536492 | Cable/Conductor | HFTD Tier 3 | Distribution | 2005-02-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005132 | 400536623 | Molding | HFTD Tier 3 | Distribution | 2006-11-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005133 | 400536798 | High Sign | HFTD Tier 2 | Distribution | 2006-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005134 | 400536812 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005135 | 400536828 | High Sign | HFTD Tier 3 | Distribution | 2008-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005136 | 400536894 | High Sign | HFTD Tier 3 | Distribution | 2005-09-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005137 | 400536966 | Molding | HFTD Tier 2 | Distribution | 2003-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005138 | 400537041 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005139 | 400537169 | Guy | HFTD Tier 3 | Distribution | 2005-07-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005140 | 400537234 | Guy | HFTD Tier 3 | Distribution | 2002-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005141 | 400537565 | High Sign | HFTD Tier 3 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005142 | 400537682 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005143 | 400537700 | Lid/Frame | HFTD Tier 3 | Distribution | 2008-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005144 | 400537722 | Molding | HFTD Tier 3 | Distribution | 2007-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005145 | 400537773 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005146 | 400537802 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005147 | 400538014 | High Sign | HFTD Tier 3 | Distribution | 2005-08-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005148 | 400538034 | High Sign | HFTD Tier 3 | Distribution | 2008-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005149 | 400538075 | Guy | HFTD Tier 3 | Distribution | 2005-08-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005150 | 400538136 | High Sign | HFTD Tier 3 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005151 | 400538230 | Guy | HFTD Tier 3 | Distribution | 2007-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005152 | 400538305 | High Sign | HFTD Tier 3 | Distribution | 2002-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005153 | 400538370 | Guy | HFTD Tier 3 | Distribution | 2004-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005154 | 400538411 | High Sign | HFTD Tier 3 | Distribution | 2001-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005155 | 400538521 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005156 | 400538703 | Molding | HFTD Tier 3 | Distribution | 2002-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005157 | 400538735 | High Sign | HFTD Tier 3 | Distribution | 2003-08-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005158 | 400539067 | Guy | HFTD Tier 3 | Distribution | 2007-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005159 | 400539156 | Guy | HFTD Tier 2 | Distribution | 2007-10-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005160 | 400539189 | High Sign | HFTD Tier 2 | Distribution | 2007-08-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005161 | 400539202 | Molding | HFTD Tier 2 | Distribution | 2006-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005162 | 400539250 | High Sign | HFTD Tier 3 | Distribution | 2005-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005163 | 400539401 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005164 | 400539441 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005165 | 400539775 | High Sign | HFTD Tier 2 | Distribution | 2003-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005166 | 400539778 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005167 | 400539781 | High Sign | HFTD Tier 2 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005168 | 400539788 | Hardware/Framing | HFTD Tier 3 | Distribution | 2003-08-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005169 | 400539885 | Guy | HFTD Tier 2 | Distribution | 2005-09-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005170 | 400539909 | High Sign | HFTD Tier 2 | Distribution | 2007-05-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005171 | 400539972 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005172 | 400540142 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005173 | 400540143 | High Sign | HFTD Tier 2 | Distribution | 2005-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005174 | 400540173 | High Sign | HFTD Tier 2 | Distribution | 2005-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005175 | 400540174 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005176 | 400540191 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-11-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005177 | 400540194 | Molding | HFTD Tier 2 | Distribution | 2007-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005178 | 400540204 | High Sign | HFTD Tier 2 | Distribution | 2005-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005179 | 400540233 | Molding | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005180 | 400540599 | High Sign | HFTD Tier 3 | Distribution | 2004-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005181 | 400540616 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005182 | 400540707 | High Sign | HFTD Tier 2 | Distribution | 2001-11-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005183 | 400540775 | Cable/Conductor | HFTD Tier 3 | Distribution | 2005-02-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005184 | 400540803 | High Sign | HFTD Tier 2 | Distribution | 2002-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005185 | 400540882 | Molding | HFTD Tier 2 | Distribution | 2003-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005186 | 400540905 | Molding | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005187 | 400541224 | Molding | HFTD Tier 2 | Distribution | 2002-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005188 | 400541530 | Molding | HFTD Tier 3 | Distribution | 2002-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005189 | 400541605 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005190 | 400541667 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005191 | 400541862 | Molding | HFTD Tier 3 | Distribution | 2005-03-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005192 | 400541972 | Guy | HFTD Tier 3 | Distribution | 2003-08-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005193 | 400542338 | Molding | HFTD Tier 2 | Distribution | 2007-08-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005194 | 400542354 | Guy | HFTD Tier 3 | Distribution | 2004-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005195 | 400542605 | High Sign | HFTD Tier 2 | Distribution | 2006-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005196 | 400542673 | Molding | HFTD Tier 2 | Distribution | 2004-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005197 | 400543123 | Molding | HFTD Tier 2 | Distribution | 2003-10-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005198 | 400543165 | Molding | HFTD Tier 3 | Distribution | 2004-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005199 | 400543174 | Guy | HFTD Tier 3 | Distribution | 2007-08-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005200 | 400543414 | High Sign | HFTD Tier 3 | Distribution | 2007-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005201 | 400543417 | High Sign | HFTD Tier 3 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005202 | 400543594 | Guy | HFTD Tier 3 | Distribution | 2007-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005203 | 400543615 | High Sign | HFTD Tier 3 | Distribution | 2005-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005204 | 400543653 | Molding | HFTD Tier 2 | Distribution | 2007-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005205 | 400543756 | High Sign | HFTD Tier 2 | Distribution | 2007-10-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005206 | 400544025 | Hardware/Framing | HFTD Tier 2 | Distribution | 2001-12-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005207 | 400544158 | Molding | HFTD Tier 2 | Distribution | 2005-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005208 | 400544306 | Molding | HFTD Tier 3 | Distribution | 2005-02-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005209 | 400544535 | High Sign | HFTD Tier 2 | Distribution | 2003-11-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005210 | 400544676 | Molding | HFTD Tier 2 | Distribution | 2007-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005211 | 400544781 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005212 | 400544875 | Molding | HFTD Tier 3 | Distribution | 2005-11-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005213 | 400544984 | Molding | HFTD Tier 2 | Distribution | 2007-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005214 | 400545044 | Guy | HFTD Tier 3 | Distribution | 2006-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005215 | 400545117 | Molding | HFTD Tier 3 | Distribution | 2002-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005216 | 400545257 | High Sign | HFTD Tier 3 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005217 | 400545278 | High Sign | HFTD Tier 2 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005218 | 400545357 | Guy | HFTD Tier 2 | Distribution | 2007-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005219 | 400545433 | Molding | HFTD Tier 2 | Distribution | 2008-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005220 | 400545597 | High Sign | HFTD Tier 3 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005221 | 400545713 | Molding | HFTD Tier 2 | Distribution | 2002-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005222 | 400546034 | High Sign | HFTD Tier 3 | Distribution | 2008-05-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005223 | 400546083 | High Sign | HFTD Tier 3 | Distribution | 2005-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005224 | 400546120 | High Sign | HFTD Tier 2 | Distribution | 2006-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005225 | 400546511 | High Sign | HFTD Tier 3 | Distribution | 2005-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005226 | 400546536 | High Sign | HFTD Tier 3 | Distribution | 2003-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005227 | 400546671 | Molding | HFTD Tier 2 | Distribution | 2005-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005228 | 400546811 | Molding | HFTD Tier 3 | Distribution | 2003-05-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005229 | 400546849 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005230 | 400546870 | Molding | HFTD Tier 2 | Distribution | 2007-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005231 | 400546982 | High Sign | HFTD Tier 2 | Distribution | 2003-11-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005232 | 400547030 | Molding | HFTD Tier 2 | Distribution | 2006-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005233 | 400547042 | Guy | HFTD Tier 3 | Distribution | 2003-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005234 | 400547129 | High Sign | HFTD Tier 3 | Distribution | 2005-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005235 | 400547179 | High Sign | HFTD Tier 3 | Distribution | 2002-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005236 | 400547189 | Molding | HFTD Tier 2 | Distribution | 2001-11-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005237 | 400547347 | High Sign | HFTD Tier 3 | Distribution | 2006-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005238 | 400547352 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005239 | 400547363 | Molding | HFTD Tier 3 | Distribution | 2005-08-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005240 | 400547374 | High Sign | HFTD Tier 3 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005241 | 400547376 | High Sign | HFTD Tier 3 | Distribution | 2006-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005242 | 400547401 | High Sign | HFTD Tier 3 | Distribution | 2006-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005243 | 400547490 | High Sign | HFTD Tier 3 | Distribution | 2006-10-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005244 | 400547526 | Molding | HFTD Tier 3 | Distribution | 2007-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005245 | 400547718 | Molding | HFTD Tier 2 | Distribution | 2003-11-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005246 | 400547763 | Molding | HFTD Tier 2 | Distribution | 2003-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005247 | 400547778 | Molding | HFTD Tier 3 | Distribution | 2007-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005248 | 400547802 | High Sign | HFTD Tier 3 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005249 | 400547803 | High Sign | HFTD Tier 2 | Distribution | 2007-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005250 | 400548054 | Molding | HFTD Tier 3 | Distribution | 2005-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005251 | 400548171 | High Sign | HFTD Tier 2 | Distribution | 2004-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005252 | 400548175 | Molding | HFTD Tier 2 | Distribution | 2005-11-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005253 | 400548219 | Molding | HFTD Tier 3 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005254 | 400548229 | High Sign | HFTD Tier 3 | Distribution | 2002-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005255 | 400548435 | Molding | HFTD Tier 2 | Distribution | 2007-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005256 | 400548656 | High Sign | HFTD Tier 3 | Distribution | 2002-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005257 | 400548709 | High Sign | HFTD Tier 3 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005258 | 400548723 | Molding | HFTD Tier 2 | Distribution | 2005-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005259 | 400548819 | Molding | HFTD Tier 2 | Distribution | 2005-09-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005260 | 400549041 | High Sign | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005261 | 400549156 | Molding | HFTD Tier 3 | Distribution | 2003-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005262 | 400549257 | Hardware/Framing | HFTD Tier 2 | Distribution | 2005-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005263 | 400549531 | High Sign | HFTD Tier 2 | Distribution | 2005-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005264 | 400549774 | Molding | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005265 | 400549893 | KV Cable Tags | HFTD Tier 3 | Distribution | 2008-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005266 | 400549899 | High Sign | HFTD Tier 2 | Distribution | 2007-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005267 | 400549956 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005268 | 400550011 | Guy | HFTD Tier 2 | Distribution | 2006-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005269 | 400550232 | Molding | HFTD Tier 2 | Distribution | 2006-01-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005270 | 400550468 | Molding | HFTD Tier 3 | Distribution | 2007-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005271 | 400550607 | Ground | HFTD Tier 3 | Distribution | 2005-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005272 | 400550696 | Molding | HFTD Tier 3 | Distribution | 2005-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005273 | 400550711 | Molding | HFTD Tier 3 | Distribution | 2006-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005274 | 400550892 | High Sign | HFTD Tier 3 | Distribution | 2006-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005275 | 400550907 | Cable/Conductor | HFTD Tier 2 | Distribution | 2005-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005276 | 400550916 | Molding | HFTD Tier 3 | Distribution | 2003-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005277 | 400550944 | Molding | HFTD Tier 3 | Distribution | 2003-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005278 | 400551035 | Molding | HFTD Tier 2 | Distribution | 2005-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005279 | 400551076 | High Sign | HFTD Tier 2 | Distribution | 2003-11-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005280 | 400551220 | Molding | HFTD Tier 3 | Distribution | 2006-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005281 | 400551440 | Molding | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005282 | 400551457 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005283 | 400551465 | High Sign | HFTD Tier 3 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005284 | 400551638 | High Sign | HFTD Tier 3 | Distribution | 2007-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005285 | 400551734 | High Sign | HFTD Tier 2 | Distribution | 2007-10-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005286 | 400551851 | Guy | HFTD Tier 3 | Distribution | 2006-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005287 | 400552071 | Guy | HFTD Tier 2 | Distribution | 2006-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005288 | 400552113 | Molding | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005289 | 400552253 | Molding | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005290 | 400552845 | High Sign | HFTD Tier 2 | Distribution | 2007-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005291 | 400552869 | Molding | HFTD Tier 2 | Distribution | 2007-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005292 | 400552902 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005293 | 400553020 | High Sign | HFTD Tier 2 | Distribution | 2001-12-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005294 | 400553062 | Molding | HFTD Tier 2 | Distribution | 2001-11-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005295 | 400553126 | Molding | HFTD Tier 3 | Distribution | 2005-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005296 | 400553294 | Molding | HFTD Tier 2 | Distribution | 2003-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005297 | 400553302 | High Sign | HFTD Tier 3 | Distribution | 2005-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005298 | 400553365 | Hardware/Framing | HFTD Tier 3 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005299 | 400553747 | High Sign | HFTD Tier 2 | Distribution | 2002-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005300 | 400553780 | High Sign | HFTD Tier 3 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005301 | 400553904 | Molding | HFTD Tier 3 | Distribution | 2005-06-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005302 | 400553962 | Crossarm | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005303 | 400554031 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005304 | 400554259 | Molding | HFTD Tier 2 | Distribution | 2004-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005305 | 400554306 | High Sign | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005306 | 400554349 | Molding | HFTD Tier 3 | Distribution | 2005-08-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005307 | 400554584 | Molding | HFTD Tier 3 | Distribution | 2006-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005308 | 400554806 | High Sign | HFTD Tier 2 | Distribution | 2007-10-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005309 | 400554822 | Molding | HFTD Tier 2 | Distribution | 2005-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005310 | 400554962 | Guy | HFTD Tier 3 | Distribution | 2006-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005311 | 400555106 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005312 | 400555213 | High Sign | HFTD Tier 3 | Distribution | 2001-01-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005313 | 400555239 | Molding | HFTD Tier 3 | Distribution | 2005-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005314 | 400555321 | High Sign | HFTD Tier 2 | Distribution | 2006-04-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005315 | 400555567 | Molding | HFTD Tier 3 | Distribution | 2005-06-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005316 | 400555710 | High Sign | HFTD Tier 3 | Distribution | 2002-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005317 | 400555805 | High Sign | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005318 | 400555823 | Molding | HFTD Tier 3 | Distribution | 2006-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005319 | 400556484 | Molding | HFTD Tier 3 | Distribution | 2007-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005320 | 400556486 | High Sign | HFTD Tier 2 | Distribution | 2007-10-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005321 | 400556497 | Guy | HFTD Tier 3 | Distribution | 2007-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005322 | 400556724 | High Sign | HFTD Tier 2 | Distribution | 2007-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005323 | 400556896 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005324 | 400556925 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005325 | 400556944 | High Sign | HFTD Tier 2 | Distribution | 2005-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005326 | 400557082 | Molding | HFTD Tier 3 | Distribution | 2007-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005327 | 400557165 | Molding | HFTD Tier 3 | Distribution | 2006-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005328 | 400557216 | High Sign | HFTD Tier 3 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005329 | 400557325 | Molding | HFTD Tier 3 | Distribution | 2005-12-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005330 | 400557328 | High Sign | HFTD Tier 2 | Distribution | 2005-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005331 | 400557428 | Molding | HFTD Tier 3 | Distribution | 2004-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005332 | 400557485 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005333 | 400557516 | Molding | HFTD Tier 2 | Distribution | 2006-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005334 | 400557568 | High Sign | HFTD Tier 3 | Distribution | 2006-10-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005335 | 400557704 | High Sign | HFTD Tier 3 | Distribution | 2003-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005336 | 400557710 | Molding | HFTD Tier 3 | Distribution | 2006-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005337 | 400557737 | High Sign | HFTD Tier 2 | Distribution | 2004-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005338 | 400557762 | Molding | HFTD Tier 2 | Distribution | 2006-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005339 | 400557925 | High Sign | HFTD Tier 2 | Distribution | 2003-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005340 | 400557926 | Guy | HFTD Tier 3 | Distribution | 2006-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005341 | 400558040 | Guy | HFTD Tier 2 | Distribution | 2007-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005342 | 400558153 | High Sign | HFTD Tier 2 | Distribution | 2006-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005343 | 400558174 | Molding | HFTD Tier 2 | Distribution | 2005-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005344 | 400558182 | High Sign | HFTD Tier 2 | Distribution | 2004-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005345 | 400558248 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005346 | 400558252 | High Sign | HFTD Tier 2 | Distribution | 2005-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005347 | 400558406 | High Sign | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005348 | 400558507 | Guy | HFTD Tier 3 | Distribution | 2007-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005349 | 400558604 | High Sign | HFTD Tier 3 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005350 | 400558734 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-01-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005351 | 400558775 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005352 | 400558821 | Hardware/Framing | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005353 | 400558823 | High Sign | HFTD Tier 3 | Distribution | 2002-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005354 | 400558923 | High Sign | HFTD Tier 3 | Distribution | 2007-01-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005355 | 400558977 | High Sign | HFTD Tier 2 | Distribution | 2007-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005356 | 400559076 | Molding | HFTD Tier 2 | Distribution | 2006-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005357 | 400559094 | High Sign | HFTD Tier 2 | Distribution | 2006-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005358 | 400559145 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005359 | 400559213 | Molding | HFTD Tier 3 | Distribution | 2007-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005360 | 400559321 | Riser/Conduit | HFTD Tier 3 | Distribution | 2006-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005361 | 400559393 | Molding | HFTD Tier 2 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005362 | 400559427 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005363 | 400559472 | Molding | HFTD Tier 2 | Distribution | 2006-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005364 | 400559529 | High Sign | HFTD Tier 3 | Distribution | 2005-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005365 | 400559544 | High Sign | HFTD Tier 3 | Distribution | 2003-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005366 | 400559685 | High Sign | HFTD Tier 2 | Distribution | 2006-05-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005367 | 400559964 | High Sign | HFTD Tier 3 | Distribution | 2007-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005368 | 400560043 | High Sign | HFTD Tier 2 | Distribution | 2003-11-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005369 | 400560063 | High Sign | HFTD Tier 3 | Distribution | 2006-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005370 | 400560147 | Guy | HFTD Tier 3 | Distribution | 2006-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005371 | 400560148 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005372 | 400560247 | High Sign | HFTD Tier 3 | Distribution | 2001-11-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005373 | 400560281 | High Sign | HFTD Tier 2 | Distribution | 2006-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005374 | 400560353 | High Sign | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005375 | 400560477 | Molding | HFTD Tier 2 | Distribution | 2006-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005376 | 400560598 | Hardware/Framing | HFTD Tier 3 | Distribution | 2001-08-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005377 | 400560607 | Molding | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005378 | 400560686 | High Sign | HFTD Tier 2 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005379 | 400560691 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005380 | 400560721 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005381 | 400560852 | Guy | HFTD Tier 3 | Distribution | 2007-08-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005382 | 400560974 | Ground | HFTD Tier 3 | Distribution | 2005-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005383 | 400561086 | High Sign | HFTD Tier 3 | Distribution | 2007-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005384 | 400561319 | High Sign | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005385 | 400561345 | High Sign | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005386 | 400561463 | Molding | HFTD Tier 2 | Distribution | 2006-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005387 | 400561524 | Molding | HFTD Tier 3 | Distribution | 2006-07-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005388 | 400561738 | Guy | HFTD Tier 3 | Distribution | 2007-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005389 | 400561829 | Molding | HFTD Tier 2 | Distribution | 2006-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005390 | 400561939 | Molding | HFTD Tier 3 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005391 | 400562098 | High Sign | HFTD Tier 3 | Distribution | 2005-10-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005392 | 400562106 | Molding | HFTD Tier 2 | Distribution | 2004-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005393 | 400562115 | Hardware/Framing | HFTD Tier 3 | Distribution | 2002-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005394 | 400562132 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005395 | 400562237 | High Sign | HFTD Tier 2 | Distribution | 2004-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005396 | 400562492 | Molding | HFTD Tier 3 | Distribution | 2006-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005397 | 400562536 | High Sign | HFTD Tier 2 | Distribution | 1999-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005398 | 400562538 | High Sign | HFTD Tier 3 | Distribution | 2005-09-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005399 | 400562611 | High Sign | HFTD Tier 3 | Distribution | 2006-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005400 | 400562841 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005401 | 400562842 | Molding | HFTD Tier 2 | Distribution | 2006-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005402 | 400562886 | Guy | HFTD Tier 2 | Distribution | 2005-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005403 | 400562985 | Molding | HFTD Tier 2 | Distribution | 2007-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005404 | 400563010 | High Sign | HFTD Tier 2 | Distribution | 2005-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005405 | 400563235 | High Sign | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005406 | 400563262 | High Sign | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005407 | 400563273 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005408 | 400563377 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005409 | 400563567 | Molding | HFTD Tier 3 | Distribution | 2006-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005410 | 400563592 | Molding | HFTD Tier 2 | Distribution | 2002-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005411 | 400563621 | Molding | HFTD Tier 2 | Distribution | 2002-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005412 | 400563636 | Molding | HFTD Tier 3 | Distribution | 2001-11-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005413 | 400564057 | High Sign | HFTD Tier 3 | Distribution | 2001-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005414 | 400564093 | Molding | HFTD Tier 2 | Distribution | 2006-09-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005415 | 400564117 | High Sign | HFTD Tier 3 | Distribution | 2001-11-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005416 | 400564158 | High Sign | HFTD Tier 3 | Distribution | 2007-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005417 | 400564183 | Molding | HFTD Tier 3 | Distribution | 2002-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005418 | 400564420 | Molding | HFTD Tier 2 | Distribution | 2006-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005419 | 400564626 | Molding | HFTD Tier 2 | Distribution | 2005-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005420 | 400564741 | Molding | HFTD Tier 3 | Distribution | 2006-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005421 | 400564746 | High Sign | HFTD Tier 2 | Distribution | 2007-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005422 | 400564864 | High Sign | HFTD Tier 3 | Distribution | 2006-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005423 | 400564897 | Molding | HFTD Tier 2 | Distribution | 2002-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005424 | 400564947 | Molding | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005425 | 400565053 | High Sign | HFTD Tier 2 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005426 | 400565357 | High Sign | HFTD Tier 2 | Distribution | 2006-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005427 | 400565505 | Hardware/Framing | HFTD Tier 3 | Distribution | 2002-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005428 | 400565513 | Molding | HFTD Tier 2 | Distribution | 2006-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005429 | 400565606 | High Sign | HFTD Tier 2 | Distribution | 2006-09-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005430 | 400565744 | High Sign | HFTD Tier 2 | Distribution | 2006-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005431 | 400565757 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005432 | 400565866 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005433 | 400565942 | High Sign | HFTD Tier 2 | Distribution | 2003-11-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005434 | 400566069 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005435 | 400566071 | Guy | HFTD Tier 3 | Distribution | 2006-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005436 | 400566338 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005437 | 400566350 | Molding | HFTD Tier 3 | Distribution | 2001-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005438 | 400566353 | High Sign | HFTD Tier 3 | Distribution | 2001-01-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005439 | 400566379 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005440 | 400566382 | Molding | HFTD Tier 2 | Distribution | 2006-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005441 | 400566407 | High Sign | HFTD Tier 2 | Distribution | 2005-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005442 | 400566412 | Molding | HFTD Tier 2 | Distribution | 2006-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005443 | 400566492 | High Sign | HFTD Tier 2 | Distribution | 2002-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005444 | 400566517 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005445 | 400566562 | High Sign | HFTD Tier 2 | Distribution | 2007-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005446 | 400566629 | Molding | HFTD Tier 3 | Distribution | 2006-01-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005447 | 400566728 | Guy | HFTD Tier 3 | Distribution | 2002-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005448 | 400566784 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005449 | 400566999 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005450 | 400567082 | High Sign | HFTD Tier 3 | Distribution | 2006-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005451 | 400567123 | Molding | HFTD Tier 2 | Distribution | 2006-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005452 | 400567166 | Insulator | HFTD Tier 2 | Distribution | 2006-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005453 | 400567264 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005454 | 400567408 | High Sign | HFTD Tier 2 | Distribution | 2002-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005455 | 400567411 | Guy | HFTD Tier 3 | Distribution | 2007-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005456 | 400567426 | Hardware/Framing | HFTD Tier 2 | Distribution | 2002-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005457 | 400567618 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005458 | 400567631 | Molding | HFTD Tier 2 | Distribution | 2006-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005459 | 400567668 | Molding | HFTD Tier 3 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005460 | 400567757 | Guy | HFTD Tier 3 | Distribution | 2002-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005461 | 400567781 | High Sign | HFTD Tier 3 | Distribution | 2006-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005462 | 400567823 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005463 | 400568296 | Molding | HFTD Tier 2 | Distribution | 2006-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005464 | 400568529 | High Sign | HFTD Tier 3 | Distribution | 2007-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005465 | 400568779 | Guy | HFTD Tier 2 | Distribution | 2007-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005466 | 400568831 | Molding | HFTD Tier 3 | Distribution | 2007-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005467 | 400569051 | Molding | HFTD Tier 3 | Distribution | 2007-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005468 | 400569127 | Molding | HFTD Tier 3 | Distribution | 2002-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005469 | 400569135 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005470 | 400569462 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-05-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005471 | 400569612 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005472 | 400569724 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005473 | 400569814 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005474 | 400569834 | High Sign | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005475 | 400569946 | High Sign | HFTD Tier 2 | Distribution | 2006-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005476 | 400569967 | High Sign | HFTD Tier 2 | Distribution | 2005-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005477 | 400570189 | Guy | HFTD Tier 3 | Distribution | 2007-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005478 | 400570268 | Molding | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005479 | 400570387 | Molding | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005480 | 400570400 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005481 | 400570443 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005482 | 400570447 | High Sign | HFTD Tier 3 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005483 | 400570566 | Molding | HFTD Tier 2 | Distribution | 2006-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005484 | 400570568 | High Sign | HFTD Tier 3 | Distribution | 2007-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005485 | 400570754 | High Sign | HFTD Tier 2 | Distribution | 2006-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005486 | 400570857 | Molding | HFTD Tier 3 | Distribution | 2002-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005487 | 400571386 | Molding | HFTD Tier 3 | Distribution | 2007-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005488 | 400571446 | High Sign | HFTD Tier 3 | Distribution | 2006-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005489 | 400571543 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2008-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005490 | 400571748 | High Sign | HFTD Tier 3 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005491 | 400571953 | Molding | HFTD Tier 3 | Distribution | 2006-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005492 | 400571969 | Molding | HFTD Tier 3 | Distribution | 2007-05-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005493 | 400571995 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005494 | 400572010 | High Sign | HFTD Tier 3 | Distribution | 2006-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005495 | 400572183 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005496 | 400572226 | High Sign | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005497 | 400572307 | High Sign | HFTD Tier 3 | Distribution | 2007-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005498 | 400572453 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005499 | 400572472 | High Sign | HFTD Tier 3 | Distribution | 2001-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005500 | 400572566 | Molding | HFTD Tier 3 | Distribution | 2007-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005501 | 400572821 | High Sign | HFTD Tier 2 | Distribution | 2006-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005502 | 400572831 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005503 | 400572981 | Molding | HFTD Tier 3 | Distribution | 2006-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005504 | 400573016 | Molding | HFTD Tier 2 | Distribution | 2001-11-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005505 | 400573076 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005506 | 400573236 | High Sign | HFTD Tier 3 | Distribution | 2006-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005507 | 400573263 | Molding | HFTD Tier 2 | Distribution | 2006-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005508 | 400573265 | High Sign | HFTD Tier 3 | Distribution | 2006-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005509 | 400573271 | High Sign | HFTD Tier 2 | Distribution | 2001-10-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005510 | 400573315 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005511 | 400573485 | Molding | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005512 | 400573542 | Molding | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005513 | 400573596 | High Sign | HFTD Tier 2 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005514 | 400573601 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005515 | 400573698 | High Sign | HFTD Tier 3 | Distribution | 2006-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005516 | 400573706 | Guy | HFTD Tier 3 | Distribution | 2007-04-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005517 | 400573716 | Guy | HFTD Tier 3 | Distribution | 2006-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005518 | 400574029 | High Sign | HFTD Tier 2 | Distribution | 2003-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005519 | 400574047 | High Sign | HFTD Tier 2 | Distribution | 2006-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005520 | 400574110 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005521 | 400574120 | Guy | HFTD Tier 3 | Distribution | 2002-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005522 | 400574146 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005523 | 400574229 | High Sign | HFTD Tier 3 | Distribution | 2006-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005524 | 400574364 | Molding | HFTD Tier 2 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005525 | 400574777 | Molding | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005526 | 400574841 | Guy | HFTD Tier 3 | Distribution | 2007-04-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005527 | 400574867 | High Sign | HFTD Tier 3 | Distribution | 2006-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005528 | 400574877 | High Sign | HFTD Tier 2 | Distribution | 2001-09-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005529 | 400574913 | High Sign | HFTD Tier 3 | Distribution | 2007-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005530 | 400575035 | Guy | HFTD Tier 3 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005531 | 400575048 | Molding | HFTD Tier 3 | Distribution | 2006-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005532 | 400575069 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2009-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005533 | 400575080 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005534 | 400575102 | High Sign | HFTD Tier 2 | Distribution | 2003-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005535 | 400575130 | High Sign | HFTD Tier 2 | Distribution | 2003-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005536 | 400575199 | High Sign | HFTD Tier 3 | Distribution | 2007-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005537 | 400575304 | High Sign | HFTD Tier 3 | Distribution | 2009-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005538 | 400575430 | High Sign | HFTD Tier 2 | Distribution | 2006-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005539 | 400575533 | Guy | HFTD Tier 3 | Distribution | 2007-08-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005540 | 400575576 | High Sign | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005541 | 400575824 | High Sign | HFTD Tier 3 | Distribution | 2005-11-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005542 | 400575981 | High Sign | HFTD Tier 3 | Distribution | 2006-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005543 | 400576008 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005544 | 400576032 | High Sign | HFTD Tier 2 | Distribution | 2005-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005545 | 400576056 | Molding | HFTD Tier 2 | Distribution | 2006-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005546 | 400576159 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005547 | 400576307 | Molding | HFTD Tier 3 | Distribution | 2007-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005548 | 400576324 | High Sign | HFTD Tier 2 | Distribution | 2002-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005549 | 400576332 | Molding | HFTD Tier 3 | Distribution | 2007-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005550 | 400576431 | Molding | HFTD Tier 3 | Distribution | 2002-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005551 | 400576487 | Guy | HFTD Tier 3 | Distribution | 2007-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005552 | 400576495 | Molding | HFTD Tier 2 | Distribution | 2006-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005553 | 400576550 | Molding | HFTD Tier 2 | Distribution | 2006-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005554 | 400576556 | High Sign | HFTD Tier 2 | Distribution | 2006-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005555 | 400576635 | Guy | HFTD Tier 2 | Distribution | 2007-08-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005556 | 400576787 | Guy | HFTD Tier 2 | Distribution | 2007-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005557 | 400576805 | High Sign | HFTD Tier 3 | Distribution | 2007-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005558 | 400576858 | High Sign | HFTD Tier 2 | Distribution | 2007-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005559 | 400576941 | Molding | HFTD Tier 2 | Distribution | 2003-04-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005560 | 400576948 | Molding | HFTD Tier 3 | Distribution | 2007-05-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005561 | 400576967 | Molding | HFTD Tier 3 | Distribution | 2007-05-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005562 | 400577033 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005563 | 400577196 | High Sign | HFTD Tier 3 | Distribution | 2007-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005564 | 400577307 | High Sign | HFTD Tier 3 | Distribution | 2008-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005565 | 400577487 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005566 | 400577593 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005567 | 400577630 | Molding | HFTD Tier 2 | Distribution | 2001-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005568 | 400577716 | Ground | HFTD Tier 3 | Distribution | 2003-08-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005569 | 400577802 | Molding | HFTD Tier 3 | Distribution | 2001-09-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005570 | 400577817 | Molding | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005571 | 400577889 | High Sign | HFTD Tier 3 | Distribution | 2002-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005572 | 400577893 | High Sign | HFTD Tier 3 | Distribution | 2007-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005573 | 400578040 | Hardware/Framing | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005574 | 400578054 | High Sign | HFTD Tier 3 | Distribution | 2007-05-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005575 | 400578213 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-09-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005576 | 400578229 | High Sign | HFTD Tier 3 | Distribution | 2004-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005577 | 400578262 | High Sign | HFTD Tier 2 | Distribution | 2006-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005578 | 400578474 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2003-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005579 | 400578593 | High Sign | HFTD Tier 2 | Distribution | 2003-11-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005580 | 400579014 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005581 | 400579511 | Molding | HFTD Tier 2 | Distribution | 2006-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005582 | 400579572 | Molding | HFTD Tier 2 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005583 | 400579626 | Molding | HFTD Tier 2 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005584 | 400579678 | High Sign | HFTD Tier 3 | Distribution | 2001-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005585 | 400579710 | High Sign | HFTD Tier 3 | Distribution | 2006-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005586 | 400579825 | Molding | HFTD Tier 3 | Distribution | 2006-11-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005587 | 400579946 | High Sign | HFTD Tier 3 | Distribution | 2008-05-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005588 | 400579955 | High Sign | HFTD Tier 2 | Distribution | 2007-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005589 | 400579992 | Guy | HFTD Tier 2 | Distribution | 2006-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005590 | 400580239 | High Sign | HFTD Tier 2 | Distribution | 2001-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005591 | 400580268 | High Sign | HFTD Tier 3 | Distribution | 2006-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005592 | 400580492 | High Sign | HFTD Tier 3 | Distribution | 2001-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005593 | 400580495 | High Sign | HFTD Tier 2 | Distribution | 2005-12-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005594 | 400580615 | Molding | HFTD Tier 3 | Distribution | 2006-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005595 | 400580695 | Molding | HFTD Tier 2 | Distribution | 2007-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005596 | 400580710 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005597 | 400580760 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005598 | 400580827 | Molding | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005599 | 400580925 | Molding | HFTD Tier 3 | Distribution | 2001-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005600 | 400580997 | High Sign | HFTD Tier 3 | Distribution | 2005-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005601 | 400581315 | Guy | HFTD Tier 2 | Distribution | 2002-01-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005602 | 400581359 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005603 | 400581391 | Molding | HFTD Tier 2 | Distribution | 2004-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005604 | 400581429 | High Sign | HFTD Tier 3 | Distribution | 2001-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005605 | 400581446 | High Sign | HFTD Tier 3 | Distribution | 2001-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005606 | 400581539 | Molding | HFTD Tier 2 | Distribution | 2008-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005607 | 400581565 | High Sign | HFTD Tier 2 | Distribution | 2003-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005608 | 400581650 | High Sign | HFTD Tier 3 | Distribution | 2005-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005609 | 400581799 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005610 | 400581845 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005611 | 400582081 | Molding | HFTD Tier 3 | Distribution | 2007-07-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005612 | 400582259 | Molding | HFTD Tier 3 | Distribution | 2002-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005613 | 400582270 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005614 | 400582380 | Molding | HFTD Tier 3 | Distribution | 2002-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005615 | 400582451 | Insulator | HFTD Tier 2 | Distribution | 2006-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005616 | 400582486 | Molding | HFTD Tier 3 | Distribution | 2008-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005617 | 400582532 | High Sign | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005618 | 400582587 | Guy | HFTD Tier 3 | Distribution | 2004-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005619 | 400582709 | Molding | HFTD Tier 3 | Distribution | 2007-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005620 | 400582809 | High Sign | HFTD Tier 3 | Distribution | 2008-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005621 | 400582878 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005622 | 400582965 | High Sign | HFTD Tier 3 | Distribution | 2008-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005623 | 400583021 | Molding | HFTD Tier 2 | Distribution | 2003-10-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005624 | 400583032 | High Sign | HFTD Tier 3 | Distribution | 2001-12-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005625 | 400583047 | High Sign | HFTD Tier 3 | Distribution | 2002-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005626 | 400583050 | Molding | HFTD Tier 2 | Distribution | 2006-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005627 | 400583083 | Molding | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005628 | 400583109 | High Sign | HFTD Tier 2 | Distribution | 2006-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005629 | 400583141 | High Sign | HFTD Tier 2 | Distribution | 2007-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005630 | 400583282 | Termination | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005631 | 400583386 | Molding | HFTD Tier 2 | Distribution | 2008-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005632 | 400583401 | High Sign | HFTD Tier 3 | Distribution | 2006-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005633 | 400583431 | Molding | HFTD Tier 3 | Distribution | 2007-08-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005634 | 400583483 | High Sign | HFTD Tier 3 | Distribution | 2007-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005635 | 400583509 | Guy | HFTD Tier 3 | Distribution | 2007-05-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005636 | 400583595 | High Sign | HFTD Tier 3 | Distribution | 2007-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005637 | 400583741 | Molding | HFTD Tier 2 | Distribution | 2003-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005638 | 400583776 | Molding | HFTD Tier 3 | Distribution | 2006-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005639 | 400583898 | High Sign | HFTD Tier 2 | Distribution | 2003-03-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005640 | 400584003 | Molding | HFTD Tier 3 | Distribution | 2005-11-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005641 | 400584184 | Molding | HFTD Tier 2 | Distribution | 2006-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005642 | 400584256 | High Sign | HFTD Tier 2 | Distribution | 2002-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005643 | 400584291 | High Sign | HFTD Tier 2 | Distribution | 2006-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005644 | 400584368 | High Sign | HFTD Tier 2 | Distribution | 2004-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005645 | 400584552 | High Sign | HFTD Tier 3 | Distribution | 2005-12-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005646 | 400584765 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005647 | 400584767 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-09-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005648 | 400584862 | Molding | HFTD Tier 2 | Distribution | 2007-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005649 | 400584896 | High Sign | HFTD Tier 3 | Distribution | 2001-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005650 | 400584920 | Molding | HFTD Tier 3 | Distribution | 2001-12-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005651 | 400584929 | High Sign | HFTD Tier 3 | Distribution | 2007-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005652 | 400585037 | Molding | HFTD Tier 3 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005653 | 400585265 | Molding | HFTD Tier 2 | Distribution | 2006-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005654 | 400585406 | Molding | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005655 | 400585430 | Guy | HFTD Tier 3 | Distribution | 2007-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005656 | 400585599 | High Sign | HFTD Tier 3 | Distribution | 2002-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005657 | 400585676 | Molding | HFTD Tier 3 | Distribution | 2003-09-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005658 | 400585862 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005659 | 400586042 | High Sign | HFTD Tier 3 | Distribution | 2002-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005660 | 400586071 | High Sign | HFTD Tier 3 | Distribution | 2007-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005661 | 400586132 | High Sign | HFTD Tier 3 | Distribution | 2004-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005662 | 400586368 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005663 | 400586542 | High Sign | HFTD Tier 2 | Distribution | 2006-01-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005664 | 400586633 | Riser/Conduit | HFTD Tier 2 | Distribution | 2007-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005665 | 400586641 | Guy | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005666 | 400586854 | Guy | HFTD Tier 3 | Distribution | 2007-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005667 | 400586940 | Molding | HFTD Tier 3 | Distribution | 2007-04-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005668 | 400587087 | Molding | HFTD Tier 2 | Distribution | 2006-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005669 | 400587234 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005670 | 400587241 | High Sign | HFTD Tier 3 | Distribution | 2001-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005671 | 400587253 | Molding | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005672 | 400587289 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005673 | 400587314 | Molding | HFTD Tier 3 | Distribution | 2003-09-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005674 | 400587416 | Molding | HFTD Tier 2 | Distribution | 2003-11-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005675 | 400587465 | Molding | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005676 | 400587472 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-09-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005677 | 400587498 | High Sign | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005678 | 400587515 | High Sign | HFTD Tier 2 | Distribution | 2004-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005679 | 400587525 | High Sign | HFTD Tier 2 | Distribution | 2001-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005680 | 400587546 | High Sign | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005681 | 400587566 | Molding | HFTD Tier 3 | Distribution | 2008-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005682 | 400587746 | Guy | HFTD Tier 3 | Distribution | 2003-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005683 | 400587752 | High Sign | HFTD Tier 3 | Distribution | 2007-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005684 | 400587771 | High Sign | HFTD Tier 3 | Distribution | 2007-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005685 | 400587947 | High Sign | HFTD Tier 3 | Distribution | 2006-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005686 | 400588047 | Molding | HFTD Tier 2 | Distribution | 2007-10-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005687 | 400588119 | Molding | HFTD Tier 3 | Distribution | 2003-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005688 | 400588138 | High Sign | HFTD Tier 2 | Distribution | 2007-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005689 | 400588153 | Molding | HFTD Tier 2 | Distribution | 2003-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005690 | 400588274 | High Sign | HFTD Tier 3 | Distribution | 2005-10-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005691 | 400588288 | High Sign | HFTD Tier 3 | Distribution | 2006-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005692 | 400588359 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005693 | 400588367 | High Sign | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005694 | 400588461 | Molding | HFTD Tier 3 | Distribution | 2001-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005695 | 400588603 | Molding | HFTD Tier 3 | Distribution | 2008-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005696 | 400588917 | Molding | HFTD Tier 2 | Distribution | 2006-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005697 | 400588946 | High Sign | HFTD Tier 2 | Distribution | 2006-01-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005698 | 400588971 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005699 | 400589135 | High Sign | HFTD Tier 2 | Distribution | 2007-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005700 | 400589240 | High Sign | HFTD Tier 3 | Distribution | 2006-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005701 | 400589346 | Guy | HFTD Tier 2 | Distribution | 2006-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005702 | 400589380 | Molding | HFTD Tier 2 | Distribution | 2006-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005703 | 400589386 | Molding | HFTD Tier 2 | Distribution | 2006-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005704 | 400589428 | Molding | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005705 | 400589435 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005706 | 400589677 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005707 | 400589681 | Molding | HFTD Tier 3 | Distribution | 2007-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005708 | 400589737 | Molding | HFTD Tier 3 | Distribution | 2003-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005709 | 400589798 | Insulator | HFTD Tier 2 | Distribution | 2006-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005710 | 400589893 | Molding | HFTD Tier 3 | Distribution | 2001-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005711 | 400589938 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005712 | 400589962 | Molding | HFTD Tier 2 | Distribution | 2006-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005713 | 400589976 | High Sign | HFTD Tier 3 | Distribution | 2007-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005714 | 400589979 | Molding | HFTD Tier 2 | Distribution | 2006-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005715 | 400590232 | High Sign | HFTD Tier 3 | Distribution | 2007-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005716 | 400590383 | High Sign | HFTD Tier 3 | Distribution | 2007-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005717 | 400590389 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005718 | 400590405 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005719 | 400590437 | High Sign | HFTD Tier 2 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005720 | 400590512 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-09-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005721 | 400590668 | Molding | HFTD Tier 2 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005722 | 400590734 | High Sign | HFTD Tier 2 | Distribution | 2003-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005723 | 400590816 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005724 | 400590830 | Molding | HFTD Tier 2 | Distribution | 2007-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005725 | 400591083 | High Sign | HFTD Tier 3 | Distribution | 2001-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005726 | 400591194 | Molding | HFTD Tier 2 | Distribution | 2007-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005727 | 400591218 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005728 | 400591255 | Molding | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005729 | 400591364 | High Sign | HFTD Tier 2 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005730 | 400591366 | Molding | HFTD Tier 3 | Distribution | 2001-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005731 | 400591403 | High Sign | HFTD Tier 2 | Distribution | 2004-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005732 | 400591442 | High Sign | HFTD Tier 2 | Distribution | 2005-12-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005733 | 400591446 | Guy | HFTD Tier 3 | Distribution | 2005-10-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005734 | 400591465 | Guy | HFTD Tier 2 | Distribution | 2006-08-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005735 | 400591490 | Molding | HFTD Tier 2 | Distribution | 2001-11-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005736 | 400591578 | Molding | HFTD Tier 2 | Distribution | 2008-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005737 | 400591581 | High Sign | HFTD Tier 3 | Distribution | 2001-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005738 | 400591654 | Molding | HFTD Tier 3 | Distribution | 2005-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005739 | 400591788 | High Sign | HFTD Tier 2 | Distribution | 2003-10-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005740 | 400591953 | Molding | HFTD Tier 3 | Distribution | 2002-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005741 | 400592272 | High Sign | HFTD Tier 3 | Distribution | 2007-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005742 | 400592302 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005743 | 400592361 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005744 | 400592391 | Molding | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005745 | 400592640 | High Sign | HFTD Tier 2 | Distribution | 2003-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005746 | 400592752 | High Sign | HFTD Tier 2 | Distribution | 2007-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005747 | 400592825 | Molding | HFTD Tier 2 | Distribution | 2005-09-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005748 | 400593057 | High Sign | HFTD Tier 2 | Distribution | 2005-12-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005749 | 400593116 | High Sign | HFTD Tier 2 | Distribution | 2002-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005750 | 400593280 | Molding | HFTD Tier 3 | Distribution | 2007-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005751 | 400593298 | Molding | HFTD Tier 2 | Distribution | 2006-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005752 | 400593309 | High Sign | HFTD Tier 3 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005753 | 400593314 | Cable/Conductor | HFTD Tier 2 | Distribution | 2005-08-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005754 | 400593353 | High Sign | HFTD Tier 3 | Distribution | 2007-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005755 | 400593465 | High Sign | HFTD Tier 2 | Distribution | 2007-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005756 | 400593466 | Molding | HFTD Tier 2 | Distribution | 2006-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005757 | 400593470 | High Sign | HFTD Tier 3 | Distribution | 2006-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005758 | 400593474 | High Sign | HFTD Tier 3 | Distribution | 2002-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005759 | 400593617 | High Sign | HFTD Tier 3 | Distribution | 2007-02-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005760 | 400593754 | High Sign | HFTD Tier 3 | Distribution | 2007-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005761 | 400593813 | High Sign | HFTD Tier 3 | Distribution | 2003-10-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005762 | 400594068 | Molding | HFTD Tier 3 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005763 | 400594115 | High Sign | HFTD Tier 3 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005764 | 400594476 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005765 | 400594658 | Molding | HFTD Tier 3 | Distribution | 2006-10-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005766 | 400594714 | Molding | HFTD Tier 2 | Distribution | 2006-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005767 | 400594716 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005768 | 400594728 | High Sign | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005769 | 400594778 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005770 | 400594811 | Molding | HFTD Tier 3 | Distribution | 2007-04-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005771 | 400594978 | High Sign | HFTD Tier 2 | Distribution | 2006-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005772 | 400595136 | Molding | HFTD Tier 3 | Distribution | 2006-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005773 | 400595143 | High Sign | HFTD Tier 3 | Distribution | 2008-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005774 | 400595266 | Molding | HFTD Tier 2 | Distribution | 2004-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005775 | 400595409 | Guy | HFTD Tier 3 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005776 | 400595476 | Guy | HFTD Tier 3 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005777 | 400595710 | High Sign | HFTD Tier 2 | Distribution | 2001-12-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005778 | 400595852 | Molding | HFTD Tier 2 | Distribution | 2005-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005779 | 400595859 | High Sign | HFTD Tier 3 | Distribution | 2005-09-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005780 | 400595891 | Molding | HFTD Tier 3 | Distribution | 2007-07-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005781 | 400596077 | High Sign | HFTD Tier 2 | Distribution | 2009-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005782 | 400596122 | Molding | HFTD Tier 3 | Distribution | 2007-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005783 | 400596158 | High Sign | HFTD Tier 2 | Distribution | 2006-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005784 | 400596329 | High Sign | HFTD Tier 3 | Distribution | 2002-08-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005785 | 400596504 | High Sign | HFTD Tier 3 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005786 | 400596581 | Molding | HFTD Tier 2 | Distribution | 2006-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005787 | 400596601 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005788 | 400596837 | High Sign | HFTD Tier 2 | Distribution | 2002-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005789 | 400596979 | Molding | HFTD Tier 3 | Distribution | 2003-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005790 | 400597108 | High Sign | HFTD Tier 2 | Distribution | 2005-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005791 | 400597113 | High Sign | HFTD Tier 3 | Distribution | 2006-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005792 | 400597171 | High Sign | HFTD Tier 3 | Distribution | 2007-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005793 | 400597172 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005794 | 400597189 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005795 | 400597255 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005796 | 400597292 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005797 | 400597370 | High Sign | HFTD Tier 3 | Distribution | 2006-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005798 | 400597528 | Molding | HFTD Tier 3 | Distribution | 2003-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005799 | 400597596 | High Sign | HFTD Tier 3 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005800 | 400597688 | High Sign | HFTD Tier 2 | Distribution | 2005-12-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005801 | 400597780 | Molding | HFTD Tier 3 | Distribution | 2006-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005802 | 400597790 | Cable/Conductor | HFTD Tier 3 | Distribution | 2006-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005803 | 400597836 | High Sign | HFTD Tier 3 | Distribution | 2002-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005804 | 400597878 | High Sign | HFTD Tier 2 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005805 | 400597879 | Molding | HFTD Tier 2 | Distribution | 2007-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005806 | 400597984 | Molding | HFTD Tier 2 | Distribution | 2006-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005807 | 400598059 | Molding | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005808 | 400598097 | Guy | HFTD Tier 3 | Distribution | 2006-11-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005809 | 400598689 | High Sign | HFTD Tier 2 | Distribution | 2006-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005810 | 400598900 | High Sign | HFTD Tier 3 | Distribution | 2008-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005811 | 400599092 | High Sign | HFTD Tier 3 | Distribution | 2008-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005812 | 400599167 | High Sign | HFTD Tier 2 | Distribution | 2006-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005813 | 400599256 | High Sign | HFTD Tier 3 | Distribution | 2002-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005814 | 400599271 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005815 | 400599470 | High Sign | HFTD Tier 2 | Distribution | 2008-01-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005816 | 400599565 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005817 | 400599597 | Molding | HFTD Tier 3 | Distribution | 2007-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005818 | 400599626 | Molding | HFTD Tier 3 | Distribution | 2007-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005819 | 400599638 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005820 | 400599682 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005821 | 400599737 | High Sign | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005822 | 400599871 | Molding | HFTD Tier 2 | Distribution | 2005-11-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005823 | 400599995 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005824 | 400600376 | Molding | HFTD Tier 3 | Distribution | 2007-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005825 | 400600475 | High Sign | HFTD Tier 2 | Distribution | 2006-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005826 | 400600518 | High Sign | HFTD Tier 3 | Distribution | 2002-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005827 | 400600535 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005828 | 400600544 | Molding | HFTD Tier 2 | Distribution | 2006-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005829 | 400600553 | Guy | HFTD Tier 3 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005830 | 400601046 | Molding | HFTD Tier 3 | Distribution | 2006-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005831 | 400601049 | Molding | HFTD Tier 3 | Distribution | 2002-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005832 | 400601130 | Molding | HFTD Tier 2 | Distribution | 2006-06-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005833 | 400601140 | Molding | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005834 | 400601236 | Molding | HFTD Tier 2 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005835 | 400601296 | Molding | HFTD Tier 3 | Distribution | 2007-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005836 | 400601527 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005837 | 400601992 | High Sign | HFTD Tier 2 | Distribution | 2002-04-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005838 | 400602012 | Molding | HFTD Tier 2 | Distribution | 2006-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005839 | 400602151 | High Sign | HFTD Tier 2 | Distribution | 2002-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005840 | 400602449 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005841 | 400602551 | High Sign | HFTD Tier 3 | Distribution | 2007-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005842 | 400602621 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005843 | 400602768 | Molding | HFTD Tier 3 | Distribution | 2005-11-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005844 | 400602818 | High Sign | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005845 | 400603435 | High Sign | HFTD Tier 3 | Distribution | 2002-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005846 | 400603480 | Molding | HFTD Tier 3 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005847 | 400603498 | Molding | HFTD Tier 3 | Distribution | 2002-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005848 | 400603538 | Molding | HFTD Tier 2 | Distribution | 2005-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005849 | 400603724 | Guy | HFTD Tier 2 | Distribution | 2006-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005850 | 400603796 | Molding | HFTD Tier 3 | Distribution | 2007-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005851 | 400603861 | High Sign | HFTD Tier 2 | Distribution | 2007-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005852 | 400603945 | Molding | HFTD Tier 3 | Distribution | 2002-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005853 | 400604091 | Riser/Conduit | HFTD Tier 2 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005854 | 400604162 | High Sign | HFTD Tier 2 | Distribution | 2001-12-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005855 | 400604311 | Guy | HFTD Tier 2 | Distribution | 2007-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005856 | 400604359 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005857 | 400604371 | Molding | HFTD Tier 2 | Distribution | 2007-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005858 | 400604503 | Molding | HFTD Tier 2 | Distribution | 2006-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005859 | 400604540 | High Sign | HFTD Tier 3 | Distribution | 2007-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005860 | 400604597 | High Sign | HFTD Tier 3 | Distribution | 2006-10-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005861 | 400604712 | High Sign | HFTD Tier 2 | Distribution | 2006-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005862 | 400604820 | High Sign | HFTD Tier 2 | Distribution | 2003-10-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005863 | 400604961 | High Sign | HFTD Tier 2 | Distribution | 2002-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005864 | 400605035 | High Sign | HFTD Tier 2 | Distribution | 2007-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005865 | 400605075 | Guy | HFTD Tier 2 | Distribution | 2007-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005866 | 400605154 | High Sign | HFTD Tier 3 | Distribution | 2007-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005867 | 400605159 | Molding | HFTD Tier 2 | Distribution | 2007-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005868 | 400605206 | Molding | HFTD Tier 3 | Distribution | 2002-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005869 | 400605485 | Molding | HFTD Tier 3 | Distribution | 2002-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005870 | 400605580 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005871 | 400605598 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005872 | 400605608 | High Sign | HFTD Tier 3 | Distribution | 2008-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005873 | 400605788 | High Sign | HFTD Tier 3 | Distribution | 2002-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005874 | 400605943 | High Sign | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005875 | 400606160 | High Sign | HFTD Tier 3 | Distribution | 2005-12-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005876 | 400606282 | Molding | HFTD Tier 3 | Distribution | 2006-10-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005877 | 400606418 | High Sign | HFTD Tier 3 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005878 | 400606428 | Guy | HFTD Tier 3 | Distribution | 2007-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005879 | 400606546 | Molding | HFTD Tier 2 | Distribution | 2003-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005880 | 400606596 | Cable/Conductor | HFTD Tier 2 | Distribution | 2003-10-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005881 | 400606635 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005882 | 400606678 | High Sign | HFTD Tier 2 | Distribution | 2002-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005883 | 400606858 | High Sign | HFTD Tier 3 | Distribution | 2007-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005884 | 400606871 | Molding | HFTD Tier 2 | Distribution | 2005-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005885 | 400607168 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005886 | 400607194 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005887 | 400607215 | High Sign | HFTD Tier 2 | Distribution | 2007-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005888 | 400607230 | High Sign | HFTD Tier 3 | Distribution | 2001-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005889 | 400607257 | High Sign | HFTD Tier 2 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005890 | 400607294 | Molding | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005891 | 400607367 | Guy | HFTD Tier 2 | Distribution | 2006-09-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005892 | 400607475 | Molding | HFTD Tier 2 | Distribution | 2005-11-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005893 | 400607494 | High Sign | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005894 | 400607505 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005895 | 400607524 | Molding | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005896 | 400607551 | Insulator | HFTD Tier 2 | Distribution | 2006-05-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005897 | 400607553 | Riser/Conduit | HFTD Tier 2 | Distribution | 2002-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005898 | 400607693 | High Sign | HFTD Tier 3 | Distribution | 2001-11-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005899 | 400607801 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005900 | 400607863 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005901 | 400607885 | High Sign | HFTD Tier 3 | Distribution | 2002-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005902 | 400608015 | Molding | HFTD Tier 2 | Distribution | 2003-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005903 | 400608035 | Molding | HFTD Tier 2 | Distribution | 2003-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005904 | 400608040 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005905 | 400608165 | Molding | HFTD Tier 2 | Distribution | 2007-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005906 | 400608283 | High Sign | HFTD Tier 3 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005907 | 400608393 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-09-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005908 | 400608398 | Guy | HFTD Tier 2 | Distribution | 2003-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005909 | 400608454 | High Sign | HFTD Tier 3 | Distribution | 2007-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005910 | 400608456 | Molding | HFTD Tier 2 | Distribution | 2006-09-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005911 | 400608664 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005912 | 400608854 | Molding | HFTD Tier 2 | Distribution | 2006-09-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005913 | 400608935 | Molding | HFTD Tier 3 | Distribution | 2001-09-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005914 | 400608936 | Molding | HFTD Tier 3 | Distribution | 2003-10-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005915 | 400609068 | Molding | HFTD Tier 2 | Distribution | 2006-08-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005916 | 400609140 | High Sign | HFTD Tier 3 | Distribution | 2006-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005917 | 400609201 | High Sign | HFTD Tier 2 | Distribution | 2003-11-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005918 | 400609326 | Molding | HFTD Tier 2 | Distribution | 2006-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005919 | 400609336 | Molding | HFTD Tier 3 | Distribution | 2002-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005920 | 400609359 | High Sign | HFTD Tier 2 | Distribution | 2007-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005921 | 400609657 | High Sign | HFTD Tier 3 | Distribution | 2007-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005922 | 400609687 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005923 | 400609692 | High Sign | HFTD Tier 3 | Distribution | 2001-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005924 | 400609881 | High Sign | HFTD Tier 3 | Distribution | 2006-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005925 | 400609914 | Cable/Conductor | HFTD Tier 3 | Distribution | 2006-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005926 | 400610024 | High Sign | HFTD Tier 3 | Distribution | 2002-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005927 | 400610041 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005928 | 400610109 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005929 | 400610167 | High Sign | HFTD Tier 2 | Distribution | 2006-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005930 | 400610201 | High Sign | HFTD Tier 2 | Distribution | 2002-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005931 | 400610438 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-10-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005932 | 400610644 | High Sign | HFTD Tier 3 | Distribution | 2007-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005933 | 400610773 | Molding | HFTD Tier 2 | Distribution | 2006-09-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005934 | 400610801 | High Sign | HFTD Tier 2 | Distribution | 2006-05-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005935 | 400610861 | Molding | HFTD Tier 3 | Distribution | 2000-09-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005936 | 400611039 | High Sign | HFTD Tier 2 | Distribution | 2002-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005937 | 400611311 | High Sign | HFTD Tier 3 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005938 | 400611336 | High Sign | HFTD Tier 2 | Distribution | 2007-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005939 | 400611363 | Guy | HFTD Tier 2 | Distribution | 2006-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005940 | 400611364 | Molding | HFTD Tier 3 | Distribution | 2007-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005941 | 400611377 | High Sign | HFTD Tier 3 | Distribution | 2007-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005942 | 400611424 | High Sign | HFTD Tier 3 | Distribution | 2002-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005943 | 400611506 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005944 | 400611614 | High Sign | HFTD Tier 2 | Distribution | 2003-11-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005945 | 400611727 | High Sign | HFTD Tier 2 | Distribution | 2002-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005946 | 400611729 | High Sign | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005947 | 400611794 | High Sign | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005948 | 400611795 | Molding | HFTD Tier 2 | Distribution | 2003-11-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005949 | 400611903 | Guy | HFTD Tier 2 | Distribution | 2003-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005950 | 400612455 | Molding | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005951 | 400612533 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005952 | 400612545 | Molding | HFTD Tier 2 | Distribution | 2001-10-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005953 | 400612631 | High Sign | HFTD Tier 2 | Distribution | 2001-10-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005954 | 400612729 | High Sign | HFTD Tier 3 | Distribution | 2001-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005955 | 400612920 | High Sign | HFTD Tier 2 | Distribution | 2003-09-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005956 | 400613159 | Cable/Conductor | HFTD Tier 2 | Distribution | 2002-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005957 | 400613211 | High Sign | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005958 | 400613231 | High Sign | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005959 | 400613273 | High Sign | HFTD Tier 2 | Distribution | 2007-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005960 | 400613274 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005961 | 400613363 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005962 | 400613373 | Molding | HFTD Tier 2 | Distribution | 2006-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005963 | 400613415 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005964 | 400613445 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005965 | 400613459 | Insulator | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005966 | 400613559 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005967 | 400613573 | Molding | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005968 | 400613577 | High Sign | HFTD Tier 2 | Distribution | 2008-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005969 | 400613745 | Molding | HFTD Tier 3 | Distribution | 2006-08-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005970 | 400613792 | High Sign | HFTD Tier 2 | Distribution | 2008-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005971 | 400613908 | High Sign | HFTD Tier 3 | Distribution | 2006-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005972 | 400614313 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005973 | 400614382 | Molding | HFTD Tier 3 | Distribution | 2006-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005974 | 400614621 | Molding | HFTD Tier 3 | Distribution | 2006-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005975 | 400614650 | Molding | HFTD Tier 2 | Distribution | 2006-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005976 | 400614713 | Molding | HFTD Tier 3 | Distribution | 2002-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005977 | 400614818 | High Sign | HFTD Tier 2 | Distribution | 2005-11-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005978 | 400614832 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005979 | 400615261 | High Sign | HFTD Tier 2 | Distribution | 2014-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005980 | 400615323 | Molding | HFTD Tier 3 | Distribution | 2007-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005981 | 400615336 | Guy | HFTD Tier 3 | Distribution | 2005-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005982 | 400615717 | Molding | HFTD Tier 2 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005983 | 400615800 | Molding | HFTD Tier 3 | Distribution | 2001-10-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005984 | 400615833 | Insulator | HFTD Tier 2 | Distribution | 2002-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005985 | 400615978 | Molding | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005986 | 400616006 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005987 | 400616197 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005988 | 400616220 | Molding | HFTD Tier 3 | Distribution | 2001-11-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005989 | 400616225 | Molding | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005990 | 400616312 | Molding | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005991 | 400616367 | High Sign | HFTD Tier 2 | Distribution | 2007-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005992 | 400616469 | Molding | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005993 | 400616612 | Molding | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005994 | 400616671 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-10-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005995 | 400616901 | Molding | HFTD Tier 2 | Distribution | 2002-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005996 | 400616917 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005997 | 400616945 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005998 | 400616969 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130005999 | 400617014 | Molding | HFTD Tier 3 | Distribution | 2001-10-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006000 | 400617042 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006001 | 400617109 | High Sign | HFTD Tier 3 | Distribution | 2006-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006002 | 400617239 | High Sign | HFTD Tier 3 | Distribution | 2005-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006003 | 400617272 | Molding | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006004 | 400617355 | Molding | HFTD Tier 2 | Distribution | 2005-11-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006005 | 400617552 | High Sign | HFTD Tier 2 | Distribution | 2006-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006006 | 400617599 | Guy | HFTD Tier 3 | Distribution | 2007-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006007 | 400617693 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006008 | 400617754 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006009 | 400617816 | High Sign | HFTD Tier 3 | Distribution | 2006-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006010 | 400617831 | High Sign | HFTD Tier 2 | Distribution | 2006-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006011 | 400617945 | Riser/Conduit | HFTD Tier 3 | Distribution | 2006-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006012 | 400618024 | High Sign | HFTD Tier 3 | Distribution | 2008-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006013 | 400618102 | High Sign | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006014 | 400618340 | Guy | HFTD Tier 2 | Distribution | 2003-11-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006015 | 400618342 | High Sign | HFTD Tier 2 | Distribution | 2006-09-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006016 | 400618407 | Molding | HFTD Tier 2 | Distribution | 2007-10-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006017 | 400618476 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-09-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006018 | 400618477 | High Sign | HFTD Tier 2 | Distribution | 2003-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006019 | 400618657 | Molding | HFTD Tier 3 | Distribution | 2006-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006020 | 400618789 | Riser/Conduit | HFTD Tier 3 | Distribution | 2007-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006021 | 400618962 | Molding | HFTD Tier 2 | Distribution | 2008-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006022 | 400619039 | High Sign | HFTD Tier 3 | Distribution | 2008-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006023 | 400619065 | Molding | HFTD Tier 3 | Distribution | 2001-10-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006024 | 400619125 | Molding | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006025 | 400619134 | Molding | HFTD Tier 3 | Distribution | 2001-12-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006026 | 400619136 | Molding | HFTD Tier 2 | Distribution | 2007-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006027 | 400619162 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006028 | 400619210 | High Sign | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006029 | 400619235 | High Sign | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006030 | 400619309 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006031 | 400619326 | Cable/Conductor | HFTD Tier 2 | Distribution | 2007-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006032 | 400619329 | Cable/Conductor | HFTD Tier 3 | Distribution | 2003-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006033 | 400619337 | Molding | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006034 | 400619450 | High Sign | HFTD Tier 2 | Distribution | 2006-10-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006035 | 400619505 | High Sign | HFTD Tier 2 | Distribution | 2002-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006036 | 400619574 | High Sign | HFTD Tier 3 | Distribution | 2006-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006037 | 400619681 | Cable/Conductor | HFTD Tier 3 | Distribution | 2006-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006038 | 400619823 | High Sign | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006039 | 400619861 | Cable/Conductor | HFTD Tier 2 | Distribution | 2007-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006040 | 400619924 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006041 | 400620023 | High Sign | HFTD Tier 3 | Distribution | 2003-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006042 | 400620077 | Molding | HFTD Tier 2 | Distribution | 2007-10-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006043 | 400620153 | High Sign | HFTD Tier 3 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006044 | 400620173 | Molding | HFTD Tier 2 | Distribution | 2005-11-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006045 | 400620259 | Molding | HFTD Tier 3 | Distribution | 2007-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006046 | 400620272 | High Sign | HFTD Tier 3 | Distribution | 2002-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006047 | 400620298 | High Sign | HFTD Tier 3 | Distribution | 2001-10-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006048 | 400620398 | Molding | HFTD Tier 2 | Distribution | 2003-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006049 | 400620739 | Molding | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006050 | 400620961 | Guy | HFTD Tier 3 | Distribution | 2006-09-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006051 | 400621184 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-08-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006052 | 400621229 | High Sign | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006053 | 400621243 | Hardware/Framing | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006054 | 400621306 | Molding | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006055 | 400621315 | Molding | HFTD Tier 2 | Distribution | 2007-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006056 | 400621456 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006057 | 400621539 | Molding | HFTD Tier 2 | Distribution | 2007-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006058 | 400621577 | Molding | HFTD Tier 2 | Distribution | 2006-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006059 | 400621637 | High Sign | HFTD Tier 3 | Distribution | 2002-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006060 | 400621706 | Molding | HFTD Tier 2 | Distribution | 2005-12-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006061 | 400621715 | High Sign | HFTD Tier 2 | Distribution | 2002-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006062 | 400621768 | High Sign | HFTD Tier 3 | Distribution | 2006-11-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006063 | 400621865 | Molding | HFTD Tier 2 | Distribution | 2006-04-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006064 | 400622027 | High Sign | HFTD Tier 2 | Distribution | 2008-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006065 | 400622204 | Molding | HFTD Tier 2 | Distribution | 2007-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006066 | 400622218 | High Sign | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006067 | 400622392 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-09-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006068 | 400622461 | Molding | HFTD Tier 3 | Distribution | 2005-11-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006069 | 400622492 | High Sign | HFTD Tier 2 | Distribution | 2007-09-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006070 | 400622533 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-10-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006071 | 400622661 | High Sign | HFTD Tier 2 | Distribution | 2007-10-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006072 | 400622682 | High Sign | HFTD Tier 3 | Distribution | 2007-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006073 | 400622793 | High Sign | HFTD Tier 3 | Distribution | 2006-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006074 | 400622966 | Molding | HFTD Tier 3 | Distribution | 2002-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006075 | 400623045 | High Sign | HFTD Tier 2 | Distribution | 2006-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006076 | 400623246 | High Sign | HFTD Tier 2 | Distribution | 2007-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006077 | 400623376 | High Sign | HFTD Tier 3 | Distribution | 2002-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006078 | 400623378 | Molding | HFTD Tier 3 | Distribution | 2006-10-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006079 | 400623506 | Molding | HFTD Tier 2 | Distribution | 2003-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006080 | 400623744 | Molding | HFTD Tier 2 | Distribution | 2002-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006081 | 400623761 | Molding | HFTD Tier 3 | Distribution | 2006-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006082 | 400623886 | High Sign | HFTD Tier 2 | Distribution | 2005-12-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006083 | 400624011 | Molding | HFTD Tier 3 | Distribution | 2007-04-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006084 | 400624065 | High Sign | HFTD Tier 3 | Distribution | 2003-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006085 | 400624083 | Molding | HFTD Tier 2 | Distribution | 2007-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006086 | 400624156 | Guy | HFTD Tier 3 | Distribution | 2002-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006087 | 400624166 | High Sign | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006088 | 400624209 | Guy | HFTD Tier 3 | Distribution | 2002-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006089 | 400624233 | High Sign | HFTD Tier 3 | Distribution | 2001-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006090 | 400624307 | High Sign | HFTD Tier 3 | Distribution | 2006-08-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006091 | 400624408 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006092 | 400624578 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006093 | 400624589 | Molding | HFTD Tier 3 | Distribution | 2005-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006094 | 400624697 | High Sign | HFTD Tier 3 | Distribution | 2002-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006095 | 400624760 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006096 | 400624767 | Molding | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006097 | 400624879 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006098 | 400624942 | Molding | HFTD Tier 3 | Distribution | 2002-08-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006099 | 400624984 | Molding | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006100 | 400625020 | High Sign | HFTD Tier 3 | Distribution | 2007-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006101 | 400625033 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006102 | 400625281 | Molding | HFTD Tier 2 | Distribution | 2007-05-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006103 | 400625336 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006104 | 400625337 | High Sign | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006105 | 400625423 | Guy | HFTD Tier 3 | Distribution | 2001-10-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006106 | 400625447 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006107 | 400625525 | Molding | HFTD Tier 2 | Distribution | 2006-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006108 | 400625800 | High Sign | HFTD Tier 3 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006109 | 400625913 | Molding | HFTD Tier 2 | Distribution | 2007-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006110 | 400625970 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-08-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006111 | 400626001 | Molding | HFTD Tier 3 | Distribution | 2002-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006112 | 400626047 | High Sign | HFTD Tier 2 | Distribution | 2003-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006113 | 400626136 | Molding | HFTD Tier 3 | Distribution | 2006-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006114 | 400626250 | High Sign | HFTD Tier 3 | Distribution | 2007-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006115 | 400626387 | High Sign | HFTD Tier 3 | Distribution | 2002-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006116 | 400626392 | Molding | HFTD Tier 3 | Distribution | 2006-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006117 | 400626449 | Insulator | HFTD Tier 2 | Distribution | 2002-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006118 | 400626460 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006119 | 400626553 | Molding | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006120 | 400626556 | Guy | HFTD Tier 2 | Distribution | 2002-02-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006121 | 400626590 | High Sign | HFTD Tier 2 | Distribution | 2006-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006122 | 400626673 | High Sign | HFTD Tier 2 | Distribution | 2002-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006123 | 400626763 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006124 | 400626802 | High Sign | HFTD Tier 2 | Distribution | 2002-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006125 | 400626830 | Molding | HFTD Tier 3 | Distribution | 2007-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006126 | 400626834 | High Sign | HFTD Tier 3 | Distribution | 2002-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006127 | 400626996 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2003-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006128 | 400626998 | High Sign | HFTD Tier 2 | Distribution | 2007-10-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006129 | 400627327 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006130 | 400627416 | Molding | HFTD Tier 2 | Distribution | 2006-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006131 | 400627539 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006132 | 400627649 | Hardware/Framing | HFTD Tier 2 | Distribution | 2005-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006133 | 400627699 | Molding | HFTD Tier 3 | Distribution | 2006-06-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006134 | 400627749 | Molding | HFTD Tier 2 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006135 | 400627753 | High Sign | HFTD Tier 3 | Distribution | 2005-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006136 | 400627868 | High Sign | HFTD Tier 2 | Distribution | 2003-09-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006137 | 400627932 | High Sign | HFTD Tier 2 | Distribution | 2006-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006138 | 400628024 | Molding | HFTD Tier 3 | Distribution | 2006-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006139 | 400628139 | Molding | HFTD Tier 2 | Distribution | 2005-10-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006140 | 400628167 | High Sign | HFTD Tier 2 | Distribution | 2007-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006141 | 400628186 | High Sign | HFTD Tier 3 | Distribution | 2007-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006142 | 400628438 | Molding | HFTD Tier 2 | Distribution | 2007-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006143 | 400628440 | High Sign | HFTD Tier 3 | Distribution | 2008-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006144 | 400628551 | Molding | HFTD Tier 2 | Distribution | 2006-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006145 | 400628589 | Molding | HFTD Tier 3 | Distribution | 2008-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006146 | 400628884 | Molding | HFTD Tier 2 | Distribution | 2002-02-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006147 | 400629032 | High Sign | HFTD Tier 3 | Distribution | 2002-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006148 | 400629124 | Molding | HFTD Tier 2 | Distribution | 2002-02-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006149 | 400629190 | High Sign | HFTD Tier 2 | Distribution | 2003-11-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006150 | 400629264 | High Sign | HFTD Tier 2 | Distribution | 2003-11-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006151 | 400629438 | Guy | HFTD Tier 3 | Distribution | 2007-01-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006152 | 400629593 | High Sign | HFTD Tier 3 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006153 | 400629607 | High Sign | HFTD Tier 2 | Distribution | 2003-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006154 | 400629802 | High Sign | HFTD Tier 2 | Distribution | 2008-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006155 | 400629839 | High Sign | HFTD Tier 2 | Distribution | 2006-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006156 | 400630006 | High Sign | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006157 | 400630061 | High Sign | HFTD Tier 2 | Distribution | 2002-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006158 | 400630174 | Guy | HFTD Tier 2 | Distribution | 2006-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006159 | 400630315 | High Sign | HFTD Tier 2 | Distribution | 2003-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006160 | 400630409 | High Sign | HFTD Tier 3 | Distribution | 2006-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006161 | 400630676 | Molding | HFTD Tier 2 | Distribution | 2006-05-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006162 | 400630742 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006163 | 400631100 | High Sign | HFTD Tier 2 | Distribution | 2007-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006164 | 400631166 | Insulator | HFTD Tier 2 | Distribution | 2001-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006165 | 400631232 | High Sign | HFTD Tier 2 | Distribution | 2002-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006166 | 400631333 | High Sign | HFTD Tier 2 | Distribution | 2003-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006167 | 400631350 | High Sign | HFTD Tier 2 | Distribution | 2007-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006168 | 400631405 | Guy | HFTD Tier 3 | Distribution | 2003-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006169 | 400631471 | High Sign | HFTD Tier 2 | Distribution | 2006-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006170 | 400631803 | Molding | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006171 | 400631804 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-05-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006172 | 400632229 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-11-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006173 | 400632251 | High Sign | HFTD Tier 2 | Distribution | 2008-07-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006174 | 400632325 | Molding | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006175 | 400632327 | Insulator | HFTD Tier 2 | Distribution | 2006-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006176 | 400632394 | Molding | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006177 | 400632469 | High Sign | HFTD Tier 2 | Distribution | 2002-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006178 | 400632537 | Guy | HFTD Tier 3 | Distribution | 2005-11-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006179 | 400632542 | High Sign | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006180 | 400632593 | Guy | HFTD Tier 3 | Distribution | 2002-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006181 | 400632680 | Molding | HFTD Tier 3 | Distribution | 2006-09-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006182 | 400632711 | High Sign | HFTD Tier 3 | Distribution | 2006-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006183 | 400633095 | Molding | HFTD Tier 3 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006184 | 400633122 | Molding | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006185 | 400633125 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006186 | 400633128 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-08-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006187 | 400633207 | High Sign | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006188 | 400633347 | Molding | HFTD Tier 3 | Distribution | 2005-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006189 | 400633357 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-11-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006190 | 400633404 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006191 | 400633416 | Molding | HFTD Tier 3 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006192 | 400633462 | Guy | HFTD Tier 3 | Distribution | 2002-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006193 | 400633519 | Cable/Conductor | HFTD Tier 3 | Distribution | 2005-11-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006194 | 400633539 | Molding | HFTD Tier 2 | Distribution | 2007-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006195 | 400633547 | Guy | HFTD Tier 2 | Distribution | 2007-09-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006196 | 400633588 | High Sign | HFTD Tier 2 | Distribution | 2001-09-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006197 | 400633591 | Molding | HFTD Tier 2 | Distribution | 2007-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006198 | 400633607 | High Sign | HFTD Tier 3 | Distribution | 2006-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006199 | 400633865 | Molding | HFTD Tier 2 | Distribution | 2007-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006200 | 400633887 | High Sign | HFTD Tier 3 | Distribution | 2007-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006201 | 400633999 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006202 | 400634351 | Molding | HFTD Tier 2 | Distribution | 2006-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006203 | 400634475 | Guy | HFTD Tier 3 | Distribution | 2007-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006204 | 400634530 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006205 | 400634638 | High Sign | HFTD Tier 2 | Distribution | 2003-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006206 | 400634648 | High Sign | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006207 | 400634665 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006208 | 400634694 | High Sign | HFTD Tier 3 | Distribution | 2007-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006209 | 400634716 | High Sign | HFTD Tier 3 | Distribution | 2007-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006210 | 400634857 | High Sign | HFTD Tier 3 | Distribution | 2005-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006211 | 400635081 | Molding | HFTD Tier 2 | Distribution | 2006-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006212 | 400635183 | Molding | HFTD Tier 2 | Distribution | 2007-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006213 | 400635256 | High Sign | HFTD Tier 3 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006214 | 400635261 | High Sign | HFTD Tier 3 | Distribution | 2005-12-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006215 | 400635523 | Molding | HFTD Tier 3 | Distribution | 2003-11-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006216 | 400635543 | High Sign | HFTD Tier 2 | Distribution | 2006-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006217 | 400635676 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006218 | 400635780 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006219 | 400635785 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006220 | 400635789 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006221 | 400635852 | High Sign | HFTD Tier 2 | Distribution | 2007-11-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006222 | 400635929 | High Sign | HFTD Tier 3 | Distribution | 2006-10-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006223 | 400635934 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006224 | 400636123 | Molding | HFTD Tier 3 | Distribution | 2006-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006225 | 400636181 | High Sign | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006226 | 400636218 | High Sign | HFTD Tier 3 | Distribution | 2006-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006227 | 400636243 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006228 | 400636257 | High Sign | HFTD Tier 2 | Distribution | 2006-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006229 | 400636333 | Guy | HFTD Tier 2 | Distribution | 2007-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006230 | 400636340 | High Sign | HFTD Tier 3 | Distribution | 2006-09-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006231 | 400636361 | High Sign | HFTD Tier 2 | Distribution | 2006-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006232 | 400636406 | High Sign | HFTD Tier 2 | Distribution | 2008-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006233 | 400636587 | Riser/Conduit | HFTD Tier 3 | Distribution | 2002-03-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006234 | 400636683 | Molding | HFTD Tier 3 | Distribution | 2007-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006235 | 400636743 | Molding | HFTD Tier 2 | Distribution | 2007-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006236 | 400636782 | Guy | HFTD Tier 3 | Distribution | 2002-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006237 | 400636830 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006238 | 400636862 | High Sign | HFTD Tier 2 | Distribution | 2006-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006239 | 400636979 | Hardware/Framing | HFTD Tier 2 | Distribution | 2002-02-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006240 | 400636996 | Molding | HFTD Tier 2 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006241 | 400637050 | High Sign | HFTD Tier 3 | Distribution | 2008-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006242 | 400637200 | High Sign | HFTD Tier 2 | Distribution | 2007-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006243 | 400637265 | High Sign | HFTD Tier 3 | Distribution | 2005-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006244 | 400637385 | Guy | HFTD Tier 3 | Distribution | 2005-11-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006245 | 400637444 | High Sign | HFTD Tier 3 | Distribution | 2007-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006246 | 400637468 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006247 | 400637554 | Molding | HFTD Tier 3 | Distribution | 2005-12-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006248 | 400637566 | Molding | HFTD Tier 2 | Distribution | 2002-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006249 | 400637585 | Guy | HFTD Tier 3 | Distribution | 2007-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006250 | 400637650 | High Sign | HFTD Tier 2 | Distribution | 2002-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006251 | 400637655 | High Sign | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006252 | 400637856 | High Sign | HFTD Tier 2 | Distribution | 2007-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006253 | 400638286 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006254 | 400638409 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006255 | 400638459 | High Sign | HFTD Tier 2 | Distribution | 2007-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006256 | 400638464 | Molding | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006257 | 400638563 | High Sign | HFTD Tier 3 | Distribution | 2006-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006258 | 400638641 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006259 | 400638664 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006260 | 400638688 | High Sign | HFTD Tier 3 | Distribution | 2007-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006261 | 400639029 | High Sign | HFTD Tier 3 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006262 | 400639203 | High Sign | HFTD Tier 3 | Distribution | 2002-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006263 | 400639236 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006264 | 400639329 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006265 | 400639338 | Guy | HFTD Tier 2 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006266 | 400639413 | Molding | HFTD Tier 2 | Distribution | 2006-11-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006267 | 400639469 | Molding | HFTD Tier 3 | Distribution | 2005-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006268 | 400639630 | Molding | HFTD Tier 2 | Distribution | 2006-04-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006269 | 400639749 | High Sign | HFTD Tier 2 | Distribution | 2007-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006270 | 400639897 | High Sign | HFTD Tier 2 | Distribution | 2003-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006271 | 400639952 | High Sign | HFTD Tier 3 | Distribution | 2006-05-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006272 | 400639969 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006273 | 400640010 | High Sign | HFTD Tier 2 | Distribution | 2002-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006274 | 400640077 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006275 | 400640119 | Guy | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006276 | 400640329 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006277 | 400640363 | Molding | HFTD Tier 3 | Distribution | 2007-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006278 | 400640517 | Guy | HFTD Tier 2 | Distribution | 2003-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006279 | 400640526 | Molding | HFTD Tier 2 | Distribution | 2002-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006280 | 400640567 | High Sign | HFTD Tier 2 | Distribution | 2002-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006281 | 400640631 | High Sign | HFTD Tier 2 | Distribution | 2002-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006282 | 400640657 | High Sign | HFTD Tier 3 | Distribution | 2003-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006283 | 400640675 | High Sign | HFTD Tier 2 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006284 | 400640894 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006285 | 400640945 | High Sign | HFTD Tier 2 | Distribution | 2001-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006286 | 400640993 | Riser/Conduit | HFTD Tier 2 | Distribution | 2001-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006287 | 400641014 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006288 | 400641096 | Molding | HFTD Tier 2 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006289 | 400641234 | High Sign | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006290 | 400641283 | Molding | HFTD Tier 2 | Distribution | 2006-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006291 | 400641312 | Guy | HFTD Tier 3 | Distribution | 2007-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006292 | 400641394 | High Sign | HFTD Tier 3 | Distribution | 2006-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006293 | 400641445 | High Sign | HFTD Tier 2 | Distribution | 2007-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006294 | 400641464 | Molding | HFTD Tier 2 | Distribution | 2007-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006295 | 400641511 | High Sign | HFTD Tier 3 | Distribution | 2007-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006296 | 400641526 | Molding | HFTD Tier 2 | Distribution | 2006-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006297 | 400641537 | Molding | HFTD Tier 2 | Distribution | 2007-09-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006298 | 400641692 | Guy | HFTD Tier 3 | Distribution | 2006-10-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006299 | 400641704 | High Sign | HFTD Tier 2 | Distribution | 2003-11-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006300 | 400641725 | Molding | HFTD Tier 3 | Distribution | 2006-10-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006301 | 400641788 | Molding | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006302 | 400641855 | Cable/Conductor | HFTD Tier 2 | Distribution | 2001-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006303 | 400642025 | Hardware/Framing | HFTD Tier 2 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006304 | 400642049 | High Sign | HFTD Tier 2 | Distribution | 2008-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006305 | 400642107 | High Sign | HFTD Tier 3 | Distribution | 2007-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006306 | 400642119 | High Sign | HFTD Tier 2 | Distribution | 2007-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006307 | 400642153 | Molding | HFTD Tier 2 | Distribution | 2006-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006308 | 400642257 | High Sign | HFTD Tier 2 | Distribution | 2002-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006309 | 400642406 | Molding | HFTD Tier 3 | Distribution | 2005-12-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006310 | 400642563 | High Sign | HFTD Tier 2 | Distribution | 2003-10-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006311 | 400642669 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006312 | 400642674 | Molding | HFTD Tier 3 | Distribution | 2007-07-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006313 | 400642700 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006314 | 400642750 | High Sign | HFTD Tier 3 | Distribution | 2006-04-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006315 | 400642770 | Molding | HFTD Tier 3 | Distribution | 2002-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006316 | 400642920 | Molding | HFTD Tier 2 | Distribution | 2006-11-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006317 | 400642972 | Molding | HFTD Tier 2 | Distribution | 2006-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006318 | 400643017 | High Sign | HFTD Tier 2 | Distribution | 2005-11-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006319 | 400643255 | High Sign | HFTD Tier 3 | Distribution | 2008-07-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006320 | 400643286 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006321 | 400643334 | High Sign | HFTD Tier 3 | Distribution | 2002-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006322 | 400643345 | High Sign | HFTD Tier 2 | Distribution | 2007-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006323 | 400643380 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006324 | 400643402 | Guy | HFTD Tier 3 | Distribution | 2007-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006325 | 400643417 | High Sign | HFTD Tier 3 | Distribution | 2002-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006326 | 400643445 | High Sign | HFTD Tier 3 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006327 | 400643478 | Molding | HFTD Tier 3 | Distribution | 2005-09-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006328 | 400643497 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006329 | 400643550 | High Sign | HFTD Tier 2 | Distribution | 2006-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006330 | 400643615 | High Sign | HFTD Tier 2 | Distribution | 2007-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006331 | 400643636 | Molding | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006332 | 400643778 | High Sign | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006333 | 400643816 | Molding | HFTD Tier 2 | Distribution | 2006-06-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006334 | 400643830 | Molding | HFTD Tier 3 | Distribution | 2006-10-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006335 | 400643835 | Molding | HFTD Tier 3 | Distribution | 2006-05-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006336 | 400643913 | High Sign | HFTD Tier 3 | Distribution | 2006-10-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006337 | 400644095 | High Sign | HFTD Tier 3 | Distribution | 2005-12-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006338 | 400644098 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006339 | 400644310 | High Sign | HFTD Tier 3 | Distribution | 2002-09-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006340 | 400644668 | High Sign | HFTD Tier 2 | Distribution | 2006-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006341 | 400644683 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006342 | 400644714 | High Sign | HFTD Tier 2 | Distribution | 2003-09-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006343 | 400644774 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006344 | 400644925 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006345 | 400645050 | High Sign | HFTD Tier 2 | Distribution | 2001-12-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006346 | 400645132 | High Sign | HFTD Tier 3 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006347 | 400645158 | Molding | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006348 | 400645172 | Guy | HFTD Tier 3 | Distribution | 2006-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006349 | 400645255 | High Sign | HFTD Tier 2 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006350 | 400645278 | High Sign | HFTD Tier 3 | Distribution | 2006-09-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006351 | 400645316 | Cable/Conductor | HFTD Tier 2 | Distribution | 2007-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006352 | 400645404 | High Sign | HFTD Tier 3 | Distribution | 2007-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006353 | 400645427 | Molding | HFTD Tier 3 | Distribution | 2006-10-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006354 | 400645441 | High Sign | HFTD Tier 2 | Distribution | 2006-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006355 | 400645450 | Molding | HFTD Tier 3 | Distribution | 2007-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006356 | 400645482 | High Sign | HFTD Tier 2 | Distribution | 2005-11-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006357 | 400645668 | High Sign | HFTD Tier 2 | Distribution | 2007-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006358 | 400645670 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006359 | 400645686 | Molding | HFTD Tier 2 | Distribution | 2007-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006360 | 400645783 | High Sign | HFTD Tier 2 | Distribution | 2007-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006361 | 400645808 | High Sign | HFTD Tier 2 | Distribution | 2002-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006362 | 400645820 | Molding | HFTD Tier 3 | Distribution | 2007-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006363 | 400645855 | High Sign | HFTD Tier 2 | Distribution | 2007-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006364 | 400646013 | Molding | HFTD Tier 2 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006365 | 400646040 | Molding | HFTD Tier 3 | Distribution | 2006-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006366 | 400646169 | High Sign | HFTD Tier 3 | Distribution | 2003-10-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006367 | 400646254 | High Sign | HFTD Tier 3 | Distribution | 2002-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006368 | 400646264 | Molding | HFTD Tier 3 | Distribution | 2006-09-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006369 | 400646398 | Molding | HFTD Tier 3 | Distribution | 2003-12-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006370 | 400646664 | High Sign | HFTD Tier 3 | Distribution | 2006-03-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006371 | 400646704 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006372 | 400646747 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006373 | 400646779 | Molding | HFTD Tier 3 | Distribution | 2007-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006374 | 400646794 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006375 | 400646798 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006376 | 400646849 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006377 | 400647069 | High Sign | HFTD Tier 3 | Distribution | 2003-10-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006378 | 400647070 | Molding | HFTD Tier 2 | Distribution | 2006-10-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006379 | 400647101 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006380 | 400647156 | Molding | HFTD Tier 3 | Distribution | 2003-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006381 | 400647215 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006382 | 400647256 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-08-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006383 | 400647272 | Molding | HFTD Tier 2 | Distribution | 2007-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006384 | 400647485 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006385 | 400647758 | Molding | HFTD Tier 3 | Distribution | 2006-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006386 | 400647786 | Molding | HFTD Tier 3 | Distribution | 2008-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006387 | 400647799 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006388 | 400647934 | High Sign | HFTD Tier 3 | Distribution | 2006-08-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006389 | 400648077 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006390 | 400648078 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006391 | 400648220 | Guy | HFTD Tier 2 | Distribution | 2007-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006392 | 400648239 | High Sign | HFTD Tier 2 | Distribution | 2005-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006393 | 400648374 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006394 | 400648418 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006395 | 400648455 | High Sign | HFTD Tier 3 | Distribution | 2006-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006396 | 400648658 | Molding | HFTD Tier 3 | Distribution | 2006-08-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006397 | 400648711 | Guy | HFTD Tier 3 | Distribution | 2007-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006398 | 400648796 | Molding | HFTD Tier 2 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006399 | 400648821 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006400 | 400648853 | High Sign | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006401 | 400649065 | Molding | HFTD Tier 2 | Distribution | 2006-05-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006402 | 400649186 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006403 | 400649191 | High Sign | HFTD Tier 3 | Distribution | 2007-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006404 | 400649195 | High Sign | HFTD Tier 2 | Distribution | 2007-10-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006405 | 400649219 | High Sign | HFTD Tier 2 | Distribution | 2007-10-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006406 | 400649241 | High Sign | HFTD Tier 2 | Distribution | 2007-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006407 | 400649381 | Hardware/Framing | HFTD Tier 3 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006408 | 400649445 | Ground | HFTD Tier 2 | Distribution | 2002-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006409 | 400649451 | High Sign | HFTD Tier 2 | Distribution | 2007-11-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006410 | 400649542 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006411 | 400649561 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-09-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006412 | 400649563 | High Sign | HFTD Tier 2 | Distribution | 2006-06-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006413 | 400649618 | Molding | HFTD Tier 3 | Distribution | 2005-12-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006414 | 400649635 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006415 | 400649656 | Molding | HFTD Tier 3 | Distribution | 2006-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006416 | 400649773 | High Sign | HFTD Tier 2 | Distribution | 2003-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006417 | 400650020 | High Sign | HFTD Tier 2 | Distribution | 2003-10-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006418 | 400650141 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006419 | 400650374 | Cable/Conductor | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006420 | 400650471 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006421 | 400650476 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006422 | 400650577 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006423 | 400650588 | High Sign | HFTD Tier 2 | Distribution | 2007-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006424 | 400650605 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006425 | 400650726 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006426 | 400650913 | High Sign | HFTD Tier 3 | Distribution | 2006-03-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006427 | 400651045 | High Sign | HFTD Tier 2 | Distribution | 2003-09-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006428 | 400651064 | Molding | HFTD Tier 2 | Distribution | 2007-09-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006429 | 400651136 | Molding | HFTD Tier 2 | Distribution | 2003-11-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006430 | 400651218 | Molding | HFTD Tier 3 | Distribution | 2001-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006431 | 400651222 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006432 | 400651440 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006433 | 400651493 | High Sign | HFTD Tier 3 | Distribution | 2008-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006434 | 400651564 | Guy | HFTD Tier 3 | Distribution | 2006-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006435 | 400651598 | High Sign | HFTD Tier 2 | Distribution | 2006-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006436 | 400651850 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006437 | 400651989 | Molding | HFTD Tier 3 | Distribution | 2006-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006438 | 400652078 | High Sign | HFTD Tier 2 | Distribution | 2007-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006439 | 400652090 | Molding | HFTD Tier 2 | Distribution | 2007-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006440 | 400652330 | Molding | HFTD Tier 3 | Distribution | 2003-12-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006441 | 400652447 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006442 | 400652475 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006443 | 400652482 | High Sign | HFTD Tier 2 | Distribution | 2007-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006444 | 400652687 | Molding | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006445 | 400652709 | High Sign | HFTD Tier 2 | Distribution | 2005-11-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006446 | 400652718 | High Sign | HFTD Tier 3 | Distribution | 2006-10-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006447 | 400652890 | High Sign | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006448 | 400652924 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006449 | 400652944 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006450 | 400652990 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006451 | 400653096 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006452 | 400653169 | Hardware/Framing | HFTD Tier 3 | Distribution | 2003-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006453 | 400653194 | High Sign | HFTD Tier 2 | Distribution | 2006-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006454 | 400653240 | Molding | HFTD Tier 3 | Distribution | 2006-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006455 | 400653272 | Guy | HFTD Tier 3 | Distribution | 2007-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006456 | 400653332 | High Sign | HFTD Tier 2 | Distribution | 2003-11-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006457 | 400653368 | High Sign | HFTD Tier 3 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006458 | 400653554 | High Sign | HFTD Tier 2 | Distribution | 2007-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006459 | 400653595 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006460 | 400653706 | Molding | HFTD Tier 2 | Distribution | 2008-07-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006461 | 400653717 | Molding | HFTD Tier 3 | Distribution | 2005-11-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006462 | 400653747 | High Sign | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006463 | 400653750 | High Sign | HFTD Tier 3 | Distribution | 2002-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006464 | 400653854 | High Sign | HFTD Tier 2 | Distribution | 2007-01-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006465 | 400653962 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006466 | 400654025 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006467 | 400654059 | High Sign | HFTD Tier 3 | Distribution | 2002-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006468 | 400654319 | High Sign | HFTD Tier 3 | Distribution | 2001-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006469 | 400654461 | Molding | HFTD Tier 3 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006470 | 400654470 | Molding | HFTD Tier 3 | Distribution | 2006-10-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006471 | 400654472 | Molding | HFTD Tier 2 | Distribution | 2003-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006472 | 400654769 | Molding | HFTD Tier 3 | Distribution | 2001-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006473 | 400654788 | High Sign | HFTD Tier 3 | Distribution | 2006-09-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006474 | 400654882 | High Sign | HFTD Tier 3 | Distribution | 2005-10-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006475 | 400655093 | Molding | HFTD Tier 2 | Distribution | 2002-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006476 | 400655164 | Molding | HFTD Tier 3 | Distribution | 2005-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006477 | 400655294 | High Sign | HFTD Tier 3 | Distribution | 2006-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006478 | 400655349 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006479 | 400655367 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006480 | 400655370 | Molding | HFTD Tier 3 | Distribution | 2005-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006481 | 400655458 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006482 | 400655553 | Molding | HFTD Tier 3 | Distribution | 2003-12-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006483 | 400655607 | Molding | HFTD Tier 3 | Distribution | 2006-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006484 | 400655624 | Molding | HFTD Tier 3 | Distribution | 2001-11-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006485 | 400655625 | Molding | HFTD Tier 2 | Distribution | 2006-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006486 | 400655649 | High Sign | HFTD Tier 2 | Distribution | 2000-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006487 | 400655791 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006488 | 400655870 | Molding | HFTD Tier 3 | Distribution | 2007-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006489 | 400655923 | Molding | HFTD Tier 2 | Distribution | 2003-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006490 | 400655930 | High Sign | HFTD Tier 3 | Distribution | 2007-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006491 | 400656041 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006492 | 400656087 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006493 | 400656157 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006494 | 400656295 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006495 | 400656355 | Molding | HFTD Tier 3 | Distribution | 2003-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006496 | 400656359 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-08-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006497 | 400656388 | Guy | HFTD Tier 3 | Distribution | 2005-12-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006498 | 400656395 | Hardware/Framing | HFTD Tier 3 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006499 | 400656564 | Molding | HFTD Tier 2 | Distribution | 2003-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006500 | 400656586 | High Sign | HFTD Tier 3 | Distribution | 2001-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006501 | 400656688 | High Sign | HFTD Tier 3 | Distribution | 2007-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006502 | 400656798 | Insulator | HFTD Tier 2 | Distribution | 2002-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006503 | 400656811 | Molding | HFTD Tier 2 | Distribution | 2003-09-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006504 | 400656843 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-10-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006505 | 400656891 | High Sign | HFTD Tier 2 | Distribution | 2007-10-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006506 | 400657111 | High Sign | HFTD Tier 3 | Distribution | 2002-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006507 | 400657133 | Riser/Conduit | HFTD Tier 3 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006508 | 400657170 | Molding | HFTD Tier 2 | Distribution | 2007-10-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006509 | 400657186 | Insulator | HFTD Tier 2 | Distribution | 2006-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006510 | 400657248 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006511 | 400657463 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2003-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006512 | 400657478 | High Sign | HFTD Tier 3 | Distribution | 2002-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006513 | 400657706 | Molding | HFTD Tier 3 | Distribution | 2001-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006514 | 400657778 | Riser/Conduit | HFTD Tier 2 | Distribution | 2006-01-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006515 | 400657865 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006516 | 400657871 | Molding | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006517 | 400657948 | Molding | HFTD Tier 3 | Distribution | 2001-11-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006518 | 400658188 | High Sign | HFTD Tier 2 | Distribution | 2007-09-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006519 | 400658329 | High Sign | HFTD Tier 2 | Distribution | 2007-10-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006520 | 400658357 | High Sign | HFTD Tier 3 | Distribution | 2006-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006521 | 400658361 | Molding | HFTD Tier 3 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006522 | 400658363 | High Sign | HFTD Tier 2 | Distribution | 2006-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006523 | 400658514 | High Sign | HFTD Tier 2 | Distribution | 2002-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006524 | 400658694 | High Sign | HFTD Tier 3 | Distribution | 2006-10-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006525 | 400658811 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006526 | 400658894 | Cable/Conductor | HFTD Tier 2 | Distribution | 2002-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006527 | 400658962 | High Sign | HFTD Tier 3 | Distribution | 2006-10-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006528 | 400658963 | Guy | HFTD Tier 3 | Distribution | 2006-10-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006529 | 400659260 | High Sign | HFTD Tier 3 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006530 | 400659310 | High Sign | HFTD Tier 3 | Distribution | 2002-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006531 | 400659397 | Guy | HFTD Tier 3 | Distribution | 2006-08-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006532 | 400659495 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006533 | 400659550 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006534 | 400659615 | Molding | HFTD Tier 3 | Distribution | 2001-12-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006535 | 400659642 | Molding | HFTD Tier 2 | Distribution | 2001-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006536 | 400659809 | Guy | HFTD Tier 3 | Distribution | 2006-10-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006537 | 400659943 | Molding | HFTD Tier 2 | Distribution | 2007-10-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006538 | 400660055 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006539 | 400660174 | Molding | HFTD Tier 2 | Distribution | 2002-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006540 | 400660193 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006541 | 400660247 | High Sign | HFTD Tier 2 | Distribution | 2006-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006542 | 400660361 | High Sign | HFTD Tier 3 | Distribution | 2006-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006543 | 400660433 | Molding | HFTD Tier 3 | Distribution | 2006-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006544 | 400660454 | Hardware/Framing | HFTD Tier 3 | Distribution | 2003-09-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006545 | 400660762 | Molding | HFTD Tier 3 | Distribution | 2007-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006546 | 400660995 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006547 | 400661089 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006548 | 400661268 | Molding | HFTD Tier 3 | Distribution | 2007-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006549 | 400661321 | Molding | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006550 | 400661324 | Molding | HFTD Tier 2 | Distribution | 2006-08-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006551 | 400661342 | Molding | HFTD Tier 2 | Distribution | 2006-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006552 | 400661350 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-05-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006553 | 400661503 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-08-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006554 | 400661533 | High Sign | HFTD Tier 3 | Distribution | 2005-12-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006555 | 400661649 | High Sign | HFTD Tier 2 | Distribution | 2003-11-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006556 | 400661662 | High Sign | HFTD Tier 2 | Distribution | 2002-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006557 | 400661690 | High Sign | HFTD Tier 3 | Distribution | 2001-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006558 | 400661726 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006559 | 400661761 | Insulator | HFTD Tier 3 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006560 | 400661851 | High Sign | HFTD Tier 2 | Distribution | 2002-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006561 | 400661921 | High Sign | HFTD Tier 3 | Distribution | 2007-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006562 | 400662071 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006563 | 400662189 | Molding | HFTD Tier 3 | Distribution | 2008-07-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006564 | 400662231 | High Sign | HFTD Tier 3 | Distribution | 2002-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006565 | 400662260 | High Sign | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006566 | 400662352 | High Sign | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006567 | 400662410 | Insulator | HFTD Tier 2 | Distribution | 2006-09-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006568 | 400662419 | Molding | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006569 | 400662437 | Molding | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006570 | 400662719 | High Sign | HFTD Tier 3 | Distribution | 2001-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006571 | 400662889 | Molding | HFTD Tier 3 | Distribution | 2007-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006572 | 400662967 | High Sign | HFTD Tier 2 | Distribution | 2006-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006573 | 400663074 | Molding | HFTD Tier 2 | Distribution | 2005-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006574 | 400663283 | Riser/Conduit | HFTD Tier 3 | Distribution | 2006-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006575 | 400663314 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006576 | 400663321 | High Sign | HFTD Tier 2 | Distribution | 2006-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006577 | 400663341 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006578 | 400663408 | Molding | HFTD Tier 2 | Distribution | 2006-11-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006579 | 400663522 | High Sign | HFTD Tier 2 | Distribution | 2006-09-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006580 | 400663535 | High Sign | HFTD Tier 2 | Distribution | 2003-09-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006581 | 400663557 | High Sign | HFTD Tier 2 | Distribution | 2007-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006582 | 400664007 | High Sign | HFTD Tier 3 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006583 | 400664052 | High Sign | HFTD Tier 3 | Distribution | 2002-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006584 | 400664095 | Molding | HFTD Tier 3 | Distribution | 2006-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006585 | 400664305 | High Sign | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006586 | 400664351 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006587 | 400664386 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006588 | 400664421 | Molding | HFTD Tier 3 | Distribution | 2005-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006589 | 400664531 | Guy | HFTD Tier 2 | Distribution | 2006-08-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006590 | 400664571 | Molding | HFTD Tier 3 | Distribution | 2007-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006591 | 400664696 | Molding | HFTD Tier 2 | Distribution | 2006-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006592 | 400664745 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006593 | 400664746 | High Sign | HFTD Tier 3 | Distribution | 2002-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006594 | 400664758 | High Sign | HFTD Tier 2 | Distribution | 2003-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006595 | 400664763 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006596 | 400664832 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006597 | 400664853 | Molding | HFTD Tier 3 | Distribution | 2007-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006598 | 400665030 | Molding | HFTD Tier 3 | Distribution | 2007-03-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006599 | 400665044 | High Sign | HFTD Tier 3 | Distribution | 2002-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006600 | 400665046 | Molding | HFTD Tier 3 | Distribution | 2007-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006601 | 400665145 | Molding | HFTD Tier 3 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006602 | 400665344 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006603 | 400665403 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006604 | 400665406 | Molding | HFTD Tier 2 | Distribution | 2005-12-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006605 | 400665468 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006606 | 400665555 | Molding | HFTD Tier 2 | Distribution | 2005-12-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006607 | 400665606 | Molding | HFTD Tier 3 | Distribution | 2007-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006608 | 400665690 | Guy | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006609 | 400665707 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006610 | 400665726 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006611 | 400665748 | Guy | HFTD Tier 2 | Distribution | 2006-10-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006612 | 400665753 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006613 | 400665778 | Molding | HFTD Tier 2 | Distribution | 2006-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006614 | 400665878 | High Sign | HFTD Tier 2 | Distribution | 2006-09-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006615 | 400666035 | High Sign | HFTD Tier 2 | Distribution | 2007-08-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006616 | 400666083 | Guy | HFTD Tier 3 | Distribution | 2007-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006617 | 400666163 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006618 | 400666214 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006619 | 400666339 | Guy | HFTD Tier 2 | Distribution | 2007-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006620 | 400666374 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006621 | 400666431 | High Sign | HFTD Tier 3 | Distribution | 2002-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006622 | 400666522 | Riser/Conduit | HFTD Tier 2 | Distribution | 2005-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006623 | 400666585 | High Sign | HFTD Tier 3 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006624 | 400666789 | High Sign | HFTD Tier 2 | Distribution | 2007-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006625 | 400666853 | High Sign | HFTD Tier 3 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006626 | 400666903 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006627 | 400666993 | High Sign | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006628 | 400667009 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006629 | 400667190 | Molding | HFTD Tier 3 | Distribution | 2006-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006630 | 400667215 | Molding | HFTD Tier 2 | Distribution | 2006-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006631 | 400667264 | High Sign | HFTD Tier 2 | Distribution | 2006-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006632 | 400667312 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006633 | 400667352 | Molding | HFTD Tier 2 | Distribution | 2002-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006634 | 400667412 | High Sign | HFTD Tier 3 | Distribution | 2007-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006635 | 400667414 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006636 | 400667522 | Molding | HFTD Tier 2 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006637 | 400667626 | Molding | HFTD Tier 3 | Distribution | 2006-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006638 | 400667731 | Guy | HFTD Tier 3 | Distribution | 2006-11-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006639 | 400667775 | Molding | HFTD Tier 2 | Distribution | 2005-12-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006640 | 400668056 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006641 | 400668204 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006642 | 400668220 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006643 | 400668245 | High Sign | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006644 | 400668306 | High Sign | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006645 | 400668330 | Molding | HFTD Tier 2 | Distribution | 2006-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006646 | 400668432 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006647 | 400668550 | Guy | HFTD Tier 3 | Distribution | 2003-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006648 | 400668574 | Molding | HFTD Tier 2 | Distribution | 2006-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006649 | 400668601 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006650 | 400669021 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006651 | 400669376 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006652 | 400669377 | Molding | HFTD Tier 2 | Distribution | 2003-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006653 | 400669514 | High Sign | HFTD Tier 2 | Distribution | 2006-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006654 | 400669573 | Cable/Conductor | HFTD Tier 2 | Distribution | 2007-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006655 | 400669592 | Molding | HFTD Tier 3 | Distribution | 2007-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006656 | 400669629 | Molding | HFTD Tier 3 | Distribution | 2003-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006657 | 400669739 | High Sign | HFTD Tier 2 | Distribution | 2007-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006658 | 400669784 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006659 | 400669796 | High Sign | HFTD Tier 2 | Distribution | 1999-09-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006660 | 400669942 | Cable/Conductor | HFTD Tier 2 | Distribution | 2002-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006661 | 400670006 | High Sign | HFTD Tier 2 | Distribution | 2007-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006662 | 400670047 | High Sign | HFTD Tier 3 | Distribution | 2002-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006663 | 400670050 | Molding | HFTD Tier 3 | Distribution | 2007-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006664 | 400670073 | High Sign | HFTD Tier 3 | Distribution | 2005-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006665 | 400670265 | High Sign | HFTD Tier 3 | Distribution | 2002-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006666 | 400670274 | Molding | HFTD Tier 3 | Distribution | 2007-03-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006667 | 400670317 | High Sign | HFTD Tier 2 | Distribution | 2002-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006668 | 400670476 | High Sign | HFTD Tier 3 | Distribution | 2006-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006669 | 400670569 | Insulator | HFTD Tier 3 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006670 | 400670576 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2007-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006671 | 400670606 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006672 | 400670626 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2007-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006673 | 400670857 | High Sign | HFTD Tier 3 | Distribution | 2006-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006674 | 400670906 | Guy | HFTD Tier 3 | Distribution | 2007-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006675 | 400670997 | Riser/Conduit | HFTD Tier 3 | Distribution | 2003-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006676 | 400671053 | Insulator | HFTD Tier 3 | Distribution | 2003-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006677 | 400671095 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006678 | 400671137 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006679 | 400671260 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006680 | 400671332 | High Sign | HFTD Tier 3 | Distribution | 2005-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006681 | 400671442 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006682 | 400671526 | High Sign | HFTD Tier 3 | Distribution | 2006-10-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006683 | 400671659 | High Sign | HFTD Tier 2 | Distribution | 2007-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006684 | 400671667 | High Sign | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006685 | 400671731 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006686 | 400671771 | High Sign | HFTD Tier 3 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006687 | 400671779 | High Sign | HFTD Tier 2 | Distribution | 2002-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006688 | 400671814 | High Sign | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006689 | 400671921 | Guy | HFTD Tier 3 | Distribution | 2007-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006690 | 400671962 | Insulator | HFTD Tier 2 | Distribution | 2006-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006691 | 400672019 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006692 | 400672054 | Molding | HFTD Tier 2 | Distribution | 2006-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006693 | 400672113 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006694 | 400672223 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006695 | 400672252 | High Sign | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006696 | 400672299 | Molding | HFTD Tier 2 | Distribution | 2008-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006697 | 400672306 | Cable/Conductor | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006698 | 400672422 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006699 | 400672441 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006700 | 400672482 | High Sign | HFTD Tier 3 | Distribution | 2003-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006701 | 400672502 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006702 | 400672648 | High Sign | HFTD Tier 2 | Distribution | 2006-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006703 | 400672970 | High Sign | HFTD Tier 3 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006704 | 400673050 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006705 | 400673071 | Molding | HFTD Tier 2 | Distribution | 2006-12-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006706 | 400673200 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006707 | 400673227 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006708 | 400673233 | High Sign | HFTD Tier 3 | Distribution | 2002-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006709 | 400673371 | Molding | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006710 | 400673468 | High Sign | HFTD Tier 3 | Distribution | 2002-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006711 | 400673539 | High Sign | HFTD Tier 2 | Distribution | 2002-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006712 | 400673590 | High Sign | HFTD Tier 3 | Distribution | 2006-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006713 | 400673599 | High Sign | HFTD Tier 2 | Distribution | 2007-01-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006714 | 400673728 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006715 | 400673982 | High Sign | HFTD Tier 3 | Distribution | 2006-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006716 | 400674025 | High Sign | HFTD Tier 2 | Distribution | 2005-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006717 | 400674038 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-08-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006718 | 400674194 | High Sign | HFTD Tier 2 | Distribution | 2006-02-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006719 | 400674261 | High Sign | HFTD Tier 3 | Distribution | 2001-12-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006720 | 400674335 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006721 | 400674343 | Riser/Conduit | HFTD Tier 3 | Distribution | 2003-12-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006722 | 400674353 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006723 | 400674443 | Molding | HFTD Tier 3 | Distribution | 2007-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006724 | 400674592 | Molding | HFTD Tier 2 | Distribution | 2006-09-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006725 | 400674648 | High Sign | HFTD Tier 3 | Distribution | 2007-01-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006726 | 400674808 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006727 | 400674838 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006728 | 400674843 | Guy | HFTD Tier 2 | Distribution | 2006-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006729 | 400674893 | Molding | HFTD Tier 2 | Distribution | 2006-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006730 | 400674937 | High Sign | HFTD Tier 2 | Distribution | 2006-09-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006731 | 400674944 | Molding | HFTD Tier 2 | Distribution | 2006-03-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006732 | 400675062 | Molding | HFTD Tier 3 | Distribution | 2006-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006733 | 400675251 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006734 | 400675269 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006735 | 400675352 | High Sign | HFTD Tier 3 | Distribution | 2002-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006736 | 400675395 | High Sign | HFTD Tier 3 | Distribution | 2002-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006737 | 400675405 | High Sign | HFTD Tier 2 | Distribution | 2007-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006738 | 400675407 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006739 | 400675512 | Molding | HFTD Tier 3 | Distribution | 2007-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006740 | 400675695 | High Sign | HFTD Tier 2 | Distribution | 2003-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006741 | 400675788 | Guy | HFTD Tier 2 | Distribution | 2005-11-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006742 | 400675980 | High Sign | HFTD Tier 3 | Distribution | 2003-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006743 | 400676267 | High Sign | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006744 | 400676331 | Molding | HFTD Tier 3 | Distribution | 2007-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006745 | 400676470 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006746 | 400676473 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006747 | 400676486 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006748 | 400676516 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006749 | 400676544 | Molding | HFTD Tier 3 | Distribution | 2001-11-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006750 | 400676607 | Molding | HFTD Tier 2 | Distribution | 2006-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006751 | 400676619 | High Sign | HFTD Tier 3 | Distribution | 2002-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006752 | 400676654 | Cable/Conductor | HFTD Tier 3 | Distribution | 2006-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006753 | 400676656 | Guy | HFTD Tier 2 | Distribution | 2006-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006754 | 400676662 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006755 | 400676693 | Molding | HFTD Tier 2 | Distribution | 2006-03-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006756 | 400676708 | Molding | HFTD Tier 2 | Distribution | 2008-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006757 | 400676710 | High Sign | HFTD Tier 3 | Distribution | 2002-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006758 | 400676758 | Molding | HFTD Tier 3 | Distribution | 2007-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006759 | 400676815 | High Sign | HFTD Tier 3 | Distribution | 2006-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006760 | 400676817 | High Sign | HFTD Tier 2 | Distribution | 2003-11-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006761 | 400677044 | Guy | HFTD Tier 3 | Distribution | 2006-12-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006762 | 400677100 | Molding | HFTD Tier 2 | Distribution | 2006-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006763 | 400677133 | High Sign | HFTD Tier 2 | Distribution | 2006-11-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006764 | 400677205 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006765 | 400677273 | High Sign | HFTD Tier 2 | Distribution | 2006-07-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006766 | 400677314 | Molding | HFTD Tier 3 | Distribution | 2006-11-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006767 | 400677344 | High Sign | HFTD Tier 3 | Distribution | 2002-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006768 | 400677489 | Molding | HFTD Tier 2 | Distribution | 2007-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006769 | 400677522 | High Sign | HFTD Tier 3 | Distribution | 2005-12-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006770 | 400677538 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006771 | 400677752 | High Sign | HFTD Tier 2 | Distribution | 2007-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006772 | 400677867 | High Sign | HFTD Tier 3 | Distribution | 2001-10-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006773 | 400677941 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006774 | 400678022 | Molding | HFTD Tier 3 | Distribution | 2006-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006775 | 400678023 | High Sign | HFTD Tier 3 | Distribution | 2003-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006776 | 400678077 | Molding | HFTD Tier 2 | Distribution | 2006-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006777 | 400678357 | Molding | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006778 | 400678366 | Molding | HFTD Tier 3 | Distribution | 2006-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006779 | 400678383 | High Sign | HFTD Tier 3 | Distribution | 2006-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006780 | 400678432 | High Sign | HFTD Tier 2 | Distribution | 2006-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006781 | 400678535 | Cable/Conductor | HFTD Tier 3 | Distribution | 2003-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006782 | 400678766 | High Sign | HFTD Tier 3 | Distribution | 2002-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006783 | 400678929 | High Sign | HFTD Tier 2 | Distribution | 2002-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006784 | 400679011 | High Sign | HFTD Tier 2 | Distribution | 2006-07-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006785 | 400679117 | High Sign | HFTD Tier 3 | Distribution | 2002-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006786 | 400679260 | High Sign | HFTD Tier 2 | Distribution | 2003-11-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006787 | 400679505 | High Sign | HFTD Tier 2 | Distribution | 2002-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006788 | 400679729 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006789 | 400679768 | Molding | HFTD Tier 3 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006790 | 400680010 | Molding | HFTD Tier 3 | Distribution | 2002-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006791 | 400680063 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006792 | 400680253 | Molding | HFTD Tier 3 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006793 | 400680256 | High Sign | HFTD Tier 3 | Distribution | 2005-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006794 | 400680294 | Guy | HFTD Tier 3 | Distribution | 2006-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006795 | 400680464 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-11-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006796 | 400680932 | High Sign | HFTD Tier 3 | Distribution | 2006-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006797 | 400681014 | Molding | HFTD Tier 3 | Distribution | 2006-08-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006798 | 400681033 | Guy | HFTD Tier 3 | Distribution | 2008-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006799 | 400681113 | High Sign | HFTD Tier 2 | Distribution | 2006-12-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006800 | 400681204 | High Sign | HFTD Tier 3 | Distribution | 2006-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006801 | 400681254 | High Sign | HFTD Tier 2 | Distribution | 2006-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006802 | 400681308 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006803 | 400681363 | Riser/Conduit | HFTD Tier 3 | Distribution | 2003-11-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006804 | 400681534 | High Sign | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006805 | 400681553 | Hardware/Framing | HFTD Tier 2 | Distribution | 2005-12-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006806 | 400681591 | Guy | HFTD Tier 3 | Distribution | 2006-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006807 | 400681602 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006808 | 400681681 | High Sign | HFTD Tier 2 | Distribution | 2002-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006809 | 400681717 | Molding | HFTD Tier 2 | Distribution | 2002-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006810 | 400681795 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-09-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006811 | 400681858 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006812 | 400681936 | High Sign | HFTD Tier 3 | Distribution | 2006-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006813 | 400682036 | Guy | HFTD Tier 3 | Distribution | 2006-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006814 | 400682054 | Guy | HFTD Tier 3 | Distribution | 2006-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006815 | 400682136 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006816 | 400682272 | Molding | HFTD Tier 3 | Distribution | 2005-11-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006817 | 400682280 | High Sign | HFTD Tier 3 | Distribution | 2008-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006818 | 400682423 | Molding | HFTD Tier 2 | Distribution | 2007-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006819 | 400682501 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006820 | 400682503 | Molding | HFTD Tier 2 | Distribution | 2005-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006821 | 400682513 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006822 | 400682532 | Molding | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006823 | 400682726 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-10-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006824 | 400682754 | Molding | HFTD Tier 3 | Distribution | 2007-10-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006825 | 400682775 | High Sign | HFTD Tier 2 | Distribution | 2006-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006826 | 400683102 | High Sign | HFTD Tier 2 | Distribution | 2007-05-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006827 | 400683157 | Molding | HFTD Tier 2 | Distribution | 2003-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006828 | 400683253 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006829 | 400683431 | Hardware/Framing | HFTD Tier 3 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006830 | 400683528 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006831 | 400683568 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006832 | 400683597 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006833 | 400684220 | High Sign | HFTD Tier 3 | Distribution | 2003-09-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006834 | 400684258 | High Sign | HFTD Tier 3 | Distribution | 2002-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006835 | 400684259 | High Sign | HFTD Tier 3 | Distribution | 2007-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006836 | 400684498 | High Sign | HFTD Tier 3 | Distribution | 2002-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006837 | 400684657 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006838 | 400684725 | Molding | HFTD Tier 3 | Distribution | 2007-05-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006839 | 400684746 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006840 | 400684758 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006841 | 400684947 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006842 | 400685088 | High Sign | HFTD Tier 3 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006843 | 400685108 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006844 | 400685114 | High Sign | HFTD Tier 3 | Distribution | 2005-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006845 | 400685152 | High Sign | HFTD Tier 3 | Distribution | 2006-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006846 | 400685167 | Molding | HFTD Tier 3 | Distribution | 2006-10-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006847 | 400685241 | High Sign | HFTD Tier 3 | Distribution | 2006-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006848 | 400685246 | Molding | HFTD Tier 3 | Distribution | 2006-10-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006849 | 400685283 | High Sign | HFTD Tier 3 | Distribution | 2008-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006850 | 400685373 | Molding | HFTD Tier 3 | Distribution | 2007-10-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006851 | 400685484 | High Sign | HFTD Tier 3 | Distribution | 2007-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006852 | 400685570 | High Sign | HFTD Tier 3 | Distribution | 2008-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006853 | 400685781 | High Sign | HFTD Tier 2 | Distribution | 2007-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006854 | 400685830 | High Sign | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006855 | 400686040 | Molding | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006856 | 400686071 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-11-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006857 | 400686108 | Guy | HFTD Tier 3 | Distribution | 2007-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006858 | 400686326 | High Sign | HFTD Tier 2 | Distribution | 2003-03-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006859 | 400686356 | Guy | HFTD Tier 3 | Distribution | 2006-10-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006860 | 400686404 | Molding | HFTD Tier 2 | Distribution | 2006-05-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006861 | 400686432 | Molding | HFTD Tier 3 | Distribution | 2006-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006862 | 400686497 | Guy | HFTD Tier 3 | Distribution | 2006-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006863 | 400686503 | Molding | HFTD Tier 3 | Distribution | 2005-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006864 | 400686739 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006865 | 400686889 | Molding | HFTD Tier 3 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006866 | 400686941 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-10-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006867 | 400687140 | High Sign | HFTD Tier 3 | Distribution | 2001-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006868 | 400687151 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2007-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006869 | 400687296 | High Sign | HFTD Tier 2 | Distribution | 2006-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006870 | 400687407 | Molding | HFTD Tier 2 | Distribution | 2006-11-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006871 | 400687414 | Molding | HFTD Tier 3 | Distribution | 2005-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006872 | 400687449 | High Sign | HFTD Tier 2 | Distribution | 2007-06-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006873 | 400687467 | Molding | HFTD Tier 3 | Distribution | 2005-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006874 | 400687505 | High Sign | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006875 | 400687522 | High Sign | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006876 | 400687539 | Molding | HFTD Tier 3 | Distribution | 2006-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006877 | 400687549 | Molding | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006878 | 400687618 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-12-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006879 | 400687623 | Molding | HFTD Tier 2 | Distribution | 2003-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006880 | 400687773 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006881 | 400687840 | Molding | HFTD Tier 2 | Distribution | 2002-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006882 | 400688001 | High Sign | HFTD Tier 2 | Distribution | 2002-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006883 | 400688003 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006884 | 400688012 | High Sign | HFTD Tier 3 | Distribution | 2008-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006885 | 400688104 | Guy | HFTD Tier 3 | Distribution | 2006-10-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006886 | 400688129 | High Sign | HFTD Tier 3 | Distribution | 2006-09-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006887 | 400688143 | Guy | HFTD Tier 3 | Distribution | 2007-09-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006888 | 400688147 | High Sign | HFTD Tier 2 | Distribution | 2006-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006889 | 400688339 | Cable/Conductor | HFTD Tier 3 | Distribution | 2003-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006890 | 400688388 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006891 | 400688397 | High Sign | HFTD Tier 3 | Distribution | 2005-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006892 | 400688449 | Molding | HFTD Tier 3 | Distribution | 2007-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006893 | 400688583 | Molding | HFTD Tier 3 | Distribution | 2007-04-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006894 | 400688711 | High Sign | HFTD Tier 3 | Distribution | 2007-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006895 | 400688863 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006896 | 400688933 | Guy | HFTD Tier 3 | Distribution | 2006-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006897 | 400689000 | High Sign | HFTD Tier 2 | Distribution | 2006-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006898 | 400689013 | Cable/Conductor | HFTD Tier 3 | Distribution | 2001-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006899 | 400689015 | Molding | HFTD Tier 2 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006900 | 400689039 | Molding | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006901 | 400689120 | Molding | HFTD Tier 2 | Distribution | 2007-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006902 | 400689218 | High Sign | HFTD Tier 2 | Distribution | 2006-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006903 | 400689360 | Molding | HFTD Tier 2 | Distribution | 2007-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006904 | 400689388 | High Sign | HFTD Tier 2 | Distribution | 2001-09-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006905 | 400689540 | High Sign | HFTD Tier 2 | Distribution | 2007-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006906 | 400689610 | Molding | HFTD Tier 3 | Distribution | 2006-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006907 | 400689702 | Molding | HFTD Tier 2 | Distribution | 2001-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006908 | 400689767 | Molding | HFTD Tier 3 | Distribution | 2006-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006909 | 400689810 | High Sign | HFTD Tier 2 | Distribution | 2003-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006910 | 400689829 | Guy | HFTD Tier 3 | Distribution | 2002-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006911 | 400689932 | Cable/Conductor | HFTD Tier 3 | Distribution | 2003-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006912 | 400690052 | Molding | HFTD Tier 2 | Distribution | 2001-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006913 | 400690069 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006914 | 400690117 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006915 | 400690143 | High Sign | HFTD Tier 2 | Distribution | 2003-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006916 | 400690172 | Molding | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006917 | 400690200 | High Sign | HFTD Tier 3 | Distribution | 2007-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006918 | 400690277 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006919 | 400690357 | High Sign | HFTD Tier 3 | Distribution | 2007-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006920 | 400690554 | High Sign | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006921 | 400690579 | High Sign | HFTD Tier 2 | Distribution | 2006-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006922 | 400690929 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006923 | 400690945 | High Sign | HFTD Tier 3 | Distribution | 2006-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006924 | 400691092 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006925 | 400691160 | High Sign | HFTD Tier 3 | Distribution | 2002-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006926 | 400691294 | Molding | HFTD Tier 2 | Distribution | 2002-02-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006927 | 400691350 | High Sign | HFTD Tier 3 | Distribution | 2002-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006928 | 400691366 | Molding | HFTD Tier 2 | Distribution | 2007-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006929 | 400691423 | High Sign | HFTD Tier 2 | Distribution | 2006-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006930 | 400691444 | High Sign | HFTD Tier 2 | Distribution | 2006-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006931 | 400691629 | High Sign | HFTD Tier 2 | Distribution | 2003-11-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006932 | 400691685 | High Sign | HFTD Tier 3 | Distribution | 2001-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006933 | 400691711 | Molding | HFTD Tier 3 | Distribution | 2002-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006934 | 400691730 | High Sign | HFTD Tier 3 | Distribution | 2002-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006935 | 400691887 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006936 | 400692102 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006937 | 400692110 | High Sign | HFTD Tier 3 | Distribution | 2007-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006938 | 400692204 | Molding | HFTD Tier 2 | Distribution | 2006-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006939 | 400692222 | High Sign | HFTD Tier 3 | Distribution | 2006-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006940 | 400692264 | High Sign | HFTD Tier 3 | Distribution | 2006-09-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006941 | 400692269 | Molding | HFTD Tier 3 | Distribution | 2006-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006942 | 400692492 | Hardware/Framing | HFTD Tier 3 | Distribution | 2001-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006943 | 400692557 | High Sign | HFTD Tier 3 | Distribution | 2006-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006944 | 400692841 | High Sign | HFTD Tier 2 | Distribution | 2003-11-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006945 | 400692913 | Molding | HFTD Tier 2 | Distribution | 2002-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006946 | 400692961 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006947 | 400693128 | High Sign | HFTD Tier 3 | Distribution | 2002-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006948 | 400693270 | High Sign | HFTD Tier 2 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006949 | 400693279 | High Sign | HFTD Tier 3 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006950 | 400693371 | High Sign | HFTD Tier 2 | Distribution | 2007-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006951 | 400693502 | Guy | HFTD Tier 3 | Distribution | 2007-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006952 | 400693528 | High Sign | HFTD Tier 3 | Distribution | 2007-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006953 | 400693546 | Molding | HFTD Tier 2 | Distribution | 2001-11-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006954 | 400693636 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006955 | 400693650 | High Sign | HFTD Tier 2 | Distribution | 2006-10-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006956 | 400693678 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006957 | 400693716 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006958 | 400693722 | Molding | HFTD Tier 3 | Distribution | 2006-10-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006959 | 400693724 | Molding | HFTD Tier 2 | Distribution | 2006-07-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006960 | 400693932 | High Sign | HFTD Tier 2 | Distribution | 2001-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006961 | 400693977 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006962 | 400694032 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006963 | 400694241 | High Sign | HFTD Tier 3 | Distribution | 2003-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006964 | 400694326 | High Sign | HFTD Tier 3 | Distribution | 2006-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006965 | 400694511 | Molding | HFTD Tier 2 | Distribution | 2003-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006966 | 400694575 | Molding | HFTD Tier 2 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006967 | 400694589 | Molding | HFTD Tier 2 | Distribution | 2002-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006968 | 400694627 | Molding | HFTD Tier 3 | Distribution | 2007-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006969 | 400694745 | Riser/Conduit | HFTD Tier 2 | Distribution | 2003-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006970 | 400694751 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006971 | 400694989 | High Sign | HFTD Tier 2 | Distribution | 2006-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006972 | 400695088 | Molding | HFTD Tier 2 | Distribution | 2006-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006973 | 400695163 | High Sign | HFTD Tier 3 | Distribution | 2007-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006974 | 400695504 | High Sign | HFTD Tier 3 | Distribution | 2006-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006975 | 400695523 | High Sign | HFTD Tier 3 | Distribution | 2007-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006976 | 400695595 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006977 | 400695759 | High Sign | HFTD Tier 2 | Distribution | 2003-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006978 | 400695774 | High Sign | HFTD Tier 3 | Distribution | 2007-03-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006979 | 400695821 | Molding | HFTD Tier 3 | Distribution | 2005-11-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006980 | 400695875 | Molding | HFTD Tier 3 | Distribution | 2006-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006981 | 400695998 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006982 | 400696161 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006983 | 400696297 | High Sign | HFTD Tier 3 | Distribution | 2007-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006984 | 400696331 | High Sign | HFTD Tier 3 | Distribution | 2007-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006985 | 400696440 | High Sign | HFTD Tier 3 | Distribution | 2006-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006986 | 400696503 | Molding | HFTD Tier 2 | Distribution | 2005-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006987 | 400696521 | Molding | HFTD Tier 3 | Distribution | 2006-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006988 | 400696679 | Vis Strips | HFTD Tier 3 | Distribution | 2008-04-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006989 | 400696730 | Molding | HFTD Tier 2 | Distribution | 2002-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006990 | 400696748 | High Sign | HFTD Tier 2 | Distribution | 2007-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006991 | 400696752 | Molding | HFTD Tier 3 | Distribution | 2005-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006992 | 400697166 | Molding | HFTD Tier 2 | Distribution | 2006-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006993 | 400697231 | Guy | HFTD Tier 3 | Distribution | 2006-10-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006994 | 400697321 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006995 | 400697357 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006996 | 400697363 | High Sign | HFTD Tier 3 | Distribution | 2006-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006997 | 400697560 | High Sign | HFTD Tier 3 | Distribution | 2006-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006998 | 400697620 | High Sign | HFTD Tier 3 | Distribution | 2006-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130006999 | 400697685 | High Sign | HFTD Tier 3 | Distribution | 2006-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007000 | 400697767 | High Sign | HFTD Tier 2 | Distribution | 2003-09-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007001 | 400697916 | Hardware/Framing | HFTD Tier 2 | Distribution | 2002-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007002 | 400697972 | High Sign | HFTD Tier 3 | Distribution | 2006-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007003 | 400698434 | Molding | HFTD Tier 2 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007004 | 400698474 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007005 | 400698490 | Molding | HFTD Tier 2 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007006 | 400698509 | Molding | HFTD Tier 3 | Distribution | 2007-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007007 | 400698531 | Molding | HFTD Tier 3 | Distribution | 2005-11-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007008 | 400698538 | High Sign | HFTD Tier 3 | Distribution | 2001-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007009 | 400698803 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007010 | 400698968 | High Sign | HFTD Tier 2 | Distribution | 2002-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007011 | 400698973 | High Sign | HFTD Tier 2 | Distribution | 2006-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007012 | 400699061 | Molding | HFTD Tier 3 | Distribution | 2001-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007013 | 400699064 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007014 | 400699090 | High Sign | HFTD Tier 3 | Distribution | 2003-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007015 | 400699182 | High Sign | HFTD Tier 3 | Distribution | 2001-07-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007016 | 400699248 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007017 | 400699274 | Molding | HFTD Tier 2 | Distribution | 2003-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007018 | 400699351 | High Sign | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007019 | 400699407 | Molding | HFTD Tier 3 | Distribution | 2001-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007020 | 400699645 | Hardware/Framing | HFTD Tier 3 | Distribution | 2003-11-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007021 | 400699769 | Molding | HFTD Tier 3 | Distribution | 2006-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007022 | 400699881 | Molding | HFTD Tier 3 | Distribution | 2001-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007023 | 400699921 | High Sign | HFTD Tier 3 | Distribution | 2006-03-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007024 | 400699960 | Molding | HFTD Tier 2 | Distribution | 2006-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007025 | 400700116 | High Sign | HFTD Tier 3 | Distribution | 2006-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007026 | 400700199 | High Sign | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007027 | 400700206 | Insulator | HFTD Tier 2 | Distribution | 2002-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007028 | 400700480 | Guy | HFTD Tier 3 | Distribution | 2007-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007029 | 400700545 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-08-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007030 | 400700847 | Molding | HFTD Tier 3 | Distribution | 2006-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007031 | 400700852 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007032 | 400700946 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007033 | 400700951 | Molding | HFTD Tier 3 | Distribution | 2003-11-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007034 | 400701085 | Molding | HFTD Tier 3 | Distribution | 2002-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007035 | 400701145 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-01-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007036 | 400701156 | High Sign | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007037 | 400701229 | High Sign | HFTD Tier 3 | Distribution | 2006-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007038 | 400701292 | Guy | HFTD Tier 2 | Distribution | 2003-12-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007039 | 400701543 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007040 | 400701575 | Molding | HFTD Tier 2 | Distribution | 2005-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007041 | 400701900 | High Sign | HFTD Tier 3 | Distribution | 2001-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007042 | 400701920 | High Sign | HFTD Tier 2 | Distribution | 2002-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007043 | 400701988 | High Sign | HFTD Tier 3 | Distribution | 2002-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007044 | 400702143 | Guy | HFTD Tier 3 | Distribution | 2001-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007045 | 400702279 | High Sign | HFTD Tier 2 | Distribution | 2002-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007046 | 400702463 | Molding | HFTD Tier 2 | Distribution | 2006-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007047 | 400702653 | Guy | HFTD Tier 2 | Distribution | 2006-05-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007048 | 400702741 | Molding | HFTD Tier 3 | Distribution | 2005-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007049 | 400702816 | Molding | HFTD Tier 2 | Distribution | 2006-11-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007050 | 400702870 | High Sign | HFTD Tier 3 | Distribution | 2006-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007051 | 400702890 | Molding | HFTD Tier 3 | Distribution | 2006-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007052 | 400702892 | High Sign | HFTD Tier 3 | Distribution | 2006-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007053 | 400702907 | Guy | HFTD Tier 3 | Distribution | 2006-10-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007054 | 400702935 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007055 | 400702939 | High Sign | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007056 | 400702967 | Molding | HFTD Tier 2 | Distribution | 2008-02-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007057 | 400703067 | High Sign | HFTD Tier 3 | Distribution | 2007-03-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007058 | 400703370 | High Sign | HFTD Tier 2 | Distribution | 2006-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007059 | 400703600 | Molding | HFTD Tier 3 | Distribution | 2007-01-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007060 | 400703665 | High Sign | HFTD Tier 2 | Distribution | 2003-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007061 | 400703686 | Molding | HFTD Tier 3 | Distribution | 2003-11-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007062 | 400703805 | Molding | HFTD Tier 3 | Distribution | 2006-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007063 | 400703857 | High Sign | HFTD Tier 3 | Distribution | 2007-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007064 | 400703862 | High Sign | HFTD Tier 2 | Distribution | 2008-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007065 | 400703885 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007066 | 400703947 | High Sign | HFTD Tier 3 | Distribution | 2001-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007067 | 400703959 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007068 | 400703992 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007069 | 400704000 | Guy | HFTD Tier 3 | Distribution | 2005-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007070 | 400704005 | Molding | HFTD Tier 3 | Distribution | 2005-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007071 | 400704700 | Molding | HFTD Tier 3 | Distribution | 2005-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007072 | 400704755 | Molding | HFTD Tier 3 | Distribution | 2007-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007073 | 400704788 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007074 | 400704824 | High Sign | HFTD Tier 2 | Distribution | 2006-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007075 | 400704882 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007076 | 400704891 | Molding | HFTD Tier 3 | Distribution | 2001-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007077 | 400704901 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007078 | 400704987 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007079 | 400705009 | High Sign | HFTD Tier 2 | Distribution | 2002-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007080 | 400705320 | Molding | HFTD Tier 3 | Distribution | 2007-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007081 | 400705461 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007082 | 400705466 | Molding | HFTD Tier 2 | Distribution | 2003-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007083 | 400705742 | High Sign | HFTD Tier 3 | Distribution | 2001-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007084 | 400705816 | Molding | HFTD Tier 3 | Distribution | 2001-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007085 | 400705850 | Molding | HFTD Tier 2 | Distribution | 2002-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007086 | 400705865 | Molding | HFTD Tier 2 | Distribution | 2002-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007087 | 400705889 | Molding | HFTD Tier 2 | Distribution | 2002-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007088 | 400705949 | High Sign | HFTD Tier 3 | Distribution | 2006-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007089 | 400705953 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007090 | 400705956 | Guy | HFTD Tier 2 | Distribution | 2002-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007091 | 400706005 | Cable/Conductor | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007092 | 400706071 | High Sign | HFTD Tier 2 | Distribution | 2006-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007093 | 400706094 | Molding | HFTD Tier 2 | Distribution | 2007-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007094 | 400706128 | High Sign | HFTD Tier 3 | Distribution | 2006-06-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007095 | 400706139 | Riser/Conduit | HFTD Tier 2 | Distribution | 2007-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007096 | 400706258 | Guy | HFTD Tier 3 | Distribution | 2006-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007097 | 400706399 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007098 | 400706426 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007099 | 400706442 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007100 | 400706588 | Molding | HFTD Tier 3 | Distribution | 2006-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007101 | 400706710 | High Sign | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007102 | 400706760 | Molding | HFTD Tier 2 | Distribution | 2005-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007103 | 400706813 | Molding | HFTD Tier 2 | Distribution | 2003-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007104 | 400706825 | High Sign | HFTD Tier 3 | Distribution | 2005-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007105 | 400706958 | Molding | HFTD Tier 3 | Distribution | 2002-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007106 | 400707011 | Molding | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007107 | 400707068 | High Sign | HFTD Tier 3 | Distribution | 2001-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007108 | 400707077 | Guy | HFTD Tier 2 | Distribution | 2006-08-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007109 | 400707097 | Molding | HFTD Tier 2 | Distribution | 2006-12-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007110 | 400707222 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007111 | 400707238 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007112 | 400707281 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007113 | 400707460 | Molding | HFTD Tier 2 | Distribution | 2002-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007114 | 400707519 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007115 | 400707550 | Molding | HFTD Tier 2 | Distribution | 2006-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007116 | 400707658 | Molding | HFTD Tier 2 | Distribution | 2006-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007117 | 400707794 | High Sign | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007118 | 400707970 | Molding | HFTD Tier 3 | Distribution | 2006-07-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007119 | 400707971 | Molding | HFTD Tier 2 | Distribution | 2001-12-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007120 | 400708111 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007121 | 400708112 | Molding | HFTD Tier 2 | Distribution | 2006-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007122 | 400708166 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007123 | 400708239 | Guy | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007124 | 400708266 | High Sign | HFTD Tier 3 | Distribution | 2007-08-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007125 | 400708376 | Molding | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007126 | 400708382 | High Sign | HFTD Tier 3 | Distribution | 2002-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007127 | 400708494 | Molding | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007128 | 400708752 | High Sign | HFTD Tier 2 | Distribution | 2002-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007129 | 400708903 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-08-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007130 | 400709003 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007131 | 400709030 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007132 | 400709073 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007133 | 400709077 | Guy | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007134 | 400709181 | High Sign | HFTD Tier 3 | Distribution | 2005-12-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007135 | 400709448 | High Sign | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007136 | 400709501 | High Sign | HFTD Tier 2 | Distribution | 2002-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007137 | 400709565 | Hardware/Framing | HFTD Tier 2 | Distribution | 2002-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007138 | 400709597 | High Sign | HFTD Tier 3 | Distribution | 2005-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007139 | 400709652 | High Sign | HFTD Tier 3 | Distribution | 2005-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007140 | 400709728 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007141 | 400709745 | High Sign | HFTD Tier 2 | Distribution | 2002-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007142 | 400709877 | Molding | HFTD Tier 2 | Distribution | 2005-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007143 | 400710048 | High Sign | HFTD Tier 2 | Distribution | 2003-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007144 | 400710228 | High Sign | HFTD Tier 3 | Distribution | 2001-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007145 | 400710285 | Molding | HFTD Tier 2 | Distribution | 2006-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007146 | 400710348 | High Sign | HFTD Tier 2 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007147 | 400710516 | High Sign | HFTD Tier 2 | Distribution | 2002-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007148 | 400710526 | High Sign | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007149 | 400710548 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007150 | 400710594 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2001-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007151 | 400710648 | High Sign | HFTD Tier 3 | Distribution | 2006-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007152 | 400710754 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007153 | 400710781 | High Sign | HFTD Tier 2 | Distribution | 2003-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007154 | 400710913 | High Sign | HFTD Tier 2 | Distribution | 2008-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007155 | 400710927 | High Sign | HFTD Tier 3 | Distribution | 2006-10-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007156 | 400711158 | Molding | HFTD Tier 2 | Distribution | 2002-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007157 | 400711311 | High Sign | HFTD Tier 2 | Distribution | 2007-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007158 | 400711316 | High Sign | HFTD Tier 3 | Distribution | 2006-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007159 | 400711432 | High Sign | HFTD Tier 3 | Distribution | 2002-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007160 | 400711500 | Ground | HFTD Tier 3 | Distribution | 2008-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007161 | 400711629 | High Sign | HFTD Tier 3 | Distribution | 2001-12-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007162 | 400711659 | High Sign | HFTD Tier 3 | Distribution | 2002-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007163 | 400711861 | Molding | HFTD Tier 2 | Distribution | 2007-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007164 | 400711873 | Molding | HFTD Tier 2 | Distribution | 2007-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007165 | 400711965 | High Sign | HFTD Tier 3 | Distribution | 2006-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007166 | 400712170 | Molding | HFTD Tier 2 | Distribution | 2006-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007167 | 400712288 | High Sign | HFTD Tier 2 | Distribution | 2006-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007168 | 400712419 | Molding | HFTD Tier 2 | Distribution | 2002-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007169 | 400712436 | Molding | HFTD Tier 2 | Distribution | 2002-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007170 | 400712473 | High Sign | HFTD Tier 2 | Distribution | 2003-09-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007171 | 400712614 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007172 | 400712747 | High Sign | HFTD Tier 2 | Distribution | 2006-07-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007173 | 400712750 | High Sign | HFTD Tier 2 | Distribution | 2002-01-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007174 | 400712785 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-06-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007175 | 400712931 | High Sign | HFTD Tier 2 | Distribution | 2006-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007176 | 400712946 | High Sign | HFTD Tier 2 | Distribution | 2008-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007177 | 400712976 | Molding | HFTD Tier 3 | Distribution | 2001-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007178 | 400713078 | High Sign | HFTD Tier 2 | Distribution | 2007-01-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007179 | 400713233 | Molding | HFTD Tier 3 | Distribution | 2003-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007180 | 400713422 | High Sign | HFTD Tier 3 | Distribution | 2007-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007181 | 400713538 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007182 | 400713551 | High Sign | HFTD Tier 3 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007183 | 400713658 | High Sign | HFTD Tier 3 | Distribution | 2006-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007184 | 400713688 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007185 | 400713691 | Molding | HFTD Tier 2 | Distribution | 2005-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007186 | 400713927 | Molding | HFTD Tier 3 | Distribution | 2006-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007187 | 400713928 | Molding | HFTD Tier 3 | Distribution | 2006-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007188 | 400713958 | High Sign | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007189 | 400713983 | High Sign | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007190 | 400714065 | High Sign | HFTD Tier 3 | Distribution | 2007-10-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007191 | 400714130 | Molding | HFTD Tier 2 | Distribution | 2007-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007192 | 400714147 | Molding | HFTD Tier 2 | Distribution | 2005-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007193 | 400714335 | Molding | HFTD Tier 2 | Distribution | 2007-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007194 | 400714382 | High Sign | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007195 | 400714565 | Molding | HFTD Tier 2 | Distribution | 2006-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007196 | 400714567 | High Sign | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007197 | 400714856 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007198 | 400714969 | High Sign | HFTD Tier 2 | Distribution | 2006-11-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007199 | 400715139 | Molding | HFTD Tier 2 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007200 | 400715165 | Cable/Conductor | HFTD Tier 3 | Distribution | 2001-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007201 | 400715249 | Guy | HFTD Tier 3 | Distribution | 2006-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007202 | 400715257 | High Sign | HFTD Tier 3 | Distribution | 2008-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007203 | 400715344 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007204 | 400715408 | Molding | HFTD Tier 2 | Distribution | 2005-12-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007205 | 400715517 | High Sign | HFTD Tier 2 | Distribution | 2007-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007206 | 400715619 | High Sign | HFTD Tier 3 | Distribution | 2006-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007207 | 400715647 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-09-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007208 | 400715804 | High Sign | HFTD Tier 3 | Distribution | 2008-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007209 | 400716099 | High Sign | HFTD Tier 2 | Distribution | 2006-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007210 | 400716100 | High Sign | HFTD Tier 3 | Distribution | 2006-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007211 | 400716121 | High Sign | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007212 | 400716299 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007213 | 400716362 | High Sign | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007214 | 400716473 | Guy | HFTD Tier 2 | Distribution | 2006-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007215 | 400716883 | High Sign | HFTD Tier 3 | Distribution | 2007-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007216 | 400716948 | High Sign | HFTD Tier 2 | Distribution | 2006-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007217 | 400717143 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007218 | 400717173 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007219 | 400717174 | Molding | HFTD Tier 3 | Distribution | 2002-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007220 | 400717184 | High Sign | HFTD Tier 3 | Distribution | 2001-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007221 | 400717407 | High Sign | HFTD Tier 2 | Distribution | 2002-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007222 | 400717606 | High Sign | HFTD Tier 2 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007223 | 400717621 | High Sign | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007224 | 400717817 | High Sign | HFTD Tier 3 | Distribution | 2006-10-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007225 | 400718004 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007226 | 400718024 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007227 | 400718051 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007228 | 400718151 | High Sign | HFTD Tier 2 | Distribution | 2006-11-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007229 | 400718214 | Molding | HFTD Tier 3 | Distribution | 2006-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007230 | 400718334 | High Sign | HFTD Tier 3 | Distribution | 2005-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007231 | 400718344 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007232 | 400718420 | Molding | HFTD Tier 2 | Distribution | 2006-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007233 | 400718446 | Guy | HFTD Tier 3 | Distribution | 2006-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007234 | 400718575 | High Sign | HFTD Tier 2 | Distribution | 2002-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007235 | 400718595 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007236 | 400718618 | High Sign | HFTD Tier 2 | Distribution | 2006-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007237 | 400718687 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007238 | 400718700 | High Sign | HFTD Tier 3 | Distribution | 2006-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007239 | 400718927 | Molding | HFTD Tier 3 | Distribution | 2001-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007240 | 400719070 | High Sign | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007241 | 400719114 | High Sign | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007242 | 400719130 | Molding | HFTD Tier 3 | Distribution | 2002-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007243 | 400719171 | Molding | HFTD Tier 2 | Distribution | 2007-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007244 | 400719307 | High Sign | HFTD Tier 2 | Distribution | 2007-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007245 | 400719337 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007246 | 400719351 | Molding | HFTD Tier 2 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007247 | 400719364 | High Sign | HFTD Tier 2 | Distribution | 2003-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007248 | 400719390 | High Sign | HFTD Tier 2 | Distribution | 2003-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007249 | 400719392 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007250 | 400719417 | Molding | HFTD Tier 2 | Distribution | 2003-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007251 | 400719461 | High Sign | HFTD Tier 2 | Distribution | 2006-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007252 | 400719509 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007253 | 400719581 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007254 | 400719657 | Molding | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007255 | 400719674 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007256 | 400719744 | High Sign | HFTD Tier 3 | Distribution | 2002-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007257 | 400720146 | High Sign | HFTD Tier 2 | Distribution | 2002-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007258 | 400720164 | Molding | HFTD Tier 3 | Distribution | 2005-12-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007259 | 400720306 | High Sign | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007260 | 400720460 | Molding | HFTD Tier 2 | Distribution | 2007-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007261 | 400720466 | Molding | HFTD Tier 2 | Distribution | 2006-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007262 | 400720489 | Molding | HFTD Tier 2 | Distribution | 2006-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007263 | 400720552 | High Sign | HFTD Tier 2 | Distribution | 2002-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007264 | 400720617 | Molding | HFTD Tier 3 | Distribution | 2006-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007265 | 400720685 | High Sign | HFTD Tier 3 | Distribution | 2006-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007266 | 400720690 | High Sign | HFTD Tier 3 | Distribution | 2002-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007267 | 400720816 | Molding | HFTD Tier 2 | Distribution | 2006-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007268 | 400720928 | High Sign | HFTD Tier 3 | Distribution | 2001-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007269 | 400721010 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007270 | 400721071 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007271 | 400721170 | Guy | HFTD Tier 3 | Distribution | 2007-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007272 | 400721226 | Molding | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007273 | 400721265 | High Sign | HFTD Tier 2 | Distribution | 2008-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007274 | 400721335 | Molding | HFTD Tier 3 | Distribution | 2001-11-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007275 | 400721561 | High Sign | HFTD Tier 3 | Distribution | 2006-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007276 | 400721705 | High Sign | HFTD Tier 3 | Distribution | 2006-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007277 | 400721829 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007278 | 400721859 | Guy | HFTD Tier 3 | Distribution | 2007-01-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007279 | 400721959 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-08-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007280 | 400722000 | High Sign | HFTD Tier 2 | Distribution | 2005-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007281 | 400722186 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007282 | 400722226 | High Sign | HFTD Tier 2 | Distribution | 2002-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007283 | 400722552 | High Sign | HFTD Tier 3 | Distribution | 2007-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007284 | 400722594 | High Sign | HFTD Tier 2 | Distribution | 2006-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007285 | 400722632 | High Sign | HFTD Tier 2 | Distribution | 2006-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007286 | 400722641 | High Sign | HFTD Tier 2 | Distribution | 2006-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007287 | 400722656 | Cable/Conductor | HFTD Tier 3 | Distribution | 2006-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007288 | 400722697 | High Sign | HFTD Tier 3 | Distribution | 2008-02-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007289 | 400722780 | Ground | HFTD Tier 3 | Distribution | 2002-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007290 | 400722809 | High Sign | HFTD Tier 2 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007291 | 400722835 | High Sign | HFTD Tier 3 | Distribution | 2006-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007292 | 400722861 | Riser/Conduit | HFTD Tier 2 | Distribution | 2002-02-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007293 | 400722872 | High Sign | HFTD Tier 2 | Distribution | 2001-11-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007294 | 400722877 | Guy | HFTD Tier 2 | Distribution | 2002-02-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007295 | 400722912 | High Sign | HFTD Tier 3 | Distribution | 2002-02-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007296 | 400722970 | Molding | HFTD Tier 3 | Distribution | 2002-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007297 | 400723017 | Guy | HFTD Tier 3 | Distribution | 2007-01-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007298 | 400723201 | High Sign | HFTD Tier 3 | Distribution | 2006-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007299 | 400723269 | Guy | HFTD Tier 2 | Distribution | 2007-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007300 | 400723424 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007301 | 400723586 | Molding | HFTD Tier 2 | Distribution | 2006-02-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007302 | 400723613 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007303 | 400723708 | High Sign | HFTD Tier 3 | Distribution | 2002-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007304 | 400723719 | Molding | HFTD Tier 3 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007305 | 400723876 | High Sign | HFTD Tier 3 | Distribution | 2002-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007306 | 400723915 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007307 | 400723998 | Guy | HFTD Tier 3 | Distribution | 2007-01-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007308 | 400724035 | Molding | HFTD Tier 3 | Distribution | 2006-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007309 | 400724110 | High Sign | HFTD Tier 2 | Distribution | 2007-06-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007310 | 400724116 | Molding | HFTD Tier 2 | Distribution | 2006-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007311 | 400724186 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-08-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007312 | 400724265 | High Sign | HFTD Tier 3 | Distribution | 2006-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007313 | 400724402 | Molding | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007314 | 400724495 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007315 | 400724531 | High Sign | HFTD Tier 3 | Distribution | 2001-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007316 | 400724566 | Molding | HFTD Tier 2 | Distribution | 2006-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007317 | 400724709 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007318 | 400724752 | High Sign | HFTD Tier 2 | Distribution | 2002-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007319 | 400724777 | Molding | HFTD Tier 3 | Distribution | 2005-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007320 | 400724797 | High Sign | HFTD Tier 2 | Distribution | 2002-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007321 | 400724926 | Molding | HFTD Tier 3 | Distribution | 2006-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007322 | 400724993 | High Sign | HFTD Tier 3 | Distribution | 2001-12-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007323 | 400725014 | High Sign | HFTD Tier 3 | Distribution | 2002-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007324 | 400725017 | Guy | HFTD Tier 3 | Distribution | 2006-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007325 | 400725107 | High Sign | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007326 | 400725133 | High Sign | HFTD Tier 3 | Distribution | 2002-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007327 | 400725219 | Molding | HFTD Tier 2 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007328 | 400725267 | Guy | HFTD Tier 2 | Distribution | 2006-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007329 | 400725346 | Molding | HFTD Tier 3 | Distribution | 2006-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007330 | 400725349 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007331 | 400725378 | High Sign | HFTD Tier 2 | Distribution | 2007-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007332 | 400725379 | High Sign | HFTD Tier 3 | Distribution | 2007-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007333 | 400725415 | High Sign | HFTD Tier 2 | Distribution | 2002-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007334 | 400725438 | High Sign | HFTD Tier 2 | Distribution | 2002-01-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007335 | 400725508 | Hardware/Framing | HFTD Tier 3 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007336 | 400725535 | High Sign | HFTD Tier 3 | Distribution | 2007-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007337 | 400725769 | High Sign | HFTD Tier 2 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007338 | 400725899 | Molding | HFTD Tier 3 | Distribution | 2001-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007339 | 400725901 | High Sign | HFTD Tier 3 | Distribution | 2006-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007340 | 400725968 | High Sign | HFTD Tier 3 | Distribution | 2005-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007341 | 400726004 | ID Markings | HFTD Tier 2 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007342 | 400726097 | High Sign | HFTD Tier 2 | Distribution | 2002-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007343 | 400726139 | Guy | HFTD Tier 3 | Distribution | 2006-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007344 | 400726150 | High Sign | HFTD Tier 2 | Distribution | 2006-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007345 | 400726183 | High Sign | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007346 | 400726254 | Molding | HFTD Tier 3 | Distribution | 2006-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007347 | 400726327 | Molding | HFTD Tier 3 | Distribution | 2006-10-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007348 | 400726352 | Molding | HFTD Tier 3 | Distribution | 2006-10-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007349 | 400726389 | High Sign | HFTD Tier 2 | Distribution | 2006-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007350 | 400726530 | Guy | HFTD Tier 3 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007351 | 400726640 | High Sign | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007352 | 400726670 | High Sign | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007353 | 400726718 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-11-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007354 | 400726751 | Molding | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007355 | 400726801 | High Sign | HFTD Tier 3 | Distribution | 2002-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007356 | 400726844 | Molding | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007357 | 400726888 | High Sign | HFTD Tier 3 | Distribution | 2001-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007358 | 400726906 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007359 | 400726950 | Molding | HFTD Tier 2 | Distribution | 2002-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007360 | 400727105 | Molding | HFTD Tier 2 | Distribution | 2007-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007361 | 400727199 | Guy | HFTD Tier 3 | Distribution | 2006-10-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007362 | 400727227 | High Sign | HFTD Tier 3 | Distribution | 2006-05-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007363 | 400727354 | Molding | HFTD Tier 2 | Distribution | 2006-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007364 | 400727355 | Molding | HFTD Tier 2 | Distribution | 2003-09-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007365 | 400727364 | High Sign | HFTD Tier 2 | Distribution | 2002-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007366 | 400727461 | Molding | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007367 | 400727544 | High Sign | HFTD Tier 2 | Distribution | 2006-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007368 | 400727604 | High Sign | HFTD Tier 2 | Distribution | 2002-09-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007369 | 400727627 | High Sign | HFTD Tier 2 | Distribution | 2003-04-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007370 | 400727679 | Molding | HFTD Tier 2 | Distribution | 2006-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007371 | 400727710 | High Sign | HFTD Tier 3 | Distribution | 2003-07-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007372 | 400727819 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007373 | 400727922 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007374 | 400727987 | Molding | HFTD Tier 2 | Distribution | 2006-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007375 | 400727991 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007376 | 400728099 | High Sign | HFTD Tier 3 | Distribution | 2002-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007377 | 400728107 | Guy | HFTD Tier 3 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007378 | 400728115 | High Sign | HFTD Tier 2 | Distribution | 2005-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007379 | 400728203 | Guy | HFTD Tier 3 | Distribution | 2006-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007380 | 400728274 | High Sign | HFTD Tier 2 | Distribution | 2002-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007381 | 400728351 | Molding | HFTD Tier 2 | Distribution | 2006-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007382 | 400728391 | Molding | HFTD Tier 3 | Distribution | 2006-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007383 | 400728500 | Guy | HFTD Tier 3 | Distribution | 2006-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007384 | 400728642 | High Sign | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007385 | 400728653 | High Sign | HFTD Tier 2 | Distribution | 2006-12-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007386 | 400728668 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007387 | 400728761 | Molding | HFTD Tier 2 | Distribution | 2006-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007388 | 400728767 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-10-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007389 | 400728774 | Molding | HFTD Tier 2 | Distribution | 2006-09-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007390 | 400728808 | Guy | HFTD Tier 3 | Distribution | 2006-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007391 | 400729032 | High Sign | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007392 | 400729127 | High Sign | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007393 | 400729400 | High Sign | HFTD Tier 2 | Distribution | 2008-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007394 | 400729577 | Termination | HFTD Tier 3 | Distribution | 2007-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007395 | 400729692 | High Sign | HFTD Tier 2 | Distribution | 2007-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007396 | 400729716 | High Sign | HFTD Tier 2 | Distribution | 2007-05-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007397 | 400729793 | Hardware/Framing | HFTD Tier 3 | Distribution | 2001-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007398 | 400729815 | Riser/Conduit | HFTD Tier 2 | Distribution | 2006-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007399 | 400729916 | High Sign | HFTD Tier 2 | Distribution | 2006-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007400 | 400730059 | High Sign | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007401 | 400730104 | High Sign | HFTD Tier 2 | Distribution | 2002-09-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007402 | 400730180 | High Sign | HFTD Tier 3 | Distribution | 2005-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007403 | 400730336 | High Sign | HFTD Tier 3 | Distribution | 2001-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007404 | 400730363 | High Sign | HFTD Tier 3 | Distribution | 2001-04-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007405 | 400730407 | Guy | HFTD Tier 2 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007406 | 400730413 | Guy | HFTD Tier 3 | Distribution | 2007-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007407 | 400730461 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007408 | 400730577 | Termination | HFTD Tier 3 | Distribution | 2007-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007409 | 400730658 | High Sign | HFTD Tier 2 | Distribution | 2002-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007410 | 400730878 | High Sign | HFTD Tier 3 | Distribution | 2002-01-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007411 | 400730912 | High Sign | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007412 | 400730942 | Molding | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007413 | 400731044 | Guy | HFTD Tier 3 | Distribution | 2007-01-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007414 | 400731104 | High Sign | HFTD Tier 2 | Distribution | 2002-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007415 | 400731169 | Molding | HFTD Tier 3 | Distribution | 2006-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007416 | 400731321 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007417 | 400731485 | Molding | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007418 | 400731505 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007419 | 400731666 | Molding | HFTD Tier 3 | Distribution | 2007-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007420 | 400731734 | High Sign | HFTD Tier 3 | Distribution | 2001-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007421 | 400731809 | Guy | HFTD Tier 3 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007422 | 400731818 | Molding | HFTD Tier 2 | Distribution | 2006-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007423 | 400732238 | Molding | HFTD Tier 2 | Distribution | 2002-02-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007424 | 400732268 | Molding | HFTD Tier 2 | Distribution | 2002-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007425 | 400732395 | High Sign | HFTD Tier 2 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007426 | 400732404 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007427 | 400732891 | High Sign | HFTD Tier 3 | Distribution | 2002-01-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007428 | 400732946 | High Sign | HFTD Tier 2 | Distribution | 2002-04-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007429 | 400733435 | High Sign | HFTD Tier 3 | Distribution | 2007-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007430 | 400733609 | Molding | HFTD Tier 3 | Distribution | 2006-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007431 | 400733641 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007432 | 400733656 | High Sign | HFTD Tier 2 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007433 | 400733668 | Molding | HFTD Tier 2 | Distribution | 2002-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007434 | 400733734 | Guy | HFTD Tier 3 | Distribution | 2007-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007435 | 400734051 | High Sign | HFTD Tier 2 | Distribution | 2001-12-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007436 | 400734278 | High Sign | HFTD Tier 3 | Distribution | 2006-10-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007437 | 400734458 | Molding | HFTD Tier 3 | Distribution | 2003-07-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007438 | 400734494 | High Sign | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007439 | 400734570 | High Sign | HFTD Tier 3 | Distribution | 2003-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007440 | 400734576 | High Sign | HFTD Tier 3 | Distribution | 2007-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007441 | 400734578 | Molding | HFTD Tier 2 | Distribution | 2007-09-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007442 | 400734657 | High Sign | HFTD Tier 3 | Distribution | 2002-01-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007443 | 400734804 | High Sign | HFTD Tier 2 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007444 | 400734806 | High Sign | HFTD Tier 3 | Distribution | 2003-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007445 | 400734860 | High Sign | HFTD Tier 2 | Distribution | 2002-09-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007446 | 400734881 | Molding | HFTD Tier 3 | Distribution | 2003-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007447 | 400734973 | Molding | HFTD Tier 3 | Distribution | 2006-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007448 | 400735020 | Molding | HFTD Tier 3 | Distribution | 2006-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007449 | 400735035 | Riser/Conduit | HFTD Tier 3 | Distribution | 2006-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007450 | 400735056 | High Sign | HFTD Tier 2 | Distribution | 2002-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007451 | 400735098 | Molding | HFTD Tier 3 | Distribution | 2002-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007452 | 400735449 | High Sign | HFTD Tier 3 | Distribution | 2002-01-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007453 | 400735474 | High Sign | HFTD Tier 2 | Distribution | 2005-12-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007454 | 400735604 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007455 | 400735928 | Molding | HFTD Tier 3 | Distribution | 2006-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007456 | 400736013 | High Sign | HFTD Tier 3 | Distribution | 2007-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007457 | 400736030 | High Sign | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007458 | 400736137 | High Sign | HFTD Tier 3 | Distribution | 2002-01-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007459 | 400736173 | High Sign | HFTD Tier 3 | Distribution | 2001-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007460 | 400736267 | High Sign | HFTD Tier 3 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007461 | 400736288 | High Sign | HFTD Tier 3 | Distribution | 2002-01-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007462 | 400736330 | High Sign | HFTD Tier 2 | Distribution | 2003-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007463 | 400736383 | High Sign | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007464 | 400736445 | Molding | HFTD Tier 2 | Distribution | 2007-08-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007465 | 400736477 | High Sign | HFTD Tier 3 | Distribution | 2006-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007466 | 400736555 | Molding | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007467 | 400736570 | Riser/Conduit | HFTD Tier 3 | Distribution | 2005-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007468 | 400736659 | Molding | HFTD Tier 2 | Distribution | 2006-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007469 | 400736675 | Molding | HFTD Tier 2 | Distribution | 2006-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007470 | 400736733 | Molding | HFTD Tier 3 | Distribution | 2005-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007471 | 400736810 | Molding | HFTD Tier 3 | Distribution | 2006-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007472 | 400736962 | Molding | HFTD Tier 3 | Distribution | 2007-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007473 | 400736974 | Molding | HFTD Tier 2 | Distribution | 2006-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007474 | 400737037 | High Sign | HFTD Tier 2 | Distribution | 2001-12-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007475 | 400737118 | Molding | HFTD Tier 3 | Distribution | 2006-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007476 | 400737139 | Hardware/Framing | HFTD Tier 3 | Distribution | 2003-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007477 | 400737297 | Molding | HFTD Tier 2 | Distribution | 2002-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007478 | 400737318 | Molding | HFTD Tier 2 | Distribution | 2008-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007479 | 400737346 | Guy | HFTD Tier 3 | Distribution | 2007-09-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007480 | 400737384 | Molding | HFTD Tier 3 | Distribution | 2003-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007481 | 400737599 | High Sign | HFTD Tier 2 | Distribution | 2006-09-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007482 | 400737620 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007483 | 400737660 | High Sign | HFTD Tier 2 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007484 | 400737924 | Guy | HFTD Tier 2 | Distribution | 2001-09-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007485 | 400737926 | Molding | HFTD Tier 3 | Distribution | 2007-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007486 | 400737927 | High Sign | HFTD Tier 2 | Distribution | 2006-10-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007487 | 400737940 | Molding | HFTD Tier 3 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007488 | 400738130 | Cable/Conductor | HFTD Tier 3 | Distribution | 2006-10-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007489 | 400738203 | Molding | HFTD Tier 3 | Distribution | 2006-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007490 | 400738303 | High Sign | HFTD Tier 3 | Distribution | 2006-09-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007491 | 400738490 | High Sign | HFTD Tier 2 | Distribution | 2006-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007492 | 400738583 | Molding | HFTD Tier 3 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007493 | 400738631 | High Sign | HFTD Tier 3 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007494 | 400738942 | High Sign | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007495 | 400738957 | High Sign | HFTD Tier 3 | Distribution | 2005-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007496 | 400738984 | High Sign | HFTD Tier 3 | Distribution | 2006-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007497 | 400739348 | Guy | HFTD Tier 3 | Distribution | 2006-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007498 | 400739423 | High Sign | HFTD Tier 2 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007499 | 400739558 | Molding | HFTD Tier 3 | Distribution | 2005-12-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007500 | 400739572 | High Sign | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007501 | 400739653 | High Sign | HFTD Tier 2 | Distribution | 2002-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007502 | 400739714 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007503 | 400739906 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007504 | 400739997 | Molding | HFTD Tier 2 | Distribution | 2006-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007505 | 400740006 | Guy | HFTD Tier 3 | Distribution | 2007-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007506 | 400740031 | High Sign | HFTD Tier 2 | Distribution | 2006-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007507 | 400740045 | High Sign | HFTD Tier 2 | Distribution | 2006-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007508 | 400740147 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-11-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007509 | 400740185 | Molding | HFTD Tier 2 | Distribution | 2007-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007510 | 400740464 | Molding | HFTD Tier 3 | Distribution | 2006-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007511 | 400740556 | Molding | HFTD Tier 2 | Distribution | 2003-08-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007512 | 400740952 | Molding | HFTD Tier 2 | Distribution | 2006-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007513 | 400741053 | High Sign | HFTD Tier 3 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007514 | 400741133 | Hardware/Framing | HFTD Tier 2 | Distribution | 2001-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007515 | 400741216 | Guy | HFTD Tier 3 | Distribution | 2001-10-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007516 | 400741230 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007517 | 400741460 | Insulator | HFTD Tier 2 | Distribution | 2002-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007518 | 400741476 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007519 | 400741575 | High Sign | HFTD Tier 2 | Distribution | 2006-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007520 | 400741808 | High Sign | HFTD Tier 2 | Distribution | 2004-10-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007521 | 400741865 | High Sign | HFTD Tier 2 | Distribution | 2002-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007522 | 400741909 | Guy | HFTD Tier 3 | Distribution | 2005-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007523 | 400741941 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007524 | 400741997 | Guy | HFTD Tier 2 | Distribution | 2002-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007525 | 400742029 | High Sign | HFTD Tier 3 | Distribution | 2003-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007526 | 400742038 | High Sign | HFTD Tier 2 | Distribution | 2007-09-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007527 | 400742039 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007528 | 400742055 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007529 | 400742101 | Guy | HFTD Tier 3 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007530 | 400742199 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007531 | 400742364 | Insulator | HFTD Tier 3 | Distribution | 2007-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007532 | 400742510 | Molding | HFTD Tier 3 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007533 | 400742582 | Guy | HFTD Tier 3 | Distribution | 2006-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007534 | 400742606 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007535 | 400742622 | Molding | HFTD Tier 3 | Distribution | 2007-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007536 | 400742631 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007537 | 400742636 | Guy | HFTD Tier 3 | Distribution | 2007-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007538 | 400742639 | Molding | HFTD Tier 3 | Distribution | 2007-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007539 | 400742641 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007540 | 400742642 | High Sign | HFTD Tier 3 | Distribution | 2006-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007541 | 400742657 | Ground | HFTD Tier 3 | Distribution | 2007-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007542 | 400742830 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007543 | 400742868 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007544 | 400742882 | Molding | HFTD Tier 2 | Distribution | 2006-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007545 | 400742934 | High Sign | HFTD Tier 3 | Distribution | 2002-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007546 | 400742962 | Molding | HFTD Tier 3 | Distribution | 2006-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007547 | 400742964 | Molding | HFTD Tier 2 | Distribution | 2006-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007548 | 400743534 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007549 | 400743535 | Guy | HFTD Tier 3 | Distribution | 2006-10-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007550 | 400743701 | High Sign | HFTD Tier 2 | Distribution | 2002-04-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007551 | 400743709 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007552 | 400743826 | Molding | HFTD Tier 3 | Distribution | 2006-09-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007553 | 400743947 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007554 | 400743988 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007555 | 400744075 | High Sign | HFTD Tier 3 | Distribution | 2006-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007556 | 400744111 | High Sign | HFTD Tier 2 | Distribution | 2005-09-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007557 | 400744146 | Molding | HFTD Tier 3 | Distribution | 2006-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007558 | 400744263 | High Sign | HFTD Tier 2 | Distribution | 2008-02-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007559 | 400744371 | High Sign | HFTD Tier 3 | Distribution | 2005-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007560 | 400744587 | Molding | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007561 | 400744654 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007562 | 400744810 | Guy | HFTD Tier 2 | Distribution | 2007-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007563 | 400744864 | Molding | HFTD Tier 2 | Distribution | 2008-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007564 | 400745037 | High Sign | HFTD Tier 3 | Distribution | 2006-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007565 | 400745151 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007566 | 400745240 | Molding | HFTD Tier 2 | Distribution | 2006-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007567 | 400745502 | High Sign | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007568 | 400745559 | High Sign | HFTD Tier 3 | Distribution | 2006-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007569 | 400745602 | High Sign | HFTD Tier 2 | Distribution | 2002-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007570 | 400745603 | Hardware/Framing | HFTD Tier 2 | Distribution | 2002-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007571 | 400745679 | Molding | HFTD Tier 3 | Distribution | 2006-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007572 | 400745728 | Molding | HFTD Tier 3 | Distribution | 2003-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007573 | 400745747 | High Sign | HFTD Tier 3 | Distribution | 2007-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007574 | 400745784 | High Sign | HFTD Tier 3 | Distribution | 2003-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007575 | 400745907 | High Sign | HFTD Tier 3 | Distribution | 2006-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007576 | 400745986 | High Sign | HFTD Tier 3 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007577 | 400746075 | High Sign | HFTD Tier 3 | Distribution | 2005-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007578 | 400746094 | Molding | HFTD Tier 2 | Distribution | 2006-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007579 | 400746099 | High Sign | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007580 | 400746191 | Guy | HFTD Tier 2 | Distribution | 2007-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007581 | 400746275 | Guy | HFTD Tier 2 | Distribution | 2006-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007582 | 400746307 | High Sign | HFTD Tier 2 | Distribution | 2006-10-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007583 | 400746378 | High Sign | HFTD Tier 2 | Distribution | 2001-11-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007584 | 400746470 | High Sign | HFTD Tier 3 | Distribution | 2006-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007585 | 400746532 | Molding | HFTD Tier 3 | Distribution | 2006-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007586 | 400746541 | High Sign | HFTD Tier 3 | Distribution | 2006-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007587 | 400746602 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007588 | 400746619 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007589 | 400746626 | High Sign | HFTD Tier 2 | Distribution | 2002-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007590 | 400746647 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007591 | 400746765 | High Sign | HFTD Tier 2 | Distribution | 2006-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007592 | 400746873 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007593 | 400746914 | Molding | HFTD Tier 2 | Distribution | 2006-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007594 | 400746960 | High Sign | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007595 | 400747013 | High Sign | HFTD Tier 3 | Distribution | 2006-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007596 | 400747302 | High Sign | HFTD Tier 3 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007597 | 400747320 | High Sign | HFTD Tier 2 | Distribution | 2008-02-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007598 | 400747568 | High Sign | HFTD Tier 3 | Distribution | 2007-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007599 | 400747613 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007600 | 400748079 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007601 | 400748097 | High Sign | HFTD Tier 3 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007602 | 400748122 | Molding | HFTD Tier 3 | Distribution | 2001-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007603 | 400748170 | High Sign | HFTD Tier 3 | Distribution | 2006-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007604 | 400748259 | High Sign | HFTD Tier 3 | Distribution | 2002-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007605 | 400748280 | High Sign | HFTD Tier 2 | Distribution | 2005-08-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007606 | 400748541 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-02-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007607 | 400748652 | Molding | HFTD Tier 3 | Distribution | 2003-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007608 | 400748670 | High Sign | HFTD Tier 3 | Distribution | 2006-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007609 | 400748719 | Molding | HFTD Tier 3 | Distribution | 2006-12-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007610 | 400748745 | Riser/Conduit | HFTD Tier 3 | Distribution | 2006-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007611 | 400748891 | Cable/Conductor | HFTD Tier 3 | Distribution | 2003-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007612 | 400748950 | High Sign | HFTD Tier 3 | Distribution | 2006-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007613 | 400749110 | Hardware/Framing | HFTD Tier 2 | Distribution | 2002-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007614 | 400749189 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007615 | 400749317 | Molding | HFTD Tier 2 | Distribution | 2007-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007616 | 400749343 | Molding | HFTD Tier 2 | Distribution | 2007-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007617 | 400749395 | High Sign | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007618 | 400749410 | Guy | HFTD Tier 3 | Distribution | 2006-12-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007619 | 400749474 | High Sign | HFTD Tier 3 | Distribution | 2005-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007620 | 400749582 | High Sign | HFTD Tier 3 | Distribution | 2006-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007621 | 400749663 | High Sign | HFTD Tier 2 | Distribution | 2001-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007622 | 400749681 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007623 | 400749695 | High Sign | HFTD Tier 3 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007624 | 400749752 | High Sign | HFTD Tier 3 | Distribution | 2001-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007625 | 400749772 | High Sign | HFTD Tier 3 | Distribution | 2001-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007626 | 400749805 | High Sign | HFTD Tier 2 | Distribution | 2002-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007627 | 400750048 | Molding | HFTD Tier 2 | Distribution | 2002-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007628 | 400750079 | High Sign | HFTD Tier 2 | Distribution | 2008-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007629 | 400750096 | High Sign | HFTD Tier 2 | Distribution | 2002-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007630 | 400750235 | High Sign | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007631 | 400750240 | High Sign | HFTD Tier 2 | Distribution | 2006-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007632 | 400750533 | Molding | HFTD Tier 3 | Distribution | 2006-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007633 | 400750856 | High Sign | HFTD Tier 2 | Distribution | 2008-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007634 | 400750940 | High Sign | HFTD Tier 3 | Distribution | 2006-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007635 | 400751062 | High Sign | HFTD Tier 3 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007636 | 400751084 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007637 | 400751351 | High Sign | HFTD Tier 2 | Distribution | 2006-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007638 | 400751527 | High Sign | HFTD Tier 3 | Distribution | 2007-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007639 | 400751548 | Guy | HFTD Tier 2 | Distribution | 2006-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007640 | 400751662 | High Sign | HFTD Tier 3 | Distribution | 2007-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007641 | 400751702 | High Sign | HFTD Tier 3 | Distribution | 2001-10-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007642 | 400751792 | Molding | HFTD Tier 2 | Distribution | 2005-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007643 | 400751825 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007644 | 400751906 | Guy | HFTD Tier 3 | Distribution | 2006-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007645 | 400752113 | Molding | HFTD Tier 2 | Distribution | 2006-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007646 | 400752119 | Guy | HFTD Tier 2 | Distribution | 2006-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007647 | 400752652 | Molding | HFTD Tier 2 | Distribution | 2002-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007648 | 400752660 | Molding | HFTD Tier 2 | Distribution | 2002-02-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007649 | 400752687 | Molding | HFTD Tier 2 | Distribution | 2006-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007650 | 400752885 | Guy | HFTD Tier 2 | Distribution | 2005-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007651 | 400752974 | Molding | HFTD Tier 3 | Distribution | 2005-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007652 | 400753042 | Riser/Conduit | HFTD Tier 2 | Distribution | 2001-11-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007653 | 400753081 | Molding | HFTD Tier 3 | Distribution | 2005-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007654 | 400753176 | Molding | HFTD Tier 3 | Distribution | 2006-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007655 | 400753191 | Molding | HFTD Tier 3 | Distribution | 2006-12-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007656 | 400753288 | High Sign | HFTD Tier 2 | Distribution | 1999-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007657 | 400753332 | High Sign | HFTD Tier 2 | Distribution | 2007-03-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007658 | 400753376 | Guy | HFTD Tier 2 | Distribution | 2006-09-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007659 | 400753397 | Molding | HFTD Tier 2 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007660 | 400753645 | Molding | HFTD Tier 2 | Distribution | 2006-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007661 | 400753693 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007662 | 400753730 | Cable/Conductor | HFTD Tier 3 | Distribution | 2006-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007663 | 400753740 | Molding | HFTD Tier 3 | Distribution | 2006-12-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007664 | 400753870 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-05-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007665 | 400754078 | High Sign | HFTD Tier 3 | Distribution | 2005-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007666 | 400754082 | High Sign | HFTD Tier 2 | Distribution | 2006-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007667 | 400754441 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007668 | 400754459 | Hardware/Framing | HFTD Tier 2 | Distribution | 2002-02-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007669 | 400755318 | Molding | HFTD Tier 2 | Distribution | 2006-08-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007670 | 400755486 | Molding | HFTD Tier 2 | Distribution | 2003-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007671 | 400755734 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007672 | 400755822 | Guy | HFTD Tier 3 | Distribution | 2002-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007673 | 400755851 | High Sign | HFTD Tier 2 | Distribution | 2006-06-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007674 | 400755950 | Riser/Conduit | HFTD Tier 3 | Distribution | 2001-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007675 | 400756231 | High Sign | HFTD Tier 3 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007676 | 400756314 | Molding | HFTD Tier 2 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007677 | 400756319 | Molding | HFTD Tier 2 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007678 | 400756553 | High Sign | HFTD Tier 2 | Distribution | 2006-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007679 | 400756556 | High Sign | HFTD Tier 3 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007680 | 400756597 | Molding | HFTD Tier 3 | Distribution | 2007-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007681 | 400756636 | Guy | HFTD Tier 3 | Distribution | 2006-09-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007682 | 400756651 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007683 | 400756730 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007684 | 400756864 | High Sign | HFTD Tier 3 | Distribution | 2006-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007685 | 400757139 | Molding | HFTD Tier 2 | Distribution | 2006-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007686 | 400757192 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007687 | 400757206 | High Sign | HFTD Tier 2 | Distribution | 2006-04-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007688 | 400757342 | High Sign | HFTD Tier 2 | Distribution | 2006-06-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007689 | 400757387 | High Sign | HFTD Tier 3 | Distribution | 2001-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007690 | 400757460 | High Sign | HFTD Tier 3 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007691 | 400757674 | High Sign | HFTD Tier 3 | Distribution | 2001-11-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007692 | 400757680 | High Sign | HFTD Tier 3 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007693 | 400757697 | High Sign | HFTD Tier 2 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007694 | 400757717 | High Sign | HFTD Tier 3 | Distribution | 2006-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007695 | 400757743 | High Sign | HFTD Tier 3 | Distribution | 2006-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007696 | 400757849 | Molding | HFTD Tier 2 | Distribution | 2006-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007697 | 400757915 | High Sign | HFTD Tier 2 | Distribution | 2006-12-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007698 | 400757982 | Guy | HFTD Tier 3 | Distribution | 2006-04-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007699 | 400757983 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2007-11-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007700 | 400758229 | Molding | HFTD Tier 2 | Distribution | 2006-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007701 | 400758248 | Molding | HFTD Tier 2 | Distribution | 2007-09-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007702 | 400758315 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007703 | 400758489 | Guy | HFTD Tier 3 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007704 | 400758535 | Molding | HFTD Tier 2 | Distribution | 2006-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007705 | 400758840 | Molding | HFTD Tier 2 | Distribution | 2003-09-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007706 | 400758853 | High Sign | HFTD Tier 2 | Distribution | 2007-05-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007707 | 400758905 | Molding | HFTD Tier 2 | Distribution | 2007-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007708 | 400759085 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-10-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007709 | 400759209 | High Sign | HFTD Tier 2 | Distribution | 2007-10-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007710 | 400759312 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007711 | 400759346 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007712 | 400759377 | High Sign | HFTD Tier 2 | Distribution | 2006-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007713 | 400759386 | High Sign | HFTD Tier 3 | Distribution | 2001-10-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007714 | 400759435 | Molding | HFTD Tier 2 | Distribution | 2006-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007715 | 400759448 | Molding | HFTD Tier 2 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007716 | 400759659 | High Sign | HFTD Tier 2 | Distribution | 2007-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007717 | 400759736 | Molding | HFTD Tier 3 | Distribution | 2006-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007718 | 400759737 | High Sign | HFTD Tier 3 | Distribution | 2007-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007719 | 400759789 | High Sign | HFTD Tier 2 | Distribution | 2006-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007720 | 400759799 | High Sign | HFTD Tier 2 | Distribution | 2006-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007721 | 400759904 | Molding | HFTD Tier 3 | Distribution | 2006-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007722 | 400759939 | High Sign | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007723 | 400760004 | High Sign | HFTD Tier 2 | Distribution | 2005-12-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007724 | 400760061 | Guy | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007725 | 400760096 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007726 | 400760125 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007727 | 400760399 | Molding | HFTD Tier 3 | Distribution | 2006-05-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007728 | 400760436 | Molding | HFTD Tier 3 | Distribution | 2006-10-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007729 | 400760602 | Molding | HFTD Tier 3 | Distribution | 2007-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007730 | 400760620 | Molding | HFTD Tier 3 | Distribution | 2006-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007731 | 400760763 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007732 | 400760801 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007733 | 400760819 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007734 | 400760908 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-07-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007735 | 400760979 | Guy | HFTD Tier 3 | Distribution | 2007-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007736 | 400761013 | High Sign | HFTD Tier 3 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007737 | 400761086 | Guy | HFTD Tier 2 | Distribution | 2006-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007738 | 400761112 | Molding | HFTD Tier 2 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007739 | 400761225 | High Sign | HFTD Tier 3 | Distribution | 2005-11-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007740 | 400761280 | High Sign | HFTD Tier 2 | Distribution | 2006-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007741 | 400761318 | High Sign | HFTD Tier 3 | Distribution | 2006-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007742 | 400761418 | Molding | HFTD Tier 3 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007743 | 400761423 | Guy | HFTD Tier 3 | Distribution | 2006-12-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007744 | 400761434 | Molding | HFTD Tier 3 | Distribution | 2002-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007745 | 400761465 | High Sign | HFTD Tier 2 | Distribution | 2006-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007746 | 400761522 | Riser/Conduit | HFTD Tier 2 | Distribution | 2006-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007747 | 400761721 | High Sign | HFTD Tier 2 | Distribution | 2002-04-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007748 | 400761752 | High Sign | HFTD Tier 2 | Distribution | 2006-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007749 | 400761757 | Hardware/Framing | HFTD Tier 3 | Distribution | 2003-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007750 | 400761826 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007751 | 400761880 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007752 | 400761986 | Molding | HFTD Tier 3 | Distribution | 2002-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007753 | 400762108 | High Sign | HFTD Tier 3 | Distribution | 2006-03-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007754 | 400762354 | High Sign | HFTD Tier 2 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007755 | 400762387 | Molding | HFTD Tier 3 | Distribution | 2005-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007756 | 400762559 | Molding | HFTD Tier 2 | Distribution | 2005-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007757 | 400762561 | High Sign | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007758 | 400762574 | Guy | HFTD Tier 2 | Distribution | 2007-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007759 | 400762623 | Guy | HFTD Tier 2 | Distribution | 2006-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007760 | 400762696 | High Sign | HFTD Tier 3 | Distribution | 2006-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007761 | 400762716 | Molding | HFTD Tier 2 | Distribution | 2002-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007762 | 400762736 | High Sign | HFTD Tier 3 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007763 | 400762777 | Molding | HFTD Tier 3 | Distribution | 2007-11-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007764 | 400762798 | High Sign | HFTD Tier 3 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007765 | 400762886 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007766 | 400762896 | Molding | HFTD Tier 2 | Distribution | 2007-11-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007767 | 400763030 | High Sign | HFTD Tier 2 | Distribution | 2006-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007768 | 400763294 | High Sign | HFTD Tier 2 | Distribution | 2006-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007769 | 400763506 | Molding | HFTD Tier 2 | Distribution | 2006-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007770 | 400763619 | Molding | HFTD Tier 3 | Distribution | 2002-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007771 | 400763779 | Molding | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007772 | 400763841 | High Sign | HFTD Tier 3 | Distribution | 2001-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007773 | 400763891 | High Sign | HFTD Tier 2 | Distribution | 2006-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007774 | 400764087 | Molding | HFTD Tier 2 | Distribution | 2006-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007775 | 400764141 | Guy | HFTD Tier 2 | Distribution | 2006-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007776 | 400764151 | High Sign | HFTD Tier 3 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007777 | 400764211 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007778 | 400764393 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007779 | 400764672 | Molding | HFTD Tier 3 | Distribution | 2007-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007780 | 400764744 | High Sign | HFTD Tier 3 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007781 | 400764799 | High Sign | HFTD Tier 2 | Distribution | 2006-07-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007782 | 400764814 | High Sign | HFTD Tier 3 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007783 | 400764815 | High Sign | HFTD Tier 2 | Distribution | 2006-07-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007784 | 400765191 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007785 | 400765261 | Riser/Conduit | HFTD Tier 2 | Distribution | 2006-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007786 | 400765347 | High Sign | HFTD Tier 3 | Distribution | 2007-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007787 | 400765368 | High Sign | HFTD Tier 2 | Distribution | 2001-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007788 | 400765369 | High Sign | HFTD Tier 3 | Distribution | 2006-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007789 | 400765399 | Molding | HFTD Tier 2 | Distribution | 2006-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007790 | 400765590 | High Sign | HFTD Tier 3 | Distribution | 2002-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007791 | 400765689 | Molding | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007792 | 400765699 | Molding | HFTD Tier 2 | Distribution | 2006-05-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007793 | 400766014 | Molding | HFTD Tier 2 | Distribution | 2002-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007794 | 400766129 | High Sign | HFTD Tier 3 | Distribution | 2006-08-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007795 | 400766130 | Molding | HFTD Tier 3 | Distribution | 2005-11-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007796 | 400766223 | High Sign | HFTD Tier 3 | Distribution | 2002-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007797 | 400766492 | Molding | HFTD Tier 3 | Distribution | 2006-10-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007798 | 400766701 | Molding | HFTD Tier 2 | Distribution | 2006-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007799 | 400766834 | Molding | HFTD Tier 3 | Distribution | 2002-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007800 | 400766919 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007801 | 400767075 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007802 | 400767303 | Insulator | HFTD Tier 2 | Distribution | 2002-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007803 | 400767480 | Guy | HFTD Tier 2 | Distribution | 2005-12-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007804 | 400767485 | Molding | HFTD Tier 2 | Distribution | 2005-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007805 | 400767536 | Molding | HFTD Tier 3 | Distribution | 2005-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007806 | 400767555 | Molding | HFTD Tier 2 | Distribution | 2001-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007807 | 400767574 | Guy | HFTD Tier 2 | Distribution | 2006-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007808 | 400767640 | Molding | HFTD Tier 2 | Distribution | 2002-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007809 | 400767702 | Molding | HFTD Tier 3 | Distribution | 2002-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007810 | 400767763 | High Sign | HFTD Tier 3 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007811 | 400767859 | Guy | HFTD Tier 2 | Distribution | 2006-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007812 | 400767889 | Cable/Conductor | HFTD Tier 2 | Distribution | 2007-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007813 | 400768026 | Molding | HFTD Tier 3 | Distribution | 2005-10-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007814 | 400768115 | High Sign | HFTD Tier 2 | Distribution | 2006-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007815 | 400768204 | High Sign | HFTD Tier 3 | Distribution | 2002-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007816 | 400768222 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007817 | 400768260 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007818 | 400768283 | Guy | HFTD Tier 3 | Distribution | 2006-10-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007819 | 400768543 | Molding | HFTD Tier 3 | Distribution | 2006-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007820 | 400768631 | Molding | HFTD Tier 3 | Distribution | 2007-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007821 | 400768709 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007822 | 400768733 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007823 | 400769137 | Guy | HFTD Tier 3 | Distribution | 2005-11-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007824 | 400769188 | High Sign | HFTD Tier 3 | Distribution | 2005-11-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007825 | 400769228 | Molding | HFTD Tier 2 | Distribution | 2006-08-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007826 | 400769287 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007827 | 400769381 | Molding | HFTD Tier 2 | Distribution | 2006-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007828 | 400769425 | Molding | HFTD Tier 3 | Distribution | 2001-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007829 | 400769562 | Molding | HFTD Tier 3 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007830 | 400769633 | Molding | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007831 | 400769850 | Molding | HFTD Tier 2 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007832 | 400769911 | High Sign | HFTD Tier 2 | Distribution | 2007-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007833 | 400769986 | High Sign | HFTD Tier 3 | Distribution | 2006-04-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007834 | 400770247 | Guy | HFTD Tier 2 | Distribution | 2002-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007835 | 400770290 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007836 | 400770303 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007837 | 400770317 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007838 | 400770340 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007839 | 400770563 | Insulator | HFTD Tier 2 | Distribution | 2008-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007840 | 400770590 | Molding | HFTD Tier 3 | Distribution | 2006-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007841 | 400770642 | Molding | HFTD Tier 3 | Distribution | 2005-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007842 | 400770674 | High Sign | HFTD Tier 3 | Distribution | 2007-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007843 | 400770703 | High Sign | HFTD Tier 2 | Distribution | 2006-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007844 | 400770707 | High Sign | HFTD Tier 3 | Distribution | 2001-10-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007845 | 400770724 | Molding | HFTD Tier 2 | Distribution | 2007-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007846 | 400770786 | Molding | HFTD Tier 2 | Distribution | 2006-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007847 | 400770881 | Molding | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007848 | 400770900 | High Sign | HFTD Tier 3 | Distribution | 2003-05-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007849 | 400771045 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007850 | 400771102 | High Sign | HFTD Tier 2 | Distribution | 2006-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007851 | 400771175 | High Sign | HFTD Tier 3 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007852 | 400771203 | Hardware/Framing | HFTD Tier 3 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007853 | 400771302 | High Sign | HFTD Tier 3 | Distribution | 2006-10-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007854 | 400771342 | Molding | HFTD Tier 3 | Distribution | 2006-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007855 | 400771470 | Molding | HFTD Tier 2 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007856 | 400771489 | High Sign | HFTD Tier 3 | Distribution | 2006-08-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007857 | 400771491 | High Sign | HFTD Tier 2 | Distribution | 2006-09-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007858 | 400771544 | Guy | HFTD Tier 3 | Distribution | 2015-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007859 | 400771613 | Guy | HFTD Tier 3 | Distribution | 2005-11-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007860 | 400771633 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007861 | 400771656 | Molding | HFTD Tier 2 | Distribution | 2002-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007862 | 400771663 | High Sign | HFTD Tier 2 | Distribution | 2001-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007863 | 400771687 | Molding | HFTD Tier 3 | Distribution | 2006-08-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007864 | 400771798 | High Sign | HFTD Tier 2 | Distribution | 2002-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007865 | 400771903 | Molding | HFTD Tier 3 | Distribution | 2006-10-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007866 | 400771919 | Guy | HFTD Tier 2 | Distribution | 2006-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007867 | 400772007 | High Sign | HFTD Tier 2 | Distribution | 2006-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007868 | 400772170 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007869 | 400772312 | High Sign | HFTD Tier 2 | Distribution | 2002-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007870 | 400772502 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007871 | 400772814 | Molding | HFTD Tier 3 | Distribution | 2006-04-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007872 | 400772931 | High Sign | HFTD Tier 2 | Distribution | 2007-11-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007873 | 400772945 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007874 | 400772956 | High Sign | HFTD Tier 3 | Distribution | 2007-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007875 | 400773019 | High Sign | HFTD Tier 3 | Distribution | 2001-12-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007876 | 400773024 | High Sign | HFTD Tier 3 | Distribution | 2006-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007877 | 400773134 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007878 | 400773170 | Molding | HFTD Tier 2 | Distribution | 2006-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007879 | 400773358 | Molding | HFTD Tier 2 | Distribution | 2006-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007880 | 400773371 | Molding | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007881 | 400773734 | High Sign | HFTD Tier 2 | Distribution | 2008-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007882 | 400773742 | Molding | HFTD Tier 3 | Distribution | 2006-11-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007883 | 400773801 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007884 | 400773908 | High Sign | HFTD Tier 2 | Distribution | 2006-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007885 | 400774069 | Molding | HFTD Tier 3 | Distribution | 2006-12-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007886 | 400774080 | High Sign | HFTD Tier 3 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007887 | 400774091 | High Sign | HFTD Tier 3 | Distribution | 2002-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007888 | 400774116 | Molding | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007889 | 400774318 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007890 | 400774333 | High Sign | HFTD Tier 3 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007891 | 400774373 | High Sign | HFTD Tier 3 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007892 | 400774401 | Molding | HFTD Tier 2 | Distribution | 2003-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007893 | 400774656 | High Sign | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007894 | 400774701 | High Sign | HFTD Tier 2 | Distribution | 2003-09-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007895 | 400774735 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007896 | 400774931 | Molding | HFTD Tier 3 | Distribution | 2007-06-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007897 | 400774945 | High Sign | HFTD Tier 2 | Distribution | 2002-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007898 | 400775049 | High Sign | HFTD Tier 3 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007899 | 400775123 | Molding | HFTD Tier 3 | Distribution | 2006-07-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007900 | 400775213 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007901 | 400775395 | High Sign | HFTD Tier 2 | Distribution | 2006-07-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007902 | 400775425 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007903 | 400775432 | Molding | HFTD Tier 3 | Distribution | 2003-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007904 | 400775504 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-11-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007905 | 400775505 | High Sign | HFTD Tier 2 | Distribution | 2006-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007906 | 400775568 | Molding | HFTD Tier 2 | Distribution | 2006-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007907 | 400775632 | High Sign | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007908 | 400775666 | High Sign | HFTD Tier 2 | Distribution | 2006-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007909 | 400775709 | Molding | HFTD Tier 2 | Distribution | 2006-07-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007910 | 400775720 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007911 | 400775929 | High Sign | HFTD Tier 2 | Distribution | 2007-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007912 | 400776026 | Molding | HFTD Tier 3 | Distribution | 2006-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007913 | 400776038 | Guy | HFTD Tier 3 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007914 | 400776054 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-10-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007915 | 400776077 | Molding | HFTD Tier 2 | Distribution | 2006-09-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007916 | 400776199 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007917 | 400776230 | Molding | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007918 | 400776391 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007919 | 400776426 | Molding | HFTD Tier 2 | Distribution | 2002-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007920 | 400776478 | High Sign | HFTD Tier 2 | Distribution | 2006-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007921 | 400776513 | Molding | HFTD Tier 3 | Distribution | 2006-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007922 | 400776544 | Guy | HFTD Tier 3 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007923 | 400776609 | Guy | HFTD Tier 3 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007924 | 400776970 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007925 | 400777264 | Molding | HFTD Tier 3 | Distribution | 2003-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007926 | 400777358 | High Sign | HFTD Tier 3 | Distribution | 2003-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007927 | 400777403 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007928 | 400777406 | High Sign | HFTD Tier 2 | Distribution | 2006-07-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007929 | 400777491 | High Sign | HFTD Tier 2 | Distribution | 2001-06-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007930 | 400778037 | Molding | HFTD Tier 3 | Distribution | 2006-04-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007931 | 400778180 | Molding | HFTD Tier 2 | Distribution | 2005-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007932 | 400778188 | Molding | HFTD Tier 3 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007933 | 400778251 | High Sign | HFTD Tier 3 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007934 | 400778430 | High Sign | HFTD Tier 2 | Distribution | 2007-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007935 | 400778436 | Molding | HFTD Tier 2 | Distribution | 2006-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007936 | 400778493 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007937 | 400778709 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007938 | 400778710 | Molding | HFTD Tier 2 | Distribution | 2006-12-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007939 | 400778711 | Molding | HFTD Tier 2 | Distribution | 2006-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007940 | 400778794 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007941 | 400778900 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007942 | 400778971 | High Sign | HFTD Tier 2 | Distribution | 2006-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007943 | 400779055 | High Sign | HFTD Tier 3 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007944 | 400779123 | High Sign | HFTD Tier 3 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007945 | 400779124 | High Sign | HFTD Tier 3 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007946 | 400779137 | High Sign | HFTD Tier 3 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007947 | 400779160 | High Sign | HFTD Tier 2 | Distribution | 2007-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007948 | 400779189 | High Sign | HFTD Tier 3 | Distribution | 2002-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007949 | 400779238 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007950 | 400779271 | Riser/Conduit | HFTD Tier 3 | Distribution | 2006-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007951 | 400779275 | Molding | HFTD Tier 3 | Distribution | 2002-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007952 | 400779322 | Guy | HFTD Tier 3 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007953 | 400779363 | High Sign | HFTD Tier 2 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007954 | 400779406 | Molding | HFTD Tier 3 | Distribution | 2006-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007955 | 400779551 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007956 | 400779660 | High Sign | HFTD Tier 3 | Distribution | 2007-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007957 | 400779758 | Molding | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007958 | 400779878 | High Sign | HFTD Tier 3 | Distribution | 2002-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007959 | 400779909 | Guy | HFTD Tier 3 | Distribution | 2007-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007960 | 400779947 | High Sign | HFTD Tier 3 | Distribution | 2006-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007961 | 400779971 | High Sign | HFTD Tier 3 | Distribution | 2006-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007962 | 400780033 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007963 | 400780136 | Molding | HFTD Tier 2 | Distribution | 2007-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007964 | 400780159 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007965 | 400780345 | Molding | HFTD Tier 2 | Distribution | 2006-07-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007966 | 400780365 | High Sign | HFTD Tier 3 | Distribution | 2002-01-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007967 | 400780415 | Molding | HFTD Tier 3 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007968 | 400780545 | Molding | HFTD Tier 3 | Distribution | 2007-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007969 | 400780577 | High Sign | HFTD Tier 3 | Distribution | 2006-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007970 | 400780690 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007971 | 400780790 | High Sign | HFTD Tier 3 | Distribution | 2006-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007972 | 400780880 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007973 | 400781019 | Molding | HFTD Tier 3 | Distribution | 2006-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007974 | 400781358 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007975 | 400781453 | Molding | HFTD Tier 3 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007976 | 400781521 | High Sign | HFTD Tier 3 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007977 | 400781702 | Guy | HFTD Tier 3 | Distribution | 2007-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007978 | 400781755 | High Sign | HFTD Tier 3 | Distribution | 2006-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007979 | 400781916 | High Sign | HFTD Tier 2 | Distribution | 2001-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007980 | 400781994 | Molding | HFTD Tier 3 | Distribution | 2003-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007981 | 400782111 | High Sign | HFTD Tier 3 | Distribution | 2005-10-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007982 | 400782117 | Riser/Conduit | HFTD Tier 2 | Distribution | 2005-12-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007983 | 400782130 | Molding | HFTD Tier 3 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007984 | 400782132 | High Sign | HFTD Tier 3 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007985 | 400782174 | Molding | HFTD Tier 2 | Distribution | 2006-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007986 | 400782334 | Hardware/Framing | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007987 | 400782423 | Molding | HFTD Tier 2 | Distribution | 2007-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007988 | 400782724 | Molding | HFTD Tier 2 | Distribution | 2001-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007989 | 400782787 | Molding | HFTD Tier 3 | Distribution | 2007-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007990 | 400782827 | Molding | HFTD Tier 2 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007991 | 400782916 | High Sign | HFTD Tier 3 | Distribution | 2006-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007992 | 400783090 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007993 | 400783096 | High Sign | HFTD Tier 2 | Distribution | 2006-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007994 | 400783322 | Molding | HFTD Tier 2 | Distribution | 2002-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007995 | 400783352 | Molding | HFTD Tier 2 | Distribution | 2006-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007996 | 400783527 | High Sign | HFTD Tier 2 | Distribution | 2007-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007997 | 400783572 | Molding | HFTD Tier 3 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007998 | 400783576 | Molding | HFTD Tier 3 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130007999 | 400783636 | Molding | HFTD Tier 3 | Distribution | 2007-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008000 | 400783659 | High Sign | HFTD Tier 3 | Distribution | 2002-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008001 | 400783688 | Molding | HFTD Tier 2 | Distribution | 2006-07-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008002 | 400783856 | Molding | HFTD Tier 3 | Distribution | 2006-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008003 | 400784125 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008004 | 400784293 | Molding | HFTD Tier 2 | Distribution | 2006-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008005 | 400784303 | High Sign | HFTD Tier 2 | Distribution | 2006-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008006 | 400784461 | High Sign | HFTD Tier 3 | Distribution | 2006-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008007 | 400784570 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008008 | 400784661 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008009 | 400784724 | High Sign | HFTD Tier 3 | Distribution | 2001-12-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008010 | 400784746 | High Sign | HFTD Tier 3 | Distribution | 2006-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008011 | 400784758 | Molding | HFTD Tier 3 | Distribution | 2005-12-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008012 | 400784760 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008013 | 400784771 | High Sign | HFTD Tier 3 | Distribution | 2006-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008014 | 400784822 | High Sign | HFTD Tier 2 | Distribution | 2002-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008015 | 400784973 | Molding | HFTD Tier 2 | Distribution | 2006-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008016 | 400785132 | High Sign | HFTD Tier 3 | Distribution | 2006-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008017 | 400785421 | High Sign | HFTD Tier 3 | Distribution | 2006-11-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008018 | 400785454 | High Sign | HFTD Tier 2 | Distribution | 2003-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008019 | 400785616 | High Sign | HFTD Tier 2 | Distribution | 2006-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008020 | 400785674 | Molding | HFTD Tier 2 | Distribution | 2007-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008021 | 400785963 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008022 | 400785971 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2007-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008023 | 400786292 | High Sign | HFTD Tier 3 | Distribution | 2001-12-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008024 | 400786342 | Molding | HFTD Tier 2 | Distribution | 2002-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008025 | 400786539 | Molding | HFTD Tier 3 | Distribution | 2006-11-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008026 | 400786588 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008027 | 400786856 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008028 | 400786906 | Molding | HFTD Tier 2 | Distribution | 2002-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008029 | 400786933 | High Sign | HFTD Tier 2 | Distribution | 2006-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008030 | 400787100 | Molding | HFTD Tier 3 | Distribution | 2003-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008031 | 400787150 | Cable/Conductor | HFTD Tier 3 | Distribution | 2003-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008032 | 400787481 | Molding | HFTD Tier 2 | Distribution | 2002-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008033 | 400787965 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008034 | 400788004 | Guy | HFTD Tier 2 | Distribution | 2006-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008035 | 400788510 | Molding | HFTD Tier 2 | Distribution | 2003-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008036 | 400788671 | High Sign | HFTD Tier 2 | Distribution | 2006-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008037 | 400788678 | High Sign | HFTD Tier 2 | Distribution | 2006-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008038 | 400788679 | Molding | HFTD Tier 3 | Distribution | 2008-02-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008039 | 400788711 | Riser/Conduit | HFTD Tier 3 | Distribution | 2005-11-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008040 | 400788725 | High Sign | HFTD Tier 2 | Distribution | 2006-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008041 | 400788757 | Molding | HFTD Tier 3 | Distribution | 2005-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008042 | 400788767 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008043 | 400788796 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008044 | 400788954 | Insulator | HFTD Tier 2 | Distribution | 2002-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008045 | 400789120 | Cable/Conductor | HFTD Tier 3 | Distribution | 2003-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008046 | 400789137 | Molding | HFTD Tier 3 | Distribution | 2007-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008047 | 400789341 | High Sign | HFTD Tier 3 | Distribution | 2006-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008048 | 400789534 | High Sign | HFTD Tier 3 | Distribution | 2002-01-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008049 | 400789614 | High Sign | HFTD Tier 3 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008050 | 400789749 | Molding | HFTD Tier 3 | Distribution | 2007-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008051 | 400789840 | High Sign | HFTD Tier 2 | Distribution | 2002-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008052 | 400789871 | High Sign | HFTD Tier 2 | Distribution | 2006-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008053 | 400790192 | Molding | HFTD Tier 3 | Distribution | 2003-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008054 | 400790210 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008055 | 400790244 | Hardware/Framing | HFTD Tier 3 | Distribution | 2003-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008056 | 400790250 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008057 | 400790300 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008058 | 400790422 | Molding | HFTD Tier 2 | Distribution | 2005-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008059 | 400790469 | Molding | HFTD Tier 2 | Distribution | 2002-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008060 | 400790493 | High Sign | HFTD Tier 2 | Distribution | 2006-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008061 | 400790505 | Molding | HFTD Tier 2 | Distribution | 2006-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008062 | 400790542 | High Sign | HFTD Tier 2 | Distribution | 2002-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008063 | 400790606 | High Sign | HFTD Tier 2 | Distribution | 2007-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008064 | 400790884 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008065 | 400790962 | High Sign | HFTD Tier 2 | Distribution | 2006-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008066 | 400791012 | High Sign | HFTD Tier 3 | Distribution | 2005-12-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008067 | 400791085 | Molding | HFTD Tier 2 | Distribution | 2006-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008068 | 400791192 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008069 | 400791733 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008070 | 400791913 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008071 | 400791937 | Molding | HFTD Tier 3 | Distribution | 2006-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008072 | 400792077 | Molding | HFTD Tier 2 | Distribution | 2006-09-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008073 | 400792096 | High Sign | HFTD Tier 3 | Distribution | 2006-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008074 | 400792107 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008075 | 400792118 | High Sign | HFTD Tier 3 | Distribution | 2001-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008076 | 400792123 | High Sign | HFTD Tier 2 | Distribution | 2002-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008077 | 400792130 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008078 | 400792235 | High Sign | HFTD Tier 2 | Distribution | 2007-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008079 | 400792268 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008080 | 400792478 | High Sign | HFTD Tier 2 | Distribution | 2005-11-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008081 | 400792522 | High Sign | HFTD Tier 3 | Distribution | 2006-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008082 | 400792628 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008083 | 400792646 | Molding | HFTD Tier 2 | Distribution | 2006-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008084 | 400792761 | Molding | HFTD Tier 3 | Distribution | 2006-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008085 | 400792827 | Molding | HFTD Tier 3 | Distribution | 2007-06-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008086 | 400792899 | Molding | HFTD Tier 3 | Distribution | 2007-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008087 | 400792910 | High Sign | HFTD Tier 2 | Distribution | 2006-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008088 | 400793003 | Molding | HFTD Tier 3 | Distribution | 2002-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008089 | 400793170 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-11-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008090 | 400793468 | High Sign | HFTD Tier 2 | Distribution | 2007-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008091 | 400793559 | High Sign | HFTD Tier 3 | Distribution | 2005-12-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008092 | 400793607 | High Sign | HFTD Tier 3 | Distribution | 2008-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008093 | 400793630 | High Sign | HFTD Tier 2 | Distribution | 2002-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008094 | 400793719 | Molding | HFTD Tier 3 | Distribution | 2002-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008095 | 400793762 | High Sign | HFTD Tier 2 | Distribution | 2001-12-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008096 | 400793876 | Molding | HFTD Tier 3 | Distribution | 2006-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008097 | 400794060 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008098 | 400794113 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008099 | 400794169 | High Sign | HFTD Tier 2 | Distribution | 2006-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008100 | 400794185 | Molding | HFTD Tier 2 | Distribution | 2002-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008101 | 400794396 | High Sign | HFTD Tier 2 | Distribution | 2002-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008102 | 400794431 | High Sign | HFTD Tier 3 | Distribution | 2006-11-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008103 | 400794584 | Molding | HFTD Tier 2 | Distribution | 2006-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008104 | 400794633 | Molding | HFTD Tier 3 | Distribution | 2005-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008105 | 400794667 | Molding | HFTD Tier 3 | Distribution | 2002-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008106 | 400794714 | High Sign | HFTD Tier 2 | Distribution | 2006-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008107 | 400794733 | High Sign | HFTD Tier 3 | Distribution | 2002-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008108 | 400794751 | Molding | HFTD Tier 2 | Distribution | 2006-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008109 | 400794777 | Molding | HFTD Tier 2 | Distribution | 2006-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008110 | 400794809 | Hardware/Framing | HFTD Tier 2 | Distribution | 2003-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008111 | 400794865 | High Sign | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008112 | 400794904 | High Sign | HFTD Tier 3 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008113 | 400794908 | High Sign | HFTD Tier 3 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008114 | 400795082 | Guy | HFTD Tier 2 | Distribution | 2006-12-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008115 | 400795141 | High Sign | HFTD Tier 2 | Distribution | 2008-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008116 | 400795259 | High Sign | HFTD Tier 3 | Distribution | 2002-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008117 | 400795284 | High Sign | HFTD Tier 3 | Distribution | 2006-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008118 | 400795306 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008119 | 400795317 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-05-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008120 | 400795318 | Molding | HFTD Tier 2 | Distribution | 2006-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008121 | 400795356 | High Sign | HFTD Tier 2 | Distribution | 2006-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008122 | 400795469 | Molding | HFTD Tier 3 | Distribution | 2003-09-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008123 | 400795591 | Insulator | HFTD Tier 3 | Distribution | 2006-12-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008124 | 400795765 | High Sign | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008125 | 400795996 | High Sign | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008126 | 400796132 | Molding | HFTD Tier 3 | Distribution | 2006-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008127 | 400796291 | High Sign | HFTD Tier 3 | Distribution | 2005-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008128 | 400796339 | High Sign | HFTD Tier 3 | Distribution | 2002-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008129 | 400796400 | Molding | HFTD Tier 3 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008130 | 400796504 | Molding | HFTD Tier 3 | Distribution | 2007-07-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008131 | 400796594 | Guy | HFTD Tier 3 | Distribution | 2007-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008132 | 400796758 | Molding | HFTD Tier 2 | Distribution | 2006-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008133 | 400796850 | Molding | HFTD Tier 3 | Distribution | 2006-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008134 | 400797049 | High Sign | HFTD Tier 3 | Distribution | 2006-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008135 | 400797052 | High Sign | HFTD Tier 3 | Distribution | 2007-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008136 | 400797141 | High Sign | HFTD Tier 2 | Distribution | 2003-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008137 | 400797224 | High Sign | HFTD Tier 2 | Distribution | 1999-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008138 | 400797231 | High Sign | HFTD Tier 2 | Distribution | 2006-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008139 | 400797280 | Molding | HFTD Tier 3 | Distribution | 2007-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008140 | 400797477 | Molding | HFTD Tier 2 | Distribution | 2002-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008141 | 400797662 | High Sign | HFTD Tier 2 | Distribution | 2006-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008142 | 400797663 | Molding | HFTD Tier 2 | Distribution | 2006-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008143 | 400797769 | Molding | HFTD Tier 3 | Distribution | 2006-07-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008144 | 400797798 | Molding | HFTD Tier 3 | Distribution | 2008-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008145 | 400797968 | High Sign | HFTD Tier 2 | Distribution | 2006-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008146 | 400797995 | High Sign | HFTD Tier 2 | Distribution | 2007-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008147 | 400798182 | Molding | HFTD Tier 2 | Distribution | 2006-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008148 | 400798297 | Molding | HFTD Tier 2 | Distribution | 2006-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008149 | 400798373 | High Sign | HFTD Tier 2 | Distribution | 2006-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008150 | 400798570 | Guy | HFTD Tier 3 | Distribution | 2007-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008151 | 400798586 | Guy | HFTD Tier 3 | Distribution | 2007-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008152 | 400798651 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-12-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008153 | 400798693 | Hardware/Framing | HFTD Tier 3 | Distribution | 2002-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008154 | 400798769 | Molding | HFTD Tier 2 | Distribution | 2006-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008155 | 400798911 | Molding | HFTD Tier 2 | Distribution | 2003-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008156 | 400798925 | High Sign | HFTD Tier 2 | Distribution | 2003-04-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008157 | 400799010 | High Sign | HFTD Tier 2 | Distribution | 2007-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008158 | 400799097 | Guy | HFTD Tier 2 | Distribution | 2006-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008159 | 400799108 | High Sign | HFTD Tier 2 | Distribution | 2001-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008160 | 400799296 | High Sign | HFTD Tier 2 | Distribution | 2003-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008161 | 400799306 | High Sign | HFTD Tier 3 | Distribution | 2005-12-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008162 | 400799557 | Molding | HFTD Tier 3 | Distribution | 2006-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008163 | 400799687 | High Sign | HFTD Tier 2 | Distribution | 1999-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008164 | 400799831 | Molding | HFTD Tier 3 | Distribution | 2006-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008165 | 400799875 | High Sign | HFTD Tier 3 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008166 | 400800431 | High Sign | HFTD Tier 3 | Distribution | 2006-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008167 | 400800652 | High Sign | HFTD Tier 3 | Distribution | 2005-12-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008168 | 400800965 | Molding | HFTD Tier 2 | Distribution | 2006-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008169 | 400800991 | Molding | HFTD Tier 2 | Distribution | 2006-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008170 | 400801141 | High Sign | HFTD Tier 3 | Distribution | 2006-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008171 | 400801330 | High Sign | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008172 | 400801378 | Guy | HFTD Tier 3 | Distribution | 2006-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008173 | 400801498 | High Sign | HFTD Tier 3 | Distribution | 2006-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008174 | 400801675 | Molding | HFTD Tier 2 | Distribution | 2006-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008175 | 400801910 | Molding | HFTD Tier 2 | Distribution | 2007-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008176 | 400801921 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008177 | 400802014 | High Sign | HFTD Tier 3 | Distribution | 2007-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008178 | 400802039 | Molding | HFTD Tier 3 | Distribution | 2006-11-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008179 | 400802047 | High Sign | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008180 | 400802078 | Guy | HFTD Tier 3 | Distribution | 2001-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008181 | 400802238 | High Sign | HFTD Tier 3 | Distribution | 2006-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008182 | 400802350 | High Sign | HFTD Tier 2 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008183 | 400802442 | High Sign | HFTD Tier 3 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008184 | 400802502 | High Sign | HFTD Tier 2 | Distribution | 2002-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008185 | 400802552 | Molding | HFTD Tier 3 | Distribution | 2005-11-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008186 | 400802858 | Molding | HFTD Tier 3 | Distribution | 2002-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008187 | 400802879 | High Sign | HFTD Tier 2 | Distribution | 2001-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008188 | 400802914 | High Sign | HFTD Tier 3 | Distribution | 2001-11-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008189 | 400802972 | High Sign | HFTD Tier 3 | Distribution | 2002-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008190 | 400803101 | Guy | HFTD Tier 2 | Distribution | 2006-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008191 | 400803320 | High Sign | HFTD Tier 3 | Distribution | 2001-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008192 | 400803479 | High Sign | HFTD Tier 3 | Distribution | 2006-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008193 | 400803489 | High Sign | HFTD Tier 2 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008194 | 400803539 | Guy | HFTD Tier 3 | Distribution | 2006-12-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008195 | 400803632 | Guy | HFTD Tier 3 | Distribution | 2007-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008196 | 400803781 | High Sign | HFTD Tier 3 | Distribution | 2002-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008197 | 400803836 | High Sign | HFTD Tier 2 | Distribution | 2006-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008198 | 400803973 | High Sign | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008199 | 400803980 | Molding | HFTD Tier 2 | Distribution | 2006-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008200 | 400804013 | High Sign | HFTD Tier 3 | Distribution | 2001-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008201 | 400804051 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008202 | 400804142 | Molding | HFTD Tier 2 | Distribution | 2003-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008203 | 400804431 | Molding | HFTD Tier 3 | Distribution | 2001-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008204 | 400804449 | Molding | HFTD Tier 3 | Distribution | 2006-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008205 | 400804471 | High Sign | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008206 | 400804665 | Molding | HFTD Tier 2 | Distribution | 2006-03-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008207 | 400804696 | Molding | HFTD Tier 3 | Distribution | 2006-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008208 | 400804764 | Hardware/Framing | HFTD Tier 3 | Distribution | 2005-11-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008209 | 400804805 | High Sign | HFTD Tier 2 | Distribution | 2006-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008210 | 400804821 | High Sign | HFTD Tier 3 | Distribution | 2003-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008211 | 400804893 | High Sign | HFTD Tier 2 | Distribution | 2006-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008212 | 400804925 | Guy | HFTD Tier 3 | Distribution | 2006-10-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008213 | 400805017 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008214 | 400805102 | Molding | HFTD Tier 2 | Distribution | 2002-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008215 | 400805120 | Guy | HFTD Tier 3 | Distribution | 2006-08-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008216 | 400805350 | Molding | HFTD Tier 3 | Distribution | 2006-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008217 | 400805477 | High Sign | HFTD Tier 2 | Distribution | 2002-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008218 | 400805516 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-02-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008219 | 400805565 | Molding | HFTD Tier 3 | Distribution | 2006-08-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008220 | 400805586 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008221 | 400805670 | Riser/Conduit | HFTD Tier 2 | Distribution | 2007-11-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008222 | 400805686 | High Sign | HFTD Tier 2 | Distribution | 2006-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008223 | 400805722 | High Sign | HFTD Tier 2 | Distribution | 2003-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008224 | 400805774 | High Sign | HFTD Tier 3 | Distribution | 2007-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008225 | 400805782 | High Sign | HFTD Tier 3 | Distribution | 2002-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008226 | 400805805 | Insulator | HFTD Tier 2 | Distribution | 2002-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008227 | 400805851 | High Sign | HFTD Tier 3 | Distribution | 2007-07-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008228 | 400805896 | High Sign | HFTD Tier 3 | Distribution | 2003-09-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008229 | 400806114 | Molding | HFTD Tier 3 | Distribution | 2006-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008230 | 400806393 | High Sign | HFTD Tier 2 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008231 | 400806504 | Molding | HFTD Tier 3 | Distribution | 2006-08-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008232 | 400806542 | Molding | HFTD Tier 2 | Distribution | 2006-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008233 | 400806634 | High Sign | HFTD Tier 3 | Distribution | 2005-12-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008234 | 400806693 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008235 | 400806739 | Molding | HFTD Tier 3 | Distribution | 2006-08-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008236 | 400806776 | High Sign | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008237 | 400806827 | Guy | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008238 | 400806834 | High Sign | HFTD Tier 3 | Distribution | 2001-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008239 | 400807388 | Insulator | HFTD Tier 2 | Distribution | 2006-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008240 | 400807390 | Guy | HFTD Tier 3 | Distribution | 2002-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008241 | 400807529 | High Sign | HFTD Tier 3 | Distribution | 2008-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008242 | 400807595 | Molding | HFTD Tier 2 | Distribution | 2006-07-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008243 | 400807600 | Molding | HFTD Tier 3 | Distribution | 2007-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008244 | 400807836 | High Sign | HFTD Tier 3 | Distribution | 2005-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008245 | 400807871 | High Sign | HFTD Tier 2 | Distribution | 2003-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008246 | 400808037 | High Sign | HFTD Tier 2 | Distribution | 2007-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008247 | 400808056 | Molding | HFTD Tier 2 | Distribution | 2006-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008248 | 400808131 | Molding | HFTD Tier 3 | Distribution | 2006-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008249 | 400808146 | Molding | HFTD Tier 3 | Distribution | 2007-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008250 | 400808409 | High Sign | HFTD Tier 2 | Distribution | 2006-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008251 | 400808415 | High Sign | HFTD Tier 2 | Distribution | 2002-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008252 | 400808433 | Molding | HFTD Tier 2 | Distribution | 2003-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008253 | 400808436 | Molding | HFTD Tier 3 | Distribution | 2006-08-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008254 | 400808439 | High Sign | HFTD Tier 2 | Distribution | 2006-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008255 | 400808489 | High Sign | HFTD Tier 3 | Distribution | 2006-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008256 | 400808543 | Molding | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008257 | 400808607 | Molding | HFTD Tier 2 | Distribution | 2006-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008258 | 400808694 | Molding | HFTD Tier 2 | Distribution | 2001-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008259 | 400808711 | Molding | HFTD Tier 2 | Distribution | 2002-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008260 | 400808728 | High Sign | HFTD Tier 3 | Distribution | 2002-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008261 | 400808904 | Molding | HFTD Tier 3 | Distribution | 2007-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008262 | 400808963 | Molding | HFTD Tier 2 | Distribution | 2006-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008263 | 400809067 | Molding | HFTD Tier 3 | Distribution | 2005-12-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008264 | 400809167 | Molding | HFTD Tier 3 | Distribution | 2007-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008265 | 400809276 | Molding | HFTD Tier 3 | Distribution | 2006-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008266 | 400809383 | Riser/Conduit | HFTD Tier 2 | Distribution | 2006-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008267 | 400809491 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008268 | 400809513 | High Sign | HFTD Tier 2 | Distribution | 2007-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008269 | 400809526 | High Sign | HFTD Tier 2 | Distribution | 2007-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008270 | 400809615 | Molding | HFTD Tier 2 | Distribution | 2006-03-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008271 | 400809673 | Molding | HFTD Tier 2 | Distribution | 2007-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008272 | 400809724 | High Sign | HFTD Tier 3 | Distribution | 2001-12-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008273 | 400809890 | Molding | HFTD Tier 2 | Distribution | 2006-02-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008274 | 400809991 | Molding | HFTD Tier 3 | Distribution | 2006-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008275 | 400810078 | Molding | HFTD Tier 2 | Distribution | 2006-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008276 | 400810085 | Molding | HFTD Tier 3 | Distribution | 2006-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008277 | 400810170 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008278 | 400810278 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008279 | 400810398 | Molding | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008280 | 400810451 | High Sign | HFTD Tier 2 | Distribution | 2007-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008281 | 400810500 | High Sign | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008282 | 400810514 | Molding | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008283 | 400810588 | High Sign | HFTD Tier 3 | Distribution | 2006-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008284 | 400810643 | High Sign | HFTD Tier 3 | Distribution | 2001-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008285 | 400810897 | Molding | HFTD Tier 3 | Distribution | 2007-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008286 | 400810954 | Molding | HFTD Tier 3 | Distribution | 2002-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008287 | 400811065 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008288 | 400811222 | Molding | HFTD Tier 3 | Distribution | 2002-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008289 | 400811303 | Molding | HFTD Tier 2 | Distribution | 2007-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008290 | 400811353 | Guy | HFTD Tier 2 | Distribution | 2002-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008291 | 400811428 | High Sign | HFTD Tier 2 | Distribution | 2002-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008292 | 400811454 | Riser/Conduit | HFTD Tier 3 | Distribution | 2006-11-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008293 | 400811679 | Guy | HFTD Tier 3 | Distribution | 2007-11-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008294 | 400811687 | High Sign | HFTD Tier 2 | Distribution | 2006-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008295 | 400811704 | Molding | HFTD Tier 2 | Distribution | 2005-11-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008296 | 400811786 | Hardware/Framing | HFTD Tier 3 | Distribution | 2003-11-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008297 | 400811817 | Guy | HFTD Tier 2 | Distribution | 2006-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008298 | 400811828 | Molding | HFTD Tier 3 | Distribution | 2006-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008299 | 400811880 | Molding | HFTD Tier 2 | Distribution | 2003-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008300 | 400811934 | High Sign | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008301 | 400811961 | Molding | HFTD Tier 2 | Distribution | 2006-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008302 | 400812041 | Molding | HFTD Tier 2 | Distribution | 2006-03-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008303 | 400812141 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2003-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008304 | 400812223 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008305 | 400812388 | Molding | HFTD Tier 2 | Distribution | 2006-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008306 | 400812484 | Molding | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008307 | 400812525 | High Sign | HFTD Tier 2 | Distribution | 2006-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008308 | 400812720 | Molding | HFTD Tier 2 | Distribution | 2006-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008309 | 400812816 | High Sign | HFTD Tier 3 | Distribution | 2006-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008310 | 400812876 | Molding | HFTD Tier 3 | Distribution | 2005-12-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008311 | 400812948 | High Sign | HFTD Tier 2 | Distribution | 2006-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008312 | 400812962 | High Sign | HFTD Tier 2 | Distribution | 2007-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008313 | 400813064 | Molding | HFTD Tier 2 | Distribution | 2002-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008314 | 400813118 | Molding | HFTD Tier 2 | Distribution | 2002-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008315 | 400813210 | High Sign | HFTD Tier 3 | Distribution | 2007-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008316 | 400813232 | Molding | HFTD Tier 2 | Distribution | 2003-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008317 | 400813238 | Molding | HFTD Tier 3 | Distribution | 2006-08-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008318 | 400813260 | Molding | HFTD Tier 3 | Distribution | 2006-08-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008319 | 400813290 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008320 | 400813393 | Molding | HFTD Tier 3 | Distribution | 2007-01-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008321 | 400813480 | Molding | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008322 | 400813575 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008323 | 400813596 | Molding | HFTD Tier 2 | Distribution | 2007-01-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008324 | 400813602 | Molding | HFTD Tier 3 | Distribution | 2001-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008325 | 400813979 | High Sign | HFTD Tier 2 | Distribution | 2003-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008326 | 400814007 | Insulator | HFTD Tier 2 | Distribution | 2006-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008327 | 400814085 | Molding | HFTD Tier 2 | Distribution | 2002-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008328 | 400814130 | High Sign | HFTD Tier 3 | Distribution | 2006-12-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008329 | 400814305 | High Sign | HFTD Tier 2 | Distribution | 2007-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008330 | 400814421 | Molding | HFTD Tier 3 | Distribution | 2007-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008331 | 400814549 | High Sign | HFTD Tier 2 | Distribution | 2007-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008332 | 400814561 | Guy | HFTD Tier 3 | Distribution | 2001-12-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008333 | 400814605 | High Sign | HFTD Tier 3 | Distribution | 2006-11-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008334 | 400814650 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008335 | 400814688 | Molding | HFTD Tier 2 | Distribution | 2006-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008336 | 400814735 | Molding | HFTD Tier 2 | Distribution | 2006-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008337 | 400814814 | Molding | HFTD Tier 3 | Distribution | 2007-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008338 | 400814997 | High Sign | HFTD Tier 3 | Distribution | 2006-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008339 | 400815119 | Cable/Conductor | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008340 | 400815151 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008341 | 400815253 | High Sign | HFTD Tier 2 | Distribution | 2006-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008342 | 400815330 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-11-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008343 | 400815341 | Molding | HFTD Tier 3 | Distribution | 2007-12-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008344 | 400815463 | Molding | HFTD Tier 3 | Distribution | 2001-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008345 | 400815601 | Molding | HFTD Tier 3 | Distribution | 2006-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008346 | 400815706 | Molding | HFTD Tier 3 | Distribution | 2006-10-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008347 | 400815757 | High Sign | HFTD Tier 2 | Distribution | 2002-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008348 | 400815772 | Molding | HFTD Tier 2 | Distribution | 2006-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008349 | 400815856 | Molding | HFTD Tier 2 | Distribution | 2005-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008350 | 400816018 | High Sign | HFTD Tier 3 | Distribution | 2001-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008351 | 400816183 | High Sign | HFTD Tier 2 | Distribution | 2002-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008352 | 400816200 | Molding | HFTD Tier 2 | Distribution | 2002-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008353 | 400816279 | Molding | HFTD Tier 3 | Distribution | 2007-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008354 | 400816344 | Guy | HFTD Tier 3 | Distribution | 2006-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008355 | 400816347 | High Sign | HFTD Tier 3 | Distribution | 2001-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008356 | 400816425 | High Sign | HFTD Tier 3 | Distribution | 2006-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008357 | 400816459 | Molding | HFTD Tier 2 | Distribution | 2007-06-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008358 | 400816581 | Molding | HFTD Tier 2 | Distribution | 2006-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008359 | 400816663 | High Sign | HFTD Tier 3 | Distribution | 2005-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008360 | 400816690 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-11-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008361 | 400816820 | High Sign | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008362 | 400817037 | High Sign | HFTD Tier 3 | Distribution | 2001-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008363 | 400817100 | Molding | HFTD Tier 2 | Distribution | 2007-09-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008364 | 400817212 | Molding | HFTD Tier 2 | Distribution | 2007-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008365 | 400817269 | High Sign | HFTD Tier 2 | Distribution | 2006-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008366 | 400817278 | Molding | HFTD Tier 3 | Distribution | 2006-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008367 | 400817292 | Molding | HFTD Tier 3 | Distribution | 2007-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008368 | 400817345 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008369 | 400817368 | Guy | HFTD Tier 3 | Distribution | 2007-01-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008370 | 400817377 | Guy | HFTD Tier 2 | Distribution | 2006-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008371 | 400817502 | Molding | HFTD Tier 3 | Distribution | 2001-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008372 | 400817604 | High Sign | HFTD Tier 3 | Distribution | 2006-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008373 | 400817688 | Molding | HFTD Tier 2 | Distribution | 2006-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008374 | 400817935 | Molding | HFTD Tier 2 | Distribution | 2006-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008375 | 400818080 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-12-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008376 | 400818148 | High Sign | HFTD Tier 3 | Distribution | 2006-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008377 | 400818270 | Molding | HFTD Tier 2 | Distribution | 2005-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008378 | 400818454 | Molding | HFTD Tier 3 | Distribution | 2003-09-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008379 | 400818549 | Molding | HFTD Tier 2 | Distribution | 2006-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008380 | 400818562 | Guy | HFTD Tier 3 | Distribution | 2007-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008381 | 400818650 | Molding | HFTD Tier 3 | Distribution | 2002-09-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008382 | 400818774 | Molding | HFTD Tier 2 | Distribution | 2006-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008383 | 400818914 | High Sign | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008384 | 400819464 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008385 | 400819468 | Molding | HFTD Tier 3 | Distribution | 2006-01-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008386 | 400819499 | Molding | HFTD Tier 3 | Distribution | 2007-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008387 | 400819757 | Molding | HFTD Tier 3 | Distribution | 2003-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008388 | 400820506 | High Sign | HFTD Tier 3 | Distribution | 2002-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008389 | 400820607 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-03-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008390 | 400820795 | High Sign | HFTD Tier 3 | Distribution | 2006-11-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008391 | 400821131 | High Sign | HFTD Tier 2 | Distribution | 2005-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008392 | 400821195 | Molding | HFTD Tier 2 | Distribution | 2005-11-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008393 | 400821258 | Insulator | HFTD Tier 3 | Distribution | 2007-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008394 | 400821659 | Molding | HFTD Tier 2 | Distribution | 2002-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008395 | 400821718 | Molding | HFTD Tier 3 | Distribution | 2002-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008396 | 400822123 | Guy | HFTD Tier 3 | Distribution | 2007-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008397 | 400822149 | Guy | HFTD Tier 3 | Distribution | 2007-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008398 | 400822198 | High Sign | HFTD Tier 3 | Distribution | 2006-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008399 | 400822218 | High Sign | HFTD Tier 2 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008400 | 400822313 | Molding | HFTD Tier 3 | Distribution | 2006-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008401 | 400822349 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-12-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008402 | 400822536 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-08-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008403 | 400822543 | Molding | HFTD Tier 2 | Distribution | 2002-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008404 | 400822724 | Molding | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008405 | 400822756 | Molding | HFTD Tier 2 | Distribution | 2002-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008406 | 400822850 | Molding | HFTD Tier 3 | Distribution | 2006-11-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008407 | 400822926 | Molding | HFTD Tier 3 | Distribution | 2006-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008408 | 400822988 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008409 | 400823036 | High Sign | HFTD Tier 2 | Distribution | 2006-08-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008410 | 400823121 | KV Cable Tags | HFTD Tier 3 | Distribution | 2008-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008411 | 400823249 | High Sign | HFTD Tier 2 | Distribution | 2006-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008412 | 400823319 | Guy | HFTD Tier 3 | Distribution | 2007-05-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008413 | 400823587 | High Sign | HFTD Tier 2 | Distribution | 2006-07-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008414 | 400823639 | High Sign | HFTD Tier 2 | Distribution | 2003-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008415 | 400823730 | Molding | HFTD Tier 2 | Distribution | 2006-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008416 | 400823928 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008417 | 400823990 | High Sign | HFTD Tier 3 | Distribution | 2005-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008418 | 400824003 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008419 | 400824406 | High Sign | HFTD Tier 2 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008420 | 400824418 | Molding | HFTD Tier 3 | Distribution | 2001-09-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008421 | 400824468 | High Sign | HFTD Tier 3 | Distribution | 2005-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008422 | 400824503 | High Sign | HFTD Tier 3 | Distribution | 2005-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008423 | 400824512 | High Sign | HFTD Tier 3 | Distribution | 2006-08-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008424 | 400824907 | Molding | HFTD Tier 2 | Distribution | 2006-09-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008425 | 400824981 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008426 | 400825047 | Molding | HFTD Tier 2 | Distribution | 2002-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008427 | 400825064 | High Sign | HFTD Tier 2 | Distribution | 2006-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008428 | 400825103 | High Sign | HFTD Tier 2 | Distribution | 2002-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008429 | 400825165 | High Sign | HFTD Tier 2 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008430 | 400825271 | Guy | HFTD Tier 3 | Distribution | 2007-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008431 | 400825287 | High Sign | HFTD Tier 3 | Distribution | 2007-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008432 | 400825404 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008433 | 400825513 | Molding | HFTD Tier 3 | Distribution | 2006-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008434 | 400825608 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008435 | 400825804 | Riser/Conduit | HFTD Tier 3 | Distribution | 2004-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008436 | 400825819 | High Sign | HFTD Tier 2 | Distribution | 2007-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008437 | 400825884 | Guy | HFTD Tier 2 | Distribution | 2001-12-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008438 | 400825938 | Molding | HFTD Tier 2 | Distribution | 2002-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008439 | 400826210 | High Sign | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008440 | 400826216 | High Sign | HFTD Tier 2 | Distribution | 2007-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008441 | 400826523 | Molding | HFTD Tier 2 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008442 | 400826548 | Molding | HFTD Tier 2 | Distribution | 2006-12-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008443 | 400826953 | Molding | HFTD Tier 3 | Distribution | 2006-02-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008444 | 400827230 | High Sign | HFTD Tier 3 | Distribution | 2002-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008445 | 400827259 | Molding | HFTD Tier 2 | Distribution | 2003-09-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008446 | 400827384 | Guy | HFTD Tier 3 | Distribution | 2007-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008447 | 400827439 | Guy | HFTD Tier 3 | Distribution | 2007-07-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008448 | 400827544 | High Sign | HFTD Tier 2 | Distribution | 2005-12-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008449 | 400827549 | High Sign | HFTD Tier 2 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008450 | 400827650 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008451 | 400827654 | Guy | HFTD Tier 2 | Distribution | 2006-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008452 | 400827833 | High Sign | HFTD Tier 2 | Distribution | 2002-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008453 | 400827848 | High Sign | HFTD Tier 3 | Distribution | 2002-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008454 | 400828001 | Molding | HFTD Tier 2 | Distribution | 2006-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008455 | 400828238 | High Sign | HFTD Tier 3 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008456 | 400828260 | High Sign | HFTD Tier 3 | Distribution | 2003-07-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008457 | 400828408 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008458 | 400828423 | Guy | HFTD Tier 2 | Distribution | 2002-01-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008459 | 400828794 | Molding | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008460 | 400828825 | Guy | HFTD Tier 3 | Distribution | 2007-12-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008461 | 400828972 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008462 | 400829098 | Molding | HFTD Tier 3 | Distribution | 2003-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008463 | 400829244 | Hardware/Framing | HFTD Tier 3 | Distribution | 2003-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008464 | 400829302 | Molding | HFTD Tier 2 | Distribution | 2001-12-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008465 | 400829465 | High Sign | HFTD Tier 2 | Distribution | 2006-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008466 | 400829819 | High Sign | HFTD Tier 3 | Distribution | 2006-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008467 | 400829823 | Molding | HFTD Tier 3 | Distribution | 2003-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008468 | 400829840 | High Sign | HFTD Tier 3 | Distribution | 2002-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008469 | 400829896 | High Sign | HFTD Tier 2 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008470 | 400829982 | High Sign | HFTD Tier 3 | Distribution | 2002-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008471 | 400830004 | High Sign | HFTD Tier 3 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008472 | 400830065 | Hardware/Framing | HFTD Tier 3 | Distribution | 2001-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008473 | 400830149 | High Sign | HFTD Tier 2 | Distribution | 2006-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008474 | 400830152 | Guy | HFTD Tier 2 | Distribution | 2006-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008475 | 400830346 | Molding | HFTD Tier 2 | Distribution | 2002-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008476 | 400830425 | High Sign | HFTD Tier 3 | Distribution | 2002-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008477 | 400830469 | High Sign | HFTD Tier 2 | Distribution | 2006-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008478 | 400830537 | Molding | HFTD Tier 2 | Distribution | 2006-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008479 | 400830539 | Molding | HFTD Tier 3 | Distribution | 2007-11-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008480 | 400830712 | High Sign | HFTD Tier 3 | Distribution | 2007-08-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008481 | 400830793 | Molding | HFTD Tier 3 | Distribution | 2006-08-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008482 | 400830889 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-11-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008483 | 400830999 | Molding | HFTD Tier 2 | Distribution | 2006-12-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008484 | 400831232 | High Sign | HFTD Tier 2 | Distribution | 2002-01-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008485 | 400831390 | Molding | HFTD Tier 2 | Distribution | 2002-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008486 | 400831487 | Molding | HFTD Tier 2 | Distribution | 2007-11-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008487 | 400831639 | Molding | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008488 | 400831770 | Molding | HFTD Tier 2 | Distribution | 2007-08-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008489 | 400831864 | High Sign | HFTD Tier 3 | Distribution | 2002-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008490 | 400832005 | High Sign | HFTD Tier 2 | Distribution | 1999-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008491 | 400832039 | Guy | HFTD Tier 2 | Distribution | 2006-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008492 | 400832131 | Molding | HFTD Tier 3 | Distribution | 2008-04-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008493 | 400832194 | Molding | HFTD Tier 2 | Distribution | 2006-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008494 | 400832302 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008495 | 400832405 | Guy | HFTD Tier 2 | Distribution | 2006-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008496 | 400832477 | Molding | HFTD Tier 3 | Distribution | 2006-11-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008497 | 400832689 | Guy | HFTD Tier 2 | Distribution | 2007-08-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008498 | 400833026 | High Sign | HFTD Tier 2 | Distribution | 2006-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008499 | 400833052 | Molding | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008500 | 400833068 | Molding | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008501 | 400833200 | Molding | HFTD Tier 2 | Distribution | 2007-02-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008502 | 400833224 | Molding | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008503 | 400833236 | Molding | HFTD Tier 3 | Distribution | 2003-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008504 | 400833403 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008505 | 400833451 | High Sign | HFTD Tier 2 | Distribution | 2006-09-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008506 | 400833499 | High Sign | HFTD Tier 2 | Distribution | 2007-07-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008507 | 400834087 | Molding | HFTD Tier 3 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008508 | 400834165 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-07-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008509 | 400834254 | Molding | HFTD Tier 2 | Distribution | 2006-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008510 | 400834311 | High Sign | HFTD Tier 2 | Distribution | 2006-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008511 | 400834472 | High Sign | HFTD Tier 3 | Distribution | 2006-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008512 | 400834542 | Molding | HFTD Tier 2 | Distribution | 2003-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008513 | 400834613 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008514 | 400834844 | Molding | HFTD Tier 2 | Distribution | 2006-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008515 | 400834878 | Molding | HFTD Tier 2 | Distribution | 2006-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008516 | 400835348 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008517 | 400835392 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008518 | 400835656 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008519 | 400835898 | High Sign | HFTD Tier 2 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008520 | 400836018 | Molding | HFTD Tier 2 | Distribution | 2002-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008521 | 400836091 | High Sign | HFTD Tier 2 | Distribution | 2006-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008522 | 400836125 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008523 | 400836148 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008524 | 400836203 | High Sign | HFTD Tier 2 | Distribution | 2002-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008525 | 400836255 | Guy | HFTD Tier 3 | Distribution | 2006-12-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008526 | 400836327 | Insulator | HFTD Tier 3 | Distribution | 2002-01-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008527 | 400836431 | Molding | HFTD Tier 2 | Distribution | 2002-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008528 | 400836527 | Molding | HFTD Tier 2 | Distribution | 2002-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008529 | 400836556 | High Sign | HFTD Tier 3 | Distribution | 2003-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008530 | 400836571 | Guy | HFTD Tier 2 | Distribution | 2006-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008531 | 400836635 | High Sign | HFTD Tier 2 | Distribution | 2001-12-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008532 | 400836680 | High Sign | HFTD Tier 3 | Distribution | 2006-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008533 | 400836686 | Molding | HFTD Tier 3 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008534 | 400836900 | Ground | HFTD Tier 2 | Distribution | 2002-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008535 | 400836940 | High Sign | HFTD Tier 3 | Distribution | 2008-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008536 | 400836959 | High Sign | HFTD Tier 3 | Distribution | 2006-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008537 | 400837115 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008538 | 400837120 | High Sign | HFTD Tier 3 | Distribution | 2006-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008539 | 400837374 | High Sign | HFTD Tier 2 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008540 | 400837529 | Molding | HFTD Tier 2 | Distribution | 2006-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008541 | 400837534 | High Sign | HFTD Tier 3 | Distribution | 2007-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008542 | 400837574 | Molding | HFTD Tier 2 | Distribution | 2006-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008543 | 400837799 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008544 | 400837809 | High Sign | HFTD Tier 2 | Distribution | 2006-11-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008545 | 400837907 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008546 | 400837966 | Guy | HFTD Tier 2 | Distribution | 2005-11-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008547 | 400838026 | Molding | HFTD Tier 2 | Distribution | 2007-06-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008548 | 400838587 | Molding | HFTD Tier 2 | Distribution | 2007-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008549 | 400838737 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008550 | 400838909 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008551 | 400838952 | Cable/Conductor | HFTD Tier 3 | Distribution | 2006-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008552 | 400839008 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008553 | 400839233 | High Sign | HFTD Tier 2 | Distribution | 2001-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008554 | 400839356 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008555 | 400839754 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008556 | 400839827 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008557 | 400839838 | High Sign | HFTD Tier 2 | Distribution | 2006-12-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008558 | 400839843 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008559 | 400839879 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008560 | 400839887 | Guy | HFTD Tier 3 | Distribution | 2007-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008561 | 400839910 | Guy | HFTD Tier 2 | Distribution | 2006-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008562 | 400839992 | Molding | HFTD Tier 3 | Distribution | 2006-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008563 | 400840035 | High Sign | HFTD Tier 3 | Distribution | 2007-02-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008564 | 400840113 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008565 | 400840135 | High Sign | HFTD Tier 3 | Distribution | 2006-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008566 | 400840288 | Molding | HFTD Tier 3 | Distribution | 2006-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008567 | 400840380 | High Sign | HFTD Tier 3 | Distribution | 2002-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008568 | 400840581 | Riser/Conduit | HFTD Tier 3 | Distribution | 2001-11-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008569 | 400840849 | High Sign | HFTD Tier 3 | Distribution | 2007-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008570 | 400840893 | Molding | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008571 | 400840936 | Molding | HFTD Tier 2 | Distribution | 2006-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008572 | 400841150 | Molding | HFTD Tier 2 | Distribution | 2006-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008573 | 400841170 | Molding | HFTD Tier 3 | Distribution | 2003-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008574 | 400841171 | High Sign | HFTD Tier 3 | Distribution | 2006-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008575 | 400841430 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008576 | 400841886 | High Sign | HFTD Tier 3 | Distribution | 2006-06-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008577 | 400841933 | Guy | HFTD Tier 3 | Distribution | 2007-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008578 | 400842069 | High Sign | HFTD Tier 2 | Distribution | 2006-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008579 | 400842201 | High Sign | HFTD Tier 2 | Distribution | 2003-08-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008580 | 400842296 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008581 | 400842337 | Molding | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008582 | 400842524 | Molding | HFTD Tier 2 | Distribution | 2005-11-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008583 | 400842615 | High Sign | HFTD Tier 3 | Distribution | 2007-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008584 | 400842661 | High Sign | HFTD Tier 3 | Distribution | 2006-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008585 | 400842703 | Molding | HFTD Tier 2 | Distribution | 2007-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008586 | 400842808 | High Sign | HFTD Tier 3 | Distribution | 2007-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008587 | 400842851 | High Sign | HFTD Tier 2 | Distribution | 2006-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008588 | 400842873 | Molding | HFTD Tier 2 | Distribution | 2005-12-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008589 | 400843017 | Molding | HFTD Tier 3 | Distribution | 2003-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008590 | 400843089 | Molding | HFTD Tier 2 | Distribution | 2006-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008591 | 400843112 | High Sign | HFTD Tier 2 | Distribution | 2002-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008592 | 400843143 | Molding | HFTD Tier 3 | Distribution | 2006-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008593 | 400843298 | High Sign | HFTD Tier 2 | Distribution | 2007-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008594 | 400843449 | High Sign | HFTD Tier 2 | Distribution | 2002-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008595 | 400843634 | High Sign | HFTD Tier 3 | Distribution | 2002-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008596 | 400843798 | Guy | HFTD Tier 3 | Distribution | 2007-06-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008597 | 400844022 | High Sign | HFTD Tier 2 | Distribution | 2006-08-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008598 | 400844285 | High Sign | HFTD Tier 3 | Distribution | 2006-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008599 | 400844312 | High Sign | HFTD Tier 2 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008600 | 400844327 | Molding | HFTD Tier 2 | Distribution | 2007-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008601 | 400844421 | Molding | HFTD Tier 3 | Distribution | 2006-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008602 | 400844448 | Molding | HFTD Tier 3 | Distribution | 2006-10-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008603 | 400844599 | High Sign | HFTD Tier 3 | Distribution | 2007-11-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008604 | 400844630 | Molding | HFTD Tier 2 | Distribution | 2007-11-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008605 | 400844638 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008606 | 400844787 | Guy | HFTD Tier 3 | Distribution | 2008-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008607 | 400844932 | High Sign | HFTD Tier 3 | Distribution | 2003-09-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008608 | 400845170 | Molding | HFTD Tier 3 | Distribution | 2007-11-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008609 | 400845171 | High Sign | HFTD Tier 3 | Distribution | 2003-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008610 | 400845217 | High Sign | HFTD Tier 2 | Distribution | 2003-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008611 | 400845225 | Molding | HFTD Tier 3 | Distribution | 2006-06-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008612 | 400845301 | Molding | HFTD Tier 2 | Distribution | 2007-02-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008613 | 400845317 | High Sign | HFTD Tier 3 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008614 | 400845355 | Molding | HFTD Tier 2 | Distribution | 2007-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008615 | 400845380 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008616 | 400845435 | High Sign | HFTD Tier 3 | Distribution | 2006-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008617 | 400845520 | High Sign | HFTD Tier 2 | Distribution | 2002-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008618 | 400845531 | Molding | HFTD Tier 2 | Distribution | 2006-01-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008619 | 400845563 | Molding | HFTD Tier 2 | Distribution | 2008-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008620 | 400845732 | High Sign | HFTD Tier 2 | Distribution | 2007-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008621 | 400845762 | High Sign | HFTD Tier 2 | Distribution | 2007-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008622 | 400845857 | Molding | HFTD Tier 3 | Distribution | 2007-08-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008623 | 400846018 | Molding | HFTD Tier 2 | Distribution | 2002-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008624 | 400846129 | High Sign | HFTD Tier 2 | Distribution | 2006-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008625 | 400846136 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008626 | 400846233 | Guy | HFTD Tier 2 | Distribution | 2006-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008627 | 400846457 | High Sign | HFTD Tier 2 | Distribution | 2006-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008628 | 400846519 | Molding | HFTD Tier 2 | Distribution | 2006-12-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008629 | 400846568 | Molding | HFTD Tier 2 | Distribution | 2002-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008630 | 400846943 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008631 | 400847061 | High Sign | HFTD Tier 2 | Distribution | 2006-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008632 | 400847154 | Guy | HFTD Tier 2 | Distribution | 2003-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008633 | 400847286 | High Sign | HFTD Tier 3 | Distribution | 2001-11-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008634 | 400847322 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2008-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008635 | 400847344 | Molding | HFTD Tier 2 | Distribution | 2006-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008636 | 400847473 | High Sign | HFTD Tier 2 | Distribution | 2002-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008637 | 400847635 | Molding | HFTD Tier 2 | Distribution | 2002-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008638 | 400847777 | Molding | HFTD Tier 3 | Distribution | 2006-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008639 | 400847946 | High Sign | HFTD Tier 3 | Distribution | 2007-10-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008640 | 400848119 | Guy | HFTD Tier 2 | Distribution | 2007-10-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008641 | 400848142 | High Sign | HFTD Tier 3 | Distribution | 2002-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008642 | 400848244 | High Sign | HFTD Tier 2 | Distribution | 2006-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008643 | 400848266 | Cable/Conductor | HFTD Tier 2 | Distribution | 2007-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008644 | 400848283 | High Sign | HFTD Tier 3 | Distribution | 2001-11-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008645 | 400848311 | Molding | HFTD Tier 3 | Distribution | 2007-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008646 | 400848336 | High Sign | HFTD Tier 2 | Distribution | 2002-02-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008647 | 400848453 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008648 | 400848529 | High Sign | HFTD Tier 3 | Distribution | 2001-01-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008649 | 400848584 | Molding | HFTD Tier 2 | Distribution | 2002-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008650 | 400848759 | Molding | HFTD Tier 2 | Distribution | 2002-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008651 | 400848787 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008652 | 400848931 | Molding | HFTD Tier 2 | Distribution | 2006-10-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008653 | 400849038 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-05-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008654 | 400849197 | High Sign | HFTD Tier 2 | Distribution | 2002-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008655 | 400849305 | Molding | HFTD Tier 2 | Distribution | 2007-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008656 | 400849322 | High Sign | HFTD Tier 2 | Distribution | 2007-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008657 | 400849551 | Molding | HFTD Tier 2 | Distribution | 2006-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008658 | 400849557 | High Sign | HFTD Tier 3 | Distribution | 2007-02-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008659 | 400849812 | High Sign | HFTD Tier 2 | Distribution | 2003-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008660 | 400849822 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008661 | 400849833 | Molding | HFTD Tier 3 | Distribution | 2006-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008662 | 400849867 | High Sign | HFTD Tier 2 | Distribution | 2002-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008663 | 400850062 | High Sign | HFTD Tier 2 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008664 | 400850079 | Molding | HFTD Tier 3 | Distribution | 2007-11-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008665 | 400850095 | Molding | HFTD Tier 3 | Distribution | 2007-11-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008666 | 400850134 | Molding | HFTD Tier 3 | Distribution | 2006-05-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008667 | 400850173 | Molding | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008668 | 400850303 | High Sign | HFTD Tier 2 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008669 | 400850367 | High Sign | HFTD Tier 2 | Distribution | 2006-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008670 | 400850628 | Molding | HFTD Tier 3 | Distribution | 2015-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008671 | 400850656 | High Sign | HFTD Tier 3 | Distribution | 2007-11-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008672 | 400850689 | Insulator | HFTD Tier 2 | Distribution | 2005-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008673 | 400850777 | High Sign | HFTD Tier 3 | Distribution | 2007-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008674 | 400850839 | Hardware/Framing | HFTD Tier 3 | Distribution | 2003-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008675 | 400851078 | High Sign | HFTD Tier 2 | Distribution | 2002-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008676 | 400851203 | Molding | HFTD Tier 3 | Distribution | 2006-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008677 | 400851427 | Molding | HFTD Tier 3 | Distribution | 2006-08-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008678 | 400851479 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008679 | 400851490 | Molding | HFTD Tier 2 | Distribution | 2002-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008680 | 400851671 | High Sign | HFTD Tier 2 | Distribution | 2003-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008681 | 400851701 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008682 | 400851708 | Molding | HFTD Tier 3 | Distribution | 2007-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008683 | 400851718 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008684 | 400851746 | Hardware/Framing | HFTD Tier 3 | Distribution | 2003-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008685 | 400851968 | Molding | HFTD Tier 2 | Distribution | 2007-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008686 | 400852066 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008687 | 400852098 | High Sign | HFTD Tier 3 | Distribution | 2001-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008688 | 400852246 | High Sign | HFTD Tier 2 | Distribution | 2006-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008689 | 400852262 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008690 | 400852483 | High Sign | HFTD Tier 3 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008691 | 400852505 | High Sign | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008692 | 400852576 | Molding | HFTD Tier 2 | Distribution | 2006-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008693 | 400852610 | High Sign | HFTD Tier 3 | Distribution | 2006-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008694 | 400852639 | Molding | HFTD Tier 3 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008695 | 400852697 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008696 | 400852723 | Molding | HFTD Tier 2 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008697 | 400852810 | Molding | HFTD Tier 2 | Distribution | 2006-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008698 | 400852831 | Molding | HFTD Tier 2 | Distribution | 2003-09-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008699 | 400852844 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008700 | 400852845 | High Sign | HFTD Tier 2 | Distribution | 2007-10-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008701 | 400853098 | Molding | HFTD Tier 2 | Distribution | 2006-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008702 | 400853216 | Molding | HFTD Tier 2 | Distribution | 2007-07-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008703 | 400853519 | Molding | HFTD Tier 3 | Distribution | 2007-07-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008704 | 400853521 | High Sign | HFTD Tier 2 | Distribution | 2003-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008705 | 400853614 | Molding | HFTD Tier 3 | Distribution | 2006-08-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008706 | 400853803 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008707 | 400853861 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008708 | 400853866 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008709 | 400854254 | High Sign | HFTD Tier 3 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008710 | 400854257 | High Sign | HFTD Tier 2 | Distribution | 2007-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008711 | 400854324 | High Sign | HFTD Tier 3 | Distribution | 2007-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008712 | 400854338 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2007-12-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008713 | 400854419 | Riser/Conduit | HFTD Tier 2 | Distribution | 2006-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008714 | 400854511 | Molding | HFTD Tier 3 | Distribution | 2006-08-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008715 | 400854517 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008716 | 400854606 | High Sign | HFTD Tier 2 | Distribution | 2006-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008717 | 400854643 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008718 | 400854684 | Molding | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008719 | 400854700 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008720 | 400854780 | Molding | HFTD Tier 2 | Distribution | 2006-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008721 | 400854787 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008722 | 400854803 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008723 | 400854965 | Molding | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008724 | 400855035 | Guy | HFTD Tier 2 | Distribution | 2007-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008725 | 400855091 | Molding | HFTD Tier 2 | Distribution | 2006-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008726 | 400855443 | Molding | HFTD Tier 3 | Distribution | 2006-10-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008727 | 400855449 | Molding | HFTD Tier 3 | Distribution | 2007-02-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008728 | 400855634 | Molding | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008729 | 400855746 | Molding | HFTD Tier 2 | Distribution | 2002-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008730 | 400855755 | Molding | HFTD Tier 2 | Distribution | 2006-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008731 | 400855757 | Molding | HFTD Tier 2 | Distribution | 2007-08-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008732 | 400855764 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008733 | 400855943 | High Sign | HFTD Tier 3 | Distribution | 2002-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008734 | 400856073 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008735 | 400856125 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008736 | 400856128 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008737 | 400856163 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008738 | 400856235 | Molding | HFTD Tier 2 | Distribution | 2007-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008739 | 400856276 | High Sign | HFTD Tier 3 | Distribution | 2006-09-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008740 | 400856286 | Molding | HFTD Tier 3 | Distribution | 2001-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008741 | 400856334 | High Sign | HFTD Tier 3 | Distribution | 2007-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008742 | 400856366 | High Sign | HFTD Tier 3 | Distribution | 2002-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008743 | 400856601 | Guy | HFTD Tier 2 | Distribution | 2007-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008744 | 400856602 | High Sign | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008745 | 400856604 | High Sign | HFTD Tier 2 | Distribution | 2002-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008746 | 400856642 | Molding | HFTD Tier 3 | Distribution | 2007-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008747 | 400856652 | High Sign | HFTD Tier 2 | Distribution | 2005-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008748 | 400856709 | High Sign | HFTD Tier 3 | Distribution | 2005-12-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008749 | 400856763 | High Sign | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008750 | 400856853 | Molding | HFTD Tier 2 | Distribution | 2006-01-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008751 | 400856865 | Molding | HFTD Tier 2 | Distribution | 2002-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008752 | 400857288 | Molding | HFTD Tier 3 | Distribution | 2007-07-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008753 | 400857419 | High Sign | HFTD Tier 3 | Distribution | 2006-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008754 | 400857512 | Molding | HFTD Tier 2 | Distribution | 2007-08-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008755 | 400858002 | High Sign | HFTD Tier 2 | Distribution | 2007-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008756 | 400858103 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008757 | 400858112 | High Sign | HFTD Tier 3 | Distribution | 2006-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008758 | 400858125 | High Sign | HFTD Tier 3 | Distribution | 2008-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008759 | 400858143 | Molding | HFTD Tier 3 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008760 | 400858174 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008761 | 400858467 | Molding | HFTD Tier 2 | Distribution | 2007-10-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008762 | 400858537 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2007-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008763 | 400858759 | Molding | HFTD Tier 2 | Distribution | 2006-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008764 | 400858790 | High Sign | HFTD Tier 3 | Distribution | 2006-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008765 | 400858897 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008766 | 400858960 | Molding | HFTD Tier 2 | Distribution | 2006-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008767 | 400859002 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008768 | 400859008 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008769 | 400859081 | Molding | HFTD Tier 3 | Distribution | 2007-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008770 | 400859309 | Guy | HFTD Tier 3 | Distribution | 2007-07-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008771 | 400859384 | High Sign | HFTD Tier 2 | Distribution | 2003-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008772 | 400859563 | Molding | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008773 | 400859682 | Molding | HFTD Tier 2 | Distribution | 2006-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008774 | 400859721 | Guy | HFTD Tier 3 | Distribution | 2007-02-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008775 | 400859762 | High Sign | HFTD Tier 3 | Distribution | 2008-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008776 | 400859765 | High Sign | HFTD Tier 3 | Distribution | 2002-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008777 | 400859917 | Molding | HFTD Tier 2 | Distribution | 2006-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008778 | 400860123 | Riser/Conduit | HFTD Tier 3 | Distribution | 2015-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008779 | 400860149 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008780 | 400860186 | High Sign | HFTD Tier 2 | Distribution | 2001-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008781 | 400860250 | Molding | HFTD Tier 2 | Distribution | 2003-09-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008782 | 400860376 | High Sign | HFTD Tier 2 | Distribution | 2007-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008783 | 400860706 | High Sign | HFTD Tier 3 | Distribution | 2005-12-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008784 | 400860736 | Molding | HFTD Tier 2 | Distribution | 2006-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008785 | 400860787 | High Sign | HFTD Tier 2 | Distribution | 2006-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008786 | 400860841 | Molding | HFTD Tier 3 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008787 | 400860981 | Guy | HFTD Tier 3 | Distribution | 2006-08-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008788 | 400861031 | High Sign | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008789 | 400861083 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008790 | 400861158 | High Sign | HFTD Tier 3 | Distribution | 2001-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008791 | 400861232 | High Sign | HFTD Tier 2 | Distribution | 2002-04-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008792 | 400861259 | Guy | HFTD Tier 2 | Distribution | 2007-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008793 | 400861313 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008794 | 400861411 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008795 | 400861587 | High Sign | HFTD Tier 3 | Distribution | 2001-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008796 | 400861607 | Guy | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008797 | 400861733 | High Sign | HFTD Tier 2 | Distribution | 2007-07-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008798 | 400861741 | High Sign | HFTD Tier 3 | Distribution | 2006-05-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008799 | 400861834 | High Sign | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008800 | 400861899 | High Sign | HFTD Tier 3 | Distribution | 2006-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008801 | 400861908 | Molding | HFTD Tier 3 | Distribution | 2006-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008802 | 400861910 | Molding | HFTD Tier 2 | Distribution | 2006-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008803 | 400861927 | Molding | HFTD Tier 3 | Distribution | 2006-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008804 | 400862069 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008805 | 400862122 | High Sign | HFTD Tier 3 | Distribution | 2002-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008806 | 400862347 | High Sign | HFTD Tier 2 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008807 | 400862616 | Cable/Conductor | HFTD Tier 3 | Distribution | 2008-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008808 | 400862633 | Molding | HFTD Tier 2 | Distribution | 2005-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008809 | 400862753 | High Sign | HFTD Tier 2 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008810 | 400862803 | Molding | HFTD Tier 2 | Distribution | 2006-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008811 | 400862855 | High Sign | HFTD Tier 2 | Distribution | 2002-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008812 | 400862862 | High Sign | HFTD Tier 3 | Distribution | 2007-07-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008813 | 400862889 | High Sign | HFTD Tier 2 | Distribution | 2006-03-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008814 | 400862898 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-12-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008815 | 400862968 | Molding | HFTD Tier 3 | Distribution | 2006-10-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008816 | 400863206 | Molding | HFTD Tier 2 | Distribution | 2005-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008817 | 400863307 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008818 | 400863398 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008819 | 400863722 | Molding | HFTD Tier 3 | Distribution | 2008-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008820 | 400863956 | High Sign | HFTD Tier 2 | Distribution | 2007-02-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008821 | 400864008 | Guy | HFTD Tier 3 | Distribution | 2007-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008822 | 400864077 | High Sign | HFTD Tier 2 | Distribution | 2006-11-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008823 | 400864110 | High Sign | HFTD Tier 2 | Distribution | 2002-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008824 | 400864111 | High Sign | HFTD Tier 2 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008825 | 400864158 | High Sign | HFTD Tier 3 | Distribution | 2002-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008826 | 400864485 | Molding | HFTD Tier 2 | Distribution | 2002-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008827 | 400864557 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008828 | 400864604 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2003-05-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008829 | 400864669 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008830 | 400864693 | Molding | HFTD Tier 3 | Distribution | 2006-09-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008831 | 400864749 | Molding | HFTD Tier 3 | Distribution | 2002-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008832 | 400864770 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008833 | 400864912 | Molding | HFTD Tier 2 | Distribution | 2006-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008834 | 400865026 | High Sign | HFTD Tier 2 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008835 | 400865503 | Guy | HFTD Tier 3 | Distribution | 2007-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008836 | 400865587 | High Sign | HFTD Tier 2 | Distribution | 2002-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008837 | 400865593 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008838 | 400865699 | High Sign | HFTD Tier 3 | Distribution | 2006-12-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008839 | 400865940 | Molding | HFTD Tier 3 | Distribution | 2005-12-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008840 | 400866076 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008841 | 400866271 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008842 | 400866279 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008843 | 400866322 | Molding | HFTD Tier 2 | Distribution | 2006-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008844 | 400866323 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008845 | 400866394 | High Sign | HFTD Tier 2 | Distribution | 2006-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008846 | 400866445 | Molding | HFTD Tier 2 | Distribution | 2006-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008847 | 400866728 | High Sign | HFTD Tier 3 | Distribution | 2006-09-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008848 | 400866753 | Molding | HFTD Tier 2 | Distribution | 2007-02-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008849 | 400866879 | High Sign | HFTD Tier 3 | Distribution | 2006-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008850 | 400866915 | Molding | HFTD Tier 3 | Distribution | 2006-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008851 | 400866946 | High Sign | HFTD Tier 2 | Distribution | 2001-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008852 | 400867031 | Insulator | HFTD Tier 2 | Distribution | 2001-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008853 | 400867070 | High Sign | HFTD Tier 2 | Distribution | 2006-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008854 | 400867112 | High Sign | HFTD Tier 3 | Distribution | 2002-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008855 | 400867205 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008856 | 400867479 | Molding | HFTD Tier 3 | Distribution | 2001-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008857 | 400867485 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008858 | 400867580 | High Sign | HFTD Tier 3 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008859 | 400867688 | High Sign | HFTD Tier 2 | Distribution | 2005-12-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008860 | 400867695 | High Sign | HFTD Tier 3 | Distribution | 2007-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008861 | 400867857 | Molding | HFTD Tier 2 | Distribution | 2001-08-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008862 | 400867968 | Molding | HFTD Tier 3 | Distribution | 2002-02-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008863 | 400867974 | Cable/Conductor | HFTD Tier 2 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008864 | 400867984 | Molding | HFTD Tier 3 | Distribution | 2007-12-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008865 | 400867989 | High Sign | HFTD Tier 3 | Distribution | 2006-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008866 | 400868028 | High Sign | HFTD Tier 3 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008867 | 400868114 | High Sign | HFTD Tier 3 | Distribution | 2001-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008868 | 400868250 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008869 | 400868325 | High Sign | HFTD Tier 3 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008870 | 400868340 | High Sign | HFTD Tier 3 | Distribution | 2007-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008871 | 400868399 | Molding | HFTD Tier 3 | Distribution | 2007-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008872 | 400868465 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008873 | 400868513 | High Sign | HFTD Tier 3 | Distribution | 2007-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008874 | 400868530 | Molding | HFTD Tier 2 | Distribution | 2006-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008875 | 400868533 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008876 | 400868549 | Molding | HFTD Tier 3 | Distribution | 2006-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008877 | 400868603 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008878 | 400868618 | Cable/Conductor | HFTD Tier 2 | Distribution | 2002-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008879 | 400868648 | Molding | HFTD Tier 3 | Distribution | 2001-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008880 | 400868678 | High Sign | HFTD Tier 2 | Distribution | 2002-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008881 | 400868733 | Hardware/Framing | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008882 | 400868824 | Insulator | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008883 | 400868825 | High Sign | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008884 | 400868833 | Molding | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008885 | 400868839 | Molding | HFTD Tier 3 | Distribution | 2003-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008886 | 400868938 | High Sign | HFTD Tier 3 | Distribution | 2002-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008887 | 400868990 | Molding | HFTD Tier 2 | Distribution | 2007-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008888 | 400869095 | Molding | HFTD Tier 2 | Distribution | 2006-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008889 | 400869142 | Molding | HFTD Tier 2 | Distribution | 2006-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008890 | 400869192 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008891 | 400869271 | High Sign | HFTD Tier 2 | Distribution | 2007-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008892 | 400869345 | High Sign | HFTD Tier 2 | Distribution | 2005-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008893 | 400869506 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008894 | 400869657 | High Sign | HFTD Tier 2 | Distribution | 2006-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008895 | 400869662 | High Sign | HFTD Tier 3 | Distribution | 2001-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008896 | 400869675 | High Sign | HFTD Tier 3 | Distribution | 2007-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008897 | 400869773 | Riser/Conduit | HFTD Tier 2 | Distribution | 2006-01-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008898 | 400869820 | High Sign | HFTD Tier 2 | Distribution | 2005-12-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008899 | 400869884 | Molding | HFTD Tier 3 | Distribution | 2006-06-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008900 | 400870136 | High Sign | HFTD Tier 2 | Distribution | 2005-12-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008901 | 400870179 | Molding | HFTD Tier 2 | Distribution | 2002-02-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008902 | 400870287 | High Sign | HFTD Tier 3 | Distribution | 2007-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008903 | 400870296 | High Sign | HFTD Tier 2 | Distribution | 2001-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008904 | 400870417 | Molding | HFTD Tier 3 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008905 | 400870611 | Molding | HFTD Tier 2 | Distribution | 2006-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008906 | 400870638 | Molding | HFTD Tier 3 | Distribution | 2003-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008907 | 400870648 | High Sign | HFTD Tier 3 | Distribution | 2002-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008908 | 400870710 | High Sign | HFTD Tier 3 | Distribution | 2006-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008909 | 400870753 | High Sign | HFTD Tier 2 | Distribution | 2006-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008910 | 400870830 | Molding | HFTD Tier 2 | Distribution | 2006-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008911 | 400870899 | High Sign | HFTD Tier 3 | Distribution | 2003-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008912 | 400871134 | High Sign | HFTD Tier 2 | Distribution | 2006-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008913 | 400871239 | High Sign | HFTD Tier 2 | Distribution | 2006-12-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008914 | 400871350 | Hardware/Framing | HFTD Tier 3 | Distribution | 2002-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008915 | 400871395 | High Sign | HFTD Tier 2 | Distribution | 2002-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008916 | 400871410 | High Sign | HFTD Tier 2 | Distribution | 2006-11-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008917 | 400871416 | High Sign | HFTD Tier 3 | Distribution | 2002-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008918 | 400871437 | High Sign | HFTD Tier 3 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008919 | 400871465 | High Sign | HFTD Tier 3 | Distribution | 2006-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008920 | 400871573 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008921 | 400871697 | Cable/Conductor | HFTD Tier 2 | Distribution | 2007-12-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008922 | 400871734 | Guy | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008923 | 400871761 | High Sign | HFTD Tier 2 | Distribution | 2007-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008924 | 400871773 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008925 | 400871838 | Molding | HFTD Tier 2 | Distribution | 2007-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008926 | 400871930 | Guy | HFTD Tier 3 | Distribution | 2002-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008927 | 400872117 | High Sign | HFTD Tier 3 | Distribution | 2001-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008928 | 400872127 | High Sign | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008929 | 400872161 | High Sign | HFTD Tier 3 | Distribution | 2007-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008930 | 400872168 | Guy | HFTD Tier 2 | Distribution | 2007-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008931 | 400872181 | High Sign | HFTD Tier 2 | Distribution | 2006-01-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008932 | 400872308 | High Sign | HFTD Tier 2 | Distribution | 2007-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008933 | 400872378 | Molding | HFTD Tier 3 | Distribution | 2007-08-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008934 | 400872443 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008935 | 400872527 | Molding | HFTD Tier 2 | Distribution | 2006-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008936 | 400872573 | Molding | HFTD Tier 2 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008937 | 400872611 | Molding | HFTD Tier 3 | Distribution | 2003-07-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008938 | 400872673 | Molding | HFTD Tier 3 | Distribution | 2002-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008939 | 400872742 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008940 | 400872747 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008941 | 400872900 | High Sign | HFTD Tier 3 | Distribution | 2006-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008942 | 400872907 | High Sign | HFTD Tier 2 | Distribution | 2007-05-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008943 | 400872939 | Molding | HFTD Tier 2 | Distribution | 2006-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008944 | 400872953 | High Sign | HFTD Tier 2 | Distribution | 2002-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008945 | 400873055 | High Sign | HFTD Tier 2 | Distribution | 2005-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008946 | 400873179 | High Sign | HFTD Tier 2 | Distribution | 2006-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008947 | 400873315 | High Sign | HFTD Tier 3 | Distribution | 2001-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008948 | 400873783 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-07-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008949 | 400873795 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008950 | 400873898 | High Sign | HFTD Tier 2 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008951 | 400874027 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008952 | 400874036 | High Sign | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008953 | 400874051 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008954 | 400874182 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008955 | 400874191 | High Sign | HFTD Tier 3 | Distribution | 2007-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008956 | 400874195 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2003-07-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008957 | 400874199 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008958 | 400874221 | Molding | HFTD Tier 3 | Distribution | 2002-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008959 | 400874252 | Ground | HFTD Tier 3 | Distribution | 2005-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008960 | 400874257 | High Sign | HFTD Tier 3 | Distribution | 2005-12-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008961 | 400874260 | High Sign | HFTD Tier 2 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008962 | 400874281 | High Sign | HFTD Tier 2 | Distribution | 2001-11-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008963 | 400874602 | Guy | HFTD Tier 3 | Distribution | 2006-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008964 | 400874681 | Riser/Conduit | HFTD Tier 2 | Distribution | 2006-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008965 | 400874726 | High Sign | HFTD Tier 2 | Distribution | 2006-11-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008966 | 400874885 | High Sign | HFTD Tier 3 | Distribution | 2006-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008967 | 400874946 | High Sign | HFTD Tier 2 | Distribution | 2006-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008968 | 400874963 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-05-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008969 | 400874989 | High Sign | HFTD Tier 3 | Distribution | 2007-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008970 | 400875030 | High Sign | HFTD Tier 3 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008971 | 400875035 | Guy | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008972 | 400875041 | High Sign | HFTD Tier 2 | Distribution | 2002-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008973 | 400875052 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008974 | 400875150 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008975 | 400875179 | Molding | HFTD Tier 2 | Distribution | 2007-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008976 | 400875259 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2003-07-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008977 | 400875298 | High Sign | HFTD Tier 3 | Distribution | 2007-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008978 | 400875299 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008979 | 400875308 | High Sign | HFTD Tier 3 | Distribution | 2002-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008980 | 400875439 | Molding | HFTD Tier 3 | Distribution | 2006-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008981 | 400875467 | Molding | HFTD Tier 2 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008982 | 400875530 | Molding | HFTD Tier 3 | Distribution | 2006-07-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008983 | 400875798 | Guy | HFTD Tier 2 | Distribution | 2007-02-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008984 | 400875879 | Molding | HFTD Tier 3 | Distribution | 2003-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008985 | 400876024 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008986 | 400876049 | Riser/Conduit | HFTD Tier 3 | Distribution | 2006-11-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008987 | 400876153 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008988 | 400876171 | High Sign | HFTD Tier 2 | Distribution | 2001-12-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008989 | 400876247 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008990 | 400876267 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008991 | 400876275 | Molding | HFTD Tier 3 | Distribution | 2006-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008992 | 400876469 | High Sign | HFTD Tier 3 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008993 | 400876504 | High Sign | HFTD Tier 3 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008994 | 400876615 | Molding | HFTD Tier 3 | Distribution | 2002-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008995 | 400876789 | High Sign | HFTD Tier 2 | Distribution | 2006-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008996 | 400876891 | High Sign | HFTD Tier 3 | Distribution | 2006-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008997 | 400877026 | Molding | HFTD Tier 3 | Distribution | 2003-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008998 | 400877027 | High Sign | HFTD Tier 2 | Distribution | 2007-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130008999 | 400877065 | High Sign | HFTD Tier 3 | Distribution | 2006-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009000 | 400877138 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009001 | 400877175 | Molding | HFTD Tier 3 | Distribution | 2002-03-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009002 | 400877186 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-06-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009003 | 400877191 | High Sign | HFTD Tier 2 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009004 | 400877377 | High Sign | HFTD Tier 3 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009005 | 400877456 | Molding | HFTD Tier 3 | Distribution | 2007-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009006 | 400877485 | Molding | HFTD Tier 2 | Distribution | 2005-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009007 | 400877535 | High Sign | HFTD Tier 2 | Distribution | 2005-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009008 | 400877577 | Guy | HFTD Tier 3 | Distribution | 2007-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009009 | 400877805 | High Sign | HFTD Tier 2 | Distribution | 2001-08-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009010 | 400878146 | High Sign | HFTD Tier 2 | Distribution | 2002-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009011 | 400878172 | High Sign | HFTD Tier 2 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009012 | 400878216 | Molding | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009013 | 400878223 | Hardware/Framing | HFTD Tier 3 | Distribution | 2002-08-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009014 | 400878231 | Molding | HFTD Tier 3 | Distribution | 2006-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009015 | 400878265 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009016 | 400878313 | Molding | HFTD Tier 2 | Distribution | 2006-07-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009017 | 400878399 | High Sign | HFTD Tier 3 | Distribution | 2002-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009018 | 400878471 | Molding | HFTD Tier 2 | Distribution | 2002-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009019 | 400878566 | High Sign | HFTD Tier 2 | Distribution | 2001-11-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009020 | 400878583 | High Sign | HFTD Tier 3 | Distribution | 2002-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009021 | 400878798 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009022 | 400878830 | Molding | HFTD Tier 3 | Distribution | 2006-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009023 | 400878861 | Molding | HFTD Tier 2 | Distribution | 2006-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009024 | 400878896 | High Sign | HFTD Tier 2 | Distribution | 2006-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009025 | 400878930 | High Sign | HFTD Tier 2 | Distribution | 2007-08-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009026 | 400878945 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009027 | 400879015 | Molding | HFTD Tier 3 | Distribution | 2006-05-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009028 | 400879402 | High Sign | HFTD Tier 2 | Distribution | 2002-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009029 | 400879495 | High Sign | HFTD Tier 3 | Distribution | 2005-11-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009030 | 400879780 | Molding | HFTD Tier 2 | Distribution | 2006-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009031 | 400879783 | High Sign | HFTD Tier 3 | Distribution | 2002-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009032 | 400879837 | High Sign | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009033 | 400879898 | Molding | HFTD Tier 3 | Distribution | 2006-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009034 | 400879971 | Insulator | HFTD Tier 2 | Distribution | 2006-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009035 | 400880094 | Molding | HFTD Tier 3 | Distribution | 2006-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009036 | 400880126 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009037 | 400880236 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009038 | 400880318 | High Sign | HFTD Tier 2 | Distribution | 2002-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009039 | 400880343 | High Sign | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009040 | 400880346 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009041 | 400880428 | High Sign | HFTD Tier 2 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009042 | 400880682 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009043 | 400880690 | Cable/Conductor | HFTD Tier 2 | Distribution | 2007-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009044 | 400880753 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009045 | 400880842 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-06-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009046 | 400880904 | High Sign | HFTD Tier 2 | Distribution | 2007-01-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009047 | 400880968 | Molding | HFTD Tier 2 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009048 | 400880981 | Molding | HFTD Tier 3 | Distribution | 2006-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009049 | 400881029 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009050 | 400881030 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009051 | 400881307 | Molding | HFTD Tier 3 | Distribution | 2002-09-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009052 | 400881393 | High Sign | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009053 | 400881425 | Molding | HFTD Tier 2 | Distribution | 2004-11-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009054 | 400881444 | High Sign | HFTD Tier 2 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009055 | 400881584 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009056 | 400881606 | Molding | HFTD Tier 2 | Distribution | 2002-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009057 | 400881700 | High Sign | HFTD Tier 3 | Distribution | 2006-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009058 | 400881743 | High Sign | HFTD Tier 3 | Distribution | 2006-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009059 | 400881824 | High Sign | HFTD Tier 3 | Distribution | 2005-12-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009060 | 400881908 | Molding | HFTD Tier 2 | Distribution | 2007-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009061 | 400881934 | High Sign | HFTD Tier 3 | Distribution | 2006-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009062 | 400882158 | High Sign | HFTD Tier 3 | Distribution | 2002-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009063 | 400882310 | Molding | HFTD Tier 3 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009064 | 400882354 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009065 | 400882394 | High Sign | HFTD Tier 3 | Distribution | 2002-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009066 | 400882443 | Molding | HFTD Tier 3 | Distribution | 2006-08-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009067 | 400882587 | Molding | HFTD Tier 3 | Distribution | 2006-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009068 | 400882928 | Molding | HFTD Tier 3 | Distribution | 2007-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009069 | 400882964 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009070 | 400882970 | High Sign | HFTD Tier 3 | Distribution | 2006-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009071 | 400883011 | Molding | HFTD Tier 3 | Distribution | 2006-08-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009072 | 400883302 | High Sign | HFTD Tier 2 | Distribution | 2006-11-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009073 | 400883365 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2003-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009074 | 400883392 | Molding | HFTD Tier 2 | Distribution | 2002-02-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009075 | 400883496 | High Sign | HFTD Tier 2 | Distribution | 2007-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009076 | 400883542 | High Sign | HFTD Tier 2 | Distribution | 2007-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009077 | 400883559 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-01-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009078 | 400883683 | High Sign | HFTD Tier 3 | Distribution | 2006-03-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009079 | 400883684 | Riser/Conduit | HFTD Tier 3 | Distribution | 2005-11-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009080 | 400883708 | Molding | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009081 | 400883779 | High Sign | HFTD Tier 3 | Distribution | 2005-12-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009082 | 400883796 | Molding | HFTD Tier 3 | Distribution | 2002-04-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009083 | 400883813 | High Sign | HFTD Tier 3 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009084 | 400883847 | High Sign | HFTD Tier 3 | Distribution | 2001-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009085 | 400883860 | High Sign | HFTD Tier 2 | Distribution | 2006-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009086 | 400883896 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009087 | 400883902 | Molding | HFTD Tier 3 | Distribution | 2006-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009088 | 400883961 | High Sign | HFTD Tier 3 | Distribution | 2006-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009089 | 400883995 | Molding | HFTD Tier 2 | Distribution | 2006-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009090 | 400883996 | High Sign | HFTD Tier 3 | Distribution | 2002-01-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009091 | 400884037 | High Sign | HFTD Tier 3 | Distribution | 2006-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009092 | 400884101 | Molding | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009093 | 400884234 | Riser/Conduit | HFTD Tier 3 | Distribution | 2007-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009094 | 400884348 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009095 | 400884519 | High Sign | HFTD Tier 3 | Distribution | 2007-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009096 | 400884599 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009097 | 400884633 | Molding | HFTD Tier 3 | Distribution | 2006-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009098 | 400884694 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009099 | 400884737 | High Sign | HFTD Tier 3 | Distribution | 2002-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009100 | 400884871 | Riser/Conduit | HFTD Tier 2 | Distribution | 2003-09-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009101 | 400884986 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009102 | 400885005 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009103 | 400885079 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009104 | 400885289 | High Sign | HFTD Tier 2 | Distribution | 2007-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009105 | 400885417 | Molding | HFTD Tier 2 | Distribution | 2006-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009106 | 400885458 | Molding | HFTD Tier 3 | Distribution | 2002-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009107 | 400885483 | Molding | HFTD Tier 2 | Distribution | 2001-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009108 | 400885499 | High Sign | HFTD Tier 3 | Distribution | 2007-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009109 | 400885637 | Insulator | HFTD Tier 3 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009110 | 400885709 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2007-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009111 | 400885768 | Molding | HFTD Tier 2 | Distribution | 2006-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009112 | 400885773 | High Sign | HFTD Tier 2 | Distribution | 2007-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009113 | 400885998 | High Sign | HFTD Tier 2 | Distribution | 2004-10-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009114 | 400886056 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009115 | 400886355 | Molding | HFTD Tier 2 | Distribution | 2006-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009116 | 400886433 | High Sign | HFTD Tier 3 | Distribution | 2008-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009117 | 400886443 | Molding | HFTD Tier 3 | Distribution | 2002-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009118 | 400886493 | Molding | HFTD Tier 3 | Distribution | 2003-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009119 | 400886555 | Molding | HFTD Tier 3 | Distribution | 2006-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009120 | 400886590 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009121 | 400886598 | Molding | HFTD Tier 2 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009122 | 400886631 | Termination | HFTD Tier 3 | Distribution | 2007-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009123 | 400886727 | High Sign | HFTD Tier 2 | Distribution | 2002-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009124 | 400886788 | Molding | HFTD Tier 3 | Distribution | 2007-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009125 | 400886829 | Molding | HFTD Tier 3 | Distribution | 2005-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009126 | 400886873 | Molding | HFTD Tier 3 | Distribution | 2001-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009127 | 400886888 | Molding | HFTD Tier 3 | Distribution | 2002-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009128 | 400887143 | Molding | HFTD Tier 2 | Distribution | 2006-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009129 | 400887272 | High Sign | HFTD Tier 3 | Distribution | 2006-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009130 | 400887304 | Insulator | HFTD Tier 3 | Distribution | 2006-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009131 | 400887496 | High Sign | HFTD Tier 2 | Distribution | 2002-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009132 | 400887503 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009133 | 400887533 | Molding | HFTD Tier 3 | Distribution | 2006-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009134 | 400887575 | High Sign | HFTD Tier 3 | Distribution | 2002-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009135 | 400887639 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009136 | 400887699 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009137 | 400887741 | Guy | HFTD Tier 2 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009138 | 400887759 | Guy | HFTD Tier 3 | Distribution | 2006-11-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009139 | 400887813 | High Sign | HFTD Tier 3 | Distribution | 2006-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009140 | 400888181 | Riser/Conduit | HFTD Tier 2 | Distribution | 2006-11-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009141 | 400888271 | Guy | HFTD Tier 3 | Distribution | 2007-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009142 | 400888378 | Molding | HFTD Tier 3 | Distribution | 2007-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009143 | 400888789 | Guy | HFTD Tier 3 | Distribution | 2006-10-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009144 | 400888998 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009145 | 400889079 | Molding | HFTD Tier 3 | Distribution | 2003-06-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009146 | 400889149 | Molding | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009147 | 400889516 | Molding | HFTD Tier 3 | Distribution | 2001-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009148 | 400889753 | Molding | HFTD Tier 3 | Distribution | 2003-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009149 | 400889848 | Guy | HFTD Tier 2 | Distribution | 2006-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009150 | 400889900 | High Sign | HFTD Tier 3 | Distribution | 2008-03-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009151 | 400889917 | Guy | HFTD Tier 3 | Distribution | 2008-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009152 | 400890026 | Molding | HFTD Tier 3 | Distribution | 2001-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009153 | 400890196 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009154 | 400890268 | High Sign | HFTD Tier 3 | Distribution | 2006-10-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009155 | 400890334 | Molding | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009156 | 400890344 | Molding | HFTD Tier 2 | Distribution | 2007-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009157 | 400890355 | Ground | HFTD Tier 3 | Distribution | 2006-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009158 | 400890527 | Molding | HFTD Tier 2 | Distribution | 2007-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009159 | 400890531 | Guy | HFTD Tier 3 | Distribution | 2002-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009160 | 400890649 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009161 | 400890691 | Guy | HFTD Tier 3 | Distribution | 2006-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009162 | 400890713 | KV Cable Tags | HFTD Tier 3 | Distribution | 2008-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009163 | 400890774 | High Sign | HFTD Tier 3 | Distribution | 2006-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009164 | 400890807 | High Sign | HFTD Tier 3 | Distribution | 2006-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009165 | 400890817 | High Sign | HFTD Tier 2 | Distribution | 2006-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009166 | 400890867 | Guy | HFTD Tier 2 | Distribution | 2006-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009167 | 400891105 | Molding | HFTD Tier 3 | Distribution | 2002-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009168 | 400891315 | Molding | HFTD Tier 2 | Distribution | 2006-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009169 | 400891334 | Molding | HFTD Tier 2 | Distribution | 2006-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009170 | 400891417 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009171 | 400891426 | Guy | HFTD Tier 3 | Distribution | 2007-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009172 | 400891446 | Molding | HFTD Tier 2 | Distribution | 2006-06-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009173 | 400891452 | High Sign | HFTD Tier 3 | Distribution | 2005-11-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009174 | 400891471 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-06-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009175 | 400891520 | Insulator | HFTD Tier 3 | Distribution | 2003-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009176 | 400891602 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009177 | 400891687 | Molding | HFTD Tier 2 | Distribution | 2002-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009178 | 400891729 | High Sign | HFTD Tier 3 | Distribution | 2001-08-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009179 | 400891805 | High Sign | HFTD Tier 2 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009180 | 400891822 | Molding | HFTD Tier 2 | Distribution | 2007-12-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009181 | 400891885 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009182 | 400892021 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009183 | 400892224 | High Sign | HFTD Tier 3 | Distribution | 2002-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009184 | 400892415 | Molding | HFTD Tier 3 | Distribution | 2006-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009185 | 400892439 | Molding | HFTD Tier 3 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009186 | 400892509 | Molding | HFTD Tier 3 | Distribution | 2005-12-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009187 | 400892643 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009188 | 400892679 | KV Cable Tags | HFTD Tier 3 | Distribution | 2008-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009189 | 400892698 | KV Cable Tags | HFTD Tier 3 | Distribution | 2008-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009190 | 400892803 | High Sign | HFTD Tier 3 | Distribution | 2007-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009191 | 400892841 | Guy | HFTD Tier 3 | Distribution | 2007-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009192 | 400892938 | Molding | HFTD Tier 3 | Distribution | 2006-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009193 | 400893133 | Molding | HFTD Tier 3 | Distribution | 2007-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009194 | 400893138 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009195 | 400893290 | High Sign | HFTD Tier 3 | Distribution | 2002-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009196 | 400893332 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009197 | 400893376 | High Sign | HFTD Tier 3 | Distribution | 2002-01-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009198 | 400893396 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009199 | 400893458 | High Sign | HFTD Tier 2 | Distribution | 2006-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009200 | 400893459 | Molding | HFTD Tier 2 | Distribution | 2006-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009201 | 400893619 | Molding | HFTD Tier 2 | Distribution | 2007-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009202 | 400893698 | Molding | HFTD Tier 3 | Distribution | 2001-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009203 | 400893827 | High Sign | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009204 | 400894084 | Molding | HFTD Tier 2 | Distribution | 2006-07-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009205 | 400894225 | Molding | HFTD Tier 3 | Distribution | 2006-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009206 | 400894399 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009207 | 400894406 | Molding | HFTD Tier 3 | Distribution | 2001-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009208 | 400894438 | High Sign | HFTD Tier 2 | Distribution | 2005-11-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009209 | 400894551 | Molding | HFTD Tier 2 | Distribution | 2006-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009210 | 400894552 | High Sign | HFTD Tier 3 | Distribution | 2006-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009211 | 400894851 | High Sign | HFTD Tier 3 | Distribution | 2004-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009212 | 400894897 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009213 | 400895087 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009214 | 400895191 | Molding | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009215 | 400895232 | Guy | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009216 | 400895593 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009217 | 400895597 | Guy | HFTD Tier 2 | Distribution | 2006-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009218 | 400895647 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009219 | 400895771 | High Sign | HFTD Tier 2 | Distribution | 2008-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009220 | 400895820 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009221 | 400895837 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009222 | 400895862 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009223 | 400896013 | High Sign | HFTD Tier 3 | Distribution | 2001-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009224 | 400896020 | Riser/Conduit | HFTD Tier 2 | Distribution | 2007-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009225 | 400896058 | High Sign | HFTD Tier 2 | Distribution | 2001-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009226 | 400896068 | Molding | HFTD Tier 3 | Distribution | 2001-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009227 | 400896220 | Molding | HFTD Tier 3 | Distribution | 2001-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009228 | 400896332 | Molding | HFTD Tier 2 | Distribution | 2005-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009229 | 400896469 | Molding | HFTD Tier 2 | Distribution | 2006-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009230 | 400896473 | High Sign | HFTD Tier 2 | Distribution | 2006-04-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009231 | 400896488 | High Sign | HFTD Tier 2 | Distribution | 2007-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009232 | 400896580 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009233 | 400896670 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009234 | 400896675 | Molding | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009235 | 400896790 | Molding | HFTD Tier 3 | Distribution | 2007-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009236 | 400896826 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009237 | 400896975 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009238 | 400896994 | High Sign | HFTD Tier 3 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009239 | 400897006 | High Sign | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009240 | 400897065 | High Sign | HFTD Tier 3 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009241 | 400897213 | High Sign | HFTD Tier 3 | Distribution | 2002-01-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009242 | 400897284 | High Sign | HFTD Tier 3 | Distribution | 2002-01-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009243 | 400897297 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009244 | 400897306 | Molding | HFTD Tier 3 | Distribution | 2003-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009245 | 400897315 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2007-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009246 | 400897514 | Hardware/Framing | HFTD Tier 3 | Distribution | 2002-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009247 | 400897520 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009248 | 400897599 | Molding | HFTD Tier 2 | Distribution | 2007-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009249 | 400897635 | High Sign | HFTD Tier 3 | Distribution | 2006-09-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009250 | 400897691 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009251 | 400897720 | High Sign | HFTD Tier 2 | Distribution | 2006-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009252 | 400897741 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009253 | 400897782 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009254 | 400897803 | High Sign | HFTD Tier 2 | Distribution | 2007-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009255 | 400898012 | Molding | HFTD Tier 2 | Distribution | 2005-09-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009256 | 400898114 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009257 | 400898118 | Guy | HFTD Tier 3 | Distribution | 2005-12-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009258 | 400898254 | High Sign | HFTD Tier 3 | Distribution | 2006-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009259 | 400898300 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2007-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009260 | 400898508 | Molding | HFTD Tier 2 | Distribution | 2005-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009261 | 400898616 | Molding | HFTD Tier 3 | Distribution | 2001-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009262 | 400898770 | High Sign | HFTD Tier 3 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009263 | 400898804 | High Sign | HFTD Tier 2 | Distribution | 2002-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009264 | 400898857 | High Sign | HFTD Tier 3 | Distribution | 2001-11-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009265 | 400898955 | Guy | HFTD Tier 3 | Distribution | 2006-10-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009266 | 400899005 | Cable/Conductor | HFTD Tier 2 | Distribution | 2007-12-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009267 | 400899070 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-09-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009268 | 400899107 | High Sign | HFTD Tier 3 | Distribution | 2006-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009269 | 400899144 | High Sign | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009270 | 400899181 | High Sign | HFTD Tier 2 | Distribution | 2007-02-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009271 | 400899261 | High Sign | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009272 | 400899350 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009273 | 400899406 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009274 | 400899418 | High Sign | HFTD Tier 3 | Distribution | 2007-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009275 | 400899510 | High Sign | HFTD Tier 2 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009276 | 400899515 | High Sign | HFTD Tier 3 | Distribution | 2002-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009277 | 400899572 | High Sign | HFTD Tier 2 | Distribution | 2002-09-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009278 | 400899649 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2007-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009279 | 400899793 | High Sign | HFTD Tier 2 | Distribution | 2007-05-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009280 | 400899798 | High Sign | HFTD Tier 2 | Distribution | 2002-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009281 | 400899948 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009282 | 400899993 | Molding | HFTD Tier 2 | Distribution | 2007-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009283 | 400900041 | Molding | HFTD Tier 3 | Distribution | 2006-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009284 | 400900616 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009285 | 400900661 | Molding | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009286 | 400900735 | Cable/Conductor | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009287 | 400900790 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-09-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009288 | 400900815 | High Sign | HFTD Tier 2 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009289 | 400900872 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009290 | 400900879 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009291 | 400900920 | Molding | HFTD Tier 2 | Distribution | 2005-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009292 | 400900921 | High Sign | HFTD Tier 2 | Distribution | 2001-09-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009293 | 400900995 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009294 | 400901056 | High Sign | HFTD Tier 3 | Distribution | 2007-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009295 | 400901092 | Molding | HFTD Tier 3 | Distribution | 2006-09-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009296 | 400901260 | Insulator | HFTD Tier 2 | Distribution | 2006-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009297 | 400901457 | Guy | HFTD Tier 3 | Distribution | 2007-01-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009298 | 400901615 | Molding | HFTD Tier 3 | Distribution | 2007-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009299 | 400901660 | High Sign | HFTD Tier 2 | Distribution | 2007-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009300 | 400901893 | Molding | HFTD Tier 2 | Distribution | 2006-09-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009301 | 400901913 | Molding | HFTD Tier 2 | Distribution | 2006-09-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009302 | 400901964 | Molding | HFTD Tier 2 | Distribution | 2002-08-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009303 | 400901965 | Guy | HFTD Tier 3 | Distribution | 2006-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009304 | 400901969 | High Sign | HFTD Tier 2 | Distribution | 2002-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009305 | 400902041 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009306 | 400902042 | Molding | HFTD Tier 3 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009307 | 400902083 | High Sign | HFTD Tier 2 | Distribution | 2002-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009308 | 400902121 | Molding | HFTD Tier 2 | Distribution | 2006-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009309 | 400902364 | High Sign | HFTD Tier 2 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009310 | 400902485 | High Sign | HFTD Tier 3 | Distribution | 2006-10-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009311 | 400902602 | Molding | HFTD Tier 3 | Distribution | 2005-12-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009312 | 400902614 | High Sign | HFTD Tier 3 | Distribution | 2001-11-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009313 | 400902752 | Molding | HFTD Tier 3 | Distribution | 2007-10-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009314 | 400902787 | Molding | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009315 | 400902825 | High Sign | HFTD Tier 3 | Distribution | 2001-11-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009316 | 400902841 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009317 | 400902924 | High Sign | HFTD Tier 2 | Distribution | 2006-11-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009318 | 400903035 | High Sign | HFTD Tier 2 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009319 | 400903273 | Molding | HFTD Tier 2 | Distribution | 2006-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009320 | 400903317 | High Sign | HFTD Tier 2 | Distribution | 2006-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009321 | 400903326 | Molding | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009322 | 400903533 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009323 | 400903573 | High Sign | HFTD Tier 3 | Distribution | 2007-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009324 | 400903754 | High Sign | HFTD Tier 3 | Distribution | 2006-04-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009325 | 400903759 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009326 | 400903799 | High Sign | HFTD Tier 2 | Distribution | 2007-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009327 | 400903938 | Molding | HFTD Tier 2 | Distribution | 2007-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009328 | 400904161 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009329 | 400904180 | Hardware/Framing | HFTD Tier 2 | Distribution | 2001-12-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009330 | 400904410 | Molding | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009331 | 400904438 | High Sign | HFTD Tier 2 | Distribution | 2006-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009332 | 400904442 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009333 | 400904576 | Molding | HFTD Tier 2 | Distribution | 2006-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009334 | 400904685 | High Sign | HFTD Tier 2 | Distribution | 2007-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009335 | 400905549 | High Sign | HFTD Tier 2 | Distribution | 2006-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009336 | 400905706 | Guy | HFTD Tier 2 | Distribution | 2007-08-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009337 | 400905770 | High Sign | HFTD Tier 2 | Distribution | 2006-04-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009338 | 400905842 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009339 | 400906087 | Molding | HFTD Tier 2 | Distribution | 2002-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009340 | 400906216 | Guy | HFTD Tier 3 | Distribution | 2007-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009341 | 400906330 | Molding | HFTD Tier 2 | Distribution | 2006-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009342 | 400906359 | High Sign | HFTD Tier 2 | Distribution | 2001-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009343 | 400906499 | Crossarm | HFTD Tier 3 | Distribution | 2008-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009344 | 400906551 | Insulator | HFTD Tier 3 | Distribution | 2001-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009345 | 400906567 | High Sign | HFTD Tier 2 | Distribution | 2007-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009346 | 400906683 | High Sign | HFTD Tier 2 | Distribution | 2002-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009347 | 400906712 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009348 | 400906817 | High Sign | HFTD Tier 3 | Distribution | 2007-12-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009349 | 400906868 | Molding | HFTD Tier 2 | Distribution | 2006-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009350 | 400906870 | Molding | HFTD Tier 2 | Distribution | 2007-10-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009351 | 400906886 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009352 | 400906937 | Molding | HFTD Tier 2 | Distribution | 2001-12-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009353 | 400906985 | High Sign | HFTD Tier 3 | Distribution | 2007-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009354 | 400907213 | High Sign | HFTD Tier 2 | Distribution | 2002-01-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009355 | 400907500 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-04-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009356 | 400907587 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009357 | 400907632 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009358 | 400907637 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009359 | 400907743 | Cable/Conductor | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009360 | 400907747 | Insulator | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009361 | 400907876 | Guy | HFTD Tier 2 | Distribution | 2006-05-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009362 | 400907922 | High Sign | HFTD Tier 2 | Distribution | 2006-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009363 | 400908005 | High Sign | HFTD Tier 3 | Distribution | 2001-09-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009364 | 400908036 | Molding | HFTD Tier 2 | Distribution | 2001-11-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009365 | 400908222 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-11-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009366 | 400908258 | Molding | HFTD Tier 3 | Distribution | 2006-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009367 | 400908273 | High Sign | HFTD Tier 3 | Distribution | 2001-10-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009368 | 400908360 | High Sign | HFTD Tier 3 | Distribution | 2001-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009369 | 400908419 | Molding | HFTD Tier 2 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009370 | 400908537 | High Sign | HFTD Tier 3 | Distribution | 2007-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009371 | 400908670 | High Sign | HFTD Tier 3 | Distribution | 2002-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009372 | 400909013 | High Sign | HFTD Tier 3 | Distribution | 2007-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009373 | 400909050 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009374 | 400909075 | Riser/Conduit | HFTD Tier 2 | Distribution | 2007-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009375 | 400909116 | High Sign | HFTD Tier 3 | Distribution | 2006-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009376 | 400909165 | Molding | HFTD Tier 2 | Distribution | 2006-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009377 | 400909669 | Molding | HFTD Tier 3 | Distribution | 2006-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009378 | 400909789 | High Sign | HFTD Tier 3 | Distribution | 2002-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009379 | 400909950 | High Sign | HFTD Tier 2 | Distribution | 2006-11-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009380 | 400909959 | High Sign | HFTD Tier 3 | Distribution | 2007-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009381 | 400910106 | High Sign | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009382 | 400910343 | High Sign | HFTD Tier 3 | Distribution | 2007-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009383 | 400910430 | High Sign | HFTD Tier 3 | Distribution | 2006-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009384 | 400910484 | High Sign | HFTD Tier 2 | Distribution | 2006-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009385 | 400910598 | Molding | HFTD Tier 2 | Distribution | 2002-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009386 | 400910778 | Molding | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009387 | 400910952 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009388 | 400911015 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009389 | 400911054 | Molding | HFTD Tier 3 | Distribution | 2007-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009390 | 400911108 | Molding | HFTD Tier 2 | Distribution | 2007-09-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009391 | 400911110 | Molding | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009392 | 400911150 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-09-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009393 | 400911259 | Molding | HFTD Tier 3 | Distribution | 2001-09-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009394 | 400911276 | Molding | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009395 | 400911378 | High Sign | HFTD Tier 3 | Distribution | 2007-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009396 | 400911401 | High Sign | HFTD Tier 2 | Distribution | 2006-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009397 | 400911508 | Molding | HFTD Tier 3 | Distribution | 2008-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009398 | 400911653 | High Sign | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009399 | 400911757 | High Sign | HFTD Tier 2 | Distribution | 2007-05-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009400 | 400911809 | High Sign | HFTD Tier 2 | Distribution | 2006-02-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009401 | 400911812 | High Sign | HFTD Tier 2 | Distribution | 2003-09-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009402 | 400911900 | High Sign | HFTD Tier 2 | Distribution | 2002-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009403 | 400912149 | Riser/Conduit | HFTD Tier 3 | Distribution | 2005-11-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009404 | 400912427 | Molding | HFTD Tier 3 | Distribution | 2006-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009405 | 400912566 | Molding | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009406 | 400912639 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009407 | 400912640 | Molding | HFTD Tier 2 | Distribution | 2006-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009408 | 400912643 | Molding | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009409 | 400912654 | High Sign | HFTD Tier 3 | Distribution | 2007-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009410 | 400912656 | High Sign | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009411 | 400912709 | Molding | HFTD Tier 2 | Distribution | 2007-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009412 | 400912816 | Molding | HFTD Tier 3 | Distribution | 2006-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009413 | 400912888 | Molding | HFTD Tier 2 | Distribution | 2006-11-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009414 | 400912900 | Molding | HFTD Tier 3 | Distribution | 2005-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009415 | 400912944 | Molding | HFTD Tier 2 | Distribution | 2006-11-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009416 | 400913355 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009417 | 400913404 | Molding | HFTD Tier 3 | Distribution | 2002-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009418 | 400913413 | High Sign | HFTD Tier 2 | Distribution | 2006-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009419 | 400913574 | Guy | HFTD Tier 3 | Distribution | 2007-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009420 | 400913622 | High Sign | HFTD Tier 3 | Distribution | 2006-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009421 | 400913656 | Molding | HFTD Tier 2 | Distribution | 2006-05-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009422 | 400913723 | High Sign | HFTD Tier 3 | Distribution | 2002-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009423 | 400913773 | Molding | HFTD Tier 3 | Distribution | 2001-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009424 | 400914005 | Molding | HFTD Tier 2 | Distribution | 2006-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009425 | 400914149 | High Sign | HFTD Tier 2 | Distribution | 2006-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009426 | 400914246 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009427 | 400914261 | High Sign | HFTD Tier 3 | Distribution | 2005-12-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009428 | 400914352 | Molding | HFTD Tier 3 | Distribution | 2006-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009429 | 400914447 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009430 | 400914452 | High Sign | HFTD Tier 3 | Distribution | 2006-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009431 | 400914535 | High Sign | HFTD Tier 3 | Distribution | 2001-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009432 | 400914629 | High Sign | HFTD Tier 3 | Distribution | 2001-12-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009433 | 400914639 | Molding | HFTD Tier 2 | Distribution | 2001-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009434 | 400914748 | Hardware/Framing | HFTD Tier 2 | Distribution | 2002-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009435 | 400914909 | Molding | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009436 | 400915023 | High Sign | HFTD Tier 3 | Distribution | 2006-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009437 | 400915067 | High Sign | HFTD Tier 2 | Distribution | 2006-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009438 | 400915226 | High Sign | HFTD Tier 2 | Distribution | 2006-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009439 | 400915247 | High Sign | HFTD Tier 2 | Distribution | 2006-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009440 | 400915366 | High Sign | HFTD Tier 2 | Distribution | 2006-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009441 | 400915526 | High Sign | HFTD Tier 2 | Distribution | 2007-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009442 | 400915556 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-05-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009443 | 400915776 | Molding | HFTD Tier 2 | Distribution | 2001-10-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009444 | 400915909 | Molding | HFTD Tier 2 | Distribution | 2006-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009445 | 400916227 | High Sign | HFTD Tier 3 | Distribution | 2006-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009446 | 400916285 | High Sign | HFTD Tier 3 | Distribution | 2006-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009447 | 400916341 | High Sign | HFTD Tier 3 | Distribution | 2001-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009448 | 400916402 | High Sign | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009449 | 400916562 | Molding | HFTD Tier 3 | Distribution | 2007-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009450 | 400916585 | Molding | HFTD Tier 2 | Distribution | 2007-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009451 | 400916899 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009452 | 400916939 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-09-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009453 | 400916990 | High Sign | HFTD Tier 2 | Distribution | 2001-12-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009454 | 400917000 | Molding | HFTD Tier 3 | Distribution | 2007-09-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009455 | 400917261 | Molding | HFTD Tier 3 | Distribution | 2001-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009456 | 400917265 | High Sign | HFTD Tier 3 | Distribution | 2001-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009457 | 400917294 | High Sign | HFTD Tier 2 | Distribution | 2007-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009458 | 400917313 | High Sign | HFTD Tier 3 | Distribution | 2001-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009459 | 400917397 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009460 | 400917434 | Guy | HFTD Tier 2 | Distribution | 2003-09-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009461 | 400917545 | Molding | HFTD Tier 3 | Distribution | 2006-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009462 | 400918113 | Guy | HFTD Tier 3 | Distribution | 2007-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009463 | 400918147 | Molding | HFTD Tier 3 | Distribution | 2007-02-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009464 | 400918175 | Molding | HFTD Tier 3 | Distribution | 2007-02-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009465 | 400918261 | High Sign | HFTD Tier 3 | Distribution | 2001-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009466 | 400918564 | Molding | HFTD Tier 3 | Distribution | 2003-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009467 | 400918734 | High Sign | HFTD Tier 2 | Distribution | 2006-03-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009468 | 400918790 | High Sign | HFTD Tier 2 | Distribution | 2006-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009469 | 400918837 | High Sign | HFTD Tier 2 | Distribution | 1999-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009470 | 400918885 | Molding | HFTD Tier 2 | Distribution | 2006-09-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009471 | 400919001 | Molding | HFTD Tier 2 | Distribution | 2006-04-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009472 | 400919085 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009473 | 400919238 | High Sign | HFTD Tier 3 | Distribution | 2006-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009474 | 400919240 | Molding | HFTD Tier 3 | Distribution | 2007-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009475 | 400919246 | Molding | HFTD Tier 2 | Distribution | 2006-04-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009476 | 400919504 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009477 | 400919655 | Molding | HFTD Tier 2 | Distribution | 2006-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009478 | 400919656 | Molding | HFTD Tier 2 | Distribution | 2006-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009479 | 400919766 | Molding | HFTD Tier 3 | Distribution | 2005-12-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009480 | 400919844 | Molding | HFTD Tier 2 | Distribution | 2003-09-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009481 | 400919875 | Molding | HFTD Tier 3 | Distribution | 2007-12-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009482 | 400919889 | Hardware/Framing | HFTD Tier 3 | Distribution | 2003-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009483 | 400919923 | High Sign | HFTD Tier 3 | Distribution | 2006-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009484 | 400920013 | High Sign | HFTD Tier 2 | Distribution | 2007-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009485 | 400920096 | Molding | HFTD Tier 2 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009486 | 400920241 | High Sign | HFTD Tier 3 | Distribution | 2006-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009487 | 400920481 | High Sign | HFTD Tier 3 | Distribution | 2006-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009488 | 400920552 | High Sign | HFTD Tier 2 | Distribution | 2006-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009489 | 400920606 | Molding | HFTD Tier 2 | Distribution | 2006-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009490 | 400920670 | Molding | HFTD Tier 3 | Distribution | 2006-07-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009491 | 400920854 | High Sign | HFTD Tier 2 | Distribution | 2007-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009492 | 400920874 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009493 | 400920901 | High Sign | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009494 | 400920948 | High Sign | HFTD Tier 3 | Distribution | 2001-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009495 | 400921053 | High Sign | HFTD Tier 2 | Distribution | 2001-08-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009496 | 400921217 | Molding | HFTD Tier 2 | Distribution | 2002-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009497 | 400921283 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009498 | 400921294 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009499 | 400921339 | Molding | HFTD Tier 3 | Distribution | 2007-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009500 | 400921394 | Molding | HFTD Tier 2 | Distribution | 2006-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009501 | 400921471 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009502 | 400921707 | Molding | HFTD Tier 3 | Distribution | 2006-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009503 | 400921743 | High Sign | HFTD Tier 3 | Distribution | 2007-12-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009504 | 400922115 | High Sign | HFTD Tier 3 | Distribution | 2002-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009505 | 400922116 | Molding | HFTD Tier 3 | Distribution | 2007-06-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009506 | 400922334 | High Sign | HFTD Tier 2 | Distribution | 2002-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009507 | 400922530 | Molding | HFTD Tier 2 | Distribution | 2006-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009508 | 400922638 | High Sign | HFTD Tier 3 | Distribution | 2007-05-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009509 | 400922649 | Molding | HFTD Tier 2 | Distribution | 2006-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009510 | 400922848 | High Sign | HFTD Tier 3 | Distribution | 2006-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009511 | 400923014 | Molding | HFTD Tier 2 | Distribution | 2002-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009512 | 400923196 | High Sign | HFTD Tier 2 | Distribution | 2003-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009513 | 400923269 | Molding | HFTD Tier 2 | Distribution | 2006-04-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009514 | 400923538 | High Sign | HFTD Tier 3 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009515 | 400923539 | High Sign | HFTD Tier 2 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009516 | 400923784 | High Sign | HFTD Tier 2 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009517 | 400923882 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009518 | 400924041 | Hardware/Framing | HFTD Tier 3 | Distribution | 2002-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009519 | 400924275 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2003-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009520 | 400924302 | High Sign | HFTD Tier 2 | Distribution | 2006-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009521 | 400924453 | High Sign | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009522 | 400924569 | Molding | HFTD Tier 2 | Distribution | 2001-08-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009523 | 400924584 | High Sign | HFTD Tier 2 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009524 | 400924595 | High Sign | HFTD Tier 2 | Distribution | 2005-12-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009525 | 400925029 | High Sign | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009526 | 400925134 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009527 | 400925282 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009528 | 400925568 | High Sign | HFTD Tier 2 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009529 | 400925715 | High Sign | HFTD Tier 2 | Distribution | 2007-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009530 | 400925914 | Molding | HFTD Tier 3 | Distribution | 2006-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009531 | 400926133 | Molding | HFTD Tier 3 | Distribution | 2007-02-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009532 | 400926144 | Guy | HFTD Tier 2 | Distribution | 2002-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009533 | 400926216 | High Sign | HFTD Tier 3 | Distribution | 2002-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009534 | 400926335 | Molding | HFTD Tier 2 | Distribution | 2007-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009535 | 400926429 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009536 | 400926624 | High Sign | HFTD Tier 2 | Distribution | 2007-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009537 | 400926642 | Riser/Conduit | HFTD Tier 2 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009538 | 400926760 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009539 | 400926809 | High Sign | HFTD Tier 2 | Distribution | 2002-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009540 | 400926834 | Molding | HFTD Tier 2 | Distribution | 2008-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009541 | 400926962 | Molding | HFTD Tier 3 | Distribution | 2006-07-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009542 | 400927064 | High Sign | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009543 | 400927148 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2002-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009544 | 400927173 | Molding | HFTD Tier 3 | Distribution | 2007-08-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009545 | 400927239 | High Sign | HFTD Tier 3 | Distribution | 2006-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009546 | 400927386 | High Sign | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009547 | 400927487 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009548 | 400927648 | Molding | HFTD Tier 3 | Distribution | 2006-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009549 | 400927680 | High Sign | HFTD Tier 3 | Distribution | 2002-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009550 | 400927757 | High Sign | HFTD Tier 2 | Distribution | 2007-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009551 | 400927824 | Molding | HFTD Tier 2 | Distribution | 2006-04-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009552 | 400927859 | High Sign | HFTD Tier 3 | Distribution | 2007-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009553 | 400928043 | High Sign | HFTD Tier 2 | Distribution | 2006-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009554 | 400928361 | High Sign | HFTD Tier 3 | Distribution | 2008-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009555 | 400928585 | Molding | HFTD Tier 2 | Distribution | 2006-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009556 | 400928715 | Molding | HFTD Tier 3 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009557 | 400928966 | Molding | HFTD Tier 2 | Distribution | 2006-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009558 | 400929040 | Insulator | HFTD Tier 3 | Distribution | 2006-09-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009559 | 400929116 | Guy | HFTD Tier 3 | Distribution | 2007-04-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009560 | 400929130 | Riser/Conduit | HFTD Tier 3 | Distribution | 2006-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009561 | 400929293 | Molding | HFTD Tier 3 | Distribution | 2007-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009562 | 400929322 | Guy | HFTD Tier 3 | Distribution | 2007-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009563 | 400929337 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009564 | 400929343 | Molding | HFTD Tier 3 | Distribution | 2007-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009565 | 400929443 | High Sign | HFTD Tier 3 | Distribution | 2001-09-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009566 | 400929494 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009567 | 400929502 | High Sign | HFTD Tier 2 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009568 | 400929601 | Molding | HFTD Tier 3 | Distribution | 2003-08-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009569 | 400929621 | High Sign | HFTD Tier 2 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009570 | 400929702 | High Sign | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009571 | 400929756 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009572 | 400929757 | High Sign | HFTD Tier 3 | Distribution | 2001-10-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009573 | 400929766 | Guy | HFTD Tier 2 | Distribution | 2006-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009574 | 400929931 | Molding | HFTD Tier 3 | Distribution | 2006-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009575 | 400930074 | High Sign | HFTD Tier 2 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009576 | 400930118 | High Sign | HFTD Tier 2 | Distribution | 2007-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009577 | 400930197 | Molding | HFTD Tier 2 | Distribution | 2006-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009578 | 400930201 | High Sign | HFTD Tier 3 | Distribution | 2003-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009579 | 400930350 | High Sign | HFTD Tier 3 | Distribution | 2006-10-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009580 | 400930654 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009581 | 400930691 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009582 | 400930714 | High Sign | HFTD Tier 2 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009583 | 400930781 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009584 | 400930963 | Hardware/Framing | HFTD Tier 3 | Distribution | 2001-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009585 | 400931066 | Molding | HFTD Tier 2 | Distribution | 2007-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009586 | 400931087 | Molding | HFTD Tier 2 | Distribution | 2007-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009587 | 400931147 | High Sign | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009588 | 400931165 | Molding | HFTD Tier 2 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009589 | 400931177 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009590 | 400931188 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009591 | 400931417 | High Sign | HFTD Tier 2 | Distribution | 2007-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009592 | 400931504 | High Sign | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009593 | 400931538 | Molding | HFTD Tier 3 | Distribution | 2001-09-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009594 | 400931639 | High Sign | HFTD Tier 3 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009595 | 400931697 | Insulator | HFTD Tier 2 | Distribution | 2006-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009596 | 400931842 | High Sign | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009597 | 400931886 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009598 | 400931994 | High Sign | HFTD Tier 2 | Distribution | 2006-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009599 | 400932002 | Molding | HFTD Tier 3 | Distribution | 2003-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009600 | 400932094 | Molding | HFTD Tier 3 | Distribution | 2006-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009601 | 400932147 | Molding | HFTD Tier 3 | Distribution | 2002-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009602 | 400932299 | Molding | HFTD Tier 3 | Distribution | 2002-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009603 | 400932528 | Molding | HFTD Tier 2 | Distribution | 2007-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009604 | 400932959 | High Sign | HFTD Tier 2 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009605 | 400933018 | High Sign | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009606 | 400933025 | Guy | HFTD Tier 3 | Distribution | 2002-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009607 | 400933104 | Molding | HFTD Tier 2 | Distribution | 2006-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009608 | 400933141 | High Sign | HFTD Tier 3 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009609 | 400933184 | Hardware/Framing | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009610 | 400933264 | High Sign | HFTD Tier 3 | Distribution | 2006-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009611 | 400933304 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009612 | 400933538 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009613 | 400933550 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009614 | 400933552 | Guy | HFTD Tier 2 | Distribution | 2006-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009615 | 400933716 | High Sign | HFTD Tier 3 | Distribution | 2007-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009616 | 400933732 | Molding | HFTD Tier 3 | Distribution | 2006-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009617 | 400933851 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009618 | 400933915 | High Sign | HFTD Tier 2 | Distribution | 2006-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009619 | 400933972 | High Sign | HFTD Tier 3 | Distribution | 2006-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009620 | 400934012 | High Sign | HFTD Tier 3 | Distribution | 2003-07-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009621 | 400934059 | Insulator | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009622 | 400934180 | High Sign | HFTD Tier 2 | Distribution | 2007-10-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009623 | 400934203 | Molding | HFTD Tier 2 | Distribution | 2006-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009624 | 400934252 | Molding | HFTD Tier 2 | Distribution | 2003-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009625 | 400934340 | High Sign | HFTD Tier 3 | Distribution | 2006-05-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009626 | 400934392 | Molding | HFTD Tier 2 | Distribution | 2003-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009627 | 400934398 | Molding | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009628 | 400934554 | High Sign | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009629 | 400934558 | High Sign | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009630 | 400934701 | High Sign | HFTD Tier 3 | Distribution | 2006-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009631 | 400934801 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009632 | 400934848 | High Sign | HFTD Tier 2 | Distribution | 2006-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009633 | 400934865 | Molding | HFTD Tier 2 | Distribution | 2006-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009634 | 400934885 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009635 | 400935005 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009636 | 400935079 | High Sign | HFTD Tier 3 | Distribution | 2007-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009637 | 400935135 | Molding | HFTD Tier 2 | Distribution | 2006-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009638 | 400935143 | High Sign | HFTD Tier 3 | Distribution | 2007-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009639 | 400935257 | High Sign | HFTD Tier 2 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009640 | 400935352 | Hardware/Framing | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009641 | 400935376 | Molding | HFTD Tier 3 | Distribution | 2006-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009642 | 400935383 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009643 | 400935435 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009644 | 400935464 | Guy | HFTD Tier 3 | Distribution | 2006-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009645 | 400935636 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009646 | 400935649 | Molding | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009647 | 400935655 | High Sign | HFTD Tier 3 | Distribution | 2001-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009648 | 400935675 | Molding | HFTD Tier 3 | Distribution | 2002-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009649 | 400935703 | High Sign | HFTD Tier 3 | Distribution | 2002-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009650 | 400935719 | High Sign | HFTD Tier 2 | Distribution | 2002-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009651 | 400935748 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009652 | 400935895 | High Sign | HFTD Tier 3 | Distribution | 2006-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009653 | 400935926 | Molding | HFTD Tier 3 | Distribution | 2007-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009654 | 400935965 | High Sign | HFTD Tier 3 | Distribution | 2007-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009655 | 400936049 | Molding | HFTD Tier 2 | Distribution | 2006-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009656 | 400936066 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009657 | 400936243 | Guy | HFTD Tier 3 | Distribution | 2002-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009658 | 400936249 | High Sign | HFTD Tier 2 | Distribution | 2006-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009659 | 400936251 | High Sign | HFTD Tier 3 | Distribution | 2002-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009660 | 400936296 | Molding | HFTD Tier 2 | Distribution | 2006-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009661 | 400936338 | Molding | HFTD Tier 2 | Distribution | 2006-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009662 | 400936572 | Molding | HFTD Tier 3 | Distribution | 2006-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009663 | 400936631 | Molding | HFTD Tier 3 | Distribution | 2002-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009664 | 400937196 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009665 | 400937204 | Hardware/Framing | HFTD Tier 3 | Distribution | 2005-11-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009666 | 400937273 | Molding | HFTD Tier 3 | Distribution | 2002-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009667 | 400937310 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009668 | 400937394 | High Sign | HFTD Tier 2 | Distribution | 2006-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009669 | 400937398 | Molding | HFTD Tier 3 | Distribution | 2002-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009670 | 400937470 | High Sign | HFTD Tier 2 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009671 | 400937613 | High Sign | HFTD Tier 3 | Distribution | 2006-01-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009672 | 400937712 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009673 | 400937719 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009674 | 400937885 | High Sign | HFTD Tier 2 | Distribution | 2006-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009675 | 400937982 | High Sign | HFTD Tier 2 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009676 | 400938020 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009677 | 400938317 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009678 | 400938333 | Guy | HFTD Tier 3 | Distribution | 2002-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009679 | 400938348 | Molding | HFTD Tier 2 | Distribution | 2006-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009680 | 400938373 | Molding | HFTD Tier 2 | Distribution | 2006-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009681 | 400938380 | Insulator | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009682 | 400938444 | Molding | HFTD Tier 2 | Distribution | 2006-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009683 | 400938685 | Molding | HFTD Tier 2 | Distribution | 2006-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009684 | 400938771 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009685 | 400938878 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009686 | 400938914 | High Sign | HFTD Tier 3 | Distribution | 2001-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009687 | 400939083 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009688 | 400939150 | High Sign | HFTD Tier 3 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009689 | 400939170 | High Sign | HFTD Tier 3 | Distribution | 2006-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009690 | 400939171 | Molding | HFTD Tier 2 | Distribution | 2006-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009691 | 400939176 | Molding | HFTD Tier 2 | Distribution | 2006-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009692 | 400939199 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009693 | 400939214 | Molding | HFTD Tier 3 | Distribution | 2001-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009694 | 400939323 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-02-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009695 | 400939371 | Guy | HFTD Tier 3 | Distribution | 2007-08-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009696 | 400939372 | High Sign | HFTD Tier 3 | Distribution | 2007-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009697 | 400939527 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009698 | 400939531 | High Sign | HFTD Tier 2 | Distribution | 2006-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009699 | 400939665 | High Sign | HFTD Tier 2 | Distribution | 2006-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009700 | 400939674 | Molding | HFTD Tier 2 | Distribution | 2006-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009701 | 400939746 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009702 | 400939776 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009703 | 400939858 | High Sign | HFTD Tier 3 | Distribution | 2001-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009704 | 400939989 | Molding | HFTD Tier 3 | Distribution | 2002-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009705 | 400940117 | Molding | HFTD Tier 2 | Distribution | 2006-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009706 | 400940265 | Molding | HFTD Tier 3 | Distribution | 2006-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009707 | 400940289 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009708 | 400940341 | High Sign | HFTD Tier 3 | Distribution | 2001-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009709 | 400940371 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009710 | 400940537 | High Sign | HFTD Tier 3 | Distribution | 2001-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009711 | 400940591 | Molding | HFTD Tier 2 | Distribution | 2006-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009712 | 400940733 | High Sign | HFTD Tier 2 | Distribution | 2006-01-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009713 | 400940753 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009714 | 400940836 | High Sign | HFTD Tier 3 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009715 | 400940847 | Molding | HFTD Tier 2 | Distribution | 2006-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009716 | 400940865 | Molding | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009717 | 400940898 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009718 | 400940949 | High Sign | HFTD Tier 3 | Distribution | 2005-12-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009719 | 400941059 | High Sign | HFTD Tier 3 | Distribution | 2001-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009720 | 400941085 | Guy | HFTD Tier 3 | Distribution | 2007-06-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009721 | 400941094 | Insulator | HFTD Tier 2 | Distribution | 2006-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009722 | 400941240 | High Sign | HFTD Tier 3 | Distribution | 2006-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009723 | 400941257 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009724 | 400941273 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009725 | 400941347 | Guy | HFTD Tier 3 | Distribution | 2002-03-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009726 | 400941467 | High Sign | HFTD Tier 3 | Distribution | 2007-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009727 | 400941469 | Guy | HFTD Tier 3 | Distribution | 2001-10-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009728 | 400941553 | Molding | HFTD Tier 2 | Distribution | 2006-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009729 | 400941555 | High Sign | HFTD Tier 2 | Distribution | 2006-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009730 | 400941585 | High Sign | HFTD Tier 2 | Distribution | 2006-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009731 | 400941598 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009732 | 400941824 | Molding | HFTD Tier 3 | Distribution | 2006-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009733 | 400941989 | High Sign | HFTD Tier 3 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009734 | 400942029 | Molding | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009735 | 400942112 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009736 | 400942170 | High Sign | HFTD Tier 3 | Distribution | 2001-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009737 | 400942254 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009738 | 400942258 | High Sign | HFTD Tier 2 | Distribution | 2001-10-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009739 | 400942330 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-02-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009740 | 400942391 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009741 | 400942435 | Molding | HFTD Tier 3 | Distribution | 2006-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009742 | 400942519 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009743 | 400942617 | High Sign | HFTD Tier 2 | Distribution | 2006-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009744 | 400942632 | High Sign | HFTD Tier 3 | Distribution | 2001-11-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009745 | 400942648 | High Sign | HFTD Tier 3 | Distribution | 2001-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009746 | 400942689 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009747 | 400942716 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009748 | 400942723 | Molding | HFTD Tier 3 | Distribution | 2001-10-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009749 | 400942883 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009750 | 400942925 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009751 | 400943025 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009752 | 400943030 | High Sign | HFTD Tier 2 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009753 | 400943099 | High Sign | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009754 | 400943186 | Guy | HFTD Tier 2 | Distribution | 2006-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009755 | 400943252 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009756 | 400943263 | Molding | HFTD Tier 3 | Distribution | 2006-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009757 | 400943276 | High Sign | HFTD Tier 3 | Distribution | 2006-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009758 | 400943335 | Molding | HFTD Tier 2 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009759 | 400943383 | High Sign | HFTD Tier 3 | Distribution | 2001-11-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009760 | 400943411 | Molding | HFTD Tier 2 | Distribution | 2001-10-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009761 | 400943453 | Molding | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009762 | 400943494 | High Sign | HFTD Tier 3 | Distribution | 2001-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009763 | 400943499 | High Sign | HFTD Tier 2 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009764 | 400943540 | Molding | HFTD Tier 3 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009765 | 400943544 | Molding | HFTD Tier 2 | Distribution | 2006-01-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009766 | 400943638 | High Sign | HFTD Tier 3 | Distribution | 2006-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009767 | 400943954 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2007-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009768 | 400943959 | Molding | HFTD Tier 3 | Distribution | 2007-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009769 | 400944098 | High Sign | HFTD Tier 3 | Distribution | 2001-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009770 | 400944113 | High Sign | HFTD Tier 3 | Distribution | 2001-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009771 | 400944164 | Guy | HFTD Tier 3 | Distribution | 2004-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009772 | 400944250 | High Sign | HFTD Tier 3 | Distribution | 2006-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009773 | 400944768 | High Sign | HFTD Tier 2 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009774 | 400945343 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009775 | 400945371 | High Sign | HFTD Tier 3 | Distribution | 2006-01-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009776 | 400945661 | Molding | HFTD Tier 3 | Distribution | 2006-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009777 | 400945672 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009778 | 400945815 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009779 | 400945837 | High Sign | HFTD Tier 2 | Distribution | 2001-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009780 | 400945869 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009781 | 400945900 | Molding | HFTD Tier 3 | Distribution | 2001-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009782 | 400945905 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009783 | 400945929 | Molding | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009784 | 400946131 | High Sign | HFTD Tier 3 | Distribution | 2001-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009785 | 400946217 | High Sign | HFTD Tier 3 | Distribution | 2002-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009786 | 400946317 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009787 | 400946320 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009788 | 400946413 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009789 | 400946755 | Molding | HFTD Tier 3 | Distribution | 2005-12-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009790 | 400946779 | Molding | HFTD Tier 2 | Distribution | 2002-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009791 | 400946978 | Cable/Conductor | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009792 | 400946981 | Molding | HFTD Tier 2 | Distribution | 2007-05-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009793 | 400947082 | Molding | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009794 | 400947086 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009795 | 400947110 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009796 | 400947174 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009797 | 400947278 | Molding | HFTD Tier 3 | Distribution | 2005-12-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009798 | 400947293 | High Sign | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009799 | 400947327 | High Sign | HFTD Tier 3 | Distribution | 2006-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009800 | 400947381 | Molding | HFTD Tier 2 | Distribution | 2002-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009801 | 400947442 | High Sign | HFTD Tier 2 | Distribution | 2007-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009802 | 400947513 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009803 | 400947518 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009804 | 400947791 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009805 | 400947975 | High Sign | HFTD Tier 2 | Distribution | 2006-04-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009806 | 400948139 | High Sign | HFTD Tier 3 | Distribution | 2002-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009807 | 400948157 | Molding | HFTD Tier 2 | Distribution | 2006-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009808 | 400948415 | Molding | HFTD Tier 3 | Distribution | 2007-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009809 | 400948624 | High Sign | HFTD Tier 2 | Distribution | 2006-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009810 | 400948690 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009811 | 400948692 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009812 | 400948763 | High Sign | HFTD Tier 3 | Distribution | 2006-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009813 | 400948859 | Molding | HFTD Tier 3 | Distribution | 2006-01-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009814 | 400949157 | Guy | HFTD Tier 3 | Distribution | 2005-11-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009815 | 400949244 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009816 | 400949379 | High Sign | HFTD Tier 2 | Distribution | 2005-12-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009817 | 400949581 | Molding | HFTD Tier 3 | Distribution | 2006-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009818 | 400949631 | High Sign | HFTD Tier 3 | Distribution | 2007-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009819 | 400949705 | Molding | HFTD Tier 3 | Distribution | 2005-11-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009820 | 400949767 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009821 | 400949861 | Guy | HFTD Tier 3 | Distribution | 2005-11-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009822 | 400949865 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009823 | 400950281 | High Sign | HFTD Tier 2 | Distribution | 2006-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009824 | 400950291 | Molding | HFTD Tier 3 | Distribution | 2002-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009825 | 400950377 | Molding | HFTD Tier 3 | Distribution | 2006-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009826 | 400950614 | High Sign | HFTD Tier 2 | Distribution | 2005-12-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009827 | 400950632 | Molding | HFTD Tier 3 | Distribution | 2005-11-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009828 | 400950640 | Molding | HFTD Tier 2 | Distribution | 2006-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009829 | 400950665 | Molding | HFTD Tier 3 | Distribution | 2005-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009830 | 400950815 | Molding | HFTD Tier 2 | Distribution | 2001-10-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009831 | 400951104 | High Sign | HFTD Tier 2 | Distribution | 2007-07-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009832 | 400951187 | High Sign | HFTD Tier 2 | Distribution | 2005-12-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009833 | 400951234 | Molding | HFTD Tier 2 | Distribution | 2005-12-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009834 | 400951263 | Molding | HFTD Tier 3 | Distribution | 2005-11-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009835 | 400951357 | Molding | HFTD Tier 3 | Distribution | 2001-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009836 | 400951360 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2007-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009837 | 400951391 | Molding | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009838 | 400951474 | Molding | HFTD Tier 2 | Distribution | 2006-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009839 | 400951609 | High Sign | HFTD Tier 2 | Distribution | 2007-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009840 | 400951694 | Guy | HFTD Tier 2 | Distribution | 2007-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009841 | 400951760 | High Sign | HFTD Tier 2 | Distribution | 2006-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009842 | 400952186 | Molding | HFTD Tier 3 | Distribution | 2006-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009843 | 400952264 | Guy | HFTD Tier 3 | Distribution | 2005-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009844 | 400952355 | Molding | HFTD Tier 2 | Distribution | 2007-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009845 | 400952374 | Molding | HFTD Tier 3 | Distribution | 2005-12-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009846 | 400952842 | High Sign | HFTD Tier 3 | Distribution | 2006-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009847 | 400952947 | Molding | HFTD Tier 2 | Distribution | 2007-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009848 | 400953006 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009849 | 400953016 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009850 | 400953075 | Molding | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009851 | 400953352 | Molding | HFTD Tier 3 | Distribution | 2005-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009852 | 400953376 | High Sign | HFTD Tier 3 | Distribution | 2007-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009853 | 400953617 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009854 | 400953636 | High Sign | HFTD Tier 2 | Distribution | 1999-09-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009855 | 400953744 | High Sign | HFTD Tier 3 | Distribution | 2006-11-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009856 | 400953893 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009857 | 400954194 | Molding | HFTD Tier 2 | Distribution | 2005-12-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009858 | 400954223 | Molding | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009859 | 400954354 | Molding | HFTD Tier 2 | Distribution | 2005-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009860 | 400954366 | Molding | HFTD Tier 3 | Distribution | 2001-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009861 | 400954420 | High Sign | HFTD Tier 3 | Distribution | 2007-07-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009862 | 400954475 | High Sign | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009863 | 400954594 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009864 | 400954635 | Molding | HFTD Tier 2 | Distribution | 2005-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009865 | 400954724 | High Sign | HFTD Tier 2 | Distribution | 2005-11-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009866 | 400954969 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-12-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009867 | 400954975 | Molding | HFTD Tier 2 | Distribution | 2005-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009868 | 400955021 | Molding | HFTD Tier 3 | Distribution | 2007-07-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009869 | 400955035 | High Sign | HFTD Tier 2 | Distribution | 1999-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009870 | 400955133 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009871 | 400955155 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009872 | 400955160 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009873 | 400955207 | Insulator | HFTD Tier 3 | Distribution | 2002-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009874 | 400955216 | High Sign | HFTD Tier 3 | Distribution | 2001-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009875 | 400955227 | Molding | HFTD Tier 2 | Distribution | 2002-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009876 | 400955258 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009877 | 400955346 | Molding | HFTD Tier 3 | Distribution | 2001-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009878 | 400955457 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009879 | 400955464 | High Sign | HFTD Tier 3 | Distribution | 2004-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009880 | 400955535 | High Sign | HFTD Tier 3 | Distribution | 2006-02-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009881 | 400955690 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009882 | 400955711 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009883 | 400955716 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009884 | 400955859 | High Sign | HFTD Tier 2 | Distribution | 2006-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009885 | 400955861 | Molding | HFTD Tier 3 | Distribution | 2007-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009886 | 400956088 | Molding | HFTD Tier 3 | Distribution | 2007-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009887 | 400956178 | High Sign | HFTD Tier 3 | Distribution | 2007-05-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009888 | 400956228 | High Sign | HFTD Tier 3 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009889 | 400956273 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009890 | 400956318 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009891 | 400956372 | High Sign | HFTD Tier 3 | Distribution | 2007-07-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009892 | 400956690 | High Sign | HFTD Tier 3 | Distribution | 2001-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009893 | 400956857 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009894 | 400956896 | High Sign | HFTD Tier 3 | Distribution | 2001-10-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009895 | 400956905 | High Sign | HFTD Tier 3 | Distribution | 2001-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009896 | 400956916 | Molding | HFTD Tier 3 | Distribution | 2001-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009897 | 400956923 | High Sign | HFTD Tier 2 | Distribution | 1999-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009898 | 400957226 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009899 | 400957246 | High Sign | HFTD Tier 2 | Distribution | 2002-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009900 | 400957252 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009901 | 400957341 | High Sign | HFTD Tier 3 | Distribution | 2006-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009902 | 400957373 | Insulator | HFTD Tier 3 | Distribution | 2001-11-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009903 | 400957389 | Molding | HFTD Tier 2 | Distribution | 2006-01-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009904 | 400957512 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009905 | 400957555 | High Sign | HFTD Tier 2 | Distribution | 2002-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009906 | 400957641 | Molding | HFTD Tier 3 | Distribution | 2007-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009907 | 400957646 | Riser/Conduit | HFTD Tier 3 | Distribution | 2007-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009908 | 400957781 | High Sign | HFTD Tier 3 | Distribution | 2006-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009909 | 400957815 | Molding | HFTD Tier 2 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009910 | 400957819 | Molding | HFTD Tier 2 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009911 | 400957986 | High Sign | HFTD Tier 3 | Distribution | 2001-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009912 | 400958090 | Molding | HFTD Tier 2 | Distribution | 2002-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009913 | 400958213 | High Sign | HFTD Tier 2 | Distribution | 2007-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009914 | 400958223 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009915 | 400958389 | Molding | HFTD Tier 3 | Distribution | 2006-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009916 | 400958466 | High Sign | HFTD Tier 3 | Distribution | 2007-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009917 | 400958498 | Molding | HFTD Tier 2 | Distribution | 2007-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009918 | 400958678 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009919 | 400958818 | Guy | HFTD Tier 3 | Distribution | 2007-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009920 | 400958832 | High Sign | HFTD Tier 2 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009921 | 400958850 | Molding | HFTD Tier 2 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009922 | 400959116 | Molding | HFTD Tier 2 | Distribution | 2007-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009923 | 400959135 | Molding | HFTD Tier 2 | Distribution | 2006-01-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009924 | 400959175 | High Sign | HFTD Tier 2 | Distribution | 2002-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009925 | 400959281 | High Sign | HFTD Tier 3 | Distribution | 2006-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009926 | 400959329 | High Sign | HFTD Tier 3 | Distribution | 2006-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009927 | 400959344 | Guy | HFTD Tier 2 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009928 | 400959347 | High Sign | HFTD Tier 3 | Distribution | 2005-12-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009929 | 400959350 | High Sign | HFTD Tier 2 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009930 | 400959585 | High Sign | HFTD Tier 2 | Distribution | 2001-11-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009931 | 400959744 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2007-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009932 | 400959783 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009933 | 400959817 | High Sign | HFTD Tier 2 | Distribution | 2006-01-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009934 | 400959897 | High Sign | HFTD Tier 2 | Distribution | 2002-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009935 | 400959945 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009936 | 400959953 | Molding | HFTD Tier 2 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009937 | 400959970 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009938 | 400960046 | Riser/Conduit | HFTD Tier 3 | Distribution | 2007-07-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009939 | 400960061 | High Sign | HFTD Tier 3 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009940 | 400960167 | Molding | HFTD Tier 3 | Distribution | 2005-12-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009941 | 400960192 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009942 | 400960332 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009943 | 400960344 | Molding | HFTD Tier 3 | Distribution | 2005-12-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009944 | 400960368 | Guy | HFTD Tier 3 | Distribution | 2006-01-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009945 | 400960398 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009946 | 400960634 | High Sign | HFTD Tier 3 | Distribution | 2002-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009947 | 400960678 | Molding | HFTD Tier 3 | Distribution | 2005-12-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009948 | 400960687 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009949 | 400960711 | Molding | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009950 | 400960745 | High Sign | HFTD Tier 3 | Distribution | 2005-12-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009951 | 400960806 | Molding | HFTD Tier 3 | Distribution | 2005-12-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009952 | 400960832 | High Sign | HFTD Tier 3 | Distribution | 2001-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009953 | 400961013 | High Sign | HFTD Tier 3 | Distribution | 2006-03-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009954 | 400961109 | Molding | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009955 | 400961144 | Guy | HFTD Tier 2 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009956 | 400961238 | High Sign | HFTD Tier 2 | Distribution | 2006-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009957 | 400961308 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009958 | 400961323 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009959 | 400961333 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009960 | 400961484 | Insulator | HFTD Tier 2 | Distribution | 2006-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009961 | 400961488 | High Sign | HFTD Tier 2 | Distribution | 2006-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009962 | 400961616 | Molding | HFTD Tier 2 | Distribution | 2006-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009963 | 400961660 | Cable/Conductor | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009964 | 400961671 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009965 | 400961677 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009966 | 400961864 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009967 | 400962158 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009968 | 400962287 | Molding | HFTD Tier 3 | Distribution | 2001-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009969 | 400962317 | High Sign | HFTD Tier 2 | Distribution | 2006-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009970 | 400962329 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009971 | 400962416 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009972 | 400962505 | Guy | HFTD Tier 2 | Distribution | 2006-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009973 | 400962601 | Molding | HFTD Tier 2 | Distribution | 2006-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009974 | 400962647 | Molding | HFTD Tier 3 | Distribution | 2007-08-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009975 | 400962690 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009976 | 400962699 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009977 | 400962714 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009978 | 400962723 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009979 | 400962736 | High Sign | HFTD Tier 3 | Distribution | 2002-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009980 | 400962764 | Molding | HFTD Tier 2 | Distribution | 2002-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009981 | 400962845 | Molding | HFTD Tier 3 | Distribution | 2001-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009982 | 400962919 | Molding | HFTD Tier 3 | Distribution | 2006-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009983 | 400963147 | High Sign | HFTD Tier 3 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009984 | 400963153 | Molding | HFTD Tier 3 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009985 | 400963232 | Molding | HFTD Tier 3 | Distribution | 2001-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009986 | 400963410 | Guy | HFTD Tier 3 | Distribution | 2007-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009987 | 400963471 | Guy | HFTD Tier 3 | Distribution | 2001-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009988 | 400963630 | Molding | HFTD Tier 2 | Distribution | 2007-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009989 | 400963633 | High Sign | HFTD Tier 3 | Distribution | 2007-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009990 | 400963662 | High Sign | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009991 | 400963771 | Molding | HFTD Tier 3 | Distribution | 2005-10-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009992 | 400963784 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-10-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009993 | 400963868 | Molding | HFTD Tier 3 | Distribution | 2005-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009994 | 400963976 | Molding | HFTD Tier 2 | Distribution | 2007-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009995 | 400964209 | Molding | HFTD Tier 3 | Distribution | 2006-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009996 | 400964218 | Molding | HFTD Tier 3 | Distribution | 2001-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009997 | 400964232 | High Sign | HFTD Tier 3 | Distribution | 2006-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009998 | 400964307 | High Sign | HFTD Tier 2 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130009999 | 400964445 | Guy | HFTD Tier 3 | Distribution | 2007-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010000 | 400964553 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010001 | 400964558 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010002 | 400964658 | Molding | HFTD Tier 3 | Distribution | 2001-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010003 | 400964663 | High Sign | HFTD Tier 3 | Distribution | 2001-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010004 | 400964664 | Molding | HFTD Tier 3 | Distribution | 2006-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010005 | 400964759 | Molding | HFTD Tier 3 | Distribution | 2006-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010006 | 400964820 | Molding | HFTD Tier 2 | Distribution | 2006-05-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010007 | 400964830 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010008 | 400964887 | Molding | HFTD Tier 3 | Distribution | 2005-12-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010009 | 400964916 | High Sign | HFTD Tier 3 | Distribution | 2006-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010010 | 400965022 | High Sign | HFTD Tier 3 | Distribution | 2006-05-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010011 | 400965340 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010012 | 400965533 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010013 | 400965642 | Molding | HFTD Tier 2 | Distribution | 2005-10-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010014 | 400965650 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010015 | 400965722 | Molding | HFTD Tier 2 | Distribution | 2006-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010016 | 400965783 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-01-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010017 | 400965950 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010018 | 400965971 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010019 | 400966018 | Molding | HFTD Tier 2 | Distribution | 2007-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010020 | 400966079 | Molding | HFTD Tier 3 | Distribution | 2006-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010021 | 400966084 | Guy | HFTD Tier 3 | Distribution | 2006-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010022 | 400966165 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010023 | 400966268 | High Sign | HFTD Tier 3 | Distribution | 2006-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010024 | 400966417 | High Sign | HFTD Tier 3 | Distribution | 2006-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010025 | 400966486 | Molding | HFTD Tier 3 | Distribution | 2006-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010026 | 400966494 | High Sign | HFTD Tier 2 | Distribution | 2002-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010027 | 400966758 | High Sign | HFTD Tier 2 | Distribution | 2006-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010028 | 400966816 | High Sign | HFTD Tier 2 | Distribution | 2007-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010029 | 400966843 | High Sign | HFTD Tier 3 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010030 | 400966932 | Molding | HFTD Tier 3 | Distribution | 2001-11-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010031 | 400966937 | Molding | HFTD Tier 3 | Distribution | 2001-11-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010032 | 400967026 | Molding | HFTD Tier 2 | Distribution | 2007-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010033 | 400967138 | Molding | HFTD Tier 2 | Distribution | 2006-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010034 | 400967178 | Molding | HFTD Tier 3 | Distribution | 2005-11-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010035 | 400967226 | Molding | HFTD Tier 3 | Distribution | 2001-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010036 | 400967231 | High Sign | HFTD Tier 3 | Distribution | 2001-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010037 | 400967484 | High Sign | HFTD Tier 2 | Distribution | 2001-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010038 | 400967601 | Molding | HFTD Tier 2 | Distribution | 2006-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010039 | 400967613 | Molding | HFTD Tier 3 | Distribution | 2007-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010040 | 400967623 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010041 | 400967869 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010042 | 400967877 | Riser/Conduit | HFTD Tier 2 | Distribution | 2006-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010043 | 400967945 | High Sign | HFTD Tier 2 | Distribution | 2006-02-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010044 | 400967957 | High Sign | HFTD Tier 3 | Distribution | 2001-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010045 | 400968068 | Molding | HFTD Tier 3 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010046 | 400968070 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2007-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010047 | 400968083 | Molding | HFTD Tier 3 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010048 | 400968246 | High Sign | HFTD Tier 2 | Distribution | 2001-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010049 | 400968295 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010050 | 400968326 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010051 | 400968368 | High Sign | HFTD Tier 3 | Distribution | 2001-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010052 | 400968526 | High Sign | HFTD Tier 2 | Distribution | 2002-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010053 | 400968568 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010054 | 400968572 | Molding | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010055 | 400968651 | Molding | HFTD Tier 2 | Distribution | 2006-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010056 | 400968767 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010057 | 400969110 | Molding | HFTD Tier 3 | Distribution | 2006-02-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010058 | 400969187 | High Sign | HFTD Tier 3 | Distribution | 2001-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010059 | 400969216 | High Sign | HFTD Tier 3 | Distribution | 2001-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010060 | 400969433 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010061 | 400969489 | High Sign | HFTD Tier 3 | Distribution | 2001-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010062 | 400969507 | High Sign | HFTD Tier 2 | Distribution | 2001-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010063 | 400969542 | High Sign | HFTD Tier 2 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010064 | 400969717 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010065 | 400969726 | High Sign | HFTD Tier 2 | Distribution | 2002-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010066 | 400969732 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010067 | 400969738 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010068 | 400969753 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010069 | 400969754 | High Sign | HFTD Tier 2 | Distribution | 2005-12-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010070 | 400969758 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010071 | 400969799 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010072 | 400969802 | Molding | HFTD Tier 2 | Distribution | 2006-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010073 | 400969804 | Molding | HFTD Tier 2 | Distribution | 2006-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010074 | 400969966 | Molding | HFTD Tier 3 | Distribution | 2001-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010075 | 400970034 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010076 | 400970087 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010077 | 400970129 | High Sign | HFTD Tier 2 | Distribution | 2001-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010078 | 400970137 | Molding | HFTD Tier 3 | Distribution | 2007-05-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010079 | 400970235 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-11-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010080 | 400970291 | High Sign | HFTD Tier 2 | Distribution | 2006-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010081 | 400970301 | High Sign | HFTD Tier 3 | Distribution | 2001-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010082 | 400970359 | Molding | HFTD Tier 3 | Distribution | 2005-12-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010083 | 400970446 | High Sign | HFTD Tier 2 | Distribution | 2005-12-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010084 | 400970466 | Molding | HFTD Tier 2 | Distribution | 2005-08-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010085 | 400970583 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010086 | 400970593 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010087 | 400970614 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-11-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010088 | 400970620 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010089 | 400970762 | High Sign | HFTD Tier 3 | Distribution | 2005-12-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010090 | 400971296 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010091 | 400971317 | High Sign | HFTD Tier 2 | Distribution | 2005-12-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010092 | 400971416 | Molding | HFTD Tier 2 | Distribution | 2006-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010093 | 400971682 | Molding | HFTD Tier 2 | Distribution | 2006-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010094 | 400971690 | Guy | HFTD Tier 3 | Distribution | 2005-11-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010095 | 400971713 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010096 | 400971729 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010097 | 400971793 | High Sign | HFTD Tier 3 | Distribution | 2001-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010098 | 400971964 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010099 | 400971975 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010100 | 400972092 | Molding | HFTD Tier 3 | Distribution | 2005-11-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010101 | 400972173 | Molding | HFTD Tier 2 | Distribution | 2006-02-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010102 | 400972199 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010103 | 400972461 | High Sign | HFTD Tier 3 | Distribution | 2001-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010104 | 400972550 | Molding | HFTD Tier 2 | Distribution | 2006-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010105 | 400972596 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010106 | 400972606 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010107 | 400972611 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010108 | 400972620 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010109 | 400972857 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010110 | 400972992 | Cable/Conductor | HFTD Tier 2 | Distribution | 2005-12-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010111 | 400973004 | High Sign | HFTD Tier 3 | Distribution | 2006-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010112 | 400973093 | Molding | HFTD Tier 2 | Distribution | 2001-12-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010113 | 400973271 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010114 | 400973281 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010115 | 400973311 | High Sign | HFTD Tier 3 | Distribution | 2006-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010116 | 400973383 | High Sign | HFTD Tier 3 | Distribution | 2001-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010117 | 400973415 | Molding | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010118 | 400973420 | Molding | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010119 | 400973430 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010120 | 400973491 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010121 | 400973494 | Molding | HFTD Tier 2 | Distribution | 2005-12-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010122 | 400973600 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010123 | 400973712 | Molding | HFTD Tier 2 | Distribution | 2006-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010124 | 400973784 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010125 | 400973799 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010126 | 400973804 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010127 | 400973824 | Molding | HFTD Tier 2 | Distribution | 2006-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010128 | 400973834 | Molding | HFTD Tier 2 | Distribution | 2006-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010129 | 400973850 | Molding | HFTD Tier 2 | Distribution | 2006-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010130 | 400974190 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010131 | 400974215 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010132 | 400974226 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010133 | 400974449 | Guy | HFTD Tier 2 | Distribution | 2005-11-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010134 | 400974480 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010135 | 400974566 | High Sign | HFTD Tier 3 | Distribution | 2005-12-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010136 | 400974622 | Molding | HFTD Tier 3 | Distribution | 2001-08-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010137 | 400974710 | Insulator | HFTD Tier 2 | Distribution | 2006-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010138 | 400975011 | Cable/Conductor | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010139 | 400975073 | Molding | HFTD Tier 3 | Distribution | 2006-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010140 | 400975077 | High Sign | HFTD Tier 3 | Distribution | 2006-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010141 | 400975100 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010142 | 400975112 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010143 | 400975200 | High Sign | HFTD Tier 2 | Distribution | 2006-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010144 | 400975231 | High Sign | HFTD Tier 2 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010145 | 400975240 | High Sign | HFTD Tier 2 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010146 | 400975310 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010147 | 400975318 | Molding | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010148 | 400975405 | High Sign | HFTD Tier 3 | Distribution | 2001-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010149 | 400975469 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010150 | 400975559 | Molding | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010151 | 400975579 | Molding | HFTD Tier 3 | Distribution | 2001-08-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010152 | 400975652 | Molding | HFTD Tier 3 | Distribution | 2006-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010153 | 400975720 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-11-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010154 | 400975870 | High Sign | HFTD Tier 2 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010155 | 400975878 | Molding | HFTD Tier 2 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010156 | 400975950 | High Sign | HFTD Tier 2 | Distribution | 2006-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010157 | 400976137 | High Sign | HFTD Tier 2 | Distribution | 1999-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010158 | 400976375 | Molding | HFTD Tier 3 | Distribution | 2001-08-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010159 | 400976426 | Molding | HFTD Tier 3 | Distribution | 2006-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010160 | 400976455 | High Sign | HFTD Tier 3 | Distribution | 2001-09-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010161 | 400976523 | High Sign | HFTD Tier 3 | Distribution | 2001-08-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010162 | 400976538 | Guy | HFTD Tier 2 | Distribution | 2006-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010163 | 400976545 | High Sign | HFTD Tier 2 | Distribution | 2006-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010164 | 400976616 | Molding | HFTD Tier 3 | Distribution | 2001-09-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010165 | 400976740 | High Sign | HFTD Tier 3 | Distribution | 2001-08-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010166 | 400976793 | High Sign | HFTD Tier 3 | Distribution | 2006-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010167 | 400976825 | High Sign | HFTD Tier 2 | Distribution | 2001-12-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010168 | 400976968 | High Sign | HFTD Tier 2 | Distribution | 2001-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010169 | 400976987 | High Sign | HFTD Tier 3 | Distribution | 2001-08-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010170 | 400977016 | Molding | HFTD Tier 3 | Distribution | 2001-09-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010171 | 400977017 | High Sign | HFTD Tier 3 | Distribution | 2001-09-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010172 | 400977042 | Molding | HFTD Tier 3 | Distribution | 2006-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010173 | 400977083 | High Sign | HFTD Tier 3 | Distribution | 2006-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010174 | 400977261 | Molding | HFTD Tier 2 | Distribution | 2006-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010175 | 400977292 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010176 | 400977320 | Molding | HFTD Tier 3 | Distribution | 2001-09-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010177 | 400977324 | High Sign | HFTD Tier 3 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010178 | 400977331 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010179 | 400977351 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010180 | 400977466 | High Sign | HFTD Tier 2 | Distribution | 2001-09-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010181 | 400977480 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010182 | 400977506 | High Sign | HFTD Tier 3 | Distribution | 2001-09-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010183 | 400977531 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010184 | 400977534 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010185 | 400977564 | High Sign | HFTD Tier 3 | Distribution | 2001-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010186 | 400977628 | High Sign | HFTD Tier 3 | Distribution | 2006-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010187 | 400977647 | High Sign | HFTD Tier 2 | Distribution | 2001-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010188 | 400977682 | High Sign | HFTD Tier 3 | Distribution | 2001-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010189 | 400977752 | High Sign | HFTD Tier 2 | Distribution | 2001-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010190 | 400977830 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010191 | 400977834 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010192 | 400977917 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010193 | 400977998 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010194 | 400978006 | High Sign | HFTD Tier 2 | Distribution | 2001-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010195 | 400978067 | High Sign | HFTD Tier 2 | Distribution | 2001-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010196 | 400978142 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010197 | 400978163 | Molding | HFTD Tier 3 | Distribution | 2006-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010198 | 400978547 | Molding | HFTD Tier 2 | Distribution | 2006-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010199 | 400978660 | High Sign | HFTD Tier 3 | Distribution | 2006-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010200 | 400978705 | Molding | HFTD Tier 3 | Distribution | 2006-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010201 | 400978751 | High Sign | HFTD Tier 2 | Distribution | 2006-02-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010202 | 400979018 | Molding | HFTD Tier 2 | Distribution | 2006-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010203 | 400979094 | High Sign | HFTD Tier 3 | Distribution | 2001-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010204 | 400979251 | High Sign | HFTD Tier 3 | Distribution | 2001-08-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010205 | 400979256 | High Sign | HFTD Tier 2 | Distribution | 2006-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010206 | 400979354 | High Sign | HFTD Tier 2 | Distribution | 2006-01-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010207 | 400979365 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-03-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010208 | 400979606 | High Sign | HFTD Tier 3 | Distribution | 2001-09-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010209 | 400979699 | Molding | HFTD Tier 3 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010210 | 400979703 | High Sign | HFTD Tier 3 | Distribution | 2001-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010211 | 400979732 | High Sign | HFTD Tier 2 | Distribution | 2006-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010212 | 400979795 | High Sign | HFTD Tier 3 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010213 | 400979801 | High Sign | HFTD Tier 2 | Distribution | 2006-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010214 | 400979964 | High Sign | HFTD Tier 3 | Distribution | 2001-09-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010215 | 400980007 | High Sign | HFTD Tier 3 | Distribution | 2001-09-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010216 | 400980024 | Molding | HFTD Tier 3 | Distribution | 2001-09-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010217 | 400980073 | Molding | HFTD Tier 3 | Distribution | 2001-09-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010218 | 400980154 | High Sign | HFTD Tier 3 | Distribution | 2001-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010219 | 400980335 | Molding | HFTD Tier 3 | Distribution | 2001-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010220 | 400980463 | High Sign | HFTD Tier 3 | Distribution | 2006-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010221 | 400980578 | High Sign | HFTD Tier 2 | Distribution | 2006-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010222 | 400980659 | Molding | HFTD Tier 3 | Distribution | 2001-09-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010223 | 400980821 | Cable/Conductor | HFTD Tier 3 | Distribution | 2006-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010224 | 400980838 | High Sign | HFTD Tier 3 | Distribution | 2001-09-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010225 | 400980930 | Molding | HFTD Tier 2 | Distribution | 2006-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010226 | 400980975 | Molding | HFTD Tier 3 | Distribution | 2001-09-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010227 | 400980981 | Molding | HFTD Tier 3 | Distribution | 2001-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010228 | 400981120 | Guy | HFTD Tier 3 | Distribution | 2001-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010229 | 400981205 | High Sign | HFTD Tier 3 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010230 | 400981210 | Molding | HFTD Tier 3 | Distribution | 2001-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010231 | 400981381 | Molding | HFTD Tier 3 | Distribution | 2001-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010232 | 400981509 | High Sign | HFTD Tier 3 | Distribution | 2006-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010233 | 400981525 | Molding | HFTD Tier 3 | Distribution | 2001-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010234 | 400981610 | Molding | HFTD Tier 3 | Distribution | 2001-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010235 | 400981612 | High Sign | HFTD Tier 3 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010236 | 400981764 | High Sign | HFTD Tier 3 | Distribution | 2006-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010237 | 400981779 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010238 | 400981819 | Molding | HFTD Tier 2 | Distribution | 2006-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010239 | 400981879 | Molding | HFTD Tier 3 | Distribution | 2001-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010240 | 400981907 | High Sign | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010241 | 400981936 | High Sign | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010242 | 400981943 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010243 | 400982008 | High Sign | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010244 | 400982033 | Guy | HFTD Tier 2 | Distribution | 2006-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010245 | 400982077 | High Sign | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010246 | 400982110 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010247 | 400982204 | High Sign | HFTD Tier 3 | Distribution | 2001-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010248 | 400982248 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010249 | 400982254 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010250 | 400982293 | Molding | HFTD Tier 3 | Distribution | 2001-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010251 | 400982381 | High Sign | HFTD Tier 3 | Distribution | 2006-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010252 | 400982436 | High Sign | HFTD Tier 3 | Distribution | 2001-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010253 | 400982490 | Molding | HFTD Tier 3 | Distribution | 2001-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010254 | 400982572 | Molding | HFTD Tier 3 | Distribution | 2001-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010255 | 400982607 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010256 | 400982649 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010257 | 400982664 | High Sign | HFTD Tier 2 | Distribution | 2006-04-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010258 | 400982688 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010259 | 400982741 | High Sign | HFTD Tier 2 | Distribution | 2006-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010260 | 400982796 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010261 | 400982821 | Insulator | HFTD Tier 2 | Distribution | 2006-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010262 | 400982879 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010263 | 400982906 | High Sign | HFTD Tier 3 | Distribution | 2006-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010264 | 400982992 | High Sign | HFTD Tier 2 | Distribution | 2006-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010265 | 400983017 | Molding | HFTD Tier 3 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010266 | 400983109 | High Sign | HFTD Tier 2 | Distribution | 2006-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010267 | 400983209 | Molding | HFTD Tier 3 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010268 | 400983210 | High Sign | HFTD Tier 3 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010269 | 400983214 | High Sign | HFTD Tier 3 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010270 | 400983429 | High Sign | HFTD Tier 3 | Distribution | 2001-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010271 | 400983446 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010272 | 400983616 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010273 | 400983653 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010274 | 400983861 | Molding | HFTD Tier 2 | Distribution | 2006-01-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010275 | 400983907 | Molding | HFTD Tier 3 | Distribution | 2006-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010276 | 400983925 | Molding | HFTD Tier 3 | Distribution | 2001-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010277 | 400984038 | High Sign | HFTD Tier 2 | Distribution | 2006-01-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010278 | 400984146 | High Sign | HFTD Tier 3 | Distribution | 2001-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010279 | 400985081 | Cable/Conductor | HFTD Tier 3 | Distribution | 2006-12-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010280 | 400985214 | Cable/Conductor | HFTD Tier 2 | Distribution | 2003-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010281 | 400985222 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010282 | 400985379 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010283 | 400985399 | Cable/Conductor | HFTD Tier 3 | Distribution | 2003-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010284 | 400985421 | Cable/Conductor | HFTD Tier 3 | Distribution | 2003-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010285 | 400985422 | Cable/Conductor | HFTD Tier 3 | Distribution | 2003-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010286 | 400985433 | Cable/Conductor | HFTD Tier 3 | Distribution | 2005-12-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010287 | 400985451 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010288 | 400985700 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010289 | 400985769 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010290 | 400985904 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010291 | 400985945 | Cable/Conductor | HFTD Tier 3 | Distribution | 2003-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010292 | 400986311 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010293 | 400987148 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010294 | 400987793 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010295 | 400988570 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010296 | 400988799 | Cable/Conductor | HFTD Tier 3 | Distribution | 2006-10-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010297 | 400988809 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010298 | 400989011 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010299 | 400989017 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010300 | 400989233 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-11-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010301 | 400989938 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010302 | 400991164 | Cable/Conductor | HFTD Tier 2 | Distribution | 2007-12-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010303 | 400991407 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010304 | 400991462 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-11-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010305 | 400991875 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010306 | 400991989 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010307 | 400992075 | Cable/Conductor | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010308 | 400992266 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010309 | 400992501 | Cable/Conductor | HFTD Tier 3 | Distribution | 2003-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010310 | 400993136 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010311 | 400993420 | Cable/Conductor | HFTD Tier 2 | Distribution | 2001-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010312 | 400993857 | Cable/Conductor | HFTD Tier 3 | Distribution | 2001-10-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010313 | 400994017 | Cable/Conductor | HFTD Tier 2 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010314 | 400994780 | Cable/Conductor | HFTD Tier 2 | Distribution | 2005-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010315 | 400995903 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010316 | 400996379 | Cable/Conductor | HFTD Tier 2 | Distribution | 2002-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010317 | 400996405 | Cable/Conductor | HFTD Tier 2 | Distribution | 2005-04-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010318 | 400996875 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010319 | 400997199 | Cable/Conductor | HFTD Tier 2 | Distribution | 2007-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010320 | 400998123 | Cable/Conductor | HFTD Tier 3 | Distribution | 2001-12-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010321 | 400998323 | Cable/Conductor | HFTD Tier 2 | Distribution | 2005-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010322 | 400998343 | Cable/Conductor | HFTD Tier 3 | Distribution | 2001-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010323 | 400998602 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010324 | 400998703 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010325 | 400999023 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010326 | 400999209 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010327 | 400999255 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010328 | 400999292 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-09-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010329 | 400999308 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010330 | 400999359 | Cable/Conductor | HFTD Tier 3 | Distribution | 2001-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010331 | 400999476 | Cable/Conductor | HFTD Tier 3 | Distribution | 2001-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010332 | 400999496 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010333 | 400999522 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010334 | 400999605 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010335 | 400999649 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-04-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010336 | 400999658 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-01-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010337 | 400999696 | Cable/Conductor | HFTD Tier 3 | Distribution | 2001-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010338 | 400999722 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010339 | 400999750 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010340 | 400999756 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010341 | 400999774 | Cable/Conductor | HFTD Tier 2 | Distribution | 2002-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010342 | 401000110 | Cable/Conductor | HFTD Tier 2 | Distribution | 2005-12-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010343 | 401000317 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010344 | 401000401 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-08-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010345 | 401000599 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-05-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010346 | 401000669 | Cable/Conductor | HFTD Tier 3 | Distribution | 2006-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010347 | 401001077 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010348 | 401001192 | Cable/Conductor | HFTD Tier 2 | Distribution | 2001-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010349 | 401001195 | Cable/Conductor | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010350 | 401001197 | Cable/Conductor | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010351 | 401001198 | Cable/Conductor | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010352 | 401001199 | Cable/Conductor | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010353 | 401001200 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-10-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010354 | 401001202 | Cable/Conductor | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010355 | 401001203 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010356 | 401001204 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010357 | 401001205 | Cable/Conductor | HFTD Tier 3 | Distribution | 2006-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010358 | 401001206 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010359 | 401001678 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010360 | 401001728 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010361 | 401002084 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010362 | 401002494 | Cable/Conductor | HFTD Tier 3 | Distribution | 2005-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010363 | 401002497 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010364 | 401002502 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010365 | 401002550 | Cable/Conductor | HFTD Tier 2 | Distribution | 2005-12-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010366 | 401003106 | High Sign | HFTD Tier 2 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010367 | 401003198 | High Sign | HFTD Tier 2 | Distribution | 2002-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010368 | 401003209 | High Sign | HFTD Tier 2 | Distribution | 2001-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010369 | 401003224 | High Sign | HFTD Tier 3 | Distribution | 2005-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010370 | 401003439 | Guy | HFTD Tier 3 | Distribution | 2007-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010371 | 401003616 | Guy | HFTD Tier 2 | Distribution | 2004-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010372 | 401003794 | High Sign | HFTD Tier 3 | Distribution | 2001-11-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010373 | 401003953 | Cable/Conductor | HFTD Tier 2 | Distribution | 2001-09-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010374 | 401003970 | High Sign | HFTD Tier 3 | Distribution | 2002-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010375 | 401004148 | Hardware/Framing | HFTD Tier 2 | Distribution | 2005-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010376 | 401004149 | High Sign | HFTD Tier 2 | Distribution | 2005-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010377 | 401004207 | High Sign | HFTD Tier 2 | Distribution | 2005-01-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010378 | 401004253 | High Sign | HFTD Tier 2 | Distribution | 2001-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010379 | 401004450 | High Sign | HFTD Tier 2 | Distribution | 2006-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010380 | 401005300 | Molding | HFTD Tier 2 | Distribution | 2002-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010381 | 401005578 | High Sign | HFTD Tier 3 | Distribution | 2004-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010382 | 401005691 | High Sign | HFTD Tier 2 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010383 | 401005875 | Hardware/Framing | HFTD Tier 3 | Distribution | 2002-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010384 | 401005876 | Molding | HFTD Tier 3 | Distribution | 2002-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010385 | 401005894 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010386 | 401005895 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010387 | 401005916 | High Sign | HFTD Tier 2 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010388 | 401005959 | High Sign | HFTD Tier 2 | Distribution | 2002-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010389 | 401005994 | High Sign | HFTD Tier 3 | Distribution | 2004-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010390 | 401006002 | High Sign | HFTD Tier 2 | Distribution | 2001-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010391 | 401006003 | Molding | HFTD Tier 2 | Distribution | 2001-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010392 | 401006038 | High Sign | HFTD Tier 3 | Distribution | 2002-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010393 | 401006039 | Molding | HFTD Tier 3 | Distribution | 2002-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010394 | 401006054 | High Sign | HFTD Tier 2 | Distribution | 2001-11-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010395 | 401006067 | High Sign | HFTD Tier 2 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010396 | 401006082 | Guy | HFTD Tier 2 | Distribution | 2001-11-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010397 | 401006099 | Molding | HFTD Tier 3 | Distribution | 2001-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010398 | 401006159 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010399 | 401006172 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010400 | 401006173 | Molding | HFTD Tier 2 | Distribution | 2002-01-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010401 | 401006197 | Molding | HFTD Tier 2 | Distribution | 2002-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010402 | 401006245 | High Sign | HFTD Tier 3 | Distribution | 2002-02-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010403 | 401006246 | Molding | HFTD Tier 3 | Distribution | 2002-02-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010404 | 401006386 | High Sign | HFTD Tier 3 | Distribution | 2009-09-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010405 | 401006387 | High Sign | HFTD Tier 3 | Distribution | 2009-09-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010406 | 401006440 | Molding | HFTD Tier 3 | Distribution | 2008-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010407 | 401006452 | High Sign | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010408 | 401006482 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010409 | 401006484 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010410 | 401006487 | Guy | HFTD Tier 3 | Distribution | 2003-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010411 | 401006489 | High Sign | HFTD Tier 3 | Distribution | 2002-03-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010412 | 401006498 | High Sign | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010413 | 401006502 | Molding | HFTD Tier 3 | Distribution | 2005-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010414 | 401006504 | Hardware/Framing | HFTD Tier 3 | Distribution | 2005-12-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010415 | 401006505 | Molding | HFTD Tier 3 | Distribution | 2005-12-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010416 | 401006516 | High Sign | HFTD Tier 3 | Distribution | 2002-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010417 | 401006518 | Molding | HFTD Tier 3 | Distribution | 2009-11-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010418 | 401006519 | High Sign | HFTD Tier 3 | Distribution | 2009-11-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010419 | 401006520 | Molding | HFTD Tier 3 | Distribution | 2001-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010420 | 401006542 | High Sign | HFTD Tier 3 | Distribution | 2001-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010421 | 401006558 | High Sign | HFTD Tier 3 | Distribution | 2001-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010422 | 401006559 | High Sign | HFTD Tier 3 | Distribution | 2002-04-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010423 | 401006560 | Molding | HFTD Tier 3 | Distribution | 2002-09-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010424 | 401006561 | High Sign | HFTD Tier 3 | Distribution | 2002-09-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010425 | 401006565 | High Sign | HFTD Tier 3 | Distribution | 2004-11-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010426 | 401006566 | Guy | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010427 | 401006570 | High Sign | HFTD Tier 3 | Distribution | 2002-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010428 | 401006571 | High Sign | HFTD Tier 2 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010429 | 401006572 | Molding | HFTD Tier 2 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010430 | 401006579 | Molding | HFTD Tier 3 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010431 | 401006580 | High Sign | HFTD Tier 3 | Distribution | 2001-09-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010432 | 401006582 | Molding | HFTD Tier 3 | Distribution | 2002-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010433 | 401006583 | High Sign | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010434 | 401006584 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010435 | 401006593 | High Sign | HFTD Tier 3 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010436 | 401006594 | High Sign | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010437 | 401006595 | Molding | HFTD Tier 3 | Distribution | 2001-12-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010438 | 401006596 | High Sign | HFTD Tier 3 | Distribution | 2001-12-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010439 | 401006597 | Molding | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010440 | 401006604 | High Sign | HFTD Tier 3 | Distribution | 2006-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010441 | 401006605 | High Sign | HFTD Tier 3 | Distribution | 2009-12-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010442 | 401006608 | High Sign | HFTD Tier 3 | Distribution | 2001-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010443 | 401006618 | High Sign | HFTD Tier 3 | Distribution | 2001-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010444 | 401006619 | Molding | HFTD Tier 3 | Distribution | 2001-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010445 | 401006621 | Molding | HFTD Tier 3 | Distribution | 2001-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010446 | 401006622 | Molding | HFTD Tier 3 | Distribution | 2007-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010447 | 401006625 | Molding | HFTD Tier 2 | Distribution | 2001-09-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010448 | 401006626 | High Sign | HFTD Tier 3 | Distribution | 2001-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010449 | 401006627 | Molding | HFTD Tier 3 | Distribution | 2001-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010450 | 401006632 | High Sign | HFTD Tier 3 | Distribution | 2002-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010451 | 401006633 | High Sign | HFTD Tier 3 | Distribution | 2001-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010452 | 401006635 | High Sign | HFTD Tier 3 | Distribution | 2002-02-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010453 | 401006641 | High Sign | HFTD Tier 3 | Distribution | 2001-11-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010454 | 401006642 | Molding | HFTD Tier 3 | Distribution | 2001-11-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010455 | 401006644 | High Sign | HFTD Tier 2 | Distribution | 2001-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010456 | 401006652 | High Sign | HFTD Tier 3 | Distribution | 2001-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010457 | 401006657 | High Sign | HFTD Tier 3 | Distribution | 2001-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010458 | 401006664 | Molding | HFTD Tier 3 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010459 | 401006670 | High Sign | HFTD Tier 3 | Distribution | 2005-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010460 | 401006671 | Molding | HFTD Tier 3 | Distribution | 2007-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010461 | 401006672 | High Sign | HFTD Tier 3 | Distribution | 2001-12-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010462 | 401006673 | High Sign | HFTD Tier 3 | Distribution | 2009-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010463 | 401006674 | High Sign | HFTD Tier 3 | Distribution | 2001-12-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010464 | 401006678 | Molding | HFTD Tier 3 | Distribution | 2008-05-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010465 | 401006679 | High Sign | HFTD Tier 3 | Distribution | 2001-11-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010466 | 401006680 | Molding | HFTD Tier 3 | Distribution | 2001-11-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010467 | 401006681 | High Sign | HFTD Tier 3 | Distribution | 2002-02-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010468 | 401006683 | High Sign | HFTD Tier 3 | Distribution | 2002-08-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010469 | 401006687 | Molding | HFTD Tier 3 | Distribution | 2007-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010470 | 401006689 | High Sign | HFTD Tier 3 | Distribution | 2002-01-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010471 | 401006690 | High Sign | HFTD Tier 3 | Distribution | 2004-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010472 | 401006691 | Molding | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010473 | 401006692 | High Sign | HFTD Tier 3 | Distribution | 2001-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010474 | 401006693 | Molding | HFTD Tier 3 | Distribution | 2001-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010475 | 401006694 | Hardware/Framing | HFTD Tier 3 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010476 | 401006695 | Hardware/Framing | HFTD Tier 3 | Distribution | 2002-01-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010477 | 401006701 | High Sign | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010478 | 401006703 | High Sign | HFTD Tier 2 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010479 | 401006706 | Molding | HFTD Tier 3 | Distribution | 2007-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010480 | 401006707 | High Sign | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010481 | 401006709 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010482 | 401006733 | High Sign | HFTD Tier 3 | Distribution | 2002-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010483 | 401006783 | Molding | HFTD Tier 3 | Distribution | 2005-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010484 | 401006785 | High Sign | HFTD Tier 3 | Distribution | 2005-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010485 | 401007659 | High Sign | HFTD Tier 2 | Distribution | 2010-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010486 | 401007705 | Molding | HFTD Tier 2 | Distribution | 2010-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010487 | 401007709 | Molding | HFTD Tier 2 | Distribution | 2010-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010488 | 401008005 | High Sign | HFTD Tier 3 | Distribution | 2010-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010489 | 401008368 | Guy | HFTD Tier 2 | Distribution | 2010-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010490 | 401008502 | High Sign | HFTD Tier 3 | Distribution | 2010-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010491 | 401009061 | High Sign | HFTD Tier 2 | Distribution | 2010-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010492 | 401009301 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010493 | 401009345 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010494 | 401009422 | Molding | HFTD Tier 2 | Distribution | 2010-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010495 | 401009435 | Riser/Conduit | HFTD Tier 2 | Distribution | 2010-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010496 | 401009510 | Molding | HFTD Tier 3 | Distribution | 2010-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010497 | 401009516 | High Sign | HFTD Tier 3 | Distribution | 2010-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010498 | 401009567 | High Sign | HFTD Tier 2 | Distribution | 2010-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010499 | 401009601 | Molding | HFTD Tier 2 | Distribution | 2010-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010500 | 401009608 | Molding | HFTD Tier 2 | Distribution | 2010-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010501 | 401009611 | Molding | HFTD Tier 2 | Distribution | 2010-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010502 | 401009614 | Guy | HFTD Tier 2 | Distribution | 2010-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010503 | 401009635 | High Sign | HFTD Tier 2 | Distribution | 2010-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010504 | 401009641 | High Sign | HFTD Tier 2 | Distribution | 2010-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010505 | 401009650 | Molding | HFTD Tier 2 | Distribution | 2010-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010506 | 401009726 | Streetlight | HFTD Tier 2 | Distribution | 2010-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010507 | 401010638 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010508 | 401010644 | High Sign | HFTD Tier 2 | Distribution | 2010-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010509 | 401010670 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010510 | 401010710 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010511 | 401010713 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010512 | 401010714 | High Sign | HFTD Tier 2 | Distribution | 2010-04-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010513 | 401010721 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010514 | 401010880 | Molding | HFTD Tier 3 | Distribution | 2010-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010515 | 401010883 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010516 | 401010945 | Riser/Conduit | HFTD Tier 3 | Distribution | 2010-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010517 | 401011099 | Vis Strips | HFTD Tier 2 | Distribution | 2010-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010518 | 401011142 | Molding | HFTD Tier 3 | Distribution | 2010-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010519 | 401011328 | Vis Strips | HFTD Tier 2 | Distribution | 2010-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010520 | 401011796 | High Sign | HFTD Tier 3 | Distribution | 2010-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010521 | 401011808 | High Sign | HFTD Tier 3 | Distribution | 2010-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010522 | 401011836 | Guy | HFTD Tier 3 | Distribution | 2010-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010523 | 401011845 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010524 | 401011849 | Molding | HFTD Tier 3 | Distribution | 2010-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010525 | 401011859 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010526 | 401011863 | Molding | HFTD Tier 3 | Distribution | 2010-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010527 | 401011864 | Guy | HFTD Tier 3 | Distribution | 2010-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010528 | 401011873 | Molding | HFTD Tier 3 | Distribution | 2010-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010529 | 401012062 | Molding | HFTD Tier 3 | Distribution | 2010-04-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010530 | 401012173 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010531 | 401012432 | High Sign | HFTD Tier 3 | Distribution | 2010-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010532 | 401012597 | High Sign | HFTD Tier 3 | Distribution | 2010-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010533 | 401012807 | High Sign | HFTD Tier 3 | Distribution | 2010-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010534 | 401012811 | Molding | HFTD Tier 3 | Distribution | 2010-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010535 | 401012912 | High Sign | HFTD Tier 3 | Distribution | 2010-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010536 | 401013175 | Molding | HFTD Tier 2 | Distribution | 2010-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010537 | 401013331 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010538 | 401013340 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010539 | 401013479 | High Sign | HFTD Tier 2 | Distribution | 2010-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010540 | 401013524 | High Sign | HFTD Tier 2 | Distribution | 2010-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010541 | 401013525 | High Sign | HFTD Tier 2 | Distribution | 2010-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010542 | 401013527 | Molding | HFTD Tier 2 | Distribution | 2010-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010543 | 401013540 | High Sign | HFTD Tier 2 | Distribution | 2010-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010544 | 401013654 | High Sign | HFTD Tier 3 | Distribution | 2010-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010545 | 401014101 | Molding | HFTD Tier 3 | Distribution | 2010-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010546 | 401014166 | Termination | HFTD Tier 2 | Distribution | 2010-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010547 | 401014172 | Molding | HFTD Tier 2 | Distribution | 2010-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010548 | 401014201 | Molding | HFTD Tier 3 | Distribution | 2010-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010549 | 401014607 | Guy | HFTD Tier 2 | Distribution | 2010-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010550 | 401014629 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010551 | 401015407 | High Sign | HFTD Tier 2 | Distribution | 2010-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010552 | 401015483 | High Sign | HFTD Tier 3 | Distribution | 2010-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010553 | 401015790 | High Sign | HFTD Tier 2 | Distribution | 2010-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010554 | 401015804 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010555 | 401015814 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010556 | 401015823 | Guy | HFTD Tier 2 | Distribution | 2010-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010557 | 401015834 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010558 | 401015853 | High Sign | HFTD Tier 2 | Distribution | 2010-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010559 | 401015928 | High Sign | HFTD Tier 3 | Distribution | 2010-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010560 | 401015931 | High Sign | HFTD Tier 3 | Distribution | 2010-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010561 | 401016218 | High Sign | HFTD Tier 3 | Distribution | 2010-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010562 | 401016247 | High Sign | HFTD Tier 3 | Distribution | 2010-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010563 | 401016324 | Vis Strips | HFTD Tier 2 | Distribution | 2010-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010564 | 401016365 | Molding | HFTD Tier 2 | Distribution | 2010-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010565 | 401016390 | Insulator | HFTD Tier 2 | Distribution | 2010-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010566 | 401016394 | Molding | HFTD Tier 2 | Distribution | 2010-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010567 | 401016396 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010568 | 401016407 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010569 | 401016410 | Molding | HFTD Tier 2 | Distribution | 2010-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010570 | 401016567 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010571 | 401016575 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010572 | 401016678 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010573 | 401016834 | Molding | HFTD Tier 2 | Distribution | 2010-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010574 | 401017040 | Molding | HFTD Tier 2 | Distribution | 2010-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010575 | 401017805 | High Sign | HFTD Tier 3 | Distribution | 2010-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010576 | 401017963 | Guy | HFTD Tier 3 | Distribution | 2010-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010577 | 401017965 | High Sign | HFTD Tier 3 | Distribution | 2010-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010578 | 401017967 | High Sign | HFTD Tier 3 | Distribution | 2010-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010579 | 401018549 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010580 | 401018592 | Molding | HFTD Tier 2 | Distribution | 2010-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010581 | 401018629 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010582 | 401018863 | High Sign | HFTD Tier 3 | Distribution | 2010-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010583 | 401019015 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010584 | 401019017 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010585 | 401084694 | Molding | HFTD Tier 3 | Distribution | 2010-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010586 | 401084918 | Molding | HFTD Tier 3 | Distribution | 2010-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010587 | 401084933 | High Sign | HFTD Tier 3 | Distribution | 2010-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010588 | 401084937 | High Sign | HFTD Tier 3 | Distribution | 2010-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010589 | 401085160 | Molding | HFTD Tier 3 | Distribution | 2010-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010590 | 401085161 | Molding | HFTD Tier 3 | Distribution | 2010-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010591 | 401085164 | Molding | HFTD Tier 3 | Distribution | 2010-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010592 | 401085165 | High Sign | HFTD Tier 3 | Distribution | 2010-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010593 | 401085170 | Molding | HFTD Tier 3 | Distribution | 2010-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010594 | 401085178 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010595 | 401085263 | High Sign | HFTD Tier 2 | Distribution | 2010-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010596 | 401085272 | High Sign | HFTD Tier 2 | Distribution | 2010-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010597 | 401085273 | High Sign | HFTD Tier 2 | Distribution | 2010-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010598 | 401085276 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2010-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010599 | 401085283 | High Sign | HFTD Tier 2 | Distribution | 2010-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010600 | 401085767 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-05-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010601 | 401085825 | Molding | HFTD Tier 2 | Distribution | 2010-05-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010602 | 401457147 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010603 | 401457456 | Cable/Conductor | HFTD Tier 2 | Distribution | 2005-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010604 | 401457708 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010605 | 401459511 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2009-08-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010606 | 401460199 | Cable/Conductor | HFTD Tier 2 | Distribution | 2005-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010607 | 401460260 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010608 | 401461014 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2008-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010609 | 401461506 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010610 | 401461803 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010611 | 401462634 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2009-09-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010612 | 401462884 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010613 | 401462984 | Molding | HFTD Tier 3 | Distribution | 2006-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010614 | 401463248 | Guy | HFTD Tier 2 | Distribution | 2006-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010615 | 401464313 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010616 | 401464346 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010617 | 401466126 | Molding | HFTD Tier 2 | Distribution | 2002-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010618 | 401466217 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010619 | 401466234 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010620 | 401466379 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2009-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010621 | 401467407 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010622 | 401468014 | High Sign | HFTD Tier 3 | Distribution | 2003-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010623 | 401468213 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010624 | 401468634 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010625 | 401468648 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010626 | 401469903 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010627 | 401470447 | High Sign | HFTD Tier 2 | Distribution | 2003-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010628 | 401470749 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010629 | 401472113 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010630 | 401472301 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010631 | 401472493 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010632 | 401472564 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010633 | 401474239 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010634 | 401474884 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2009-10-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010635 | 401477931 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010636 | 401478399 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-09-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010637 | 401478688 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2005-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010638 | 401481425 | Cable/Conductor | HFTD Tier 2 | Distribution | 2005-09-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010639 | 401486475 | Cable/Conductor | HFTD Tier 2 | Distribution | 2005-11-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010640 | 401491352 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-12-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010641 | 401491664 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010642 | 401492307 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-07-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010643 | 401492599 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010644 | 401494930 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010645 | 401496880 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010646 | 401499317 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010647 | 401500937 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2009-11-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010648 | 401502153 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-03-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010649 | 401502348 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010650 | 401503789 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010651 | 401506491 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2009-12-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010652 | 401514208 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010653 | 401516933 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010654 | 401517620 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010655 | 401518057 | Cable/Conductor | HFTD Tier 3 | Distribution | 2006-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010656 | 401518528 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010657 | 401519196 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010658 | 401519208 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010659 | 401519255 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010660 | 401520819 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2009-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010661 | 401520937 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010662 | 401520978 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010663 | 401522666 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010664 | 401522913 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010665 | 401524151 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010666 | 401528231 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010667 | 401530681 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010668 | 401530738 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-09-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010669 | 401530899 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010670 | 401532245 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2009-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010671 | 401533709 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010672 | 401536508 | Cable/Conductor | HFTD Tier 3 | Distribution | 2006-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010673 | 401538886 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-12-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010674 | 401540127 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-12-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010675 | 401541528 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-08-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010676 | 401551099 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010677 | 401552723 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010678 | 401555293 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-08-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010679 | 401555415 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-09-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010680 | 401555428 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-09-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010681 | 401556616 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-09-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010682 | 401557274 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-09-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010683 | 401557467 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-09-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010684 | 401565012 | Cable/Conductor | HFTD Tier 2 | Distribution | 2007-11-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010685 | 401569103 | Cable/Conductor | HFTD Tier 3 | Distribution | 2008-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010686 | 401569256 | Cable/Conductor | HFTD Tier 3 | Distribution | 2008-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010687 | 401569533 | Insulator | HFTD Tier 3 | Distribution | 2008-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010688 | 401570019 | Cable/Conductor | HFTD Tier 3 | Distribution | 2008-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010689 | 401570431 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010690 | 401570527 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010691 | 401570564 | Ground | HFTD Tier 3 | Distribution | 2008-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010692 | 401570603 | Insulator | HFTD Tier 3 | Distribution | 2008-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010693 | 401571216 | Cable/Conductor | HFTD Tier 3 | Distribution | 2008-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010694 | 401571454 | Cable/Conductor | HFTD Tier 3 | Distribution | 2008-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010695 | 401572854 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010696 | 401577890 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010697 | 401578875 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010698 | 401579604 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010699 | 401579827 | Ground | HFTD Tier 2 | Distribution | 2008-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010700 | 401580915 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010701 | 401581129 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-03-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010702 | 401581164 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010703 | 401581173 | Ground | HFTD Tier 3 | Distribution | 2008-03-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010704 | 401581612 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010705 | 401582480 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010706 | 401585207 | Cable/Conductor | HFTD Tier 3 | Distribution | 2008-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010707 | 401587874 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-04-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010708 | 401588293 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010709 | 401590999 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2008-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010710 | 401594450 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-12-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010711 | 401596211 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010712 | 401599978 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010713 | 401609135 | Cable/Conductor | HFTD Tier 3 | Distribution | 2003-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010714 | 401610973 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010715 | 401625096 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-05-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010716 | 401628718 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2008-11-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010717 | 401638155 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-12-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010718 | 401638651 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010719 | 401638977 | Cable/Conductor | HFTD Tier 3 | Distribution | 2008-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010720 | 401657953 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2009-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010721 | 401665718 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2009-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010722 | 401676039 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010723 | 401681932 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2009-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010724 | 401686290 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2009-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010725 | 401690344 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2009-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010726 | 401703350 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2009-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010727 | 401704282 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010728 | 401705589 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010729 | 401712500 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010730 | 401712889 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2009-08-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010731 | 401714732 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010732 | 401720812 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010733 | 401732683 | Molding | HFTD Tier 2 | Distribution | 2010-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010734 | 401732778 | Molding | HFTD Tier 2 | Distribution | 2010-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010735 | 401732859 | Guy | HFTD Tier 2 | Distribution | 2010-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010736 | 401737122 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010737 | 401737420 | Insulator | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010738 | 401737514 | Molding | HFTD Tier 2 | Distribution | 2010-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010739 | 402398621 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010740 | 402400251 | High Sign | HFTD Tier 3 | Distribution | 2010-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010741 | 402400264 | Molding | HFTD Tier 3 | Distribution | 2010-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010742 | 402400341 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010743 | 402401647 | Molding | HFTD Tier 2 | Distribution | 2010-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010744 | 402401655 | High Sign | HFTD Tier 2 | Distribution | 2010-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010745 | 402401668 | Molding | HFTD Tier 2 | Distribution | 2010-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010746 | 402401681 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010747 | 402402149 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010748 | 402402184 | High Sign | HFTD Tier 3 | Distribution | 2010-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010749 | 402402188 | Molding | HFTD Tier 3 | Distribution | 2010-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010750 | 402402189 | Riser/Conduit | HFTD Tier 3 | Distribution | 2010-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010751 | 402402254 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010752 | 402403176 | Molding | HFTD Tier 3 | Distribution | 2010-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010753 | 402403318 | Molding | HFTD Tier 3 | Distribution | 2010-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010754 | 402403327 | Molding | HFTD Tier 3 | Distribution | 2010-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010755 | 402405682 | Bond | HFTD Tier 3 | Distribution | 2010-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010756 | 402406821 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010757 | 402406860 | Insulator | HFTD Tier 2 | Distribution | 2010-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010758 | 402407919 | High Sign | HFTD Tier 2 | Distribution | 2010-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010759 | 402409339 | High Sign | HFTD Tier 2 | Distribution | 2010-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010760 | 402410798 | High Sign | HFTD Tier 2 | Distribution | 2010-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010761 | 402411911 | Molding | HFTD Tier 3 | Distribution | 2010-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010762 | 402412515 | High Sign | HFTD Tier 2 | Distribution | 2010-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010763 | 402413528 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010764 | 402416600 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010765 | 402416602 | High Sign | HFTD Tier 2 | Distribution | 2010-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010766 | 402417383 | High Sign | HFTD Tier 3 | Distribution | 2010-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010767 | 402417521 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010768 | 402418319 | High Sign | HFTD Tier 2 | Distribution | 2010-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010769 | 402418358 | High Sign | HFTD Tier 2 | Distribution | 2010-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010770 | 402418359 | High Sign | HFTD Tier 2 | Distribution | 2010-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010771 | 402418362 | High Sign | HFTD Tier 2 | Distribution | 2010-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010772 | 402418363 | Molding | HFTD Tier 2 | Distribution | 2010-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010773 | 402418369 | High Sign | HFTD Tier 2 | Distribution | 2010-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010774 | 402418370 | High Sign | HFTD Tier 2 | Distribution | 2010-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010775 | 402418376 | High Sign | HFTD Tier 2 | Distribution | 2010-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010776 | 402418379 | High Sign | HFTD Tier 2 | Distribution | 2010-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010777 | 402419287 | High Sign | HFTD Tier 3 | Distribution | 2010-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010778 | 402421264 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010779 | 402423162 | Molding | HFTD Tier 3 | Distribution | 2010-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010780 | 402423215 | Molding | HFTD Tier 3 | Distribution | 2010-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010781 | 402423216 | High Sign | HFTD Tier 3 | Distribution | 2010-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010782 | 402423436 | Molding | HFTD Tier 3 | Distribution | 2010-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010783 | 402423437 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010784 | 402423438 | Molding | HFTD Tier 3 | Distribution | 2010-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010785 | 402423455 | High Sign | HFTD Tier 3 | Distribution | 2010-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010786 | 402423456 | High Sign | HFTD Tier 3 | Distribution | 2010-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010787 | 402423465 | Riser/Conduit | HFTD Tier 3 | Distribution | 2010-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010788 | 402423467 | High Sign | HFTD Tier 3 | Distribution | 2010-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010789 | 402423481 | High Sign | HFTD Tier 3 | Distribution | 2010-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010790 | 402423482 | High Sign | HFTD Tier 3 | Distribution | 2010-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010791 | 402423553 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010792 | 402424105 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010793 | 402424121 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010794 | 402424463 | Riser/Conduit | HFTD Tier 3 | Distribution | 2010-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010795 | 402424759 | High Sign | HFTD Tier 3 | Distribution | 2010-06-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010796 | 402425030 | High Sign | HFTD Tier 3 | Distribution | 2010-06-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010797 | 402429442 | Molding | HFTD Tier 3 | Distribution | 2010-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010798 | 402429451 | High Sign | HFTD Tier 3 | Distribution | 2010-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010799 | 402429857 | Bond | HFTD Tier 3 | Distribution | 2010-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010800 | 402429858 | Bond | HFTD Tier 3 | Distribution | 2010-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010801 | 402429868 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010802 | 402434312 | High Sign | HFTD Tier 2 | Distribution | 2010-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010803 | 402434313 | Molding | HFTD Tier 2 | Distribution | 2010-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010804 | 402434330 | Guy | HFTD Tier 2 | Distribution | 2010-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010805 | 402435618 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010806 | 402435624 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010807 | 402435628 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010808 | 402435632 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010809 | 402436574 | Molding | HFTD Tier 3 | Distribution | 2010-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010810 | 402436621 | Molding | HFTD Tier 3 | Distribution | 2010-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010811 | 402436647 | Molding | HFTD Tier 3 | Distribution | 2010-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010812 | 402439047 | High Sign | HFTD Tier 3 | Distribution | 2010-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010813 | 402440077 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010814 | 402442809 | High Sign | HFTD Tier 3 | Distribution | 2010-06-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010815 | 402442811 | Molding | HFTD Tier 3 | Distribution | 2010-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010816 | 402443154 | High Sign | HFTD Tier 3 | Distribution | 2010-06-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010817 | 402444186 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010818 | 402445054 | Riser/Conduit | HFTD Tier 3 | Distribution | 2010-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010819 | 402445057 | Guy | HFTD Tier 3 | Distribution | 2010-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010820 | 402445059 | Riser/Conduit | HFTD Tier 3 | Distribution | 2010-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010821 | 402447126 | Molding | HFTD Tier 3 | Distribution | 2010-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010822 | 402447500 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010823 | 402451208 | High Sign | HFTD Tier 3 | Distribution | 2010-07-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010824 | 402451209 | High Sign | HFTD Tier 3 | Distribution | 2010-07-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010825 | 402451210 | High Sign | HFTD Tier 3 | Distribution | 2010-07-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010826 | 402451211 | High Sign | HFTD Tier 3 | Distribution | 2010-07-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010827 | 402454450 | Molding | HFTD Tier 2 | Distribution | 2010-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010828 | 402918191 | Molding | HFTD Tier 3 | Distribution | 2010-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010829 | 403009035 | High Sign | HFTD Tier 3 | Distribution | 2010-07-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010830 | 403009036 | High Sign | HFTD Tier 3 | Distribution | 2010-07-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010831 | 403009037 | Bond | HFTD Tier 3 | Distribution | 2010-07-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010832 | 403009046 | Bond | HFTD Tier 3 | Distribution | 2010-07-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010833 | 403009048 | Bond | HFTD Tier 3 | Distribution | 2010-07-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010834 | 403009062 | Bond | HFTD Tier 3 | Distribution | 2010-07-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010835 | 403009064 | Bond | HFTD Tier 3 | Distribution | 2010-07-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010836 | 403012120 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010837 | 403013329 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2010-07-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010838 | 403016170 | Guy | HFTD Tier 2 | Distribution | 2010-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010839 | 403016743 | High Sign | HFTD Tier 3 | Distribution | 2010-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010840 | 403016756 | High Sign | HFTD Tier 3 | Distribution | 2010-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010841 | 403017455 | Molding | HFTD Tier 3 | Distribution | 2010-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010842 | 403027952 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010843 | 403027965 | Anchor | HFTD Tier 2 | Distribution | 2010-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010844 | 403030616 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010845 | 403031628 | High Sign | HFTD Tier 2 | Distribution | 2010-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010846 | 403031630 | High Sign | HFTD Tier 2 | Distribution | 2010-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010847 | 403035057 | Molding | HFTD Tier 3 | Distribution | 2010-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010848 | 403035062 | Bond | HFTD Tier 3 | Distribution | 2010-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010849 | 403035455 | High Sign | HFTD Tier 2 | Distribution | 2010-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010850 | 403035456 | High Sign | HFTD Tier 2 | Distribution | 2010-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010851 | 403035457 | High Sign | HFTD Tier 2 | Distribution | 2010-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010852 | 403035703 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010853 | 403035722 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010854 | 403035724 | High Sign | HFTD Tier 2 | Distribution | 2010-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010855 | 403037744 | High Sign | HFTD Tier 2 | Distribution | 2010-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010856 | 403037745 | High Sign | HFTD Tier 2 | Distribution | 2010-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010857 | 403037746 | High Sign | HFTD Tier 2 | Distribution | 2010-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010858 | 403037747 | High Sign | HFTD Tier 2 | Distribution | 2010-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010859 | 403037756 | High Sign | HFTD Tier 2 | Distribution | 2010-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010860 | 403037758 | High Sign | HFTD Tier 2 | Distribution | 2010-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010861 | 403037766 | High Sign | HFTD Tier 2 | Distribution | 2010-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010862 | 403037770 | High Sign | HFTD Tier 2 | Distribution | 2010-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010863 | 403037771 | High Sign | HFTD Tier 2 | Distribution | 2010-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010864 | 403040222 | Molding | HFTD Tier 3 | Distribution | 2010-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010865 | 403040998 | Molding | HFTD Tier 3 | Distribution | 2010-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010866 | 403042604 | Bond | HFTD Tier 3 | Distribution | 2010-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010867 | 403042610 | High Sign | HFTD Tier 3 | Distribution | 2010-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010868 | 403042613 | High Sign | HFTD Tier 3 | Distribution | 2010-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010869 | 403042831 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010870 | 403042841 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010871 | 403042890 | High Sign | HFTD Tier 2 | Distribution | 2010-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010872 | 403042893 | High Sign | HFTD Tier 2 | Distribution | 2010-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010873 | 403042900 | High Sign | HFTD Tier 2 | Distribution | 2010-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010874 | 403043892 | Guy | HFTD Tier 2 | Distribution | 2010-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010875 | 403043895 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010876 | 403044198 | High Sign | HFTD Tier 3 | Distribution | 2010-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010877 | 403044210 | High Sign | HFTD Tier 3 | Distribution | 2010-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010878 | 403044232 | High Sign | HFTD Tier 3 | Distribution | 2010-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010879 | 403044402 | Molding | HFTD Tier 2 | Distribution | 2010-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010880 | 403044482 | Bond | HFTD Tier 3 | Distribution | 2010-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010881 | 403044617 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010882 | 403044630 | Molding | HFTD Tier 2 | Distribution | 2010-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010883 | 403044631 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010884 | 403044637 | High Sign | HFTD Tier 3 | Distribution | 2010-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010885 | 403045445 | High Sign | HFTD Tier 3 | Distribution | 2010-07-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010886 | 403045446 | Molding | HFTD Tier 3 | Distribution | 2010-07-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010887 | 403045449 | Molding | HFTD Tier 3 | Distribution | 2010-07-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010888 | 403045481 | Riser/Conduit | HFTD Tier 3 | Distribution | 2010-07-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010889 | 403045501 | Molding | HFTD Tier 3 | Distribution | 2010-07-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010890 | 403045543 | Molding | HFTD Tier 2 | Distribution | 2010-07-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010891 | 403045985 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010892 | 403046006 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2005-12-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010893 | 403046022 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-09-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010894 | 403046028 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-11-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010895 | 403046035 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010896 | 403046046 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010897 | 403046057 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-01-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010898 | 403046061 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010899 | 403046063 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010900 | 403046064 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010901 | 403046084 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2003-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010902 | 403046095 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010903 | 403046097 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010904 | 403046100 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010905 | 403046105 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010906 | 403046107 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-01-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010907 | 403046153 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010908 | 403046156 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010909 | 403046181 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010910 | 403046195 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010911 | 403046198 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-01-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010912 | 403046210 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010913 | 403046237 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2005-12-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010914 | 403046263 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010915 | 403046337 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010916 | 403046436 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010917 | 403046480 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2009-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010918 | 403046562 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2003-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010919 | 403046566 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2003-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010920 | 403046690 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2003-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010921 | 403046691 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2003-11-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010922 | 403046700 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2003-11-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010923 | 403046776 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010924 | 403046795 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2003-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010925 | 403046971 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010926 | 403047039 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010927 | 403047041 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010928 | 403047058 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010929 | 403047062 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010930 | 403047065 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010931 | 403047072 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010932 | 403047142 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010933 | 403047145 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-02-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010934 | 403047255 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2004-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010935 | 403047295 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010936 | 403047433 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2004-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010937 | 403047523 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-10-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010938 | 403047573 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-08-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010939 | 403047733 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010940 | 403047884 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2005-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010941 | 403047916 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010942 | 403047940 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2005-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010943 | 403048027 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010944 | 403048134 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2007-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010945 | 403048249 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010946 | 403048567 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2005-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010947 | 403048570 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2005-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010948 | 403048663 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2005-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010949 | 403048664 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010950 | 403048772 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-11-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010951 | 403048781 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2008-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010952 | 403048805 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-11-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010953 | 403048812 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-11-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010954 | 403048843 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010955 | 403048881 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2005-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010956 | 403048890 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2007-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010957 | 403048937 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2009-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010958 | 403050746 | High Sign | HFTD Tier 2 | Distribution | 2010-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010959 | 403050747 | High Sign | HFTD Tier 2 | Distribution | 2010-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010960 | 403050749 | High Sign | HFTD Tier 2 | Distribution | 2010-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010961 | 403050753 | High Sign | HFTD Tier 2 | Distribution | 2010-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010962 | 403050754 | High Sign | HFTD Tier 2 | Distribution | 2010-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010963 | 403050755 | High Sign | HFTD Tier 2 | Distribution | 2010-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010964 | 403050759 | High Sign | HFTD Tier 2 | Distribution | 2010-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010965 | 403050763 | High Sign | HFTD Tier 2 | Distribution | 2010-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010966 | 403050766 | High Sign | HFTD Tier 2 | Distribution | 2010-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010967 | 403050768 | High Sign | HFTD Tier 2 | Distribution | 2010-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010968 | 403050769 | High Sign | HFTD Tier 2 | Distribution | 2010-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010969 | 403051685 | Molding | HFTD Tier 3 | Distribution | 2010-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010970 | 403051751 | High Sign | HFTD Tier 3 | Distribution | 2010-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010971 | 403051753 | High Sign | HFTD Tier 3 | Distribution | 2010-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010972 | 403051980 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-08-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010973 | 403051983 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-08-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010974 | 403052673 | High Sign | HFTD Tier 2 | Distribution | 2010-08-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010975 | 403053859 | High Sign | HFTD Tier 2 | Distribution | 2010-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010976 | 403053870 | High Sign | HFTD Tier 2 | Distribution | 2010-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010977 | 403054037 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2010-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010978 | 403055796 | High Sign | HFTD Tier 2 | Distribution | 2010-08-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010979 | 403055798 | High Sign | HFTD Tier 2 | Distribution | 2010-08-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010980 | 403055805 | High Sign | HFTD Tier 2 | Distribution | 2010-08-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010981 | 403055814 | High Sign | HFTD Tier 2 | Distribution | 2010-08-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010982 | 403055815 | High Sign | HFTD Tier 2 | Distribution | 2010-08-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010983 | 403056857 | High Sign | HFTD Tier 3 | Distribution | 2010-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010984 | 403056872 | Molding | HFTD Tier 3 | Distribution | 2010-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010985 | 403057068 | High Sign | HFTD Tier 3 | Distribution | 2010-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010986 | 403057069 | High Sign | HFTD Tier 3 | Distribution | 2010-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010987 | 403057076 | Guy | HFTD Tier 3 | Distribution | 2010-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010988 | 403057077 | High Sign | HFTD Tier 3 | Distribution | 2010-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010989 | 403057079 | Guy | HFTD Tier 3 | Distribution | 2010-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010990 | 403057088 | High Sign | HFTD Tier 2 | Distribution | 2010-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010991 | 403057090 | Guy | HFTD Tier 3 | Distribution | 2010-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010992 | 403057091 | High Sign | HFTD Tier 3 | Distribution | 2010-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010993 | 403057102 | High Sign | HFTD Tier 2 | Distribution | 2010-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010994 | 403058067 | Molding | HFTD Tier 3 | Distribution | 2010-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010995 | 403058856 | Molding | HFTD Tier 3 | Distribution | 2010-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010996 | 403058861 | Guy | HFTD Tier 3 | Distribution | 2010-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010997 | 403058896 | Molding | HFTD Tier 3 | Distribution | 2010-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010998 | 403059023 | High Sign | HFTD Tier 3 | Distribution | 2010-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130010999 | 403059180 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011000 | 403059196 | Riser/Conduit | HFTD Tier 3 | Distribution | 2010-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011001 | 403060024 | Guy | HFTD Tier 2 | Distribution | 2010-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011002 | 403060025 | High Sign | HFTD Tier 2 | Distribution | 2010-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011003 | 403060027 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2010-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011004 | 403062014 | High Sign | HFTD Tier 2 | Distribution | 2010-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011005 | 403062020 | High Sign | HFTD Tier 2 | Distribution | 2010-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011006 | 403062021 | High Sign | HFTD Tier 2 | Distribution | 2010-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011007 | 403062025 | High Sign | HFTD Tier 2 | Distribution | 2010-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011008 | 403062026 | High Sign | HFTD Tier 2 | Distribution | 2010-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011009 | 403062033 | High Sign | HFTD Tier 2 | Distribution | 2010-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011010 | 403062034 | High Sign | HFTD Tier 2 | Distribution | 2010-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011011 | 403062059 | Molding | HFTD Tier 3 | Distribution | 2010-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011012 | 403062113 | Guy | HFTD Tier 3 | Distribution | 2010-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011013 | 403062129 | High Sign | HFTD Tier 3 | Distribution | 2010-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011014 | 403062133 | High Sign | HFTD Tier 3 | Distribution | 2010-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011015 | 403062141 | High Sign | HFTD Tier 3 | Distribution | 2010-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011016 | 403063122 | Molding | HFTD Tier 3 | Distribution | 2010-08-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011017 | 403064497 | High Sign | HFTD Tier 3 | Distribution | 2010-08-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011018 | 403065686 | High Sign | HFTD Tier 3 | Distribution | 2010-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011019 | 403066384 | High Sign | HFTD Tier 3 | Distribution | 2010-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011020 | 403066386 | High Sign | HFTD Tier 3 | Distribution | 2010-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011021 | 403066387 | High Sign | HFTD Tier 3 | Distribution | 2010-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011022 | 403066388 | High Sign | HFTD Tier 3 | Distribution | 2010-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011023 | 403066395 | High Sign | HFTD Tier 3 | Distribution | 2010-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011024 | 403066555 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011025 | 403066667 | High Sign | HFTD Tier 3 | Distribution | 2010-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011026 | 403067239 | Bond | HFTD Tier 3 | Distribution | 2010-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011027 | 403067769 | Molding | HFTD Tier 3 | Distribution | 2010-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011028 | 403067775 | Molding | HFTD Tier 3 | Distribution | 2010-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011029 | 403067947 | Guy | HFTD Tier 3 | Distribution | 2010-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011030 | 403068701 | High Sign | HFTD Tier 3 | Distribution | 2010-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011031 | 403072972 | Guy | HFTD Tier 3 | Distribution | 2010-08-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011032 | 403072984 | Guy | HFTD Tier 3 | Distribution | 2010-08-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011033 | 403073941 | Guy | HFTD Tier 3 | Distribution | 2010-08-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011034 | 403074762 | Molding | HFTD Tier 2 | Distribution | 2010-08-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011035 | 403076135 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2010-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011036 | 403076287 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011037 | 403076724 | High Sign | HFTD Tier 3 | Distribution | 2010-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011038 | 403076753 | High Sign | HFTD Tier 3 | Distribution | 2010-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011039 | 403077075 | High Sign | HFTD Tier 3 | Distribution | 2010-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011040 | 403077083 | Bond | HFTD Tier 3 | Distribution | 2010-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011041 | 403077090 | High Sign | HFTD Tier 3 | Distribution | 2010-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011042 | 403077091 | Bond | HFTD Tier 3 | Distribution | 2010-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011043 | 403077120 | High Sign | HFTD Tier 3 | Distribution | 2010-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011044 | 403077192 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011045 | 403077283 | High Sign | HFTD Tier 3 | Distribution | 2010-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011046 | 403077291 | Molding | HFTD Tier 3 | Distribution | 2010-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011047 | 403077407 | High Sign | HFTD Tier 3 | Distribution | 2010-08-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011048 | 403077411 | High Sign | HFTD Tier 3 | Distribution | 2010-08-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011049 | 403078367 | Molding | HFTD Tier 3 | Distribution | 2010-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011050 | 403078679 | Guy | HFTD Tier 3 | Distribution | 2010-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011051 | 403078720 | High Sign | HFTD Tier 3 | Distribution | 2010-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011052 | 403078725 | Molding | HFTD Tier 3 | Distribution | 2010-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011053 | 403078856 | Molding | HFTD Tier 3 | Distribution | 2010-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011054 | 403079761 | Molding | HFTD Tier 2 | Distribution | 2010-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011055 | 403079762 | High Sign | HFTD Tier 2 | Distribution | 2010-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011056 | 403079776 | High Sign | HFTD Tier 2 | Distribution | 2010-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011057 | 403079890 | High Sign | HFTD Tier 3 | Distribution | 2010-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011058 | 403080951 | Molding | HFTD Tier 2 | Distribution | 2010-08-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011059 | 403081043 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011060 | 403081099 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011061 | 403081106 | Molding | HFTD Tier 3 | Distribution | 2010-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011062 | 403081473 | Molding | HFTD Tier 2 | Distribution | 2010-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011063 | 403082370 | High Sign | HFTD Tier 2 | Distribution | 2010-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011064 | 403082511 | High Sign | HFTD Tier 2 | Distribution | 2010-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011065 | 403086946 | Molding | HFTD Tier 3 | Distribution | 2010-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011066 | 403087080 | Riser/Conduit | HFTD Tier 2 | Distribution | 2010-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011067 | 403087177 | Guy | HFTD Tier 2 | Distribution | 2010-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011068 | 403087182 | Ground | HFTD Tier 2 | Distribution | 2010-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011069 | 403087188 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011070 | 403087194 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2010-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011071 | 403088866 | Molding | HFTD Tier 2 | Distribution | 2010-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011072 | 403088867 | Riser/Conduit | HFTD Tier 2 | Distribution | 2010-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011073 | 403088868 | Molding | HFTD Tier 2 | Distribution | 2010-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011074 | 403088869 | Bond | HFTD Tier 2 | Distribution | 2010-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011075 | 403088872 | Bond | HFTD Tier 2 | Distribution | 2010-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011076 | 403088880 | Bond | HFTD Tier 2 | Distribution | 2010-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011077 | 403088881 | Molding | HFTD Tier 2 | Distribution | 2010-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011078 | 403089434 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011079 | 403090473 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2010-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011080 | 403090978 | Molding | HFTD Tier 2 | Distribution | 2010-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011081 | 403091918 | High Sign | HFTD Tier 3 | Distribution | 2010-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011082 | 403091919 | Guy | HFTD Tier 3 | Distribution | 2010-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011083 | 403092097 | Molding | HFTD Tier 2 | Distribution | 2010-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011084 | 403092417 | Bond | HFTD Tier 2 | Distribution | 2010-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011085 | 403092418 | Bond | HFTD Tier 2 | Distribution | 2010-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011086 | 403092452 | High Sign | HFTD Tier 3 | Distribution | 2010-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011087 | 403092462 | High Sign | HFTD Tier 3 | Distribution | 2010-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011088 | 403093119 | High Sign | HFTD Tier 2 | Distribution | 2010-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011089 | 403093122 | High Sign | HFTD Tier 2 | Distribution | 2010-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011090 | 403093650 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-08-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011091 | 403093980 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011092 | 403093981 | High Sign | HFTD Tier 3 | Distribution | 2010-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011093 | 403093983 | Molding | HFTD Tier 3 | Distribution | 2010-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011094 | 403093985 | High Sign | HFTD Tier 3 | Distribution | 2010-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011095 | 403094031 | Molding | HFTD Tier 3 | Distribution | 2010-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011096 | 403094053 | Molding | HFTD Tier 3 | Distribution | 2010-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011097 | 403094058 | High Sign | HFTD Tier 3 | Distribution | 2010-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011098 | 403094063 | Molding | HFTD Tier 3 | Distribution | 2010-08-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011099 | 403094133 | Molding | HFTD Tier 3 | Distribution | 2010-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011100 | 403094244 | Guy | HFTD Tier 2 | Distribution | 2010-08-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011101 | 403094630 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-08-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011102 | 403094830 | Molding | HFTD Tier 2 | Distribution | 2010-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011103 | 403094835 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011104 | 403094856 | Molding | HFTD Tier 2 | Distribution | 2010-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011105 | 403094869 | Molding | HFTD Tier 3 | Distribution | 2010-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011106 | 403094888 | Molding | HFTD Tier 2 | Distribution | 2010-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011107 | 403094896 | Molding | HFTD Tier 3 | Distribution | 2010-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011108 | 403094960 | Molding | HFTD Tier 2 | Distribution | 2010-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011109 | 403095001 | Molding | HFTD Tier 2 | Distribution | 2010-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011110 | 403095108 | Molding | HFTD Tier 2 | Distribution | 2010-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011111 | 403095830 | Guy | HFTD Tier 3 | Distribution | 2010-08-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011112 | 403096182 | High Sign | HFTD Tier 3 | Distribution | 2010-08-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011113 | 403096369 | Molding | HFTD Tier 2 | Distribution | 2010-08-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011114 | 403096413 | Guy | HFTD Tier 2 | Distribution | 2010-08-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011115 | 403096417 | High Sign | HFTD Tier 2 | Distribution | 2010-08-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011116 | 403096423 | Ground | HFTD Tier 2 | Distribution | 2010-08-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011117 | 403096446 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-08-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011118 | 403099554 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2010-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011119 | 403101841 | Molding | HFTD Tier 3 | Distribution | 2010-08-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011120 | 403101843 | High Sign | HFTD Tier 3 | Distribution | 2010-08-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011121 | 403102782 | Molding | HFTD Tier 3 | Distribution | 2010-08-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011122 | 403102816 | High Sign | HFTD Tier 3 | Distribution | 2010-08-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011123 | 403103098 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-08-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011124 | 403103244 | Guy | HFTD Tier 3 | Distribution | 2010-08-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011125 | 403106777 | High Sign | HFTD Tier 2 | Distribution | 2010-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011126 | 403106847 | Guy | HFTD Tier 3 | Distribution | 2010-08-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011127 | 403106870 | High Sign | HFTD Tier 3 | Distribution | 2010-08-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011128 | 403106874 | Riser/Conduit | HFTD Tier 3 | Distribution | 2010-08-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011129 | 403106907 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-08-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011130 | 403106923 | Molding | HFTD Tier 2 | Distribution | 2010-09-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011131 | 403106938 | Molding | HFTD Tier 3 | Distribution | 2010-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011132 | 403106939 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011133 | 403106955 | Molding | HFTD Tier 3 | Distribution | 2010-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011134 | 403106997 | Molding | HFTD Tier 3 | Distribution | 2010-08-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011135 | 403107025 | Molding | HFTD Tier 3 | Distribution | 2010-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011136 | 403107066 | Molding | HFTD Tier 3 | Distribution | 2010-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011137 | 403107298 | High Sign | HFTD Tier 3 | Distribution | 2010-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011138 | 403107308 | Crossarm | HFTD Tier 3 | Distribution | 2010-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011139 | 403107319 | High Sign | HFTD Tier 3 | Distribution | 2010-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011140 | 403107330 | Molding | HFTD Tier 3 | Distribution | 2010-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011141 | 403107878 | Molding | HFTD Tier 3 | Distribution | 2010-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011142 | 403109490 | High Sign | HFTD Tier 2 | Distribution | 2010-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011143 | 403109515 | High Sign | HFTD Tier 2 | Distribution | 2010-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011144 | 403109545 | High Sign | HFTD Tier 3 | Distribution | 2010-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011145 | 403110067 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-09-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011146 | 403110074 | Molding | HFTD Tier 2 | Distribution | 2010-09-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011147 | 403110082 | High Sign | HFTD Tier 2 | Distribution | 2010-09-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011148 | 403110141 | Molding | HFTD Tier 2 | Distribution | 2010-09-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011149 | 403110430 | Molding | HFTD Tier 3 | Distribution | 2010-09-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011150 | 403113849 | Vis Strips | HFTD Tier 3 | Distribution | 2010-09-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011151 | 403113850 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-09-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011152 | 403114623 | Guy | HFTD Tier 3 | Distribution | 2010-09-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011153 | 403116160 | Molding | HFTD Tier 3 | Distribution | 2010-09-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011154 | 403116165 | High Sign | HFTD Tier 3 | Distribution | 2010-09-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011155 | 403116187 | Guy | HFTD Tier 3 | Distribution | 2010-09-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011156 | 403116213 | Molding | HFTD Tier 3 | Distribution | 2010-09-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011157 | 403116260 | High Sign | HFTD Tier 3 | Distribution | 2010-09-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011158 | 403116474 | Molding | HFTD Tier 3 | Distribution | 2010-09-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011159 | 403117182 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-09-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011160 | 403117185 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2010-09-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011161 | 403117226 | High Sign | HFTD Tier 3 | Distribution | 2010-09-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011162 | 403117245 | High Sign | HFTD Tier 3 | Distribution | 2010-09-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011163 | 403119602 | Molding | HFTD Tier 3 | Distribution | 2010-09-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011164 | 403119606 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-09-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011165 | 403119895 | High Sign | HFTD Tier 2 | Distribution | 2010-09-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011166 | 403119958 | Molding | HFTD Tier 2 | Distribution | 2010-09-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011167 | 403122534 | Molding | HFTD Tier 2 | Distribution | 2010-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011168 | 403122537 | Molding | HFTD Tier 2 | Distribution | 2010-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011169 | 403126066 | Guy | HFTD Tier 2 | Distribution | 2010-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011170 | 403126093 | High Sign | HFTD Tier 2 | Distribution | 2010-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011171 | 403126100 | Guy | HFTD Tier 2 | Distribution | 2010-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011172 | 403126213 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011173 | 403128566 | High Sign | HFTD Tier 2 | Distribution | 2010-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011174 | 403128573 | High Sign | HFTD Tier 2 | Distribution | 2010-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011175 | 403128574 | High Sign | HFTD Tier 2 | Distribution | 2010-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011176 | 403128605 | High Sign | HFTD Tier 2 | Distribution | 2010-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011177 | 403128609 | High Sign | HFTD Tier 2 | Distribution | 2010-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011178 | 403128612 | High Sign | HFTD Tier 2 | Distribution | 2010-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011179 | 403128615 | High Sign | HFTD Tier 2 | Distribution | 2010-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011180 | 403128620 | High Sign | HFTD Tier 2 | Distribution | 2010-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011181 | 403128623 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011182 | 403128631 | Molding | HFTD Tier 2 | Distribution | 2010-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011183 | 403128667 | Crossarm | HFTD Tier 2 | Distribution | 2010-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011184 | 403131334 | High Sign | HFTD Tier 2 | Distribution | 2010-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011185 | 403131354 | Molding | HFTD Tier 2 | Distribution | 2010-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011186 | 403131372 | Molding | HFTD Tier 2 | Distribution | 2010-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011187 | 403131419 | Molding | HFTD Tier 2 | Distribution | 2010-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011188 | 403131421 | Molding | HFTD Tier 3 | Distribution | 2010-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011189 | 403131482 | High Sign | HFTD Tier 2 | Distribution | 2010-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011190 | 403131513 | Molding | HFTD Tier 2 | Distribution | 2010-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011191 | 403131547 | High Sign | HFTD Tier 2 | Distribution | 2010-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011192 | 403131548 | High Sign | HFTD Tier 2 | Distribution | 2010-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011193 | 403131557 | High Sign | HFTD Tier 2 | Distribution | 2010-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011194 | 403131581 | Guy | HFTD Tier 2 | Distribution | 2010-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011195 | 403131582 | High Sign | HFTD Tier 2 | Distribution | 2010-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011196 | 403131585 | High Sign | HFTD Tier 2 | Distribution | 2010-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011197 | 403131593 | Molding | HFTD Tier 2 | Distribution | 2010-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011198 | 403131698 | Molding | HFTD Tier 2 | Distribution | 2010-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011199 | 403131712 | High Sign | HFTD Tier 2 | Distribution | 2010-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011200 | 403131718 | High Sign | HFTD Tier 2 | Distribution | 2010-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011201 | 403131732 | Molding | HFTD Tier 2 | Distribution | 2010-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011202 | 403131737 | High Sign | HFTD Tier 2 | Distribution | 2010-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011203 | 403131781 | Riser/Conduit | HFTD Tier 2 | Distribution | 2010-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011204 | 403131783 | High Sign | HFTD Tier 2 | Distribution | 2010-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011205 | 403131784 | High Sign | HFTD Tier 2 | Distribution | 2010-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011206 | 403131811 | High Sign | HFTD Tier 2 | Distribution | 2010-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011207 | 403131813 | High Sign | HFTD Tier 2 | Distribution | 2010-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011208 | 403131814 | High Sign | HFTD Tier 2 | Distribution | 2010-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011209 | 403132101 | High Sign | HFTD Tier 2 | Distribution | 2010-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011210 | 403132108 | High Sign | HFTD Tier 2 | Distribution | 2010-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011211 | 403132127 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2010-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011212 | 403132489 | Guy | HFTD Tier 3 | Distribution | 2010-09-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011213 | 403132515 | Guy | HFTD Tier 3 | Distribution | 2010-09-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011214 | 403132995 | High Sign | HFTD Tier 2 | Distribution | 2010-09-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011215 | 403133641 | Molding | HFTD Tier 3 | Distribution | 2010-09-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011216 | 403133663 | High Sign | HFTD Tier 3 | Distribution | 2010-09-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011217 | 403134501 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-09-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011218 | 403134505 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-09-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011219 | 403134511 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-09-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011220 | 403134512 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-09-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011221 | 403134537 | High Sign | HFTD Tier 2 | Distribution | 2010-09-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011222 | 403134544 | High Sign | HFTD Tier 2 | Distribution | 2010-09-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011223 | 403134569 | Bond | HFTD Tier 2 | Distribution | 2010-09-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011224 | 403134578 | High Sign | HFTD Tier 2 | Distribution | 2010-09-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011225 | 403134610 | High Sign | HFTD Tier 2 | Distribution | 2010-09-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011226 | 403134646 | High Sign | HFTD Tier 2 | Distribution | 2010-09-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011227 | 403134647 | Molding | HFTD Tier 2 | Distribution | 2010-09-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011228 | 403136317 | Molding | HFTD Tier 3 | Distribution | 2010-09-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011229 | 403136679 | High Sign | HFTD Tier 3 | Distribution | 2010-09-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011230 | 403136681 | Molding | HFTD Tier 3 | Distribution | 2010-09-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011231 | 403137675 | High Sign | HFTD Tier 3 | Distribution | 2010-09-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011232 | 403138656 | Molding | HFTD Tier 3 | Distribution | 2010-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011233 | 403138657 | High Sign | HFTD Tier 3 | Distribution | 2010-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011234 | 403138880 | Molding | HFTD Tier 3 | Distribution | 2010-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011235 | 403138900 | Molding | HFTD Tier 3 | Distribution | 2010-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011236 | 403139997 | Riser/Conduit | HFTD Tier 2 | Distribution | 2010-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011237 | 403141234 | Molding | HFTD Tier 3 | Distribution | 2010-09-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011238 | 403141455 | Molding | HFTD Tier 3 | Distribution | 2010-09-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011239 | 403151551 | High Sign | HFTD Tier 3 | Distribution | 2010-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011240 | 403151562 | Molding | HFTD Tier 2 | Distribution | 2010-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011241 | 403151571 | High Sign | HFTD Tier 2 | Distribution | 2010-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011242 | 403151600 | Molding | HFTD Tier 2 | Distribution | 2010-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011243 | 403151603 | Guy | HFTD Tier 2 | Distribution | 2010-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011244 | 403153199 | Molding | HFTD Tier 3 | Distribution | 2010-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011245 | 403153206 | High Sign | HFTD Tier 3 | Distribution | 2010-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011246 | 403154000 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011247 | 403154542 | High Sign | HFTD Tier 3 | Distribution | 2010-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011248 | 403154548 | Molding | HFTD Tier 3 | Distribution | 2010-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011249 | 403154589 | High Sign | HFTD Tier 2 | Distribution | 2010-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011250 | 403155395 | Molding | HFTD Tier 3 | Distribution | 2010-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011251 | 403155405 | High Sign | HFTD Tier 3 | Distribution | 2010-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011252 | 403155537 | Molding | HFTD Tier 2 | Distribution | 2010-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011253 | 403156089 | Molding | HFTD Tier 3 | Distribution | 2010-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011254 | 403156125 | High Sign | HFTD Tier 3 | Distribution | 2010-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011255 | 403156128 | High Sign | HFTD Tier 3 | Distribution | 2010-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011256 | 403156135 | High Sign | HFTD Tier 3 | Distribution | 2010-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011257 | 403157289 | Molding | HFTD Tier 3 | Distribution | 2010-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011258 | 403157487 | Molding | HFTD Tier 3 | Distribution | 2010-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011259 | 403163027 | Molding | HFTD Tier 2 | Distribution | 2010-10-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011260 | 403163059 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-10-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011261 | 403163075 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-10-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011262 | 403163799 | Molding | HFTD Tier 3 | Distribution | 2010-10-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011263 | 403163835 | Guy | HFTD Tier 3 | Distribution | 2010-10-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011264 | 403168456 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011265 | 403168490 | Molding | HFTD Tier 2 | Distribution | 2010-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011266 | 403168500 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011267 | 403168502 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011268 | 403168511 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011269 | 403170438 | High Sign | HFTD Tier 2 | Distribution | 2010-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011270 | 403170441 | Molding | HFTD Tier 2 | Distribution | 2010-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011271 | 403171808 | Molding | HFTD Tier 2 | Distribution | 2010-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011272 | 403171809 | Molding | HFTD Tier 2 | Distribution | 2010-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011273 | 403171829 | High Sign | HFTD Tier 2 | Distribution | 2010-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011274 | 403171833 | High Sign | HFTD Tier 2 | Distribution | 2010-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011275 | 403172301 | Molding | HFTD Tier 2 | Distribution | 2010-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011276 | 403172302 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011277 | 403172424 | Molding | HFTD Tier 3 | Distribution | 2010-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011278 | 403172426 | Molding | HFTD Tier 3 | Distribution | 2010-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011279 | 403172430 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011280 | 403172432 | High Sign | HFTD Tier 3 | Distribution | 2010-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011281 | 403172437 | High Sign | HFTD Tier 3 | Distribution | 2010-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011282 | 403172438 | Molding | HFTD Tier 3 | Distribution | 2010-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011283 | 403172488 | Molding | HFTD Tier 2 | Distribution | 2010-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011284 | 403172500 | Guy | HFTD Tier 2 | Distribution | 2010-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011285 | 403173704 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011286 | 403174004 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011287 | 403174536 | Molding | HFTD Tier 2 | Distribution | 2010-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011288 | 403174538 | High Sign | HFTD Tier 2 | Distribution | 2010-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011289 | 403174553 | Molding | HFTD Tier 2 | Distribution | 2010-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011290 | 403174556 | High Sign | HFTD Tier 2 | Distribution | 2010-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011291 | 403174558 | Molding | HFTD Tier 2 | Distribution | 2010-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011292 | 403174571 | High Sign | HFTD Tier 2 | Distribution | 2010-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011293 | 403174663 | High Sign | HFTD Tier 2 | Distribution | 2010-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011294 | 403174681 | High Sign | HFTD Tier 2 | Distribution | 2010-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011295 | 403175061 | High Sign | HFTD Tier 3 | Distribution | 2010-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011296 | 403180304 | Guy | HFTD Tier 3 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011297 | 403181757 | Molding | HFTD Tier 3 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011298 | 403181774 | Molding | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011299 | 403181775 | High Sign | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011300 | 403181776 | High Sign | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011301 | 403181777 | Molding | HFTD Tier 3 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011302 | 403181778 | Molding | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011303 | 403181782 | Ground | HFTD Tier 3 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011304 | 403181785 | Molding | HFTD Tier 3 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011305 | 403181792 | Molding | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011306 | 403181793 | Molding | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011307 | 403181796 | Molding | HFTD Tier 3 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011308 | 403181797 | Molding | HFTD Tier 3 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011309 | 403181804 | Molding | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011310 | 403181811 | Molding | HFTD Tier 3 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011311 | 403181812 | Molding | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011312 | 403182155 | Molding | HFTD Tier 3 | Distribution | 2010-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011313 | 403182162 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011314 | 403182164 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011315 | 403182165 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011316 | 403182187 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011317 | 403182189 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011318 | 403182196 | Molding | HFTD Tier 3 | Distribution | 2010-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011319 | 403182224 | Guy | HFTD Tier 3 | Distribution | 2010-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011320 | 403182257 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011321 | 403183267 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011322 | 403183268 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011323 | 403183292 | High Sign | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011324 | 403183293 | High Sign | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011325 | 403183294 | High Sign | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011326 | 403183296 | High Sign | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011327 | 403183297 | Molding | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011328 | 403183298 | High Sign | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011329 | 403183299 | High Sign | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011330 | 403183300 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011331 | 403183303 | High Sign | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011332 | 403183304 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011333 | 403183306 | High Sign | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011334 | 403183307 | High Sign | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011335 | 403183308 | High Sign | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011336 | 403183309 | High Sign | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011337 | 403183320 | High Sign | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011338 | 403183321 | High Sign | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011339 | 403183322 | Molding | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011340 | 403183323 | High Sign | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011341 | 403183326 | Molding | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011342 | 403183337 | Molding | HFTD Tier 2 | Distribution | 2010-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011343 | 403183339 | High Sign | HFTD Tier 2 | Distribution | 2010-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011344 | 403183345 | Guy | HFTD Tier 2 | Distribution | 2010-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011345 | 403183358 | High Sign | HFTD Tier 2 | Distribution | 2010-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011346 | 403183367 | High Sign | HFTD Tier 2 | Distribution | 2010-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011347 | 403183894 | High Sign | HFTD Tier 3 | Distribution | 2010-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011348 | 403183933 | Molding | HFTD Tier 3 | Distribution | 2010-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011349 | 403183949 | High Sign | HFTD Tier 3 | Distribution | 2010-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011350 | 403183957 | Molding | HFTD Tier 3 | Distribution | 2010-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011351 | 403183959 | Molding | HFTD Tier 3 | Distribution | 2010-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011352 | 403183962 | Molding | HFTD Tier 3 | Distribution | 2010-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011353 | 403184459 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011354 | 403184473 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011355 | 403184599 | Molding | HFTD Tier 3 | Distribution | 2010-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011356 | 403184617 | High Sign | HFTD Tier 3 | Distribution | 2010-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011357 | 403184619 | Molding | HFTD Tier 3 | Distribution | 2010-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011358 | 403184685 | Molding | HFTD Tier 3 | Distribution | 2010-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011359 | 403184686 | Molding | HFTD Tier 3 | Distribution | 2010-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011360 | 403184689 | Guy | HFTD Tier 3 | Distribution | 2010-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011361 | 403185929 | High Sign | HFTD Tier 2 | Distribution | 2010-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011362 | 403186006 | High Sign | HFTD Tier 2 | Distribution | 2010-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011363 | 403186014 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2010-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011364 | 403186451 | Molding | HFTD Tier 2 | Distribution | 2010-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011365 | 403186460 | High Sign | HFTD Tier 2 | Distribution | 2010-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011366 | 403186587 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-10-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011367 | 403187612 | Molding | HFTD Tier 2 | Distribution | 2010-10-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011368 | 403194830 | Molding | HFTD Tier 2 | Distribution | 2010-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011369 | 403194868 | Molding | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011370 | 403194882 | High Sign | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011371 | 403195027 | Molding | HFTD Tier 2 | Distribution | 2010-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011372 | 403195215 | High Sign | HFTD Tier 2 | Distribution | 2010-10-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011373 | 403195352 | Molding | HFTD Tier 2 | Distribution | 2010-10-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011374 | 403195928 | Molding | HFTD Tier 2 | Distribution | 2010-10-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011375 | 403202250 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011376 | 403202285 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2010-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011377 | 403203835 | High Sign | HFTD Tier 2 | Distribution | 2010-10-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011378 | 403204096 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-10-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011379 | 403204355 | Riser/Conduit | HFTD Tier 2 | Distribution | 2010-10-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011380 | 403205251 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-10-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011381 | 403211553 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-10-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011382 | 403211859 | Guy | HFTD Tier 2 | Distribution | 2010-10-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011383 | 403211870 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2010-10-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011384 | 403213033 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-10-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011385 | 403215293 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011386 | 403215297 | Molding | HFTD Tier 2 | Distribution | 2010-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011387 | 403215306 | Molding | HFTD Tier 2 | Distribution | 2010-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011388 | 403215338 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011389 | 403216678 | Guy | HFTD Tier 2 | Distribution | 2010-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011390 | 403216723 | Molding | HFTD Tier 2 | Distribution | 2010-10-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011391 | 403216742 | Molding | HFTD Tier 2 | Distribution | 2010-10-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011392 | 403216747 | High Sign | HFTD Tier 2 | Distribution | 2010-10-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011393 | 403216758 | High Sign | HFTD Tier 2 | Distribution | 2010-10-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011394 | 403216759 | High Sign | HFTD Tier 2 | Distribution | 2010-10-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011395 | 403216783 | High Sign | HFTD Tier 2 | Distribution | 2010-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011396 | 403216795 | Molding | HFTD Tier 2 | Distribution | 2010-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011397 | 403218125 | Guy | HFTD Tier 3 | Distribution | 2010-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011398 | 403218144 | High Sign | HFTD Tier 3 | Distribution | 2010-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011399 | 403218817 | High Sign | HFTD Tier 2 | Distribution | 2010-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011400 | 403218842 | High Sign | HFTD Tier 2 | Distribution | 2010-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011401 | 403218846 | High Sign | HFTD Tier 2 | Distribution | 2010-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011402 | 403218870 | Riser/Conduit | HFTD Tier 2 | Distribution | 2010-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011403 | 403220039 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011404 | 403220081 | Guy | HFTD Tier 2 | Distribution | 2010-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011405 | 403222040 | High Sign | HFTD Tier 2 | Distribution | 2010-10-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011406 | 403222305 | Guy | HFTD Tier 3 | Distribution | 2010-10-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011407 | 403225708 | Molding | HFTD Tier 2 | Distribution | 2010-11-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011408 | 403225709 | High Sign | HFTD Tier 2 | Distribution | 2010-11-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011409 | 403227772 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-11-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011410 | 403227784 | High Sign | HFTD Tier 3 | Distribution | 2010-11-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011411 | 403229432 | Molding | HFTD Tier 2 | Distribution | 2010-11-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011412 | 403229955 | Riser/Conduit | HFTD Tier 2 | Distribution | 2010-11-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011413 | 403229960 | Molding | HFTD Tier 2 | Distribution | 2010-11-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011414 | 403230199 | Molding | HFTD Tier 3 | Distribution | 2010-11-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011415 | 403230394 | High Sign | HFTD Tier 2 | Distribution | 2010-11-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011416 | 403230855 | Riser/Conduit | HFTD Tier 3 | Distribution | 2010-11-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011417 | 403230887 | Molding | HFTD Tier 3 | Distribution | 2010-11-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011418 | 403231698 | Ground | HFTD Tier 3 | Distribution | 2010-11-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011419 | 403231742 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-11-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011420 | 403231963 | Molding | HFTD Tier 3 | Distribution | 2010-11-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011421 | 403231966 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-11-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011422 | 403231968 | Molding | HFTD Tier 3 | Distribution | 2010-11-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011423 | 403233794 | Molding | HFTD Tier 2 | Distribution | 2010-11-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011424 | 403238556 | Molding | HFTD Tier 3 | Distribution | 2010-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011425 | 403238600 | Molding | HFTD Tier 3 | Distribution | 2010-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011426 | 403238673 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011427 | 403238692 | Molding | HFTD Tier 2 | Distribution | 2010-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011428 | 403240439 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011429 | 403240450 | High Sign | HFTD Tier 3 | Distribution | 2010-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011430 | 403240598 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011431 | 403240709 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011432 | 403240717 | Molding | HFTD Tier 3 | Distribution | 2010-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011433 | 403242373 | Molding | HFTD Tier 3 | Distribution | 2010-11-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011434 | 403243289 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2010-11-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011435 | 403244327 | Guy | HFTD Tier 3 | Distribution | 2010-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011436 | 403248242 | Molding | HFTD Tier 2 | Distribution | 2010-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011437 | 403248448 | Molding | HFTD Tier 3 | Distribution | 2010-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011438 | 403248632 | Crossarm | HFTD Tier 3 | Distribution | 2010-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011439 | 403250854 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2010-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011440 | 403251914 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-11-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011441 | 403253517 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-11-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011442 | 403253610 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-11-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011443 | 403255716 | Molding | HFTD Tier 3 | Distribution | 2010-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011444 | 403272810 | Molding | HFTD Tier 3 | Distribution | 2010-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011445 | 403273193 | High Sign | HFTD Tier 3 | Distribution | 2010-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011446 | 403284564 | High Sign | HFTD Tier 2 | Distribution | 2010-11-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011447 | 403284565 | High Sign | HFTD Tier 2 | Distribution | 2010-11-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011448 | 403284570 | High Sign | HFTD Tier 2 | Distribution | 2010-11-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011449 | 403284572 | High Sign | HFTD Tier 2 | Distribution | 2010-11-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011450 | 403284573 | High Sign | HFTD Tier 2 | Distribution | 2010-11-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011451 | 403284576 | High Sign | HFTD Tier 2 | Distribution | 2010-11-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011452 | 403284578 | High Sign | HFTD Tier 2 | Distribution | 2010-11-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011453 | 403284608 | High Sign | HFTD Tier 2 | Distribution | 2010-11-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011454 | 403284633 | High Sign | HFTD Tier 2 | Distribution | 2010-11-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011455 | 403285512 | Molding | HFTD Tier 3 | Distribution | 2010-11-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011456 | 403285531 | Ground | HFTD Tier 3 | Distribution | 2010-11-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011457 | 403285542 | Molding | HFTD Tier 3 | Distribution | 2010-11-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011458 | 403285912 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-11-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011459 | 403285913 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-11-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011460 | 403285914 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-11-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011461 | 403288629 | High Sign | HFTD Tier 2 | Distribution | 2010-11-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011462 | 403288634 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-11-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011463 | 403291418 | Guy | HFTD Tier 3 | Distribution | 2010-11-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011464 | 403291434 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-11-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011465 | 403291445 | Molding | HFTD Tier 2 | Distribution | 2010-11-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011466 | 403291446 | High Sign | HFTD Tier 2 | Distribution | 2010-11-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011467 | 403291459 | High Sign | HFTD Tier 3 | Distribution | 2010-11-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011468 | 403291469 | High Sign | HFTD Tier 2 | Distribution | 2010-11-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011469 | 403293913 | Riser/Conduit | HFTD Tier 3 | Distribution | 2010-12-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011470 | 403294275 | High Sign | HFTD Tier 3 | Distribution | 2010-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011471 | 403294302 | High Sign | HFTD Tier 2 | Distribution | 2010-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011472 | 403294327 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-12-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011473 | 403294328 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-12-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011474 | 403294331 | High Sign | HFTD Tier 2 | Distribution | 2010-12-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011475 | 403294333 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-12-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011476 | 403294335 | High Sign | HFTD Tier 2 | Distribution | 2010-12-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011477 | 403294342 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-12-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011478 | 403294347 | High Sign | HFTD Tier 2 | Distribution | 2010-12-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011479 | 403294354 | High Sign | HFTD Tier 2 | Distribution | 2010-12-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011480 | 403294358 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-12-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011481 | 403294426 | Guy | HFTD Tier 2 | Distribution | 2010-12-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011482 | 403294438 | High Sign | HFTD Tier 2 | Distribution | 2010-12-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011483 | 403294822 | High Sign | HFTD Tier 3 | Distribution | 2010-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011484 | 403299826 | Molding | HFTD Tier 2 | Distribution | 2010-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011485 | 403299839 | High Sign | HFTD Tier 2 | Distribution | 2010-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011486 | 403299864 | High Sign | HFTD Tier 2 | Distribution | 2010-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011487 | 403300997 | High Sign | HFTD Tier 2 | Distribution | 2010-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011488 | 403301207 | High Sign | HFTD Tier 2 | Distribution | 2010-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011489 | 403301211 | High Sign | HFTD Tier 3 | Distribution | 2010-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011490 | 403301213 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011491 | 403301214 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011492 | 403301215 | High Sign | HFTD Tier 2 | Distribution | 2010-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011493 | 403310442 | Molding | HFTD Tier 2 | Distribution | 2010-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011494 | 403310630 | Anchor | HFTD Tier 2 | Distribution | 2010-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011495 | 403310640 | Molding | HFTD Tier 2 | Distribution | 2010-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011496 | 403310939 | High Sign | HFTD Tier 2 | Distribution | 2010-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011497 | 403310945 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011498 | 403310957 | High Sign | HFTD Tier 2 | Distribution | 2010-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011499 | 403311105 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011500 | 403313632 | High Sign | HFTD Tier 2 | Distribution | 2010-12-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011501 | 403314116 | High Sign | HFTD Tier 3 | Distribution | 2010-12-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011502 | 403314150 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2010-12-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011503 | 403315333 | High Sign | HFTD Tier 3 | Distribution | 2010-12-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011504 | 403315348 | High Sign | HFTD Tier 3 | Distribution | 2010-12-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011505 | 403315376 | Molding | HFTD Tier 3 | Distribution | 2010-12-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011506 | 403315385 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-12-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011507 | 403315483 | Ground | HFTD Tier 3 | Distribution | 2010-12-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011508 | 403321238 | High Sign | HFTD Tier 2 | Distribution | 2010-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011509 | 403321283 | High Sign | HFTD Tier 2 | Distribution | 2010-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011510 | 403321284 | High Sign | HFTD Tier 2 | Distribution | 2010-12-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011511 | 403322688 | High Sign | HFTD Tier 3 | Distribution | 2010-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011512 | 403323140 | Molding | HFTD Tier 2 | Distribution | 2010-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011513 | 403323235 | Molding | HFTD Tier 2 | Distribution | 2010-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011514 | 403323243 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011515 | 403323395 | Riser/Conduit | HFTD Tier 2 | Distribution | 2010-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011516 | 403323855 | High Sign | HFTD Tier 3 | Distribution | 2010-12-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011517 | 403323862 | High Sign | HFTD Tier 3 | Distribution | 2010-12-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011518 | 403323864 | High Sign | HFTD Tier 3 | Distribution | 2010-12-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011519 | 403324403 | Molding | HFTD Tier 2 | Distribution | 2010-12-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011520 | 403324791 | Guy | HFTD Tier 3 | Distribution | 2010-12-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011521 | 403324813 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-12-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011522 | 403324965 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-12-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011523 | 403325801 | Guy | HFTD Tier 2 | Distribution | 2010-12-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011524 | 403325919 | High Sign | HFTD Tier 3 | Distribution | 2010-12-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011525 | 403338911 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2010-12-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011526 | 403339162 | Molding | HFTD Tier 3 | Distribution | 2010-12-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011527 | 403339541 | Molding | HFTD Tier 3 | Distribution | 2010-12-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011528 | 403347014 | High Sign | HFTD Tier 2 | Distribution | 2010-12-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011529 | 403347694 | Molding | HFTD Tier 3 | Distribution | 2010-12-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011530 | 403347728 | High Sign | HFTD Tier 2 | Distribution | 2010-12-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011531 | 403347738 | High Sign | HFTD Tier 2 | Distribution | 2010-12-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011532 | 403347740 | Molding | HFTD Tier 2 | Distribution | 2010-12-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011533 | 403347932 | Molding | HFTD Tier 3 | Distribution | 2010-12-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011534 | 403348365 | High Sign | HFTD Tier 3 | Distribution | 2010-12-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011535 | 403348381 | High Sign | HFTD Tier 3 | Distribution | 2010-12-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011536 | 403353765 | High Sign | HFTD Tier 2 | Distribution | 2011-01-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011537 | 403353766 | Molding | HFTD Tier 2 | Distribution | 2011-01-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011538 | 403353967 | High Sign | HFTD Tier 2 | Distribution | 2011-01-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011539 | 403354007 | High Sign | HFTD Tier 3 | Distribution | 2011-01-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011540 | 403354008 | High Sign | HFTD Tier 3 | Distribution | 2011-01-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011541 | 403354032 | High Sign | HFTD Tier 3 | Distribution | 2011-01-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011542 | 403354358 | High Sign | HFTD Tier 3 | Distribution | 2011-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011543 | 403354381 | Molding | HFTD Tier 3 | Distribution | 2011-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011544 | 403354460 | Pole Tag | HFTD Tier 3 | Distribution | 2011-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011545 | 403354519 | High Sign | HFTD Tier 3 | Distribution | 2011-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011546 | 403354567 | High Sign | HFTD Tier 2 | Distribution | 2011-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011547 | 403355355 | High Sign | HFTD Tier 2 | Distribution | 2011-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011548 | 403355356 | Molding | HFTD Tier 2 | Distribution | 2011-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011549 | 403355357 | Molding | HFTD Tier 2 | Distribution | 2011-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011550 | 403355364 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011551 | 403355407 | Molding | HFTD Tier 2 | Distribution | 2011-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011552 | 403355437 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011553 | 403355800 | High Sign | HFTD Tier 2 | Distribution | 2011-01-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011554 | 403355806 | Molding | HFTD Tier 3 | Distribution | 2011-01-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011555 | 403355824 | Insulator | HFTD Tier 3 | Distribution | 2011-01-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011556 | 403355863 | Molding | HFTD Tier 3 | Distribution | 2011-01-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011557 | 403355865 | Molding | HFTD Tier 3 | Distribution | 2011-01-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011558 | 403356248 | Molding | HFTD Tier 3 | Distribution | 2011-01-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011559 | 403356258 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-01-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011560 | 403356259 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-01-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011561 | 403356968 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-01-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011562 | 403356995 | Molding | HFTD Tier 2 | Distribution | 2011-01-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011563 | 403357067 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-01-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011564 | 403357069 | Insulator | HFTD Tier 2 | Distribution | 2011-01-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011565 | 403357337 | High Sign | HFTD Tier 3 | Distribution | 2011-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011566 | 403357365 | High Sign | HFTD Tier 3 | Distribution | 2011-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011567 | 403357428 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-01-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011568 | 403357687 | High Sign | HFTD Tier 2 | Distribution | 2011-01-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011569 | 403357691 | Molding | HFTD Tier 2 | Distribution | 2011-01-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011570 | 403357695 | High Sign | HFTD Tier 3 | Distribution | 2011-01-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011571 | 403357698 | Molding | HFTD Tier 3 | Distribution | 2011-01-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011572 | 403357699 | High Sign | HFTD Tier 3 | Distribution | 2011-01-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011573 | 403357830 | High Sign | HFTD Tier 3 | Distribution | 2011-01-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011574 | 403357839 | High Sign | HFTD Tier 3 | Distribution | 2011-01-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011575 | 403357849 | High Sign | HFTD Tier 3 | Distribution | 2011-01-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011576 | 403358345 | Molding | HFTD Tier 2 | Distribution | 2011-01-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011577 | 403358346 | Molding | HFTD Tier 2 | Distribution | 2011-01-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011578 | 403358357 | High Sign | HFTD Tier 2 | Distribution | 2011-01-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011579 | 403358409 | Molding | HFTD Tier 2 | Distribution | 2011-01-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011580 | 403358425 | Molding | HFTD Tier 2 | Distribution | 2011-01-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011581 | 403359118 | High Sign | HFTD Tier 3 | Distribution | 2011-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011582 | 403359121 | Molding | HFTD Tier 3 | Distribution | 2011-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011583 | 403359160 | High Sign | HFTD Tier 3 | Distribution | 2011-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011584 | 403359313 | High Sign | HFTD Tier 2 | Distribution | 2011-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011585 | 403359587 | Molding | HFTD Tier 2 | Distribution | 2011-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011586 | 403359593 | High Sign | HFTD Tier 2 | Distribution | 2011-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011587 | 403360903 | High Sign | HFTD Tier 3 | Distribution | 2011-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011588 | 403361253 | High Sign | HFTD Tier 3 | Distribution | 2011-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011589 | 403361256 | High Sign | HFTD Tier 3 | Distribution | 2011-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011590 | 403361370 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011591 | 403361524 | Molding | HFTD Tier 3 | Distribution | 2011-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011592 | 403361546 | Molding | HFTD Tier 3 | Distribution | 2011-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011593 | 403361582 | High Sign | HFTD Tier 3 | Distribution | 2011-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011594 | 403361909 | Molding | HFTD Tier 2 | Distribution | 2011-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011595 | 403362467 | High Sign | HFTD Tier 2 | Distribution | 2011-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011596 | 403362468 | High Sign | HFTD Tier 2 | Distribution | 2011-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011597 | 403362470 | High Sign | HFTD Tier 2 | Distribution | 2011-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011598 | 403362485 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011599 | 403363075 | Molding | HFTD Tier 2 | Distribution | 2011-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011600 | 403363093 | High Sign | HFTD Tier 2 | Distribution | 2011-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011601 | 403363105 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011602 | 403363135 | Molding | HFTD Tier 3 | Distribution | 2011-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011603 | 403363973 | High Sign | HFTD Tier 2 | Distribution | 2011-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011604 | 403364433 | Molding | HFTD Tier 2 | Distribution | 2011-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011605 | 403364894 | High Sign | HFTD Tier 2 | Distribution | 2011-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011606 | 403364942 | Molding | HFTD Tier 2 | Distribution | 2011-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011607 | 403365000 | Molding | HFTD Tier 3 | Distribution | 2011-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011608 | 403365142 | Molding | HFTD Tier 2 | Distribution | 2011-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011609 | 403365367 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011610 | 403365782 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011611 | 403366847 | Molding | HFTD Tier 2 | Distribution | 2011-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011612 | 403366922 | High Sign | HFTD Tier 2 | Distribution | 2011-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011613 | 403366931 | Molding | HFTD Tier 2 | Distribution | 2011-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011614 | 403366944 | Molding | HFTD Tier 2 | Distribution | 2011-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011615 | 403367510 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011616 | 403367531 | Molding | HFTD Tier 2 | Distribution | 2011-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011617 | 403367857 | High Sign | HFTD Tier 2 | Distribution | 2011-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011618 | 403368250 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011619 | 403368616 | Guy | HFTD Tier 2 | Distribution | 2011-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011620 | 403368617 | Molding | HFTD Tier 2 | Distribution | 2011-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011621 | 403368618 | High Sign | HFTD Tier 2 | Distribution | 2011-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011622 | 403368619 | Molding | HFTD Tier 2 | Distribution | 2011-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011623 | 403368649 | High Sign | HFTD Tier 2 | Distribution | 2011-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011624 | 403368692 | High Sign | HFTD Tier 3 | Distribution | 2011-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011625 | 403368779 | Molding | HFTD Tier 3 | Distribution | 2011-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011626 | 403368785 | Molding | HFTD Tier 3 | Distribution | 2011-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011627 | 403368860 | High Sign | HFTD Tier 2 | Distribution | 2011-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011628 | 403368879 | High Sign | HFTD Tier 2 | Distribution | 2011-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011629 | 403368885 | High Sign | HFTD Tier 2 | Distribution | 2011-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011630 | 403368912 | Molding | HFTD Tier 2 | Distribution | 2011-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011631 | 403369328 | High Sign | HFTD Tier 2 | Distribution | 2011-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011632 | 403369471 | Molding | HFTD Tier 2 | Distribution | 2011-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011633 | 403369664 | Molding | HFTD Tier 2 | Distribution | 2011-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011634 | 403369677 | High Sign | HFTD Tier 2 | Distribution | 2011-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011635 | 403370838 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011636 | 403370971 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011637 | 403371037 | High Sign | HFTD Tier 2 | Distribution | 2011-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011638 | 403371050 | High Sign | HFTD Tier 2 | Distribution | 2011-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011639 | 403371062 | High Sign | HFTD Tier 2 | Distribution | 2011-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011640 | 403371068 | Guy | HFTD Tier 2 | Distribution | 2011-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011641 | 403371790 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011642 | 403371893 | Guy | HFTD Tier 2 | Distribution | 2011-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011643 | 403371910 | Guy | HFTD Tier 2 | Distribution | 2011-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011644 | 403372129 | Molding | HFTD Tier 2 | Distribution | 2011-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011645 | 403372642 | Molding | HFTD Tier 3 | Distribution | 2011-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011646 | 403372724 | High Sign | HFTD Tier 3 | Distribution | 2011-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011647 | 403372744 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011648 | 403372745 | Molding | HFTD Tier 3 | Distribution | 2011-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011649 | 403373359 | High Sign | HFTD Tier 3 | Distribution | 2011-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011650 | 403373368 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011651 | 403373373 | High Sign | HFTD Tier 3 | Distribution | 2011-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011652 | 403373402 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011653 | 403373659 | High Sign | HFTD Tier 2 | Distribution | 2011-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011654 | 403373898 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011655 | 403373903 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011656 | 403373905 | High Sign | HFTD Tier 2 | Distribution | 2011-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011657 | 403373918 | High Sign | HFTD Tier 2 | Distribution | 2011-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011658 | 403374611 | High Sign | HFTD Tier 2 | Distribution | 2011-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011659 | 403374971 | Molding | HFTD Tier 3 | Distribution | 2011-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011660 | 403374976 | Molding | HFTD Tier 3 | Distribution | 2011-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011661 | 403374977 | Molding | HFTD Tier 3 | Distribution | 2011-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011662 | 403374992 | High Sign | HFTD Tier 3 | Distribution | 2011-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011663 | 403375258 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011664 | 403375265 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011665 | 403375293 | High Sign | HFTD Tier 2 | Distribution | 2011-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011666 | 403375295 | Molding | HFTD Tier 2 | Distribution | 2011-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011667 | 403375543 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011668 | 403375553 | High Sign | HFTD Tier 3 | Distribution | 2011-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011669 | 403375576 | Bond | HFTD Tier 3 | Distribution | 2011-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011670 | 403376158 | Guy | HFTD Tier 2 | Distribution | 2011-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011671 | 403376788 | High Sign | HFTD Tier 2 | Distribution | 2011-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011672 | 403376800 | High Sign | HFTD Tier 2 | Distribution | 2011-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011673 | 403376838 | High Sign | HFTD Tier 3 | Distribution | 2011-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011674 | 403376854 | High Sign | HFTD Tier 3 | Distribution | 2011-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011675 | 403377819 | Bond | HFTD Tier 3 | Distribution | 2011-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011676 | 403377827 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011677 | 403377828 | Riser/Conduit | HFTD Tier 3 | Distribution | 2011-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011678 | 403377833 | High Sign | HFTD Tier 3 | Distribution | 2011-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011679 | 403377840 | Bond | HFTD Tier 3 | Distribution | 2011-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011680 | 403377846 | Molding | HFTD Tier 3 | Distribution | 2011-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011681 | 403378675 | Molding | HFTD Tier 2 | Distribution | 2011-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011682 | 403378795 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011683 | 403381034 | High Sign | HFTD Tier 2 | Distribution | 2011-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011684 | 403381131 | Molding | HFTD Tier 2 | Distribution | 2011-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011685 | 403381152 | Guy | HFTD Tier 2 | Distribution | 2011-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011686 | 403381153 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011687 | 403381373 | High Sign | HFTD Tier 2 | Distribution | 2011-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011688 | 403381378 | High Sign | HFTD Tier 2 | Distribution | 2011-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011689 | 403381495 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011690 | 403381504 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011691 | 403381505 | High Sign | HFTD Tier 3 | Distribution | 2011-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011692 | 403382517 | Molding | HFTD Tier 2 | Distribution | 2011-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011693 | 403382537 | Guy | HFTD Tier 2 | Distribution | 2011-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011694 | 403382548 | High Sign | HFTD Tier 2 | Distribution | 2011-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011695 | 403383163 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-01-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011696 | 403383328 | High Sign | HFTD Tier 2 | Distribution | 2011-01-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011697 | 403383420 | Molding | HFTD Tier 3 | Distribution | 2011-01-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011698 | 403383495 | High Sign | HFTD Tier 3 | Distribution | 2011-01-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011699 | 403383607 | High Sign | HFTD Tier 2 | Distribution | 2011-01-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011700 | 403384518 | Riser/Conduit | HFTD Tier 3 | Distribution | 2011-01-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011701 | 403384667 | High Sign | HFTD Tier 3 | Distribution | 2011-01-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011702 | 403385187 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011703 | 403385236 | High Sign | HFTD Tier 2 | Distribution | 2011-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011704 | 403385238 | High Sign | HFTD Tier 2 | Distribution | 2011-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011705 | 403385241 | High Sign | HFTD Tier 2 | Distribution | 2011-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011706 | 403385962 | High Sign | HFTD Tier 2 | Distribution | 2011-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011707 | 403386009 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011708 | 403386010 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011709 | 403386850 | Guy | HFTD Tier 2 | Distribution | 2011-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011710 | 403386999 | High Sign | HFTD Tier 2 | Distribution | 2011-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011711 | 403387000 | High Sign | HFTD Tier 2 | Distribution | 2011-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011712 | 403387072 | Molding | HFTD Tier 2 | Distribution | 2011-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011713 | 403387076 | Molding | HFTD Tier 2 | Distribution | 2011-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011714 | 403387083 | Guy | HFTD Tier 2 | Distribution | 2011-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011715 | 403387195 | High Sign | HFTD Tier 2 | Distribution | 2011-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011716 | 403387409 | Molding | HFTD Tier 3 | Distribution | 2011-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011717 | 403387419 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011718 | 403387493 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011719 | 403387976 | High Sign | HFTD Tier 3 | Distribution | 2011-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011720 | 403387977 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011721 | 403388108 | Molding | HFTD Tier 3 | Distribution | 2011-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011722 | 403388256 | Molding | HFTD Tier 2 | Distribution | 2011-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011723 | 403388260 | Molding | HFTD Tier 2 | Distribution | 2011-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011724 | 403389226 | High Sign | HFTD Tier 3 | Distribution | 2011-01-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011725 | 403389692 | High Sign | HFTD Tier 2 | Distribution | 2011-01-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011726 | 403391006 | Guy | HFTD Tier 2 | Distribution | 2011-01-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011727 | 403391017 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-01-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011728 | 403391031 | Insulator | HFTD Tier 2 | Distribution | 2011-01-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011729 | 403391138 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-01-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011730 | 403391139 | Guy | HFTD Tier 2 | Distribution | 2011-01-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011731 | 403391331 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-01-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011732 | 403391336 | Guy | HFTD Tier 2 | Distribution | 2011-01-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011733 | 403391358 | High Sign | HFTD Tier 2 | Distribution | 2011-01-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011734 | 403391377 | High Sign | HFTD Tier 2 | Distribution | 2011-01-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011735 | 403391793 | Molding | HFTD Tier 2 | Distribution | 2011-01-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011736 | 403391886 | High Sign | HFTD Tier 3 | Distribution | 2011-01-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011737 | 403393922 | Crossarm | HFTD Tier 2 | Distribution | 2011-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011738 | 403395190 | Molding | HFTD Tier 3 | Distribution | 2011-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011739 | 403395289 | Insulator | HFTD Tier 2 | Distribution | 2011-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011740 | 403395355 | High Sign | HFTD Tier 2 | Distribution | 2011-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011741 | 403395474 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011742 | 403395477 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011743 | 403395481 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011744 | 403395486 | High Sign | HFTD Tier 2 | Distribution | 2011-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011745 | 403395489 | High Sign | HFTD Tier 2 | Distribution | 2011-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011746 | 403395490 | High Sign | HFTD Tier 2 | Distribution | 2011-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011747 | 403395499 | High Sign | HFTD Tier 2 | Distribution | 2011-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011748 | 403395937 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011749 | 403397020 | High Sign | HFTD Tier 2 | Distribution | 2011-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011750 | 403397028 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011751 | 403397212 | High Sign | HFTD Tier 2 | Distribution | 2011-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011752 | 403397292 | High Sign | HFTD Tier 2 | Distribution | 2011-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011753 | 403397455 | Guy | HFTD Tier 2 | Distribution | 2011-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011754 | 403397828 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011755 | 403397840 | Molding | HFTD Tier 3 | Distribution | 2011-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011756 | 403398832 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011757 | 403398901 | High Sign | HFTD Tier 3 | Distribution | 2011-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011758 | 403399206 | Molding | HFTD Tier 2 | Distribution | 2011-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011759 | 403399207 | Ground | HFTD Tier 2 | Distribution | 2011-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011760 | 403399568 | Molding | HFTD Tier 2 | Distribution | 2011-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011761 | 403400357 | Crossarm | HFTD Tier 2 | Distribution | 2011-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011762 | 403400364 | Guy | HFTD Tier 2 | Distribution | 2011-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011763 | 403400368 | Riser/Conduit | HFTD Tier 2 | Distribution | 2011-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011764 | 403400371 | High Sign | HFTD Tier 2 | Distribution | 2011-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011765 | 403400385 | Vis Strips | HFTD Tier 2 | Distribution | 2011-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011766 | 403400400 | Molding | HFTD Tier 2 | Distribution | 2011-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011767 | 403400757 | High Sign | HFTD Tier 2 | Distribution | 2011-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011768 | 403401667 | Guy | HFTD Tier 2 | Distribution | 2011-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011769 | 403401917 | Molding | HFTD Tier 3 | Distribution | 2011-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011770 | 403402403 | High Sign | HFTD Tier 3 | Distribution | 2011-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011771 | 403402544 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011772 | 403403711 | Molding | HFTD Tier 2 | Distribution | 2011-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011773 | 403404297 | Bond | HFTD Tier 3 | Distribution | 2011-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011774 | 403404302 | Molding | HFTD Tier 3 | Distribution | 2011-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011775 | 403404707 | Molding | HFTD Tier 3 | Distribution | 2011-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011776 | 403404718 | High Sign | HFTD Tier 3 | Distribution | 2011-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011777 | 403405277 | High Sign | HFTD Tier 2 | Distribution | 2011-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011778 | 403405279 | Ground | HFTD Tier 2 | Distribution | 2011-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011779 | 403405708 | Molding | HFTD Tier 2 | Distribution | 2011-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011780 | 403406004 | Molding | HFTD Tier 2 | Distribution | 2011-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011781 | 403406245 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011782 | 403406272 | Molding | HFTD Tier 3 | Distribution | 2011-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011783 | 403408953 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011784 | 403409061 | High Sign | HFTD Tier 3 | Distribution | 2011-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011785 | 403409127 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011786 | 403409213 | Molding | HFTD Tier 3 | Distribution | 2011-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011787 | 403410507 | High Sign | HFTD Tier 2 | Distribution | 2011-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011788 | 403410538 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011789 | 403410543 | Molding | HFTD Tier 2 | Distribution | 2011-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011790 | 403410545 | Molding | HFTD Tier 2 | Distribution | 2011-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011791 | 403412301 | Molding | HFTD Tier 3 | Distribution | 2011-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011792 | 403412389 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011793 | 403412948 | Molding | HFTD Tier 3 | Distribution | 2011-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011794 | 403413022 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011795 | 403413785 | High Sign | HFTD Tier 2 | Distribution | 2011-02-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011796 | 403413925 | Molding | HFTD Tier 2 | Distribution | 2011-02-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011797 | 403413962 | Riser/Conduit | HFTD Tier 2 | Distribution | 2011-02-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011798 | 403415273 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-02-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011799 | 403416246 | Molding | HFTD Tier 2 | Distribution | 2011-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011800 | 403416254 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011801 | 403416276 | Molding | HFTD Tier 2 | Distribution | 2011-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011802 | 403416351 | Molding | HFTD Tier 2 | Distribution | 2011-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011803 | 403416352 | High Sign | HFTD Tier 2 | Distribution | 2011-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011804 | 403416353 | Molding | HFTD Tier 2 | Distribution | 2011-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011805 | 403416362 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011806 | 403416431 | High Sign | HFTD Tier 2 | Distribution | 2011-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011807 | 403416638 | High Sign | HFTD Tier 2 | Distribution | 2011-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011808 | 403416643 | High Sign | HFTD Tier 2 | Distribution | 2011-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011809 | 403416654 | High Sign | HFTD Tier 2 | Distribution | 2011-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011810 | 403418966 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-02-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011811 | 403419819 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011812 | 403419855 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011813 | 403420152 | Molding | HFTD Tier 2 | Distribution | 2011-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011814 | 403421935 | Molding | HFTD Tier 3 | Distribution | 2011-02-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011815 | 403422272 | Insulator | HFTD Tier 2 | Distribution | 2011-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011816 | 403423016 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011817 | 403423089 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011818 | 403423105 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011819 | 403424368 | High Sign | HFTD Tier 2 | Distribution | 2011-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011820 | 403424379 | High Sign | HFTD Tier 2 | Distribution | 2011-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011821 | 403424389 | Molding | HFTD Tier 2 | Distribution | 2011-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011822 | 403424685 | High Sign | HFTD Tier 3 | Distribution | 2011-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011823 | 403424854 | Molding | HFTD Tier 2 | Distribution | 2011-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011824 | 403424865 | Molding | HFTD Tier 2 | Distribution | 2011-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011825 | 403424937 | High Sign | HFTD Tier 2 | Distribution | 2011-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011826 | 403426457 | Molding | HFTD Tier 2 | Distribution | 2011-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011827 | 403427249 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011828 | 403428934 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011829 | 403428938 | High Sign | HFTD Tier 2 | Distribution | 2011-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011830 | 403429367 | High Sign | HFTD Tier 2 | Distribution | 2011-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011831 | 403429381 | High Sign | HFTD Tier 2 | Distribution | 2011-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011832 | 403429386 | High Sign | HFTD Tier 2 | Distribution | 2011-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011833 | 403429388 | High Sign | HFTD Tier 2 | Distribution | 2011-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011834 | 403429389 | High Sign | HFTD Tier 2 | Distribution | 2011-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011835 | 403431211 | High Sign | HFTD Tier 2 | Distribution | 2011-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011836 | 403431213 | High Sign | HFTD Tier 2 | Distribution | 2011-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011837 | 403431912 | High Sign | HFTD Tier 2 | Distribution | 2011-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011838 | 403434046 | Molding | HFTD Tier 2 | Distribution | 2011-02-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011839 | 403434896 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011840 | 403434897 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011841 | 403434898 | High Sign | HFTD Tier 2 | Distribution | 2011-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011842 | 403434904 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011843 | 403434906 | High Sign | HFTD Tier 2 | Distribution | 2011-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011844 | 403434911 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011845 | 403434921 | Molding | HFTD Tier 2 | Distribution | 2011-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011846 | 403434941 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011847 | 403434986 | High Sign | HFTD Tier 2 | Distribution | 2011-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011848 | 403434990 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011849 | 403434991 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011850 | 403435172 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011851 | 403435969 | High Sign | HFTD Tier 2 | Distribution | 2011-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011852 | 403435972 | High Sign | HFTD Tier 2 | Distribution | 2011-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011853 | 403435981 | High Sign | HFTD Tier 2 | Distribution | 2011-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011854 | 403437136 | Molding | HFTD Tier 2 | Distribution | 2011-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011855 | 403437172 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011856 | 403437299 | High Sign | HFTD Tier 2 | Distribution | 2011-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011857 | 403437317 | Molding | HFTD Tier 2 | Distribution | 2011-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011858 | 403437346 | High Sign | HFTD Tier 2 | Distribution | 2011-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011859 | 403437503 | High Sign | HFTD Tier 3 | Distribution | 2011-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011860 | 403437504 | Molding | HFTD Tier 3 | Distribution | 2011-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011861 | 403437510 | High Sign | HFTD Tier 3 | Distribution | 2011-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011862 | 403437516 | Molding | HFTD Tier 3 | Distribution | 2011-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011863 | 403437522 | High Sign | HFTD Tier 3 | Distribution | 2011-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011864 | 403439379 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011865 | 403439393 | Guy | HFTD Tier 2 | Distribution | 2011-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011866 | 403439462 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011867 | 403439868 | Molding | HFTD Tier 2 | Distribution | 2011-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011868 | 403439869 | Molding | HFTD Tier 3 | Distribution | 2011-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011869 | 403440108 | Molding | HFTD Tier 3 | Distribution | 2011-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011870 | 403440109 | High Sign | HFTD Tier 3 | Distribution | 2011-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011871 | 403440400 | Molding | HFTD Tier 2 | Distribution | 2011-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011872 | 403440552 | Ground | HFTD Tier 3 | Distribution | 2011-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011873 | 403440580 | Guy | HFTD Tier 3 | Distribution | 2011-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011874 | 403441598 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011875 | 403442511 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011876 | 403444179 | Insulator | HFTD Tier 2 | Distribution | 2011-03-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011877 | 403444188 | Insulator | HFTD Tier 2 | Distribution | 2011-03-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011878 | 403444473 | High Sign | HFTD Tier 2 | Distribution | 2011-03-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011879 | 403444475 | Molding | HFTD Tier 2 | Distribution | 2011-03-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011880 | 403444581 | High Sign | HFTD Tier 3 | Distribution | 2011-03-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011881 | 403444591 | High Sign | HFTD Tier 3 | Distribution | 2011-03-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011882 | 403444598 | High Sign | HFTD Tier 3 | Distribution | 2011-03-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011883 | 403444603 | High Sign | HFTD Tier 3 | Distribution | 2011-03-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011884 | 403444605 | Molding | HFTD Tier 3 | Distribution | 2011-03-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011885 | 403445477 | High Sign | HFTD Tier 2 | Distribution | 2011-03-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011886 | 403445485 | Molding | HFTD Tier 2 | Distribution | 2011-03-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011887 | 403446345 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011888 | 403446346 | Molding | HFTD Tier 2 | Distribution | 2011-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011889 | 403446749 | High Sign | HFTD Tier 3 | Distribution | 2011-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011890 | 403446757 | High Sign | HFTD Tier 3 | Distribution | 2011-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011891 | 403446762 | High Sign | HFTD Tier 3 | Distribution | 2011-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011892 | 403446771 | High Sign | HFTD Tier 3 | Distribution | 2011-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011893 | 403446773 | High Sign | HFTD Tier 3 | Distribution | 2011-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011894 | 403446838 | Molding | HFTD Tier 2 | Distribution | 2011-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011895 | 403447628 | High Sign | HFTD Tier 3 | Distribution | 2011-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011896 | 403447649 | High Sign | HFTD Tier 3 | Distribution | 2011-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011897 | 403447650 | Molding | HFTD Tier 3 | Distribution | 2011-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011898 | 403447745 | Molding | HFTD Tier 3 | Distribution | 2011-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011899 | 403448234 | Molding | HFTD Tier 3 | Distribution | 2011-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011900 | 403448248 | Molding | HFTD Tier 3 | Distribution | 2011-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011901 | 403448264 | Molding | HFTD Tier 3 | Distribution | 2011-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011902 | 403448912 | High Sign | HFTD Tier 3 | Distribution | 2011-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011903 | 403448941 | High Sign | HFTD Tier 3 | Distribution | 2011-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011904 | 403448946 | High Sign | HFTD Tier 3 | Distribution | 2011-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011905 | 403448947 | High Sign | HFTD Tier 3 | Distribution | 2011-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011906 | 403449437 | Molding | HFTD Tier 2 | Distribution | 2011-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011907 | 403449457 | Guy | HFTD Tier 2 | Distribution | 2011-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011908 | 403449534 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011909 | 403450032 | High Sign | HFTD Tier 3 | Distribution | 2011-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011910 | 403450253 | Molding | HFTD Tier 3 | Distribution | 2011-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011911 | 403450260 | High Sign | HFTD Tier 3 | Distribution | 2011-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011912 | 403450278 | Molding | HFTD Tier 3 | Distribution | 2011-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011913 | 403451700 | Molding | HFTD Tier 3 | Distribution | 2011-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011914 | 403452006 | High Sign | HFTD Tier 3 | Distribution | 2011-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011915 | 403452335 | Guy | HFTD Tier 3 | Distribution | 2011-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011916 | 403453411 | Molding | HFTD Tier 2 | Distribution | 2011-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011917 | 403456531 | Insulator | HFTD Tier 2 | Distribution | 2011-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011918 | 403457231 | Molding | HFTD Tier 3 | Distribution | 2011-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011919 | 403458373 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011920 | 403459660 | High Sign | HFTD Tier 3 | Distribution | 2011-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011921 | 403460402 | Molding | HFTD Tier 2 | Distribution | 2011-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011922 | 403460961 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011923 | 403462063 | Cutout/Fuse | HFTD Tier 2 | Distribution | 2011-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011924 | 403462086 | High Sign | HFTD Tier 2 | Distribution | 2011-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011925 | 403463263 | Molding | HFTD Tier 2 | Distribution | 2011-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011926 | 403463667 | High Sign | HFTD Tier 3 | Distribution | 2011-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011927 | 403463687 | High Sign | HFTD Tier 3 | Distribution | 2011-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011928 | 403463688 | Molding | HFTD Tier 3 | Distribution | 2011-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011929 | 403463703 | High Sign | HFTD Tier 3 | Distribution | 2011-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011930 | 403463713 | High Sign | HFTD Tier 3 | Distribution | 2011-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011931 | 403463714 | High Sign | HFTD Tier 3 | Distribution | 2011-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011932 | 403463725 | High Sign | HFTD Tier 3 | Distribution | 2011-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011933 | 403463776 | Insulator | HFTD Tier 3 | Distribution | 2011-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011934 | 403463782 | High Sign | HFTD Tier 3 | Distribution | 2011-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011935 | 403465286 | High Sign | HFTD Tier 3 | Distribution | 2011-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011936 | 403465488 | Vis Strips | HFTD Tier 2 | Distribution | 2011-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011937 | 403465490 | Vis Strips | HFTD Tier 2 | Distribution | 2011-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011938 | 403465960 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011939 | 403468559 | High Sign | HFTD Tier 3 | Distribution | 2011-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011940 | 403468578 | High Sign | HFTD Tier 3 | Distribution | 2011-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011941 | 403469656 | High Sign | HFTD Tier 2 | Distribution | 2011-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011942 | 403469672 | Molding | HFTD Tier 2 | Distribution | 2011-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011943 | 403469685 | High Sign | HFTD Tier 2 | Distribution | 2011-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011944 | 403469694 | High Sign | HFTD Tier 2 | Distribution | 2011-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011945 | 403469697 | High Sign | HFTD Tier 2 | Distribution | 2011-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011946 | 403473376 | High Sign | HFTD Tier 3 | Distribution | 2011-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011947 | 403473472 | High Sign | HFTD Tier 2 | Distribution | 2011-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011948 | 403473473 | Molding | HFTD Tier 2 | Distribution | 2011-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011949 | 403475709 | Molding | HFTD Tier 3 | Distribution | 2011-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011950 | 403479931 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011951 | 403480227 | Molding | HFTD Tier 3 | Distribution | 2011-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011952 | 403480233 | High Sign | HFTD Tier 3 | Distribution | 2011-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011953 | 403480586 | Molding | HFTD Tier 2 | Distribution | 2011-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011954 | 403481124 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011955 | 403481125 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011956 | 403481143 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011957 | 403481242 | Insulator | HFTD Tier 2 | Distribution | 2011-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011958 | 403481247 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011959 | 403481254 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011960 | 403481255 | High Sign | HFTD Tier 2 | Distribution | 2011-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011961 | 403481256 | Crossarm | HFTD Tier 2 | Distribution | 2011-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011962 | 403481258 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011963 | 403481273 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011964 | 403481481 | Molding | HFTD Tier 3 | Distribution | 2011-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011965 | 403481778 | Molding | HFTD Tier 2 | Distribution | 2011-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011966 | 403481963 | Molding | HFTD Tier 3 | Distribution | 2011-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011967 | 403481966 | High Sign | HFTD Tier 3 | Distribution | 2011-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011968 | 403481973 | Molding | HFTD Tier 3 | Distribution | 2011-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011969 | 403481982 | High Sign | HFTD Tier 3 | Distribution | 2011-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011970 | 403482010 | Molding | HFTD Tier 2 | Distribution | 2011-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011971 | 403482021 | Molding | HFTD Tier 2 | Distribution | 2011-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011972 | 403482049 | High Sign | HFTD Tier 2 | Distribution | 2011-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011973 | 403482056 | Crossarm | HFTD Tier 2 | Distribution | 2011-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011974 | 403482057 | Molding | HFTD Tier 2 | Distribution | 2011-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011975 | 403482077 | High Sign | HFTD Tier 2 | Distribution | 2011-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011976 | 403482690 | High Sign | HFTD Tier 3 | Distribution | 2011-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011977 | 403482700 | High Sign | HFTD Tier 3 | Distribution | 2011-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011978 | 403482703 | Riser/Conduit | HFTD Tier 3 | Distribution | 2011-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011979 | 403483123 | Insulator | HFTD Tier 2 | Distribution | 2011-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011980 | 403484464 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011981 | 403484912 | High Sign | HFTD Tier 3 | Distribution | 2011-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011982 | 403485989 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011983 | 403486157 | Molding | HFTD Tier 2 | Distribution | 2011-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011984 | 403486169 | High Sign | HFTD Tier 2 | Distribution | 2011-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011985 | 403486170 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011986 | 403486185 | Molding | HFTD Tier 2 | Distribution | 2011-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011987 | 403486432 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011988 | 403486734 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011989 | 403487204 | Guy | HFTD Tier 3 | Distribution | 2011-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011990 | 403487208 | High Sign | HFTD Tier 3 | Distribution | 2011-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011991 | 403487967 | High Sign | HFTD Tier 2 | Distribution | 2011-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011992 | 403487974 | High Sign | HFTD Tier 2 | Distribution | 2011-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011993 | 403487982 | Molding | HFTD Tier 2 | Distribution | 2011-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011994 | 403488117 | High Sign | HFTD Tier 2 | Distribution | 2011-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011995 | 403488422 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011996 | 403488451 | High Sign | HFTD Tier 3 | Distribution | 2011-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011997 | 403490095 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011998 | 403490096 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130011999 | 403490097 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012000 | 403490098 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012001 | 403490099 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012002 | 403490101 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012003 | 403490102 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012004 | 403490848 | Molding | HFTD Tier 2 | Distribution | 2011-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012005 | 403491044 | Molding | HFTD Tier 2 | Distribution | 2011-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012006 | 403491056 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012007 | 403491103 | Molding | HFTD Tier 2 | Distribution | 2011-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012008 | 403491114 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012009 | 403493077 | Molding | HFTD Tier 2 | Distribution | 2011-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012010 | 403493101 | Molding | HFTD Tier 2 | Distribution | 2011-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012011 | 403493112 | Cutout/Fuse | HFTD Tier 2 | Distribution | 2011-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012012 | 403493125 | High Sign | HFTD Tier 2 | Distribution | 2011-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012013 | 403493204 | High Sign | HFTD Tier 2 | Distribution | 2011-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012014 | 403493494 | Molding | HFTD Tier 3 | Distribution | 2011-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012015 | 403493497 | Molding | HFTD Tier 3 | Distribution | 2011-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012016 | 403493506 | Molding | HFTD Tier 3 | Distribution | 2011-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012017 | 403495434 | High Sign | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012018 | 403495464 | High Sign | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012019 | 403495472 | High Sign | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012020 | 403495474 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012021 | 403495475 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012022 | 403495483 | High Sign | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012023 | 403495500 | Molding | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012024 | 403495726 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012025 | 403495727 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012026 | 403495728 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012027 | 403495740 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012028 | 403495741 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012029 | 403495743 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012030 | 403495745 | High Sign | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012031 | 403495746 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012032 | 403495748 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012033 | 403495751 | High Sign | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012034 | 403495752 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012035 | 403495761 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012036 | 403495778 | High Sign | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012037 | 403495802 | High Sign | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012038 | 403495805 | Molding | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012039 | 403495852 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012040 | 403496285 | Molding | HFTD Tier 3 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012041 | 403496328 | Crossarm | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012042 | 403496636 | High Sign | HFTD Tier 3 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012043 | 403498050 | Insulator | HFTD Tier 2 | Distribution | 2011-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012044 | 403498099 | Molding | HFTD Tier 2 | Distribution | 2011-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012045 | 403498107 | High Sign | HFTD Tier 2 | Distribution | 2011-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012046 | 403498110 | Molding | HFTD Tier 2 | Distribution | 2011-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012047 | 403498111 | High Sign | HFTD Tier 2 | Distribution | 2011-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012048 | 403498114 | High Sign | HFTD Tier 2 | Distribution | 2011-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012049 | 403498117 | High Sign | HFTD Tier 2 | Distribution | 2011-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012050 | 403498155 | High Sign | HFTD Tier 2 | Distribution | 2011-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012051 | 403498170 | High Sign | HFTD Tier 2 | Distribution | 2011-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012052 | 403498572 | Molding | HFTD Tier 2 | Distribution | 2011-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012053 | 403498582 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012054 | 403499403 | High Sign | HFTD Tier 3 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012055 | 403500766 | Riser/Conduit | HFTD Tier 3 | Distribution | 2011-04-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012056 | 403500963 | High Sign | HFTD Tier 2 | Distribution | 2011-04-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012057 | 403500988 | High Sign | HFTD Tier 2 | Distribution | 2011-04-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012058 | 403501693 | High Sign | HFTD Tier 2 | Distribution | 2011-04-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012059 | 403501714 | Molding | HFTD Tier 2 | Distribution | 2011-04-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012060 | 403595810 | High Sign | HFTD Tier 3 | Distribution | 2011-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012061 | 403595945 | High Sign | HFTD Tier 3 | Distribution | 2011-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012062 | 403596397 | High Sign | HFTD Tier 2 | Distribution | 2011-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012063 | 403596407 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012064 | 403596409 | High Sign | HFTD Tier 2 | Distribution | 2011-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012065 | 403596884 | Riser/Conduit | HFTD Tier 2 | Distribution | 2011-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012066 | 403597227 | Molding | HFTD Tier 2 | Distribution | 2011-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012067 | 403597729 | High Sign | HFTD Tier 3 | Distribution | 2011-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012068 | 403597740 | High Sign | HFTD Tier 3 | Distribution | 2011-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012069 | 403597742 | High Sign | HFTD Tier 3 | Distribution | 2011-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012070 | 403597744 | High Sign | HFTD Tier 3 | Distribution | 2011-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012071 | 403597745 | High Sign | HFTD Tier 3 | Distribution | 2011-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012072 | 403597833 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012073 | 403597834 | High Sign | HFTD Tier 2 | Distribution | 2011-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012074 | 403598503 | Molding | HFTD Tier 3 | Distribution | 2011-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012075 | 403599070 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012076 | 403599080 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012077 | 403600536 | High Sign | HFTD Tier 2 | Distribution | 2011-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012078 | 403600537 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012079 | 403600540 | High Sign | HFTD Tier 2 | Distribution | 2011-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012080 | 403600550 | High Sign | HFTD Tier 2 | Distribution | 2011-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012081 | 403602015 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012082 | 403602859 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012083 | 403602871 | High Sign | HFTD Tier 2 | Distribution | 2011-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012084 | 403602919 | High Sign | HFTD Tier 3 | Distribution | 2011-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012085 | 403603176 | High Sign | HFTD Tier 2 | Distribution | 2011-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012086 | 403603177 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012087 | 403606051 | Molding | HFTD Tier 2 | Distribution | 2011-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012088 | 403606155 | Molding | HFTD Tier 3 | Distribution | 2011-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012089 | 403606224 | Pole Tag | HFTD Tier 2 | Distribution | 2011-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012090 | 403606232 | Molding | HFTD Tier 2 | Distribution | 2011-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012091 | 403606578 | High Sign | HFTD Tier 3 | Distribution | 2011-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012092 | 403636805 | High Sign | HFTD Tier 2 | Distribution | 2011-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012093 | 403637237 | High Sign | HFTD Tier 3 | Distribution | 2011-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012094 | 403638454 | Molding | HFTD Tier 2 | Distribution | 2011-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012095 | 403638457 | Riser/Conduit | HFTD Tier 2 | Distribution | 2011-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012096 | 403638458 | High Sign | HFTD Tier 2 | Distribution | 2011-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012097 | 403638480 | Molding | HFTD Tier 2 | Distribution | 2011-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012098 | 403638558 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012099 | 403638567 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012100 | 403638570 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012101 | 403638572 | High Sign | HFTD Tier 2 | Distribution | 2011-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012102 | 403638573 | Molding | HFTD Tier 2 | Distribution | 2011-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012103 | 403638587 | High Sign | HFTD Tier 2 | Distribution | 2011-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012104 | 403638594 | Molding | HFTD Tier 2 | Distribution | 2011-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012105 | 403638716 | High Sign | HFTD Tier 2 | Distribution | 2011-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012106 | 403638726 | High Sign | HFTD Tier 2 | Distribution | 2011-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012107 | 403638741 | High Sign | HFTD Tier 2 | Distribution | 2011-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012108 | 403638743 | Molding | HFTD Tier 2 | Distribution | 2011-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012109 | 403638745 | Molding | HFTD Tier 2 | Distribution | 2011-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012110 | 403638746 | High Sign | HFTD Tier 2 | Distribution | 2011-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012111 | 403638758 | High Sign | HFTD Tier 2 | Distribution | 2011-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012112 | 403640644 | High Sign | HFTD Tier 3 | Distribution | 2011-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012113 | 403640744 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012114 | 403640746 | High Sign | HFTD Tier 2 | Distribution | 2011-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012115 | 403640795 | High Sign | HFTD Tier 2 | Distribution | 2011-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012116 | 403640810 | High Sign | HFTD Tier 2 | Distribution | 2011-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012117 | 403640821 | High Sign | HFTD Tier 2 | Distribution | 2011-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012118 | 403641419 | Molding | HFTD Tier 3 | Distribution | 2011-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012119 | 403641444 | High Sign | HFTD Tier 3 | Distribution | 2011-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012120 | 403641729 | Riser/Conduit | HFTD Tier 2 | Distribution | 2011-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012121 | 403641760 | Molding | HFTD Tier 2 | Distribution | 2011-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012122 | 403641977 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012123 | 403642734 | Insulator | HFTD Tier 3 | Distribution | 2011-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012124 | 403642740 | High Sign | HFTD Tier 3 | Distribution | 2011-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012125 | 403642753 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012126 | 403643159 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012127 | 403643167 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012128 | 403643169 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012129 | 403643558 | Ground | HFTD Tier 2 | Distribution | 2011-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012130 | 403644758 | High Sign | HFTD Tier 3 | Distribution | 2011-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012131 | 403645789 | High Sign | HFTD Tier 3 | Distribution | 2011-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012132 | 403645821 | Molding | HFTD Tier 3 | Distribution | 2011-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012133 | 403645830 | Guy | HFTD Tier 3 | Distribution | 2011-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012134 | 403646448 | High Sign | HFTD Tier 3 | Distribution | 2011-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012135 | 403646459 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012136 | 403646992 | High Sign | HFTD Tier 3 | Distribution | 2011-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012137 | 403647000 | High Sign | HFTD Tier 3 | Distribution | 2011-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012138 | 403647244 | Guy | HFTD Tier 2 | Distribution | 2011-04-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012139 | 403647292 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-04-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012140 | 403647315 | Molding | HFTD Tier 2 | Distribution | 2011-04-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012141 | 403647330 | Molding | HFTD Tier 3 | Distribution | 2011-04-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012142 | 403648108 | Guy | HFTD Tier 2 | Distribution | 2011-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012143 | 403648362 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012144 | 403649375 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012145 | 403649386 | High Sign | HFTD Tier 3 | Distribution | 2011-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012146 | 403650018 | Molding | HFTD Tier 2 | Distribution | 2011-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012147 | 403650553 | High Sign | HFTD Tier 2 | Distribution | 2011-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012148 | 403650658 | Molding | HFTD Tier 3 | Distribution | 2011-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012149 | 403650665 | High Sign | HFTD Tier 3 | Distribution | 2011-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012150 | 403650680 | Molding | HFTD Tier 3 | Distribution | 2011-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012151 | 403653238 | High Sign | HFTD Tier 3 | Distribution | 2011-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012152 | 403653248 | Molding | HFTD Tier 3 | Distribution | 2011-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012153 | 403654059 | High Sign | HFTD Tier 3 | Distribution | 2011-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012154 | 403654766 | Molding | HFTD Tier 3 | Distribution | 2011-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012155 | 403654767 | Molding | HFTD Tier 3 | Distribution | 2011-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012156 | 403655261 | High Sign | HFTD Tier 2 | Distribution | 2011-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012157 | 403655267 | High Sign | HFTD Tier 2 | Distribution | 2011-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012158 | 403655529 | High Sign | HFTD Tier 3 | Distribution | 2011-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012159 | 403655532 | High Sign | HFTD Tier 3 | Distribution | 2011-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012160 | 403657206 | Molding | HFTD Tier 3 | Distribution | 2011-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012161 | 403657216 | Molding | HFTD Tier 3 | Distribution | 2011-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012162 | 403657218 | High Sign | HFTD Tier 3 | Distribution | 2011-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012163 | 403657219 | Molding | HFTD Tier 3 | Distribution | 2011-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012164 | 403657751 | Molding | HFTD Tier 3 | Distribution | 2011-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012165 | 403658264 | High Sign | HFTD Tier 3 | Distribution | 2011-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012166 | 403661400 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012167 | 403661434 | Molding | HFTD Tier 2 | Distribution | 2011-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012168 | 403661444 | High Sign | HFTD Tier 2 | Distribution | 2011-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012169 | 403661470 | Molding | HFTD Tier 2 | Distribution | 2011-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012170 | 403662516 | High Sign | HFTD Tier 2 | Distribution | 2011-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012171 | 403663060 | Riser/Conduit | HFTD Tier 2 | Distribution | 2011-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012172 | 403663679 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012173 | 403664808 | Insulator | HFTD Tier 2 | Distribution | 2011-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012174 | 403664820 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012175 | 403665847 | High Sign | HFTD Tier 3 | Distribution | 2011-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012176 | 403667387 | High Sign | HFTD Tier 2 | Distribution | 2011-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012177 | 403667442 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012178 | 403667480 | Molding | HFTD Tier 3 | Distribution | 2011-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012179 | 403667487 | High Sign | HFTD Tier 3 | Distribution | 2011-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012180 | 403667493 | Molding | HFTD Tier 3 | Distribution | 2011-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012181 | 403667494 | Molding | HFTD Tier 3 | Distribution | 2011-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012182 | 403667516 | Molding | HFTD Tier 2 | Distribution | 2011-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012183 | 403667520 | Molding | HFTD Tier 2 | Distribution | 2011-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012184 | 403667525 | Molding | HFTD Tier 2 | Distribution | 2011-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012185 | 403667526 | Molding | HFTD Tier 2 | Distribution | 2011-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012186 | 403668007 | High Sign | HFTD Tier 2 | Distribution | 2011-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012187 | 403668008 | Molding | HFTD Tier 2 | Distribution | 2011-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012188 | 403668061 | Guy | HFTD Tier 2 | Distribution | 2011-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012189 | 403668174 | Guy | HFTD Tier 2 | Distribution | 2011-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012190 | 403668180 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012191 | 403669069 | Riser/Conduit | HFTD Tier 2 | Distribution | 2011-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012192 | 403669184 | High Sign | HFTD Tier 2 | Distribution | 2011-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012193 | 403669753 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012194 | 403669783 | High Sign | HFTD Tier 2 | Distribution | 2011-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012195 | 403669790 | Molding | HFTD Tier 2 | Distribution | 2011-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012196 | 403672159 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012197 | 403672191 | High Sign | HFTD Tier 3 | Distribution | 2011-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012198 | 403672193 | High Sign | HFTD Tier 3 | Distribution | 2011-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012199 | 403672216 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012200 | 403672572 | High Sign | HFTD Tier 2 | Distribution | 2011-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012201 | 403672578 | Molding | HFTD Tier 2 | Distribution | 2011-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012202 | 403672586 | Molding | HFTD Tier 2 | Distribution | 2011-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012203 | 403673409 | Molding | HFTD Tier 2 | Distribution | 2011-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012204 | 403673567 | Molding | HFTD Tier 3 | Distribution | 2011-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012205 | 403676065 | High Sign | HFTD Tier 2 | Distribution | 2011-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012206 | 403676071 | High Sign | HFTD Tier 2 | Distribution | 2011-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012207 | 403676368 | High Sign | HFTD Tier 2 | Distribution | 2011-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012208 | 403676382 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012209 | 403676527 | High Sign | HFTD Tier 3 | Distribution | 2011-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012210 | 403676664 | Molding | HFTD Tier 2 | Distribution | 2011-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012211 | 403676690 | High Sign | HFTD Tier 2 | Distribution | 2011-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012212 | 403676861 | High Sign | HFTD Tier 2 | Distribution | 2011-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012213 | 403676983 | High Sign | HFTD Tier 3 | Distribution | 2011-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012214 | 403678519 | Insulator | HFTD Tier 2 | Distribution | 2011-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012215 | 403678553 | Molding | HFTD Tier 2 | Distribution | 2011-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012216 | 403678554 | High Sign | HFTD Tier 2 | Distribution | 2011-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012217 | 403679851 | Molding | HFTD Tier 3 | Distribution | 2011-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012218 | 403681035 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012219 | 403681054 | High Sign | HFTD Tier 2 | Distribution | 2011-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012220 | 403681282 | High Sign | HFTD Tier 2 | Distribution | 2011-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012221 | 403681291 | High Sign | HFTD Tier 2 | Distribution | 2011-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012222 | 403681578 | High Sign | HFTD Tier 2 | Distribution | 2011-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012223 | 403681614 | Guy | HFTD Tier 2 | Distribution | 2011-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012224 | 403681897 | High Sign | HFTD Tier 2 | Distribution | 2011-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012225 | 403684213 | Guy | HFTD Tier 2 | Distribution | 2011-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012226 | 403684635 | High Sign | HFTD Tier 2 | Distribution | 2011-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012227 | 403684641 | High Sign | HFTD Tier 2 | Distribution | 2011-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012228 | 403684642 | High Sign | HFTD Tier 2 | Distribution | 2011-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012229 | 403684697 | High Sign | HFTD Tier 2 | Distribution | 2011-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012230 | 403686414 | Riser/Conduit | HFTD Tier 2 | Distribution | 2011-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012231 | 403686437 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012232 | 403686439 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012233 | 403686441 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012234 | 403686447 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012235 | 403686448 | Riser/Conduit | HFTD Tier 2 | Distribution | 2011-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012236 | 403690978 | High Sign | HFTD Tier 2 | Distribution | 2011-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012237 | 403690987 | High Sign | HFTD Tier 2 | Distribution | 2011-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012238 | 403690991 | Molding | HFTD Tier 2 | Distribution | 2011-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012239 | 403690993 | High Sign | HFTD Tier 2 | Distribution | 2011-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012240 | 403690994 | High Sign | HFTD Tier 2 | Distribution | 2011-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012241 | 403691314 | Guy | HFTD Tier 2 | Distribution | 2011-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012242 | 403691321 | High Sign | HFTD Tier 2 | Distribution | 2011-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012243 | 403691331 | High Sign | HFTD Tier 2 | Distribution | 2011-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012244 | 403693204 | High Sign | HFTD Tier 3 | Distribution | 2011-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012245 | 403693399 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012246 | 403693413 | Guy | HFTD Tier 2 | Distribution | 2011-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012247 | 403693425 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012248 | 403693478 | High Sign | HFTD Tier 2 | Distribution | 2011-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012249 | 403693803 | High Sign | HFTD Tier 2 | Distribution | 2011-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012250 | 403693804 | High Sign | HFTD Tier 2 | Distribution | 2011-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012251 | 403695288 | High Sign | HFTD Tier 3 | Distribution | 2011-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012252 | 403695939 | Riser/Conduit | HFTD Tier 2 | Distribution | 2011-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012253 | 403695973 | Molding | HFTD Tier 2 | Distribution | 2011-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012254 | 403695974 | High Sign | HFTD Tier 2 | Distribution | 2011-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012255 | 403696227 | High Sign | HFTD Tier 2 | Distribution | 2011-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012256 | 403696233 | Molding | HFTD Tier 2 | Distribution | 2011-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012257 | 403698618 | Molding | HFTD Tier 2 | Distribution | 2011-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012258 | 403698619 | High Sign | HFTD Tier 2 | Distribution | 2011-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012259 | 403698636 | Guy | HFTD Tier 2 | Distribution | 2011-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012260 | 403701638 | High Sign | HFTD Tier 2 | Distribution | 2011-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012261 | 403701716 | High Sign | HFTD Tier 2 | Distribution | 2011-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012262 | 403701725 | High Sign | HFTD Tier 2 | Distribution | 2011-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012263 | 403703458 | High Sign | HFTD Tier 2 | Distribution | 2011-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012264 | 403703466 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012265 | 403703470 | High Sign | HFTD Tier 2 | Distribution | 2011-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012266 | 403703476 | Vis Strips | HFTD Tier 2 | Distribution | 2011-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012267 | 403703659 | High Sign | HFTD Tier 3 | Distribution | 2011-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012268 | 403703802 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012269 | 403705811 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012270 | 403705812 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012271 | 403705813 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012272 | 403705820 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012273 | 403706264 | Molding | HFTD Tier 2 | Distribution | 2011-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012274 | 403706271 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012275 | 403706294 | Molding | HFTD Tier 2 | Distribution | 2011-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012276 | 403706341 | Molding | HFTD Tier 2 | Distribution | 2011-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012277 | 403706351 | High Sign | HFTD Tier 2 | Distribution | 2011-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012278 | 403706360 | Molding | HFTD Tier 2 | Distribution | 2011-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012279 | 403706914 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012280 | 403707646 | High Sign | HFTD Tier 2 | Distribution | 2011-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012281 | 403707712 | High Sign | HFTD Tier 2 | Distribution | 2011-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012282 | 403708192 | Molding | HFTD Tier 3 | Distribution | 2011-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012283 | 403708240 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012284 | 403708271 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012285 | 403708869 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012286 | 403710171 | Molding | HFTD Tier 3 | Distribution | 2011-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012287 | 403711503 | Crossarm | HFTD Tier 3 | Distribution | 2011-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012288 | 403711615 | High Sign | HFTD Tier 2 | Distribution | 2011-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012289 | 403711616 | High Sign | HFTD Tier 2 | Distribution | 2011-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012290 | 403711617 | High Sign | HFTD Tier 2 | Distribution | 2011-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012291 | 403712234 | High Sign | HFTD Tier 3 | Distribution | 2011-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012292 | 403712767 | Molding | HFTD Tier 3 | Distribution | 2011-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012293 | 403712772 | High Sign | HFTD Tier 3 | Distribution | 2011-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012294 | 403712788 | High Sign | HFTD Tier 3 | Distribution | 2011-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012295 | 403712811 | High Sign | HFTD Tier 3 | Distribution | 2011-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012296 | 403713918 | Molding | HFTD Tier 3 | Distribution | 2011-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012297 | 403714380 | High Sign | HFTD Tier 2 | Distribution | 2011-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012298 | 403714384 | High Sign | HFTD Tier 2 | Distribution | 2011-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012299 | 403715991 | High Sign | HFTD Tier 2 | Distribution | 2011-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012300 | 403715995 | High Sign | HFTD Tier 2 | Distribution | 2011-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012301 | 403717048 | Molding | HFTD Tier 3 | Distribution | 2011-05-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012302 | 403717058 | Riser/Conduit | HFTD Tier 3 | Distribution | 2011-05-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012303 | 403720436 | High Sign | HFTD Tier 2 | Distribution | 2011-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012304 | 403720437 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012305 | 403720850 | High Sign | HFTD Tier 2 | Distribution | 2011-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012306 | 403720853 | High Sign | HFTD Tier 2 | Distribution | 2011-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012307 | 403721115 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012308 | 403721753 | Guy | HFTD Tier 3 | Distribution | 2011-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012309 | 403722491 | Molding | HFTD Tier 3 | Distribution | 2011-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012310 | 403724951 | High Sign | HFTD Tier 3 | Distribution | 2011-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012311 | 403727281 | High Sign | HFTD Tier 3 | Distribution | 2011-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012312 | 403727529 | Molding | HFTD Tier 3 | Distribution | 2011-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012313 | 403727699 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012314 | 403735030 | Molding | HFTD Tier 2 | Distribution | 2011-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012315 | 403736185 | Molding | HFTD Tier 3 | Distribution | 2011-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012316 | 403736188 | High Sign | HFTD Tier 3 | Distribution | 2011-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012317 | 403736206 | Molding | HFTD Tier 3 | Distribution | 2011-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012318 | 403736210 | High Sign | HFTD Tier 3 | Distribution | 2011-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012319 | 403737118 | High Sign | HFTD Tier 2 | Distribution | 2011-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012320 | 403738988 | Guy | HFTD Tier 3 | Distribution | 2011-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012321 | 403738999 | Molding | HFTD Tier 3 | Distribution | 2011-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012322 | 403739022 | Guy | HFTD Tier 3 | Distribution | 2011-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012323 | 403739032 | High Sign | HFTD Tier 3 | Distribution | 2011-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012324 | 403739912 | High Sign | HFTD Tier 3 | Distribution | 2011-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012325 | 403740268 | Molding | HFTD Tier 2 | Distribution | 2011-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012326 | 403740363 | Molding | HFTD Tier 2 | Distribution | 2011-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012327 | 403741792 | High Sign | HFTD Tier 2 | Distribution | 2011-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012328 | 403741833 | Molding | HFTD Tier 3 | Distribution | 2011-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012329 | 403741890 | Molding | HFTD Tier 3 | Distribution | 2011-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012330 | 403742576 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012331 | 403742736 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012332 | 403742942 | High Sign | HFTD Tier 2 | Distribution | 2011-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012333 | 403743204 | High Sign | HFTD Tier 2 | Distribution | 2011-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012334 | 403743233 | High Sign | HFTD Tier 2 | Distribution | 2011-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012335 | 403743963 | Molding | HFTD Tier 3 | Distribution | 2011-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012336 | 403743981 | High Sign | HFTD Tier 3 | Distribution | 2011-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012337 | 403745978 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012338 | 403746559 | High Sign | HFTD Tier 3 | Distribution | 2011-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012339 | 403746649 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012340 | 403746713 | Guy | HFTD Tier 3 | Distribution | 2011-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012341 | 403746776 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012342 | 403750527 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012343 | 403753134 | High Sign | HFTD Tier 3 | Distribution | 2011-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012344 | 403753135 | Molding | HFTD Tier 3 | Distribution | 2011-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012345 | 403753143 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012346 | 403753152 | High Sign | HFTD Tier 3 | Distribution | 2011-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012347 | 403753609 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012348 | 403753823 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012349 | 403754228 | Molding | HFTD Tier 2 | Distribution | 2011-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012350 | 403754476 | High Sign | HFTD Tier 2 | Distribution | 2011-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012351 | 403754558 | High Sign | HFTD Tier 2 | Distribution | 2011-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012352 | 403754560 | Molding | HFTD Tier 2 | Distribution | 2011-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012353 | 403754633 | Molding | HFTD Tier 2 | Distribution | 2011-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012354 | 403754952 | High Sign | HFTD Tier 2 | Distribution | 2011-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012355 | 403756250 | High Sign | HFTD Tier 2 | Distribution | 2011-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012356 | 403756726 | Molding | HFTD Tier 2 | Distribution | 2011-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012357 | 403756746 | High Sign | HFTD Tier 2 | Distribution | 2011-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012358 | 403756753 | Molding | HFTD Tier 2 | Distribution | 2011-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012359 | 403756940 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012360 | 403758760 | Guy | HFTD Tier 2 | Distribution | 2011-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012361 | 403759334 | Molding | HFTD Tier 3 | Distribution | 2011-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012362 | 403759353 | High Sign | HFTD Tier 3 | Distribution | 2011-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012363 | 403759360 | Guy | HFTD Tier 3 | Distribution | 2011-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012364 | 403761829 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012365 | 403767035 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-06-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012366 | 403768351 | Molding | HFTD Tier 3 | Distribution | 2011-06-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012367 | 403768731 | High Sign | HFTD Tier 2 | Distribution | 2011-06-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012368 | 403768993 | Molding | HFTD Tier 3 | Distribution | 2011-06-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012369 | 403769343 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012370 | 403769747 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012371 | 403770515 | High Sign | HFTD Tier 2 | Distribution | 2011-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012372 | 403770818 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012373 | 403771385 | Ground | HFTD Tier 3 | Distribution | 2011-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012374 | 403771386 | Molding | HFTD Tier 3 | Distribution | 2011-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012375 | 403771559 | High Sign | HFTD Tier 2 | Distribution | 2011-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012376 | 403772754 | High Sign | HFTD Tier 3 | Distribution | 2011-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012377 | 403772765 | Molding | HFTD Tier 3 | Distribution | 2011-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012378 | 403773650 | Guy | HFTD Tier 2 | Distribution | 2011-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012379 | 403773651 | Molding | HFTD Tier 2 | Distribution | 2011-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012380 | 403773664 | High Sign | HFTD Tier 2 | Distribution | 2011-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012381 | 403774439 | Bond | HFTD Tier 2 | Distribution | 2011-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012382 | 403774967 | High Sign | HFTD Tier 3 | Distribution | 2011-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012383 | 403774981 | Molding | HFTD Tier 3 | Distribution | 2011-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012384 | 403775039 | High Sign | HFTD Tier 3 | Distribution | 2011-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012385 | 403775045 | Molding | HFTD Tier 3 | Distribution | 2011-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012386 | 403775242 | High Sign | HFTD Tier 3 | Distribution | 2011-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012387 | 403775513 | Molding | HFTD Tier 2 | Distribution | 2011-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012388 | 403776369 | Molding | HFTD Tier 2 | Distribution | 2011-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012389 | 403776542 | Molding | HFTD Tier 2 | Distribution | 2011-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012390 | 403776829 | Molding | HFTD Tier 2 | Distribution | 2011-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012391 | 403776837 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012392 | 403776853 | Molding | HFTD Tier 3 | Distribution | 2011-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012393 | 403776973 | Guy | HFTD Tier 2 | Distribution | 2011-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012394 | 403781422 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012395 | 403782926 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012396 | 403783174 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-06-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012397 | 403784075 | Guy | HFTD Tier 3 | Distribution | 2011-06-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012398 | 403784230 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-06-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012399 | 403784272 | High Sign | HFTD Tier 2 | Distribution | 2011-06-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012400 | 403785228 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012401 | 403786560 | High Sign | HFTD Tier 2 | Distribution | 2011-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012402 | 403786562 | Molding | HFTD Tier 2 | Distribution | 2011-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012403 | 403786837 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012404 | 403787068 | High Sign | HFTD Tier 3 | Distribution | 2011-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012405 | 403788977 | High Sign | HFTD Tier 2 | Distribution | 2011-07-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012406 | 403789167 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-07-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012407 | 403789875 | Guy | HFTD Tier 3 | Distribution | 2011-07-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012408 | 403789892 | High Sign | HFTD Tier 3 | Distribution | 2011-07-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012409 | 403789893 | Guy | HFTD Tier 3 | Distribution | 2011-07-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012410 | 403790531 | High Sign | HFTD Tier 2 | Distribution | 2011-07-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012411 | 403790533 | High Sign | HFTD Tier 2 | Distribution | 2011-07-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012412 | 403792689 | Molding | HFTD Tier 3 | Distribution | 2011-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012413 | 403793179 | High Sign | HFTD Tier 3 | Distribution | 2011-07-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012414 | 403793180 | High Sign | HFTD Tier 3 | Distribution | 2011-07-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012415 | 403794093 | High Sign | HFTD Tier 2 | Distribution | 2011-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012416 | 403795667 | High Sign | HFTD Tier 3 | Distribution | 2011-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012417 | 403802857 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-07-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012418 | 403802861 | Molding | HFTD Tier 3 | Distribution | 2011-07-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012419 | 403804392 | High Sign | HFTD Tier 3 | Distribution | 2011-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012420 | 403804395 | High Sign | HFTD Tier 3 | Distribution | 2011-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012421 | 403804415 | High Sign | HFTD Tier 3 | Distribution | 2011-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012422 | 403804680 | High Sign | HFTD Tier 2 | Distribution | 2011-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012423 | 403805538 | Molding | HFTD Tier 3 | Distribution | 2011-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012424 | 403806193 | Molding | HFTD Tier 3 | Distribution | 2011-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012425 | 403806216 | Molding | HFTD Tier 3 | Distribution | 2011-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012426 | 403808919 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012427 | 403811643 | Molding | HFTD Tier 3 | Distribution | 2011-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012428 | 403811872 | Molding | HFTD Tier 2 | Distribution | 2011-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012429 | 403811882 | Molding | HFTD Tier 3 | Distribution | 2011-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012430 | 403811886 | Molding | HFTD Tier 3 | Distribution | 2011-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012431 | 403812437 | Molding | HFTD Tier 3 | Distribution | 2011-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012432 | 403812439 | High Sign | HFTD Tier 3 | Distribution | 2011-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012433 | 403813285 | Molding | HFTD Tier 3 | Distribution | 2011-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012434 | 403813288 | High Sign | HFTD Tier 3 | Distribution | 2011-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012435 | 403813358 | High Sign | HFTD Tier 2 | Distribution | 2011-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012436 | 403814315 | High Sign | HFTD Tier 2 | Distribution | 2011-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012437 | 403815621 | High Sign | HFTD Tier 3 | Distribution | 2011-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012438 | 403815670 | High Sign | HFTD Tier 3 | Distribution | 2011-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012439 | 403816036 | High Sign | HFTD Tier 2 | Distribution | 2011-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012440 | 403816053 | High Sign | HFTD Tier 2 | Distribution | 2011-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012441 | 403819109 | Molding | HFTD Tier 2 | Distribution | 2011-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012442 | 403820562 | High Sign | HFTD Tier 2 | Distribution | 2011-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012443 | 403820680 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012444 | 403820684 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012445 | 403822347 | High Sign | HFTD Tier 2 | Distribution | 2011-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012446 | 403822350 | Guy | HFTD Tier 2 | Distribution | 2011-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012447 | 403822665 | Guy | HFTD Tier 2 | Distribution | 2011-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012448 | 403822702 | High Sign | HFTD Tier 2 | Distribution | 2011-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012449 | 403823894 | Molding | HFTD Tier 3 | Distribution | 2011-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012450 | 403824223 | Molding | HFTD Tier 3 | Distribution | 2011-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012451 | 403824231 | High Sign | HFTD Tier 3 | Distribution | 2011-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012452 | 403824736 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012453 | 403824747 | High Sign | HFTD Tier 3 | Distribution | 2011-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012454 | 403827762 | Molding | HFTD Tier 3 | Distribution | 2011-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012455 | 403827765 | Molding | HFTD Tier 3 | Distribution | 2011-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012456 | 403827776 | Molding | HFTD Tier 3 | Distribution | 2011-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012457 | 403827792 | High Sign | HFTD Tier 3 | Distribution | 2011-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012458 | 403827813 | Molding | HFTD Tier 3 | Distribution | 2011-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012459 | 403827874 | High Sign | HFTD Tier 3 | Distribution | 2011-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012460 | 403827960 | Guy | HFTD Tier 2 | Distribution | 2011-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012461 | 403829483 | High Sign | HFTD Tier 3 | Distribution | 2011-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012462 | 403833226 | High Sign | HFTD Tier 3 | Distribution | 2011-07-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012463 | 403834986 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-07-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012464 | 403836228 | Molding | HFTD Tier 3 | Distribution | 2011-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012465 | 403844300 | Molding | HFTD Tier 2 | Distribution | 2011-08-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012466 | 403845792 | High Sign | HFTD Tier 2 | Distribution | 2011-08-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012467 | 403845813 | High Sign | HFTD Tier 2 | Distribution | 2011-08-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012468 | 403846846 | High Sign | HFTD Tier 2 | Distribution | 2011-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012469 | 403848459 | Guy | HFTD Tier 3 | Distribution | 2011-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012470 | 403848464 | Molding | HFTD Tier 3 | Distribution | 2011-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012471 | 403848469 | Molding | HFTD Tier 3 | Distribution | 2011-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012472 | 403848481 | Guy | HFTD Tier 3 | Distribution | 2011-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012473 | 403849222 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-08-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012474 | 403849309 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-08-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012475 | 403849330 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-08-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012476 | 403849357 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-08-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012477 | 403850910 | Guy | HFTD Tier 3 | Distribution | 2011-08-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012478 | 403851261 | High Sign | HFTD Tier 3 | Distribution | 2011-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012479 | 403851273 | Guy | HFTD Tier 3 | Distribution | 2011-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012480 | 403851350 | High Sign | HFTD Tier 3 | Distribution | 2011-08-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012481 | 403851351 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-08-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012482 | 403851538 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012483 | 403852832 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012484 | 403853775 | Molding | HFTD Tier 3 | Distribution | 2011-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012485 | 403853778 | Riser/Conduit | HFTD Tier 3 | Distribution | 2011-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012486 | 403854666 | Guy | HFTD Tier 2 | Distribution | 2011-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012487 | 403854683 | High Sign | HFTD Tier 2 | Distribution | 2011-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012488 | 403856062 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012489 | 403856823 | Molding | HFTD Tier 2 | Distribution | 2011-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012490 | 403856835 | Riser/Conduit | HFTD Tier 2 | Distribution | 2011-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012491 | 403857512 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012492 | 403857513 | High Sign | HFTD Tier 2 | Distribution | 2011-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012493 | 403858048 | Molding | HFTD Tier 3 | Distribution | 2011-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012494 | 403858053 | Molding | HFTD Tier 3 | Distribution | 2011-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012495 | 403858081 | Guy | HFTD Tier 3 | Distribution | 2011-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012496 | 403859159 | High Sign | HFTD Tier 2 | Distribution | 2011-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012497 | 403859173 | Molding | HFTD Tier 2 | Distribution | 2011-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012498 | 403859174 | High Sign | HFTD Tier 2 | Distribution | 2011-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012499 | 403859205 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012500 | 403859486 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012501 | 403859510 | Anchor | HFTD Tier 3 | Distribution | 2011-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012502 | 403859515 | Molding | HFTD Tier 3 | Distribution | 2011-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012503 | 403859528 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012504 | 403859545 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012505 | 403859551 | Guy | HFTD Tier 3 | Distribution | 2011-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012506 | 403859957 | High Sign | HFTD Tier 2 | Distribution | 2011-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012507 | 403859990 | High Sign | HFTD Tier 2 | Distribution | 2011-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012508 | 403859992 | High Sign | HFTD Tier 2 | Distribution | 2011-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012509 | 403860692 | Insulator | HFTD Tier 2 | Distribution | 2011-08-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012510 | 403860855 | Molding | HFTD Tier 2 | Distribution | 2011-08-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012511 | 403860856 | High Sign | HFTD Tier 2 | Distribution | 2011-08-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012512 | 403861895 | Guy | HFTD Tier 2 | Distribution | 2011-08-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012513 | 403861896 | Guy | HFTD Tier 2 | Distribution | 2011-08-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012514 | 403861905 | Guy | HFTD Tier 2 | Distribution | 2011-08-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012515 | 403861915 | Guy | HFTD Tier 2 | Distribution | 2011-08-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012516 | 403862281 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-08-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012517 | 403864030 | High Sign | HFTD Tier 2 | Distribution | 2011-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012518 | 403867579 | Molding | HFTD Tier 3 | Distribution | 2011-08-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012519 | 403867930 | High Sign | HFTD Tier 2 | Distribution | 2011-08-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012520 | 403867988 | High Sign | HFTD Tier 2 | Distribution | 2011-08-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012521 | 403868703 | Guy | HFTD Tier 2 | Distribution | 2011-08-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012522 | 403869698 | High Sign | HFTD Tier 2 | Distribution | 2011-08-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012523 | 403869899 | High Sign | HFTD Tier 2 | Distribution | 2011-08-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012524 | 403869952 | High Sign | HFTD Tier 2 | Distribution | 2011-08-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012525 | 403870755 | Molding | HFTD Tier 2 | Distribution | 2011-08-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012526 | 403870854 | Molding | HFTD Tier 3 | Distribution | 2011-08-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012527 | 403871872 | High Sign | HFTD Tier 3 | Distribution | 2011-08-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012528 | 403871880 | High Sign | HFTD Tier 3 | Distribution | 2011-08-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012529 | 403872558 | High Sign | HFTD Tier 2 | Distribution | 2011-08-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012530 | 403873340 | High Sign | HFTD Tier 2 | Distribution | 2011-08-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012531 | 403873470 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-08-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012532 | 403873516 | Molding | HFTD Tier 3 | Distribution | 2011-08-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012533 | 403873530 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-08-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012534 | 403875190 | High Sign | HFTD Tier 2 | Distribution | 2011-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012535 | 403875859 | Molding | HFTD Tier 2 | Distribution | 2011-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012536 | 403875880 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012537 | 403876071 | High Sign | HFTD Tier 2 | Distribution | 2011-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012538 | 403876075 | High Sign | HFTD Tier 2 | Distribution | 2011-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012539 | 403877006 | High Sign | HFTD Tier 2 | Distribution | 2011-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012540 | 403879092 | Molding | HFTD Tier 3 | Distribution | 2011-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012541 | 403879095 | Molding | HFTD Tier 3 | Distribution | 2011-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012542 | 403879101 | High Sign | HFTD Tier 3 | Distribution | 2011-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012543 | 403879105 | Riser/Conduit | HFTD Tier 3 | Distribution | 2011-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012544 | 403883096 | Bond | HFTD Tier 2 | Distribution | 2011-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012545 | 403883098 | Molding | HFTD Tier 2 | Distribution | 2011-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012546 | 403883116 | Molding | HFTD Tier 2 | Distribution | 2011-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012547 | 403883582 | Molding | HFTD Tier 3 | Distribution | 2011-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012548 | 403883718 | Molding | HFTD Tier 3 | Distribution | 2009-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012549 | 403883743 | Molding | HFTD Tier 3 | Distribution | 2009-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012550 | 403883808 | High Sign | HFTD Tier 3 | Distribution | 2009-10-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012551 | 403883838 | High Sign | HFTD Tier 3 | Distribution | 2009-10-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012552 | 403883957 | High Sign | HFTD Tier 3 | Distribution | 2009-08-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012553 | 403884764 | High Sign | HFTD Tier 3 | Distribution | 2011-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012554 | 403884765 | Molding | HFTD Tier 3 | Distribution | 2011-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012555 | 403885746 | Guy | HFTD Tier 2 | Distribution | 2011-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012556 | 403886365 | Guy | HFTD Tier 2 | Distribution | 2011-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012557 | 403886377 | High Sign | HFTD Tier 2 | Distribution | 2011-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012558 | 403886496 | High Sign | HFTD Tier 2 | Distribution | 2011-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012559 | 403886505 | Molding | HFTD Tier 2 | Distribution | 2011-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012560 | 403886749 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012561 | 403886752 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012562 | 403889023 | Riser/Conduit | HFTD Tier 2 | Distribution | 2011-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012563 | 403889198 | High Sign | HFTD Tier 2 | Distribution | 2011-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012564 | 403889411 | Molding | HFTD Tier 2 | Distribution | 2011-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012565 | 403889415 | High Sign | HFTD Tier 2 | Distribution | 2011-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012566 | 403889417 | Molding | HFTD Tier 2 | Distribution | 2011-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012567 | 403889459 | Molding | HFTD Tier 2 | Distribution | 2011-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012568 | 403889503 | Molding | HFTD Tier 2 | Distribution | 2011-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012569 | 403889505 | High Sign | HFTD Tier 2 | Distribution | 2011-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012570 | 403890967 | High Sign | HFTD Tier 2 | Distribution | 2011-08-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012571 | 403891874 | High Sign | HFTD Tier 3 | Distribution | 2011-08-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012572 | 403893735 | High Sign | HFTD Tier 2 | Distribution | 2011-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012573 | 403895314 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012574 | 403896614 | High Sign | HFTD Tier 3 | Distribution | 2011-08-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012575 | 403900652 | High Sign | HFTD Tier 2 | Distribution | 2011-08-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012576 | 403900984 | Molding | HFTD Tier 3 | Distribution | 2011-08-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012577 | 403901347 | High Sign | HFTD Tier 3 | Distribution | 2011-08-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012578 | 403901362 | Molding | HFTD Tier 3 | Distribution | 2011-08-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012579 | 403904866 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012580 | 403904869 | Molding | HFTD Tier 2 | Distribution | 2011-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012581 | 403904873 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012582 | 403904881 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012583 | 403912121 | Molding | HFTD Tier 2 | Distribution | 2011-09-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012584 | 403913688 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-09-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012585 | 403913694 | High Sign | HFTD Tier 2 | Distribution | 2011-09-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012586 | 403917273 | High Sign | HFTD Tier 3 | Distribution | 2011-09-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012587 | 403919287 | Molding | HFTD Tier 3 | Distribution | 2011-09-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012588 | 403920547 | Molding | HFTD Tier 2 | Distribution | 2011-09-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012589 | 403920548 | High Sign | HFTD Tier 2 | Distribution | 2011-09-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012590 | 403924797 | Molding | HFTD Tier 3 | Distribution | 2011-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012591 | 403924802 | High Sign | HFTD Tier 3 | Distribution | 2011-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012592 | 403924810 | Molding | HFTD Tier 3 | Distribution | 2011-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012593 | 403926299 | Guy | HFTD Tier 2 | Distribution | 2011-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012594 | 403926302 | High Sign | HFTD Tier 2 | Distribution | 2011-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012595 | 403926318 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-09-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012596 | 403928272 | High Sign | HFTD Tier 3 | Distribution | 2011-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012597 | 403928300 | Molding | HFTD Tier 3 | Distribution | 2011-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012598 | 403928326 | High Sign | HFTD Tier 3 | Distribution | 2011-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012599 | 403928437 | High Sign | HFTD Tier 3 | Distribution | 2011-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012600 | 403929404 | High Sign | HFTD Tier 2 | Distribution | 2011-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012601 | 403929411 | Molding | HFTD Tier 2 | Distribution | 2011-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012602 | 403930435 | Molding | HFTD Tier 2 | Distribution | 2011-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012603 | 403930438 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012604 | 403930439 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012605 | 403930564 | Guy | HFTD Tier 2 | Distribution | 2011-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012606 | 403934986 | Guy | HFTD Tier 2 | Distribution | 2011-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012607 | 403934987 | Guy | HFTD Tier 2 | Distribution | 2011-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012608 | 403935089 | Guy | HFTD Tier 2 | Distribution | 2011-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012609 | 403935109 | Guy | HFTD Tier 2 | Distribution | 2011-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012610 | 403935117 | High Sign | HFTD Tier 2 | Distribution | 2011-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012611 | 403935124 | High Sign | HFTD Tier 2 | Distribution | 2011-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012612 | 403935946 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-09-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012613 | 403939925 | High Sign | HFTD Tier 2 | Distribution | 2011-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012614 | 403939939 | Molding | HFTD Tier 2 | Distribution | 2011-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012615 | 403939945 | High Sign | HFTD Tier 2 | Distribution | 2011-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012616 | 403939960 | Guy | HFTD Tier 2 | Distribution | 2011-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012617 | 403939965 | Guy | HFTD Tier 2 | Distribution | 2011-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012618 | 403942737 | High Sign | HFTD Tier 2 | Distribution | 2011-09-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012619 | 403951301 | Molding | HFTD Tier 2 | Distribution | 2011-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012620 | 403951320 | High Sign | HFTD Tier 2 | Distribution | 2011-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012621 | 403951330 | Guy | HFTD Tier 2 | Distribution | 2011-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012622 | 403951484 | High Sign | HFTD Tier 2 | Distribution | 2011-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012623 | 403953804 | Molding | HFTD Tier 2 | Distribution | 2011-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012624 | 403953805 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012625 | 403959609 | High Sign | HFTD Tier 2 | Distribution | 2011-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012626 | 403962718 | Molding | HFTD Tier 2 | Distribution | 2011-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012627 | 403967247 | High Sign | HFTD Tier 2 | Distribution | 2011-10-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012628 | 403967847 | High Sign | HFTD Tier 2 | Distribution | 2011-10-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012629 | 403969939 | High Sign | HFTD Tier 2 | Distribution | 2011-10-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012630 | 403971885 | Ground | HFTD Tier 2 | Distribution | 2011-10-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012631 | 403971886 | Molding | HFTD Tier 2 | Distribution | 2011-10-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012632 | 403971895 | Molding | HFTD Tier 2 | Distribution | 2011-10-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012633 | 403971896 | Molding | HFTD Tier 2 | Distribution | 2011-10-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012634 | 403971910 | Molding | HFTD Tier 2 | Distribution | 2011-10-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012635 | 403971936 | Molding | HFTD Tier 2 | Distribution | 2011-10-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012636 | 403971945 | High Sign | HFTD Tier 2 | Distribution | 2011-10-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012637 | 403971947 | Molding | HFTD Tier 2 | Distribution | 2011-10-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012638 | 403971958 | Molding | HFTD Tier 2 | Distribution | 2011-10-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012639 | 403971993 | Molding | HFTD Tier 2 | Distribution | 2011-10-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012640 | 403971997 | Molding | HFTD Tier 2 | Distribution | 2011-10-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012641 | 403976299 | Molding | HFTD Tier 2 | Distribution | 2011-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012642 | 403985519 | High Sign | HFTD Tier 2 | Distribution | 2011-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012643 | 403985530 | Ground | HFTD Tier 2 | Distribution | 2011-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012644 | 403985531 | Molding | HFTD Tier 2 | Distribution | 2011-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012645 | 403985533 | Molding | HFTD Tier 2 | Distribution | 2011-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012646 | 403985536 | Molding | HFTD Tier 2 | Distribution | 2011-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012647 | 403985537 | High Sign | HFTD Tier 2 | Distribution | 2011-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012648 | 403985540 | High Sign | HFTD Tier 2 | Distribution | 2011-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012649 | 403985543 | Molding | HFTD Tier 2 | Distribution | 2011-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012650 | 403985545 | Molding | HFTD Tier 2 | Distribution | 2011-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012651 | 403985546 | Molding | HFTD Tier 2 | Distribution | 2011-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012652 | 403985548 | Molding | HFTD Tier 2 | Distribution | 2011-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012653 | 403985550 | Molding | HFTD Tier 2 | Distribution | 2011-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012654 | 403985554 | Molding | HFTD Tier 2 | Distribution | 2011-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012655 | 403985556 | High Sign | HFTD Tier 2 | Distribution | 2011-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012656 | 403985565 | High Sign | HFTD Tier 2 | Distribution | 2011-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012657 | 403990356 | High Sign | HFTD Tier 2 | Distribution | 2011-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012658 | 403990359 | High Sign | HFTD Tier 2 | Distribution | 2011-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012659 | 403990373 | Ground | HFTD Tier 2 | Distribution | 2011-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012660 | 403990591 | Molding | HFTD Tier 2 | Distribution | 2011-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012661 | 403993906 | Molding | HFTD Tier 3 | Distribution | 2011-10-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012662 | 403997902 | High Sign | HFTD Tier 2 | Distribution | 2011-10-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012663 | 404012424 | High Sign | HFTD Tier 3 | Distribution | 2011-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012664 | 404012426 | High Sign | HFTD Tier 3 | Distribution | 2011-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012665 | 404012427 | High Sign | HFTD Tier 3 | Distribution | 2011-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012666 | 404012428 | High Sign | HFTD Tier 3 | Distribution | 2011-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012667 | 404012434 | High Sign | HFTD Tier 3 | Distribution | 2011-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012668 | 404020649 | High Sign | HFTD Tier 3 | Distribution | 2011-11-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012669 | 404026109 | Molding | HFTD Tier 3 | Distribution | 2011-11-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012670 | 404033467 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-11-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012671 | 404033769 | High Sign | HFTD Tier 3 | Distribution | 2011-11-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012672 | 404035928 | Guy | HFTD Tier 3 | Distribution | 2011-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012673 | 404035942 | High Sign | HFTD Tier 3 | Distribution | 2011-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012674 | 404035966 | High Sign | HFTD Tier 3 | Distribution | 2011-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012675 | 404036037 | High Sign | HFTD Tier 3 | Distribution | 2011-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012676 | 404036041 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012677 | 404037819 | High Sign | HFTD Tier 3 | Distribution | 2011-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012678 | 404037835 | Molding | HFTD Tier 3 | Distribution | 2011-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012679 | 404037840 | High Sign | HFTD Tier 3 | Distribution | 2011-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012680 | 404037842 | High Sign | HFTD Tier 3 | Distribution | 2011-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012681 | 404038357 | High Sign | HFTD Tier 3 | Distribution | 2011-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012682 | 404038358 | Molding | HFTD Tier 3 | Distribution | 2011-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012683 | 404038359 | High Sign | HFTD Tier 3 | Distribution | 2011-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012684 | 404040389 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-11-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012685 | 404040390 | Molding | HFTD Tier 3 | Distribution | 2011-11-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012686 | 404042799 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-11-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012687 | 404042814 | Molding | HFTD Tier 3 | Distribution | 2011-11-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012688 | 404042829 | High Sign | HFTD Tier 3 | Distribution | 2011-11-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012689 | 404042832 | High Sign | HFTD Tier 3 | Distribution | 2011-11-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012690 | 404042834 | High Sign | HFTD Tier 3 | Distribution | 2011-11-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012691 | 404042835 | High Sign | HFTD Tier 3 | Distribution | 2011-11-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012692 | 404045376 | High Sign | HFTD Tier 2 | Distribution | 2011-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012693 | 404045513 | Molding | HFTD Tier 3 | Distribution | 2011-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012694 | 404045562 | High Sign | HFTD Tier 3 | Distribution | 2011-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012695 | 404047982 | High Sign | HFTD Tier 3 | Distribution | 2011-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012696 | 404047984 | High Sign | HFTD Tier 3 | Distribution | 2011-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012697 | 404047992 | Molding | HFTD Tier 3 | Distribution | 2011-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012698 | 404048198 | High Sign | HFTD Tier 3 | Distribution | 2011-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012699 | 404049769 | Molding | HFTD Tier 2 | Distribution | 2011-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012700 | 404049821 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012701 | 404050828 | High Sign | HFTD Tier 3 | Distribution | 2011-11-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012702 | 404050840 | High Sign | HFTD Tier 3 | Distribution | 2011-11-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012703 | 404050848 | Molding | HFTD Tier 3 | Distribution | 2011-11-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012704 | 404050852 | High Sign | HFTD Tier 3 | Distribution | 2011-11-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012705 | 404050854 | High Sign | HFTD Tier 3 | Distribution | 2011-11-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012706 | 404050856 | Molding | HFTD Tier 3 | Distribution | 2011-11-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012707 | 404050862 | High Sign | HFTD Tier 3 | Distribution | 2011-11-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012708 | 404050864 | High Sign | HFTD Tier 3 | Distribution | 2011-11-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012709 | 404050865 | High Sign | HFTD Tier 3 | Distribution | 2011-11-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012710 | 404050870 | High Sign | HFTD Tier 3 | Distribution | 2011-11-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012711 | 404052112 | Molding | HFTD Tier 2 | Distribution | 2011-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012712 | 404052718 | High Sign | HFTD Tier 3 | Distribution | 2011-11-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012713 | 404052940 | High Sign | HFTD Tier 3 | Distribution | 2011-11-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012714 | 404052946 | High Sign | HFTD Tier 3 | Distribution | 2011-11-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012715 | 404052947 | High Sign | HFTD Tier 3 | Distribution | 2011-11-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012716 | 404052950 | Guy | HFTD Tier 3 | Distribution | 2011-11-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012717 | 404052952 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-11-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012718 | 404052953 | High Sign | HFTD Tier 3 | Distribution | 2011-11-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012719 | 404052957 | High Sign | HFTD Tier 3 | Distribution | 2011-11-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012720 | 404052961 | High Sign | HFTD Tier 3 | Distribution | 2011-11-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012721 | 404052964 | High Sign | HFTD Tier 3 | Distribution | 2011-11-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012722 | 404054308 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012723 | 404054319 | High Sign | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012724 | 404054328 | High Sign | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012725 | 404054332 | High Sign | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012726 | 404054351 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012727 | 404054359 | High Sign | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012728 | 404054364 | High Sign | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012729 | 404054373 | High Sign | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012730 | 404054380 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012731 | 404054382 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012732 | 404054386 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012733 | 404054391 | High Sign | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012734 | 404054401 | High Sign | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012735 | 404054408 | High Sign | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012736 | 404054411 | High Sign | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012737 | 404054420 | High Sign | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012738 | 404054422 | High Sign | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012739 | 404054424 | Molding | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012740 | 404054442 | Molding | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012741 | 404054446 | High Sign | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012742 | 404054895 | High Sign | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012743 | 404054896 | High Sign | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012744 | 404054978 | High Sign | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012745 | 404054979 | High Sign | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012746 | 404054989 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012747 | 404054996 | High Sign | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012748 | 404055006 | High Sign | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012749 | 404055013 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012750 | 404055023 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012751 | 404055024 | Molding | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012752 | 404055027 | Molding | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012753 | 404055029 | High Sign | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012754 | 404055845 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-11-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012755 | 404055876 | High Sign | HFTD Tier 3 | Distribution | 2011-11-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012756 | 404055877 | Molding | HFTD Tier 3 | Distribution | 2011-11-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012757 | 404055919 | High Sign | HFTD Tier 3 | Distribution | 2011-11-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012758 | 404059431 | Riser/Conduit | HFTD Tier 3 | Distribution | 2011-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012759 | 404059433 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012760 | 404059436 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012761 | 404059446 | Molding | HFTD Tier 3 | Distribution | 2011-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012762 | 404059447 | High Sign | HFTD Tier 3 | Distribution | 2011-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012763 | 404059460 | Molding | HFTD Tier 3 | Distribution | 2011-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012764 | 404059461 | Molding | HFTD Tier 3 | Distribution | 2011-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012765 | 404059462 | High Sign | HFTD Tier 3 | Distribution | 2011-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012766 | 404059463 | High Sign | HFTD Tier 3 | Distribution | 2011-11-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012767 | 404061599 | Guy | HFTD Tier 3 | Distribution | 2011-11-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012768 | 404061602 | Riser/Conduit | HFTD Tier 3 | Distribution | 2011-11-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012769 | 404061604 | Bond | HFTD Tier 3 | Distribution | 2011-11-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012770 | 404061613 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-11-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012771 | 404061630 | Molding | HFTD Tier 3 | Distribution | 2011-11-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012772 | 404061633 | Molding | HFTD Tier 3 | Distribution | 2011-11-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012773 | 404061636 | High Sign | HFTD Tier 3 | Distribution | 2011-11-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012774 | 404061650 | High Sign | HFTD Tier 3 | Distribution | 2011-11-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012775 | 404062138 | High Sign | HFTD Tier 2 | Distribution | 2011-11-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012776 | 404062161 | High Sign | HFTD Tier 2 | Distribution | 2011-11-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012777 | 404063768 | Molding | HFTD Tier 3 | Distribution | 2011-11-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012778 | 404063769 | High Sign | HFTD Tier 3 | Distribution | 2011-11-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012779 | 404063772 | Bond | HFTD Tier 3 | Distribution | 2011-11-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012780 | 404063801 | High Sign | HFTD Tier 3 | Distribution | 2011-11-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012781 | 404066337 | Molding | HFTD Tier 3 | Distribution | 2011-11-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012782 | 404066385 | Molding | HFTD Tier 3 | Distribution | 2011-11-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012783 | 404067024 | Molding | HFTD Tier 3 | Distribution | 2011-11-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012784 | 404067040 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-11-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012785 | 404067044 | Molding | HFTD Tier 3 | Distribution | 2011-11-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012786 | 404067053 | High Sign | HFTD Tier 3 | Distribution | 2011-11-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012787 | 404067058 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-11-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012788 | 404069358 | Riser/Conduit | HFTD Tier 3 | Distribution | 2011-11-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012789 | 404069364 | Molding | HFTD Tier 3 | Distribution | 2011-11-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012790 | 404069365 | High Sign | HFTD Tier 3 | Distribution | 2011-11-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012791 | 404069367 | High Sign | HFTD Tier 3 | Distribution | 2011-11-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012792 | 404069368 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-11-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012793 | 404069380 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-11-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012794 | 404069401 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-11-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012795 | 404071377 | Riser/Conduit | HFTD Tier 3 | Distribution | 2011-11-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012796 | 404071398 | High Sign | HFTD Tier 3 | Distribution | 2011-11-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012797 | 404071413 | High Sign | HFTD Tier 3 | Distribution | 2011-11-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012798 | 404071431 | High Sign | HFTD Tier 3 | Distribution | 2011-11-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012799 | 404073493 | High Sign | HFTD Tier 3 | Distribution | 2011-12-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012800 | 404073546 | High Sign | HFTD Tier 3 | Distribution | 2011-12-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012801 | 404073550 | Molding | HFTD Tier 3 | Distribution | 2011-12-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012802 | 404074804 | Molding | HFTD Tier 2 | Distribution | 2011-12-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012803 | 404075536 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-12-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012804 | 404086962 | High Sign | HFTD Tier 2 | Distribution | 2011-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012805 | 404087586 | High Sign | HFTD Tier 2 | Distribution | 2011-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012806 | 404088499 | Guy | HFTD Tier 3 | Distribution | 2011-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012807 | 404088506 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012808 | 404088575 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012809 | 404088591 | Guy | HFTD Tier 3 | Distribution | 2011-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012810 | 404090148 | High Sign | HFTD Tier 3 | Distribution | 2011-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012811 | 404090805 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-12-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012812 | 404093127 | High Sign | HFTD Tier 3 | Distribution | 2011-12-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012813 | 404093153 | Molding | HFTD Tier 3 | Distribution | 2011-12-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012814 | 404093603 | Molding | HFTD Tier 2 | Distribution | 2011-12-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012815 | 404094609 | High Sign | HFTD Tier 3 | Distribution | 2011-12-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012816 | 404094611 | High Sign | HFTD Tier 3 | Distribution | 2011-12-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012817 | 404108724 | High Sign | HFTD Tier 2 | Distribution | 2011-12-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012818 | 404111301 | High Sign | HFTD Tier 3 | Distribution | 2011-12-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012819 | 404117025 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012820 | 404117026 | Riser/Conduit | HFTD Tier 3 | Distribution | 2011-12-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012821 | 404119822 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-12-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012822 | 404119835 | Molding | HFTD Tier 3 | Distribution | 2011-12-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012823 | 404121083 | Molding | HFTD Tier 3 | Distribution | 2011-12-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012824 | 404121114 | Guy | HFTD Tier 3 | Distribution | 2011-12-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012825 | 404121124 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-12-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012826 | 404154596 | Guy | HFTD Tier 2 | Distribution | 2012-01-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012827 | 404158144 | Guy | HFTD Tier 3 | Distribution | 2012-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012828 | 404161344 | High Sign | HFTD Tier 2 | Distribution | 2012-01-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012829 | 404176999 | Molding | HFTD Tier 2 | Distribution | 2012-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012830 | 404180083 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012831 | 404180087 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012832 | 404181460 | Molding | HFTD Tier 2 | Distribution | 2012-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012833 | 404182398 | Riser/Conduit | HFTD Tier 3 | Distribution | 2012-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012834 | 404182425 | Molding | HFTD Tier 3 | Distribution | 2012-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012835 | 404182444 | Guy | HFTD Tier 3 | Distribution | 2012-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012836 | 404183533 | Molding | HFTD Tier 3 | Distribution | 2012-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012837 | 404183599 | High Sign | HFTD Tier 3 | Distribution | 2012-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012838 | 404183678 | High Sign | HFTD Tier 3 | Distribution | 2012-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012839 | 404183687 | Molding | HFTD Tier 3 | Distribution | 2012-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012840 | 404183959 | High Sign | HFTD Tier 3 | Distribution | 2012-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012841 | 404183964 | High Sign | HFTD Tier 2 | Distribution | 2012-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012842 | 404183971 | High Sign | HFTD Tier 2 | Distribution | 2012-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012843 | 404184002 | High Sign | HFTD Tier 2 | Distribution | 2012-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012844 | 404184022 | High Sign | HFTD Tier 2 | Distribution | 2012-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012845 | 404184026 | High Sign | HFTD Tier 2 | Distribution | 2012-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012846 | 404184999 | Molding | HFTD Tier 2 | Distribution | 2012-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012847 | 404185729 | High Sign | HFTD Tier 3 | Distribution | 2012-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012848 | 404185862 | Molding | HFTD Tier 3 | Distribution | 2012-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012849 | 404185863 | High Sign | HFTD Tier 3 | Distribution | 2012-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012850 | 404186683 | Guy | HFTD Tier 3 | Distribution | 2012-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012851 | 404187066 | High Sign | HFTD Tier 2 | Distribution | 2012-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012852 | 404187087 | Molding | HFTD Tier 2 | Distribution | 2012-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012853 | 404187879 | Molding | HFTD Tier 3 | Distribution | 2012-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012854 | 404188803 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012855 | 404190479 | Riser/Conduit | HFTD Tier 2 | Distribution | 2012-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012856 | 404190846 | High Sign | HFTD Tier 3 | Distribution | 2012-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012857 | 404191220 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012858 | 404191916 | Molding | HFTD Tier 2 | Distribution | 2012-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012859 | 404192809 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012860 | 404193920 | Molding | HFTD Tier 3 | Distribution | 2012-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012861 | 404194239 | Molding | HFTD Tier 3 | Distribution | 2012-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012862 | 404194544 | Molding | HFTD Tier 2 | Distribution | 2012-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012863 | 404194553 | High Sign | HFTD Tier 2 | Distribution | 2012-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012864 | 404194558 | High Sign | HFTD Tier 2 | Distribution | 2012-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012865 | 404194561 | High Sign | HFTD Tier 2 | Distribution | 2012-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012866 | 404194567 | High Sign | HFTD Tier 2 | Distribution | 2012-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012867 | 404194571 | Molding | HFTD Tier 2 | Distribution | 2012-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012868 | 404194572 | Molding | HFTD Tier 2 | Distribution | 2012-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012869 | 404194578 | Molding | HFTD Tier 2 | Distribution | 2012-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012870 | 404194612 | Molding | HFTD Tier 2 | Distribution | 2012-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012871 | 404194637 | Molding | HFTD Tier 2 | Distribution | 2012-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012872 | 404194657 | High Sign | HFTD Tier 2 | Distribution | 2012-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012873 | 404194661 | Molding | HFTD Tier 2 | Distribution | 2012-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012874 | 404194665 | Molding | HFTD Tier 2 | Distribution | 2012-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012875 | 404195535 | High Sign | HFTD Tier 3 | Distribution | 2012-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012876 | 404195543 | High Sign | HFTD Tier 3 | Distribution | 2012-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012877 | 404195574 | High Sign | HFTD Tier 3 | Distribution | 2012-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012878 | 404195723 | Molding | HFTD Tier 3 | Distribution | 2012-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012879 | 404195724 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012880 | 404195732 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012881 | 404195749 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012882 | 404195897 | Riser/Conduit | HFTD Tier 3 | Distribution | 2012-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012883 | 404196475 | Guy | HFTD Tier 3 | Distribution | 2012-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012884 | 404198651 | High Sign | HFTD Tier 3 | Distribution | 2012-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012885 | 404199984 | High Sign | HFTD Tier 3 | Distribution | 2012-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012886 | 404199986 | High Sign | HFTD Tier 3 | Distribution | 2012-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012887 | 404199998 | High Sign | HFTD Tier 3 | Distribution | 2012-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012888 | 404200001 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012889 | 404200009 | High Sign | HFTD Tier 3 | Distribution | 2012-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012890 | 404200019 | High Sign | HFTD Tier 3 | Distribution | 2012-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012891 | 404200030 | High Sign | HFTD Tier 3 | Distribution | 2012-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012892 | 404200588 | Molding | HFTD Tier 2 | Distribution | 2012-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012893 | 404200617 | Molding | HFTD Tier 3 | Distribution | 2012-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012894 | 404200623 | Molding | HFTD Tier 3 | Distribution | 2012-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012895 | 404201496 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012896 | 404201517 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012897 | 404203565 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012898 | 404203585 | Molding | HFTD Tier 3 | Distribution | 2012-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012899 | 404203592 | High Sign | HFTD Tier 3 | Distribution | 2012-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012900 | 404205415 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012901 | 404205449 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012902 | 404205454 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012903 | 404205461 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012904 | 404206104 | Molding | HFTD Tier 2 | Distribution | 2012-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012905 | 404206713 | Molding | HFTD Tier 2 | Distribution | 2012-01-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012906 | 404206865 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-01-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012907 | 404209672 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-01-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012908 | 404209675 | Riser/Conduit | HFTD Tier 3 | Distribution | 2012-01-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012909 | 404209693 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-01-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012910 | 404209729 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-01-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012911 | 404210643 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012912 | 404210809 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012913 | 404210817 | Molding | HFTD Tier 3 | Distribution | 2012-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012914 | 404210837 | Molding | HFTD Tier 3 | Distribution | 2012-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012915 | 404210841 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012916 | 404210851 | Molding | HFTD Tier 3 | Distribution | 2012-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012917 | 404210882 | Guy | HFTD Tier 2 | Distribution | 2012-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012918 | 404211245 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012919 | 404211557 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012920 | 404212830 | High Sign | HFTD Tier 2 | Distribution | 2012-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012921 | 404213239 | Molding | HFTD Tier 2 | Distribution | 2012-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012922 | 404213434 | High Sign | HFTD Tier 3 | Distribution | 2012-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012923 | 404213435 | High Sign | HFTD Tier 3 | Distribution | 2012-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012924 | 404214435 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012925 | 404214449 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012926 | 404214470 | High Sign | HFTD Tier 3 | Distribution | 2012-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012927 | 404214711 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012928 | 404216342 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-01-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012929 | 404216652 | High Sign | HFTD Tier 3 | Distribution | 2012-01-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012930 | 404216738 | High Sign | HFTD Tier 3 | Distribution | 2012-01-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012931 | 404216742 | Molding | HFTD Tier 3 | Distribution | 2012-01-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012932 | 404216754 | High Sign | HFTD Tier 3 | Distribution | 2012-01-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012933 | 404216768 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-01-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012934 | 404218264 | Guy | HFTD Tier 3 | Distribution | 2012-01-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012935 | 404218809 | High Sign | HFTD Tier 2 | Distribution | 2012-01-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012936 | 404218814 | Molding | HFTD Tier 2 | Distribution | 2012-01-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012937 | 404218822 | Molding | HFTD Tier 2 | Distribution | 2012-01-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012938 | 404220188 | High Sign | HFTD Tier 3 | Distribution | 2012-01-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012939 | 404223119 | High Sign | HFTD Tier 2 | Distribution | 2012-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012940 | 404223123 | High Sign | HFTD Tier 2 | Distribution | 2012-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012941 | 404223137 | High Sign | HFTD Tier 2 | Distribution | 2012-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012942 | 404223378 | Molding | HFTD Tier 2 | Distribution | 2012-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012943 | 404224363 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012944 | 404224366 | Guy | HFTD Tier 3 | Distribution | 2012-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012945 | 404224388 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012946 | 404224669 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012947 | 404225897 | High Sign | HFTD Tier 2 | Distribution | 2012-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012948 | 404225931 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012949 | 404226209 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012950 | 404226233 | High Sign | HFTD Tier 3 | Distribution | 2012-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012951 | 404226593 | High Sign | HFTD Tier 3 | Distribution | 2012-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012952 | 404227617 | High Sign | HFTD Tier 3 | Distribution | 2012-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012953 | 404228805 | Riser/Conduit | HFTD Tier 2 | Distribution | 2012-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012954 | 404230160 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012955 | 404230176 | Bond | HFTD Tier 3 | Distribution | 2012-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012956 | 404230179 | Riser/Conduit | HFTD Tier 3 | Distribution | 2012-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012957 | 404230183 | Bond | HFTD Tier 3 | Distribution | 2012-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012958 | 404233609 | High Sign | HFTD Tier 3 | Distribution | 2012-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012959 | 404233643 | Guy | HFTD Tier 3 | Distribution | 2012-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012960 | 404234161 | Molding | HFTD Tier 3 | Distribution | 2012-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012961 | 404234198 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012962 | 404234207 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012963 | 404234234 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012964 | 404235379 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012965 | 404235382 | Molding | HFTD Tier 2 | Distribution | 2012-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012966 | 404235911 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012967 | 404236742 | High Sign | HFTD Tier 3 | Distribution | 2012-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012968 | 404236763 | High Sign | HFTD Tier 3 | Distribution | 2012-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012969 | 404236767 | Molding | HFTD Tier 3 | Distribution | 2012-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012970 | 404236828 | High Sign | HFTD Tier 3 | Distribution | 2012-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012971 | 404236836 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012972 | 404236854 | Guy | HFTD Tier 2 | Distribution | 2012-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012973 | 404236906 | Guy | HFTD Tier 2 | Distribution | 2012-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012974 | 404238774 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012975 | 404238889 | Molding | HFTD Tier 2 | Distribution | 2012-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012976 | 404238930 | High Sign | HFTD Tier 2 | Distribution | 2012-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012977 | 404238965 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012978 | 404238966 | High Sign | HFTD Tier 2 | Distribution | 2012-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012979 | 404238967 | Molding | HFTD Tier 2 | Distribution | 2012-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012980 | 404238975 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012981 | 404238976 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012982 | 404239006 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012983 | 404240000 | High Sign | HFTD Tier 2 | Distribution | 2012-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012984 | 404243066 | High Sign | HFTD Tier 3 | Distribution | 2012-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012985 | 404243081 | High Sign | HFTD Tier 3 | Distribution | 2012-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012986 | 404243086 | Molding | HFTD Tier 3 | Distribution | 2012-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012987 | 404244527 | High Sign | HFTD Tier 3 | Distribution | 2012-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012988 | 404246079 | Molding | HFTD Tier 2 | Distribution | 2012-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012989 | 404246875 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012990 | 404247526 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012991 | 404247958 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012992 | 404248258 | Molding | HFTD Tier 2 | Distribution | 2012-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012993 | 404248656 | Molding | HFTD Tier 3 | Distribution | 2012-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012994 | 404248672 | Molding | HFTD Tier 3 | Distribution | 2012-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012995 | 404248675 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012996 | 404249764 | Molding | HFTD Tier 2 | Distribution | 2012-02-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012997 | 404250177 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-02-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012998 | 404250276 | Molding | HFTD Tier 2 | Distribution | 2012-02-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130012999 | 404252389 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-02-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013000 | 404255338 | Cutout/Fuse | HFTD Tier 3 | Distribution | 2012-02-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013001 | 404255911 | Molding | HFTD Tier 2 | Distribution | 2012-02-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013002 | 404257211 | High Sign | HFTD Tier 3 | Distribution | 2012-02-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013003 | 404258257 | Molding | HFTD Tier 2 | Distribution | 2012-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013004 | 404258277 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-02-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013005 | 404258280 | Molding | HFTD Tier 2 | Distribution | 2012-02-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013006 | 404258288 | Molding | HFTD Tier 2 | Distribution | 2012-02-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013007 | 404259305 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013008 | 404261374 | Ground | HFTD Tier 3 | Distribution | 2012-02-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013009 | 404261948 | Molding | HFTD Tier 2 | Distribution | 2012-02-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013010 | 404262085 | High Sign | HFTD Tier 3 | Distribution | 2012-02-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013011 | 404262099 | Molding | HFTD Tier 3 | Distribution | 2012-02-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013012 | 404264633 | High Sign | HFTD Tier 3 | Distribution | 2012-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013013 | 404264829 | High Sign | HFTD Tier 2 | Distribution | 2012-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013014 | 404264833 | Molding | HFTD Tier 2 | Distribution | 2012-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013015 | 404264838 | Molding | HFTD Tier 2 | Distribution | 2012-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013016 | 404266410 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013017 | 404268423 | Guy | HFTD Tier 2 | Distribution | 2012-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013018 | 404269546 | Molding | HFTD Tier 3 | Distribution | 2012-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013019 | 404269567 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013020 | 404270661 | High Sign | HFTD Tier 3 | Distribution | 2012-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013021 | 404270665 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013022 | 404270692 | Molding | HFTD Tier 3 | Distribution | 2012-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013023 | 404270843 | Molding | HFTD Tier 2 | Distribution | 2012-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013024 | 404270844 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013025 | 404273954 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013026 | 404273959 | Guy | HFTD Tier 2 | Distribution | 2012-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013027 | 404273967 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013028 | 404273968 | Molding | HFTD Tier 2 | Distribution | 2012-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013029 | 404273972 | Guy | HFTD Tier 2 | Distribution | 2012-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013030 | 404274002 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013031 | 404274034 | Molding | HFTD Tier 2 | Distribution | 2012-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013032 | 404274288 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-02-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013033 | 404274846 | Molding | HFTD Tier 2 | Distribution | 2012-02-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013034 | 404274860 | High Sign | HFTD Tier 2 | Distribution | 2012-02-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013035 | 404277646 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-02-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013036 | 404278397 | High Sign | HFTD Tier 2 | Distribution | 2012-02-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013037 | 404278402 | High Sign | HFTD Tier 2 | Distribution | 2012-02-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013038 | 404278403 | High Sign | HFTD Tier 2 | Distribution | 2012-02-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013039 | 404278405 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-02-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013040 | 404278451 | Molding | HFTD Tier 2 | Distribution | 2012-02-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013041 | 404278453 | Molding | HFTD Tier 2 | Distribution | 2012-02-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013042 | 404278462 | High Sign | HFTD Tier 2 | Distribution | 2012-02-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013043 | 404278468 | High Sign | HFTD Tier 2 | Distribution | 2012-02-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013044 | 404278486 | Molding | HFTD Tier 2 | Distribution | 2012-02-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013045 | 404278489 | Vis Strips | HFTD Tier 2 | Distribution | 2012-02-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013046 | 404278561 | High Sign | HFTD Tier 2 | Distribution | 2012-02-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013047 | 404278864 | High Sign | HFTD Tier 2 | Distribution | 2012-02-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013048 | 404280884 | High Sign | HFTD Tier 3 | Distribution | 2012-02-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013049 | 404280895 | Molding | HFTD Tier 3 | Distribution | 2012-02-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013050 | 404280914 | Molding | HFTD Tier 3 | Distribution | 2012-02-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013051 | 404282842 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-02-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013052 | 404284052 | Molding | HFTD Tier 3 | Distribution | 2012-02-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013053 | 404284053 | Molding | HFTD Tier 3 | Distribution | 2012-02-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013054 | 404284109 | Guy | HFTD Tier 3 | Distribution | 2012-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013055 | 404284119 | Insulator | HFTD Tier 3 | Distribution | 2012-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013056 | 404284120 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013057 | 404284328 | Molding | HFTD Tier 2 | Distribution | 2012-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013058 | 404284343 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013059 | 404284346 | Molding | HFTD Tier 2 | Distribution | 2012-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013060 | 404286938 | High Sign | HFTD Tier 2 | Distribution | 2012-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013061 | 404287247 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013062 | 404287292 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013063 | 404287299 | High Sign | HFTD Tier 2 | Distribution | 2012-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013064 | 404287957 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013065 | 404291137 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013066 | 404291207 | High Sign | HFTD Tier 2 | Distribution | 2012-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013067 | 404291333 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013068 | 404291341 | Molding | HFTD Tier 2 | Distribution | 2012-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013069 | 404291344 | High Sign | HFTD Tier 2 | Distribution | 2012-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013070 | 404291433 | High Sign | HFTD Tier 3 | Distribution | 2012-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013071 | 404291456 | Molding | HFTD Tier 3 | Distribution | 2012-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013072 | 404291459 | High Sign | HFTD Tier 3 | Distribution | 2012-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013073 | 404291487 | High Sign | HFTD Tier 3 | Distribution | 2012-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013074 | 404291734 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013075 | 404291752 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013076 | 404291756 | High Sign | HFTD Tier 2 | Distribution | 2012-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013077 | 404292789 | Bond | HFTD Tier 3 | Distribution | 2012-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013078 | 404292841 | High Sign | HFTD Tier 3 | Distribution | 2012-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013079 | 404292851 | High Sign | HFTD Tier 3 | Distribution | 2012-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013080 | 404293982 | High Sign | HFTD Tier 3 | Distribution | 2012-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013081 | 404293983 | Molding | HFTD Tier 3 | Distribution | 2012-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013082 | 404293984 | High Sign | HFTD Tier 3 | Distribution | 2012-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013083 | 404294059 | Guy | HFTD Tier 3 | Distribution | 2012-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013084 | 404294065 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013085 | 404294070 | Guy | HFTD Tier 3 | Distribution | 2012-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013086 | 404296956 | Molding | HFTD Tier 2 | Distribution | 2012-03-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013087 | 404296971 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-03-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013088 | 404301926 | High Sign | HFTD Tier 2 | Distribution | 2012-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013089 | 404301931 | Guy | HFTD Tier 2 | Distribution | 2012-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013090 | 404302061 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013091 | 404304099 | Riser/Conduit | HFTD Tier 2 | Distribution | 2012-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013092 | 404304125 | Molding | HFTD Tier 2 | Distribution | 2012-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013093 | 404306835 | Molding | HFTD Tier 3 | Distribution | 2012-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013094 | 404306846 | High Sign | HFTD Tier 3 | Distribution | 2012-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013095 | 404307501 | High Sign | HFTD Tier 2 | Distribution | 2012-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013096 | 404307530 | Guy | HFTD Tier 2 | Distribution | 2012-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013097 | 404309218 | High Sign | HFTD Tier 3 | Distribution | 2012-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013098 | 404309243 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013099 | 404309685 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013100 | 404309700 | Molding | HFTD Tier 2 | Distribution | 2012-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013101 | 404310476 | Ground | HFTD Tier 2 | Distribution | 2012-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013102 | 404310723 | High Sign | HFTD Tier 2 | Distribution | 2012-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013103 | 404311229 | High Sign | HFTD Tier 3 | Distribution | 2012-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013104 | 404311248 | High Sign | HFTD Tier 3 | Distribution | 2012-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013105 | 404313603 | High Sign | HFTD Tier 3 | Distribution | 2012-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013106 | 404314229 | High Sign | HFTD Tier 2 | Distribution | 2012-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013107 | 404315179 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013108 | 404317374 | Molding | HFTD Tier 2 | Distribution | 2012-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013109 | 404317419 | Molding | HFTD Tier 2 | Distribution | 2012-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013110 | 404317435 | High Sign | HFTD Tier 2 | Distribution | 2012-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013111 | 404317851 | Molding | HFTD Tier 2 | Distribution | 2012-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013112 | 404317852 | High Sign | HFTD Tier 2 | Distribution | 2012-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013113 | 404317860 | Molding | HFTD Tier 2 | Distribution | 2012-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013114 | 404317882 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013115 | 404317949 | High Sign | HFTD Tier 2 | Distribution | 2012-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013116 | 404319272 | Molding | HFTD Tier 3 | Distribution | 2012-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013117 | 404320758 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013118 | 404320858 | High Sign | HFTD Tier 2 | Distribution | 2012-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013119 | 404320876 | Molding | HFTD Tier 2 | Distribution | 2012-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013120 | 404321047 | High Sign | HFTD Tier 2 | Distribution | 2012-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013121 | 404321065 | Molding | HFTD Tier 2 | Distribution | 2012-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013122 | 404322980 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013123 | 404324776 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013124 | 404324787 | Vis Strips | HFTD Tier 2 | Distribution | 2012-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013125 | 404324806 | Vis Strips | HFTD Tier 2 | Distribution | 2012-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013126 | 404326078 | Insulator | HFTD Tier 3 | Distribution | 2012-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013127 | 404327559 | High Sign | HFTD Tier 2 | Distribution | 2012-03-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013128 | 404327581 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-03-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013129 | 404327596 | Pole Tag | HFTD Tier 2 | Distribution | 2012-03-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013130 | 404327600 | Molding | HFTD Tier 2 | Distribution | 2012-03-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013131 | 404327622 | High Sign | HFTD Tier 2 | Distribution | 2012-03-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013132 | 404330647 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013133 | 404331857 | Riser/Conduit | HFTD Tier 3 | Distribution | 2012-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013134 | 404331888 | High Sign | HFTD Tier 3 | Distribution | 2012-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013135 | 404331900 | High Sign | HFTD Tier 3 | Distribution | 2012-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013136 | 404332130 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013137 | 404335598 | Molding | HFTD Tier 2 | Distribution | 2012-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013138 | 404335617 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013139 | 404335620 | High Sign | HFTD Tier 2 | Distribution | 2012-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013140 | 404339045 | Molding | HFTD Tier 2 | Distribution | 2012-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013141 | 404339047 | High Sign | HFTD Tier 2 | Distribution | 2012-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013142 | 404339072 | High Sign | HFTD Tier 2 | Distribution | 2012-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013143 | 404339074 | Molding | HFTD Tier 2 | Distribution | 2012-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013144 | 404339093 | Molding | HFTD Tier 2 | Distribution | 2012-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013145 | 404339100 | High Sign | HFTD Tier 2 | Distribution | 2012-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013146 | 404339115 | Molding | HFTD Tier 2 | Distribution | 2012-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013147 | 404339118 | High Sign | HFTD Tier 2 | Distribution | 2012-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013148 | 404339119 | Molding | HFTD Tier 2 | Distribution | 2012-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013149 | 404339367 | High Sign | HFTD Tier 2 | Distribution | 2012-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013150 | 404339383 | Molding | HFTD Tier 2 | Distribution | 2012-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013151 | 404339388 | Molding | HFTD Tier 2 | Distribution | 2012-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013152 | 404340078 | High Sign | HFTD Tier 2 | Distribution | 2012-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013153 | 404340085 | High Sign | HFTD Tier 2 | Distribution | 2012-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013154 | 404340088 | Molding | HFTD Tier 2 | Distribution | 2012-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013155 | 404340094 | High Sign | HFTD Tier 2 | Distribution | 2012-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013156 | 404340110 | High Sign | HFTD Tier 2 | Distribution | 2012-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013157 | 404340826 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013158 | 404343648 | High Sign | HFTD Tier 2 | Distribution | 2012-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013159 | 404343830 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013160 | 404343848 | Molding | HFTD Tier 2 | Distribution | 2012-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013161 | 404345403 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013162 | 404345419 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013163 | 404347083 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013164 | 404347086 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013165 | 404347129 | High Sign | HFTD Tier 3 | Distribution | 2012-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013166 | 404347134 | Molding | HFTD Tier 3 | Distribution | 2012-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013167 | 404347163 | High Sign | HFTD Tier 3 | Distribution | 2012-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013168 | 404347197 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013169 | 404347243 | Guy | HFTD Tier 2 | Distribution | 2012-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013170 | 404347272 | High Sign | HFTD Tier 2 | Distribution | 2012-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013171 | 404347430 | Molding | HFTD Tier 2 | Distribution | 2012-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013172 | 404347487 | Guy | HFTD Tier 2 | Distribution | 2012-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013173 | 404347615 | Molding | HFTD Tier 3 | Distribution | 2012-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013174 | 404348699 | High Sign | HFTD Tier 2 | Distribution | 2012-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013175 | 404348702 | High Sign | HFTD Tier 2 | Distribution | 2012-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013176 | 404348728 | High Sign | HFTD Tier 3 | Distribution | 2012-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013177 | 404348736 | High Sign | HFTD Tier 3 | Distribution | 2012-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013178 | 404350491 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013179 | 404350531 | High Sign | HFTD Tier 3 | Distribution | 2012-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013180 | 404350537 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013181 | 404350563 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013182 | 404350715 | Molding | HFTD Tier 2 | Distribution | 2012-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013183 | 404350717 | High Sign | HFTD Tier 2 | Distribution | 2012-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013184 | 404350718 | High Sign | HFTD Tier 2 | Distribution | 2012-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013185 | 404350731 | Molding | HFTD Tier 2 | Distribution | 2012-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013186 | 404350738 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013187 | 404350742 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013188 | 404352902 | High Sign | HFTD Tier 2 | Distribution | 2012-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013189 | 404353260 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013190 | 404353288 | Molding | HFTD Tier 2 | Distribution | 2012-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013191 | 404353361 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013192 | 404353370 | High Sign | HFTD Tier 2 | Distribution | 2012-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013193 | 404353393 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013194 | 404353705 | High Sign | HFTD Tier 3 | Distribution | 2012-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013195 | 404354835 | Guy | HFTD Tier 2 | Distribution | 2012-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013196 | 404354838 | Molding | HFTD Tier 2 | Distribution | 2012-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013197 | 404354839 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013198 | 404356246 | Molding | HFTD Tier 2 | Distribution | 2012-04-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013199 | 404357801 | High Sign | HFTD Tier 2 | Distribution | 2012-04-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013200 | 404357969 | Guy | HFTD Tier 3 | Distribution | 2012-04-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013201 | 404357993 | Guy | HFTD Tier 3 | Distribution | 2012-04-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013202 | 404357999 | High Sign | HFTD Tier 3 | Distribution | 2012-04-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013203 | 404358001 | Guy | HFTD Tier 3 | Distribution | 2012-04-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013204 | 404358019 | High Sign | HFTD Tier 3 | Distribution | 2012-04-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013205 | 404359321 | Molding | HFTD Tier 2 | Distribution | 2012-04-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013206 | 404359471 | Molding | HFTD Tier 2 | Distribution | 2012-04-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013207 | 404361088 | High Sign | HFTD Tier 3 | Distribution | 2012-04-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013208 | 404361256 | Molding | HFTD Tier 3 | Distribution | 2012-04-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013209 | 404361362 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-04-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013210 | 404361705 | High Sign | HFTD Tier 2 | Distribution | 2012-04-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013211 | 404361713 | High Sign | HFTD Tier 2 | Distribution | 2012-04-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013212 | 404362694 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013213 | 404362744 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013214 | 404362906 | High Sign | HFTD Tier 2 | Distribution | 2012-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013215 | 404364409 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013216 | 404364589 | Molding | HFTD Tier 2 | Distribution | 2012-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013217 | 404364602 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013218 | 404364672 | Guy | HFTD Tier 2 | Distribution | 2012-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013219 | 404364785 | Molding | HFTD Tier 3 | Distribution | 2012-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013220 | 404365792 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013221 | 404367210 | High Sign | HFTD Tier 2 | Distribution | 2012-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013222 | 404367272 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013223 | 404367335 | Molding | HFTD Tier 3 | Distribution | 2012-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013224 | 404367349 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013225 | 404368365 | High Sign | HFTD Tier 2 | Distribution | 2012-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013226 | 404368368 | High Sign | HFTD Tier 2 | Distribution | 2012-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013227 | 404369402 | High Sign | HFTD Tier 3 | Distribution | 2012-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013228 | 404369470 | Guy | HFTD Tier 3 | Distribution | 2012-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013229 | 404369493 | Molding | HFTD Tier 3 | Distribution | 2012-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013230 | 404369696 | Guy | HFTD Tier 3 | Distribution | 2012-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013231 | 404369746 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013232 | 404369751 | High Sign | HFTD Tier 3 | Distribution | 2012-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013233 | 404369755 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013234 | 404372502 | High Sign | HFTD Tier 3 | Distribution | 2012-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013235 | 404373619 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013236 | 404373630 | High Sign | HFTD Tier 3 | Distribution | 2012-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013237 | 404373700 | Guy | HFTD Tier 3 | Distribution | 2012-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013238 | 404374196 | High Sign | HFTD Tier 3 | Distribution | 2012-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013239 | 404375218 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013240 | 404375226 | High Sign | HFTD Tier 3 | Distribution | 2012-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013241 | 404376428 | Molding | HFTD Tier 3 | Distribution | 2012-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013242 | 404376447 | High Sign | HFTD Tier 3 | Distribution | 2012-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013243 | 404382551 | High Sign | HFTD Tier 3 | Distribution | 2012-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013244 | 404383034 | Guy | HFTD Tier 2 | Distribution | 2012-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013245 | 404383274 | Molding | HFTD Tier 3 | Distribution | 2012-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013246 | 404383338 | High Sign | HFTD Tier 2 | Distribution | 2012-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013247 | 404383348 | High Sign | HFTD Tier 2 | Distribution | 2012-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013248 | 404383365 | High Sign | HFTD Tier 2 | Distribution | 2012-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013249 | 404383367 | High Sign | HFTD Tier 2 | Distribution | 2012-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013250 | 404383381 | High Sign | HFTD Tier 2 | Distribution | 2012-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013251 | 404383382 | High Sign | HFTD Tier 2 | Distribution | 2012-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013252 | 404383387 | High Sign | HFTD Tier 2 | Distribution | 2012-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013253 | 404383388 | High Sign | HFTD Tier 2 | Distribution | 2012-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013254 | 404383392 | High Sign | HFTD Tier 2 | Distribution | 2012-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013255 | 404383415 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013256 | 404384163 | High Sign | HFTD Tier 2 | Distribution | 2012-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013257 | 404385708 | Molding | HFTD Tier 2 | Distribution | 2012-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013258 | 404385721 | High Sign | HFTD Tier 2 | Distribution | 2012-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013259 | 404385722 | High Sign | HFTD Tier 2 | Distribution | 2012-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013260 | 404385723 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013261 | 404385732 | Molding | HFTD Tier 2 | Distribution | 2012-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013262 | 404386563 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013263 | 404386963 | High Sign | HFTD Tier 2 | Distribution | 2012-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013264 | 404387268 | High Sign | HFTD Tier 2 | Distribution | 2012-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013265 | 404388121 | High Sign | HFTD Tier 2 | Distribution | 2012-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013266 | 404388126 | Molding | HFTD Tier 3 | Distribution | 2012-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013267 | 404388246 | High Sign | HFTD Tier 3 | Distribution | 2012-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013268 | 404390418 | Molding | HFTD Tier 3 | Distribution | 2012-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013269 | 404390451 | Guy | HFTD Tier 3 | Distribution | 2012-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013270 | 404391314 | High Sign | HFTD Tier 2 | Distribution | 2012-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013271 | 404391325 | High Sign | HFTD Tier 2 | Distribution | 2012-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013272 | 404391342 | High Sign | HFTD Tier 2 | Distribution | 2012-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013273 | 404391450 | High Sign | HFTD Tier 2 | Distribution | 2012-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013274 | 404394200 | Guy | HFTD Tier 3 | Distribution | 2012-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013275 | 404394415 | High Sign | HFTD Tier 3 | Distribution | 2012-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013276 | 404395287 | Guy | HFTD Tier 2 | Distribution | 2012-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013277 | 404395302 | Guy | HFTD Tier 2 | Distribution | 2012-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013278 | 404395612 | High Sign | HFTD Tier 3 | Distribution | 2012-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013279 | 404396512 | Molding | HFTD Tier 2 | Distribution | 2012-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013280 | 404396737 | Molding | HFTD Tier 2 | Distribution | 2012-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013281 | 404396779 | Riser/Conduit | HFTD Tier 3 | Distribution | 2012-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013282 | 404397289 | High Sign | HFTD Tier 3 | Distribution | 2012-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013283 | 404397301 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013284 | 404397310 | High Sign | HFTD Tier 3 | Distribution | 2012-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013285 | 404398005 | Guy | HFTD Tier 2 | Distribution | 2012-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013286 | 404398011 | Guy | HFTD Tier 2 | Distribution | 2012-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013287 | 404398016 | High Sign | HFTD Tier 2 | Distribution | 2012-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013288 | 404398134 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013289 | 404399006 | Molding | HFTD Tier 3 | Distribution | 2012-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013290 | 404400464 | Molding | HFTD Tier 2 | Distribution | 2012-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013291 | 404400768 | Guy | HFTD Tier 3 | Distribution | 2012-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013292 | 404400857 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013293 | 404406484 | High Sign | HFTD Tier 2 | Distribution | 2012-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013294 | 404406682 | Insulator | HFTD Tier 3 | Distribution | 2012-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013295 | 404406683 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013296 | 404407956 | Guy | HFTD Tier 3 | Distribution | 2012-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013297 | 404407959 | Guy | HFTD Tier 3 | Distribution | 2012-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013298 | 404408209 | High Sign | HFTD Tier 2 | Distribution | 2012-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013299 | 404409519 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013300 | 404409531 | High Sign | HFTD Tier 3 | Distribution | 2012-04-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013301 | 404409536 | High Sign | HFTD Tier 3 | Distribution | 2012-04-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013302 | 404410377 | High Sign | HFTD Tier 3 | Distribution | 2012-04-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013303 | 404410391 | Molding | HFTD Tier 3 | Distribution | 2012-04-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013304 | 404412558 | High Sign | HFTD Tier 2 | Distribution | 2012-04-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013305 | 404412571 | Molding | HFTD Tier 2 | Distribution | 2012-04-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013306 | 404412589 | Molding | HFTD Tier 3 | Distribution | 2012-04-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013307 | 404413150 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013308 | 404413164 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013309 | 404413489 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-04-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013310 | 404413495 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-04-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013311 | 404413590 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013312 | 404415927 | Molding | HFTD Tier 3 | Distribution | 2012-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013313 | 404415936 | Riser/Conduit | HFTD Tier 3 | Distribution | 2012-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013314 | 404417055 | High Sign | HFTD Tier 3 | Distribution | 2012-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013315 | 404417060 | High Sign | HFTD Tier 3 | Distribution | 2012-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013316 | 404418374 | Molding | HFTD Tier 3 | Distribution | 2012-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013317 | 404418378 | Molding | HFTD Tier 3 | Distribution | 2012-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013318 | 404418406 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013319 | 404418423 | Guy | HFTD Tier 3 | Distribution | 2012-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013320 | 404418572 | High Sign | HFTD Tier 3 | Distribution | 2012-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013321 | 404418618 | Bond | HFTD Tier 2 | Distribution | 2012-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013322 | 404419688 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013323 | 404419704 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013324 | 404420321 | Molding | HFTD Tier 2 | Distribution | 2012-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013325 | 404421731 | Molding | HFTD Tier 2 | Distribution | 2012-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013326 | 404421759 | High Sign | HFTD Tier 2 | Distribution | 2012-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013327 | 404421760 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013328 | 404421866 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013329 | 404421867 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013330 | 404421871 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013331 | 404421873 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013332 | 404421877 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013333 | 404421878 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013334 | 404421879 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013335 | 404421881 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013336 | 404421884 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013337 | 404422538 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013338 | 404424351 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013339 | 404424719 | High Sign | HFTD Tier 2 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013340 | 404426937 | Guy | HFTD Tier 3 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013341 | 404426938 | High Sign | HFTD Tier 3 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013342 | 404426957 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013343 | 404426972 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013344 | 404426978 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013345 | 404426982 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013346 | 404427018 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013347 | 404427019 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013348 | 404427020 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013349 | 404427022 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013350 | 404427024 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013351 | 404427025 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013352 | 404427026 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013353 | 404427027 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013354 | 404427028 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013355 | 404427030 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013356 | 404427031 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013357 | 404427032 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013358 | 404427061 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013359 | 404427086 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013360 | 404430020 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-05-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013361 | 404430210 | Molding | HFTD Tier 2 | Distribution | 2012-05-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013362 | 404430219 | Guy | HFTD Tier 2 | Distribution | 2012-05-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013363 | 404430236 | High Sign | HFTD Tier 2 | Distribution | 2012-05-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013364 | 404430242 | Guy | HFTD Tier 2 | Distribution | 2012-05-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013365 | 404430243 | High Sign | HFTD Tier 2 | Distribution | 2012-05-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013366 | 404430245 | Guy | HFTD Tier 2 | Distribution | 2012-05-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013367 | 404430248 | High Sign | HFTD Tier 2 | Distribution | 2012-05-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013368 | 404430288 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013369 | 404431396 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-05-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013370 | 404431486 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013371 | 404431516 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013372 | 404432977 | Molding | HFTD Tier 3 | Distribution | 2012-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013373 | 404432991 | High Sign | HFTD Tier 3 | Distribution | 2012-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013374 | 404432994 | High Sign | HFTD Tier 3 | Distribution | 2012-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013375 | 404433066 | High Sign | HFTD Tier 2 | Distribution | 2012-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013376 | 404434406 | Molding | HFTD Tier 2 | Distribution | 2012-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013377 | 404434415 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013378 | 404434432 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013379 | 404434506 | High Sign | HFTD Tier 3 | Distribution | 2012-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013380 | 404434535 | High Sign | HFTD Tier 3 | Distribution | 2012-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013381 | 404435567 | High Sign | HFTD Tier 3 | Distribution | 2012-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013382 | 404435569 | High Sign | HFTD Tier 3 | Distribution | 2012-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013383 | 404435706 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013384 | 404437491 | Termination | HFTD Tier 3 | Distribution | 2012-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013385 | 404442273 | Insulator | HFTD Tier 2 | Distribution | 2012-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013386 | 404446133 | High Sign | HFTD Tier 2 | Distribution | 2012-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013387 | 404446424 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013388 | 404446432 | High Sign | HFTD Tier 3 | Distribution | 2012-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013389 | 404447267 | Molding | HFTD Tier 3 | Distribution | 2012-05-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013390 | 404449029 | Molding | HFTD Tier 2 | Distribution | 2012-05-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013391 | 404449054 | Molding | HFTD Tier 2 | Distribution | 2012-05-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013392 | 404449065 | Guy | HFTD Tier 2 | Distribution | 2012-05-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013393 | 404449131 | Molding | HFTD Tier 3 | Distribution | 2012-05-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013394 | 404450255 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013395 | 404450259 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013396 | 404451698 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013397 | 404451832 | High Sign | HFTD Tier 3 | Distribution | 2012-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013398 | 404451850 | High Sign | HFTD Tier 3 | Distribution | 2012-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013399 | 404452112 | Molding | HFTD Tier 2 | Distribution | 2012-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013400 | 404452972 | High Sign | HFTD Tier 2 | Distribution | 2012-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013401 | 404452977 | High Sign | HFTD Tier 2 | Distribution | 2012-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013402 | 404452995 | High Sign | HFTD Tier 2 | Distribution | 2012-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013403 | 404452998 | High Sign | HFTD Tier 2 | Distribution | 2012-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013404 | 404453001 | High Sign | HFTD Tier 2 | Distribution | 2012-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013405 | 404453317 | High Sign | HFTD Tier 3 | Distribution | 2012-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013406 | 404453350 | Molding | HFTD Tier 3 | Distribution | 2012-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013407 | 404453435 | Insulator | HFTD Tier 2 | Distribution | 2012-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013408 | 404454841 | Molding | HFTD Tier 3 | Distribution | 2012-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013409 | 404454860 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013410 | 404455141 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013411 | 404455287 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013412 | 404455333 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013413 | 404455366 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013414 | 404456042 | Molding | HFTD Tier 3 | Distribution | 2012-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013415 | 404456219 | Molding | HFTD Tier 3 | Distribution | 2012-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013416 | 404456317 | High Sign | HFTD Tier 3 | Distribution | 2012-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013417 | 404456455 | Molding | HFTD Tier 3 | Distribution | 2012-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013418 | 404457477 | High Sign | HFTD Tier 3 | Distribution | 2012-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013419 | 404457494 | Insulator | HFTD Tier 3 | Distribution | 2012-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013420 | 404457765 | Molding | HFTD Tier 3 | Distribution | 2012-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013421 | 404458047 | Vis Strips | HFTD Tier 2 | Distribution | 2012-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013422 | 404458085 | Guy | HFTD Tier 2 | Distribution | 2012-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013423 | 404458677 | High Sign | HFTD Tier 3 | Distribution | 2012-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013424 | 404458685 | High Sign | HFTD Tier 3 | Distribution | 2012-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013425 | 404461475 | Riser/Conduit | HFTD Tier 3 | Distribution | 2012-05-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013426 | 404461484 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-05-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013427 | 404461617 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-05-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013428 | 404461668 | Molding | HFTD Tier 3 | Distribution | 2012-05-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013429 | 404461750 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-05-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013430 | 404462680 | High Sign | HFTD Tier 3 | Distribution | 2012-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013431 | 404462681 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013432 | 404464339 | Molding | HFTD Tier 2 | Distribution | 2012-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013433 | 404464959 | High Sign | HFTD Tier 2 | Distribution | 2012-05-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013434 | 404465286 | High Sign | HFTD Tier 3 | Distribution | 2012-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013435 | 404465443 | Guy | HFTD Tier 2 | Distribution | 2012-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013436 | 404466842 | Molding | HFTD Tier 3 | Distribution | 2012-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013437 | 404466865 | Molding | HFTD Tier 3 | Distribution | 2012-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013438 | 404467340 | Guy | HFTD Tier 2 | Distribution | 2012-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013439 | 404468552 | Molding | HFTD Tier 3 | Distribution | 2012-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013440 | 404468561 | Molding | HFTD Tier 3 | Distribution | 2012-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013441 | 404468569 | Molding | HFTD Tier 3 | Distribution | 2012-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013442 | 404468577 | Molding | HFTD Tier 3 | Distribution | 2012-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013443 | 404468591 | Riser/Conduit | HFTD Tier 3 | Distribution | 2012-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013444 | 404468598 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013445 | 404468603 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013446 | 404470060 | High Sign | HFTD Tier 2 | Distribution | 2012-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013447 | 404470065 | Molding | HFTD Tier 3 | Distribution | 2012-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013448 | 404470244 | High Sign | HFTD Tier 3 | Distribution | 2012-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013449 | 404471211 | High Sign | HFTD Tier 2 | Distribution | 2012-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013450 | 404471237 | Crossarm | HFTD Tier 2 | Distribution | 2012-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013451 | 404471248 | High Sign | HFTD Tier 2 | Distribution | 2012-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013452 | 404471253 | Molding | HFTD Tier 2 | Distribution | 2012-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013453 | 404471269 | High Sign | HFTD Tier 2 | Distribution | 2012-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013454 | 404471283 | High Sign | HFTD Tier 2 | Distribution | 2012-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013455 | 404471288 | Molding | HFTD Tier 2 | Distribution | 2012-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013456 | 404471298 | High Sign | HFTD Tier 2 | Distribution | 2012-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013457 | 404471354 | High Sign | HFTD Tier 2 | Distribution | 2012-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013458 | 404471380 | High Sign | HFTD Tier 2 | Distribution | 2012-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013459 | 404471385 | High Sign | HFTD Tier 2 | Distribution | 2012-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013460 | 404471388 | High Sign | HFTD Tier 2 | Distribution | 2012-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013461 | 404471389 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013462 | 404471391 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013463 | 404471394 | High Sign | HFTD Tier 2 | Distribution | 2012-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013464 | 404471400 | High Sign | HFTD Tier 2 | Distribution | 2012-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013465 | 404472770 | High Sign | HFTD Tier 3 | Distribution | 2012-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013466 | 404472771 | High Sign | HFTD Tier 2 | Distribution | 2012-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013467 | 404472781 | High Sign | HFTD Tier 3 | Distribution | 2012-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013468 | 404472858 | Molding | HFTD Tier 3 | Distribution | 2012-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013469 | 404472975 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013470 | 404472981 | Molding | HFTD Tier 3 | Distribution | 2012-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013471 | 404472986 | Molding | HFTD Tier 3 | Distribution | 2012-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013472 | 404473004 | High Sign | HFTD Tier 3 | Distribution | 2012-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013473 | 404473737 | High Sign | HFTD Tier 3 | Distribution | 2012-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013474 | 404473758 | High Sign | HFTD Tier 3 | Distribution | 2012-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013475 | 404473761 | High Sign | HFTD Tier 3 | Distribution | 2012-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013476 | 404473762 | Molding | HFTD Tier 3 | Distribution | 2012-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013477 | 404474778 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013478 | 404474861 | Molding | HFTD Tier 2 | Distribution | 2012-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013479 | 404474936 | Molding | HFTD Tier 2 | Distribution | 2012-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013480 | 404476459 | High Sign | HFTD Tier 2 | Distribution | 2012-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013481 | 404476802 | Molding | HFTD Tier 2 | Distribution | 2012-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013482 | 404476838 | Guy | HFTD Tier 2 | Distribution | 2012-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013483 | 404476840 | High Sign | HFTD Tier 2 | Distribution | 2012-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013484 | 404477655 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013485 | 404477665 | High Sign | HFTD Tier 3 | Distribution | 2012-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013486 | 404477682 | High Sign | HFTD Tier 3 | Distribution | 2012-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013487 | 404477683 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013488 | 404477687 | Termination | HFTD Tier 3 | Distribution | 2012-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013489 | 404477712 | High Sign | HFTD Tier 3 | Distribution | 2012-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013490 | 404477728 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013491 | 404479027 | High Sign | HFTD Tier 3 | Distribution | 2012-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013492 | 404479031 | High Sign | HFTD Tier 3 | Distribution | 2012-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013493 | 404479315 | Guy | HFTD Tier 3 | Distribution | 2012-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013494 | 404479344 | High Sign | HFTD Tier 3 | Distribution | 2012-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013495 | 404479493 | High Sign | HFTD Tier 2 | Distribution | 2012-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013496 | 404479654 | High Sign | HFTD Tier 2 | Distribution | 2012-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013497 | 404479665 | Molding | HFTD Tier 2 | Distribution | 2012-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013498 | 404479667 | Molding | HFTD Tier 2 | Distribution | 2012-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013499 | 404479677 | High Sign | HFTD Tier 2 | Distribution | 2012-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013500 | 404479681 | Molding | HFTD Tier 2 | Distribution | 2012-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013501 | 404480211 | High Sign | HFTD Tier 3 | Distribution | 2012-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013502 | 404480225 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013503 | 404480236 | Molding | HFTD Tier 3 | Distribution | 2012-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013504 | 404480275 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013505 | 404485156 | High Sign | HFTD Tier 3 | Distribution | 2012-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013506 | 404485164 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013507 | 404485181 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013508 | 404485272 | High Sign | HFTD Tier 3 | Distribution | 2012-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013509 | 404487013 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013510 | 404487107 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013511 | 404487141 | High Sign | HFTD Tier 2 | Distribution | 2012-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013512 | 404487142 | Molding | HFTD Tier 2 | Distribution | 2012-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013513 | 404489431 | High Sign | HFTD Tier 3 | Distribution | 2012-05-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013514 | 404489870 | Molding | HFTD Tier 3 | Distribution | 2012-05-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013515 | 404490004 | Riser/Conduit | HFTD Tier 2 | Distribution | 2012-05-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013516 | 404490008 | High Sign | HFTD Tier 2 | Distribution | 2012-05-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013517 | 404490013 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-05-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013518 | 404490588 | High Sign | HFTD Tier 3 | Distribution | 2012-05-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013519 | 404490589 | High Sign | HFTD Tier 3 | Distribution | 2012-05-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013520 | 404490603 | High Sign | HFTD Tier 3 | Distribution | 2012-05-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013521 | 404490605 | High Sign | HFTD Tier 3 | Distribution | 2012-05-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013522 | 404490606 | High Sign | HFTD Tier 3 | Distribution | 2012-05-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013523 | 404492893 | Molding | HFTD Tier 3 | Distribution | 2012-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013524 | 404493369 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013525 | 404493407 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013526 | 404493411 | High Sign | HFTD Tier 3 | Distribution | 2012-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013527 | 404493501 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013528 | 404495449 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013529 | 404495454 | High Sign | HFTD Tier 2 | Distribution | 2012-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013530 | 404496375 | High Sign | HFTD Tier 3 | Distribution | 2012-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013531 | 404496398 | High Sign | HFTD Tier 3 | Distribution | 2012-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013532 | 404496424 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013533 | 404496433 | Molding | HFTD Tier 3 | Distribution | 2012-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013534 | 404497640 | Molding | HFTD Tier 3 | Distribution | 2012-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013535 | 404499027 | Molding | HFTD Tier 3 | Distribution | 2012-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013536 | 404499537 | High Sign | HFTD Tier 2 | Distribution | 2012-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013537 | 404499555 | Molding | HFTD Tier 2 | Distribution | 2012-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013538 | 404499556 | High Sign | HFTD Tier 2 | Distribution | 2012-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013539 | 404499561 | High Sign | HFTD Tier 2 | Distribution | 2012-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013540 | 404499576 | Molding | HFTD Tier 2 | Distribution | 2012-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013541 | 404499590 | Molding | HFTD Tier 2 | Distribution | 2012-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013542 | 404500439 | Riser/Conduit | HFTD Tier 3 | Distribution | 2012-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013543 | 404500479 | High Sign | HFTD Tier 3 | Distribution | 2012-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013544 | 404500592 | Guy | HFTD Tier 2 | Distribution | 2012-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013545 | 404502221 | High Sign | HFTD Tier 3 | Distribution | 2012-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013546 | 404502320 | Molding | HFTD Tier 3 | Distribution | 2012-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013547 | 404502683 | High Sign | HFTD Tier 2 | Distribution | 2012-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013548 | 404502690 | Guy | HFTD Tier 2 | Distribution | 2012-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013549 | 404502715 | High Sign | HFTD Tier 2 | Distribution | 2012-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013550 | 404505437 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013551 | 404505549 | High Sign | HFTD Tier 3 | Distribution | 2012-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013552 | 404507904 | High Sign | HFTD Tier 2 | Distribution | 2012-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013553 | 404507907 | High Sign | HFTD Tier 2 | Distribution | 2012-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013554 | 404508352 | Molding | HFTD Tier 3 | Distribution | 2012-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013555 | 404509265 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013556 | 404511710 | High Sign | HFTD Tier 3 | Distribution | 2012-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013557 | 404511807 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013558 | 404512069 | High Sign | HFTD Tier 2 | Distribution | 2012-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013559 | 404512101 | Guy | HFTD Tier 2 | Distribution | 2012-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013560 | 404512128 | Crossarm | HFTD Tier 2 | Distribution | 2012-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013561 | 404512137 | High Sign | HFTD Tier 2 | Distribution | 2012-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013562 | 404512139 | Molding | HFTD Tier 2 | Distribution | 2012-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013563 | 404512162 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013564 | 404512165 | High Sign | HFTD Tier 2 | Distribution | 2012-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013565 | 404512167 | Molding | HFTD Tier 2 | Distribution | 2012-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013566 | 404512291 | Guy | HFTD Tier 2 | Distribution | 2012-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013567 | 404512335 | High Sign | HFTD Tier 2 | Distribution | 2012-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013568 | 404512357 | High Sign | HFTD Tier 2 | Distribution | 2012-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013569 | 404512775 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013570 | 404512888 | High Sign | HFTD Tier 2 | Distribution | 2012-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013571 | 404512928 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013572 | 404512961 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013573 | 404514242 | Molding | HFTD Tier 2 | Distribution | 2012-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013574 | 404514243 | Guy | HFTD Tier 2 | Distribution | 2012-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013575 | 404514694 | High Sign | HFTD Tier 2 | Distribution | 2012-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013576 | 404515318 | High Sign | HFTD Tier 2 | Distribution | 2012-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013577 | 404516349 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013578 | 404516356 | Molding | HFTD Tier 3 | Distribution | 2012-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013579 | 404516360 | High Sign | HFTD Tier 3 | Distribution | 2012-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013580 | 404516377 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013581 | 404516410 | Molding | HFTD Tier 3 | Distribution | 2012-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013582 | 404518020 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013583 | 404518083 | Guy | HFTD Tier 2 | Distribution | 2012-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013584 | 404518131 | High Sign | HFTD Tier 2 | Distribution | 2012-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013585 | 404518168 | Guy | HFTD Tier 2 | Distribution | 2012-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013586 | 404518290 | Guy | HFTD Tier 2 | Distribution | 2012-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013587 | 404518317 | Molding | HFTD Tier 2 | Distribution | 2012-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013588 | 404518462 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013589 | 404518888 | High Sign | HFTD Tier 3 | Distribution | 2012-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013590 | 404518901 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013591 | 404519668 | High Sign | HFTD Tier 3 | Distribution | 2012-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013592 | 404519685 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013593 | 404519691 | Termination | HFTD Tier 3 | Distribution | 2012-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013594 | 404521478 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013595 | 404521588 | Molding | HFTD Tier 3 | Distribution | 2012-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013596 | 404521660 | Riser/Conduit | HFTD Tier 2 | Distribution | 2012-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013597 | 404522132 | High Sign | HFTD Tier 3 | Distribution | 2012-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013598 | 404522149 | Molding | HFTD Tier 3 | Distribution | 2012-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013599 | 404522151 | Molding | HFTD Tier 3 | Distribution | 2012-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013600 | 404522180 | High Sign | HFTD Tier 3 | Distribution | 2012-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013601 | 404522538 | High Sign | HFTD Tier 3 | Distribution | 2012-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013602 | 404522557 | High Sign | HFTD Tier 3 | Distribution | 2012-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013603 | 404522559 | High Sign | HFTD Tier 3 | Distribution | 2012-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013604 | 404522571 | High Sign | HFTD Tier 3 | Distribution | 2012-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013605 | 404522572 | High Sign | HFTD Tier 3 | Distribution | 2012-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013606 | 404522573 | High Sign | HFTD Tier 3 | Distribution | 2012-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013607 | 404522574 | High Sign | HFTD Tier 3 | Distribution | 2012-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013608 | 404522581 | High Sign | HFTD Tier 3 | Distribution | 2012-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013609 | 404523411 | High Sign | HFTD Tier 2 | Distribution | 2012-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013610 | 404523415 | Riser/Conduit | HFTD Tier 2 | Distribution | 2012-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013611 | 404523440 | High Sign | HFTD Tier 2 | Distribution | 2012-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013612 | 404523443 | Streetlight | HFTD Tier 2 | Distribution | 2012-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013613 | 404524371 | Molding | HFTD Tier 3 | Distribution | 2012-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013614 | 404524382 | High Sign | HFTD Tier 3 | Distribution | 2012-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013615 | 404524395 | Molding | HFTD Tier 3 | Distribution | 2012-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013616 | 404524429 | Riser/Conduit | HFTD Tier 3 | Distribution | 2012-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013617 | 404524487 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013618 | 404524690 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013619 | 404526384 | High Sign | HFTD Tier 3 | Distribution | 2012-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013620 | 404527166 | High Sign | HFTD Tier 2 | Distribution | 2012-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013621 | 404527182 | High Sign | HFTD Tier 2 | Distribution | 2012-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013622 | 404528038 | High Sign | HFTD Tier 3 | Distribution | 2012-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013623 | 404528088 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013624 | 404528104 | High Sign | HFTD Tier 3 | Distribution | 2012-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013625 | 404528120 | Riser/Conduit | HFTD Tier 3 | Distribution | 2012-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013626 | 404529358 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013627 | 404529370 | Vis Strips | HFTD Tier 3 | Distribution | 2012-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013628 | 404529569 | Molding | HFTD Tier 2 | Distribution | 2012-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013629 | 404529804 | Guy | HFTD Tier 3 | Distribution | 2012-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013630 | 404529823 | High Sign | HFTD Tier 3 | Distribution | 2012-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013631 | 404529828 | Molding | HFTD Tier 3 | Distribution | 2012-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013632 | 404529835 | High Sign | HFTD Tier 3 | Distribution | 2012-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013633 | 404529841 | High Sign | HFTD Tier 3 | Distribution | 2012-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013634 | 404529842 | High Sign | HFTD Tier 3 | Distribution | 2012-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013635 | 404529844 | Molding | HFTD Tier 3 | Distribution | 2012-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013636 | 404529861 | Molding | HFTD Tier 3 | Distribution | 2012-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013637 | 404532657 | High Sign | HFTD Tier 2 | Distribution | 2012-06-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013638 | 404532679 | Guy | HFTD Tier 2 | Distribution | 2012-06-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013639 | 404532682 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-06-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013640 | 404532685 | High Sign | HFTD Tier 2 | Distribution | 2012-06-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013641 | 404532690 | High Sign | HFTD Tier 2 | Distribution | 2012-06-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013642 | 404533710 | High Sign | HFTD Tier 3 | Distribution | 2012-06-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013643 | 404535214 | Molding | HFTD Tier 2 | Distribution | 2012-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013644 | 404535234 | High Sign | HFTD Tier 2 | Distribution | 2012-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013645 | 404535287 | High Sign | HFTD Tier 2 | Distribution | 2012-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013646 | 404535292 | High Sign | HFTD Tier 2 | Distribution | 2012-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013647 | 404535311 | High Sign | HFTD Tier 2 | Distribution | 2012-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013648 | 404535378 | High Sign | HFTD Tier 2 | Distribution | 2012-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013649 | 404537671 | High Sign | HFTD Tier 2 | Distribution | 2012-06-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013650 | 404539146 | High Sign | HFTD Tier 3 | Distribution | 2012-06-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013651 | 404540415 | Guy | HFTD Tier 2 | Distribution | 2012-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013652 | 404540510 | Molding | HFTD Tier 3 | Distribution | 2012-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013653 | 404540511 | High Sign | HFTD Tier 3 | Distribution | 2012-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013654 | 404540552 | Molding | HFTD Tier 2 | Distribution | 2012-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013655 | 404540708 | Guy | HFTD Tier 2 | Distribution | 2012-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013656 | 404540717 | High Sign | HFTD Tier 2 | Distribution | 2012-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013657 | 404540719 | High Sign | HFTD Tier 2 | Distribution | 2012-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013658 | 404540721 | High Sign | HFTD Tier 2 | Distribution | 2012-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013659 | 404540730 | High Sign | HFTD Tier 2 | Distribution | 2012-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013660 | 404540765 | High Sign | HFTD Tier 2 | Distribution | 2012-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013661 | 404540773 | High Sign | HFTD Tier 2 | Distribution | 2012-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013662 | 404542628 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013663 | 404542947 | High Sign | HFTD Tier 2 | Distribution | 2012-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013664 | 404543138 | Molding | HFTD Tier 3 | Distribution | 2012-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013665 | 404543139 | High Sign | HFTD Tier 3 | Distribution | 2012-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013666 | 404543412 | High Sign | HFTD Tier 3 | Distribution | 2012-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013667 | 404543413 | High Sign | HFTD Tier 3 | Distribution | 2012-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013668 | 404543414 | High Sign | HFTD Tier 3 | Distribution | 2012-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013669 | 404543415 | High Sign | HFTD Tier 3 | Distribution | 2012-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013670 | 404543937 | Molding | HFTD Tier 3 | Distribution | 2012-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013671 | 404543968 | High Sign | HFTD Tier 3 | Distribution | 2012-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013672 | 404543973 | Molding | HFTD Tier 3 | Distribution | 2012-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013673 | 404543974 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013674 | 404543981 | Molding | HFTD Tier 3 | Distribution | 2012-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013675 | 404543983 | High Sign | HFTD Tier 3 | Distribution | 2012-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013676 | 404543996 | High Sign | HFTD Tier 3 | Distribution | 2012-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013677 | 404543998 | High Sign | HFTD Tier 3 | Distribution | 2012-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013678 | 404544509 | Guy | HFTD Tier 3 | Distribution | 2012-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013679 | 404545655 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013680 | 404545665 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013681 | 404545683 | Guy | HFTD Tier 3 | Distribution | 2012-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013682 | 404547216 | Molding | HFTD Tier 3 | Distribution | 2012-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013683 | 404547221 | High Sign | HFTD Tier 3 | Distribution | 2012-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013684 | 404547230 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013685 | 404547556 | High Sign | HFTD Tier 3 | Distribution | 2012-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013686 | 404547880 | Molding | HFTD Tier 2 | Distribution | 2012-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013687 | 404547881 | High Sign | HFTD Tier 2 | Distribution | 2012-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013688 | 404548317 | Molding | HFTD Tier 3 | Distribution | 2012-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013689 | 404548318 | Molding | HFTD Tier 3 | Distribution | 2012-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013690 | 404548325 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013691 | 404548332 | Molding | HFTD Tier 3 | Distribution | 2012-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013692 | 404549884 | Guy | HFTD Tier 3 | Distribution | 2012-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013693 | 404550106 | Molding | HFTD Tier 3 | Distribution | 2012-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013694 | 404550157 | Vis Strips | HFTD Tier 3 | Distribution | 2012-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013695 | 404550163 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013696 | 404550262 | High Sign | HFTD Tier 3 | Distribution | 2012-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013697 | 404550274 | High Sign | HFTD Tier 3 | Distribution | 2012-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013698 | 404550280 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013699 | 404550289 | Molding | HFTD Tier 3 | Distribution | 2012-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013700 | 404550353 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013701 | 404550355 | High Sign | HFTD Tier 3 | Distribution | 2012-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013702 | 404550361 | High Sign | HFTD Tier 3 | Distribution | 2012-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013703 | 404550370 | High Sign | HFTD Tier 3 | Distribution | 2012-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013704 | 404551014 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013705 | 404551026 | Molding | HFTD Tier 3 | Distribution | 2012-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013706 | 404551081 | Guy | HFTD Tier 3 | Distribution | 2012-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013707 | 404552476 | Molding | HFTD Tier 3 | Distribution | 2012-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013708 | 404552483 | Guy | HFTD Tier 3 | Distribution | 2012-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013709 | 404552501 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013710 | 404555430 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013711 | 404555681 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013712 | 404556063 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013713 | 404556143 | Guy | HFTD Tier 2 | Distribution | 2012-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013714 | 404557837 | Pole Tag | HFTD Tier 3 | Distribution | 2012-06-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013715 | 404557866 | Molding | HFTD Tier 3 | Distribution | 2012-06-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013716 | 404558572 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-06-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013717 | 404558602 | Molding | HFTD Tier 3 | Distribution | 2012-06-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013718 | 404558766 | Guy | HFTD Tier 3 | Distribution | 2012-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013719 | 404558793 | Molding | HFTD Tier 3 | Distribution | 2012-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013720 | 404558812 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013721 | 404558862 | Molding | HFTD Tier 3 | Distribution | 2012-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013722 | 404558872 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013723 | 404558880 | Molding | HFTD Tier 3 | Distribution | 2012-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013724 | 404558887 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013725 | 404558956 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013726 | 404558962 | Molding | HFTD Tier 3 | Distribution | 2012-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013727 | 404558980 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013728 | 404558989 | Vis Strips | HFTD Tier 3 | Distribution | 2012-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013729 | 404559012 | Vis Strips | HFTD Tier 3 | Distribution | 2012-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013730 | 404561772 | High Sign | HFTD Tier 3 | Distribution | 2012-07-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013731 | 404561773 | High Sign | HFTD Tier 3 | Distribution | 2012-07-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013732 | 404561783 | High Sign | HFTD Tier 3 | Distribution | 2012-07-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013733 | 404561791 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-07-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013734 | 404561800 | Guy | HFTD Tier 3 | Distribution | 2012-07-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013735 | 404561808 | High Sign | HFTD Tier 3 | Distribution | 2012-07-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013736 | 404562179 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-07-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013737 | 404565479 | Molding | HFTD Tier 2 | Distribution | 2012-07-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013738 | 404568736 | Molding | HFTD Tier 2 | Distribution | 2012-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013739 | 404568764 | Riser/Conduit | HFTD Tier 2 | Distribution | 2012-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013740 | 404568820 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013741 | 404568854 | High Sign | HFTD Tier 2 | Distribution | 2012-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013742 | 404572970 | High Sign | HFTD Tier 3 | Distribution | 2012-07-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013743 | 404573443 | Molding | HFTD Tier 3 | Distribution | 2012-07-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013744 | 404573580 | Molding | HFTD Tier 3 | Distribution | 2012-07-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013745 | 404573582 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-07-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013746 | 404573587 | Molding | HFTD Tier 3 | Distribution | 2012-07-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013747 | 404573610 | High Sign | HFTD Tier 3 | Distribution | 2012-07-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013748 | 404573623 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-07-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013749 | 404575275 | Molding | HFTD Tier 3 | Distribution | 2012-07-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013750 | 404577950 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013751 | 404578168 | High Sign | HFTD Tier 2 | Distribution | 2012-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013752 | 404578764 | High Sign | HFTD Tier 2 | Distribution | 2012-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013753 | 404580358 | High Sign | HFTD Tier 3 | Distribution | 2012-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013754 | 404581567 | High Sign | HFTD Tier 3 | Distribution | 2012-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013755 | 404583825 | High Sign | HFTD Tier 3 | Distribution | 2012-07-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013756 | 404583828 | High Sign | HFTD Tier 2 | Distribution | 2012-07-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013757 | 404583833 | High Sign | HFTD Tier 3 | Distribution | 2012-07-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013758 | 404585276 | Vis Strips | HFTD Tier 2 | Distribution | 2012-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013759 | 404585287 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013760 | 404586796 | High Sign | HFTD Tier 2 | Distribution | 2012-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013761 | 404587760 | High Sign | HFTD Tier 2 | Distribution | 2012-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013762 | 404589989 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013763 | 404590049 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013764 | 404592387 | High Sign | HFTD Tier 2 | Distribution | 2012-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013765 | 404592388 | High Sign | HFTD Tier 2 | Distribution | 2012-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013766 | 404592397 | High Sign | HFTD Tier 2 | Distribution | 2012-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013767 | 404592403 | Molding | HFTD Tier 2 | Distribution | 2012-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013768 | 404592404 | Molding | HFTD Tier 2 | Distribution | 2012-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013769 | 404594898 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013770 | 404594901 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013771 | 404594927 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013772 | 404594928 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013773 | 404594929 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013774 | 404594936 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013775 | 404594937 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013776 | 404594943 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013777 | 404594945 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013778 | 404594946 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013779 | 404594948 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013780 | 404594949 | Molding | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013781 | 404594950 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013782 | 404594951 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013783 | 404594960 | Guy | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013784 | 404594961 | Molding | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013785 | 404594964 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013786 | 404594968 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013787 | 404594990 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013788 | 404595348 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013789 | 404595349 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013790 | 404597202 | High Sign | HFTD Tier 2 | Distribution | 2012-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013791 | 404597205 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013792 | 404597206 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013793 | 404597209 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013794 | 404597214 | High Sign | HFTD Tier 2 | Distribution | 2012-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013795 | 404597215 | High Sign | HFTD Tier 2 | Distribution | 2012-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013796 | 404597217 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013797 | 404597220 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013798 | 404597221 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013799 | 404597222 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013800 | 404597223 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013801 | 404597224 | Guy | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013802 | 404597227 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013803 | 404597228 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013804 | 404597229 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013805 | 404597232 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013806 | 404597233 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013807 | 404597234 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013808 | 404597235 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013809 | 404597236 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013810 | 404597237 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013811 | 404597238 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013812 | 404597240 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013813 | 404597241 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013814 | 404597243 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013815 | 404597246 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013816 | 404597249 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013817 | 404597253 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013818 | 404597255 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013819 | 404597257 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013820 | 404597260 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013821 | 404597261 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013822 | 404597262 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013823 | 404597271 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013824 | 404597294 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013825 | 404597295 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013826 | 404597296 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013827 | 404597299 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013828 | 404597300 | Guy | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013829 | 404597301 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013830 | 404597305 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013831 | 404597306 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013832 | 404597310 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013833 | 404597312 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013834 | 404597313 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013835 | 404597314 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013836 | 404597315 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013837 | 404597316 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013838 | 404597317 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013839 | 404597318 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013840 | 404597319 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013841 | 404597320 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013842 | 404597321 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013843 | 404597322 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013844 | 404597323 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013845 | 404597324 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013846 | 404597325 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013847 | 404597326 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013848 | 404597328 | Molding | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013849 | 404597329 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013850 | 404597330 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013851 | 404597331 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013852 | 404597332 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013853 | 404597334 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013854 | 404597337 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013855 | 404597343 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013856 | 404597347 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013857 | 404597352 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013858 | 404597354 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013859 | 404597357 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013860 | 404597360 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013861 | 404597943 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013862 | 404597963 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013863 | 404597980 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013864 | 404598003 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013865 | 404598063 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013866 | 404598483 | Molding | HFTD Tier 2 | Distribution | 2012-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013867 | 404598493 | Guy | HFTD Tier 2 | Distribution | 2012-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013868 | 404598523 | Guy | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013869 | 404598527 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013870 | 404598558 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013871 | 404598569 | High Sign | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013872 | 404598573 | High Sign | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013873 | 404598593 | High Sign | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013874 | 404599767 | High Sign | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013875 | 404599854 | High Sign | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013876 | 404600773 | Guy | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013877 | 404600809 | Molding | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013878 | 404600817 | High Sign | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013879 | 404600820 | High Sign | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013880 | 404600821 | Guy | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013881 | 404602134 | High Sign | HFTD Tier 2 | Distribution | 2012-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013882 | 404602155 | High Sign | HFTD Tier 2 | Distribution | 2012-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013883 | 404602156 | High Sign | HFTD Tier 2 | Distribution | 2012-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013884 | 404602157 | High Sign | HFTD Tier 2 | Distribution | 2012-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013885 | 404602158 | High Sign | HFTD Tier 2 | Distribution | 2012-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013886 | 404602162 | Guy | HFTD Tier 2 | Distribution | 2012-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013887 | 404602163 | High Sign | HFTD Tier 2 | Distribution | 2012-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013888 | 404602165 | High Sign | HFTD Tier 2 | Distribution | 2012-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013889 | 404602166 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013890 | 404602167 | High Sign | HFTD Tier 2 | Distribution | 2012-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013891 | 404602168 | High Sign | HFTD Tier 2 | Distribution | 2012-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013892 | 404602171 | High Sign | HFTD Tier 2 | Distribution | 2012-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013893 | 404602180 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013894 | 404602198 | High Sign | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013895 | 404602209 | Molding | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013896 | 404602210 | High Sign | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013897 | 404602212 | High Sign | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013898 | 404602213 | High Sign | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013899 | 404602214 | High Sign | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013900 | 404602220 | High Sign | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013901 | 404602223 | High Sign | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013902 | 404602224 | High Sign | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013903 | 404602226 | High Sign | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013904 | 404602241 | Guy | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013905 | 404602251 | High Sign | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013906 | 404602255 | Guy | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013907 | 404602256 | High Sign | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013908 | 404602441 | Riser/Conduit | HFTD Tier 2 | Distribution | 2012-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013909 | 404602463 | High Sign | HFTD Tier 2 | Distribution | 2012-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013910 | 404603668 | High Sign | HFTD Tier 3 | Distribution | 2012-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013911 | 404603677 | High Sign | HFTD Tier 3 | Distribution | 2012-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013912 | 404603741 | Molding | HFTD Tier 3 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013913 | 404606049 | Guy | HFTD Tier 2 | Distribution | 2012-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013914 | 404606063 | High Sign | HFTD Tier 2 | Distribution | 2012-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013915 | 404606469 | Insulator | HFTD Tier 3 | Distribution | 2012-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013916 | 404606497 | High Sign | HFTD Tier 3 | Distribution | 2012-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013917 | 404606517 | High Sign | HFTD Tier 3 | Distribution | 2012-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013918 | 404606631 | High Sign | HFTD Tier 2 | Distribution | 2012-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013919 | 404606674 | High Sign | HFTD Tier 2 | Distribution | 2012-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013920 | 404606675 | Molding | HFTD Tier 2 | Distribution | 2012-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013921 | 404608548 | Guy | HFTD Tier 2 | Distribution | 2012-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013922 | 404608999 | High Sign | HFTD Tier 2 | Distribution | 2012-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013923 | 404610429 | Guy | HFTD Tier 2 | Distribution | 2012-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013924 | 404610964 | High Sign | HFTD Tier 2 | Distribution | 2012-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013925 | 404611010 | Molding | HFTD Tier 2 | Distribution | 2012-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013926 | 404611765 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013927 | 404611819 | High Sign | HFTD Tier 3 | Distribution | 2012-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013928 | 404618937 | High Sign | HFTD Tier 2 | Distribution | 2012-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013929 | 404618955 | High Sign | HFTD Tier 2 | Distribution | 2012-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013930 | 404618991 | High Sign | HFTD Tier 2 | Distribution | 2012-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013931 | 404618993 | High Sign | HFTD Tier 2 | Distribution | 2012-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013932 | 404618994 | High Sign | HFTD Tier 2 | Distribution | 2012-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013933 | 404619001 | High Sign | HFTD Tier 2 | Distribution | 2012-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013934 | 404619003 | High Sign | HFTD Tier 2 | Distribution | 2012-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013935 | 404619004 | High Sign | HFTD Tier 2 | Distribution | 2012-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013936 | 404619007 | High Sign | HFTD Tier 2 | Distribution | 2012-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013937 | 404619008 | High Sign | HFTD Tier 2 | Distribution | 2012-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013938 | 404619012 | High Sign | HFTD Tier 2 | Distribution | 2012-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013939 | 404619214 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-07-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013940 | 404620621 | Guy | HFTD Tier 3 | Distribution | 2012-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013941 | 404621838 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013942 | 404621852 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013943 | 404624024 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013944 | 404624029 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013945 | 404624072 | High Sign | HFTD Tier 3 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013946 | 404624501 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013947 | 404624502 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013948 | 404624503 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013949 | 404624504 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013950 | 404624505 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013951 | 404624506 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013952 | 404624507 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013953 | 404624508 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013954 | 404624509 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013955 | 404624511 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013956 | 404624512 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013957 | 404624514 | Molding | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013958 | 404624515 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013959 | 404624517 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013960 | 404624518 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013961 | 404624521 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013962 | 404624522 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013963 | 404624523 | Molding | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013964 | 404624524 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013965 | 404624525 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013966 | 404624526 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013967 | 404624534 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013968 | 404624540 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013969 | 404624542 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013970 | 404624544 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013971 | 404624546 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013972 | 404624550 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013973 | 404624551 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013974 | 404624552 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013975 | 404624553 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013976 | 404624554 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013977 | 404624555 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013978 | 404624556 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013979 | 404624557 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013980 | 404624585 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013981 | 404624586 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013982 | 404624587 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013983 | 404624588 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013984 | 404624595 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013985 | 404626524 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-08-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013986 | 404629018 | High Sign | HFTD Tier 2 | Distribution | 2012-08-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013987 | 404629999 | High Sign | HFTD Tier 2 | Distribution | 2012-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013988 | 404630004 | High Sign | HFTD Tier 2 | Distribution | 2012-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013989 | 404631398 | Guy | HFTD Tier 2 | Distribution | 2012-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013990 | 404631399 | Guy | HFTD Tier 2 | Distribution | 2012-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013991 | 404631409 | High Sign | HFTD Tier 2 | Distribution | 2012-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013992 | 404631450 | Guy | HFTD Tier 2 | Distribution | 2012-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013993 | 404631451 | High Sign | HFTD Tier 2 | Distribution | 2012-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013994 | 404631455 | High Sign | HFTD Tier 2 | Distribution | 2012-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013995 | 404631457 | High Sign | HFTD Tier 2 | Distribution | 2012-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013996 | 404631458 | High Sign | HFTD Tier 2 | Distribution | 2012-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013997 | 404631461 | Guy | HFTD Tier 2 | Distribution | 2012-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013998 | 404631957 | High Sign | HFTD Tier 2 | Distribution | 2012-08-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130013999 | 404632050 | High Sign | HFTD Tier 2 | Distribution | 2012-08-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014000 | 404632142 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-08-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014001 | 404632143 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-08-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014002 | 404632431 | Molding | HFTD Tier 2 | Distribution | 2012-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014003 | 404632432 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014004 | 404632433 | High Sign | HFTD Tier 2 | Distribution | 2012-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014005 | 404632450 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014006 | 404632508 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014007 | 404632593 | High Sign | HFTD Tier 2 | Distribution | 2012-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014008 | 404632594 | Molding | HFTD Tier 2 | Distribution | 2012-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014009 | 404632608 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014010 | 404632619 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014011 | 404632638 | High Sign | HFTD Tier 2 | Distribution | 2012-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014012 | 404632651 | Cutout/Fuse | HFTD Tier 2 | Distribution | 2012-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014013 | 404633211 | Guy | HFTD Tier 3 | Distribution | 2012-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014014 | 404633222 | High Sign | HFTD Tier 3 | Distribution | 2012-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014015 | 404633229 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014016 | 404633242 | Riser/Conduit | HFTD Tier 3 | Distribution | 2012-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014017 | 404633635 | Molding | HFTD Tier 2 | Distribution | 2012-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014018 | 404635747 | Molding | HFTD Tier 3 | Distribution | 2012-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014019 | 404635748 | Guy | HFTD Tier 3 | Distribution | 2012-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014020 | 404635757 | Guy | HFTD Tier 3 | Distribution | 2012-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014021 | 404637350 | Molding | HFTD Tier 3 | Distribution | 2012-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014022 | 404637366 | High Sign | HFTD Tier 3 | Distribution | 2012-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014023 | 404637395 | High Sign | HFTD Tier 3 | Distribution | 2012-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014024 | 404637665 | High Sign | HFTD Tier 2 | Distribution | 2012-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014025 | 404637671 | Guy | HFTD Tier 2 | Distribution | 2012-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014026 | 404637673 | High Sign | HFTD Tier 2 | Distribution | 2012-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014027 | 404637776 | High Sign | HFTD Tier 2 | Distribution | 2012-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014028 | 404639002 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014029 | 404641417 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014030 | 404641803 | High Sign | HFTD Tier 3 | Distribution | 2012-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014031 | 404641940 | Molding | HFTD Tier 3 | Distribution | 2012-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014032 | 404642747 | High Sign | HFTD Tier 3 | Distribution | 2012-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014033 | 404642790 | Guy | HFTD Tier 3 | Distribution | 2012-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014034 | 404643454 | Guy | HFTD Tier 3 | Distribution | 2012-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014035 | 404643489 | Molding | HFTD Tier 3 | Distribution | 2012-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014036 | 404645510 | Molding | HFTD Tier 3 | Distribution | 2012-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014037 | 404650917 | Molding | HFTD Tier 3 | Distribution | 2012-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014038 | 404653402 | High Sign | HFTD Tier 3 | Distribution | 2012-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014039 | 404653436 | Molding | HFTD Tier 3 | Distribution | 2012-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014040 | 404653444 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014041 | 404653453 | Molding | HFTD Tier 3 | Distribution | 2012-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014042 | 404653501 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014043 | 404655710 | Insulator | HFTD Tier 3 | Distribution | 2012-08-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014044 | 404655711 | Insulator | HFTD Tier 3 | Distribution | 2012-08-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014045 | 404656118 | Molding | HFTD Tier 2 | Distribution | 2012-08-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014046 | 404659327 | High Sign | HFTD Tier 3 | Distribution | 2012-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014047 | 404659328 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014048 | 404659375 | High Sign | HFTD Tier 3 | Distribution | 2012-08-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014049 | 404659377 | High Sign | HFTD Tier 3 | Distribution | 2012-08-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014050 | 404659382 | High Sign | HFTD Tier 3 | Distribution | 2012-08-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014051 | 404659385 | Molding | HFTD Tier 3 | Distribution | 2012-08-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014052 | 404659392 | High Sign | HFTD Tier 3 | Distribution | 2012-08-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014053 | 404659396 | High Sign | HFTD Tier 3 | Distribution | 2012-08-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014054 | 404659397 | High Sign | HFTD Tier 3 | Distribution | 2012-08-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014055 | 404659404 | High Sign | HFTD Tier 3 | Distribution | 2012-08-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014056 | 404659414 | High Sign | HFTD Tier 3 | Distribution | 2012-08-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014057 | 404661410 | High Sign | HFTD Tier 3 | Distribution | 2012-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014058 | 404663768 | High Sign | HFTD Tier 3 | Distribution | 2012-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014059 | 404663792 | High Sign | HFTD Tier 3 | Distribution | 2012-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014060 | 404663802 | Molding | HFTD Tier 3 | Distribution | 2012-08-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014061 | 404663814 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-08-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014062 | 404663816 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-08-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014063 | 404665087 | Guy | HFTD Tier 3 | Distribution | 2012-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014064 | 404665608 | Molding | HFTD Tier 3 | Distribution | 2012-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014065 | 404665636 | Molding | HFTD Tier 3 | Distribution | 2012-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014066 | 404668460 | Molding | HFTD Tier 2 | Distribution | 2012-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014067 | 404668485 | Guy | HFTD Tier 3 | Distribution | 2012-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014068 | 404669191 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014069 | 404669200 | Guy | HFTD Tier 3 | Distribution | 2012-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014070 | 404669206 | Molding | HFTD Tier 3 | Distribution | 2012-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014071 | 404669218 | Molding | HFTD Tier 3 | Distribution | 2012-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014072 | 404669242 | High Sign | HFTD Tier 3 | Distribution | 2012-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014073 | 404669246 | Molding | HFTD Tier 3 | Distribution | 2012-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014074 | 404669248 | High Sign | HFTD Tier 3 | Distribution | 2012-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014075 | 404669260 | Molding | HFTD Tier 3 | Distribution | 2012-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014076 | 404669272 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014077 | 404669284 | Molding | HFTD Tier 3 | Distribution | 2012-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014078 | 404669285 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014079 | 404669286 | High Sign | HFTD Tier 3 | Distribution | 2012-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014080 | 404672178 | High Sign | HFTD Tier 3 | Distribution | 2012-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014081 | 404672254 | Molding | HFTD Tier 3 | Distribution | 2012-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014082 | 404672269 | Molding | HFTD Tier 3 | Distribution | 2012-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014083 | 404672287 | Molding | HFTD Tier 3 | Distribution | 2012-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014084 | 404672540 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014085 | 404672541 | Molding | HFTD Tier 2 | Distribution | 2012-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014086 | 404672543 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014087 | 404673994 | High Sign | HFTD Tier 3 | Distribution | 2012-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014088 | 404674027 | Molding | HFTD Tier 3 | Distribution | 2012-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014089 | 404674078 | Molding | HFTD Tier 3 | Distribution | 2012-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014090 | 404674096 | High Sign | HFTD Tier 3 | Distribution | 2012-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014091 | 404674139 | Molding | HFTD Tier 3 | Distribution | 2012-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014092 | 404674152 | Molding | HFTD Tier 3 | Distribution | 2012-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014093 | 404674160 | High Sign | HFTD Tier 3 | Distribution | 2012-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014094 | 404674681 | Molding | HFTD Tier 3 | Distribution | 2012-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014095 | 404674684 | Molding | HFTD Tier 3 | Distribution | 2012-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014096 | 404674695 | High Sign | HFTD Tier 3 | Distribution | 2012-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014097 | 404675768 | Molding | HFTD Tier 3 | Distribution | 2012-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014098 | 404676547 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014099 | 404676907 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014100 | 404677262 | Molding | HFTD Tier 3 | Distribution | 2012-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014101 | 404677274 | Molding | HFTD Tier 3 | Distribution | 2012-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014102 | 404677287 | High Sign | HFTD Tier 2 | Distribution | 2012-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014103 | 404677330 | High Sign | HFTD Tier 2 | Distribution | 2012-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014104 | 404677334 | High Sign | HFTD Tier 2 | Distribution | 2012-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014105 | 404677515 | Molding | HFTD Tier 3 | Distribution | 2012-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014106 | 404677530 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014107 | 404677584 | Molding | HFTD Tier 3 | Distribution | 2012-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014108 | 404677768 | Molding | HFTD Tier 2 | Distribution | 2012-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014109 | 404677769 | High Sign | HFTD Tier 2 | Distribution | 2012-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014110 | 404677907 | Guy | HFTD Tier 2 | Distribution | 2012-08-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014111 | 404678161 | High Sign | HFTD Tier 2 | Distribution | 2012-08-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014112 | 404678798 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-08-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014113 | 404678800 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-08-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014114 | 404680579 | High Sign | HFTD Tier 3 | Distribution | 2012-08-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014115 | 404681523 | High Sign | HFTD Tier 3 | Distribution | 2012-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014116 | 404681565 | Molding | HFTD Tier 3 | Distribution | 2012-08-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014117 | 404681566 | High Sign | HFTD Tier 3 | Distribution | 2012-08-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014118 | 404681956 | Molding | HFTD Tier 2 | Distribution | 2012-08-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014119 | 404682772 | High Sign | HFTD Tier 3 | Distribution | 2012-08-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014120 | 404683825 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-08-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014121 | 404683826 | Molding | HFTD Tier 2 | Distribution | 2012-08-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014122 | 404683928 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-08-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014123 | 404683974 | Molding | HFTD Tier 3 | Distribution | 2012-08-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014124 | 404683979 | Guy | HFTD Tier 3 | Distribution | 2012-08-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014125 | 404684043 | Molding | HFTD Tier 3 | Distribution | 2012-08-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014126 | 404684045 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-08-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014127 | 404686871 | High Sign | HFTD Tier 2 | Distribution | 2012-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014128 | 404689968 | High Sign | HFTD Tier 3 | Distribution | 2012-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014129 | 404689974 | High Sign | HFTD Tier 3 | Distribution | 2012-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014130 | 404689984 | Molding | HFTD Tier 3 | Distribution | 2012-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014131 | 404689999 | Guy | HFTD Tier 3 | Distribution | 2012-08-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014132 | 404690007 | Guy | HFTD Tier 3 | Distribution | 2012-08-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014133 | 404690165 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014134 | 404690167 | High Sign | HFTD Tier 3 | Distribution | 2012-08-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014135 | 404691665 | High Sign | HFTD Tier 3 | Distribution | 2012-08-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014136 | 404691675 | High Sign | HFTD Tier 3 | Distribution | 2012-08-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014137 | 404691811 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-09-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014138 | 404691884 | High Sign | HFTD Tier 3 | Distribution | 2012-09-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014139 | 404691930 | High Sign | HFTD Tier 2 | Distribution | 2012-09-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014140 | 404697608 | High Sign | HFTD Tier 3 | Distribution | 2012-09-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014141 | 404697609 | High Sign | HFTD Tier 3 | Distribution | 2012-09-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014142 | 404697659 | High Sign | HFTD Tier 3 | Distribution | 2012-09-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014143 | 404697667 | High Sign | HFTD Tier 3 | Distribution | 2012-09-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014144 | 404697671 | High Sign | HFTD Tier 3 | Distribution | 2012-09-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014145 | 404697680 | Molding | HFTD Tier 3 | Distribution | 2012-09-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014146 | 404697691 | Molding | HFTD Tier 3 | Distribution | 2012-09-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014147 | 404697713 | High Sign | HFTD Tier 3 | Distribution | 2012-09-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014148 | 404697721 | High Sign | HFTD Tier 3 | Distribution | 2012-09-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014149 | 404698045 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-09-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014150 | 404700421 | High Sign | HFTD Tier 3 | Distribution | 2012-09-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014151 | 404700426 | High Sign | HFTD Tier 3 | Distribution | 2012-09-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014152 | 404700427 | High Sign | HFTD Tier 3 | Distribution | 2012-09-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014153 | 404700434 | High Sign | HFTD Tier 3 | Distribution | 2012-09-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014154 | 404709384 | High Sign | HFTD Tier 3 | Distribution | 2012-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014155 | 404709393 | High Sign | HFTD Tier 3 | Distribution | 2012-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014156 | 404709397 | Molding | HFTD Tier 3 | Distribution | 2012-09-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014157 | 404709414 | High Sign | HFTD Tier 3 | Distribution | 2012-09-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014158 | 404709420 | High Sign | HFTD Tier 3 | Distribution | 2012-09-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014159 | 404712090 | High Sign | HFTD Tier 3 | Distribution | 2012-09-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014160 | 404719189 | High Sign | HFTD Tier 2 | Distribution | 2012-09-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014161 | 404719207 | Molding | HFTD Tier 2 | Distribution | 2012-09-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014162 | 404719209 | Molding | HFTD Tier 2 | Distribution | 2012-09-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014163 | 404721519 | High Sign | HFTD Tier 3 | Distribution | 2012-09-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014164 | 404730100 | Bond | HFTD Tier 3 | Distribution | 2012-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014165 | 404730353 | Molding | HFTD Tier 3 | Distribution | 2012-09-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014166 | 404734942 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014167 | 404738311 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014168 | 404738485 | High Sign | HFTD Tier 3 | Distribution | 2012-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014169 | 404738513 | Guy | HFTD Tier 3 | Distribution | 2012-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014170 | 404742641 | Molding | HFTD Tier 2 | Distribution | 2012-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014171 | 404742642 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014172 | 404742645 | Pole Tag | HFTD Tier 2 | Distribution | 2012-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014173 | 404742647 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014174 | 404743085 | High Sign | HFTD Tier 3 | Distribution | 2012-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014175 | 404743090 | High Sign | HFTD Tier 3 | Distribution | 2012-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014176 | 404743180 | Molding | HFTD Tier 3 | Distribution | 2012-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014177 | 404743182 | High Sign | HFTD Tier 3 | Distribution | 2012-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014178 | 404743193 | High Sign | HFTD Tier 3 | Distribution | 2012-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014179 | 404743194 | High Sign | HFTD Tier 3 | Distribution | 2012-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014180 | 404743205 | High Sign | HFTD Tier 3 | Distribution | 2012-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014181 | 404743808 | High Sign | HFTD Tier 2 | Distribution | 2012-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014182 | 404743820 | Molding | HFTD Tier 2 | Distribution | 2012-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014183 | 404747042 | High Sign | HFTD Tier 3 | Distribution | 2012-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014184 | 404749429 | Crossarm | HFTD Tier 3 | Distribution | 2012-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014185 | 404751343 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014186 | 404751344 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014187 | 404751626 | Molding | HFTD Tier 3 | Distribution | 2012-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014188 | 404752186 | High Sign | HFTD Tier 2 | Distribution | 2012-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014189 | 404752203 | High Sign | HFTD Tier 2 | Distribution | 2012-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014190 | 404752211 | High Sign | HFTD Tier 2 | Distribution | 2012-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014191 | 404752213 | High Sign | HFTD Tier 2 | Distribution | 2012-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014192 | 404752214 | High Sign | HFTD Tier 2 | Distribution | 2012-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014193 | 404752215 | High Sign | HFTD Tier 2 | Distribution | 2012-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014194 | 404752216 | High Sign | HFTD Tier 2 | Distribution | 2012-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014195 | 404752226 | High Sign | HFTD Tier 2 | Distribution | 2012-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014196 | 404752242 | High Sign | HFTD Tier 2 | Distribution | 2012-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014197 | 404752255 | High Sign | HFTD Tier 2 | Distribution | 2012-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014198 | 404752263 | High Sign | HFTD Tier 2 | Distribution | 2012-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014199 | 404754588 | Molding | HFTD Tier 2 | Distribution | 2012-10-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014200 | 404755562 | Guy | HFTD Tier 2 | Distribution | 2012-10-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014201 | 404755709 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-10-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014202 | 404757447 | High Sign | HFTD Tier 3 | Distribution | 2012-10-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014203 | 404761547 | High Sign | HFTD Tier 3 | Distribution | 2012-10-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014204 | 404763960 | Molding | HFTD Tier 3 | Distribution | 2012-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014205 | 404763967 | Molding | HFTD Tier 3 | Distribution | 2012-10-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014206 | 404765717 | High Sign | HFTD Tier 3 | Distribution | 2012-10-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014207 | 404765905 | High Sign | HFTD Tier 2 | Distribution | 2012-10-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014208 | 404772753 | High Sign | HFTD Tier 3 | Distribution | 2012-10-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014209 | 404774925 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-10-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014210 | 404779331 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014211 | 404779341 | Molding | HFTD Tier 3 | Distribution | 2012-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014212 | 404779373 | High Sign | HFTD Tier 3 | Distribution | 2012-10-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014213 | 404779375 | Molding | HFTD Tier 3 | Distribution | 2012-10-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014214 | 404779395 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-10-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014215 | 404783315 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-10-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014216 | 404789376 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014217 | 404789625 | High Sign | HFTD Tier 3 | Distribution | 2012-10-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014218 | 404789626 | High Sign | HFTD Tier 3 | Distribution | 2012-10-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014219 | 404791816 | High Sign | HFTD Tier 3 | Distribution | 2012-10-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014220 | 404791841 | High Sign | HFTD Tier 3 | Distribution | 2012-10-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014221 | 404791842 | High Sign | HFTD Tier 3 | Distribution | 2012-10-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014222 | 404792557 | Riser/Conduit | HFTD Tier 2 | Distribution | 2012-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014223 | 404792903 | High Sign | HFTD Tier 2 | Distribution | 2012-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014224 | 404793778 | High Sign | HFTD Tier 3 | Distribution | 2012-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014225 | 404793785 | High Sign | HFTD Tier 3 | Distribution | 2012-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014226 | 404797289 | Molding | HFTD Tier 2 | Distribution | 2012-10-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014227 | 404797294 | Ground | HFTD Tier 2 | Distribution | 2012-10-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014228 | 404798947 | Molding | HFTD Tier 3 | Distribution | 2012-10-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014229 | 404798949 | Molding | HFTD Tier 3 | Distribution | 2012-10-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014230 | 404808059 | Molding | HFTD Tier 3 | Distribution | 2012-11-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014231 | 404808069 | High Sign | HFTD Tier 3 | Distribution | 2012-11-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014232 | 404808079 | High Sign | HFTD Tier 3 | Distribution | 2012-11-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014233 | 404808095 | Molding | HFTD Tier 3 | Distribution | 2012-11-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014234 | 404808100 | High Sign | HFTD Tier 3 | Distribution | 2012-11-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014235 | 404808103 | High Sign | HFTD Tier 3 | Distribution | 2012-11-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014236 | 404808106 | High Sign | HFTD Tier 3 | Distribution | 2012-11-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014237 | 404823412 | Molding | HFTD Tier 3 | Distribution | 2012-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014238 | 404823441 | High Sign | HFTD Tier 3 | Distribution | 2012-11-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014239 | 404823462 | Molding | HFTD Tier 3 | Distribution | 2012-11-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014240 | 404823524 | High Sign | HFTD Tier 3 | Distribution | 2012-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014241 | 404823530 | High Sign | HFTD Tier 3 | Distribution | 2012-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014242 | 404823532 | High Sign | HFTD Tier 3 | Distribution | 2012-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014243 | 404823548 | Molding | HFTD Tier 3 | Distribution | 2012-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014244 | 404823552 | Molding | HFTD Tier 3 | Distribution | 2012-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014245 | 404823618 | High Sign | HFTD Tier 3 | Distribution | 2012-11-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014246 | 404823622 | High Sign | HFTD Tier 3 | Distribution | 2012-11-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014247 | 404823623 | High Sign | HFTD Tier 3 | Distribution | 2012-11-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014248 | 404824831 | Riser/Conduit | HFTD Tier 3 | Distribution | 2012-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014249 | 404824841 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014250 | 404824842 | Molding | HFTD Tier 3 | Distribution | 2012-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014251 | 404825844 | Molding | HFTD Tier 3 | Distribution | 2012-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014252 | 404825848 | Molding | HFTD Tier 3 | Distribution | 2012-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014253 | 404825851 | Molding | HFTD Tier 3 | Distribution | 2012-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014254 | 404825858 | Molding | HFTD Tier 3 | Distribution | 2012-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014255 | 404825865 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014256 | 404825881 | Molding | HFTD Tier 3 | Distribution | 2012-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014257 | 404825905 | Molding | HFTD Tier 3 | Distribution | 2012-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014258 | 404827888 | High Sign | HFTD Tier 3 | Distribution | 2012-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014259 | 404827895 | High Sign | HFTD Tier 3 | Distribution | 2012-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014260 | 404827904 | High Sign | HFTD Tier 3 | Distribution | 2012-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014261 | 404827906 | High Sign | HFTD Tier 3 | Distribution | 2012-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014262 | 404827907 | High Sign | HFTD Tier 3 | Distribution | 2012-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014263 | 404827908 | High Sign | HFTD Tier 3 | Distribution | 2012-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014264 | 404827909 | High Sign | HFTD Tier 3 | Distribution | 2012-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014265 | 404827911 | High Sign | HFTD Tier 3 | Distribution | 2012-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014266 | 404828107 | High Sign | HFTD Tier 3 | Distribution | 2012-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014267 | 404828133 | Molding | HFTD Tier 3 | Distribution | 2012-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014268 | 404829070 | High Sign | HFTD Tier 3 | Distribution | 2012-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014269 | 404829073 | Molding | HFTD Tier 3 | Distribution | 2012-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014270 | 404829075 | High Sign | HFTD Tier 3 | Distribution | 2012-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014271 | 404829087 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014272 | 404829327 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-11-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014273 | 404830153 | High Sign | HFTD Tier 3 | Distribution | 2012-11-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014274 | 404830161 | Molding | HFTD Tier 3 | Distribution | 2012-11-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014275 | 404838318 | Molding | HFTD Tier 3 | Distribution | 2012-11-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014276 | 404838357 | High Sign | HFTD Tier 3 | Distribution | 2012-11-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014277 | 404838364 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-11-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014278 | 404838377 | Riser/Conduit | HFTD Tier 3 | Distribution | 2012-11-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014279 | 404838819 | High Sign | HFTD Tier 2 | Distribution | 2012-11-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014280 | 404838828 | High Sign | HFTD Tier 2 | Distribution | 2012-11-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014281 | 404838836 | High Sign | HFTD Tier 2 | Distribution | 2012-11-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014282 | 404838838 | High Sign | HFTD Tier 2 | Distribution | 2012-11-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014283 | 404838856 | High Sign | HFTD Tier 2 | Distribution | 2012-11-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014284 | 404841953 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-11-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014285 | 404841954 | Molding | HFTD Tier 2 | Distribution | 2012-11-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014286 | 404841963 | Molding | HFTD Tier 2 | Distribution | 2012-11-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014287 | 404841970 | Molding | HFTD Tier 2 | Distribution | 2012-11-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014288 | 404841985 | Guy | HFTD Tier 2 | Distribution | 2012-11-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014289 | 404842003 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-11-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014290 | 404847485 | Molding | HFTD Tier 2 | Distribution | 2012-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014291 | 404849399 | Molding | HFTD Tier 3 | Distribution | 2012-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014292 | 404849403 | Molding | HFTD Tier 3 | Distribution | 2012-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014293 | 404849411 | Molding | HFTD Tier 3 | Distribution | 2012-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014294 | 404851017 | High Sign | HFTD Tier 3 | Distribution | 2012-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014295 | 404851030 | Molding | HFTD Tier 3 | Distribution | 2012-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014296 | 404859289 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014297 | 404859323 | Molding | HFTD Tier 3 | Distribution | 2012-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014298 | 404859352 | High Sign | HFTD Tier 3 | Distribution | 2012-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014299 | 404859358 | High Sign | HFTD Tier 3 | Distribution | 2012-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014300 | 404859360 | High Sign | HFTD Tier 3 | Distribution | 2012-12-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014301 | 404867428 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-12-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014302 | 404893699 | Molding | HFTD Tier 2 | Distribution | 2013-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014303 | 404893868 | High Sign | HFTD Tier 2 | Distribution | 2013-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014304 | 404894218 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014305 | 404897256 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014306 | 404897354 | High Sign | HFTD Tier 3 | Distribution | 2013-01-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014307 | 404898223 | Riser/Conduit | HFTD Tier 2 | Distribution | 2013-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014308 | 404899085 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014309 | 404899088 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014310 | 404899102 | Molding | HFTD Tier 2 | Distribution | 2013-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014311 | 404899488 | Molding | HFTD Tier 3 | Distribution | 2013-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014312 | 404899915 | Molding | HFTD Tier 2 | Distribution | 2013-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014313 | 404899957 | Molding | HFTD Tier 2 | Distribution | 2013-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014314 | 404899992 | High Sign | HFTD Tier 3 | Distribution | 2013-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014315 | 404899999 | High Sign | HFTD Tier 3 | Distribution | 2013-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014316 | 404900014 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014317 | 404900217 | High Sign | HFTD Tier 2 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014318 | 404900385 | Guy | HFTD Tier 2 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014319 | 404900386 | Guy | HFTD Tier 2 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014320 | 404900394 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014321 | 404900396 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014322 | 404900399 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014323 | 404900401 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014324 | 404900435 | Molding | HFTD Tier 2 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014325 | 404900446 | High Sign | HFTD Tier 2 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014326 | 404900452 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014327 | 404900460 | Termination | HFTD Tier 2 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014328 | 404900462 | High Sign | HFTD Tier 2 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014329 | 404901572 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014330 | 404901573 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014331 | 404902108 | Molding | HFTD Tier 3 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014332 | 404902116 | Molding | HFTD Tier 3 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014333 | 404902157 | Insulator | HFTD Tier 3 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014334 | 404902172 | Molding | HFTD Tier 3 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014335 | 404902214 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014336 | 404903172 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014337 | 404903249 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014338 | 404903319 | High Sign | HFTD Tier 2 | Distribution | 2013-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014339 | 404903321 | Molding | HFTD Tier 2 | Distribution | 2013-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014340 | 404903328 | High Sign | HFTD Tier 2 | Distribution | 2013-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014341 | 404903329 | High Sign | HFTD Tier 2 | Distribution | 2013-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014342 | 404903586 | Guy | HFTD Tier 3 | Distribution | 2013-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014343 | 404905144 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014344 | 404905154 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014345 | 404905205 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014346 | 404905251 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014347 | 404905254 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014348 | 404905259 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014349 | 404905277 | Molding | HFTD Tier 3 | Distribution | 2013-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014350 | 404905281 | Molding | HFTD Tier 3 | Distribution | 2013-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014351 | 404905283 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014352 | 404905306 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014353 | 404905923 | Termination | HFTD Tier 2 | Distribution | 2013-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014354 | 404906020 | Molding | HFTD Tier 2 | Distribution | 2013-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014355 | 404906021 | High Sign | HFTD Tier 2 | Distribution | 2013-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014356 | 404906034 | Molding | HFTD Tier 2 | Distribution | 2013-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014357 | 404906208 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014358 | 404907681 | High Sign | HFTD Tier 2 | Distribution | 2013-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014359 | 404907708 | Molding | HFTD Tier 2 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014360 | 404907711 | High Sign | HFTD Tier 2 | Distribution | 2013-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014361 | 404907712 | High Sign | HFTD Tier 2 | Distribution | 2013-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014362 | 404907717 | High Sign | HFTD Tier 2 | Distribution | 2013-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014363 | 404907765 | High Sign | HFTD Tier 2 | Distribution | 2013-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014364 | 404908435 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014365 | 404908436 | High Sign | HFTD Tier 3 | Distribution | 2013-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014366 | 404908441 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014367 | 404908443 | Guy | HFTD Tier 3 | Distribution | 2013-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014368 | 404915225 | Molding | HFTD Tier 3 | Distribution | 2013-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014369 | 404915871 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014370 | 404915899 | Molding | HFTD Tier 3 | Distribution | 2013-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014371 | 404915912 | Molding | HFTD Tier 3 | Distribution | 2013-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014372 | 404915942 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014373 | 404915949 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014374 | 404915950 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014375 | 404931886 | High Sign | HFTD Tier 3 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014376 | 404932001 | High Sign | HFTD Tier 3 | Distribution | 2013-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014377 | 404932019 | High Sign | HFTD Tier 3 | Distribution | 2013-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014378 | 404932030 | High Sign | HFTD Tier 3 | Distribution | 2013-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014379 | 404932033 | High Sign | HFTD Tier 3 | Distribution | 2013-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014380 | 404932040 | Molding | HFTD Tier 3 | Distribution | 2013-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014381 | 404932049 | Molding | HFTD Tier 3 | Distribution | 2013-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014382 | 404932062 | Molding | HFTD Tier 3 | Distribution | 2013-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014383 | 404932063 | High Sign | HFTD Tier 3 | Distribution | 2013-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014384 | 404932071 | Molding | HFTD Tier 3 | Distribution | 2013-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014385 | 404932482 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014386 | 404932486 | Molding | HFTD Tier 2 | Distribution | 2013-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014387 | 404932487 | High Sign | HFTD Tier 2 | Distribution | 2013-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014388 | 404932521 | Guy | HFTD Tier 3 | Distribution | 2013-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014389 | 404932522 | High Sign | HFTD Tier 2 | Distribution | 2013-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014390 | 404932530 | Molding | HFTD Tier 2 | Distribution | 2013-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014391 | 404932531 | High Sign | HFTD Tier 3 | Distribution | 2013-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014392 | 404932532 | Molding | HFTD Tier 2 | Distribution | 2013-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014393 | 404934208 | Molding | HFTD Tier 3 | Distribution | 2013-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014394 | 404934295 | Molding | HFTD Tier 3 | Distribution | 2013-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014395 | 404934309 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014396 | 404934318 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014397 | 404934320 | Molding | HFTD Tier 3 | Distribution | 2013-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014398 | 404934321 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014399 | 404934327 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014400 | 404934819 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014401 | 404934950 | High Sign | HFTD Tier 2 | Distribution | 2013-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014402 | 404934951 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014403 | 404934953 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014404 | 404937160 | Molding | HFTD Tier 3 | Distribution | 2013-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014405 | 404937454 | High Sign | HFTD Tier 2 | Distribution | 2013-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014406 | 404937464 | Termination | HFTD Tier 2 | Distribution | 2013-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014407 | 404937477 | High Sign | HFTD Tier 2 | Distribution | 2013-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014408 | 404937812 | High Sign | HFTD Tier 3 | Distribution | 2013-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014409 | 404938519 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014410 | 404939239 | Molding | HFTD Tier 3 | Distribution | 2013-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014411 | 404939264 | Molding | HFTD Tier 3 | Distribution | 2013-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014412 | 404939265 | High Sign | HFTD Tier 3 | Distribution | 2013-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014413 | 404939274 | High Sign | HFTD Tier 3 | Distribution | 2013-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014414 | 404939388 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014415 | 404939400 | Molding | HFTD Tier 3 | Distribution | 2013-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014416 | 404939403 | Molding | HFTD Tier 3 | Distribution | 2013-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014417 | 404939407 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014418 | 404939422 | Molding | HFTD Tier 3 | Distribution | 2013-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014419 | 404939437 | Molding | HFTD Tier 3 | Distribution | 2013-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014420 | 404939453 | Molding | HFTD Tier 3 | Distribution | 2013-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014421 | 404939469 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014422 | 404939484 | High Sign | HFTD Tier 3 | Distribution | 2013-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014423 | 404939495 | Molding | HFTD Tier 3 | Distribution | 2013-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014424 | 404939506 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014425 | 404939516 | Molding | HFTD Tier 3 | Distribution | 2013-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014426 | 404939523 | High Sign | HFTD Tier 3 | Distribution | 2013-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014427 | 404939524 | Molding | HFTD Tier 3 | Distribution | 2013-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014428 | 404939526 | High Sign | HFTD Tier 3 | Distribution | 2013-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014429 | 404939529 | Molding | HFTD Tier 3 | Distribution | 2013-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014430 | 404939530 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014431 | 404939553 | High Sign | HFTD Tier 3 | Distribution | 2013-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014432 | 404940264 | High Sign | HFTD Tier 2 | Distribution | 2013-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014433 | 404940269 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014434 | 404940272 | Molding | HFTD Tier 2 | Distribution | 2013-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014435 | 404940368 | High Sign | HFTD Tier 2 | Distribution | 2013-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014436 | 404940378 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014437 | 404940380 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014438 | 404940383 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014439 | 404940384 | Molding | HFTD Tier 2 | Distribution | 2013-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014440 | 404940386 | High Sign | HFTD Tier 2 | Distribution | 2013-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014441 | 404940393 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014442 | 404947621 | High Sign | HFTD Tier 2 | Distribution | 2013-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014443 | 404952782 | Vis Strips | HFTD Tier 2 | Distribution | 2013-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014444 | 404952881 | High Sign | HFTD Tier 3 | Distribution | 2013-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014445 | 404952935 | High Sign | HFTD Tier 2 | Distribution | 2013-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014446 | 404953739 | Guy | HFTD Tier 2 | Distribution | 2013-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014447 | 404953740 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014448 | 404953741 | High Sign | HFTD Tier 2 | Distribution | 2013-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014449 | 404953742 | Molding | HFTD Tier 2 | Distribution | 2013-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014450 | 404953754 | Molding | HFTD Tier 2 | Distribution | 2013-01-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014451 | 404954372 | High Sign | HFTD Tier 3 | Distribution | 2013-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014452 | 404954373 | Molding | HFTD Tier 3 | Distribution | 2013-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014453 | 404954374 | High Sign | HFTD Tier 3 | Distribution | 2013-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014454 | 404954380 | High Sign | HFTD Tier 3 | Distribution | 2013-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014455 | 404954385 | Molding | HFTD Tier 3 | Distribution | 2013-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014456 | 404954386 | High Sign | HFTD Tier 3 | Distribution | 2013-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014457 | 404954420 | Molding | HFTD Tier 3 | Distribution | 2013-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014458 | 404954422 | Molding | HFTD Tier 3 | Distribution | 2013-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014459 | 404963157 | High Sign | HFTD Tier 3 | Distribution | 2013-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014460 | 404963170 | Guy | HFTD Tier 3 | Distribution | 2013-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014461 | 404963220 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014462 | 404967315 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2013-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014463 | 404967905 | High Sign | HFTD Tier 2 | Distribution | 2013-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014464 | 404967926 | High Sign | HFTD Tier 2 | Distribution | 2013-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014465 | 404967978 | Molding | HFTD Tier 2 | Distribution | 2013-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014466 | 404967980 | Molding | HFTD Tier 2 | Distribution | 2013-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014467 | 404967991 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014468 | 404970732 | High Sign | HFTD Tier 3 | Distribution | 2013-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014469 | 404970805 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014470 | 404976233 | Molding | HFTD Tier 2 | Distribution | 2013-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014471 | 404976252 | High Sign | HFTD Tier 3 | Distribution | 2013-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014472 | 404976254 | Molding | HFTD Tier 3 | Distribution | 2013-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014473 | 404976262 | Guy | HFTD Tier 3 | Distribution | 2013-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014474 | 404976271 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014475 | 404976293 | Molding | HFTD Tier 2 | Distribution | 2013-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014476 | 404976370 | Guy | HFTD Tier 3 | Distribution | 2013-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014477 | 404977812 | Molding | HFTD Tier 3 | Distribution | 2013-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014478 | 404977922 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014479 | 404978183 | Molding | HFTD Tier 3 | Distribution | 2013-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014480 | 404978287 | Molding | HFTD Tier 3 | Distribution | 2013-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014481 | 404978365 | High Sign | HFTD Tier 2 | Distribution | 2013-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014482 | 404978366 | High Sign | HFTD Tier 2 | Distribution | 2013-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014483 | 404978392 | Molding | HFTD Tier 2 | Distribution | 2013-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014484 | 404978393 | Guy | HFTD Tier 2 | Distribution | 2013-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014485 | 404978665 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014486 | 404978690 | Molding | HFTD Tier 3 | Distribution | 2013-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014487 | 404978761 | Molding | HFTD Tier 2 | Distribution | 2013-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014488 | 404984397 | Guy | HFTD Tier 3 | Distribution | 2013-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014489 | 404987805 | Molding | HFTD Tier 2 | Distribution | 2013-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014490 | 404987809 | Molding | HFTD Tier 3 | Distribution | 2013-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014491 | 404987811 | Molding | HFTD Tier 2 | Distribution | 2013-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014492 | 404987812 | High Sign | HFTD Tier 2 | Distribution | 2013-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014493 | 404987818 | Guy | HFTD Tier 3 | Distribution | 2013-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014494 | 404987821 | Guy | HFTD Tier 3 | Distribution | 2013-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014495 | 404987833 | Molding | HFTD Tier 3 | Distribution | 2013-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014496 | 404987834 | High Sign | HFTD Tier 3 | Distribution | 2013-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014497 | 404987836 | High Sign | HFTD Tier 3 | Distribution | 2013-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014498 | 404988062 | Molding | HFTD Tier 2 | Distribution | 2013-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014499 | 404989688 | High Sign | HFTD Tier 2 | Distribution | 2013-01-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014500 | 404990192 | High Sign | HFTD Tier 3 | Distribution | 2013-01-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014501 | 404990565 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-01-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014502 | 404991723 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-01-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014503 | 404991724 | High Sign | HFTD Tier 3 | Distribution | 2013-01-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014504 | 404991733 | Insulator | HFTD Tier 3 | Distribution | 2013-01-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014505 | 404991735 | Guy | HFTD Tier 3 | Distribution | 2013-01-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014506 | 404991736 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-01-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014507 | 404992756 | Guy | HFTD Tier 3 | Distribution | 2013-01-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014508 | 404993784 | High Sign | HFTD Tier 3 | Distribution | 2013-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014509 | 404994408 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014510 | 404994413 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014511 | 404994414 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014512 | 404994428 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014513 | 404996844 | High Sign | HFTD Tier 3 | Distribution | 2013-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014514 | 404996875 | High Sign | HFTD Tier 3 | Distribution | 2013-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014515 | 404996911 | Guy | HFTD Tier 2 | Distribution | 2013-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014516 | 404996920 | Guy | HFTD Tier 2 | Distribution | 2013-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014517 | 405003492 | Molding | HFTD Tier 3 | Distribution | 2013-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014518 | 405003501 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014519 | 405003856 | Molding | HFTD Tier 3 | Distribution | 2013-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014520 | 405005373 | Molding | HFTD Tier 3 | Distribution | 2013-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014521 | 405005414 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014522 | 405005455 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-02-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014523 | 405006513 | Vis Strips | HFTD Tier 2 | Distribution | 2013-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014524 | 405006556 | Vis Strips | HFTD Tier 2 | Distribution | 2013-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014525 | 405007760 | High Sign | HFTD Tier 3 | Distribution | 2013-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014526 | 405007791 | High Sign | HFTD Tier 2 | Distribution | 2013-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014527 | 405008090 | Guy | HFTD Tier 3 | Distribution | 2013-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014528 | 405011087 | High Sign | HFTD Tier 3 | Distribution | 2013-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014529 | 405011658 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014530 | 405011674 | High Sign | HFTD Tier 3 | Distribution | 2013-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014531 | 405011735 | Molding | HFTD Tier 3 | Distribution | 2013-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014532 | 405012128 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014533 | 405012132 | Molding | HFTD Tier 3 | Distribution | 2013-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014534 | 405012162 | Molding | HFTD Tier 3 | Distribution | 2013-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014535 | 405013509 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014536 | 405013981 | Molding | HFTD Tier 3 | Distribution | 2013-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014537 | 405013998 | Molding | HFTD Tier 3 | Distribution | 2013-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014538 | 405016457 | High Sign | HFTD Tier 3 | Distribution | 2013-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014539 | 405016463 | High Sign | HFTD Tier 3 | Distribution | 2013-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014540 | 405017213 | Guy | HFTD Tier 3 | Distribution | 2013-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014541 | 405017215 | Guy | HFTD Tier 3 | Distribution | 2013-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014542 | 405017217 | Molding | HFTD Tier 3 | Distribution | 2013-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014543 | 405017225 | Molding | HFTD Tier 3 | Distribution | 2013-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014544 | 405017579 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-02-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014545 | 405017633 | Ground | HFTD Tier 3 | Distribution | 2013-02-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014546 | 405017652 | Guy | HFTD Tier 3 | Distribution | 2013-02-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014547 | 405018933 | Molding | HFTD Tier 3 | Distribution | 2013-02-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014548 | 405019621 | High Sign | HFTD Tier 2 | Distribution | 2013-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014549 | 405019935 | Riser/Conduit | HFTD Tier 2 | Distribution | 2013-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014550 | 405020037 | Guy | HFTD Tier 2 | Distribution | 2013-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014551 | 405020047 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014552 | 405020071 | High Sign | HFTD Tier 2 | Distribution | 2013-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014553 | 405020385 | Guy | HFTD Tier 2 | Distribution | 2013-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014554 | 405020484 | Vis Strips | HFTD Tier 2 | Distribution | 2013-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014555 | 405021132 | Molding | HFTD Tier 3 | Distribution | 2013-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014556 | 405022297 | Molding | HFTD Tier 3 | Distribution | 2013-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014557 | 405022300 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014558 | 405022308 | Molding | HFTD Tier 3 | Distribution | 2013-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014559 | 405022314 | High Sign | HFTD Tier 3 | Distribution | 2013-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014560 | 405022315 | Molding | HFTD Tier 3 | Distribution | 2013-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014561 | 405022320 | High Sign | HFTD Tier 3 | Distribution | 2013-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014562 | 405022323 | Molding | HFTD Tier 3 | Distribution | 2013-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014563 | 405023071 | High Sign | HFTD Tier 2 | Distribution | 2013-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014564 | 405023202 | High Sign | HFTD Tier 2 | Distribution | 2013-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014565 | 405023205 | High Sign | HFTD Tier 2 | Distribution | 2013-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014566 | 405023209 | Molding | HFTD Tier 2 | Distribution | 2013-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014567 | 405023221 | High Sign | HFTD Tier 2 | Distribution | 2013-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014568 | 405023222 | High Sign | HFTD Tier 2 | Distribution | 2013-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014569 | 405023250 | High Sign | HFTD Tier 2 | Distribution | 2013-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014570 | 405023279 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014571 | 405025016 | High Sign | HFTD Tier 3 | Distribution | 2013-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014572 | 405025812 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014573 | 405025821 | High Sign | HFTD Tier 3 | Distribution | 2013-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014574 | 405025830 | Molding | HFTD Tier 3 | Distribution | 2013-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014575 | 405025832 | High Sign | HFTD Tier 3 | Distribution | 2013-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014576 | 405026333 | Molding | HFTD Tier 2 | Distribution | 2013-02-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014577 | 405027028 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-02-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014578 | 405027032 | Guy | HFTD Tier 2 | Distribution | 2013-02-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014579 | 405028775 | Vis Strips | HFTD Tier 2 | Distribution | 2013-02-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014580 | 405028973 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-02-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014581 | 405028987 | High Sign | HFTD Tier 2 | Distribution | 2013-02-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014582 | 405029055 | High Sign | HFTD Tier 2 | Distribution | 2013-02-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014583 | 405029190 | Molding | HFTD Tier 2 | Distribution | 2013-02-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014584 | 405029202 | High Sign | HFTD Tier 2 | Distribution | 2013-02-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014585 | 405030030 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-02-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014586 | 405031245 | High Sign | HFTD Tier 3 | Distribution | 2013-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014587 | 405031307 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014588 | 405031377 | Molding | HFTD Tier 3 | Distribution | 2013-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014589 | 405031380 | Molding | HFTD Tier 3 | Distribution | 2013-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014590 | 405033352 | Molding | HFTD Tier 2 | Distribution | 2013-02-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014591 | 405033932 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014592 | 405033936 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014593 | 405033955 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014594 | 405033960 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014595 | 405034262 | Vis Strips | HFTD Tier 2 | Distribution | 2013-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014596 | 405034321 | Vis Strips | HFTD Tier 2 | Distribution | 2013-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014597 | 405034342 | Vis Strips | HFTD Tier 2 | Distribution | 2013-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014598 | 405035543 | High Sign | HFTD Tier 2 | Distribution | 2013-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014599 | 405035639 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014600 | 405035653 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014601 | 405035664 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014602 | 405036126 | Molding | HFTD Tier 3 | Distribution | 2013-02-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014603 | 405036744 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-02-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014604 | 405038028 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-02-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014605 | 405038058 | ID Markings | HFTD Tier 2 | Distribution | 2013-02-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014606 | 405038573 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-02-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014607 | 405038579 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-02-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014608 | 405038663 | High Sign | HFTD Tier 2 | Distribution | 2013-02-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014609 | 405038680 | High Sign | HFTD Tier 2 | Distribution | 2013-02-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014610 | 405039113 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-02-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014611 | 405039125 | High Sign | HFTD Tier 2 | Distribution | 2013-02-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014612 | 405039145 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-02-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014613 | 405039147 | High Sign | HFTD Tier 2 | Distribution | 2013-02-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014614 | 405040644 | High Sign | HFTD Tier 2 | Distribution | 2013-02-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014615 | 405040647 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-02-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014616 | 405040653 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-02-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014617 | 405040658 | High Sign | HFTD Tier 2 | Distribution | 2013-02-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014618 | 405040659 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-02-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014619 | 405040660 | High Sign | HFTD Tier 2 | Distribution | 2013-02-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014620 | 405040661 | High Sign | HFTD Tier 2 | Distribution | 2013-02-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014621 | 405040663 | High Sign | HFTD Tier 2 | Distribution | 2013-02-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014622 | 405040665 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-02-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014623 | 405040670 | High Sign | HFTD Tier 2 | Distribution | 2013-02-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014624 | 405040672 | Molding | HFTD Tier 2 | Distribution | 2013-02-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014625 | 405041034 | Ground | HFTD Tier 3 | Distribution | 2013-02-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014626 | 405041048 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-02-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014627 | 405041064 | Guy | HFTD Tier 3 | Distribution | 2013-02-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014628 | 405042358 | High Sign | HFTD Tier 3 | Distribution | 2013-02-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014629 | 405044553 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-02-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014630 | 405045078 | Molding | HFTD Tier 2 | Distribution | 2013-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014631 | 405045303 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014632 | 405046664 | Molding | HFTD Tier 3 | Distribution | 2013-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014633 | 405046793 | Molding | HFTD Tier 3 | Distribution | 2013-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014634 | 405046851 | High Sign | HFTD Tier 3 | Distribution | 2013-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014635 | 405047486 | Molding | HFTD Tier 2 | Distribution | 2013-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014636 | 405047490 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014637 | 405047982 | Molding | HFTD Tier 3 | Distribution | 2013-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014638 | 405047989 | High Sign | HFTD Tier 3 | Distribution | 2013-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014639 | 405048274 | Molding | HFTD Tier 3 | Distribution | 2013-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014640 | 405048288 | Molding | HFTD Tier 2 | Distribution | 2013-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014641 | 405048339 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014642 | 405048359 | Guy | HFTD Tier 3 | Distribution | 2013-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014643 | 405048718 | High Sign | HFTD Tier 3 | Distribution | 2013-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014644 | 405048743 | High Sign | HFTD Tier 3 | Distribution | 2013-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014645 | 405048744 | Guy | HFTD Tier 3 | Distribution | 2013-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014646 | 405048746 | High Sign | HFTD Tier 3 | Distribution | 2013-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014647 | 405048749 | High Sign | HFTD Tier 3 | Distribution | 2013-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014648 | 405048752 | Molding | HFTD Tier 3 | Distribution | 2013-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014649 | 405048756 | High Sign | HFTD Tier 3 | Distribution | 2013-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014650 | 405048774 | High Sign | HFTD Tier 3 | Distribution | 2013-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014651 | 405050574 | High Sign | HFTD Tier 2 | Distribution | 2013-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014652 | 405051067 | Molding | HFTD Tier 3 | Distribution | 2013-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014653 | 405051081 | Molding | HFTD Tier 2 | Distribution | 2013-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014654 | 405051294 | High Sign | HFTD Tier 3 | Distribution | 2013-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014655 | 405051303 | High Sign | HFTD Tier 2 | Distribution | 2013-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014656 | 405051331 | Guy | HFTD Tier 2 | Distribution | 2013-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014657 | 405051341 | Molding | HFTD Tier 2 | Distribution | 2013-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014658 | 405051503 | High Sign | HFTD Tier 3 | Distribution | 2013-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014659 | 405051516 | High Sign | HFTD Tier 3 | Distribution | 2013-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014660 | 405051541 | Molding | HFTD Tier 3 | Distribution | 2013-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014661 | 405053397 | Molding | HFTD Tier 3 | Distribution | 2013-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014662 | 405053403 | High Sign | HFTD Tier 3 | Distribution | 2013-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014663 | 405053411 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014664 | 405053429 | High Sign | HFTD Tier 3 | Distribution | 2013-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014665 | 405053626 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014666 | 405053637 | Molding | HFTD Tier 3 | Distribution | 2013-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014667 | 405053638 | High Sign | HFTD Tier 3 | Distribution | 2013-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014668 | 405053667 | Molding | HFTD Tier 3 | Distribution | 2013-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014669 | 405053669 | Molding | HFTD Tier 3 | Distribution | 2013-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014670 | 405056063 | High Sign | HFTD Tier 2 | Distribution | 2013-03-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014671 | 405056066 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-03-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014672 | 405056072 | Molding | HFTD Tier 2 | Distribution | 2013-03-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014673 | 405056093 | Molding | HFTD Tier 2 | Distribution | 2013-03-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014674 | 405056133 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2013-03-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014675 | 405056144 | Termination | HFTD Tier 2 | Distribution | 2013-03-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014676 | 405056237 | High Sign | HFTD Tier 3 | Distribution | 2013-03-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014677 | 405059661 | High Sign | HFTD Tier 2 | Distribution | 2013-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014678 | 405059678 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014679 | 405060208 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014680 | 405061033 | Molding | HFTD Tier 3 | Distribution | 2013-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014681 | 405061034 | Molding | HFTD Tier 3 | Distribution | 2013-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014682 | 405061698 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014683 | 405062084 | High Sign | HFTD Tier 3 | Distribution | 2013-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014684 | 405062095 | High Sign | HFTD Tier 3 | Distribution | 2013-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014685 | 405062104 | High Sign | HFTD Tier 3 | Distribution | 2013-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014686 | 405062106 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014687 | 405062111 | High Sign | HFTD Tier 3 | Distribution | 2013-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014688 | 405062124 | High Sign | HFTD Tier 3 | Distribution | 2013-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014689 | 405062409 | Molding | HFTD Tier 3 | Distribution | 2013-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014690 | 405062425 | Molding | HFTD Tier 3 | Distribution | 2013-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014691 | 405062433 | Molding | HFTD Tier 3 | Distribution | 2013-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014692 | 405062441 | High Sign | HFTD Tier 3 | Distribution | 2013-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014693 | 405063216 | High Sign | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014694 | 405063250 | High Sign | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014695 | 405063473 | High Sign | HFTD Tier 2 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014696 | 405063869 | High Sign | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014697 | 405063878 | High Sign | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014698 | 405063879 | High Sign | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014699 | 405063881 | Molding | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014700 | 405063882 | High Sign | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014701 | 405063886 | High Sign | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014702 | 405063892 | High Sign | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014703 | 405063893 | High Sign | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014704 | 405063896 | High Sign | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014705 | 405063904 | High Sign | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014706 | 405063909 | High Sign | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014707 | 405063911 | High Sign | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014708 | 405063913 | Molding | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014709 | 405063915 | High Sign | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014710 | 405065316 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014711 | 405065383 | High Sign | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014712 | 405065716 | Molding | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014713 | 405066000 | High Sign | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014714 | 405066018 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014715 | 405066021 | Molding | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014716 | 405066022 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014717 | 405066031 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014718 | 405066047 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014719 | 405066062 | Molding | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014720 | 405066418 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014721 | 405066434 | High Sign | HFTD Tier 3 | Distribution | 2013-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014722 | 405066437 | High Sign | HFTD Tier 3 | Distribution | 2013-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014723 | 405066467 | High Sign | HFTD Tier 3 | Distribution | 2013-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014724 | 405066468 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014725 | 405066476 | Molding | HFTD Tier 3 | Distribution | 2013-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014726 | 405066573 | Guy | HFTD Tier 2 | Distribution | 2013-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014727 | 405066590 | Molding | HFTD Tier 2 | Distribution | 2013-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014728 | 405068696 | High Sign | HFTD Tier 3 | Distribution | 2013-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014729 | 405068712 | Molding | HFTD Tier 3 | Distribution | 2013-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014730 | 405068732 | High Sign | HFTD Tier 3 | Distribution | 2013-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014731 | 405068743 | High Sign | HFTD Tier 3 | Distribution | 2013-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014732 | 405069220 | Molding | HFTD Tier 3 | Distribution | 2013-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014733 | 405069239 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014734 | 405069240 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014735 | 405069246 | High Sign | HFTD Tier 3 | Distribution | 2013-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014736 | 405069261 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014737 | 405069262 | Molding | HFTD Tier 3 | Distribution | 2013-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014738 | 405069458 | Molding | HFTD Tier 3 | Distribution | 2013-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014739 | 405069471 | High Sign | HFTD Tier 3 | Distribution | 2013-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014740 | 405069473 | High Sign | HFTD Tier 3 | Distribution | 2013-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014741 | 405070147 | High Sign | HFTD Tier 3 | Distribution | 2013-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014742 | 405070150 | High Sign | HFTD Tier 3 | Distribution | 2013-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014743 | 405070161 | High Sign | HFTD Tier 3 | Distribution | 2013-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014744 | 405070163 | High Sign | HFTD Tier 3 | Distribution | 2013-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014745 | 405070164 | Molding | HFTD Tier 3 | Distribution | 2013-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014746 | 405070167 | High Sign | HFTD Tier 3 | Distribution | 2013-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014747 | 405070169 | High Sign | HFTD Tier 3 | Distribution | 2013-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014748 | 405070676 | Molding | HFTD Tier 3 | Distribution | 2013-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014749 | 405071252 | High Sign | HFTD Tier 3 | Distribution | 2013-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014750 | 405071262 | High Sign | HFTD Tier 3 | Distribution | 2013-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014751 | 405071265 | Molding | HFTD Tier 3 | Distribution | 2013-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014752 | 405071269 | Molding | HFTD Tier 3 | Distribution | 2013-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014753 | 405071279 | High Sign | HFTD Tier 3 | Distribution | 2013-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014754 | 405071301 | High Sign | HFTD Tier 3 | Distribution | 2013-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014755 | 405071304 | High Sign | HFTD Tier 3 | Distribution | 2013-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014756 | 405071306 | Molding | HFTD Tier 3 | Distribution | 2013-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014757 | 405073101 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014758 | 405075363 | High Sign | HFTD Tier 3 | Distribution | 2013-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014759 | 405075364 | Molding | HFTD Tier 3 | Distribution | 2013-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014760 | 405075366 | Molding | HFTD Tier 3 | Distribution | 2013-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014761 | 405075410 | Molding | HFTD Tier 3 | Distribution | 2013-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014762 | 405075411 | Molding | HFTD Tier 3 | Distribution | 2013-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014763 | 405075423 | High Sign | HFTD Tier 2 | Distribution | 2013-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014764 | 405075442 | High Sign | HFTD Tier 2 | Distribution | 2013-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014765 | 405075444 | Molding | HFTD Tier 2 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014766 | 405076649 | High Sign | HFTD Tier 3 | Distribution | 2013-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014767 | 405076659 | High Sign | HFTD Tier 3 | Distribution | 2013-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014768 | 405076686 | Molding | HFTD Tier 3 | Distribution | 2013-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014769 | 405076687 | Molding | HFTD Tier 3 | Distribution | 2013-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014770 | 405078238 | High Sign | HFTD Tier 2 | Distribution | 2013-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014771 | 405078578 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014772 | 405078595 | Guy | HFTD Tier 2 | Distribution | 2013-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014773 | 405078884 | Molding | HFTD Tier 3 | Distribution | 2013-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014774 | 405078885 | Molding | HFTD Tier 3 | Distribution | 2013-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014775 | 405078890 | Molding | HFTD Tier 3 | Distribution | 2013-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014776 | 405078893 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014777 | 405078900 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014778 | 405078904 | High Sign | HFTD Tier 3 | Distribution | 2013-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014779 | 405081430 | High Sign | HFTD Tier 2 | Distribution | 2013-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014780 | 405081461 | Molding | HFTD Tier 2 | Distribution | 2013-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014781 | 405081493 | High Sign | HFTD Tier 2 | Distribution | 2013-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014782 | 405081508 | High Sign | HFTD Tier 2 | Distribution | 2013-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014783 | 405081509 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014784 | 405081834 | High Sign | HFTD Tier 3 | Distribution | 2013-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014785 | 405081843 | Molding | HFTD Tier 3 | Distribution | 2013-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014786 | 405081901 | Molding | HFTD Tier 3 | Distribution | 2013-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014787 | 405081910 | High Sign | HFTD Tier 3 | Distribution | 2013-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014788 | 405082087 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014789 | 405082095 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014790 | 405082114 | High Sign | HFTD Tier 3 | Distribution | 2013-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014791 | 405082168 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014792 | 405082182 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014793 | 405083029 | Molding | HFTD Tier 2 | Distribution | 2013-03-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014794 | 405083734 | High Sign | HFTD Tier 2 | Distribution | 2013-03-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014795 | 405085411 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-03-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014796 | 405087898 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014797 | 405087914 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014798 | 405087916 | Guy | HFTD Tier 3 | Distribution | 2013-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014799 | 405087920 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014800 | 405087921 | Guy | HFTD Tier 3 | Distribution | 2013-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014801 | 405087925 | High Sign | HFTD Tier 3 | Distribution | 2013-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014802 | 405087939 | Guy | HFTD Tier 3 | Distribution | 2013-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014803 | 405088181 | High Sign | HFTD Tier 3 | Distribution | 2013-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014804 | 405088183 | Molding | HFTD Tier 3 | Distribution | 2013-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014805 | 405088192 | High Sign | HFTD Tier 3 | Distribution | 2013-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014806 | 405089477 | Molding | HFTD Tier 3 | Distribution | 2013-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014807 | 405090629 | Bond | HFTD Tier 2 | Distribution | 2013-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014808 | 405090638 | Guy | HFTD Tier 2 | Distribution | 2013-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014809 | 405090665 | Bond | HFTD Tier 2 | Distribution | 2013-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014810 | 405090878 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014811 | 405091073 | High Sign | HFTD Tier 3 | Distribution | 2013-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014812 | 405091366 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014813 | 405091371 | Guy | HFTD Tier 3 | Distribution | 2013-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014814 | 405091376 | Guy | HFTD Tier 3 | Distribution | 2013-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014815 | 405093120 | Molding | HFTD Tier 3 | Distribution | 2013-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014816 | 405094112 | Molding | HFTD Tier 3 | Distribution | 2013-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014817 | 405094123 | Guy | HFTD Tier 3 | Distribution | 2013-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014818 | 405094172 | Guy | HFTD Tier 3 | Distribution | 2013-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014819 | 405094379 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014820 | 405094402 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014821 | 405094443 | Molding | HFTD Tier 3 | Distribution | 2013-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014822 | 405095017 | Molding | HFTD Tier 3 | Distribution | 2013-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014823 | 405095022 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014824 | 405095023 | Molding | HFTD Tier 3 | Distribution | 2013-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014825 | 405095946 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014826 | 405097390 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014827 | 405098054 | Molding | HFTD Tier 3 | Distribution | 2013-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014828 | 405098056 | Guy | HFTD Tier 3 | Distribution | 2013-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014829 | 405098057 | High Sign | HFTD Tier 3 | Distribution | 2013-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014830 | 405098065 | High Sign | HFTD Tier 3 | Distribution | 2013-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014831 | 405098066 | Guy | HFTD Tier 3 | Distribution | 2013-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014832 | 405098076 | High Sign | HFTD Tier 3 | Distribution | 2013-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014833 | 405098104 | Molding | HFTD Tier 3 | Distribution | 2013-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014834 | 405098136 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014835 | 405098163 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014836 | 405099002 | High Sign | HFTD Tier 3 | Distribution | 2013-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014837 | 405099040 | Molding | HFTD Tier 3 | Distribution | 2013-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014838 | 405099049 | Molding | HFTD Tier 3 | Distribution | 2013-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014839 | 405099074 | Molding | HFTD Tier 3 | Distribution | 2013-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014840 | 405099080 | High Sign | HFTD Tier 3 | Distribution | 2013-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014841 | 405099081 | Molding | HFTD Tier 3 | Distribution | 2013-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014842 | 405099089 | High Sign | HFTD Tier 3 | Distribution | 2013-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014843 | 405099090 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014844 | 405099091 | Molding | HFTD Tier 3 | Distribution | 2013-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014845 | 405099092 | Guy | HFTD Tier 3 | Distribution | 2013-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014846 | 405099096 | High Sign | HFTD Tier 3 | Distribution | 2013-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014847 | 405099100 | High Sign | HFTD Tier 3 | Distribution | 2013-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014848 | 405099102 | High Sign | HFTD Tier 3 | Distribution | 2013-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014849 | 405099107 | High Sign | HFTD Tier 3 | Distribution | 2013-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014850 | 405099108 | High Sign | HFTD Tier 3 | Distribution | 2013-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014851 | 405100858 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014852 | 405100871 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014853 | 405100876 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014854 | 405100884 | Molding | HFTD Tier 3 | Distribution | 2013-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014855 | 405100913 | High Sign | HFTD Tier 3 | Distribution | 2013-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014856 | 405103634 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014857 | 405103913 | Molding | HFTD Tier 3 | Distribution | 2013-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014858 | 405104305 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014859 | 405105017 | Riser/Conduit | HFTD Tier 2 | Distribution | 2013-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014860 | 405105022 | High Sign | HFTD Tier 2 | Distribution | 2013-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014861 | 405105025 | High Sign | HFTD Tier 2 | Distribution | 2013-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014862 | 405105035 | High Sign | HFTD Tier 2 | Distribution | 2013-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014863 | 405105038 | Molding | HFTD Tier 2 | Distribution | 2013-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014864 | 405105113 | Bond | HFTD Tier 2 | Distribution | 2013-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014865 | 405105975 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014866 | 405105978 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014867 | 405105989 | High Sign | HFTD Tier 3 | Distribution | 2013-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014868 | 405105996 | Molding | HFTD Tier 3 | Distribution | 2013-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014869 | 405106293 | Molding | HFTD Tier 3 | Distribution | 2013-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014870 | 405107306 | High Sign | HFTD Tier 2 | Distribution | 2013-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014871 | 405107336 | Guy | HFTD Tier 2 | Distribution | 2013-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014872 | 405107342 | High Sign | HFTD Tier 2 | Distribution | 2013-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014873 | 405108930 | Riser/Conduit | HFTD Tier 2 | Distribution | 2013-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014874 | 405108934 | Molding | HFTD Tier 2 | Distribution | 2013-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014875 | 405108942 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014876 | 405108945 | Termination | HFTD Tier 2 | Distribution | 2013-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014877 | 405108957 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2013-04-01 | 1956-04-14 | 2 | Ignition Risk, no GO95 exception | [6 empty] | SCE | 2025 | 4
1130014878 | 405110008 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014879 | 405110127 | High Sign | HFTD Tier 2 | Distribution | 2013-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014880 | 405110143 | High Sign | HFTD Tier 2 | Distribution | 2013-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014881 | 405110156 | Molding | HFTD Tier 2 | Distribution | 2013-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014882 | 405110163 | Handhole | HFTD Tier 2 | Distribution | 2013-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014883 | 405110180 | Molding | HFTD Tier 2 | Distribution | 2013-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014884 | 405110227 | Molding | HFTD Tier 3 | Distribution | 2013-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014885 | 405110236 | High Sign | HFTD Tier 3 | Distribution | 2013-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014886 | 405112283 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2013-04-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014887 | 405113358 | Molding | HFTD Tier 2 | Distribution | 2013-04-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014888 | 405113486 | Molding | HFTD Tier 2 | Distribution | 2013-04-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014889 | 405113503 | Molding | HFTD Tier 2 | Distribution | 2013-04-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014890 | 405115235 | Guy | HFTD Tier 2 | Distribution | 2013-04-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014891 | 405116762 | High Sign | HFTD Tier 3 | Distribution | 2013-04-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014892 | 405116802 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-04-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014893 | 405117539 | Guy | HFTD Tier 2 | Distribution | 2013-04-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014894 | 405117546 | High Sign | HFTD Tier 2 | Distribution | 2013-04-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014895 | 405118620 | High Sign | HFTD Tier 2 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014896 | 405120153 | Vis Strips | HFTD Tier 2 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014897 | 405120155 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014898 | 405120160 | Molding | HFTD Tier 2 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014899 | 405120162 | Molding | HFTD Tier 2 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014900 | 405120245 | Molding | HFTD Tier 2 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014901 | 405120268 | Guy | HFTD Tier 2 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014902 | 405120271 | Molding | HFTD Tier 2 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014903 | 405120449 | Pole Tag | HFTD Tier 3 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014904 | 405120458 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014905 | 405120460 | Molding | HFTD Tier 3 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014906 | 405120470 | Pole Tag | HFTD Tier 3 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014907 | 405120472 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014908 | 405120474 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014909 | 405120475 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014910 | 405120488 | Guy | HFTD Tier 3 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014911 | 405120489 | Molding | HFTD Tier 3 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014912 | 405121032 | Molding | HFTD Tier 2 | Distribution | 2013-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014913 | 405122246 | Molding | HFTD Tier 2 | Distribution | 2013-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014914 | 405123234 | High Sign | HFTD Tier 2 | Distribution | 2013-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014915 | 405123254 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014916 | 405123271 | Guy | HFTD Tier 2 | Distribution | 2013-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014917 | 405123832 | Molding | HFTD Tier 3 | Distribution | 2013-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014918 | 405123833 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014919 | 405123834 | Guy | HFTD Tier 3 | Distribution | 2013-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014920 | 405124058 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014921 | 405124063 | High Sign | HFTD Tier 3 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014922 | 405124070 | High Sign | HFTD Tier 3 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014923 | 405124076 | High Sign | HFTD Tier 3 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014924 | 405124079 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014925 | 405124091 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014926 | 405125851 | Crossarm | HFTD Tier 2 | Distribution | 2013-04-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014927 | 405126811 | Guy | HFTD Tier 2 | Distribution | 2013-04-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014928 | 405126813 | Molding | HFTD Tier 2 | Distribution | 2013-04-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014929 | 405126815 | Guy | HFTD Tier 2 | Distribution | 2013-04-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014930 | 405126921 | High Sign | HFTD Tier 2 | Distribution | 2013-04-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014931 | 405127585 | High Sign | HFTD Tier 3 | Distribution | 2013-04-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014932 | 405127675 | Molding | HFTD Tier 3 | Distribution | 2013-04-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014933 | 405128039 | High Sign | HFTD Tier 2 | Distribution | 2013-04-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014934 | 405128042 | High Sign | HFTD Tier 2 | Distribution | 2013-04-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014935 | 405129488 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014936 | 405130338 | Riser/Conduit | HFTD Tier 2 | Distribution | 2013-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014937 | 405130374 | Molding | HFTD Tier 2 | Distribution | 2013-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014938 | 405130454 | Molding | HFTD Tier 3 | Distribution | 2013-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014939 | 405130465 | Guy | HFTD Tier 3 | Distribution | 2013-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014940 | 405130467 | Guy | HFTD Tier 3 | Distribution | 2013-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014941 | 405130484 | Molding | HFTD Tier 3 | Distribution | 2013-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014942 | 405130498 | High Sign | HFTD Tier 3 | Distribution | 2013-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014943 | 405130500 | High Sign | HFTD Tier 3 | Distribution | 2013-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014944 | 405130502 | High Sign | HFTD Tier 3 | Distribution | 2013-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014945 | 405130693 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2013-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014946 | 405130817 | Insulator | HFTD Tier 3 | Distribution | 2013-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014947 | 405131143 | Molding | HFTD Tier 3 | Distribution | 2013-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014948 | 405131144 | High Sign | HFTD Tier 3 | Distribution | 2013-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014949 | 405131148 | Molding | HFTD Tier 3 | Distribution | 2013-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014950 | 405131159 | High Sign | HFTD Tier 3 | Distribution | 2013-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014951 | 405131162 | Molding | HFTD Tier 3 | Distribution | 2013-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014952 | 405131183 | Ground | HFTD Tier 3 | Distribution | 2013-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014953 | 405133821 | High Sign | HFTD Tier 2 | Distribution | 2013-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014954 | 405134151 | Molding | HFTD Tier 2 | Distribution | 2013-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014955 | 405134298 | Molding | HFTD Tier 3 | Distribution | 2013-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014956 | 405134305 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014957 | 405134685 | Molding | HFTD Tier 3 | Distribution | 2013-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014958 | 405134691 | Molding | HFTD Tier 3 | Distribution | 2013-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014959 | 405138086 | Riser/Conduit | HFTD Tier 2 | Distribution | 2013-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014960 | 405138091 | High Sign | HFTD Tier 3 | Distribution | 2013-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014961 | 405138095 | Guy | HFTD Tier 2 | Distribution | 2013-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014962 | 405139445 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014963 | 405141005 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014964 | 405141007 | Molding | HFTD Tier 3 | Distribution | 2013-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014965 | 405141014 | High Sign | HFTD Tier 3 | Distribution | 2013-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014966 | 405143025 | Molding | HFTD Tier 3 | Distribution | 2013-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014967 | 405143031 | High Sign | HFTD Tier 3 | Distribution | 2013-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014968 | 405143032 | Molding | HFTD Tier 3 | Distribution | 2013-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014969 | 405143039 | Molding | HFTD Tier 3 | Distribution | 2013-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014970 | 405143064 | High Sign | HFTD Tier 3 | Distribution | 2013-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014971 | 405144259 | High Sign | HFTD Tier 2 | Distribution | 2013-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014972 | 405144269 | High Sign | HFTD Tier 2 | Distribution | 2013-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014973 | 405144278 | High Sign | HFTD Tier 2 | Distribution | 2013-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014974 | 405144280 | High Sign | HFTD Tier 2 | Distribution | 2013-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014975 | 405144281 | High Sign | HFTD Tier 2 | Distribution | 2013-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014976 | 405144284 | High Sign | HFTD Tier 2 | Distribution | 2013-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014977 | 405144691 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014978 | 405144738 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014979 | 405144741 | Guy | HFTD Tier 3 | Distribution | 2013-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014980 | 405144744 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014981 | 405144754 | Molding | HFTD Tier 3 | Distribution | 2013-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014982 | 405144757 | High Sign | HFTD Tier 3 | Distribution | 2013-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014983 | 405144759 | Guy | HFTD Tier 3 | Distribution | 2013-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014984 | 405144760 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014985 | 405144791 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014986 | 405144808 | Guy | HFTD Tier 3 | Distribution | 2013-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014987 | 405144824 | Guy | HFTD Tier 3 | Distribution | 2013-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014988 | 405144826 | Molding | HFTD Tier 3 | Distribution | 2013-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014989 | 405144921 | Guy | HFTD Tier 3 | Distribution | 2013-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014990 | 405145067 | Molding | HFTD Tier 3 | Distribution | 2013-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014991 | 405145068 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014992 | 405145092 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014993 | 405145134 | Molding | HFTD Tier 3 | Distribution | 2013-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014994 | 405145147 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014995 | 405145165 | High Sign | HFTD Tier 3 | Distribution | 2013-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014996 | 405145170 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014997 | 405145646 | High Sign | HFTD Tier 3 | Distribution | 2013-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014998 | 405145662 | Molding | HFTD Tier 3 | Distribution | 2013-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130014999 | 405145681 | High Sign | HFTD Tier 3 | Distribution | 2013-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015000 | 405145688 | Molding | HFTD Tier 3 | Distribution | 2013-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015001 | 405145692 | High Sign | HFTD Tier 3 | Distribution | 2013-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015002 | 405147030 | High Sign | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015003 | 405147041 | High Sign | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015004 | 405147058 | High Sign | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015005 | 405148290 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015006 | 405148492 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015007 | 405148500 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015008 | 405148543 | Molding | HFTD Tier 2 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015009 | 405148552 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015010 | 405148979 | Guy | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015011 | 405148990 | High Sign | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015012 | 405149126 | High Sign | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015013 | 405149136 | High Sign | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015014 | 405149144 | High Sign | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015015 | 405149178 | High Sign | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015016 | 405149184 | Molding | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015017 | 405149542 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015018 | 405149543 | Guy | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015019 | 405149544 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015020 | 405149546 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015021 | 405150240 | High Sign | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015022 | 405150253 | High Sign | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015023 | 405150255 | High Sign | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015024 | 405150742 | High Sign | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015025 | 405152065 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015026 | 405152136 | Molding | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015027 | 405152219 | Guy | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015028 | 405152223 | High Sign | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015029 | 405152246 | High Sign | HFTD Tier 2 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015030 | 405152248 | High Sign | HFTD Tier 2 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015031 | 405152320 | Guy | HFTD Tier 2 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015032 | 405152436 | Guy | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015033 | 405152437 | Guy | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015034 | 405152446 | High Sign | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015035 | 405152450 | High Sign | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015036 | 405153221 | Molding | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015037 | 405153262 | Molding | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015038 | 405153268 | High Sign | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015039 | 405153294 | Molding | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015040 | 405153304 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015041 | 405153313 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015042 | 405153315 | Molding | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015043 | 405153341 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015044 | 405153360 | Ground | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015045 | 405153361 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015046 | 405153363 | Guy | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015047 | 405153382 | High Sign | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015048 | 405153387 | Guy | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015049 | 405153442 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015050 | 405153457 | Ground | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015051 | 405153472 | Guy | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015052 | 405153473 | Guy | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015053 | 405153514 | Molding | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015054 | 405153523 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015055 | 405153535 | Molding | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015056 | 405153557 | Molding | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015057 | 405153558 | Guy | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015058 | 405153560 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015059 | 405153575 | High Sign | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015060 | 405156023 | Guy | HFTD Tier 2 | Distribution | 2013-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015061 | 405156028 | Bond | HFTD Tier 2 | Distribution | 2013-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015062 | 405156119 | High Sign | HFTD Tier 3 | Distribution | 2013-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015063 | 405156150 | High Sign | HFTD Tier 3 | Distribution | 2013-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015064 | 405156213 | Molding | HFTD Tier 3 | Distribution | 2013-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015065 | 405156217 | High Sign | HFTD Tier 3 | Distribution | 2013-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015066 | 405156240 | Molding | HFTD Tier 3 | Distribution | 2013-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015067 | 405156425 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015068 | 405156446 | Molding | HFTD Tier 2 | Distribution | 2013-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015069 | 405156467 | High Sign | HFTD Tier 2 | Distribution | 2013-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015070 | 405156546 | High Sign | HFTD Tier 3 | Distribution | 2013-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015071 | 405156550 | Guy | HFTD Tier 3 | Distribution | 2013-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015072 | 405156552 | Molding | HFTD Tier 3 | Distribution | 2013-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015073 | 405157399 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015074 | 405157531 | High Sign | HFTD Tier 3 | Distribution | 2013-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015075 | 405157555 | Guy | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015076 | 405157556 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015077 | 405157621 | Guy | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015078 | 405157641 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015079 | 405157876 | High Sign | HFTD Tier 3 | Distribution | 2013-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015080 | 405157881 | Guy | HFTD Tier 3 | Distribution | 2013-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015081 | 405157884 | Molding | HFTD Tier 3 | Distribution | 2013-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015082 | 405159328 | Molding | HFTD Tier 3 | Distribution | 2013-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015083 | 405160238 | Molding | HFTD Tier 3 | Distribution | 2013-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015084 | 405162603 | Molding | HFTD Tier 2 | Distribution | 2013-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015085 | 405164220 | High Sign | HFTD Tier 3 | Distribution | 2013-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015086 | 405164235 | Molding | HFTD Tier 3 | Distribution | 2013-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015087 | 405164238 | High Sign | HFTD Tier 3 | Distribution | 2013-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015088 | 405164253 | Molding | HFTD Tier 3 | Distribution | 2013-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015089 | 405165354 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015090 | 405169760 | High Sign | HFTD Tier 3 | Distribution | 2013-04-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015091 | 405170140 | Molding | HFTD Tier 3 | Distribution | 2013-04-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015092 | 405171877 | Molding | HFTD Tier 2 | Distribution | 2013-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015093 | 405171888 | Molding | HFTD Tier 2 | Distribution | 2013-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015094 | 405171895 | Guy | HFTD Tier 2 | Distribution | 2013-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015095 | 405172336 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015096 | 405172693 | Molding | HFTD Tier 3 | Distribution | 2013-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015097 | 405173056 | High Sign | HFTD Tier 3 | Distribution | 2013-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015098 | 405173075 | High Sign | HFTD Tier 3 | Distribution | 2013-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015099 | 405173124 | Molding | HFTD Tier 3 | Distribution | 2013-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015100 | 405173136 | Molding | HFTD Tier 3 | Distribution | 2013-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015101 | 405173139 | Molding | HFTD Tier 3 | Distribution | 2013-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015102 | 405173153 | Molding | HFTD Tier 3 | Distribution | 2013-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015103 | 405174012 | Molding | HFTD Tier 2 | Distribution | 2013-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015104 | 405175003 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015105 | 405175157 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015106 | 405175181 | High Sign | HFTD Tier 3 | Distribution | 2013-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015107 | 405175422 | High Sign | HFTD Tier 3 | Distribution | 2013-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015108 | 405180421 | Molding | HFTD Tier 2 | Distribution | 2013-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015109 | 405180527 | High Sign | HFTD Tier 3 | Distribution | 2013-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015110 | 405180546 | Guy | HFTD Tier 3 | Distribution | 2013-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015111 | 405180782 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2013-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015112 | 405180794 | Molding | HFTD Tier 2 | Distribution | 2013-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015113 | 405180803 | Molding | HFTD Tier 2 | Distribution | 2013-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015114 | 405181763 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015115 | 405182422 | Guy | HFTD Tier 3 | Distribution | 2013-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015116 | 405183373 | Molding | HFTD Tier 2 | Distribution | 2013-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015117 | 405183376 | Molding | HFTD Tier 2 | Distribution | 2013-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015118 | 405183381 | High Sign | HFTD Tier 2 | Distribution | 2013-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015119 | 405183407 | Molding | HFTD Tier 2 | Distribution | 2013-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015120 | 405183629 | Guy | HFTD Tier 2 | Distribution | 2013-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015121 | 405183648 | Guy | HFTD Tier 3 | Distribution | 2013-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015122 | 405185160 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-05-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015123 | 405185171 | Guy | HFTD Tier 3 | Distribution | 2013-05-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015124 | 405185181 | Molding | HFTD Tier 3 | Distribution | 2013-05-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015125 | 405186819 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-05-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015126 | 405186891 | High Sign | HFTD Tier 2 | Distribution | 2013-05-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015127 | 405188767 | High Sign | HFTD Tier 3 | Distribution | 2013-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015128 | 405188769 | Molding | HFTD Tier 3 | Distribution | 2013-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015129 | 405188805 | Guy | HFTD Tier 3 | Distribution | 2013-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015130 | 405188809 | High Sign | HFTD Tier 3 | Distribution | 2013-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015131 | 405188813 | High Sign | HFTD Tier 3 | Distribution | 2013-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015132 | 405191657 | Molding | HFTD Tier 3 | Distribution | 2013-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015133 | 405194006 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015134 | 405194010 | High Sign | HFTD Tier 3 | Distribution | 2013-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015135 | 405199397 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015136 | 405201596 | High Sign | HFTD Tier 3 | Distribution | 2013-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015137 | 405201598 | High Sign | HFTD Tier 3 | Distribution | 2013-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015138 | 405201620 | High Sign | HFTD Tier 3 | Distribution | 2013-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015139 | 405201660 | Molding | HFTD Tier 3 | Distribution | 2013-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015140 | 405201661 | Molding | HFTD Tier 3 | Distribution | 2013-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015141 | 405201662 | High Sign | HFTD Tier 3 | Distribution | 2013-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015142 | 405201802 | High Sign | HFTD Tier 2 | Distribution | 2013-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015143 | 405201809 | Molding | HFTD Tier 2 | Distribution | 2013-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015144 | 405201837 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015145 | 405202657 | High Sign | HFTD Tier 2 | Distribution | 2013-05-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015146 | 405205105 | Molding | HFTD Tier 3 | Distribution | 2013-05-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015147 | 405205111 | Guy | HFTD Tier 2 | Distribution | 2013-05-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015148 | 405211938 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015149 | 405215937 | Riser/Conduit | HFTD Tier 2 | Distribution | 2013-05-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015150 | 405218109 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-05-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015151 | 405219357 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015152 | 405219364 | High Sign | HFTD Tier 3 | Distribution | 2013-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015153 | 405219365 | High Sign | HFTD Tier 3 | Distribution | 2013-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015154 | 405219377 | High Sign | HFTD Tier 3 | Distribution | 2013-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015155 | 405219555 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015156 | 405219933 | High Sign | HFTD Tier 2 | Distribution | 2013-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015157 | 405221464 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015158 | 405221604 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015159 | 405221623 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015160 | 405221627 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015161 | 405221636 | Molding | HFTD Tier 3 | Distribution | 2013-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015162 | 405221666 | High Sign | HFTD Tier 3 | Distribution | 2013-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015163 | 405221667 | Molding | HFTD Tier 3 | Distribution | 2013-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015164 | 405221668 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015165 | 405221669 | High Sign | HFTD Tier 3 | Distribution | 2013-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015166 | 405221671 | High Sign | HFTD Tier 3 | Distribution | 2013-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015167 | 405221683 | High Sign | HFTD Tier 3 | Distribution | 2013-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015168 | 405223294 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015169 | 405223298 | Guy | HFTD Tier 3 | Distribution | 2013-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015170 | 405223301 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015171 | 405225406 | Molding | HFTD Tier 3 | Distribution | 2013-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015172 | 405225411 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015173 | 405225419 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015174 | 405225422 | Molding | HFTD Tier 3 | Distribution | 2013-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015175 | 405225425 | High Sign | HFTD Tier 3 | Distribution | 2013-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015176 | 405225427 | Molding | HFTD Tier 3 | Distribution | 2013-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015177 | 405225432 | High Sign | HFTD Tier 3 | Distribution | 2013-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015178 | 405228963 | High Sign | HFTD Tier 3 | Distribution | 2013-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015179 | 405230605 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015180 | 405230636 | Ground | HFTD Tier 2 | Distribution | 2013-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015181 | 405232109 | Molding | HFTD Tier 3 | Distribution | 2013-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015182 | 405232115 | High Sign | HFTD Tier 3 | Distribution | 2013-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015183 | 405232118 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015184 | 405233511 | Guy | HFTD Tier 2 | Distribution | 2013-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015185 | 405233518 | High Sign | HFTD Tier 2 | Distribution | 2013-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015186 | 405233633 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015187 | 405235212 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015188 | 405235216 | Molding | HFTD Tier 2 | Distribution | 2013-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015189 | 405235217 | High Sign | HFTD Tier 2 | Distribution | 2013-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015190 | 405235219 | Molding | HFTD Tier 2 | Distribution | 2013-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015191 | 405235549 | Molding | HFTD Tier 3 | Distribution | 2013-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015192 | 405235557 | Molding | HFTD Tier 3 | Distribution | 2013-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015193 | 405235610 | Molding | HFTD Tier 3 | Distribution | 2013-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015194 | 405235623 | Molding | HFTD Tier 3 | Distribution | 2013-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015195 | 405236640 | High Sign | HFTD Tier 2 | Distribution | 2013-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015196 | 405236718 | High Sign | HFTD Tier 2 | Distribution | 2013-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015197 | 405236738 | Molding | HFTD Tier 2 | Distribution | 2013-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015198 | 405236739 | Molding | HFTD Tier 2 | Distribution | 2013-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015199 | 405236755 | Guy | HFTD Tier 2 | Distribution | 2013-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015200 | 405236787 | Guy | HFTD Tier 2 | Distribution | 2013-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015201 | 405238298 | High Sign | HFTD Tier 2 | Distribution | 2013-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015202 | 405238303 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015203 | 405238456 | High Sign | HFTD Tier 3 | Distribution | 2013-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015204 | 405238487 | Molding | HFTD Tier 3 | Distribution | 2013-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015205 | 405238499 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015206 | 405238502 | Molding | HFTD Tier 3 | Distribution | 2013-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015207 | 405238503 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015208 | 405238505 | High Sign | HFTD Tier 3 | Distribution | 2013-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015209 | 405238512 | Molding | HFTD Tier 3 | Distribution | 2013-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015210 | 405238528 | Molding | HFTD Tier 3 | Distribution | 2013-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015211 | 405239504 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015212 | 405240107 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015213 | 405241363 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015214 | 405241383 | High Sign | HFTD Tier 2 | Distribution | 2013-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015215 | 405241407 | Molding | HFTD Tier 2 | Distribution | 2013-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015216 | 405241432 | High Sign | HFTD Tier 2 | Distribution | 2013-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015217 | 405241462 | Guy | HFTD Tier 2 | Distribution | 2013-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015218 | 405241464 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2013-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015219 | 405241861 | Molding | HFTD Tier 3 | Distribution | 2013-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015220 | 405241868 | High Sign | HFTD Tier 3 | Distribution | 2013-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015221 | 405241872 | High Sign | HFTD Tier 3 | Distribution | 2013-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015222 | 405241881 | Molding | HFTD Tier 3 | Distribution | 2013-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015223 | 405241886 | Molding | HFTD Tier 3 | Distribution | 2013-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015224 | 405241891 | High Sign | HFTD Tier 3 | Distribution | 2013-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015225 | 405241892 | Molding | HFTD Tier 3 | Distribution | 2013-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015226 | 405241895 | High Sign | HFTD Tier 3 | Distribution | 2013-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015227 | 405241896 | High Sign | HFTD Tier 3 | Distribution | 2013-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015228 | 405241904 | Guy | HFTD Tier 3 | Distribution | 2013-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015229 | 405241909 | Connector | HFTD Tier 3 | Distribution | 2013-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015230 | 405241913 | Guy | HFTD Tier 3 | Distribution | 2013-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015231 | 405241915 | Insulator | HFTD Tier 3 | Distribution | 2013-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015232 | 405242978 | High Sign | HFTD Tier 3 | Distribution | 2013-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015233 | 405242992 | High Sign | HFTD Tier 3 | Distribution | 2013-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015234 | 405243048 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015235 | 405243847 | Guy | HFTD Tier 2 | Distribution | 2013-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015236 | 405245521 | High Sign | HFTD Tier 2 | Distribution | 2013-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015237 | 405245527 | High Sign | HFTD Tier 2 | Distribution | 2013-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015238 | 405245530 | High Sign | HFTD Tier 2 | Distribution | 2013-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015239 | 405245534 | High Sign | HFTD Tier 2 | Distribution | 2013-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015240 | 405245547 | High Sign | HFTD Tier 2 | Distribution | 2013-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015241 | 405245551 | High Sign | HFTD Tier 2 | Distribution | 2013-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015242 | 405245853 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015243 | 405245867 | Molding | HFTD Tier 2 | Distribution | 2013-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015244 | 405245879 | Riser/Conduit | HFTD Tier 2 | Distribution | 2013-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015245 | 405245880 | Molding | HFTD Tier 2 | Distribution | 2013-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015246 | 405248291 | High Sign | HFTD Tier 2 | Distribution | 2013-05-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015247 | 405248307 | High Sign | HFTD Tier 2 | Distribution | 2013-05-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015248 | 405248448 | High Sign | HFTD Tier 2 | Distribution | 2013-05-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015249 | 405248753 | High Sign | HFTD Tier 2 | Distribution | 2013-05-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015250 | 405249038 | High Sign | HFTD Tier 3 | Distribution | 2013-05-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015251 | 405250192 | High Sign | HFTD Tier 3 | Distribution | 2013-05-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015252 | 405250195 | Molding | HFTD Tier 3 | Distribution | 2013-05-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015253 | 405250200 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-05-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015254 | 405251409 | High Sign | HFTD Tier 2 | Distribution | 2013-05-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015255 | 405251425 | High Sign | HFTD Tier 2 | Distribution | 2013-05-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015256 | 405251853 | High Sign | HFTD Tier 2 | Distribution | 2013-05-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015257 | 405251864 | Molding | HFTD Tier 2 | Distribution | 2013-05-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015258 | 405251873 | Molding | HFTD Tier 2 | Distribution | 2013-05-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015259 | 405253378 | Molding | HFTD Tier 3 | Distribution | 2013-05-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015260 | 405253389 | High Sign | HFTD Tier 3 | Distribution | 2013-05-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015261 | 405253391 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-05-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015262 | 405253394 | Molding | HFTD Tier 3 | Distribution | 2013-05-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015263 | 405253406 | Molding | HFTD Tier 3 | Distribution | 2013-05-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015264 | 405253408 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-05-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015265 | 405253410 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-05-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015266 | 405253457 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-05-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015267 | 405253465 | Guy | HFTD Tier 3 | Distribution | 2013-05-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015268 | 405253488 | High Sign | HFTD Tier 3 | Distribution | 2013-05-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015269 | 405253514 | Guy | HFTD Tier 3 | Distribution | 2013-05-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015270 | 405255138 | Molding | HFTD Tier 2 | Distribution | 2013-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015271 | 405257048 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015272 | 405257096 | Molding | HFTD Tier 2 | Distribution | 2013-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015273 | 405257435 | High Sign | HFTD Tier 3 | Distribution | 2013-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015274 | 405257520 | Guy | HFTD Tier 3 | Distribution | 2013-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015275 | 405257533 | Guy | HFTD Tier 3 | Distribution | 2013-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015276 | 405257582 | High Sign | HFTD Tier 3 | Distribution | 2013-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015277 | 405257609 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015278 | 405257642 | Molding | HFTD Tier 3 | Distribution | 2013-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015279 | 405261863 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015280 | 405261870 | High Sign | HFTD Tier 3 | Distribution | 2013-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015281 | 405261886 | Riser/Conduit | HFTD Tier 2 | Distribution | 2013-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015282 | 405261918 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015283 | 405261921 | Molding | HFTD Tier 2 | Distribution | 2013-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015284 | 405261922 | Riser/Conduit | HFTD Tier 2 | Distribution | 2013-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015285 | 405261927 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015286 | 405261933 | Riser/Conduit | HFTD Tier 2 | Distribution | 2013-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015287 | 405261934 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015288 | 405261939 | Riser/Conduit | HFTD Tier 2 | Distribution | 2013-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015289 | 405261950 | Molding | HFTD Tier 2 | Distribution | 2013-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015290 | 405261951 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015291 | 405264200 | Molding | HFTD Tier 2 | Distribution | 2013-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015292 | 405264296 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015293 | 405264301 | Molding | HFTD Tier 3 | Distribution | 2013-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015294 | 405264309 | High Sign | HFTD Tier 3 | Distribution | 2013-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015295 | 405264325 | Molding | HFTD Tier 3 | Distribution | 2013-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015296 | 405264607 | Molding | HFTD Tier 2 | Distribution | 2013-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015297 | 405264616 | Insulator | HFTD Tier 2 | Distribution | 2013-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015298 | 405264622 | Molding | HFTD Tier 2 | Distribution | 2013-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015299 | 405264655 | High Sign | HFTD Tier 2 | Distribution | 2013-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015300 | 405264679 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015301 | 405264692 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015302 | 405265679 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015303 | 405266038 | Guy | HFTD Tier 2 | Distribution | 2013-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015304 | 405266496 | High Sign | HFTD Tier 2 | Distribution | 2013-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015305 | 405268256 | Molding | HFTD Tier 3 | Distribution | 2013-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015306 | 405268261 | High Sign | HFTD Tier 3 | Distribution | 2013-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015307 | 405268517 | Molding | HFTD Tier 2 | Distribution | 2013-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015308 | 405269153 | High Sign | HFTD Tier 2 | Distribution | 2013-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015309 | 405271467 | High Sign | HFTD Tier 3 | Distribution | 2013-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015310 | 405271835 | High Sign | HFTD Tier 3 | Distribution | 2013-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015311 | 405271875 | Molding | HFTD Tier 3 | Distribution | 2013-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015312 | 405275037 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015313 | 405275038 | Molding | HFTD Tier 3 | Distribution | 2013-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015314 | 405275045 | Molding | HFTD Tier 3 | Distribution | 2013-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015315 | 405275053 | Molding | HFTD Tier 3 | Distribution | 2013-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015316 | 405275058 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015317 | 405276008 | Molding | HFTD Tier 2 | Distribution | 2013-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015318 | 405276030 | High Sign | HFTD Tier 2 | Distribution | 2013-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015319 | 405276041 | Molding | HFTD Tier 2 | Distribution | 2013-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015320 | 405276043 | High Sign | HFTD Tier 2 | Distribution | 2013-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015321 | 405276052 | Molding | HFTD Tier 2 | Distribution | 2013-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015322 | 405276054 | High Sign | HFTD Tier 2 | Distribution | 2013-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015323 | 405279128 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015324 | 405279129 | Molding | HFTD Tier 3 | Distribution | 2013-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015325 | 405279139 | Molding | HFTD Tier 3 | Distribution | 2013-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015326 | 405279151 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015327 | 405279152 | High Sign | HFTD Tier 3 | Distribution | 2013-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015328 | 405279154 | High Sign | HFTD Tier 3 | Distribution | 2013-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015329 | 405279161 | High Sign | HFTD Tier 3 | Distribution | 2013-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015330 | 405279168 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015331 | 405279176 | Molding | HFTD Tier 3 | Distribution | 2013-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015332 | 405281198 | High Sign | HFTD Tier 3 | Distribution | 2013-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015333 | 405283383 | Molding | HFTD Tier 3 | Distribution | 2013-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015334 | 405283384 | High Sign | HFTD Tier 3 | Distribution | 2013-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015335 | 405283402 | Guy | HFTD Tier 3 | Distribution | 2013-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015336 | 405283404 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015337 | 405284256 | Molding | HFTD Tier 3 | Distribution | 2013-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015338 | 405285776 | Molding | HFTD Tier 3 | Distribution | 2013-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015339 | 405285800 | Molding | HFTD Tier 3 | Distribution | 2013-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015340 | 405285803 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015341 | 405285986 | High Sign | HFTD Tier 3 | Distribution | 2013-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015342 | 405285990 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015343 | 405285998 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015344 | 405286005 | High Sign | HFTD Tier 3 | Distribution | 2013-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015345 | 405286020 | High Sign | HFTD Tier 3 | Distribution | 2013-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015346 | 405286027 | Molding | HFTD Tier 3 | Distribution | 2013-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015347 | 405286029 | High Sign | HFTD Tier 3 | Distribution | 2013-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015348 | 405286037 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015349 | 405286038 | High Sign | HFTD Tier 3 | Distribution | 2013-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015350 | 405286042 | High Sign | HFTD Tier 3 | Distribution | 2013-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015351 | 405286046 | Molding | HFTD Tier 3 | Distribution | 2013-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015352 | 405286051 | Molding | HFTD Tier 3 | Distribution | 2013-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015353 | 405286062 | Molding | HFTD Tier 3 | Distribution | 2013-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015354 | 405286071 | High Sign | HFTD Tier 3 | Distribution | 2013-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015355 | 405286086 | High Sign | HFTD Tier 3 | Distribution | 2013-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015356 | 405286847 | Molding | HFTD Tier 2 | Distribution | 2013-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015357 | 405288025 | High Sign | HFTD Tier 3 | Distribution | 2013-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015358 | 405288031 | High Sign | HFTD Tier 3 | Distribution | 2013-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015359 | 405291952 | High Sign | HFTD Tier 3 | Distribution | 2013-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015360 | 405291975 | Molding | HFTD Tier 3 | Distribution | 2013-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015361 | 405292071 | High Sign | HFTD Tier 2 | Distribution | 2013-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015362 | 405292980 | Molding | HFTD Tier 2 | Distribution | 2013-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015363 | 405295006 | Molding | HFTD Tier 3 | Distribution | 2013-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015364 | 405295022 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015365 | 405295025 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015366 | 405295028 | High Sign | HFTD Tier 3 | Distribution | 2013-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015367 | 405295039 | High Sign | HFTD Tier 3 | Distribution | 2013-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015368 | 405295048 | Molding | HFTD Tier 3 | Distribution | 2013-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015369 | 405295057 | Molding | HFTD Tier 3 | Distribution | 2013-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015370 | 405295059 | Molding | HFTD Tier 3 | Distribution | 2013-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015371 | 405296241 | High Sign | HFTD Tier 2 | Distribution | 2013-06-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015372 | 405296776 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-06-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015373 | 405298530 | High Sign | HFTD Tier 3 | Distribution | 2013-06-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015374 | 405298549 | High Sign | HFTD Tier 3 | Distribution | 2013-06-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015375 | 405298553 | Molding | HFTD Tier 3 | Distribution | 2013-06-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015376 | 405300326 | Guy | HFTD Tier 2 | Distribution | 2013-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015377 | 405301309 | High Sign | HFTD Tier 2 | Distribution | 2013-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015378 | 405301961 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015379 | 405301962 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015380 | 405301983 | High Sign | HFTD Tier 3 | Distribution | 2013-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015381 | 405301984 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015382 | 405301987 | High Sign | HFTD Tier 3 | Distribution | 2013-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015383 | 405301992 | Molding | HFTD Tier 3 | Distribution | 2013-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015384 | 405301995 | High Sign | HFTD Tier 3 | Distribution | 2013-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015385 | 405301997 | Molding | HFTD Tier 3 | Distribution | 2013-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015386 | 405301998 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015387 | 405302000 | Molding | HFTD Tier 3 | Distribution | 2013-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015388 | 405302001 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015389 | 405304977 | High Sign | HFTD Tier 3 | Distribution | 2013-06-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015390 | 405304978 | Molding | HFTD Tier 3 | Distribution | 2013-06-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015391 | 405307899 | Molding | HFTD Tier 2 | Distribution | 2013-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015392 | 405307913 | High Sign | HFTD Tier 2 | Distribution | 2013-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015393 | 405308353 | High Sign | HFTD Tier 3 | Distribution | 2013-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015394 | 405308357 | Guy | HFTD Tier 3 | Distribution | 2013-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015395 | 405308358 | High Sign | HFTD Tier 3 | Distribution | 2013-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015396 | 405308362 | High Sign | HFTD Tier 3 | Distribution | 2013-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015397 | 405308364 | Guy | HFTD Tier 3 | Distribution | 2013-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015398 | 405308370 | Guy | HFTD Tier 3 | Distribution | 2013-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015399 | 405308375 | High Sign | HFTD Tier 3 | Distribution | 2013-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015400 | 405308394 | High Sign | HFTD Tier 3 | Distribution | 2013-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015401 | 405308516 | Guy | HFTD Tier 3 | Distribution | 2013-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015402 | 405308531 | Molding | HFTD Tier 3 | Distribution | 2013-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015403 | 405309616 | Molding | HFTD Tier 3 | Distribution | 2013-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015404 | 405309622 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015405 | 405309929 | Molding | HFTD Tier 3 | Distribution | 2013-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015406 | 405309948 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015407 | 405309958 | Molding | HFTD Tier 3 | Distribution | 2013-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015408 | 405311849 | Guy | HFTD Tier 3 | Distribution | 2013-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015409 | 405311850 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015410 | 405311910 | Guy | HFTD Tier 3 | Distribution | 2013-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015411 | 405312467 | Molding | HFTD Tier 2 | Distribution | 2013-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015412 | 405312485 | High Sign | HFTD Tier 2 | Distribution | 2013-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015413 | 405312991 | Guy | HFTD Tier 3 | Distribution | 2013-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015414 | 405314820 | Molding | HFTD Tier 3 | Distribution | 2013-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015415 | 405314826 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015416 | 405314843 | Guy | HFTD Tier 3 | Distribution | 2013-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015417 | 405315523 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015418 | 405315586 | Guy | HFTD Tier 3 | Distribution | 2013-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015419 | 405315596 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015420 | 405317933 | Molding | HFTD Tier 2 | Distribution | 2013-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015421 | 405318397 | Molding | HFTD Tier 3 | Distribution | 2013-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015422 | 405318789 | Molding | HFTD Tier 3 | Distribution | 2013-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015423 | 405318791 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015424 | 405318793 | High Sign | HFTD Tier 3 | Distribution | 2013-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015425 | 405318797 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015426 | 405318799 | Molding | HFTD Tier 3 | Distribution | 2013-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015427 | 405318805 | High Sign | HFTD Tier 3 | Distribution | 2013-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015428 | 405319028 | Guy | HFTD Tier 3 | Distribution | 2013-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015429 | 405319031 | Guy | HFTD Tier 3 | Distribution | 2013-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015430 | 405319298 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015431 | 405320145 | High Sign | HFTD Tier 3 | Distribution | 2013-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015432 | 405320148 | Guy | HFTD Tier 3 | Distribution | 2013-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015433 | 405320164 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015434 | 405320165 | Molding | HFTD Tier 3 | Distribution | 2013-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015435 | 405320171 | Molding | HFTD Tier 3 | Distribution | 2013-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015436 | 405321296 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015437 | 405322261 | Molding | HFTD Tier 2 | Distribution | 2013-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015438 | 405322288 | High Sign | HFTD Tier 2 | Distribution | 2013-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015439 | 405322505 | High Sign | HFTD Tier 3 | Distribution | 2013-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015440 | 405322513 | High Sign | HFTD Tier 3 | Distribution | 2013-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015441 | 405322549 | Guy | HFTD Tier 2 | Distribution | 2013-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015442 | 405323850 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015443 | 405323876 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015444 | 405324205 | Molding | HFTD Tier 3 | Distribution | 2013-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015445 | 405324250 | High Sign | HFTD Tier 3 | Distribution | 2013-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015446 | 405325194 | Guy | HFTD Tier 2 | Distribution | 2013-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015447 | 405325196 | Guy | HFTD Tier 2 | Distribution | 2013-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015448 | 405325200 | Guy | HFTD Tier 2 | Distribution | 2013-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015449 | 405325205 | Guy | HFTD Tier 2 | Distribution | 2013-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015450 | 405325398 | Molding | HFTD Tier 3 | Distribution | 2013-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015451 | 405327363 | Molding | HFTD Tier 3 | Distribution | 2013-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015452 | 405327368 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015453 | 405327369 | Molding | HFTD Tier 3 | Distribution | 2013-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015454 | 405327372 | Molding | HFTD Tier 3 | Distribution | 2013-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015455 | 405327380 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015456 | 405327382 | Molding | HFTD Tier 3 | Distribution | 2013-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015457 | 405327390 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015458 | 405327395 | Molding | HFTD Tier 3 | Distribution | 2013-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015459 | 405329922 | Molding | HFTD Tier 2 | Distribution | 2013-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015460 | 405329923 | High Sign | HFTD Tier 2 | Distribution | 2013-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015461 | 405330232 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015462 | 405332881 | Molding | HFTD Tier 3 | Distribution | 2013-07-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015463 | 405334476 | Molding | HFTD Tier 2 | Distribution | 2013-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015464 | 405334533 | Molding | HFTD Tier 2 | Distribution | 2013-07-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015465 | 405334559 | Molding | HFTD Tier 2 | Distribution | 2013-07-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015466 | 405334564 | Molding | HFTD Tier 2 | Distribution | 2013-07-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015467 | 405335212 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-07-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015468 | 405335227 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-07-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015469 | 405335229 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-07-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015470 | 405337398 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-07-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015471 | 405337475 | Guy | HFTD Tier 3 | Distribution | 2013-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015472 | 405337490 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015473 | 405337529 | Guy | HFTD Tier 3 | Distribution | 2013-07-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015474 | 405343626 | Ground | HFTD Tier 2 | Distribution | 2013-07-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015475 | 405345619 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015476 | 405345716 | Molding | HFTD Tier 3 | Distribution | 2013-07-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015477 | 405346988 | High Sign | HFTD Tier 3 | Distribution | 2013-07-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015478 | 405346998 | Molding | HFTD Tier 3 | Distribution | 2013-07-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015479 | 405347196 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-07-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015480 | 405347205 | Guy | HFTD Tier 3 | Distribution | 2013-07-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015481 | 405347210 | Guy | HFTD Tier 3 | Distribution | 2013-07-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015482 | 405348543 | Molding | HFTD Tier 3 | Distribution | 2013-07-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015483 | 405348581 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-07-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015484 | 405348600 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-07-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015485 | 405348610 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-07-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015486 | 405348635 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015487 | 405350700 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-07-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015488 | 405351793 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015489 | 405351830 | Guy | HFTD Tier 3 | Distribution | 2013-07-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015490 | 405351916 | Molding | HFTD Tier 3 | Distribution | 2013-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015491 | 405351948 | Molding | HFTD Tier 3 | Distribution | 2013-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015492 | 405352885 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015493 | 405355459 | High Sign | HFTD Tier 3 | Distribution | 2013-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015494 | 405355758 | Molding | HFTD Tier 3 | Distribution | 2013-07-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015495 | 405355759 | High Sign | HFTD Tier 3 | Distribution | 2013-07-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015496 | 405355760 | Molding | HFTD Tier 3 | Distribution | 2013-07-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015497 | 405355767 | Molding | HFTD Tier 3 | Distribution | 2013-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015498 | 405355770 | High Sign | HFTD Tier 3 | Distribution | 2013-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015499 | 405355825 | Molding | HFTD Tier 3 | Distribution | 2013-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015500 | 405355837 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015501 | 405357081 | Molding | HFTD Tier 2 | Distribution | 2013-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015502 | 405357083 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015503 | 405357093 | Insulator | HFTD Tier 2 | Distribution | 2013-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015504 | 405358190 | High Sign | HFTD Tier 3 | Distribution | 2013-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015505 | 405358632 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015506 | 405358960 | High Sign | HFTD Tier 2 | Distribution | 2013-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015507 | 405358968 | High Sign | HFTD Tier 2 | Distribution | 2013-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015508 | 405359055 | High Sign | HFTD Tier 3 | Distribution | 2013-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015509 | 405359057 | Molding | HFTD Tier 3 | Distribution | 2013-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015510 | 405359349 | High Sign | HFTD Tier 3 | Distribution | 2013-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015511 | 405359357 | High Sign | HFTD Tier 3 | Distribution | 2013-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015512 | 405359399 | Molding | HFTD Tier 3 | Distribution | 2013-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015513 | 405359400 | Ground | HFTD Tier 3 | Distribution | 2013-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015514 | 405359446 | Molding | HFTD Tier 3 | Distribution | 2013-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015515 | 405359471 | Molding | HFTD Tier 3 | Distribution | 2013-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015516 | 405360374 | Molding | HFTD Tier 2 | Distribution | 2013-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015517 | 405362240 | Guy | HFTD Tier 3 | Distribution | 2013-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015518 | 405362389 | Guy | HFTD Tier 3 | Distribution | 2013-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015519 | 405364036 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015520 | 405365090 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015521 | 405365094 | Molding | HFTD Tier 3 | Distribution | 2013-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015522 | 405365388 | Molding | HFTD Tier 3 | Distribution | 2013-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015523 | 405365396 | High Sign | HFTD Tier 3 | Distribution | 2013-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015524 | 405365403 | High Sign | HFTD Tier 3 | Distribution | 2013-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015525 | 405365404 | Molding | HFTD Tier 3 | Distribution | 2013-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015526 | 405366008 | Pole Tag | HFTD Tier 2 | Distribution | 2013-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015527 | 405366055 | High Sign | HFTD Tier 3 | Distribution | 2013-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015528 | 405366057 | High Sign | HFTD Tier 3 | Distribution | 2013-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015529 | 405367147 | Molding | HFTD Tier 2 | Distribution | 2013-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015530 | 405367152 | High Sign | HFTD Tier 2 | Distribution | 2013-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015531 | 405367153 | High Sign | HFTD Tier 2 | Distribution | 2013-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015532 | 405367160 | High Sign | HFTD Tier 2 | Distribution | 2013-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015533 | 405367161 | Molding | HFTD Tier 2 | Distribution | 2013-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015534 | 405367162 | High Sign | HFTD Tier 2 | Distribution | 2013-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015535 | 405367747 | Molding | HFTD Tier 3 | Distribution | 2013-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015536 | 405368896 | Guy | HFTD Tier 2 | Distribution | 2013-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015537 | 405370113 | High Sign | HFTD Tier 3 | Distribution | 2013-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015538 | 405375643 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015539 | 405379708 | Molding | HFTD Tier 2 | Distribution | 2013-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015540 | 405379717 | Molding | HFTD Tier 2 | Distribution | 2013-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015541 | 405381227 | High Sign | HFTD Tier 2 | Distribution | 2013-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015542 | 405383319 | High Sign | HFTD Tier 2 | Distribution | 2013-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015543 | 405383330 | Molding | HFTD Tier 2 | Distribution | 2013-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015544 | 405385397 | Molding | HFTD Tier 3 | Distribution | 2013-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015545 | 405385402 | High Sign | HFTD Tier 3 | Distribution | 2013-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015546 | 405385828 | Guy | HFTD Tier 3 | Distribution | 2013-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015547 | 405385893 | Molding | HFTD Tier 2 | Distribution | 2013-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015548 | 405386498 | Vis Strips | HFTD Tier 2 | Distribution | 2013-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015549 | 405386587 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015550 | 405388374 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2013-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015551 | 405388516 | Molding | HFTD Tier 2 | Distribution | 2013-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015552 | 405388544 | Molding | HFTD Tier 2 | Distribution | 2013-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015553 | 405388565 | Guy | HFTD Tier 2 | Distribution | 2013-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015554 | 405388576 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015555 | 405388724 | High Sign | HFTD Tier 3 | Distribution | 2013-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015556 | 405388726 | Bond | HFTD Tier 3 | Distribution | 2013-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015557 | 405388728 | Molding | HFTD Tier 3 | Distribution | 2013-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015558 | 405388739 | High Sign | HFTD Tier 3 | Distribution | 2013-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015559 | 405388740 | Molding | HFTD Tier 3 | Distribution | 2013-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015560 | 405388756 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015561 | 405388778 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015562 | 405388826 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-07-25 | 1945-04-18 | 2 | Ignition Risk, no GO95 exception | [6 empty] | SCE | 2025 | 4
1130015563 | 405388987 | Guy | HFTD Tier 3 | Distribution | 2013-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015564 | 405389023 | Molding | HFTD Tier 3 | Distribution | 2013-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015565 | 405389773 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2013-07-26 | 1984-04-16 | 2 | Ignition Risk, no GO95 exception | [6 empty] | SCE | 2025 | 4
1130015566 | 405389815 | Molding | HFTD Tier 3 | Distribution | 2013-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015567 | 405391017 | Molding | HFTD Tier 3 | Distribution | 2013-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015568 | 405391042 | Molding | HFTD Tier 3 | Distribution | 2013-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015569 | 405391574 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2013-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015570 | 405391664 | Guy | HFTD Tier 2 | Distribution | 2013-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015571 | 405391667 | High Sign | HFTD Tier 2 | Distribution | 2013-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015572 | 405391690 | Molding | HFTD Tier 2 | Distribution | 2013-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015573 | 405391717 | High Sign | HFTD Tier 2 | Distribution | 2013-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015574 | 405393382 | Molding | HFTD Tier 3 | Distribution | 2013-07-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015575 | 405394558 | Molding | HFTD Tier 2 | Distribution | 2013-07-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015576 | 405394766 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-07-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015577 | 405394785 | Molding | HFTD Tier 3 | Distribution | 2013-07-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015578 | 405397861 | Molding | HFTD Tier 3 | Distribution | 2013-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015579 | 405400237 | High Sign | HFTD Tier 3 | Distribution | 2013-07-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015580 | 405401453 | High Sign | HFTD Tier 2 | Distribution | 2013-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015581 | 405401644 | Molding | HFTD Tier 3 | Distribution | 2013-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015582 | 405401875 | Molding | HFTD Tier 3 | Distribution | 2013-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015583 | 405401911 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015584 | 405402023 | Molding | HFTD Tier 3 | Distribution | 2013-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015585 | 405402078 | High Sign | HFTD Tier 3 | Distribution | 2013-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015586 | 405402190 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015587 | 405404694 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2013-08-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015588 | 405404697 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-08-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015589 | 405404698 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2013-08-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015590 | 405405842 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-08-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015591 | 405406081 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-08-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015592 | 405406830 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-08-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015593 | 405407091 | High Sign | HFTD Tier 3 | Distribution | 2013-08-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015594 | 405407092 | High Sign | HFTD Tier 3 | Distribution | 2013-08-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015595 | 405408939 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-08-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015596 | 405409025 | ID Markings | HFTD Tier 3 | Distribution | 2013-08-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015597 | 405409067 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-08-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015598 | 405415826 | High Sign | HFTD Tier 3 | Distribution | 2013-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015599 | 405415829 | Guy | HFTD Tier 3 | Distribution | 2013-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015600 | 405415882 | Molding | HFTD Tier 3 | Distribution | 2013-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015601 | 405416292 | Molding | HFTD Tier 2 | Distribution | 2013-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015602 | 405416316 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015603 | 405420319 | Guy | HFTD Tier 2 | Distribution | 2013-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015604 | 405420343 | Molding | HFTD Tier 2 | Distribution | 2013-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015605 | 405420344 | Molding | HFTD Tier 2 | Distribution | 2013-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015606 | 405420346 | High Sign | HFTD Tier 2 | Distribution | 2013-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015607 | 405420372 | Molding | HFTD Tier 2 | Distribution | 2013-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015608 | 405420381 | Molding | HFTD Tier 2 | Distribution | 2013-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015609 | 405420384 | Molding | HFTD Tier 2 | Distribution | 2013-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015610 | 405420428 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015611 | 405420624 | Molding | HFTD Tier 2 | Distribution | 2013-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015612 | 405420626 | Guy | HFTD Tier 2 | Distribution | 2013-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015613 | 405420655 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2013-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015614 | 405420745 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015615 | 405424729 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2013-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015616 | 405425043 | Molding | HFTD Tier 2 | Distribution | 2013-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015617 | 405425044 | High Sign | HFTD Tier 3 | Distribution | 2013-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015618 | 405425050 | Molding | HFTD Tier 2 | Distribution | 2013-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015619 | 405425052 | High Sign | HFTD Tier 2 | Distribution | 2013-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015620 | 405425055 | High Sign | HFTD Tier 3 | Distribution | 2013-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015621 | 405425059 | Molding | HFTD Tier 3 | Distribution | 2013-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015622 | 405425064 | Guy | HFTD Tier 2 | Distribution | 2013-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015623 | 405425065 | High Sign | HFTD Tier 3 | Distribution | 2013-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015624 | 405427173 | High Sign | HFTD Tier 2 | Distribution | 2013-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015625 | 405428357 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015626 | 405430295 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015627 | 405431356 | Molding | HFTD Tier 3 | Distribution | 2013-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015628 | 405431366 | Molding | HFTD Tier 3 | Distribution | 2013-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015629 | 405431373 | Molding | HFTD Tier 3 | Distribution | 2013-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015630 | 405431562 | High Sign | HFTD Tier 3 | Distribution | 2013-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015631 | 405432014 | Molding | HFTD Tier 2 | Distribution | 2013-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015632 | 405432015 | Molding | HFTD Tier 2 | Distribution | 2013-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015633 | 405432016 | High Sign | HFTD Tier 2 | Distribution | 2013-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015634 | 405432034 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015635 | 405432036 | Molding | HFTD Tier 2 | Distribution | 2013-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015636 | 405432064 | Molding | HFTD Tier 2 | Distribution | 2013-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015637 | 405432083 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015638 | 405432085 | Molding | HFTD Tier 2 | Distribution | 2013-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015639 | 405432103 | Molding | HFTD Tier 2 | Distribution | 2013-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015640 | 405432792 | Molding | HFTD Tier 2 | Distribution | 2013-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015641 | 405432809 | Molding | HFTD Tier 2 | Distribution | 2013-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015642 | 405432824 | Molding | HFTD Tier 2 | Distribution | 2013-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015643 | 405432830 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015644 | 405432862 | High Sign | HFTD Tier 2 | Distribution | 2013-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015645 | 405432869 | Molding | HFTD Tier 2 | Distribution | 2013-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015646 | 405432880 | Guy | HFTD Tier 2 | Distribution | 2013-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015647 | 405432895 | Molding | HFTD Tier 2 | Distribution | 2013-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015648 | 405432896 | Molding | HFTD Tier 2 | Distribution | 2013-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015649 | 405432947 | Guy | HFTD Tier 2 | Distribution | 2013-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015650 | 405432974 | Molding | HFTD Tier 2 | Distribution | 2013-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015651 | 405432976 | High Sign | HFTD Tier 2 | Distribution | 2013-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015652 | 405437562 | Molding | HFTD Tier 3 | Distribution | 2013-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015653 | 405437563 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015654 | 405437565 | Molding | HFTD Tier 3 | Distribution | 2013-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015655 | 405437574 | High Sign | HFTD Tier 3 | Distribution | 2013-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015656 | 405437576 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015657 | 405437585 | High Sign | HFTD Tier 3 | Distribution | 2013-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015658 | 405437586 | High Sign | HFTD Tier 3 | Distribution | 2013-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015659 | 405437664 | Molding | HFTD Tier 3 | Distribution | 2013-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015660 | 405437997 | Molding | HFTD Tier 3 | Distribution | 2013-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015661 | 405438008 | High Sign | HFTD Tier 3 | Distribution | 2013-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015662 | 405438020 | Molding | HFTD Tier 3 | Distribution | 2013-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015663 | 405438026 | Molding | HFTD Tier 3 | Distribution | 2013-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015664 | 405438030 | High Sign | HFTD Tier 3 | Distribution | 2013-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015665 | 405441647 | High Sign | HFTD Tier 3 | Distribution | 2013-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015666 | 405441671 | Molding | HFTD Tier 3 | Distribution | 2013-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015667 | 405442968 | High Sign | HFTD Tier 3 | Distribution | 2013-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015668 | 405443213 | High Sign | HFTD Tier 3 | Distribution | 2013-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015669 | 405443218 | High Sign | HFTD Tier 3 | Distribution | 2013-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015670 | 405443230 | High Sign | HFTD Tier 3 | Distribution | 2013-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015671 | 405443233 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015672 | 405443238 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015673 | 405448347 | Molding | HFTD Tier 3 | Distribution | 2013-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015674 | 405448348 | Molding | HFTD Tier 3 | Distribution | 2013-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015675 | 405448351 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015676 | 405448449 | Guy | HFTD Tier 3 | Distribution | 2013-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015677 | 405448698 | Molding | HFTD Tier 3 | Distribution | 2013-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015678 | 405448712 | High Sign | HFTD Tier 3 | Distribution | 2013-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015679 | 405448724 | High Sign | HFTD Tier 3 | Distribution | 2013-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015680 | 405451576 | High Sign | HFTD Tier 2 | Distribution | 2013-08-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015681 | 405451586 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-08-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015682 | 405458383 | High Sign | HFTD Tier 3 | Distribution | 2013-08-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015683 | 405458399 | High Sign | HFTD Tier 3 | Distribution | 2013-08-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015684 | 405458400 | High Sign | HFTD Tier 3 | Distribution | 2013-08-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015685 | 405458415 | High Sign | HFTD Tier 3 | Distribution | 2013-08-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015686 | 405466438 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-08-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015687 | 405485027 | High Sign | HFTD Tier 3 | Distribution | 2013-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015688 | 405491506 | High Sign | HFTD Tier 3 | Distribution | 2013-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015689 | 405491512 | High Sign | HFTD Tier 3 | Distribution | 2013-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015690 | 405491513 | High Sign | HFTD Tier 3 | Distribution | 2013-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015691 | 405491718 | Molding | HFTD Tier 3 | Distribution | 2013-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015692 | 405491747 | Molding | HFTD Tier 3 | Distribution | 2013-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015693 | 405491770 | High Sign | HFTD Tier 3 | Distribution | 2013-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015694 | 405491825 | High Sign | HFTD Tier 3 | Distribution | 2013-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015695 | 405494641 | High Sign | HFTD Tier 3 | Distribution | 2013-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015696 | 405494680 | Molding | HFTD Tier 3 | Distribution | 2013-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015697 | 405494681 | High Sign | HFTD Tier 3 | Distribution | 2013-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015698 | 405494806 | High Sign | HFTD Tier 3 | Distribution | 2013-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015699 | 405496592 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015700 | 405497586 | Molding | HFTD Tier 3 | Distribution | 2013-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015701 | 405497781 | Molding | HFTD Tier 3 | Distribution | 2013-08-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015702 | 405499960 | High Sign | HFTD Tier 3 | Distribution | 2013-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015703 | 405500279 | Bond | HFTD Tier 2 | Distribution | 2013-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015704 | 405500283 | Molding | HFTD Tier 2 | Distribution | 2013-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015705 | 405500368 | High Sign | HFTD Tier 3 | Distribution | 2013-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015706 | 405508812 | Molding | HFTD Tier 3 | Distribution | 2013-08-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015707 | 405508825 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-08-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015708 | 405509392 | Retaining Wall | HFTD Tier 2 | Transmission | 2013-08-29 | 2011-04-26 | 2 | [7 empty] | SCE | 2025 | 4
1130015709 | 405524604 | Molding | HFTD Tier 3 | Distribution | 2013-09-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015710 | 405533073 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-09-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015711 | 405537349 | Molding | HFTD Tier 2 | Distribution | 2013-09-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015712 | 405537360 | Guy | HFTD Tier 2 | Distribution | 2013-09-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015713 | 405537387 | Molding | HFTD Tier 2 | Distribution | 2013-09-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015714 | 405537446 | Molding | HFTD Tier 2 | Distribution | 2013-09-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015715 | 405537453 | Molding | HFTD Tier 2 | Distribution | 2013-09-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015716 | 405537456 | Molding | HFTD Tier 2 | Distribution | 2013-09-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015717 | 405537457 | High Sign | HFTD Tier 2 | Distribution | 2013-09-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015718 | 405537466 | Molding | HFTD Tier 2 | Distribution | 2013-09-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015719 | 405537473 | Molding | HFTD Tier 2 | Distribution | 2013-09-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015720 | 405537491 | High Sign | HFTD Tier 2 | Distribution | 2013-09-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015721 | 405537494 | Molding | HFTD Tier 2 | Distribution | 2013-09-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015722 | 405540205 | Molding | HFTD Tier 2 | Distribution | 2013-09-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015723 | 405550518 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-09-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015724 | 405551348 | High Sign | HFTD Tier 3 | Distribution | 2013-09-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015725 | 405551371 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-09-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015726 | 405557384 | High Sign | HFTD Tier 3 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015727 | 405557393 | High Sign | HFTD Tier 3 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015728 | 405557394 | High Sign | HFTD Tier 3 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015729 | 405557396 | High Sign | HFTD Tier 3 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015730 | 405557404 | High Sign | HFTD Tier 3 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015731 | 405557406 | High Sign | HFTD Tier 3 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015732 | 405557411 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015733 | 405557434 | High Sign | HFTD Tier 3 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015734 | 405557441 | High Sign | HFTD Tier 3 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015735 | 405557443 | High Sign | HFTD Tier 3 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015736 | 405557445 | High Sign | HFTD Tier 3 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015737 | 405557448 | High Sign | HFTD Tier 3 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015738 | 405557452 | Molding | HFTD Tier 3 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015739 | 405557463 | High Sign | HFTD Tier 3 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015740 | 405557464 | High Sign | HFTD Tier 3 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015741 | 405557472 | High Sign | HFTD Tier 3 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015742 | 405557739 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015743 | 405557762 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015744 | 405557770 | Molding | HFTD Tier 2 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015745 | 405557774 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015746 | 405557777 | High Sign | HFTD Tier 2 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015747 | 405557792 | High Sign | HFTD Tier 2 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015748 | 405564017 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-09-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015749 | 405564100 | Termination | HFTD Tier 2 | Distribution | 2013-09-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015750 | 405564133 | Molding | HFTD Tier 2 | Distribution | 2013-09-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015751 | 405564140 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-09-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015752 | 405564161 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-09-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015753 | 405564183 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-09-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015754 | 405565026 | Molding | HFTD Tier 3 | Distribution | 2013-09-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015755 | 405565034 | High Sign | HFTD Tier 3 | Distribution | 2013-09-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015756 | 405565036 | Molding | HFTD Tier 3 | Distribution | 2013-09-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015757 | 405565038 | High Sign | HFTD Tier 3 | Distribution | 2013-09-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015758 | 405566703 | High Sign | HFTD Tier 2 | Distribution | 2013-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015759 | 405567112 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015760 | 405568643 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015761 | 405573125 | Handhole | HFTD Tier 3 | Distribution | 2013-09-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015762 | 405573569 | Guy | HFTD Tier 2 | Distribution | 2013-09-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015763 | 405576645 | Molding | HFTD Tier 2 | Distribution | 2013-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015764 | 405576660 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015765 | 405576664 | Molding | HFTD Tier 2 | Distribution | 2013-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015766 | 405576669 | High Sign | HFTD Tier 2 | Distribution | 2013-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015767 | 405578688 | High Sign | HFTD Tier 3 | Distribution | 2013-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015768 | 405578690 | High Sign | HFTD Tier 3 | Distribution | 2013-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015769 | 405578960 | High Sign | HFTD Tier 2 | Distribution | 2013-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015770 | 405580297 | High Sign | HFTD Tier 3 | Distribution | 2013-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015771 | 405580817 | Molding | HFTD Tier 2 | Distribution | 2013-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015772 | 405580830 | High Sign | HFTD Tier 2 | Distribution | 2013-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015773 | 405582739 | High Sign | HFTD Tier 3 | Distribution | 2013-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015774 | 405582755 | High Sign | HFTD Tier 3 | Distribution | 2013-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015775 | 405582756 | High Sign | HFTD Tier 3 | Distribution | 2013-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015776 | 405582769 | Bond | HFTD Tier 3 | Distribution | 2013-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015777 | 405582776 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015778 | 405582780 | High Sign | HFTD Tier 3 | Distribution | 2013-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015779 | 405582791 | High Sign | HFTD Tier 3 | Distribution | 2013-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015780 | 405584504 | High Sign | HFTD Tier 2 | Distribution | 2013-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015781 | 405588262 | High Sign | HFTD Tier 3 | Distribution | 2013-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015782 | 405588263 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-09-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015783 | 405590278 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015784 | 405595538 | High Sign | HFTD Tier 3 | Distribution | 2013-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015785 | 405595550 | High Sign | HFTD Tier 3 | Distribution | 2013-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015786 | 405599008 | Molding | HFTD Tier 3 | Distribution | 2013-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015787 | 405607287 | High Sign | HFTD Tier 3 | Distribution | 2013-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015788 | 405607298 | Molding | HFTD Tier 3 | Distribution | 2013-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015789 | 405611875 | High Sign | HFTD Tier 3 | Distribution | 2013-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015790 | 405617224 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-10-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015791 | 405618049 | Molding | HFTD Tier 3 | Distribution | 2013-10-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015792 | 405618099 | High Sign | HFTD Tier 3 | Distribution | 2013-10-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015793 | 405618107 | High Sign | HFTD Tier 3 | Distribution | 2013-10-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015794 | 405618108 | High Sign | HFTD Tier 3 | Distribution | 2013-10-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015795 | 405618109 | Molding | HFTD Tier 3 | Distribution | 2013-10-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015796 | 405618111 | High Sign | HFTD Tier 3 | Distribution | 2013-10-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015797 | 405618113 | High Sign | HFTD Tier 3 | Distribution | 2013-10-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015798 | 405618131 | High Sign | HFTD Tier 3 | Distribution | 2013-10-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015799 | 405618139 | High Sign | HFTD Tier 3 | Distribution | 2013-10-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015800 | 405618146 | High Sign | HFTD Tier 3 | Distribution | 2013-10-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015801 | 405618148 | High Sign | HFTD Tier 3 | Distribution | 2013-10-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015802 | 405618161 | High Sign | HFTD Tier 3 | Distribution | 2013-10-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015803 | 405620331 | High Sign | HFTD Tier 3 | Distribution | 2013-10-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015804 | 405620332 | High Sign | HFTD Tier 3 | Distribution | 2013-10-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015805 | 405623929 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-10-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015806 | 405623965 | High Sign | HFTD Tier 3 | Distribution | 2013-10-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015807 | 405624177 | High Sign | HFTD Tier 3 | Distribution | 2013-10-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015808 | 405624181 | High Sign | HFTD Tier 3 | Distribution | 2013-10-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015809 | 405625778 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-10-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015810 | 405627323 | Molding | HFTD Tier 3 | Distribution | 2013-10-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015811 | 405627402 | High Sign | HFTD Tier 3 | Distribution | 2013-10-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015812 | 405630486 | Molding | HFTD Tier 3 | Distribution | 2013-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015813 | 405630492 | Molding | HFTD Tier 3 | Distribution | 2013-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015814 | 405630497 | Molding | HFTD Tier 3 | Distribution | 2013-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015815 | 405630499 | Bond | HFTD Tier 3 | Distribution | 2013-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015816 | 405630500 | Molding | HFTD Tier 3 | Distribution | 2013-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015817 | 405630842 | Molding | HFTD Tier 3 | Distribution | 2013-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015818 | 405630850 | Molding | HFTD Tier 3 | Distribution | 2013-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015819 | 405633159 | Molding | HFTD Tier 3 | Distribution | 2013-10-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015820 | 405633161 | Molding | HFTD Tier 3 | Distribution | 2013-10-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015821 | 405639569 | High Sign | HFTD Tier 3 | Distribution | 2013-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015822 | 405639581 | Molding | HFTD Tier 3 | Distribution | 2013-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015823 | 405651199 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-10-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015824 | 405651207 | Molding | HFTD Tier 3 | Distribution | 2013-10-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015825 | 405655708 | High Sign | HFTD Tier 3 | Distribution | 2013-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015826 | 405655714 | High Sign | HFTD Tier 3 | Distribution | 2013-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015827 | 405655735 | High Sign | HFTD Tier 3 | Distribution | 2013-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015828 | 405655744 | High Sign | HFTD Tier 3 | Distribution | 2013-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015829 | 405655752 | High Sign | HFTD Tier 3 | Distribution | 2013-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015830 | 405658289 | High Sign | HFTD Tier 3 | Distribution | 2013-10-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015831 | 405658306 | High Sign | HFTD Tier 3 | Distribution | 2013-10-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015832 | 405658307 | High Sign | HFTD Tier 3 | Distribution | 2013-10-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015833 | 405658309 | Molding | HFTD Tier 3 | Distribution | 2013-10-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015834 | 405658311 | High Sign | HFTD Tier 3 | Distribution | 2013-10-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015835 | 405658318 | High Sign | HFTD Tier 3 | Distribution | 2013-10-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015836 | 405659403 | High Sign | HFTD Tier 3 | Distribution | 2013-10-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015837 | 405661195 | Molding | HFTD Tier 3 | Distribution | 2013-10-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015838 | 405661204 | Molding | HFTD Tier 3 | Distribution | 2013-10-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015839 | 405661220 | Molding | HFTD Tier 3 | Distribution | 2013-10-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015840 | 405661222 | Molding | HFTD Tier 3 | Distribution | 2013-10-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015841 | 405661225 | Molding | HFTD Tier 3 | Distribution | 2013-10-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015842 | 405661227 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-10-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015843 | 405661232 | Molding | HFTD Tier 3 | Distribution | 2013-10-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015844 | 405661235 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-10-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015845 | 405661237 | High Sign | HFTD Tier 3 | Distribution | 2013-10-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015846 | 405661241 | Molding | HFTD Tier 3 | Distribution | 2013-10-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015847 | 405661244 | Molding | HFTD Tier 3 | Distribution | 2013-10-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015848 | 405666191 | High Sign | HFTD Tier 3 | Distribution | 2013-11-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015849 | 405666192 | Molding | HFTD Tier 3 | Distribution | 2013-11-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015850 | 405666193 | High Sign | HFTD Tier 3 | Distribution | 2013-11-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015851 | 405666195 | Molding | HFTD Tier 3 | Distribution | 2013-11-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015852 | 405666201 | Molding | HFTD Tier 3 | Distribution | 2013-11-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015853 | 405666244 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-11-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015854 | 405670035 | High Sign | HFTD Tier 3 | Distribution | 2013-11-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015855 | 405670043 | Molding | HFTD Tier 3 | Distribution | 2013-11-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015856 | 405670047 | High Sign | HFTD Tier 3 | Distribution | 2013-11-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015857 | 405670071 | Molding | HFTD Tier 3 | Distribution | 2013-11-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015858 | 405670078 | High Sign | HFTD Tier 3 | Distribution | 2013-11-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015859 | 405674677 | High Sign | HFTD Tier 3 | Distribution | 2013-11-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015860 | 405674678 | High Sign | HFTD Tier 3 | Distribution | 2013-11-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015861 | 405674681 | High Sign | HFTD Tier 3 | Distribution | 2013-11-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015862 | 405674686 | High Sign | HFTD Tier 3 | Distribution | 2013-11-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015863 | 405674693 | High Sign | HFTD Tier 3 | Distribution | 2013-11-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015864 | 405674694 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-11-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015865 | 405674696 | Molding | HFTD Tier 3 | Distribution | 2013-11-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015866 | 405674704 | High Sign | HFTD Tier 3 | Distribution | 2013-11-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015867 | 405674716 | High Sign | HFTD Tier 3 | Distribution | 2013-11-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015868 | 405674718 | High Sign | HFTD Tier 3 | Distribution | 2013-11-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015869 | 405679093 | High Sign | HFTD Tier 3 | Distribution | 2013-11-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015870 | 405679098 | Molding | HFTD Tier 3 | Distribution | 2013-11-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015871 | 405679107 | High Sign | HFTD Tier 3 | Distribution | 2013-11-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015872 | 405679110 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-11-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015873 | 405679114 | Molding | HFTD Tier 3 | Distribution | 2013-11-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015874 | 405679119 | High Sign | HFTD Tier 3 | Distribution | 2013-11-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015875 | 405679127 | High Sign | HFTD Tier 3 | Distribution | 2013-11-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015876 | 405684422 | High Sign | HFTD Tier 3 | Distribution | 2013-11-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015877 | 405684435 | High Sign | HFTD Tier 3 | Distribution | 2013-11-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015878 | 405684437 | High Sign | HFTD Tier 3 | Distribution | 2013-11-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015879 | 405684448 | High Sign | HFTD Tier 3 | Distribution | 2013-11-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015880 | 405684450 | High Sign | HFTD Tier 3 | Distribution | 2013-11-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015881 | 405684451 | High Sign | HFTD Tier 3 | Distribution | 2013-11-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015882 | 405684461 | High Sign | HFTD Tier 3 | Distribution | 2013-11-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015883 | 405690908 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015884 | 405690912 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015885 | 405690921 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015886 | 405690931 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015887 | 405691039 | Guy | HFTD Tier 3 | Distribution | 2013-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015888 | 405691050 | Molding | HFTD Tier 3 | Distribution | 2013-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015889 | 405691059 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-11-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015890 | 405691443 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015891 | 405691444 | Molding | HFTD Tier 3 | Distribution | 2013-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015892 | 405691451 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015893 | 405693467 | High Sign | HFTD Tier 3 | Distribution | 2013-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015894 | 405693472 | High Sign | HFTD Tier 3 | Distribution | 2013-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015895 | 405693491 | High Sign | HFTD Tier 3 | Distribution | 2013-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015896 | 405693494 | Molding | HFTD Tier 3 | Distribution | 2013-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015897 | 405693495 | Molding | HFTD Tier 3 | Distribution | 2013-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015898 | 405693512 | High Sign | HFTD Tier 3 | Distribution | 2013-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015899 | 405700703 | High Sign | HFTD Tier 3 | Distribution | 2013-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015900 | 405700713 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015901 | 405700738 | Molding | HFTD Tier 3 | Distribution | 2013-11-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015902 | 405706578 | High Sign | HFTD Tier 3 | Distribution | 2013-11-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015903 | 405706592 | Molding | HFTD Tier 3 | Distribution | 2013-11-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015904 | 405706597 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-11-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015905 | 405706599 | Molding | HFTD Tier 3 | Distribution | 2013-11-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015906 | 405706602 | Molding | HFTD Tier 3 | Distribution | 2013-11-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015907 | 405709983 | Molding | HFTD Tier 3 | Distribution | 2013-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015908 | 405711638 | Molding | HFTD Tier 3 | Distribution | 2013-11-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015909 | 405711647 | Molding | HFTD Tier 3 | Distribution | 2013-11-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015910 | 405711653 | High Sign | HFTD Tier 3 | Distribution | 2013-11-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015911 | 405736786 | Riser/Conduit | HFTD Tier 2 | Distribution | 2013-12-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015912 | 405753375 | Guy | HFTD Tier 3 | Distribution | 2013-12-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015913 | 405754296 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-12-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015914 | 405759284 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-12-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015915 | 405777343 | High Sign | HFTD Tier 3 | Distribution | 2014-01-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015916 | 405779059 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-01-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015917 | 405780624 | High Sign | HFTD Tier 3 | Distribution | 2014-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015918 | 405780627 | High Sign | HFTD Tier 3 | Distribution | 2014-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015919 | 405780647 | High Sign | HFTD Tier 3 | Distribution | 2014-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015920 | 405780819 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015921 | 405780839 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015922 | 405780855 | High Sign | HFTD Tier 3 | Distribution | 2014-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015923 | 405780866 | High Sign | HFTD Tier 3 | Distribution | 2014-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015924 | 405780985 | Molding | HFTD Tier 2 | Distribution | 2014-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015925 | 405780986 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015926 | 405781690 | Molding | HFTD Tier 3 | Distribution | 2014-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015927 | 405781710 | Molding | HFTD Tier 3 | Distribution | 2014-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015928 | 405781711 | Riser/Conduit | HFTD Tier 3 | Distribution | 2014-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015929 | 405781775 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015930 | 405781778 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015931 | 405782143 | High Sign | HFTD Tier 3 | Distribution | 2014-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015932 | 405782255 | High Sign | HFTD Tier 3 | Distribution | 2014-01-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015933 | 405782259 | Molding | HFTD Tier 3 | Distribution | 2014-01-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015934 | 405782265 | Molding | HFTD Tier 3 | Distribution | 2014-01-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015935 | 405782272 | High Sign | HFTD Tier 3 | Distribution | 2014-01-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015936 | 405782276 | High Sign | HFTD Tier 3 | Distribution | 2014-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015937 | 405784006 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015938 | 405784686 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015939 | 405784703 | High Sign | HFTD Tier 3 | Distribution | 2014-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015940 | 405784705 | High Sign | HFTD Tier 3 | Distribution | 2014-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015941 | 405784715 | High Sign | HFTD Tier 3 | Distribution | 2014-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015942 | 405785033 | High Sign | HFTD Tier 2 | Distribution | 2014-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015943 | 405785090 | Molding | HFTD Tier 3 | Distribution | 2014-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015944 | 405785204 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015945 | 405785990 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015946 | 405786003 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015947 | 405786004 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015948 | 405786411 | Guy | HFTD Tier 3 | Distribution | 2014-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015949 | 405786443 | Guy | HFTD Tier 3 | Distribution | 2014-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015950 | 405786574 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015951 | 405786579 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015952 | 405786591 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015953 | 405787466 | High Sign | HFTD Tier 3 | Distribution | 2014-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015954 | 405787659 | High Sign | HFTD Tier 3 | Distribution | 2014-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015955 | 405787898 | High Sign | HFTD Tier 3 | Distribution | 2014-01-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015956 | 405787899 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015957 | 405787962 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015958 | 405788987 | Molding | HFTD Tier 2 | Distribution | 2014-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015959 | 405789033 | High Sign | HFTD Tier 2 | Distribution | 2014-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015960 | 405789042 | Molding | HFTD Tier 2 | Distribution | 2014-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015961 | 405789714 | High Sign | HFTD Tier 2 | Distribution | 2014-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015962 | 405789716 | High Sign | HFTD Tier 2 | Distribution | 2014-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015963 | 405789737 | High Sign | HFTD Tier 2 | Distribution | 2014-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015964 | 405789746 | Molding | HFTD Tier 2 | Distribution | 2014-01-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015965 | 405791534 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015966 | 405791736 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015967 | 405792350 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015968 | 405792570 | High Sign | HFTD Tier 3 | Distribution | 2014-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015969 | 405792572 | High Sign | HFTD Tier 3 | Distribution | 2014-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015970 | 405792904 | Molding | HFTD Tier 3 | Distribution | 2014-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015971 | 405792915 | Riser/Conduit | HFTD Tier 3 | Distribution | 2014-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015972 | 405792921 | Molding | HFTD Tier 3 | Distribution | 2014-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015973 | 405792928 | Molding | HFTD Tier 3 | Distribution | 2014-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015974 | 405792937 | High Sign | HFTD Tier 3 | Distribution | 2014-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015975 | 405792943 | High Sign | HFTD Tier 3 | Distribution | 2014-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015976 | 405794034 | Riser/Conduit | HFTD Tier 2 | Distribution | 2014-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015977 | 405794368 | Guy | HFTD Tier 2 | Distribution | 2014-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015978 | 405795909 | High Sign | HFTD Tier 3 | Distribution | 2014-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015979 | 405795919 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015980 | 405797179 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015981 | 405797520 | Guy | HFTD Tier 2 | Distribution | 2014-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015982 | 405797534 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015983 | 405797560 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015984 | 405798157 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015985 | 405798861 | Guy | HFTD Tier 3 | Distribution | 2014-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015986 | 405798959 | High Sign | HFTD Tier 3 | Distribution | 2014-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015987 | 405799142 | Molding | HFTD Tier 3 | Distribution | 2014-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015988 | 405799159 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015989 | 405800226 | Guy | HFTD Tier 2 | Distribution | 2014-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015990 | 405800278 | Molding | HFTD Tier 2 | Distribution | 2014-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015991 | 405801113 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015992 | 405801605 | Molding | HFTD Tier 3 | Distribution | 2014-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015993 | 405801609 | Molding | HFTD Tier 3 | Distribution | 2014-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015994 | 405802353 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015995 | 405802422 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015996 | 405802620 | Guy | HFTD Tier 2 | Distribution | 2014-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015997 | 405802623 | Molding | HFTD Tier 2 | Distribution | 2014-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015998 | 405803346 | Vis Strips | HFTD Tier 2 | Distribution | 2014-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130015999 | 405803777 | Guy | HFTD Tier 3 | Distribution | 2014-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016000 | 405803787 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016001 | 405804633 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016002 | 405804635 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016003 | 405804642 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016004 | 405805321 | Guy | HFTD Tier 3 | Distribution | 2014-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016005 | 405805323 | High Sign | HFTD Tier 3 | Distribution | 2014-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016006 | 405805635 | High Sign | HFTD Tier 3 | Distribution | 2014-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016007 | 405805843 | Ground | HFTD Tier 2 | Distribution | 2014-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016008 | 405805878 | High Sign | HFTD Tier 3 | Distribution | 2014-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016009 | 405807511 | High Sign | HFTD Tier 2 | Distribution | 2014-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016010 | 405807537 | Molding | HFTD Tier 2 | Distribution | 2014-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016011 | 405807551 | High Sign | HFTD Tier 2 | Distribution | 2014-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016012 | 405807839 | Molding | HFTD Tier 3 | Distribution | 2014-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016013 | 405808514 | Molding | HFTD Tier 2 | Distribution | 2014-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016014 | 405808527 | High Sign | HFTD Tier 2 | Distribution | 2014-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016015 | 405808528 | Molding | HFTD Tier 2 | Distribution | 2014-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016016 | 405808532 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016017 | 405809094 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016018 | 405809210 | Molding | HFTD Tier 3 | Distribution | 2014-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016019 | 405810602 | Molding | HFTD Tier 2 | Distribution | 2014-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016020 | 405810609 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016021 | 405810620 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016022 | 405810623 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016023 | 405810625 | Riser/Conduit | HFTD Tier 3 | Distribution | 2014-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016024 | 405810702 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016025 | 405810704 | Guy | HFTD Tier 3 | Distribution | 2014-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016026 | 405810714 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016027 | 405810724 | Molding | HFTD Tier 3 | Distribution | 2014-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016028 | 405812563 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016029 | 405812669 | High Sign | HFTD Tier 2 | Distribution | 2014-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016030 | 405812716 | Molding | HFTD Tier 2 | Distribution | 2014-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016031 | 405812719 | High Sign | HFTD Tier 2 | Distribution | 2014-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016032 | 405813068 | Molding | HFTD Tier 3 | Distribution | 2014-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016033 | 405813074 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016034 | 405814668 | Molding | HFTD Tier 2 | Distribution | 2014-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016035 | 405814748 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016036 | 405815029 | Molding | HFTD Tier 3 | Distribution | 2014-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016037 | 405815033 | High Sign | HFTD Tier 3 | Distribution | 2014-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016038 | 405815035 | High Sign | HFTD Tier 3 | Distribution | 2014-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016039 | 405815036 | Molding | HFTD Tier 3 | Distribution | 2014-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016040 | 405815052 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016041 | 405815076 | High Sign | HFTD Tier 3 | Distribution | 2014-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016042 | 405815080 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016043 | 405815434 | High Sign | HFTD Tier 2 | Distribution | 2014-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016044 | 405815443 | High Sign | HFTD Tier 2 | Distribution | 2014-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016045 | 405815447 | High Sign | HFTD Tier 2 | Distribution | 2014-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016046 | 405815463 | Molding | HFTD Tier 2 | Distribution | 2014-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016047 | 405816199 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016048 | 405816265 | High Sign | HFTD Tier 3 | Distribution | 2014-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016049 | 405816330 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016050 | 405817900 | Molding | HFTD Tier 3 | Distribution | 2014-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016051 | 405818866 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016052 | 405818889 | Molding | HFTD Tier 3 | Distribution | 2014-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016053 | 405819800 | High Sign | HFTD Tier 3 | Distribution | 2014-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016054 | 405819812 | Molding | HFTD Tier 3 | Distribution | 2014-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016055 | 405819814 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016056 | 405819845 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016057 | 405819850 | Riser/Conduit | HFTD Tier 3 | Distribution | 2014-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016058 | 405819851 | Guy | HFTD Tier 3 | Distribution | 2014-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016059 | 405819994 | High Sign | HFTD Tier 2 | Distribution | 2014-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016060 | 405820018 | High Sign | HFTD Tier 2 | Distribution | 2014-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016061 | 405820032 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016062 | 405820033 | High Sign | HFTD Tier 2 | Distribution | 2014-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016063 | 405820042 | High Sign | HFTD Tier 2 | Distribution | 2014-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016064 | 405820044 | High Sign | HFTD Tier 2 | Distribution | 2014-01-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016065 | 405821656 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016066 | 405821701 | Molding | HFTD Tier 3 | Distribution | 2014-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016067 | 405821719 | Molding | HFTD Tier 3 | Distribution | 2014-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016068 | 405823138 | Molding | HFTD Tier 3 | Distribution | 2014-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016069 | 405823144 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016070 | 405823148 | High Sign | HFTD Tier 3 | Distribution | 2014-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016071 | 405823153 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016072 | 405823372 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016073 | 405825165 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016074 | 405826228 | Riser/Conduit | HFTD Tier 3 | Distribution | 2014-01-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016075 | 405826235 | Guy | HFTD Tier 2 | Distribution | 2014-01-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016076 | 405826248 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016077 | 405826256 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-01-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016078 | 405830491 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016079 | 405830642 | Molding | HFTD Tier 3 | Distribution | 2014-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016080 | 405832310 | High Sign | HFTD Tier 3 | Distribution | 2014-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016081 | 405832503 | High Sign | HFTD Tier 3 | Distribution | 2014-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016082 | 405832508 | Molding | HFTD Tier 3 | Distribution | 2014-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016083 | 405832512 | Molding | HFTD Tier 3 | Distribution | 2014-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016084 | 405832516 | High Sign | HFTD Tier 3 | Distribution | 2014-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016085 | 405832527 | Ground | HFTD Tier 3 | Distribution | 2014-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016086 | 405832871 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-01-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016087 | 405832918 | High Sign | HFTD Tier 3 | Distribution | 2014-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016088 | 405832922 | Riser/Conduit | HFTD Tier 3 | Distribution | 2014-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016089 | 405832962 | High Sign | HFTD Tier 3 | Distribution | 2014-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016090 | 405834386 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-01-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016091 | 405834403 | Guy | HFTD Tier 3 | Distribution | 2014-01-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016092 | 405835745 | Molding | HFTD Tier 3 | Distribution | 2014-01-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016093 | 405837351 | Molding | HFTD Tier 2 | Distribution | 2014-01-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016094 | 405837375 | Molding | HFTD Tier 2 | Distribution | 2014-01-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016095 | 405839453 | Guy | HFTD Tier 3 | Distribution | 2014-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016096 | 405839544 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-01-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016097 | 405840547 | High Sign | HFTD Tier 2 | Distribution | 2014-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016098 | 405840560 | High Sign | HFTD Tier 2 | Distribution | 2014-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016099 | 405840624 | High Sign | HFTD Tier 3 | Distribution | 2014-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016100 | 405843759 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016101 | 405843791 | Molding | HFTD Tier 3 | Distribution | 2014-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016102 | 405844072 | Guy | HFTD Tier 2 | Distribution | 2014-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016103 | 405844075 | High Sign | HFTD Tier 3 | Distribution | 2014-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016104 | 405844080 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016105 | 405844093 | High Sign | HFTD Tier 2 | Distribution | 2014-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016106 | 405844369 | High Sign | HFTD Tier 2 | Distribution | 2014-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016107 | 405844384 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016108 | 405844386 | Molding | HFTD Tier 2 | Distribution | 2014-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016109 | 405844406 | High Sign | HFTD Tier 2 | Distribution | 2014-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016110 | 405846209 | Molding | HFTD Tier 3 | Distribution | 2014-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016111 | 405846260 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016112 | 405848517 | High Sign | HFTD Tier 2 | Distribution | 2014-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016113 | 405852069 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016114 | 405854666 | High Sign | HFTD Tier 3 | Distribution | 2014-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016115 | 405854710 | High Sign | HFTD Tier 3 | Distribution | 2014-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016116 | 405854713 | Guy | HFTD Tier 3 | Distribution | 2014-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016117 | 405854724 | High Sign | HFTD Tier 3 | Distribution | 2014-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016118 | 405854734 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016119 | 405854736 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016120 | 405854740 | Guy | HFTD Tier 3 | Distribution | 2014-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016121 | 405855231 | Molding | HFTD Tier 2 | Distribution | 2014-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016122 | 405855238 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016123 | 405855246 | Molding | HFTD Tier 2 | Distribution | 2014-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016124 | 405858784 | High Sign | HFTD Tier 2 | Distribution | 2014-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016125 | 405858792 | High Sign | HFTD Tier 2 | Distribution | 2014-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016126 | 405860868 | Guy | HFTD Tier 3 | Distribution | 2014-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016127 | 405860887 | High Sign | HFTD Tier 3 | Distribution | 2014-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016128 | 405862886 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016129 | 405862892 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016130 | 405864562 | Molding | HFTD Tier 3 | Distribution | 2014-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016131 | 405868702 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016132 | 405868718 | High Sign | HFTD Tier 3 | Distribution | 2014-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016133 | 405870170 | High Sign | HFTD Tier 2 | Distribution | 2014-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016134 | 405870173 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016135 | 405872457 | Guy | HFTD Tier 3 | Distribution | 2014-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016136 | 405872629 | High Sign | HFTD Tier 3 | Distribution | 2014-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016137 | 405872663 | High Sign | HFTD Tier 3 | Distribution | 2014-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016138 | 405872688 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016139 | 405872714 | High Sign | HFTD Tier 3 | Distribution | 2014-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016140 | 405872742 | High Sign | HFTD Tier 3 | Distribution | 2014-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016141 | 405874022 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-02-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016142 | 405874277 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-02-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016143 | 405874286 | Molding | HFTD Tier 2 | Distribution | 2014-02-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016144 | 405874287 | Molding | HFTD Tier 2 | Distribution | 2014-02-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016145 | 405874694 | Molding | HFTD Tier 2 | Distribution | 2014-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016146 | 405874752 | Guy | HFTD Tier 3 | Distribution | 2014-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016147 | 405874762 | Guy | HFTD Tier 3 | Distribution | 2014-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016148 | 405874764 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016149 | 405874827 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016150 | 405874835 | Molding | HFTD Tier 2 | Distribution | 2014-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016151 | 405874840 | Guy | HFTD Tier 2 | Distribution | 2014-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016152 | 405874895 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016153 | 405874905 | Guy | HFTD Tier 2 | Distribution | 2014-02-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016154 | 405875157 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016155 | 405876459 | Molding | HFTD Tier 2 | Distribution | 2014-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016156 | 405876484 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016157 | 405876554 | High Sign | HFTD Tier 3 | Distribution | 2014-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016158 | 405876780 | Molding | HFTD Tier 3 | Distribution | 2014-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016159 | 405876789 | High Sign | HFTD Tier 3 | Distribution | 2014-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016160 | 405878750 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016161 | 405879245 | Guy | HFTD Tier 3 | Distribution | 2014-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016162 | 405880277 | Guy | HFTD Tier 3 | Distribution | 2014-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016163 | 405884967 | High Sign | HFTD Tier 3 | Distribution | 2014-02-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016164 | 405885095 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-02-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016165 | 405885107 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-02-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016166 | 405885110 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-02-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016167 | 405886470 | High Sign | HFTD Tier 3 | Distribution | 2014-02-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016168 | 405886491 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-02-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016169 | 405886779 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-02-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016170 | 405886783 | Molding | HFTD Tier 2 | Distribution | 2014-02-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016171 | 405887023 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-02-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016172 | 405887048 | High Sign | HFTD Tier 3 | Distribution | 2014-02-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016173 | 405888344 | Molding | HFTD Tier 2 | Distribution | 2014-02-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016174 | 405889802 | High Sign | HFTD Tier 3 | Distribution | 2014-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016175 | 405889811 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016176 | 405891452 | Riser/Conduit | HFTD Tier 2 | Distribution | 2014-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016177 | 405893161 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016178 | 405893163 | High Sign | HFTD Tier 3 | Distribution | 2014-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016179 | 405893165 | High Sign | HFTD Tier 3 | Distribution | 2014-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016180 | 405893938 | Guy | HFTD Tier 3 | Distribution | 2014-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016181 | 405893939 | Guy | HFTD Tier 3 | Distribution | 2014-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016182 | 405893947 | Molding | HFTD Tier 3 | Distribution | 2014-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016183 | 405893972 | High Sign | HFTD Tier 3 | Distribution | 2014-02-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016184 | 405893973 | High Sign | HFTD Tier 3 | Distribution | 2014-02-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016185 | 405893989 | Molding | HFTD Tier 3 | Distribution | 2014-02-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016186 | 405893991 | High Sign | HFTD Tier 3 | Distribution | 2014-02-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016187 | 405894074 | Molding | HFTD Tier 3 | Distribution | 2014-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016188 | 405894177 | Molding | HFTD Tier 3 | Distribution | 2014-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016189 | 405900935 | High Sign | HFTD Tier 3 | Distribution | 2014-02-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016190 | 405901244 | Molding | HFTD Tier 2 | Distribution | 2014-02-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016191 | 405901246 | Molding | HFTD Tier 2 | Distribution | 2014-02-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016192 | 405901405 | Molding | HFTD Tier 2 | Distribution | 2014-02-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016193 | 405901408 | Guy | HFTD Tier 3 | Distribution | 2014-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016194 | 405901411 | High Sign | HFTD Tier 2 | Distribution | 2014-02-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016195 | 405904647 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016196 | 405904659 | High Sign | HFTD Tier 3 | Distribution | 2014-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016197 | 405904661 | Riser/Conduit | HFTD Tier 3 | Distribution | 2014-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016198 | 405904695 | Guy | HFTD Tier 3 | Distribution | 2014-02-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016199 | 405904744 | High Sign | HFTD Tier 3 | Distribution | 2014-02-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016200 | 405906801 | Guy | HFTD Tier 3 | Distribution | 2014-02-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016201 | 405906806 | High Sign | HFTD Tier 3 | Distribution | 2014-02-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016202 | 405908095 | Molding | HFTD Tier 2 | Distribution | 2014-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016203 | 405908141 | Molding | HFTD Tier 2 | Distribution | 2014-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016204 | 405909185 | Guy | HFTD Tier 2 | Distribution | 2014-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016205 | 405909193 | Guy | HFTD Tier 2 | Distribution | 2014-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016206 | 405910961 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016207 | 405917016 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016208 | 405917019 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016209 | 405917036 | Molding | HFTD Tier 3 | Distribution | 2014-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016210 | 405917039 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016211 | 405917040 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016212 | 405917073 | Riser/Conduit | HFTD Tier 3 | Distribution | 2014-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016213 | 405917081 | Guy | HFTD Tier 3 | Distribution | 2014-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016214 | 405917117 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016215 | 405917123 | Molding | HFTD Tier 3 | Distribution | 2014-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016216 | 405922011 | Riser/Conduit | HFTD Tier 2 | Distribution | 2014-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016217 | 405922063 | High Sign | HFTD Tier 2 | Distribution | 2014-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016218 | 405922532 | Molding | HFTD Tier 2 | Distribution | 2014-03-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016219 | 405922555 | High Sign | HFTD Tier 2 | Distribution | 2014-03-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016220 | 405924930 | Molding | HFTD Tier 2 | Distribution | 2014-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016221 | 405924941 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016222 | 405928367 | Guy | HFTD Tier 3 | Distribution | 2014-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016223 | 405928392 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016224 | 405928393 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016225 | 405928400 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016226 | 405928402 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016227 | 405928410 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016228 | 405928413 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016229 | 405928420 | Molding | HFTD Tier 3 | Distribution | 2014-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016230 | 405928421 | Molding | HFTD Tier 3 | Distribution | 2014-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016231 | 405928424 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016232 | 405928433 | High Sign | HFTD Tier 3 | Distribution | 2014-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016233 | 405928795 | High Sign | HFTD Tier 2 | Distribution | 2014-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016234 | 405932435 | High Sign | HFTD Tier 3 | Distribution | 2014-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016235 | 405932677 | Molding | HFTD Tier 2 | Distribution | 2014-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016236 | 405932690 | High Sign | HFTD Tier 2 | Distribution | 2014-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016237 | 405932704 | High Sign | HFTD Tier 2 | Distribution | 2014-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016238 | 405932882 | High Sign | HFTD Tier 2 | Distribution | 2014-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016239 | 405934116 | High Sign | HFTD Tier 2 | Distribution | 2014-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016240 | 405936252 | High Sign | HFTD Tier 3 | Distribution | 2014-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016241 | 405936253 | Guy | HFTD Tier 3 | Distribution | 2014-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016242 | 405936256 | Molding | HFTD Tier 3 | Distribution | 2014-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016243 | 405936264 | Guy | HFTD Tier 3 | Distribution | 2014-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016244 | 405936268 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016245 | 405936274 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016246 | 405936291 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016247 | 405936295 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016248 | 405936298 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016249 | 405936304 | Molding | HFTD Tier 3 | Distribution | 2014-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016250 | 405936306 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016251 | 405936331 | Termination | HFTD Tier 3 | Distribution | 2014-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016252 | 405936346 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016253 | 405936360 | Molding | HFTD Tier 3 | Distribution | 2014-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016254 | 405936366 | Guy | HFTD Tier 3 | Distribution | 2014-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016255 | 405936370 | Molding | HFTD Tier 3 | Distribution | 2014-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016256 | 405936372 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016257 | 405936374 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016258 | 405936379 | High Sign | HFTD Tier 3 | Distribution | 2014-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016259 | 405936800 | High Sign | HFTD Tier 2 | Distribution | 2014-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016260 | 405938265 | Molding | HFTD Tier 2 | Distribution | 2014-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016261 | 405938316 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016262 | 405939565 | High Sign | HFTD Tier 3 | Distribution | 2014-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016263 | 405939567 | High Sign | HFTD Tier 3 | Distribution | 2014-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016264 | 405939999 | Molding | HFTD Tier 2 | Distribution | 2014-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016265 | 405940289 | Molding | HFTD Tier 3 | Distribution | 2014-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016266 | 405940294 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016267 | 405940308 | High Sign | HFTD Tier 3 | Distribution | 2014-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016268 | 405940329 | Molding | HFTD Tier 3 | Distribution | 2014-03-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016269 | 405941716 | Molding | HFTD Tier 3 | Distribution | 2014-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016270 | 405944360 | Molding | HFTD Tier 3 | Distribution | 2014-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016271 | 405944363 | Riser/Conduit | HFTD Tier 3 | Distribution | 2014-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016272 | 405944364 | Molding | HFTD Tier 3 | Distribution | 2014-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016273 | 405944475 | Right of Way | HFTD Tier 2 | Transmission | 2014-03-16 | 1979-04-20 | 2 | Ignition Risk, no GO95 exception | [6 empty] | SCE | 2025 | 4
1130016274 | 405946037 | Guy | HFTD Tier 3 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016275 | 405946041 | Molding | HFTD Tier 3 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016276 | 405946045 | Molding | HFTD Tier 3 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016277 | 405946046 | High Sign | HFTD Tier 3 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016278 | 405946053 | Molding | HFTD Tier 3 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016279 | 405946062 | High Sign | HFTD Tier 3 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016280 | 405946072 | Molding | HFTD Tier 3 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016281 | 405946545 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016282 | 405946565 | High Sign | HFTD Tier 2 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016283 | 405946568 | High Sign | HFTD Tier 2 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016284 | 405946572 | High Sign | HFTD Tier 2 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016285 | 405946577 | High Sign | HFTD Tier 2 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016286 | 405948623 | High Sign | HFTD Tier 2 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016287 | 405949012 | Guy | HFTD Tier 2 | Distribution | 2014-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016288 | 405949153 | Guy | HFTD Tier 2 | Distribution | 2014-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016289 | 405949203 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016290 | 405950418 | High Sign | HFTD Tier 2 | Distribution | 2014-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016291 | 405952202 | Molding | HFTD Tier 3 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016292 | 405952205 | Molding | HFTD Tier 3 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016293 | 405952206 | Molding | HFTD Tier 3 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016294 | 405952209 | Guy | HFTD Tier 3 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016295 | 405952212 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016296 | 405952213 | High Sign | HFTD Tier 3 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016297 | 405952221 | High Sign | HFTD Tier 3 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016298 | 405952224 | Molding | HFTD Tier 3 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016299 | 405952233 | High Sign | HFTD Tier 3 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016300 | 405952236 | High Sign | HFTD Tier 3 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016301 | 405952241 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016302 | 405952243 | High Sign | HFTD Tier 3 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016303 | 405952252 | Molding | HFTD Tier 3 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016304 | 405952256 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016305 | 405952263 | ID Markings | HFTD Tier 3 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016306 | 405952302 | High Sign | HFTD Tier 3 | Distribution | 2014-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016307 | 405952315 | Molding | HFTD Tier 3 | Distribution | 2014-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016308 | 405952326 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016309 | 405959990 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016310 | 405960007 | Molding | HFTD Tier 3 | Distribution | 2014-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016311 | 405960037 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016312 | 405960114 | Molding | HFTD Tier 3 | Distribution | 2014-03-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016313 | 405960117 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-03-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016314 | 405960484 | Molding | HFTD Tier 2 | Distribution | 2014-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016315 | 405960487 | Molding | HFTD Tier 2 | Distribution | 2014-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016316 | 405961466 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016317 | 405961471 | High Sign | HFTD Tier 2 | Distribution | 2014-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016318 | 405962236 | Molding | HFTD Tier 3 | Distribution | 2014-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016319 | 405964328 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016320 | 405964340 | Molding | HFTD Tier 2 | Distribution | 2014-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016321 | 405965693 | Molding | HFTD Tier 3 | Distribution | 2014-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016322 | 405965737 | Molding | HFTD Tier 3 | Distribution | 2014-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016323 | 405967133 | Molding | HFTD Tier 3 | Distribution | 2014-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016324 | 405967190 | High Sign | HFTD Tier 3 | Distribution | 2014-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016325 | 405973110 | Molding | HFTD Tier 2 | Distribution | 2014-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016326 | 405977109 | Molding | HFTD Tier 3 | Distribution | 2014-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016327 | 405978627 | Molding | HFTD Tier 3 | Distribution | 2014-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016328 | 405978860 | High Sign | HFTD Tier 2 | Distribution | 2014-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016329 | 405979067 | High Sign | HFTD Tier 3 | Distribution | 2014-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016330 | 405982131 | High Sign | HFTD Tier 3 | Distribution | 2014-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016331 | 405982134 | High Sign | HFTD Tier 3 | Distribution | 2014-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016332 | 405982166 | High Sign | HFTD Tier 3 | Distribution | 2014-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016333 | 405983437 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2014-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016334 | 405983451 | High Sign | HFTD Tier 2 | Distribution | 2014-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016335 | 405985342 | Guy | HFTD Tier 3 | Distribution | 2014-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016336 | 405985948 | Molding | HFTD Tier 3 | Distribution | 2014-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016337 | 405985987 | Molding | HFTD Tier 3 | Distribution | 2014-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016338 | 405986210 | High Sign | HFTD Tier 2 | Distribution | 2014-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016339 | 405986824 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016340 | 405986844 | Molding | HFTD Tier 2 | Distribution | 2014-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016341 | 405986957 | High Sign | HFTD Tier 3 | Distribution | 2014-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016342 | 405987225 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016343 | 405988862 | Guy | HFTD Tier 3 | Distribution | 2014-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016344 | 405989020 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016345 | 405989030 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016346 | 405989061 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016347 | 405989204 | High Sign | HFTD Tier 2 | Distribution | 2014-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016348 | 405989245 | Molding | HFTD Tier 2 | Distribution | 2014-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016349 | 405996502 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016350 | 405996557 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016351 | 405996571 | Molding | HFTD Tier 3 | Distribution | 2014-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016352 | 405996620 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-04-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016353 | 405996640 | High Sign | HFTD Tier 3 | Distribution | 2014-04-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016354 | 405996656 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-04-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016355 | 405996673 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-04-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016356 | 405999237 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-04-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016357 | 405999624 | Molding | HFTD Tier 2 | Distribution | 2014-04-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016358 | 405999630 | Molding | HFTD Tier 2 | Distribution | 2014-04-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016359 | 405999631 | Molding | HFTD Tier 2 | Distribution | 2014-04-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016360 | 405999697 | High Sign | HFTD Tier 2 | Distribution | 2014-04-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016361 | 405999706 | Molding | HFTD Tier 2 | Distribution | 2014-04-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016362 | 405999716 | High Sign | HFTD Tier 2 | Distribution | 2014-04-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016363 | 406002788 | High Sign | HFTD Tier 2 | Distribution | 2014-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016364 | 406004198 | High Sign | HFTD Tier 3 | Distribution | 2014-04-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016365 | 406005332 | Molding | HFTD Tier 3 | Distribution | 2014-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016366 | 406005795 | High Sign | HFTD Tier 2 | Distribution | 2014-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016367 | 406007458 | Molding | HFTD Tier 3 | Distribution | 2014-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016368 | 406007459 | Ground | HFTD Tier 3 | Distribution | 2014-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016369 | 406007467 | Molding | HFTD Tier 3 | Distribution | 2014-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016370 | 406007998 | High Sign | HFTD Tier 3 | Distribution | 2014-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016371 | 406007999 | Molding | HFTD Tier 3 | Distribution | 2014-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016372 | 406008002 | Molding | HFTD Tier 3 | Distribution | 2014-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016373 | 406008005 | High Sign | HFTD Tier 3 | Distribution | 2014-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016374 | 406011474 | Molding | HFTD Tier 3 | Distribution | 2014-04-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016375 | 406012802 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016376 | 406013043 | High Sign | HFTD Tier 2 | Distribution | 2014-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016377 | 406013051 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016378 | 406013054 | High Sign | HFTD Tier 2 | Distribution | 2014-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016379 | 406013065 | High Sign | HFTD Tier 2 | Distribution | 2014-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016380 | 406013069 | Molding | HFTD Tier 2 | Distribution | 2014-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016381 | 406013072 | Molding | HFTD Tier 2 | Distribution | 2014-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016382 | 406013075 | High Sign | HFTD Tier 2 | Distribution | 2014-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016383 | 406013082 | High Sign | HFTD Tier 2 | Distribution | 2014-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016384 | 406014887 | Molding | HFTD Tier 3 | Distribution | 2014-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016385 | 406015623 | High Sign | HFTD Tier 3 | Distribution | 2014-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016386 | 406018425 | Molding | HFTD Tier 3 | Distribution | 2014-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016387 | 406018805 | High Sign | HFTD Tier 2 | Distribution | 2014-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016388 | 406018816 | Molding | HFTD Tier 2 | Distribution | 2014-04-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016389 | 406020115 | Molding | HFTD Tier 3 | Distribution | 2014-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016390 | 406021335 | Molding | HFTD Tier 3 | Distribution | 2014-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016391 | 406021336 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016392 | 406021346 | Molding | HFTD Tier 3 | Distribution | 2014-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016393 | 406023836 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016394 | 406023842 | Bond | HFTD Tier 2 | Distribution | 2014-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016395 | 406023845 | Guy | HFTD Tier 2 | Distribution | 2014-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016396 | 406024205 | High Sign | HFTD Tier 2 | Distribution | 2014-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016397 | 406025456 | Guy | HFTD Tier 3 | Distribution | 2014-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016398 | 406025480 | High Sign | HFTD Tier 3 | Distribution | 2014-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016399 | 406025696 | Guy | HFTD Tier 3 | Distribution | 2014-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016400 | 406025709 | High Sign | HFTD Tier 3 | Distribution | 2014-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016401 | 406027528 | High Sign | HFTD Tier 2 | Distribution | 2014-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016402 | 406027537 | High Sign | HFTD Tier 2 | Distribution | 2014-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016403 | 406027594 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016404 | 406027597 | Molding | HFTD Tier 2 | Distribution | 2014-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016405 | 406027606 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016406 | 406028409 | High Sign | HFTD Tier 3 | Distribution | 2014-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016407 | 406029439 | Molding | HFTD Tier 3 | Distribution | 2014-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016408 | 406029824 | Molding | HFTD Tier 2 | Distribution | 2014-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016409 | 406031639 | Molding | HFTD Tier 2 | Distribution | 2014-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016410 | 406031650 | Riser/Conduit | HFTD Tier 2 | Distribution | 2014-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016411 | 406031656 | High Sign | HFTD Tier 2 | Distribution | 2014-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016412 | 406031711 | High Sign | HFTD Tier 2 | Distribution | 2014-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016413 | 406034429 | High Sign | HFTD Tier 2 | Distribution | 2014-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016414 | 406035679 | Guy | HFTD Tier 2 | Distribution | 2014-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016415 | 406035703 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016416 | 406035705 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016417 | 406035976 | Riser/Conduit | HFTD Tier 3 | Distribution | 2014-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016418 | 406036000 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016419 | 406037575 | Molding | HFTD Tier 2 | Distribution | 2014-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016420 | 406044397 | High Sign | HFTD Tier 3 | Distribution | 2014-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016421 | 406044399 | High Sign | HFTD Tier 3 | Distribution | 2014-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016422 | 406047559 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016423 | 406047663 | Molding | HFTD Tier 2 | Distribution | 2014-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016424 | 406047665 | High Sign | HFTD Tier 2 | Distribution | 2014-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016425 | 406047666 | High Sign | HFTD Tier 2 | Distribution | 2014-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016426 | 406051719 | High Sign | HFTD Tier 3 | Distribution | 2014-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016427 | 406051725 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016428 | 406051744 | High Sign | HFTD Tier 3 | Distribution | 2014-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016429 | 406055759 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2014-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016430 | 406055887 | Riser/Conduit | HFTD Tier 3 | Distribution | 2014-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016431 | 406055912 | Guy | HFTD Tier 3 | Distribution | 2014-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016432 | 406056670 | Molding | HFTD Tier 3 | Distribution | 2014-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016433 | 406057418 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016434 | 406057432 | High Sign | HFTD Tier 2 | Distribution | 2014-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016435 | 406057654 | High Sign | HFTD Tier 3 | Distribution | 2014-04-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016436 | 406057735 | Molding | HFTD Tier 3 | Distribution | 2014-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016437 | 406057737 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016438 | 406057748 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016439 | 406057760 | Molding | HFTD Tier 3 | Distribution | 2014-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016440 | 406057765 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016441 | 406058169 | Guy | HFTD Tier 2 | Distribution | 2014-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016442 | 406058180 | Molding | HFTD Tier 2 | Distribution | 2014-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016443 | 406058183 | Guy | HFTD Tier 2 | Distribution | 2014-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016444 | 406058456 | Guy | HFTD Tier 3 | Distribution | 2014-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016445 | 406058457 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016446 | 406060334 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016447 | 406060336 | Molding | HFTD Tier 2 | Distribution | 2014-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016448 | 406060355 | High Sign | HFTD Tier 2 | Distribution | 2014-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016449 | 406060359 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016450 | 406061940 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2014-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016451 | 406062170 | Guy | HFTD Tier 2 | Distribution | 2014-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016452 | 406063038 | Molding | HFTD Tier 2 | Distribution | 2014-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016453 | 406063415 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016454 | 406063417 | Molding | HFTD Tier 3 | Distribution | 2014-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016455 | 406063449 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016456 | 406063492 | Molding | HFTD Tier 3 | Distribution | 2014-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016457 | 406063528 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016458 | 406063536 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016459 | 406063563 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016460 | 406063580 | Molding | HFTD Tier 3 | Distribution | 2014-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016461 | 406063601 | Guy | HFTD Tier 3 | Distribution | 2014-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016462 | 406063790 | High Sign | HFTD Tier 3 | Distribution | 2014-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016463 | 406064451 | Molding | HFTD Tier 2 | Distribution | 2014-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016464 | 406065532 | Molding | HFTD Tier 3 | Distribution | 2014-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016465 | 406066558 | High Sign | HFTD Tier 3 | Distribution | 2014-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016466 | 406066559 | Molding | HFTD Tier 3 | Distribution | 2014-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016467 | 406066567 | Guy | HFTD Tier 3 | Distribution | 2014-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016468 | 406066568 | Molding | HFTD Tier 3 | Distribution | 2014-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016469 | 406066572 | High Sign | HFTD Tier 3 | Distribution | 2014-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016470 | 406066574 | Molding | HFTD Tier 3 | Distribution | 2014-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016471 | 406066578 | High Sign | HFTD Tier 3 | Distribution | 2014-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016472 | 406066590 | High Sign | HFTD Tier 3 | Distribution | 2014-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016473 | 406068113 | Molding | HFTD Tier 3 | Distribution | 2014-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016474 | 406070355 | Guy | HFTD Tier 2 | Distribution | 2014-05-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016475 | 406070363 | Molding | HFTD Tier 3 | Distribution | 2014-05-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016476 | 406070370 | Guy | HFTD Tier 3 | Distribution | 2014-05-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016477 | 406070655 | Molding | HFTD Tier 2 | Distribution | 2014-05-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016478 | 406071280 | High Sign | HFTD Tier 3 | Distribution | 2014-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016479 | 406072508 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016480 | 406072517 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016481 | 406072524 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016482 | 406072798 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016483 | 406072820 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016484 | 406073722 | Molding | HFTD Tier 3 | Distribution | 2014-05-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016485 | 406073736 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-05-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016486 | 406076697 | ID Markings | HFTD Tier 3 | Distribution | 2014-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016487 | 406076702 | High Sign | HFTD Tier 3 | Distribution | 2014-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016488 | 406076759 | Riser/Conduit | HFTD Tier 2 | Distribution | 2014-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016489 | 406079159 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016490 | 406081194 | Molding | HFTD Tier 2 | Distribution | 2014-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016491 | 406081471 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016492 | 406081700 | Guy | HFTD Tier 3 | Distribution | 2014-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016493 | 406081718 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016494 | 406085835 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016495 | 406085837 | Molding | HFTD Tier 2 | Distribution | 2014-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016496 | 406085852 | High Sign | HFTD Tier 2 | Distribution | 2014-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016497 | 406085855 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2014-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016498 | 406085955 | Guy | HFTD Tier 3 | Distribution | 2014-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016499 | 406085966 | Guy | HFTD Tier 3 | Distribution | 2014-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016500 | 406085971 | Guy | HFTD Tier 3 | Distribution | 2014-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016501 | 406085972 | Molding | HFTD Tier 3 | Distribution | 2014-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016502 | 406086033 | Molding | HFTD Tier 3 | Distribution | 2014-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016503 | 406091109 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016504 | 406091122 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016505 | 406091130 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016506 | 406091134 | Termination | HFTD Tier 3 | Distribution | 2014-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016507 | 406091201 | Riser/Conduit | HFTD Tier 3 | Distribution | 2014-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016508 | 406091207 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016509 | 406091215 | Guy | HFTD Tier 3 | Distribution | 2014-05-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016510 | 406094795 | Molding | HFTD Tier 3 | Distribution | 2014-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016511 | 406095972 | Insulator | HFTD Tier 2 | Distribution | 2014-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016512 | 406098170 | Guy | HFTD Tier 3 | Distribution | 2014-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016513 | 406098560 | Guy | HFTD Tier 3 | Distribution | 2014-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016514 | 406098565 | High Sign | HFTD Tier 3 | Distribution | 2014-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016515 | 406099969 | Guy | HFTD Tier 3 | Distribution | 2014-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016516 | 406103844 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016517 | 406103872 | High Sign | HFTD Tier 3 | Distribution | 2014-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016518 | 406104919 | High Sign | HFTD Tier 2 | Distribution | 2014-05-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016519 | 406105271 | High Sign | HFTD Tier 3 | Distribution | 2014-05-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016520 | 406105549 | Molding | HFTD Tier 2 | Distribution | 2014-05-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016521 | 406107927 | High Sign | HFTD Tier 3 | Distribution | 2014-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016522 | 406118480 | Molding | HFTD Tier 3 | Distribution | 2014-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016523 | 406118496 | Guy | HFTD Tier 3 | Distribution | 2014-05-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016524 | 406122924 | High Sign | HFTD Tier 3 | Distribution | 2014-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016525 | 406122984 | High Sign | HFTD Tier 3 | Distribution | 2014-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016526 | 406125407 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016527 | 406126757 | Vis Strips | HFTD Tier 2 | Distribution | 2014-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016528 | 406127948 | Molding | HFTD Tier 3 | Distribution | 2014-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016529 | 406128606 | Guy | HFTD Tier 3 | Distribution | 2014-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016530 | 406128667 | Molding | HFTD Tier 3 | Distribution | 2014-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016531 | 406128673 | High Sign | HFTD Tier 3 | Distribution | 2014-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016532 | 406128680 | High Sign | HFTD Tier 3 | Distribution | 2014-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016533 | 406133415 | Ground | HFTD Tier 3 | Distribution | 2014-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016534 | 406133421 | High Sign | HFTD Tier 3 | Distribution | 2014-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016535 | 406136469 | Molding | HFTD Tier 3 | Distribution | 2014-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016536 | 406140537 | Molding | HFTD Tier 2 | Distribution | 2014-05-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016537 | 406141048 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-05-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016538 | 406141052 | High Sign | HFTD Tier 3 | Distribution | 2014-05-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016539 | 406141614 | High Sign | HFTD Tier 3 | Distribution | 2014-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016540 | 406141701 | High Sign | HFTD Tier 3 | Distribution | 2014-05-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016541 | 406141750 | High Sign | HFTD Tier 3 | Distribution | 2014-05-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016542 | 406141752 | High Sign | HFTD Tier 3 | Distribution | 2014-05-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016543 | 406141839 | Molding | HFTD Tier 3 | Distribution | 2014-05-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016544 | 406142472 | High Sign | HFTD Tier 2 | Distribution | 2014-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016545 | 406145183 | Molding | HFTD Tier 3 | Distribution | 2014-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016546 | 406145630 | High Sign | HFTD Tier 2 | Distribution | 2014-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016547 | 406147686 | High Sign | HFTD Tier 3 | Distribution | 2014-05-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016548 | 406154681 | High Sign | HFTD Tier 3 | Distribution | 2014-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016549 | 406156372 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016550 | 406156408 | High Sign | HFTD Tier 3 | Distribution | 2014-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016551 | 406156909 | Guy | HFTD Tier 3 | Distribution | 2014-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016552 | 406156920 | Guy | HFTD Tier 3 | Distribution | 2014-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016553 | 406157424 | Guy | HFTD Tier 3 | Distribution | 2014-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016554 | 406157426 | Guy | HFTD Tier 3 | Distribution | 2014-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016555 | 406157430 | Guy | HFTD Tier 3 | Distribution | 2014-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016556 | 406159650 | Molding | HFTD Tier 3 | Distribution | 2014-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016557 | 406160869 | High Sign | HFTD Tier 3 | Distribution | 2014-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016558 | 406160874 | Molding | HFTD Tier 3 | Distribution | 2014-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016559 | 406160876 | High Sign | HFTD Tier 3 | Distribution | 2014-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016560 | 406163448 | Molding | HFTD Tier 3 | Distribution | 2014-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016561 | 406163485 | High Sign | HFTD Tier 2 | Distribution | 2014-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016562 | 406165807 | Molding | HFTD Tier 3 | Distribution | 2014-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016563 | 406165808 | High Sign | HFTD Tier 3 | Distribution | 2014-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016564 | 406165809 | Molding | HFTD Tier 3 | Distribution | 2014-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016565 | 406167548 | High Sign | HFTD Tier 2 | Distribution | 2014-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016566 | 406167551 | Molding | HFTD Tier 2 | Distribution | 2014-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016567 | 406167553 | Molding | HFTD Tier 2 | Distribution | 2014-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016568 | 406167559 | High Sign | HFTD Tier 2 | Distribution | 2014-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016569 | 406167596 | Molding | HFTD Tier 3 | Distribution | 2014-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016570 | 406168358 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016571 | 406168479 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016572 | 406168487 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016573 | 406170293 | Guy | HFTD Tier 2 | Distribution | 2014-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016574 | 406170807 | Molding | HFTD Tier 2 | Distribution | 2014-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016575 | 406174019 | Guy | HFTD Tier 2 | Distribution | 2014-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016576 | 406174031 | Guy | HFTD Tier 2 | Distribution | 2014-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016577 | 406174290 | ID Markings | HFTD Tier 3 | Distribution | 2014-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016578 | 406175247 | Bond | HFTD Tier 2 | Distribution | 2014-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016579 | 406175943 | High Sign | HFTD Tier 2 | Distribution | 2014-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016580 | 406177537 | High Sign | HFTD Tier 2 | Distribution | 2014-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016581 | 406177585 | Molding | HFTD Tier 2 | Distribution | 2014-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016582 | 406178802 | Molding | HFTD Tier 2 | Distribution | 2014-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016583 | 406180199 | High Sign | HFTD Tier 3 | Distribution | 2014-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016584 | 406180423 | Guy | HFTD Tier 3 | Distribution | 2014-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016585 | 406180798 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016586 | 406180802 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016587 | 406180805 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016588 | 406182664 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2014-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016589 | 406183403 | Guy | HFTD Tier 3 | Distribution | 2014-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016590 | 406183421 | Guy | HFTD Tier 3 | Distribution | 2014-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016591 | 406186119 | Guy | HFTD Tier 3 | Distribution | 2014-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016592 | 406186374 | Molding | HFTD Tier 2 | Distribution | 2014-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016593 | 406186375 | Molding | HFTD Tier 2 | Distribution | 2014-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016594 | 406186377 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016595 | 406186774 | High Sign | HFTD Tier 2 | Distribution | 2014-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016596 | 406189374 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2014-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016597 | 406189380 | Molding | HFTD Tier 2 | Distribution | 2014-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016598 | 406192072 | High Sign | HFTD Tier 3 | Distribution | 2014-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016599 | 406200606 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016600 | 406203854 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-06-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016601 | 406204674 | Molding | HFTD Tier 2 | Distribution | 2014-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016602 | 406204690 | High Sign | HFTD Tier 2 | Distribution | 2014-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016603 | 406207449 | High Sign | HFTD Tier 2 | Distribution | 2014-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016604 | 406207671 | Guy | HFTD Tier 2 | Distribution | 2014-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016605 | 406208226 | High Sign | HFTD Tier 2 | Distribution | 2014-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016606 | 406208240 | High Sign | HFTD Tier 2 | Distribution | 2014-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016607 | 406208242 | High Sign | HFTD Tier 2 | Distribution | 2014-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016608 | 406208243 | High Sign | HFTD Tier 2 | Distribution | 2014-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016609 | 406208244 | High Sign | HFTD Tier 2 | Distribution | 2014-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016610 | 406208424 | Molding | HFTD Tier 2 | Distribution | 2014-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016611 | 406208430 | High Sign | HFTD Tier 2 | Distribution | 2014-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016612 | 406208494 | Molding | HFTD Tier 3 | Distribution | 2014-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016613 | 406209142 | High Sign | HFTD Tier 2 | Distribution | 2014-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016614 | 406209513 | Molding | HFTD Tier 3 | Distribution | 2014-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016615 | 406211007 | High Sign | HFTD Tier 2 | Distribution | 2014-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016616 | 406211008 | High Sign | HFTD Tier 2 | Distribution | 2014-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016617 | 406211014 | High Sign | HFTD Tier 2 | Distribution | 2014-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016618 | 406216922 | High Sign | HFTD Tier 2 | Distribution | 2014-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016619 | 406217833 | Molding | HFTD Tier 3 | Distribution | 2014-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016620 | 406217926 | Guy | HFTD Tier 3 | Distribution | 2014-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016621 | 406217935 | High Sign | HFTD Tier 3 | Distribution | 2014-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016622 | 406217949 | Molding | HFTD Tier 3 | Distribution | 2014-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016623 | 406217950 | Molding | HFTD Tier 3 | Distribution | 2014-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016624 | 406218164 | Molding | HFTD Tier 3 | Distribution | 2014-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016625 | 406218219 | Guy | HFTD Tier 3 | Distribution | 2014-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016626 | 406218235 | Guy | HFTD Tier 3 | Distribution | 2014-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016627 | 406218241 | Molding | HFTD Tier 3 | Distribution | 2014-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016628 | 406218243 | High Sign | HFTD Tier 3 | Distribution | 2014-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016629 | 406218251 | Molding | HFTD Tier 3 | Distribution | 2014-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016630 | 406218799 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016631 | 406220075 | Molding | HFTD Tier 3 | Distribution | 2014-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016632 | 406222297 | Guy | HFTD Tier 3 | Distribution | 2014-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016633 | 406222328 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016634 | 406222340 | Guy | HFTD Tier 3 | Distribution | 2014-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016635 | 406225055 | Molding | HFTD Tier 3 | Distribution | 2014-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016636 | 406225571 | Guy | HFTD Tier 3 | Distribution | 2014-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016637 | 406225964 | Molding | HFTD Tier 3 | Distribution | 2014-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016638 | 406225998 | Guy | HFTD Tier 3 | Distribution | 2014-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016639 | 406226161 | Molding | HFTD Tier 3 | Distribution | 2014-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016640 | 406226338 | High Sign | HFTD Tier 2 | Distribution | 2014-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016641 | 406226339 | High Sign | HFTD Tier 2 | Distribution | 2014-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016642 | 406226415 | High Sign | HFTD Tier 2 | Distribution | 2014-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016643 | 406226452 | High Sign | HFTD Tier 2 | Distribution | 2014-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016644 | 406228874 | High Sign | HFTD Tier 2 | Distribution | 2014-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016645 | 406228882 | High Sign | HFTD Tier 2 | Distribution | 2014-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016646 | 406228927 | High Sign | HFTD Tier 2 | Distribution | 2014-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016647 | 406228929 | High Sign | HFTD Tier 2 | Distribution | 2014-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016648 | 406229201 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-07-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016649 | 406229675 | Guy | HFTD Tier 3 | Distribution | 2014-07-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016650 | 406229676 | Guy | HFTD Tier 3 | Distribution | 2014-07-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016651 | 406229777 | Guy | HFTD Tier 3 | Distribution | 2014-07-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016652 | 406234889 | Guy | HFTD Tier 3 | Distribution | 2014-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016653 | 406235984 | Molding | HFTD Tier 3 | Distribution | 2014-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016654 | 406237629 | Molding | HFTD Tier 3 | Distribution | 2014-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016655 | 406237825 | Molding | HFTD Tier 3 | Distribution | 2014-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016656 | 406237840 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016657 | 406237850 | Molding | HFTD Tier 3 | Distribution | 2014-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016658 | 406238900 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016659 | 406239360 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016660 | 406239370 | High Sign | HFTD Tier 3 | Distribution | 2014-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016661 | 406240851 | Guy | HFTD Tier 3 | Distribution | 2014-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016662 | 406241456 | Molding | HFTD Tier 3 | Distribution | 2014-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016663 | 406241465 | Guy | HFTD Tier 3 | Distribution | 2014-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016664 | 406241514 | Molding | HFTD Tier 3 | Distribution | 2014-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016665 | 406241515 | Guy | HFTD Tier 3 | Distribution | 2014-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016666 | 406245167 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-07-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016667 | 406246934 | High Sign | HFTD Tier 2 | Distribution | 2014-07-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016668 | 406250652 | High Sign | HFTD Tier 3 | Distribution | 2014-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016669 | 406250789 | High Sign | HFTD Tier 3 | Distribution | 2014-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016670 | 406250798 | High Sign | HFTD Tier 3 | Distribution | 2014-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016671 | 406250971 | Guy | HFTD Tier 3 | Distribution | 2014-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016672 | 406251050 | Molding | HFTD Tier 3 | Distribution | 2014-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016673 | 406254149 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016674 | 406254513 | High Sign | HFTD Tier 2 | Distribution | 2014-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016675 | 406254755 | Guy | HFTD Tier 3 | Distribution | 2014-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016676 | 406257538 | Guy | HFTD Tier 3 | Distribution | 2014-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016677 | 406257616 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016678 | 406257617 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016679 | 406257770 | Guy | HFTD Tier 3 | Distribution | 2014-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016680 | 406258117 | Riser/Conduit | HFTD Tier 2 | Distribution | 2014-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016681 | 406258568 | High Sign | HFTD Tier 2 | Distribution | 2014-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016682 | 406262082 | Molding | HFTD Tier 2 | Distribution | 2014-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016683 | 406262197 | High Sign | HFTD Tier 2 | Distribution | 2014-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016684 | 406262318 | Guy | HFTD Tier 3 | Distribution | 2014-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016685 | 406262319 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016686 | 406262340 | Molding | HFTD Tier 3 | Distribution | 2014-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016687 | 406262617 | Guy | HFTD Tier 2 | Distribution | 2014-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016688 | 406262618 | Guy | HFTD Tier 2 | Distribution | 2014-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016689 | 406265027 | Molding | HFTD Tier 3 | Distribution | 2014-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016690 | 406265121 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016691 | 406265464 | Guy | HFTD Tier 2 | Distribution | 2014-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016692 | 406265822 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016693 | 406266334 | Molding | HFTD Tier 2 | Distribution | 2014-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016694 | 406267119 | High Sign | HFTD Tier 3 | Distribution | 2014-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016695 | 406269108 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016696 | 406269115 | Molding | HFTD Tier 3 | Distribution | 2014-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016697 | 406269145 | Molding | HFTD Tier 3 | Distribution | 2014-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016698 | 406269153 | Molding | HFTD Tier 3 | Distribution | 2014-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016699 | 406269948 | Guy | HFTD Tier 2 | Distribution | 2014-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016700 | 406270062 | Molding | HFTD Tier 3 | Distribution | 2014-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016701 | 406270386 | Riser/Conduit | HFTD Tier 3 | Distribution | 2014-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016702 | 406270811 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016703 | 406271094 | High Sign | HFTD Tier 2 | Distribution | 2014-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016704 | 406271095 | Molding | HFTD Tier 2 | Distribution | 2014-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016705 | 406271256 | Molding | HFTD Tier 3 | Distribution | 2014-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016706 | 406271845 | Guy | HFTD Tier 2 | Distribution | 2014-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016707 | 406272418 | Molding | HFTD Tier 2 | Distribution | 2014-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016708 | 406273754 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016709 | 406273842 | High Sign | HFTD Tier 3 | Distribution | 2014-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016710 | 406273850 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016711 | 406274126 | Guy | HFTD Tier 2 | Distribution | 2014-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016712 | 406274139 | Guy | HFTD Tier 3 | Distribution | 2014-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016713 | 406274144 | Guy | HFTD Tier 2 | Distribution | 2014-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016714 | 406274157 | High Sign | HFTD Tier 3 | Distribution | 2014-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016715 | 406274172 | Guy | HFTD Tier 3 | Distribution | 2014-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016716 | 406274220 | Guy | HFTD Tier 2 | Distribution | 2014-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016717 | 406274461 | Guy | HFTD Tier 2 | Distribution | 2014-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016718 | 406274536 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016719 | 406274547 | Guy | HFTD Tier 2 | Distribution | 2014-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016720 | 406274664 | High Sign | HFTD Tier 2 | Distribution | 2014-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016721 | 406274666 | Guy | HFTD Tier 2 | Distribution | 2014-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016722 | 406274674 | Guy | HFTD Tier 2 | Distribution | 2014-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016723 | 406274758 | High Sign | HFTD Tier 3 | Distribution | 2014-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016724 | 406278228 | Guy | HFTD Tier 3 | Distribution | 2014-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016725 | 406278468 | Guy | HFTD Tier 3 | Distribution | 2014-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016726 | 406279830 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016727 | 406279854 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016728 | 406280984 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016729 | 406281138 | High Sign | HFTD Tier 3 | Distribution | 2014-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016730 | 406281253 | Molding | HFTD Tier 2 | Distribution | 2014-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016731 | 406281263 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016732 | 406281371 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-07-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016733 | 406281799 | Molding | HFTD Tier 3 | Distribution | 2014-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016734 | 406283838 | High Sign | HFTD Tier 3 | Distribution | 2014-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016735 | 406284421 | High Sign | HFTD Tier 3 | Distribution | 2014-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016736 | 406285163 | Guy | HFTD Tier 3 | Distribution | 2014-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016737 | 406285171 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016738 | 406285629 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2014-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016739 | 406285757 | High Sign | HFTD Tier 2 | Distribution | 2014-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016740 | 406286455 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016741 | 406286467 | Riser/Conduit | HFTD Tier 2 | Distribution | 2014-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016742 | 406286534 | High Sign | HFTD Tier 3 | Distribution | 2014-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016743 | 406286592 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016744 | 406287885 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016745 | 406287914 | High Sign | HFTD Tier 3 | Distribution | 2014-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016746 | 406289100 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016747 | 406289105 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016748 | 406289369 | Molding | HFTD Tier 3 | Distribution | 2014-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016749 | 406289806 | Molding | HFTD Tier 2 | Distribution | 2014-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016750 | 406289815 | High Sign | HFTD Tier 2 | Distribution | 2014-07-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016751 | 406290959 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016752 | 406290980 | Guy | HFTD Tier 2 | Distribution | 2014-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016753 | 406291004 | Molding | HFTD Tier 2 | Distribution | 2014-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016754 | 406291125 | Molding | HFTD Tier 2 | Distribution | 2014-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016755 | 406291435 | High Sign | HFTD Tier 2 | Distribution | 2014-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016756 | 406291452 | Molding | HFTD Tier 3 | Distribution | 2014-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016757 | 406292093 | Guy | HFTD Tier 3 | Distribution | 2014-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016758 | 406293621 | Molding | HFTD Tier 2 | Distribution | 2014-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016759 | 406294058 | High Sign | HFTD Tier 3 | Distribution | 2014-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016760 | 406294075 | Molding | HFTD Tier 3 | Distribution | 2014-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016761 | 406294104 | High Sign | HFTD Tier 3 | Distribution | 2014-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016762 | 406294105 | Guy | HFTD Tier 3 | Distribution | 2014-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016763 | 406294112 | Guy | HFTD Tier 3 | Distribution | 2014-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016764 | 406294121 | Guy | HFTD Tier 3 | Distribution | 2014-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016765 | 406294875 | Guy | HFTD Tier 2 | Distribution | 2014-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016766 | 406296842 | ID Markings | HFTD Tier 3 | Distribution | 2014-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016767 | 406298210 | High Sign | HFTD Tier 2 | Distribution | 2014-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016768 | 406299468 | High Sign | HFTD Tier 3 | Distribution | 2014-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016769 | 406299927 | Guy | HFTD Tier 2 | Distribution | 2014-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016770 | 406300078 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2014-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016771 | 406300967 | High Sign | HFTD Tier 3 | Distribution | 2014-07-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016772 | 406303476 | Molding | HFTD Tier 3 | Distribution | 2014-07-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016773 | 406303497 | High Sign | HFTD Tier 3 | Distribution | 2014-07-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016774 | 406303498 | High Sign | HFTD Tier 3 | Distribution | 2014-07-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016775 | 406303505 | High Sign | HFTD Tier 3 | Distribution | 2014-07-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016776 | 406303509 | High Sign | HFTD Tier 3 | Distribution | 2014-07-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016777 | 406303510 | High Sign | HFTD Tier 3 | Distribution | 2014-07-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016778 | 406303522 | Molding | HFTD Tier 3 | Distribution | 2014-07-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016779 | 406303606 | Guy | HFTD Tier 3 | Distribution | 2014-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016780 | 406303700 | Molding | HFTD Tier 3 | Distribution | 2014-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016781 | 406303728 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016782 | 406303752 | High Sign | HFTD Tier 3 | Distribution | 2014-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016783 | 406303754 | Molding | HFTD Tier 3 | Distribution | 2014-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016784 | 406303755 | High Sign | HFTD Tier 3 | Distribution | 2014-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016785 | 406303781 | Molding | HFTD Tier 3 | Distribution | 2014-07-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016786 | 406303818 | High Sign | HFTD Tier 3 | Distribution | 2014-07-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016787 | 406303841 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-07-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016788 | 406303857 | High Sign | HFTD Tier 3 | Distribution | 2014-07-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016789 | 406303859 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-07-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016790 | 406303860 | High Sign | HFTD Tier 3 | Distribution | 2014-07-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016791 | 406304254 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-07-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016792 | 406304569 | High Sign | HFTD Tier 2 | Distribution | 2014-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016793 | 406304810 | High Sign | HFTD Tier 2 | Distribution | 2014-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016794 | 406304860 | High Sign | HFTD Tier 3 | Distribution | 2014-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016795 | 406305107 | High Sign | HFTD Tier 3 | Distribution | 2014-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016796 | 406305218 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2014-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016797 | 406306161 | High Sign | HFTD Tier 3 | Distribution | 2014-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016798 | 406306167 | Guy | HFTD Tier 3 | Distribution | 2014-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016799 | 406307495 | High Sign | HFTD Tier 3 | Distribution | 2014-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016800 | 406307547 | High Sign | HFTD Tier 3 | Distribution | 2014-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016801 | 406307616 | High Sign | HFTD Tier 2 | Distribution | 2014-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016802 | 406307630 | Riser/Conduit | HFTD Tier 2 | Distribution | 2014-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016803 | 406307833 | High Sign | HFTD Tier 3 | Distribution | 2014-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016804 | 406307850 | Molding | HFTD Tier 3 | Distribution | 2014-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016805 | 406307851 | Molding | HFTD Tier 3 | Distribution | 2014-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016806 | 406309278 | High Sign | HFTD Tier 3 | Distribution | 2014-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016807 | 406309302 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016808 | 406309898 | Bond | HFTD Tier 3 | Distribution | 2014-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016809 | 406310292 | Guy | HFTD Tier 3 | Distribution | 2014-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016810 | 406311720 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2014-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016811 | 406312849 | High Sign | HFTD Tier 3 | Distribution | 2014-08-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016812 | 406313925 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016813 | 406313926 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016814 | 406313940 | Molding | HFTD Tier 2 | Distribution | 2014-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016815 | 406313947 | Molding | HFTD Tier 2 | Distribution | 2014-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016816 | 406313960 | Molding | HFTD Tier 2 | Distribution | 2014-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016817 | 406313961 | Molding | HFTD Tier 2 | Distribution | 2014-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016818 | 406316459 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-08-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016819 | 406321912 | Molding | HFTD Tier 3 | Distribution | 2014-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016820 | 406322229 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016821 | 406322266 | High Sign | HFTD Tier 3 | Distribution | 2014-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016822 | 406323542 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016823 | 406323647 | High Sign | HFTD Tier 3 | Distribution | 2014-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016824 | 406325120 | High Sign | HFTD Tier 3 | Distribution | 2014-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016825 | 406325135 | Insulator | HFTD Tier 3 | Distribution | 2014-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016826 | 406325267 | Guy | HFTD Tier 3 | Distribution | 2014-08-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016827 | 406326657 | Guy | HFTD Tier 3 | Distribution | 2014-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016828 | 406327694 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016829 | 406327833 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016830 | 406327834 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016831 | 406327835 | High Sign | HFTD Tier 3 | Distribution | 2014-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016832 | 406328282 | High Sign | HFTD Tier 3 | Distribution | 2014-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016833 | 406329415 | Molding | HFTD Tier 3 | Distribution | 2014-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016834 | 406329417 | High Sign | HFTD Tier 3 | Distribution | 2014-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016835 | 406329430 | Molding | HFTD Tier 3 | Distribution | 2014-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016836 | 406330190 | Guy | HFTD Tier 3 | Distribution | 2014-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016837 | 406331564 | Guy | HFTD Tier 3 | Distribution | 2014-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016838 | 406331571 | Riser/Conduit | HFTD Tier 3 | Distribution | 2014-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016839 | 406332207 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016840 | 406332539 | Guy | HFTD Tier 3 | Distribution | 2014-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016841 | 406332658 | High Sign | HFTD Tier 3 | Distribution | 2014-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016842 | 406332665 | High Sign | HFTD Tier 3 | Distribution | 2014-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016843 | 406332671 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016844 | 406332739 | Guy | HFTD Tier 3 | Distribution | 2014-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016845 | 406333388 | High Sign | HFTD Tier 2 | Distribution | 2014-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016846 | 406333391 | Termination | HFTD Tier 3 | Distribution | 2014-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016847 | 406333744 | High Sign | HFTD Tier 3 | Distribution | 2014-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016848 | 406336979 | Molding | HFTD Tier 2 | Distribution | 2014-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016849 | 406337456 | High Sign | HFTD Tier 3 | Distribution | 2014-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016850 | 406337457 | Molding | HFTD Tier 3 | Distribution | 2014-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016851 | 406337458 | High Sign | HFTD Tier 3 | Distribution | 2014-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016852 | 406337461 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016853 | 406338241 | Molding | HFTD Tier 3 | Distribution | 2014-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016854 | 406338254 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016855 | 406338264 | High Sign | HFTD Tier 3 | Distribution | 2014-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016856 | 406338281 | High Sign | HFTD Tier 3 | Distribution | 2014-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016857 | 406338282 | Termination | HFTD Tier 3 | Distribution | 2014-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016858 | 406338667 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2014-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016859 | 406338676 | High Sign | HFTD Tier 2 | Distribution | 2014-08-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016860 | 406339026 | Molding | HFTD Tier 3 | Distribution | 2014-08-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016861 | 406341164 | High Sign | HFTD Tier 3 | Distribution | 2014-08-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016862 | 406341751 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-08-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016863 | 406341764 | Guy | HFTD Tier 3 | Distribution | 2014-08-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016864 | 406341765 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-08-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016865 | 406341829 | Molding | HFTD Tier 3 | Distribution | 2014-08-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016866 | 406341834 | High Sign | HFTD Tier 3 | Distribution | 2014-08-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016867 | 406342589 | High Sign | HFTD Tier 3 | Distribution | 2014-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016868 | 406342597 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016869 | 406343620 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016870 | 406343876 | Guy | HFTD Tier 3 | Distribution | 2014-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016871 | 406343877 | Guy | HFTD Tier 3 | Distribution | 2014-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016872 | 406344006 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016873 | 406344142 | Guy | HFTD Tier 3 | Distribution | 2014-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016874 | 406344143 | High Sign | HFTD Tier 3 | Distribution | 2014-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016875 | 406344145 | High Sign | HFTD Tier 3 | Distribution | 2014-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016876 | 406344147 | Guy | HFTD Tier 3 | Distribution | 2014-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016877 | 406344158 | Guy | HFTD Tier 3 | Distribution | 2014-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016878 | 406344159 | High Sign | HFTD Tier 3 | Distribution | 2014-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016879 | 406344190 | High Sign | HFTD Tier 3 | Distribution | 2014-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016880 | 406345870 | Guy | HFTD Tier 2 | Distribution | 2014-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016881 | 406346146 | Molding | HFTD Tier 3 | Distribution | 2014-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016882 | 406347135 | Molding | HFTD Tier 2 | Distribution | 2014-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016883 | 406347164 | Guy | HFTD Tier 2 | Distribution | 2014-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016884 | 406347457 | High Sign | HFTD Tier 2 | Distribution | 2014-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016885 | 406348274 | Molding | HFTD Tier 3 | Distribution | 2014-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016886 | 406348277 | Molding | HFTD Tier 3 | Distribution | 2014-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016887 | 406349489 | Guy | HFTD Tier 3 | Distribution | 2014-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016888 | 406351117 | High Sign | HFTD Tier 3 | Distribution | 2014-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016889 | 406351754 | Guy | HFTD Tier 2 | Distribution | 2014-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016890 | 406351758 | Guy | HFTD Tier 2 | Distribution | 2014-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016891 | 406351796 | Guy | HFTD Tier 2 | Distribution | 2014-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016892 | 406352934 | Guy | HFTD Tier 2 | Distribution | 2014-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016893 | 406353786 | High Sign | HFTD Tier 2 | Distribution | 2014-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016894 | 406353790 | High Sign | HFTD Tier 2 | Distribution | 2014-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016895 | 406353795 | Guy | HFTD Tier 2 | Distribution | 2014-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016896 | 406353796 | High Sign | HFTD Tier 2 | Distribution | 2014-08-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016897 | 406357625 | Guy | HFTD Tier 2 | Distribution | 2014-08-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016898 | 406357628 | Guy | HFTD Tier 2 | Distribution | 2014-08-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016899 | 406357641 | Guy | HFTD Tier 2 | Distribution | 2014-08-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016900 | 406359133 | High Sign | HFTD Tier 3 | Distribution | 2014-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016901 | 406359256 | Guy | HFTD Tier 3 | Distribution | 2014-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016902 | 406359395 | Guy | HFTD Tier 3 | Distribution | 2014-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016903 | 406359415 | Guy | HFTD Tier 3 | Distribution | 2014-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016904 | 406359453 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016905 | 406359934 | Guy | HFTD Tier 3 | Distribution | 2014-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016906 | 406360038 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016907 | 406362944 | High Sign | HFTD Tier 2 | Distribution | 2014-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016908 | 406362945 | Molding | HFTD Tier 2 | Distribution | 2014-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016909 | 406363720 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016910 | 406363775 | High Sign | HFTD Tier 3 | Distribution | 2014-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016911 | 406365223 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016912 | 406365225 | Guy | HFTD Tier 3 | Distribution | 2014-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016913 | 406366199 | Riser/Conduit | HFTD Tier 3 | Distribution | 2014-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016914 | 406368304 | Molding | HFTD Tier 3 | Distribution | 2014-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016915 | 406368597 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016916 | 406369089 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016917 | 406369872 | Molding | HFTD Tier 2 | Distribution | 2014-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016918 | 406370176 | High Sign | HFTD Tier 3 | Distribution | 2014-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016919 | 406372906 | Molding | HFTD Tier 3 | Distribution | 2014-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016920 | 406374058 | Guy | HFTD Tier 3 | Distribution | 2014-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016921 | 406374814 | Right of Way | HFTD Tier 2 | Transmission | 2014-08-21 | 1937-04-22 | 2 | [7 empty] | SCE | 2025 | 4
1130016922 | 406374834 | Molding | HFTD Tier 3 | Distribution | 2014-08-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016923 | 406377937 | Guy | HFTD Tier 3 | Distribution | 2014-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016924 | 406377945 | Guy | HFTD Tier 3 | Distribution | 2014-08-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016925 | 406379358 | High Sign | HFTD Tier 3 | Distribution | 2014-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016926 | 406379710 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016927 | 406380463 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-08-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016928 | 406384330 | Molding | HFTD Tier 3 | Distribution | 2014-08-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016929 | 406385094 | High Sign | HFTD Tier 3 | Distribution | 2014-08-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016930 | 406385095 | Molding | HFTD Tier 3 | Distribution | 2014-08-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016931 | 406387706 | High Sign | HFTD Tier 2 | Distribution | 2014-08-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016932 | 406387707 | High Sign | HFTD Tier 2 | Distribution | 2014-08-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016933 | 406387709 | High Sign | HFTD Tier 2 | Distribution | 2014-08-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016934 | 406387710 | High Sign | HFTD Tier 2 | Distribution | 2014-08-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016935 | 406387850 | High Sign | HFTD Tier 3 | Distribution | 2014-08-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016936 | 406389395 | Molding | HFTD Tier 2 | Distribution | 2014-08-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016937 | 406389454 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2014-08-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016938 | 406391401 | Guy | HFTD Tier 3 | Distribution | 2014-08-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016939 | 406391855 | Molding | HFTD Tier 3 | Distribution | 2014-08-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016940 | 406391897 | High Sign | HFTD Tier 3 | Distribution | 2014-08-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016941 | 406391898 | Molding | HFTD Tier 3 | Distribution | 2014-08-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016942 | 406392241 | Guy | HFTD Tier 2 | Distribution | 2014-08-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016943 | 406392312 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-08-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016944 | 406392337 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-08-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016945 | 406392343 | Molding | HFTD Tier 3 | Distribution | 2014-08-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016946 | 406392647 | High Sign | HFTD Tier 2 | Distribution | 2014-08-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016947 | 406393394 | High Sign | HFTD Tier 3 | Distribution | 2014-08-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016948 | 406394193 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-08-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016949 | 406394488 | Molding | HFTD Tier 2 | Distribution | 2014-08-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016950 | 406394590 | Molding | HFTD Tier 2 | Distribution | 2014-08-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016951 | 406395228 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016952 | 406395280 | High Sign | HFTD Tier 2 | Distribution | 2014-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016953 | 406395322 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016954 | 406395324 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-08-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016955 | 406395648 | Molding | HFTD Tier 2 | Distribution | 2014-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016956 | 406396975 | Molding | HFTD Tier 3 | Distribution | 2014-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016957 | 406397861 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-08-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016958 | 406398561 | High Sign | HFTD Tier 3 | Distribution | 2014-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016959 | 406399939 | Molding | HFTD Tier 3 | Distribution | 2014-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016960 | 406399949 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016961 | 406399952 | High Sign | HFTD Tier 3 | Distribution | 2014-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016962 | 406401615 | Molding | HFTD Tier 2 | Distribution | 2014-08-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016963 | 406401973 | Molding | HFTD Tier 2 | Distribution | 2014-09-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016964 | 406403247 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-09-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016965 | 406403576 | High Sign | HFTD Tier 2 | Distribution | 2014-09-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016966 | 406403590 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-09-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016967 | 406403640 | Guy | HFTD Tier 3 | Distribution | 2014-09-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016968 | 406404938 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-09-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016969 | 406404949 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-09-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016970 | 406406300 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-09-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016971 | 406406310 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-09-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016972 | 406407247 | Molding | HFTD Tier 2 | Distribution | 2014-09-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016973 | 406407265 | High Sign | HFTD Tier 2 | Distribution | 2014-09-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016974 | 406407981 | Riser/Conduit | HFTD Tier 2 | Distribution | 2014-09-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016975 | 406408321 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-09-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016976 | 406410128 | High Sign | HFTD Tier 2 | Distribution | 2014-09-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016977 | 406410220 | Guy | HFTD Tier 3 | Distribution | 2014-09-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016978 | 406410385 | High Sign | HFTD Tier 2 | Distribution | 2014-09-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016979 | 406410449 | Guy | HFTD Tier 3 | Distribution | 2014-09-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016980 | 406410464 | Guy | HFTD Tier 3 | Distribution | 2014-09-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016981 | 406410477 | Guy | HFTD Tier 3 | Distribution | 2014-09-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016982 | 406411629 | High Sign | HFTD Tier 3 | Distribution | 2014-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016983 | 406412534 | Molding | HFTD Tier 2 | Distribution | 2014-09-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016984 | 406417427 | High Sign | HFTD Tier 3 | Distribution | 2014-09-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016985 | 406417879 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-09-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016986 | 406418377 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-09-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016987 | 406418393 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-09-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016988 | 406418556 | High Sign | HFTD Tier 2 | Distribution | 2014-09-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016989 | 406419557 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-09-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016990 | 406421126 | High Sign | HFTD Tier 3 | Distribution | 2014-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016991 | 406421132 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016992 | 406422085 | Molding | HFTD Tier 3 | Distribution | 2014-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016993 | 406422224 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016994 | 406422458 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016995 | 406423749 | Molding | HFTD Tier 2 | Distribution | 2014-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016996 | 406423799 | High Sign | HFTD Tier 2 | Distribution | 2014-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016997 | 406423808 | Molding | HFTD Tier 2 | Distribution | 2014-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016998 | 406424096 | High Sign | HFTD Tier 2 | Distribution | 2014-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130016999 | 406424104 | High Sign | HFTD Tier 2 | Distribution | 2014-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017000 | 406426063 | High Sign | HFTD Tier 2 | Distribution | 2014-09-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017001 | 406426071 | High Sign | HFTD Tier 2 | Distribution | 2014-09-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017002 | 406426074 | Insulator | HFTD Tier 2 | Distribution | 2014-09-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017003 | 406426150 | High Sign | HFTD Tier 2 | Distribution | 2014-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017004 | 406427327 | High Sign | HFTD Tier 2 | Distribution | 2014-09-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017005 | 406427329 | High Sign | HFTD Tier 2 | Distribution | 2014-09-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017006 | 406427330 | Molding | HFTD Tier 2 | Distribution | 2014-09-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017007 | 406427335 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-09-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017008 | 406427775 | High Sign | HFTD Tier 3 | Distribution | 2014-09-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017009 | 406429235 | Molding | HFTD Tier 3 | Distribution | 2014-09-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017010 | 406429474 | Molding | HFTD Tier 3 | Distribution | 2014-09-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017011 | 406429544 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-09-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017012 | 406433565 | High Sign | HFTD Tier 3 | Distribution | 2014-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017013 | 406434898 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017014 | 406434910 | High Sign | HFTD Tier 3 | Distribution | 2014-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017015 | 406436311 | High Sign | HFTD Tier 3 | Distribution | 2014-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017016 | 406436419 | Guy | HFTD Tier 3 | Distribution | 2014-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017017 | 406437258 | Molding | HFTD Tier 3 | Distribution | 2014-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017018 | 406437732 | Guy | HFTD Tier 3 | Distribution | 2014-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017019 | 406437832 | Guy | HFTD Tier 3 | Distribution | 2014-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017020 | 406437846 | Molding | HFTD Tier 3 | Distribution | 2014-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017021 | 406437852 | Molding | HFTD Tier 3 | Distribution | 2014-09-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017022 | 406437862 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017023 | 406438832 | High Sign | HFTD Tier 3 | Distribution | 2014-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017024 | 406439752 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-09-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017025 | 406440555 | Molding | HFTD Tier 3 | Distribution | 2014-09-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017026 | 406440619 | High Sign | HFTD Tier 2 | Distribution | 2014-09-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017027 | 406440626 | High Sign | HFTD Tier 2 | Distribution | 2014-09-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017028 | 406441016 | Guy | HFTD Tier 3 | Distribution | 2014-09-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017029 | 406441860 | High Sign | HFTD Tier 2 | Distribution | 2014-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017030 | 406443974 | Molding | HFTD Tier 3 | Distribution | 2014-09-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017031 | 406444255 | High Sign | HFTD Tier 2 | Distribution | 2014-09-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017032 | 406446106 | High Sign | HFTD Tier 3 | Distribution | 2014-09-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017033 | 406446879 | Molding | HFTD Tier 3 | Distribution | 2014-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017034 | 406446944 | Molding | HFTD Tier 3 | Distribution | 2014-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017035 | 406447415 | High Sign | HFTD Tier 3 | Distribution | 2014-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017036 | 406448192 | Molding | HFTD Tier 3 | Distribution | 2014-09-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017037 | 406453447 | High Sign | HFTD Tier 2 | Distribution | 2014-09-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017038 | 406453463 | High Sign | HFTD Tier 2 | Distribution | 2014-09-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017039 | 406454563 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-09-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017040 | 406454572 | Molding | HFTD Tier 3 | Distribution | 2014-09-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017041 | 406461578 | High Sign | HFTD Tier 3 | Distribution | 2014-09-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017042 | 406461580 | Molding | HFTD Tier 3 | Distribution | 2014-09-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017043 | 406461869 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-09-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017044 | 406461881 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-09-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017045 | 406469465 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-09-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017046 | 406471363 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017047 | 406471507 | High Sign | HFTD Tier 3 | Distribution | 2014-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017048 | 406472801 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-09-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017049 | 406475255 | High Sign | HFTD Tier 2 | Distribution | 2014-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017050 | 406475256 | High Sign | HFTD Tier 2 | Distribution | 2014-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017051 | 406475519 | Guy | HFTD Tier 3 | Distribution | 2014-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017052 | 406475659 | High Sign | HFTD Tier 2 | Distribution | 2014-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017053 | 406475842 | High Sign | HFTD Tier 3 | Distribution | 2014-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017054 | 406476335 | High Sign | HFTD Tier 3 | Distribution | 2014-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017055 | 406476832 | Molding | HFTD Tier 2 | Distribution | 2014-09-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017056 | 406479257 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017057 | 406479379 | Guy | HFTD Tier 3 | Distribution | 2014-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017058 | 406482178 | Molding | HFTD Tier 3 | Distribution | 2014-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017059 | 406482190 | High Sign | HFTD Tier 3 | Distribution | 2014-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017060 | 406482191 | High Sign | HFTD Tier 3 | Distribution | 2014-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017061 | 406483847 | Guy | HFTD Tier 3 | Distribution | 2014-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017062 | 406483858 | Guy | HFTD Tier 3 | Distribution | 2014-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017063 | 406484203 | Guy | HFTD Tier 3 | Distribution | 2014-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017064 | 406488514 | Insulator | HFTD Tier 3 | Distribution | 2014-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017065 | 406489284 | High Sign | HFTD Tier 3 | Distribution | 2014-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017066 | 406489581 | High Sign | HFTD Tier 3 | Distribution | 2014-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017067 | 406489635 | Molding | HFTD Tier 2 | Distribution | 2014-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017068 | 406493853 | High Sign | HFTD Tier 3 | Distribution | 2014-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017069 | 406495078 | High Sign | HFTD Tier 3 | Distribution | 2014-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017070 | 406495080 | Molding | HFTD Tier 3 | Distribution | 2014-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017071 | 406495101 | Molding | HFTD Tier 3 | Distribution | 2014-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017072 | 406495102 | Guy | HFTD Tier 3 | Distribution | 2014-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017073 | 406503073 | Guy | HFTD Tier 2 | Distribution | 2014-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017074 | 406503079 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017075 | 406507585 | High Sign | HFTD Tier 2 | Distribution | 2014-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017076 | 406507594 | Molding | HFTD Tier 2 | Distribution | 2014-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017077 | 406512103 | Guy | HFTD Tier 2 | Distribution | 2014-10-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017078 | 406516574 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-10-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017079 | 406517116 | High Sign | HFTD Tier 2 | Distribution | 2014-10-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017080 | 406517117 | High Sign | HFTD Tier 2 | Distribution | 2014-10-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017081 | 406517150 | Molding | HFTD Tier 2 | Distribution | 2014-10-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017082 | 406519439 | Guy | HFTD Tier 3 | Distribution | 2014-10-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017083 | 406519543 | Molding | HFTD Tier 3 | Distribution | 2014-10-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017084 | 406520616 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-10-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017085 | 406520618 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-10-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017086 | 406520728 | Guy | HFTD Tier 3 | Distribution | 2014-10-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017087 | 406523144 | Guy | HFTD Tier 3 | Distribution | 2014-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017088 | 406523390 | High Sign | HFTD Tier 3 | Distribution | 2014-10-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017089 | 406523487 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017090 | 406524166 | Guy | HFTD Tier 3 | Distribution | 2014-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017091 | 406524492 | High Sign | HFTD Tier 2 | Distribution | 2014-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017092 | 406524536 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017093 | 406524543 | Guy | HFTD Tier 2 | Distribution | 2014-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017094 | 406524617 | Molding | HFTD Tier 2 | Distribution | 2014-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017095 | 406525227 | Molding | HFTD Tier 2 | Distribution | 2014-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017096 | 406525382 | Guy | HFTD Tier 2 | Distribution | 2014-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017097 | 406527891 | Guy | HFTD Tier 3 | Distribution | 2014-10-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017098 | 406529325 | Molding | HFTD Tier 2 | Distribution | 2014-10-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017099 | 406529337 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2014-10-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017100 | 406529362 | Guy | HFTD Tier 3 | Distribution | 2014-10-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017101 | 406529409 | High Sign | HFTD Tier 2 | Distribution | 2014-10-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017102 | 406529642 | Riser/Conduit | HFTD Tier 2 | Distribution | 2014-10-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017103 | 406529651 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-10-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017104 | 406532090 | Guy | HFTD Tier 3 | Distribution | 2014-10-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017105 | 406532161 | Guy | HFTD Tier 3 | Distribution | 2014-10-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017106 | 406532677 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-10-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017107 | 406532811 | Guy | HFTD Tier 3 | Distribution | 2014-10-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017108 | 406533267 | Molding | HFTD Tier 2 | Distribution | 2014-10-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017109 | 406533282 | High Sign | HFTD Tier 2 | Distribution | 2014-10-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017110 | 406534831 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-10-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017111 | 406535741 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017112 | 406536422 | High Sign | HFTD Tier 3 | Distribution | 2014-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017113 | 406536862 | Guy | HFTD Tier 3 | Distribution | 2014-10-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017114 | 406539884 | Guy | HFTD Tier 3 | Distribution | 2014-10-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017115 | 406539891 | Molding | HFTD Tier 3 | Distribution | 2014-10-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017116 | 406540868 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-10-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017117 | 406540881 | Molding | HFTD Tier 2 | Distribution | 2014-10-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017118 | 406540882 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-10-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017119 | 406540904 | Molding | HFTD Tier 2 | Distribution | 2014-10-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017120 | 406544003 | Guy | HFTD Tier 3 | Distribution | 2014-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017121 | 406544306 | Molding | HFTD Tier 2 | Distribution | 2014-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017122 | 406544581 | Termination | HFTD Tier 2 | Distribution | 2014-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017123 | 406548640 | Guy | HFTD Tier 2 | Distribution | 2014-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017124 | 406548652 | High Sign | HFTD Tier 2 | Distribution | 2014-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017125 | 406548657 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-10-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017126 | 406550923 | High Sign | HFTD Tier 2 | Distribution | 2014-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017127 | 406552317 | High Sign | HFTD Tier 2 | Distribution | 2014-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017128 | 406554848 | Insulator | HFTD Tier 3 | Distribution | 2014-10-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017129 | 406554884 | Molding | HFTD Tier 3 | Distribution | 2014-10-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017130 | 406554900 | Guy | HFTD Tier 3 | Distribution | 2014-10-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017131 | 406558565 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017132 | 406561782 | High Sign | HFTD Tier 3 | Distribution | 2014-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017133 | 406561785 | High Sign | HFTD Tier 3 | Distribution | 2014-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017134 | 406561794 | High Sign | HFTD Tier 3 | Distribution | 2014-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017135 | 406561806 | Molding | HFTD Tier 3 | Distribution | 2014-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017136 | 406564830 | High Sign | HFTD Tier 2 | Distribution | 2014-10-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017137 | 406564885 | Molding | HFTD Tier 2 | Distribution | 2014-10-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017138 | 406565435 | Molding | HFTD Tier 2 | Distribution | 2014-10-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017139 | 406579441 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-11-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017140 | 406579444 | Molding | HFTD Tier 2 | Distribution | 2014-11-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017141 | 406587636 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-11-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017142 | 406587719 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-11-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017143 | 406588122 | Guy | HFTD Tier 2 | Distribution | 2014-11-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017144 | 406588456 | Molding | HFTD Tier 2 | Distribution | 2014-11-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017145 | 406591046 | Guy | HFTD Tier 2 | Distribution | 2014-11-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017146 | 406594876 | High Sign | HFTD Tier 2 | Distribution | 2014-11-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017147 | 406595996 | Guy | HFTD Tier 2 | Distribution | 2014-11-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017148 | 406596182 | High Sign | HFTD Tier 2 | Distribution | 2014-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017149 | 406596924 | High Sign | HFTD Tier 2 | Distribution | 2014-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017150 | 406596983 | Guy | HFTD Tier 3 | Distribution | 2014-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017151 | 406596992 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017152 | 406597131 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017153 | 406597338 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017154 | 406597340 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017155 | 406597455 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017156 | 406597619 | Guy | HFTD Tier 2 | Distribution | 2014-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017157 | 406598763 | Guy | HFTD Tier 3 | Distribution | 2014-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017158 | 406598979 | High Sign | HFTD Tier 2 | Distribution | 2014-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017159 | 406599291 | Riser/Conduit | HFTD Tier 3 | Distribution | 2014-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017160 | 406599532 | High Sign | HFTD Tier 2 | Distribution | 2014-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017161 | 406599798 | Guy | HFTD Tier 2 | Distribution | 2014-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017162 | 406599939 | Molding | HFTD Tier 3 | Distribution | 2014-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017163 | 406599944 | High Sign | HFTD Tier 3 | Distribution | 2014-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017164 | 406599984 | Molding | HFTD Tier 3 | Distribution | 2014-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017165 | 406603699 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-11-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017166 | 406605756 | High Sign | HFTD Tier 2 | Distribution | 2014-11-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017167 | 406607799 | Molding | HFTD Tier 3 | Distribution | 2014-11-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017168 | 406607922 | High Sign | HFTD Tier 2 | Distribution | 2014-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017169 | 406607938 | High Sign | HFTD Tier 2 | Distribution | 2014-11-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017170 | 406608342 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-11-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017171 | 406608848 | Termination | HFTD Tier 3 | Distribution | 2014-11-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017172 | 406611396 | Guy | HFTD Tier 3 | Distribution | 2014-11-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017173 | 406611428 | ID Markings | HFTD Tier 3 | Distribution | 2014-11-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017174 | 406612861 | Molding | HFTD Tier 3 | Distribution | 2014-11-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017175 | 406613302 | High Sign | HFTD Tier 3 | Distribution | 2014-11-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017176 | 406615693 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017177 | 406615786 | Molding | HFTD Tier 2 | Distribution | 2014-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017178 | 406615934 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017179 | 406619123 | Molding | HFTD Tier 3 | Distribution | 2014-11-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017180 | 406619140 | High Sign | HFTD Tier 3 | Distribution | 2014-11-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017181 | 406621620 | High Sign | HFTD Tier 2 | Distribution | 2014-11-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017182 | 406628337 | Guy | HFTD Tier 3 | Distribution | 2014-11-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017183 | 406628898 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-11-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017184 | 406631593 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-11-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017185 | 406634279 | High Sign | HFTD Tier 2 | Distribution | 2014-11-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017186 | 406640272 | High Sign | HFTD Tier 2 | Distribution | 2014-12-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017187 | 406651037 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017188 | 406651568 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017189 | 406651599 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017190 | 406651605 | Guy | HFTD Tier 3 | Distribution | 2014-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017191 | 406652053 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017192 | 406652058 | High Sign | HFTD Tier 3 | Distribution | 2014-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017193 | 406652092 | High Sign | HFTD Tier 3 | Distribution | 2014-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017194 | 406652266 | High Sign | HFTD Tier 3 | Distribution | 2014-12-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017195 | 406654318 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-12-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017196 | 406656205 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-12-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017197 | 406656208 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-12-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017198 | 406656211 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-12-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017199 | 406656369 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-12-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017200 | 406656397 | Molding | HFTD Tier 3 | Distribution | 2014-12-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017201 | 406656742 | Guy | HFTD Tier 3 | Distribution | 2014-12-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017202 | 406658131 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-12-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017203 | 406658529 | Molding | HFTD Tier 3 | Distribution | 2014-12-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017204 | 406658532 | High Sign | HFTD Tier 3 | Distribution | 2014-12-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017205 | 406660665 | Molding | HFTD Tier 3 | Distribution | 2014-12-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017206 | 406672178 | Guy | HFTD Tier 3 | Distribution | 2014-12-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017207 | 406674644 | Guy | HFTD Tier 3 | Distribution | 2014-12-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017208 | 406680015 | Structure/Equip Itself | HFTD Tier 2 | Transmission | 2014-11-25 | 1964-04-30 | 2 | [7 empty] | SCE | 2025 | 4
1130017209 | 406683001 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-12-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017210 | 406687934 | Guy | HFTD Tier 2 | Distribution | 2015-01-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017211 | 406688578 | Molding | HFTD Tier 3 | Distribution | 2015-01-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017212 | 406688706 | High Sign | HFTD Tier 3 | Distribution | 2015-01-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017213 | 406688736 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-01-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017214 | 406688866 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-01-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017215 | 406689395 | High Sign | HFTD Tier 2 | Distribution | 2015-01-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017216 | 406689412 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-01-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017217 | 406689413 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-01-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017218 | 406689416 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-01-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017219 | 406690391 | High Sign | HFTD Tier 3 | Distribution | 2015-01-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017220 | 406690394 | Guy | HFTD Tier 3 | Distribution | 2015-01-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017221 | 406691072 | Guy | HFTD Tier 3 | Distribution | 2015-01-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017222 | 406693241 | Insulator | HFTD Tier 2 | Distribution | 2015-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017223 | 406693282 | High Sign | HFTD Tier 3 | Distribution | 2015-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017224 | 406693446 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2015-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017225 | 406693480 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2015-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017226 | 406693622 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017227 | 406693726 | High Sign | HFTD Tier 2 | Distribution | 2015-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017228 | 406694123 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017229 | 406695050 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2015-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017230 | 406695559 | Molding | HFTD Tier 2 | Distribution | 2015-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017231 | 406695900 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2015-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017232 | 406695920 | Guy | HFTD Tier 3 | Distribution | 2015-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017233 | 406696147 | High Sign | HFTD Tier 2 | Distribution | 2015-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017234 | 406696551 | Guy | HFTD Tier 2 | Distribution | 2015-01-08 | 1977-04-23 | 2 | Ignition Risk, no GO95 exception | [6 empty] | SCE | 2025 | 4
1130017235 | 406696564 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017236 | 406697054 | High Sign | HFTD Tier 2 | Distribution | 2015-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017237 | 406697055 | Molding | HFTD Tier 2 | Distribution | 2015-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017238 | 406697882 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017239 | 406697937 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017240 | 406699964 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2015-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017241 | 406700482 | Guy | HFTD Tier 2 | Distribution | 2015-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017242 | 406700809 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017243 | 406700924 | Guy | HFTD Tier 2 | Distribution | 2015-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017244 | 406701862 | Guy | HFTD Tier 2 | Distribution | 2015-01-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017245 | 406702670 | High Sign | HFTD Tier 3 | Distribution | 2015-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017246 | 406702874 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017247 | 406703634 | Molding | HFTD Tier 3 | Distribution | 2015-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017248 | 406703857 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017249 | 406704141 | Riser/Conduit | HFTD Tier 3 | Distribution | 2015-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017250 | 406704430 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017251 | 406704431 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017252 | 406704442 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017253 | 406705251 | Molding | HFTD Tier 2 | Distribution | 2015-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017254 | 406705254 | High Sign | HFTD Tier 2 | Distribution | 2015-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017255 | 406705594 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017256 | 406705681 | High Sign | HFTD Tier 3 | Distribution | 2015-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017257 | 406705905 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017258 | 406706003 | High Sign | HFTD Tier 3 | Distribution | 2015-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017259 | 406706027 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017260 | 406706219 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017261 | 406706247 | High Sign | HFTD Tier 3 | Distribution | 2015-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017262 | 406706352 | High Sign | HFTD Tier 2 | Distribution | 2015-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017263 | 406706568 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017264 | 406706604 | High Sign | HFTD Tier 2 | Distribution | 2015-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017265 | 406706843 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017266 | 406706920 | High Sign | HFTD Tier 3 | Distribution | 2015-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017267 | 406706966 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017268 | 406707249 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017269 | 406707250 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017270 | 406707258 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017271 | 406709421 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017272 | 406710109 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017273 | 406710124 | High Sign | HFTD Tier 2 | Distribution | 2015-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017274 | 406710139 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017275 | 406710141 | Molding | HFTD Tier 3 | Distribution | 2015-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017276 | 406710274 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017277 | 406710301 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017278 | 406710697 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017279 | 406710785 | Insulator | HFTD Tier 2 | Distribution | 2015-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017280 | 406710836 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017281 | 406710837 | Guy | HFTD Tier 3 | Distribution | 2015-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017282 | 406710901 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017283 | 406711160 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017284 | 406711188 | Guy | HFTD Tier 3 | Distribution | 2015-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017285 | 406712338 | Molding | HFTD Tier 2 | Distribution | 2015-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017286 | 406712342 | Molding | HFTD Tier 2 | Distribution | 2015-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017287 | 406712433 | Molding | HFTD Tier 2 | Distribution | 2015-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017288 | 406713010 | Vis Strips | HFTD Tier 3 | Distribution | 2015-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017289 | 406713127 | Molding | HFTD Tier 2 | Distribution | 2015-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017290 | 406713166 | Molding | HFTD Tier 2 | Distribution | 2015-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017291 | 406713190 | Molding | HFTD Tier 2 | Distribution | 2015-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017292 | 406713292 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-01-15 | 1984-04-23 | 2 | Ignition Risk, no GO95 exception | [6 empty] | SCE | 2025 | 4
1130017293 | 406713560 | Riser/Conduit | HFTD Tier 3 | Distribution | 2015-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017294 | 406713575 | Guy | HFTD Tier 2 | Distribution | 2015-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017295 | 406713578 | High Sign | HFTD Tier 2 | Distribution | 2015-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017296 | 406713785 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017297 | 406714029 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017298 | 406714043 | Guy | HFTD Tier 2 | Distribution | 2015-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017299 | 406714364 | Molding | HFTD Tier 2 | Distribution | 2015-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017300 | 406714371 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017301 | 406715410 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017302 | 406715432 | Molding | HFTD Tier 2 | Distribution | 2015-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017303 | 406715554 | Molding | HFTD Tier 2 | Distribution | 2015-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017304 | 406715573 | High Sign | HFTD Tier 2 | Distribution | 2015-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017305 | 406715582 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017306 | 406715664 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017307 | 406715677 | Molding | HFTD Tier 2 | Distribution | 2015-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017308 | 406716174 | High Sign | HFTD Tier 2 | Distribution | 2015-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017309 | 406718436 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017310 | 406718539 | Molding | HFTD Tier 2 | Distribution | 2015-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017311 | 406719333 | High Sign | HFTD Tier 2 | Distribution | 2015-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017312 | 406719377 | Guy | HFTD Tier 2 | Distribution | 2015-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017313 | 406719379 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017314 | 406719388 | High Sign | HFTD Tier 2 | Distribution | 2015-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017315 | 406719498 | Molding | HFTD Tier 3 | Distribution | 2015-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017316 | 406719735 | Riser/Conduit | HFTD Tier 2 | Distribution | 2015-01-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017317 | 406723294 | High Sign | HFTD Tier 2 | Distribution | 2015-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017318 | 406723298 | Molding | HFTD Tier 2 | Distribution | 2015-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017319 | 406723300 | Molding | HFTD Tier 2 | Distribution | 2015-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017320 | 406723303 | High Sign | HFTD Tier 2 | Distribution | 2015-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017321 | 406723854 | Guy | HFTD Tier 2 | Distribution | 2015-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017322 | 406724083 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017323 | 406724344 | High Sign | HFTD Tier 2 | Distribution | 2015-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017324 | 406724431 | Molding | HFTD Tier 3 | Distribution | 2015-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017325 | 406724866 | Molding | HFTD Tier 3 | Distribution | 2015-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017326 | 406724891 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017327 | 406726801 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017328 | 406727324 | High Sign | HFTD Tier 2 | Distribution | 2015-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017329 | 406727531 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017330 | 406728559 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017331 | 406729657 | High Sign | HFTD Tier 2 | Distribution | 2015-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017332 | 406729783 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017333 | 406730353 | Molding | HFTD Tier 3 | Distribution | 2015-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017334 | 406730486 | Guy | HFTD Tier 3 | Distribution | 2015-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017335 | 406730630 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017336 | 406731154 | High Sign | HFTD Tier 2 | Distribution | 2015-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017337 | 406731318 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017338 | 406731541 | Insulator | HFTD Tier 2 | Distribution | 2015-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017339 | 406731552 | Molding | HFTD Tier 2 | Distribution | 2015-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017340 | 406731957 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017341 | 406731967 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017342 | 406733012 | Molding | HFTD Tier 2 | Distribution | 2015-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017343 | 406733148 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017344 | 406733155 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017345 | 406734306 | Vis Strips | HFTD Tier 3 | Distribution | 2015-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017346 | 406734515 | Molding | HFTD Tier 2 | Distribution | 2015-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017347 | 406734967 | Guy | HFTD Tier 2 | Distribution | 2015-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017348 | 406735441 | Molding | HFTD Tier 2 | Distribution | 2015-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017349 | 406736076 | High Sign | HFTD Tier 2 | Distribution | 2015-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017350 | 406736079 | Molding | HFTD Tier 2 | Distribution | 2015-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017351 | 406736188 | High Sign | HFTD Tier 3 | Distribution | 2015-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017352 | 406736189 | High Sign | HFTD Tier 3 | Distribution | 2015-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017353 | 406736193 | Guy | HFTD Tier 3 | Distribution | 2015-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017354 | 406736194 | High Sign | HFTD Tier 3 | Distribution | 2015-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017355 | 406736358 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017356 | 406736408 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017357 | 406738045 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017358 | 406738714 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017359 | 406739261 | High Sign | HFTD Tier 3 | Distribution | 2015-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017360 | 406739307 | Molding | HFTD Tier 2 | Distribution | 2015-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017361 | 406739308 | Riser/Conduit | HFTD Tier 2 | Distribution | 2015-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017362 | 406739340 | High Sign | HFTD Tier 2 | Distribution | 2015-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017363 | 406741556 | Riser/Conduit | HFTD Tier 3 | Distribution | 2015-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017364 | 406741684 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017365 | 406743514 | High Sign | HFTD Tier 3 | Distribution | 2015-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017366 | 406744297 | High Sign | HFTD Tier 3 | Distribution | 2015-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017367 | 406744581 | Molding | HFTD Tier 2 | Distribution | 2015-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017368 | 406745021 | High Sign | HFTD Tier 2 | Distribution | 2015-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017369 | 406745081 | Molding | HFTD Tier 2 | Distribution | 2015-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017370 | 406745186 | Guy | HFTD Tier 3 | Distribution | 2015-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017371 | 406745206 | High Sign | HFTD Tier 3 | Distribution | 2015-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017372 | 406745800 | High Sign | HFTD Tier 2 | Distribution | 2015-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017373 | 406745811 | Molding | HFTD Tier 2 | Distribution | 2015-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017374 | 406746103 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017375 | 406747478 | Guy | HFTD Tier 3 | Distribution | 2015-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017376 | 406748186 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-01-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017377 | 406748254 | Guy | HFTD Tier 2 | Distribution | 2015-01-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017378 | 406748505 | Molding | HFTD Tier 3 | Distribution | 2015-01-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017379 | 406748519 | Molding | HFTD Tier 3 | Distribution | 2015-01-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017380 | 406748558 | Guy | HFTD Tier 2 | Distribution | 2015-01-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017381 | 406750028 | Guy | HFTD Tier 3 | Distribution | 2015-01-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017382 | 406750036 | High Sign | HFTD Tier 3 | Distribution | 2015-01-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017383 | 406750094 | High Sign | HFTD Tier 3 | Distribution | 2015-01-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017384 | 406750103 | High Sign | HFTD Tier 3 | Distribution | 2015-01-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017385 | 406750105 | High Sign | HFTD Tier 3 | Distribution | 2015-01-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017386 | 406750866 | Molding | HFTD Tier 3 | Distribution | 2015-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017387 | 406751561 | High Sign | HFTD Tier 2 | Distribution | 2015-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017388 | 406751778 | High Sign | HFTD Tier 2 | Distribution | 2015-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017389 | 406753697 | Molding | HFTD Tier 3 | Distribution | 2015-01-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017390 | 406755906 | High Sign | HFTD Tier 3 | Distribution | 2015-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017391 | 406755962 | Molding | HFTD Tier 2 | Distribution | 2015-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017392 | 406756622 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017393 | 406756910 | High Sign | HFTD Tier 2 | Distribution | 2015-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017394 | 406757149 | Molding | HFTD Tier 2 | Distribution | 2015-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017395 | 406758553 | Molding | HFTD Tier 2 | Distribution | 2015-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017396 | 406758569 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017397 | 406759567 | Guy | HFTD Tier 3 | Distribution | 2015-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017398 | 406762012 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017399 | 406762946 | High Sign | HFTD Tier 2 | Distribution | 2015-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017400 | 406763098 | Molding | HFTD Tier 2 | Distribution | 2015-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017401 | 406764848 | High Sign | HFTD Tier 3 | Distribution | 2015-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017402 | 406765472 | High Sign | HFTD Tier 2 | Distribution | 2015-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017403 | 406766088 | Molding | HFTD Tier 2 | Distribution | 2015-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017404 | 406766255 | High Sign | HFTD Tier 2 | Distribution | 2015-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017405 | 406766338 | High Sign | HFTD Tier 2 | Distribution | 2015-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017406 | 406766813 | High Sign | HFTD Tier 3 | Distribution | 2015-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017407 | 406766825 | Molding | HFTD Tier 3 | Distribution | 2015-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017408 | 406766830 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017409 | 406767246 | High Sign | HFTD Tier 2 | Distribution | 2015-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017410 | 406768929 | Guy | HFTD Tier 2 | Distribution | 2015-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017411 | 406769457 | Molding | HFTD Tier 2 | Distribution | 2015-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017412 | 406769966 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017413 | 406769967 | Guy | HFTD Tier 2 | Distribution | 2015-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017414 | 406772458 | High Sign | HFTD Tier 2 | Distribution | 2015-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017415 | 406775339 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017416 | 406775342 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017417 | 406776091 | Molding | HFTD Tier 2 | Distribution | 2015-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017418 | 406776173 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2015-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017419 | 406778727 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2015-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017420 | 406778829 | Molding | HFTD Tier 2 | Distribution | 2015-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017421 | 406779190 | High Sign | HFTD Tier 2 | Distribution | 2015-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017422 | 406779524 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017423 | 406779723 | High Sign | HFTD Tier 3 | Distribution | 2015-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017424 | 406779737 | High Sign | HFTD Tier 3 | Distribution | 2015-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017425 | 406781807 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017426 | 406782655 | Molding | HFTD Tier 3 | Distribution | 2015-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017427 | 406782664 | High Sign | HFTD Tier 3 | Distribution | 2015-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017428 | 406782930 | Molding | HFTD Tier 2 | Distribution | 2015-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017429 | 406784046 | Molding | HFTD Tier 2 | Distribution | 2015-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017430 | 406784687 | Molding | HFTD Tier 3 | Distribution | 2015-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017431 | 406784691 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017432 | 406785311 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017433 | 406789495 | High Sign | HFTD Tier 3 | Distribution | 2015-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017434 | 406789521 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017435 | 406789804 | High Sign | HFTD Tier 3 | Distribution | 2015-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017436 | 406790140 | High Sign | HFTD Tier 3 | Distribution | 2015-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017437 | 406792753 | Guy | HFTD Tier 2 | Distribution | 2015-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017438 | 406793044 | High Sign | HFTD Tier 2 | Distribution | 2015-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017439 | 406795514 | Guy | HFTD Tier 3 | Distribution | 2015-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017440 | 406797102 | Molding | HFTD Tier 3 | Distribution | 2015-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017441 | 406797115 | Guy | HFTD Tier 3 | Distribution | 2015-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017442 | 406797260 | Guy | HFTD Tier 3 | Distribution | 2015-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017443 | 406797316 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017444 | 406797418 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017445 | 406797465 | Guy | HFTD Tier 3 | Distribution | 2015-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017446 | 406800102 | High Sign | HFTD Tier 2 | Distribution | 2015-02-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017447 | 406800904 | High Sign | HFTD Tier 3 | Distribution | 2015-02-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017448 | 406802781 | High Sign | HFTD Tier 3 | Distribution | 2015-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017449 | 406803073 | Molding | HFTD Tier 2 | Distribution | 2015-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017450 | 406803736 | High Sign | HFTD Tier 3 | Distribution | 2015-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017451 | 406806153 | High Sign | HFTD Tier 2 | Distribution | 2015-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017452 | 406806297 | High Sign | HFTD Tier 3 | Distribution | 2015-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017453 | 406806313 | Molding | HFTD Tier 3 | Distribution | 2015-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017454 | 406806500 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017455 | 406806764 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017456 | 406807028 | High Sign | HFTD Tier 3 | Distribution | 2015-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017457 | 406807311 | High Sign | HFTD Tier 2 | Distribution | 2015-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017458 | 406807330 | Molding | HFTD Tier 2 | Distribution | 2015-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017459 | 406807334 | Molding | HFTD Tier 2 | Distribution | 2015-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017460 | 406807504 | Guy | HFTD Tier 2 | Distribution | 2015-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017461 | 406808652 | High Sign | HFTD Tier 3 | Distribution | 2015-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017462 | 406808665 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017463 | 406808670 | Molding | HFTD Tier 3 | Distribution | 2015-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017464 | 406808702 | High Sign | HFTD Tier 3 | Distribution | 2015-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017465 | 406809302 | High Sign | HFTD Tier 3 | Distribution | 2015-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017466 | 406809338 | High Sign | HFTD Tier 3 | Distribution | 2015-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017467 | 406809486 | Molding | HFTD Tier 3 | Distribution | 2015-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017468 | 406809511 | High Sign | HFTD Tier 2 | Distribution | 2015-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017469 | 406809545 | High Sign | HFTD Tier 3 | Distribution | 2015-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017470 | 406809872 | High Sign | HFTD Tier 3 | Distribution | 2015-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017471 | 406809873 | High Sign | HFTD Tier 3 | Distribution | 2015-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017472 | 406810142 | High Sign | HFTD Tier 3 | Distribution | 2015-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017473 | 406810151 | High Sign | HFTD Tier 3 | Distribution | 2015-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017474 | 406810388 | Guy | HFTD Tier 3 | Distribution | 2015-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017475 | 406810419 | High Sign | HFTD Tier 3 | Distribution | 2015-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017476 | 406810490 | High Sign | HFTD Tier 3 | Distribution | 2015-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017477 | 406810910 | High Sign | HFTD Tier 3 | Distribution | 2015-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017478 | 406813922 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-02-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017479 | 406814343 | Molding | HFTD Tier 3 | Distribution | 2015-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017480 | 406814344 | Guy | HFTD Tier 3 | Distribution | 2015-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017481 | 406814386 | High Sign | HFTD Tier 3 | Distribution | 2015-02-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017482 | 406816051 | High Sign | HFTD Tier 3 | Distribution | 2015-02-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017483 | 406816311 | High Sign | HFTD Tier 3 | Distribution | 2015-02-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017484 | 406816699 | Molding | HFTD Tier 3 | Distribution | 2015-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017485 | 406816773 | High Sign | HFTD Tier 3 | Distribution | 2015-02-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017486 | 406816788 | High Sign | HFTD Tier 3 | Distribution | 2015-02-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017487 | 406816792 | High Sign | HFTD Tier 3 | Distribution | 2015-02-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017488 | 406816802 | Molding | HFTD Tier 3 | Distribution | 2015-02-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017489 | 406816882 | High Sign | HFTD Tier 3 | Distribution | 2015-02-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017490 | 406816949 | High Sign | HFTD Tier 3 | Distribution | 2015-02-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017491 | 406817037 | High Sign | HFTD Tier 3 | Distribution | 2015-02-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017492 | 406817039 | High Sign | HFTD Tier 3 | Distribution | 2015-02-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017493 | 406819425 | High Sign | HFTD Tier 3 | Distribution | 2015-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017494 | 406819450 | High Sign | HFTD Tier 3 | Distribution | 2015-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017495 | 406820281 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017496 | 406822192 | High Sign | HFTD Tier 2 | Distribution | 2015-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017497 | 406822752 | High Sign | HFTD Tier 3 | Distribution | 2015-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017498 | 406822939 | High Sign | HFTD Tier 3 | Distribution | 2015-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017499 | 406823145 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2015-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017500 | 406823248 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017501 | 406826444 | Guy | HFTD Tier 3 | Distribution | 2015-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017502 | 406826455 | Guy | HFTD Tier 3 | Distribution | 2015-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017503 | 406826958 | High Sign | HFTD Tier 3 | Distribution | 2015-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017504 | 406826959 | High Sign | HFTD Tier 3 | Distribution | 2015-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017505 | 406826964 | High Sign | HFTD Tier 3 | Distribution | 2015-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017506 | 406826965 | High Sign | HFTD Tier 3 | Distribution | 2015-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017507 | 406827207 | High Sign | HFTD Tier 3 | Distribution | 2015-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017508 | 406827444 | High Sign | HFTD Tier 3 | Distribution | 2015-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017509 | 406828044 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017510 | 406829307 | High Sign | HFTD Tier 2 | Distribution | 2015-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017511 | 406830145 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017512 | 406830543 | High Sign | HFTD Tier 3 | Distribution | 2015-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017513 | 406830546 | High Sign | HFTD Tier 3 | Distribution | 2015-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017514 | 406830596 | High Sign | HFTD Tier 3 | Distribution | 2015-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017515 | 406830923 | Molding | HFTD Tier 3 | Distribution | 2015-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017516 | 406831022 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017517 | 406831041 | High Sign | HFTD Tier 3 | Distribution | 2015-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017518 | 406831046 | Molding | HFTD Tier 3 | Distribution | 2015-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017519 | 406831150 | Guy | HFTD Tier 3 | Distribution | 2015-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017520 | 406831217 | Molding | HFTD Tier 3 | Distribution | 2015-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017521 | 406831237 | High Sign | HFTD Tier 3 | Distribution | 2015-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017522 | 406831357 | High Sign | HFTD Tier 3 | Distribution | 2015-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017523 | 406831409 | High Sign | HFTD Tier 3 | Distribution | 2015-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017524 | 406831411 | High Sign | HFTD Tier 3 | Distribution | 2015-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017525 | 406831413 | High Sign | HFTD Tier 3 | Distribution | 2015-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017526 | 406831487 | High Sign | HFTD Tier 3 | Distribution | 2015-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017527 | 406831494 | High Sign | HFTD Tier 3 | Distribution | 2015-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017528 | 406834074 | High Sign | HFTD Tier 3 | Distribution | 2015-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017529 | 406834099 | Guy | HFTD Tier 3 | Distribution | 2015-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017530 | 406834104 | Guy | HFTD Tier 3 | Distribution | 2015-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017531 | 406834193 | High Sign | HFTD Tier 3 | Distribution | 2015-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017532 | 406834194 | High Sign | HFTD Tier 3 | Distribution | 2015-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017533 | 406834390 | High Sign | HFTD Tier 3 | Distribution | 2015-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017534 | 406834569 | High Sign | HFTD Tier 3 | Distribution | 2015-03-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017535 | 406837960 | Guy | HFTD Tier 3 | Distribution | 2015-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017536 | 406838021 | High Sign | HFTD Tier 3 | Distribution | 2015-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017537 | 406838270 | Guy | HFTD Tier 3 | Distribution | 2015-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017538 | 406838328 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017539 | 406838580 | Riser/Conduit | HFTD Tier 2 | Distribution | 2015-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017540 | 406840265 | High Sign | HFTD Tier 2 | Distribution | 2015-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017541 | 406840791 | Molding | HFTD Tier 2 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017542 | 406840813 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017543 | 406840866 | Molding | HFTD Tier 3 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017544 | 406840927 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017545 | 406840930 | High Sign | HFTD Tier 2 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017546 | 406841023 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017547 | 406841025 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017548 | 406841183 | High Sign | HFTD Tier 2 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017549 | 406841297 | High Sign | HFTD Tier 2 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017550 | 406841367 | High Sign | HFTD Tier 3 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017551 | 406841376 | Molding | HFTD Tier 3 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017552 | 406841467 | Molding | HFTD Tier 2 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017553 | 406841477 | Molding | HFTD Tier 2 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017554 | 406841482 | High Sign | HFTD Tier 2 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017555 | 406841503 | High Sign | HFTD Tier 2 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017556 | 406841607 | Termination | HFTD Tier 2 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017557 | 406841664 | High Sign | HFTD Tier 2 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017558 | 406841713 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017559 | 406841718 | Molding | HFTD Tier 2 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017560 | 406841748 | Guy | HFTD Tier 2 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017561 | 406841867 | Guy | HFTD Tier 2 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017562 | 406841982 | Termination | HFTD Tier 2 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017563 | 406842030 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017564 | 406842031 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017565 | 406842074 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017566 | 406842346 | Guy | HFTD Tier 3 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017567 | 406842351 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017568 | 406842900 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017569 | 406844592 | Termination | HFTD Tier 2 | Distribution | 2015-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017570 | 406844744 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017571 | 406844840 | High Sign | HFTD Tier 2 | Distribution | 2015-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017572 | 406845042 | Guy | HFTD Tier 3 | Distribution | 2015-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017573 | 406845235 | High Sign | HFTD Tier 3 | Distribution | 2015-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017574 | 406845236 | Molding | HFTD Tier 3 | Distribution | 2015-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017575 | 406845269 | Molding | HFTD Tier 2 | Distribution | 2015-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017576 | 406845945 | Molding | HFTD Tier 3 | Distribution | 2015-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017577 | 406848302 | Guy | HFTD Tier 3 | Distribution | 2015-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017578 | 406848486 | Guy | HFTD Tier 2 | Distribution | 2015-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017579 | 406848974 | High Sign | HFTD Tier 2 | Distribution | 2015-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017580 | 406848975 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017581 | 406848989 | High Sign | HFTD Tier 2 | Distribution | 2015-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017582 | 406848998 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017583 | 406850394 | Molding | HFTD Tier 3 | Distribution | 2015-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017584 | 406850408 | High Sign | HFTD Tier 3 | Distribution | 2015-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017585 | 406850412 | Molding | HFTD Tier 3 | Distribution | 2015-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017586 | 406852603 | Insulator | HFTD Tier 3 | Distribution | 2015-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017587 | 406852954 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017588 | 406853190 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017589 | 406853233 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017590 | 406853634 | Riser/Conduit | HFTD Tier 3 | Distribution | 2015-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017591 | 406853676 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017592 | 406853960 | High Sign | HFTD Tier 3 | Distribution | 2015-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017593 | 406853982 | Molding | HFTD Tier 3 | Distribution | 2015-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017594 | 406853993 | High Sign | HFTD Tier 3 | Distribution | 2015-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017595 | 406854145 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017596 | 406854739 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017597 | 406856385 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017598 | 406856386 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017599 | 406856727 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017600 | 406856917 | High Sign | HFTD Tier 3 | Distribution | 2015-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017601 | 406857389 | Molding | HFTD Tier 3 | Distribution | 2015-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017602 | 406858347 | Molding | HFTD Tier 2 | Distribution | 2015-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017603 | 406859600 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017604 | 406860860 | Riser/Conduit | HFTD Tier 3 | Distribution | 2015-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017605 | 406860944 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017606 | 406861252 | Molding | HFTD Tier 3 | Distribution | 2015-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017607 | 406862462 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017608 | 406862468 | Molding | HFTD Tier 3 | Distribution | 2015-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017609 | 406862849 | Molding | HFTD Tier 3 | Distribution | 2015-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017610 | 406863372 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017611 | 406863374 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017612 | 406863578 | Guy | HFTD Tier 3 | Distribution | 2015-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017613 | 406863613 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017614 | 406863878 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017615 | 406863982 | Guy | HFTD Tier 3 | Distribution | 2015-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017616 | 406869482 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017617 | 406869502 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017618 | 406869503 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017619 | 406869587 | Molding | HFTD Tier 3 | Distribution | 2015-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017620 | 406869638 | Molding | HFTD Tier 3 | Distribution | 2015-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017621 | 406870470 | High Sign | HFTD Tier 3 | Distribution | 2015-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017622 | 406873228 | High Sign | HFTD Tier 2 | Distribution | 2015-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017623 | 406873234 | High Sign | HFTD Tier 2 | Distribution | 2015-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017624 | 406873313 | Molding | HFTD Tier 3 | Distribution | 2015-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017625 | 406873899 | Molding | HFTD Tier 3 | Distribution | 2015-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017626 | 406873950 | High Sign | HFTD Tier 2 | Distribution | 2015-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017627 | 406875480 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017628 | 406875501 | High Sign | HFTD Tier 2 | Distribution | 2015-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017629 | 406875970 | Molding | HFTD Tier 3 | Distribution | 2015-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017630 | 406875981 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017631 | 406876321 | Molding | HFTD Tier 3 | Distribution | 2015-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017632 | 406876543 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017633 | 406876545 | High Sign | HFTD Tier 3 | Distribution | 2015-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017634 | 406876549 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017635 | 406876553 | Molding | HFTD Tier 3 | Distribution | 2015-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017636 | 406876566 | High Sign | HFTD Tier 3 | Distribution | 2015-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017637 | 406876678 | High Sign | HFTD Tier 3 | Distribution | 2015-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017638 | 406877011 | High Sign | HFTD Tier 3 | Distribution | 2015-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017639 | 406877433 | Molding | HFTD Tier 3 | Distribution | 2015-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017640 | 406878870 | Molding | HFTD Tier 3 | Distribution | 2015-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017641 | 406878871 | High Sign | HFTD Tier 3 | Distribution | 2015-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017642 | 406879307 | High Sign | HFTD Tier 3 | Distribution | 2015-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017643 | 406879452 | High Sign | HFTD Tier 3 | Distribution | 2015-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017644 | 406879455 | High Sign | HFTD Tier 3 | Distribution | 2015-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017645 | 406880712 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-03-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017646 | 406884654 | High Sign | HFTD Tier 3 | Distribution | 2015-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017647 | 406884670 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-03-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017648 | 406884814 | Guy | HFTD Tier 3 | Distribution | 2015-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017649 | 406885158 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017650 | 406885351 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017651 | 406885392 | Riser/Conduit | HFTD Tier 2 | Distribution | 2015-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017652 | 406885614 | Guy | HFTD Tier 3 | Distribution | 2015-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017653 | 406885620 | Guy | HFTD Tier 3 | Distribution | 2015-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017654 | 406886907 | Molding | HFTD Tier 3 | Distribution | 2015-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017655 | 406886917 | Pole Tag | HFTD Tier 3 | Distribution | 2015-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017656 | 406886918 | Pole Tag | HFTD Tier 3 | Distribution | 2015-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017657 | 406887779 | High Sign | HFTD Tier 2 | Distribution | 2015-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017658 | 406887782 | High Sign | HFTD Tier 2 | Distribution | 2015-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017659 | 406887783 | Molding | HFTD Tier 2 | Distribution | 2015-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017660 | 406887796 | High Sign | HFTD Tier 2 | Distribution | 2015-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017661 | 406888232 | High Sign | HFTD Tier 3 | Distribution | 2015-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017662 | 406888234 | Molding | HFTD Tier 3 | Distribution | 2015-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017663 | 406888368 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017664 | 406888373 | Molding | HFTD Tier 3 | Distribution | 2015-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017665 | 406888717 | Molding | HFTD Tier 3 | Distribution | 2015-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017666 | 406889472 | Guy | HFTD Tier 2 | Distribution | 2015-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017667 | 406890285 | Guy | HFTD Tier 3 | Distribution | 2015-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017668 | 406890531 | High Sign | HFTD Tier 3 | Distribution | 2015-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017669 | 406891400 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017670 | 406891826 | Guy | HFTD Tier 3 | Distribution | 2015-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017671 | 406891830 | Guy | HFTD Tier 3 | Distribution | 2015-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017672 | 406891840 | Molding | HFTD Tier 3 | Distribution | 2015-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017673 | 406892163 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017674 | 406892745 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017675 | 406892764 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017676 | 406904901 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017677 | 406905025 | Molding | HFTD Tier 3 | Distribution | 2015-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017678 | 406905171 | Molding | HFTD Tier 3 | Distribution | 2015-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017679 | 406905670 | Molding | HFTD Tier 3 | Distribution | 2015-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017680 | 406905990 | Guy | HFTD Tier 3 | Distribution | 2015-04-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017681 | 406906270 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-04-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017682 | 406912656 | Molding | HFTD Tier 3 | Distribution | 2015-04-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017683 | 406915531 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017684 | 406915979 | Molding | HFTD Tier 3 | Distribution | 2015-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017685 | 406916008 | High Sign | HFTD Tier 3 | Distribution | 2015-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017686 | 406916012 | Guy | HFTD Tier 3 | Distribution | 2015-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017687 | 406916037 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017688 | 406916190 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017689 | 406916254 | High Sign | HFTD Tier 3 | Distribution | 2015-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017690 | 406916307 | High Sign | HFTD Tier 3 | Distribution | 2015-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017691 | 406916392 | Molding | HFTD Tier 3 | Distribution | 2015-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017692 | 406916497 | High Sign | HFTD Tier 3 | Distribution | 2015-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017693 | 406916505 | Molding | HFTD Tier 2 | Distribution | 2015-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017694 | 406916506 | High Sign | HFTD Tier 2 | Distribution | 2015-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017695 | 406916508 | Molding | HFTD Tier 3 | Distribution | 2015-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017696 | 406916518 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017697 | 406917298 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017698 | 406917403 | Molding | HFTD Tier 3 | Distribution | 2015-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017699 | 406917501 | Molding | HFTD Tier 3 | Distribution | 2015-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017700 | 406918187 | High Sign | HFTD Tier 3 | Distribution | 2015-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017701 | 406918337 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017702 | 406918338 | Molding | HFTD Tier 3 | Distribution | 2015-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017703 | 406918555 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017704 | 406919039 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017705 | 406919175 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017706 | 406919176 | Molding | HFTD Tier 3 | Distribution | 2015-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017707 | 406919507 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017708 | 406919780 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017709 | 406921630 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-04-08 | 1967-04-24 | 2 | Ignition Risk, no GO95 exception | [6 empty] | SCE | 2025 | 4
1130017710 | 406922061 | High Sign | HFTD Tier 3 | Distribution | 2015-04-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017711 | 406922762 | Molding | HFTD Tier 3 | Distribution | 2015-04-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017712 | 406923088 | High Sign | HFTD Tier 3 | Distribution | 2015-04-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017713 | 406923098 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-04-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017714 | 406923100 | Guy | HFTD Tier 3 | Distribution | 2015-04-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017715 | 406924189 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017716 | 406924959 | Guy | HFTD Tier 3 | Distribution | 2015-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017717 | 406924963 | High Sign | HFTD Tier 3 | Distribution | 2015-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017718 | 406924964 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017719 | 406925279 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017720 | 406925880 | Guy | HFTD Tier 2 | Distribution | 2015-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017721 | 406928083 | Molding | HFTD Tier 3 | Distribution | 2015-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017722 | 406928085 | Molding | HFTD Tier 3 | Distribution | 2015-04-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017723 | 406932180 | High Sign | HFTD Tier 3 | Distribution | 2015-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017724 | 406932191 | Guy | HFTD Tier 3 | Distribution | 2015-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017725 | 406932536 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017726 | 406932537 | Molding | HFTD Tier 3 | Distribution | 2015-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017727 | 406932569 | Molding | HFTD Tier 3 | Distribution | 2015-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017728 | 406934383 | Molding | HFTD Tier 3 | Distribution | 2015-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017729 | 406934389 | Guy | HFTD Tier 3 | Distribution | 2015-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017730 | 406934393 | Molding | HFTD Tier 3 | Distribution | 2015-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017731 | 406934395 | Guy | HFTD Tier 3 | Distribution | 2015-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017732 | 406934411 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017733 | 406934420 | Guy | HFTD Tier 3 | Distribution | 2015-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017734 | 406934550 | High Sign | HFTD Tier 3 | Distribution | 2015-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017735 | 406936003 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017736 | 406937892 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017737 | 406938338 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017738 | 406938570 | Molding | HFTD Tier 3 | Distribution | 2015-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017739 | 406938575 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017740 | 406939721 | High Sign | HFTD Tier 3 | Distribution | 2015-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017741 | 406940468 | High Sign | HFTD Tier 3 | Distribution | 2015-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017742 | 406940481 | High Sign | HFTD Tier 3 | Distribution | 2015-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017743 | 406940482 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017744 | 406940483 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017745 | 406940484 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017746 | 406940722 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017747 | 406941017 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017748 | 406941337 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017749 | 406941348 | Guy | HFTD Tier 3 | Distribution | 2015-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017750 | 406941360 | Guy | HFTD Tier 3 | Distribution | 2015-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017751 | 406941361 | High Sign | HFTD Tier 3 | Distribution | 2015-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017752 | 406941372 | High Sign | HFTD Tier 3 | Distribution | 2015-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017753 | 406943117 | Guy | HFTD Tier 3 | Distribution | 2015-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017754 | 406943777 | Molding | HFTD Tier 2 | Distribution | 2015-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017755 | 406944450 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017756 | 406945306 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017757 | 406947574 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017758 | 406947886 | High Sign | HFTD Tier 2 | Distribution | 2015-04-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017759 | 406948617 | Molding | HFTD Tier 3 | Distribution | 2015-04-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017760 | 406950207 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2015-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017761 | 406951000 | High Sign | HFTD Tier 2 | Distribution | 2015-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017762 | 406951001 | Molding | HFTD Tier 2 | Distribution | 2015-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017763 | 406951024 | Vis Strips | HFTD Tier 3 | Distribution | 2015-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017764 | 406951031 | Guy | HFTD Tier 2 | Distribution | 2015-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017765 | 406952178 | High Sign | HFTD Tier 2 | Distribution | 2015-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017766 | 406953006 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017767 | 406953468 | Molding | HFTD Tier 3 | Distribution | 2015-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017768 | 406953469 | Molding | HFTD Tier 3 | Distribution | 2015-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017769 | 406953478 | High Sign | HFTD Tier 3 | Distribution | 2015-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017770 | 406953483 | Molding | HFTD Tier 3 | Distribution | 2015-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017771 | 406953486 | High Sign | HFTD Tier 3 | Distribution | 2015-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017772 | 406953487 | High Sign | HFTD Tier 3 | Distribution | 2015-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017773 | 406953502 | High Sign | HFTD Tier 3 | Distribution | 2015-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017774 | 406953504 | High Sign | HFTD Tier 3 | Distribution | 2015-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017775 | 406953506 | High Sign | HFTD Tier 3 | Distribution | 2015-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017776 | 406953510 | High Sign | HFTD Tier 3 | Distribution | 2015-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017777 | 406953731 | Molding | HFTD Tier 3 | Distribution | 2015-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017778 | 406953902 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017779 | 406953955 | Guy | HFTD Tier 3 | Distribution | 2015-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017780 | 406954971 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017781 | 406955359 | High Sign | HFTD Tier 3 | Distribution | 2015-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017782 | 406955365 | High Sign | HFTD Tier 3 | Distribution | 2015-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017783 | 406955416 | Guy | HFTD Tier 3 | Distribution | 2015-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017784 | 406955442 | Molding | HFTD Tier 2 | Distribution | 2015-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017785 | 406955637 | Molding | HFTD Tier 3 | Distribution | 2015-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017786 | 406955638 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017787 | 406955645 | Molding | HFTD Tier 3 | Distribution | 2015-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017788 | 406956873 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2015-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017789 | 406957029 | Guy | HFTD Tier 3 | Distribution | 2015-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017790 | 406957665 | Molding | HFTD Tier 3 | Distribution | 2015-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017791 | 406957751 | Molding | HFTD Tier 2 | Distribution | 2015-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017792 | 406957897 | Riser/Conduit | HFTD Tier 2 | Distribution | 2015-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017793 | 406957907 | High Sign | HFTD Tier 2 | Distribution | 2015-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017794 | 406957908 | Molding | HFTD Tier 2 | Distribution | 2015-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017795 | 406958369 | Molding | HFTD Tier 3 | Distribution | 2015-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017796 | 406959049 | High Sign | HFTD Tier 3 | Distribution | 2015-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017797 | 406959306 | Molding | HFTD Tier 3 | Distribution | 2015-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017798 | 406959652 | Guy | HFTD Tier 2 | Distribution | 2015-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017799 | 406961727 | Molding | HFTD Tier 3 | Distribution | 2015-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017800 | 406962804 | Guy | HFTD Tier 3 | Distribution | 2015-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017801 | 406962971 | Molding | HFTD Tier 2 | Distribution | 2015-04-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017802 | 406965622 | Molding | HFTD Tier 3 | Distribution | 2015-04-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017803 | 406965874 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-04-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017804 | 406965882 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-04-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017805 | 406968228 | Guy | HFTD Tier 3 | Distribution | 2015-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017806 | 406968819 | Molding | HFTD Tier 3 | Distribution | 2015-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017807 | 406968822 | Guy | HFTD Tier 3 | Distribution | 2015-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017808 | 406969231 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017809 | 406969736 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017810 | 406969757 | High Sign | HFTD Tier 3 | Distribution | 2015-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017811 | 406969761 | High Sign | HFTD Tier 3 | Distribution | 2015-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017812 | 406969766 | High Sign | HFTD Tier 3 | Distribution | 2015-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017813 | 406969767 | Molding | HFTD Tier 3 | Distribution | 2015-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017814 | 406969812 | High Sign | HFTD Tier 2 | Distribution | 2015-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017815 | 406969813 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017816 | 406969978 | High Sign | HFTD Tier 2 | Distribution | 2015-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017817 | 406970080 | Guy | HFTD Tier 2 | Distribution | 2015-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017818 | 406970167 | Guy | HFTD Tier 3 | Distribution | 2015-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017819 | 406971914 | High Sign | HFTD Tier 3 | Distribution | 2015-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017820 | 406971917 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017821 | 406971928 | Molding | HFTD Tier 3 | Distribution | 2015-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017822 | 406971929 | High Sign | HFTD Tier 3 | Distribution | 2015-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017823 | 406972994 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017824 | 406973362 | Molding | HFTD Tier 3 | Distribution | 2015-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017825 | 406973622 | Molding | HFTD Tier 3 | Distribution | 2015-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017826 | 406974071 | High Sign | HFTD Tier 3 | Distribution | 2015-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017827 | 406976220 | Molding | HFTD Tier 3 | Distribution | 2015-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017828 | 406976402 | Guy | HFTD Tier 2 | Distribution | 2015-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017829 | 406976929 | Guy | HFTD Tier 3 | Distribution | 2015-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017830 | 406976942 | High Sign | HFTD Tier 3 | Distribution | 2015-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017831 | 406978876 | Riser/Conduit | HFTD Tier 3 | Distribution | 2015-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017832 | 406979225 | Molding | HFTD Tier 3 | Distribution | 2015-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017833 | 406979226 | Molding | HFTD Tier 3 | Distribution | 2015-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017834 | 406981398 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017835 | 406981403 | Riser/Conduit | HFTD Tier 3 | Distribution | 2015-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017836 | 406981406 | Molding | HFTD Tier 3 | Distribution | 2015-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017837 | 406981414 | High Sign | HFTD Tier 3 | Distribution | 2015-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017838 | 406981416 | Molding | HFTD Tier 3 | Distribution | 2015-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017839 | 406981633 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017840 | 406981671 | Molding | HFTD Tier 3 | Distribution | 2015-04-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017841 | 406983080 | Molding | HFTD Tier 3 | Distribution | 2015-05-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017842 | 406984587 | High Sign | HFTD Tier 3 | Distribution | 2015-05-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017843 | 406984600 | Molding | HFTD Tier 3 | Distribution | 2015-05-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017844 | 406984603 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-05-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017845 | 406985765 | Guy | HFTD Tier 2 | Distribution | 2015-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017846 | 406985854 | Guy | HFTD Tier 2 | Distribution | 2015-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017847 | 406986043 | Guy | HFTD Tier 2 | Distribution | 2015-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017848 | 406986706 | High Sign | HFTD Tier 2 | Distribution | 2015-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017849 | 406986783 | High Sign | HFTD Tier 3 | Distribution | 2015-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017850 | 406986825 | Guy | HFTD Tier 3 | Distribution | 2015-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017851 | 406986936 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017852 | 406986993 | High Sign | HFTD Tier 2 | Distribution | 2015-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017853 | 406987000 | High Sign | HFTD Tier 2 | Distribution | 2015-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017854 | 406987009 | Molding | HFTD Tier 3 | Distribution | 2015-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017855 | 406987013 | Guy | HFTD Tier 2 | Distribution | 2015-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017856 | 406987419 | High Sign | HFTD Tier 3 | Distribution | 2015-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017857 | 406987495 | Guy | HFTD Tier 3 | Distribution | 2015-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017858 | 406987496 | Molding | HFTD Tier 3 | Distribution | 2015-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017859 | 406987497 | Guy | HFTD Tier 3 | Distribution | 2015-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017860 | 406988265 | High Sign | HFTD Tier 2 | Distribution | 2015-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017861 | 406988945 | Molding | HFTD Tier 3 | Distribution | 2015-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017862 | 406989672 | Guy | HFTD Tier 3 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017863 | 406989712 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017864 | 406989799 | Molding | HFTD Tier 3 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017865 | 406989806 | High Sign | HFTD Tier 3 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017866 | 406989829 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017867 | 406989918 | Pole Tag | HFTD Tier 3 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017868 | 406989994 | Guy | HFTD Tier 3 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017869 | 406990084 | High Sign | HFTD Tier 3 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017870 | 406990107 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017871 | 406990168 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017872 | 406990169 | Guy | HFTD Tier 2 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017873 | 406990180 | High Sign | HFTD Tier 2 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017874 | 406990735 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017875 | 406990888 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017876 | 406991451 | Guy | HFTD Tier 3 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017877 | 406992650 | Molding | HFTD Tier 2 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017878 | 406992800 | Molding | HFTD Tier 2 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017879 | 406992814 | Molding | HFTD Tier 2 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017880 | 406992910 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017881 | 406993201 | High Sign | HFTD Tier 3 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017882 | 406993244 | High Sign | HFTD Tier 2 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017883 | 406993435 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017884 | 406993634 | High Sign | HFTD Tier 3 | Distribution | 2015-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017885 | 406993785 | High Sign | HFTD Tier 2 | Distribution | 2015-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017886 | 406994477 | High Sign | HFTD Tier 2 | Distribution | 2015-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017887 | 406994719 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017888 | 406994957 | High Sign | HFTD Tier 3 | Distribution | 2015-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017889 | 406995390 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017890 | 406996362 | High Sign | HFTD Tier 2 | Distribution | 2015-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017891 | 406996655 | High Sign | HFTD Tier 2 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017892 | 406996883 | High Sign | HFTD Tier 3 | Distribution | 2015-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017893 | 406996890 | High Sign | HFTD Tier 3 | Distribution | 2015-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017894 | 406997020 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017895 | 406997308 | Guy | HFTD Tier 3 | Distribution | 2015-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017896 | 406997467 | High Sign | HFTD Tier 2 | Distribution | 2015-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017897 | 406997490 | High Sign | HFTD Tier 3 | Distribution | 2015-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017898 | 406997702 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017899 | 406997704 | Molding | HFTD Tier 3 | Distribution | 2015-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017900 | 406997712 | High Sign | HFTD Tier 3 | Distribution | 2015-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017901 | 406998074 | Guy | HFTD Tier 2 | Distribution | 2015-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017902 | 406998355 | Riser/Conduit | HFTD Tier 2 | Distribution | 2015-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017903 | 406998398 | Molding | HFTD Tier 2 | Distribution | 2015-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017904 | 406998481 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017905 | 406998828 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017906 | 406998889 | Riser/Conduit | HFTD Tier 3 | Distribution | 2015-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017907 | 406998891 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017908 | 406998984 | High Sign | HFTD Tier 2 | Distribution | 2015-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017909 | 407000260 | High Sign | HFTD Tier 2 | Distribution | 2015-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017910 | 407000262 | High Sign | HFTD Tier 2 | Distribution | 2015-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017911 | 407000892 | High Sign | HFTD Tier 2 | Distribution | 2015-05-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017912 | 407005118 | Guy | HFTD Tier 2 | Distribution | 2015-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017913 | 407005133 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017914 | 407005466 | High Sign | HFTD Tier 3 | Distribution | 2015-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017915 | 407006227 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017916 | 407008044 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017917 | 407008259 | Guy | HFTD Tier 3 | Distribution | 2015-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017918 | 407008755 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017919 | 407008907 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017920 | 407009695 | Guy | HFTD Tier 2 | Distribution | 2015-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017921 | 407011314 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017922 | 407011394 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017923 | 407011808 | Molding | HFTD Tier 3 | Distribution | 2015-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017924 | 407011817 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017925 | 407012338 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017926 | 407012397 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017927 | 407013680 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017928 | 407013711 | Molding | HFTD Tier 3 | Distribution | 2015-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017929 | 407014424 | Molding | HFTD Tier 2 | Distribution | 2015-05-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017930 | 407015797 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-05-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017931 | 407016524 | High Sign | HFTD Tier 3 | Distribution | 2015-05-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017932 | 407022511 | Molding | HFTD Tier 3 | Distribution | 2015-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017933 | 407022962 | Insulator | HFTD Tier 3 | Distribution | 2015-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017934 | 407023052 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017935 | 407026403 | Guy | HFTD Tier 3 | Distribution | 2015-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017936 | 407026423 | Guy | HFTD Tier 3 | Distribution | 2015-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017937 | 407026589 | High Sign | HFTD Tier 2 | Distribution | 2015-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017938 | 407026802 | Molding | HFTD Tier 2 | Distribution | 2015-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017939 | 407031534 | High Sign | HFTD Tier 2 | Distribution | 2015-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017940 | 407035570 | Cutout/Fuse | HFTD Tier 3 | Distribution | 2015-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017941 | 407035600 | High Sign | HFTD Tier 3 | Distribution | 2015-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017942 | 407036052 | Molding | HFTD Tier 3 | Distribution | 2015-05-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017943 | 407038406 | High Sign | HFTD Tier 3 | Distribution | 2015-05-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017944 | 407041042 | Guy | HFTD Tier 3 | Distribution | 2015-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017945 | 407041146 | Guy | HFTD Tier 3 | Distribution | 2015-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017946 | 407041731 | Guy | HFTD Tier 3 | Distribution | 2015-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017947 | 407042356 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017948 | 407043048 | Molding | HFTD Tier 3 | Distribution | 2015-05-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017949 | 407043400 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-05-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017950 | 407044259 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-05-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017951 | 407046491 | Guy | HFTD Tier 3 | Distribution | 2015-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017952 | 407047298 | Guy | HFTD Tier 3 | Distribution | 2015-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017953 | 407047426 | High Sign | HFTD Tier 2 | Distribution | 2015-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017954 | 407047613 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-05-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017955 | 407050023 | High Sign | HFTD Tier 2 | Distribution | 2015-05-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017956 | 407051143 | High Sign | HFTD Tier 3 | Distribution | 2015-05-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017957 | 407052386 | Riser/Conduit | HFTD Tier 3 | Distribution | 2015-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017958 | 407052405 | Molding | HFTD Tier 3 | Distribution | 2015-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017959 | 407052999 | Molding | HFTD Tier 3 | Distribution | 2015-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017960 | 407053081 | High Sign | HFTD Tier 3 | Distribution | 2015-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017961 | 407053114 | Guy | HFTD Tier 3 | Distribution | 2015-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017962 | 407053272 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017963 | 407053340 | Guy | HFTD Tier 3 | Distribution | 2015-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017964 | 407054436 | Guy | HFTD Tier 3 | Distribution | 2015-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017965 | 407054602 | Guy | HFTD Tier 3 | Distribution | 2015-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017966 | 407055480 | Molding | HFTD Tier 3 | Distribution | 2015-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017967 | 407055767 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017968 | 407056587 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017969 | 407056890 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017970 | 407057657 | High Sign | HFTD Tier 3 | Distribution | 2015-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017971 | 407057878 | High Sign | HFTD Tier 3 | Distribution | 2015-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017972 | 407058496 | High Sign | HFTD Tier 3 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017973 | 407058542 | Molding | HFTD Tier 3 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017974 | 407058735 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017975 | 407058796 | High Sign | HFTD Tier 2 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017976 | 407058836 | High Sign | HFTD Tier 2 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017977 | 407058890 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017978 | 407058893 | High Sign | HFTD Tier 2 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017979 | 407059238 | Guy | HFTD Tier 3 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017980 | 407059259 | Molding | HFTD Tier 3 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017981 | 407059484 | Guy | HFTD Tier 3 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017982 | 407059519 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017983 | 407059638 | Molding | HFTD Tier 3 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017984 | 407059656 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017985 | 407059692 | High Sign | HFTD Tier 3 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017986 | 407059745 | Guy | HFTD Tier 3 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017987 | 407059798 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017988 | 407059887 | High Sign | HFTD Tier 3 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017989 | 407059908 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017990 | 407059945 | Molding | HFTD Tier 3 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017991 | 407060038 | Molding | HFTD Tier 3 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017992 | 407060099 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017993 | 407060100 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017994 | 407060216 | Guy | HFTD Tier 3 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017995 | 407060280 | Molding | HFTD Tier 3 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017996 | 407060485 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017997 | 407060489 | High Sign | HFTD Tier 2 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017998 | 407060688 | High Sign | HFTD Tier 2 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130017999 | 407060920 | Molding | HFTD Tier 2 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018000 | 407061466 | High Sign | HFTD Tier 2 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018001 | 407061663 | High Sign | HFTD Tier 2 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018002 | 407061695 | High Sign | HFTD Tier 2 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018003 | 407061737 | High Sign | HFTD Tier 2 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018004 | 407061738 | High Sign | HFTD Tier 2 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018005 | 407061750 | High Sign | HFTD Tier 2 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018006 | 407061751 | High Sign | HFTD Tier 2 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018007 | 407061752 | High Sign | HFTD Tier 2 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018008 | 407061761 | High Sign | HFTD Tier 2 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018009 | 407061768 | High Sign | HFTD Tier 2 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018010 | 407061770 | High Sign | HFTD Tier 2 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018011 | 407061811 | High Sign | HFTD Tier 2 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018012 | 407062272 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018013 | 407062374 | High Sign | HFTD Tier 2 | Distribution | 2015-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018014 | 407062502 | Insulator | HFTD Tier 3 | Distribution | 2015-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018015 | 407062518 | High Sign | HFTD Tier 3 | Distribution | 2015-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018016 | 407062529 | High Sign | HFTD Tier 3 | Distribution | 2015-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018017 | 407063309 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018018 | 407063409 | Molding | HFTD Tier 3 | Distribution | 2015-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018019 | 407063417 | Molding | HFTD Tier 2 | Distribution | 2015-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018020 | 407063424 | High Sign | HFTD Tier 3 | Distribution | 2015-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018021 | 407063823 | Guy | HFTD Tier 3 | Distribution | 2015-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018022 | 407063864 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018023 | 407063989 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018024 | 407064141 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018025 | 407064343 | High Sign | HFTD Tier 3 | Distribution | 2015-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018026 | 407066081 | High Sign | HFTD Tier 3 | Distribution | 2015-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018027 | 407066102 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018028 | 407066193 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018029 | 407066328 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018030 | 407066423 | Molding | HFTD Tier 3 | Distribution | 2015-06-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018031 | 407069930 | Guy | HFTD Tier 3 | Distribution | 2015-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018032 | 407070035 | Molding | HFTD Tier 2 | Distribution | 2015-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018033 | 407071119 | High Sign | HFTD Tier 2 | Distribution | 2015-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018034 | 407071425 | High Sign | HFTD Tier 2 | Distribution | 2015-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018035 | 407071576 | High Sign | HFTD Tier 2 | Distribution | 2015-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018036 | 407072823 | Guy | HFTD Tier 2 | Distribution | 2015-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018037 | 407072835 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018038 | 407072842 | Guy | HFTD Tier 2 | Distribution | 2015-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018039 | 407072845 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018040 | 407072855 | Guy | HFTD Tier 2 | Distribution | 2015-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018041 | 407072864 | High Sign | HFTD Tier 2 | Distribution | 2015-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018042 | 407074869 | Guy | HFTD Tier 3 | Distribution | 2015-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018043 | 407074874 | Molding | HFTD Tier 3 | Distribution | 2015-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018044 | 407074971 | Guy | HFTD Tier 3 | Distribution | 2015-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018045 | 407074972 | High Sign | HFTD Tier 3 | Distribution | 2015-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018046 | 407076117 | Molding | HFTD Tier 3 | Distribution | 2015-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018047 | 407077664 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018048 | 407077865 | Guy | HFTD Tier 3 | Distribution | 2015-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018049 | 407078073 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018050 | 407078151 | High Sign | HFTD Tier 3 | Distribution | 2015-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018051 | 407078553 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018052 | 407079747 | High Sign | HFTD Tier 3 | Distribution | 2015-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018053 | 407079748 | High Sign | HFTD Tier 3 | Distribution | 2015-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018054 | 407079785 | High Sign | HFTD Tier 3 | Distribution | 2015-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018055 | 407079891 | High Sign | HFTD Tier 3 | Distribution | 2015-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018056 | 407080586 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018057 | 407080684 | Molding | HFTD Tier 3 | Distribution | 2015-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018058 | 407081699 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018059 | 407082865 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2015-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018060 | 407083397 | Guy | HFTD Tier 3 | Distribution | 2015-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018061 | 407083442 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018062 | 407083461 | Molding | HFTD Tier 3 | Distribution | 2015-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018063 | 407084698 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018064 | 407084705 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-06-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018065 | 407086347 | Riser/Conduit | HFTD Tier 3 | Distribution | 2015-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018066 | 407086485 | Molding | HFTD Tier 3 | Distribution | 2015-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018067 | 407086531 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018068 | 407086656 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018069 | 407087322 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018070 | 407087623 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018071 | 407087715 | High Sign | HFTD Tier 3 | Distribution | 2015-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018072 | 407087760 | High Sign | HFTD Tier 3 | Distribution | 2015-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018073 | 407087774 | High Sign | HFTD Tier 2 | Distribution | 2015-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018074 | 407088740 | Guy | HFTD Tier 3 | Distribution | 2015-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018075 | 407089662 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018076 | 407089687 | Molding | HFTD Tier 3 | Distribution | 2015-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018077 | 407089889 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018078 | 407089968 | Guy | HFTD Tier 3 | Distribution | 2015-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018079 | 407090001 | Guy | HFTD Tier 3 | Distribution | 2015-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018080 | 407090239 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018081 | 407090610 | Molding | HFTD Tier 2 | Distribution | 2015-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018082 | 407090701 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018083 | 407091878 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018084 | 407091965 | High Sign | HFTD Tier 3 | Distribution | 2015-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018085 | 407091966 | High Sign | HFTD Tier 3 | Distribution | 2015-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018086 | 407091985 | Molding | HFTD Tier 3 | Distribution | 2015-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018087 | 407092053 | Ground | HFTD Tier 3 | Distribution | 2015-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018088 | 407092082 | High Sign | HFTD Tier 3 | Distribution | 2015-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018089 | 407092198 | High Sign | HFTD Tier 3 | Distribution | 2015-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018090 | 407092553 | High Sign | HFTD Tier 3 | Distribution | 2015-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018091 | 407092646 | Molding | HFTD Tier 3 | Distribution | 2015-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018092 | 407092673 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018093 | 407092696 | High Sign | HFTD Tier 3 | Distribution | 2015-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018094 | 407092979 | High Sign | HFTD Tier 3 | Distribution | 2015-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018095 | 407093092 | Molding | HFTD Tier 3 | Distribution | 2015-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018096 | 407095303 | Guy | HFTD Tier 3 | Distribution | 2015-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018097 | 407096011 | Molding | HFTD Tier 2 | Distribution | 2015-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018098 | 407096515 | Guy | HFTD Tier 3 | Distribution | 2015-06-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018099 | 407097102 | Guy | HFTD Tier 2 | Distribution | 2015-06-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018100 | 407097103 | Guy | HFTD Tier 2 | Distribution | 2015-06-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018101 | 407099799 | Guy | HFTD Tier 3 | Distribution | 2015-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018102 | 407099886 | Guy | HFTD Tier 3 | Distribution | 2015-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018103 | 407099937 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018104 | 407099977 | High Sign | HFTD Tier 2 | Distribution | 2015-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018105 | 407100098 | Molding | HFTD Tier 3 | Distribution | 2015-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018106 | 407100452 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018107 | 407100500 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018108 | 407100649 | Molding | HFTD Tier 2 | Distribution | 2015-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018109 | 407100674 | High Sign | HFTD Tier 2 | Distribution | 2015-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018110 | 407101524 | Molding | HFTD Tier 2 | Distribution | 2015-06-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018111 | 407104634 | Guy | HFTD Tier 2 | Distribution | 2015-06-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018112 | 407105962 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018113 | 407106077 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018114 | 407106177 | Guy | HFTD Tier 3 | Distribution | 2015-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018115 | 407106732 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018116 | 407106913 | High Sign | HFTD Tier 3 | Distribution | 2015-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018117 | 407106941 | High Sign | HFTD Tier 3 | Distribution | 2015-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018118 | 407106950 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018119 | 407108016 | Molding | HFTD Tier 3 | Distribution | 2015-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018120 | 407109125 | Molding | HFTD Tier 3 | Distribution | 2015-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018121 | 407109284 | Molding | HFTD Tier 3 | Distribution | 2015-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018122 | 407109286 | High Sign | HFTD Tier 2 | Distribution | 2015-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018123 | 407109325 | Molding | HFTD Tier 3 | Distribution | 2015-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018124 | 407109792 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018125 | 407109827 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018126 | 407113471 | Molding | HFTD Tier 3 | Distribution | 2015-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018127 | 407113620 | Molding | HFTD Tier 2 | Distribution | 2015-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018128 | 407113935 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018129 | 407115090 | High Sign | HFTD Tier 3 | Distribution | 2015-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018130 | 407115691 | High Sign | HFTD Tier 2 | Distribution | 2015-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018131 | 407116270 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018132 | 407116863 | Molding | HFTD Tier 2 | Distribution | 2015-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018133 | 407116912 | High Sign | HFTD Tier 3 | Distribution | 2015-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018134 | 407117342 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018135 | 407117800 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018136 | 407117801 | Molding | HFTD Tier 2 | Distribution | 2015-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018137 | 407118017 | Molding | HFTD Tier 3 | Distribution | 2015-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018138 | 407118332 | Molding | HFTD Tier 3 | Distribution | 2015-06-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018139 | 407119096 | High Sign | HFTD Tier 3 | Distribution | 2015-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018140 | 407119494 | Molding | HFTD Tier 3 | Distribution | 2015-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018141 | 407119671 | High Sign | HFTD Tier 3 | Distribution | 2015-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018142 | 407122217 | Guy | HFTD Tier 2 | Distribution | 2015-06-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018143 | 407122529 | Molding | HFTD Tier 2 | Distribution | 2015-06-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018144 | 407123721 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-06-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018145 | 407125073 | Guy | HFTD Tier 2 | Distribution | 2015-06-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018146 | 407125082 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-06-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018147 | 407125850 | High Sign | HFTD Tier 3 | Distribution | 2015-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018148 | 407126413 | High Sign | HFTD Tier 2 | Distribution | 2015-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018149 | 407128793 | High Sign | HFTD Tier 2 | Distribution | 2015-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018150 | 407129897 | Molding | HFTD Tier 2 | Distribution | 2015-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018151 | 407133374 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-07-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018152 | 407134128 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-07-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018153 | 407134348 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-07-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018154 | 407134449 | Guy | HFTD Tier 2 | Distribution | 2015-07-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018155 | 407134456 | Guy | HFTD Tier 2 | Distribution | 2015-07-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018156 | 407134476 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-07-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018157 | 407139119 | High Sign | HFTD Tier 3 | Distribution | 2015-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018158 | 407139482 | High Sign | HFTD Tier 3 | Distribution | 2015-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018159 | 407139559 | High Sign | HFTD Tier 3 | Distribution | 2015-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018160 | 407139585 | Guy | HFTD Tier 3 | Distribution | 2015-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018161 | 407139609 | Molding | HFTD Tier 3 | Distribution | 2015-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018162 | 407139620 | Guy | HFTD Tier 3 | Distribution | 2015-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018163 | 407140048 | High Sign | HFTD Tier 3 | Distribution | 2015-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018164 | 407140060 | Guy | HFTD Tier 3 | Distribution | 2015-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018165 | 407140064 | Streetlight | HFTD Tier 3 | Distribution | 2015-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018166 | 407140361 | Molding | HFTD Tier 2 | Distribution | 2015-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018167 | 407141968 | High Sign | HFTD Tier 3 | Distribution | 2015-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018168 | 407142168 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018169 | 407142184 | Guy | HFTD Tier 2 | Distribution | 2015-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018170 | 407142292 | High Sign | HFTD Tier 3 | Distribution | 2015-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018171 | 407142398 | Guy | HFTD Tier 3 | Distribution | 2015-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018172 | 407142414 | High Sign | HFTD Tier 2 | Distribution | 2015-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018173 | 407142421 | Molding | HFTD Tier 2 | Distribution | 2015-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018174 | 407142486 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018175 | 407142489 | Molding | HFTD Tier 2 | Distribution | 2015-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018176 | 407142648 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018177 | 407142779 | Guy | HFTD Tier 2 | Distribution | 2015-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018178 | 407143348 | High Sign | HFTD Tier 2 | Distribution | 2015-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018179 | 407144786 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018180 | 407144795 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018181 | 407144831 | Molding | HFTD Tier 3 | Distribution | 2015-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018182 | 407144837 | Molding | HFTD Tier 3 | Distribution | 2015-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018183 | 407145028 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018184 | 407146465 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018185 | 407146571 | High Sign | HFTD Tier 3 | Distribution | 2015-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018186 | 407146719 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018187 | 407146748 | Molding | HFTD Tier 3 | Distribution | 2015-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018188 | 407146792 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018189 | 407150651 | Molding | HFTD Tier 3 | Distribution | 2015-07-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018190 | 407155337 | High Sign | HFTD Tier 3 | Distribution | 2015-07-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018191 | 407155432 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-07-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018192 | 407158549 | Guy | HFTD Tier 2 | Distribution | 2015-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018193 | 407160487 | Molding | HFTD Tier 3 | Distribution | 2015-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018194 | 407160643 | Guy | HFTD Tier 3 | Distribution | 2015-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018195 | 407161029 | Guy | HFTD Tier 3 | Distribution | 2015-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018196 | 407161045 | High Sign | HFTD Tier 2 | Distribution | 2015-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018197 | 407162136 | High Sign | HFTD Tier 2 | Distribution | 2015-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018198 | 407165145 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018199 | 407166464 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018200 | 407167335 | High Sign | HFTD Tier 3 | Distribution | 2015-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018201 | 407167353 | Guy | HFTD Tier 3 | Distribution | 2015-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018202 | 407167532 | High Sign | HFTD Tier 3 | Distribution | 2015-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018203 | 407168554 | High Sign | HFTD Tier 3 | Distribution | 2015-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018204 | 407168842 | High Sign | HFTD Tier 2 | Distribution | 2015-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018205 | 407168884 | Molding | HFTD Tier 2 | Distribution | 2015-07-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018206 | 407169398 | Molding | HFTD Tier 3 | Distribution | 2015-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018207 | 407169907 | Guy | HFTD Tier 3 | Distribution | 2015-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018208 | 407169956 | Guy | HFTD Tier 3 | Distribution | 2015-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018209 | 407169958 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018210 | 407170020 | Guy | HFTD Tier 3 | Distribution | 2015-07-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018211 | 407173994 | Riser/Conduit | HFTD Tier 2 | Distribution | 2015-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018212 | 407174080 | High Sign | HFTD Tier 2 | Distribution | 2015-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018213 | 407174349 | Vis Strips | HFTD Tier 3 | Distribution | 2015-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018214 | 407174351 | Molding | HFTD Tier 3 | Distribution | 2015-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018215 | 407175248 | High Sign | HFTD Tier 3 | Distribution | 2015-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018216 | 407176253 | Molding | HFTD Tier 3 | Distribution | 2015-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018217 | 407176355 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018218 | 407176580 | High Sign | HFTD Tier 2 | Distribution | 2015-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018219 | 407176697 | Guy | HFTD Tier 2 | Distribution | 2015-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018220 | 407176835 | Guy | HFTD Tier 2 | Distribution | 2015-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018221 | 407176870 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018222 | 407176969 | High Sign | HFTD Tier 2 | Distribution | 2015-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018223 | 407177081 | High Sign | HFTD Tier 2 | Distribution | 2015-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018224 | 407178208 | Guy | HFTD Tier 3 | Distribution | 2015-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018225 | 407178209 | High Sign | HFTD Tier 3 | Distribution | 2015-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018226 | 407178309 | Guy | HFTD Tier 3 | Distribution | 2015-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018227 | 407178332 | Guy | HFTD Tier 3 | Distribution | 2015-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018228 | 407178342 | Guy | HFTD Tier 3 | Distribution | 2015-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018229 | 407178352 | Guy | HFTD Tier 3 | Distribution | 2015-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018230 | 407178360 | Guy | HFTD Tier 3 | Distribution | 2015-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018231 | 407178365 | High Sign | HFTD Tier 3 | Distribution | 2015-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018232 | 407178372 | Guy | HFTD Tier 3 | Distribution | 2015-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018233 | 407178376 | Guy | HFTD Tier 3 | Distribution | 2015-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018234 | 407179657 | Molding | HFTD Tier 3 | Distribution | 2015-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018235 | 407179727 | High Sign | HFTD Tier 3 | Distribution | 2015-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018236 | 407179896 | Guy | HFTD Tier 3 | Distribution | 2015-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018237 | 407179897 | High Sign | HFTD Tier 3 | Distribution | 2015-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018238 | 407179937 | High Sign | HFTD Tier 2 | Distribution | 2015-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018239 | 407179991 | High Sign | HFTD Tier 3 | Distribution | 2015-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018240 | 407180010 | Molding | HFTD Tier 2 | Distribution | 2015-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018241 | 407180055 | Molding | HFTD Tier 2 | Distribution | 2015-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018242 | 407180287 | Molding | HFTD Tier 2 | Distribution | 2015-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018243 | 407181738 | Molding | HFTD Tier 2 | Distribution | 2015-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018244 | 407182626 | Guy | HFTD Tier 3 | Distribution | 2015-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018245 | 407183768 | Pole step | HFTD Tier 3 | Distribution | 2015-07-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018246 | 407190442 | Guy | HFTD Tier 3 | Distribution | 2015-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018247 | 407192949 | High Sign | HFTD Tier 2 | Distribution | 2015-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018248 | 407193646 | Guy | HFTD Tier 2 | Distribution | 2015-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018249 | 407196215 | Molding | HFTD Tier 2 | Distribution | 2015-07-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018250 | 407197804 | Guy | HFTD Tier 2 | Distribution | 2015-07-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018251 | 407201002 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018252 | 407201030 | High Sign | HFTD Tier 2 | Distribution | 2015-07-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018253 | 407202861 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018254 | 407203691 | High Sign | HFTD Tier 3 | Distribution | 2015-07-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018255 | 407205473 | Molding | HFTD Tier 3 | Distribution | 2015-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018256 | 407205490 | Molding | HFTD Tier 3 | Distribution | 2015-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018257 | 407206084 | Molding | HFTD Tier 3 | Distribution | 2015-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018258 | 407206995 | Guy | HFTD Tier 3 | Distribution | 2015-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018259 | 407213285 | Guy | HFTD Tier 3 | Distribution | 2015-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018260 | 407213323 | High Sign | HFTD Tier 3 | Distribution | 2015-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018261 | 407213324 | High Sign | HFTD Tier 3 | Distribution | 2015-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018262 | 407213334 | Guy | HFTD Tier 3 | Distribution | 2015-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018263 | 407213344 | Guy | HFTD Tier 3 | Distribution | 2015-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018264 | 407213350 | Molding | HFTD Tier 3 | Distribution | 2015-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018265 | 407213360 | Guy | HFTD Tier 3 | Distribution | 2015-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018266 | 407214528 | Molding | HFTD Tier 3 | Distribution | 2015-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018267 | 407215472 | High Sign | HFTD Tier 2 | Distribution | 2015-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018268 | 407216247 | Molding | HFTD Tier 3 | Distribution | 2015-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018269 | 407217251 | High Sign | HFTD Tier 3 | Distribution | 2015-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018270 | 407223646 | Guy | HFTD Tier 2 | Distribution | 2015-08-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018271 | 407223695 | High Sign | HFTD Tier 2 | Distribution | 2015-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018272 | 407223713 | High Sign | HFTD Tier 2 | Distribution | 2015-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018273 | 407223721 | High Sign | HFTD Tier 2 | Distribution | 2015-08-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018274 | 407224952 | Molding | HFTD Tier 2 | Distribution | 2015-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018275 | 407224955 | Riser/Conduit | HFTD Tier 2 | Distribution | 2015-08-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018276 | 407227918 | High Sign | HFTD Tier 2 | Distribution | 2015-08-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018277 | 407230539 | High Sign | HFTD Tier 2 | Distribution | 2015-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018278 | 407230628 | High Sign | HFTD Tier 2 | Distribution | 2015-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018279 | 407232824 | Molding | HFTD Tier 3 | Distribution | 2015-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018280 | 407232944 | High Sign | HFTD Tier 2 | Distribution | 2015-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018281 | 407232953 | High Sign | HFTD Tier 2 | Distribution | 2015-08-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018282 | 407234198 | High Sign | HFTD Tier 2 | Distribution | 2015-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018283 | 407234238 | Molding | HFTD Tier 2 | Distribution | 2015-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018284 | 407234261 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018285 | 407234321 | High Sign | HFTD Tier 2 | Distribution | 2015-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018286 | 407234330 | High Sign | HFTD Tier 2 | Distribution | 2015-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018287 | 407234599 | Guy | HFTD Tier 3 | Distribution | 2015-08-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018288 | 407242972 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-08-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018289 | 407243054 | High Sign | HFTD Tier 2 | Distribution | 2015-08-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018290 | 407244163 | High Sign | HFTD Tier 2 | Distribution | 2015-08-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018291 | 407245510 | Bond | HFTD Tier 3 | Distribution | 2015-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018292 | 407248042 | High Sign | HFTD Tier 2 | Distribution | 2015-08-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018293 | 407250998 | Guy | HFTD Tier 2 | Distribution | 2015-08-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018294 | 407251984 | Pole step | HFTD Tier 2 | Distribution | 2015-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018295 | 407252059 | Molding | HFTD Tier 2 | Distribution | 2015-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018296 | 407252838 | Vis Strips | HFTD Tier 2 | Distribution | 2015-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018297 | 407253222 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018298 | 407259797 | Bond | HFTD Tier 3 | Distribution | 2015-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018299 | 407259856 | Bond | HFTD Tier 3 | Distribution | 2015-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018300 | 407260158 | Pole step | HFTD Tier 3 | Distribution | 2015-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018301 | 407260203 | Pole step | HFTD Tier 3 | Distribution | 2015-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018302 | 407260216 | Guy | HFTD Tier 3 | Distribution | 2015-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018303 | 407260983 | Pole step | HFTD Tier 3 | Distribution | 2015-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018304 | 407261363 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-08-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018305 | 407261937 | Molding | HFTD Tier 3 | Distribution | 2015-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018306 | 407262367 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018307 | 407262898 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-08-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018308 | 407264556 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-08-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018309 | 407267855 | Molding | HFTD Tier 3 | Distribution | 2015-08-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018310 | 407268716 | High Sign | HFTD Tier 2 | Distribution | 2015-08-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018311 | 407268946 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-08-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018312 | 407272424 | Riser/Conduit | HFTD Tier 3 | Distribution | 2015-08-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018313 | 407276691 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-08-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018314 | 407279075 | Guy | HFTD Tier 3 | Distribution | 2015-09-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018315 | 407279693 | Molding | HFTD Tier 3 | Distribution | 2015-09-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018316 | 407279851 | ID Markings | HFTD Tier 3 | Distribution | 2015-09-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018317 | 407280206 | High Sign | HFTD Tier 2 | Distribution | 2015-09-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018318 | 407280245 | Guy | HFTD Tier 3 | Distribution | 2015-09-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018319 | 407281546 | Molding | HFTD Tier 3 | Distribution | 2015-09-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018320 | 407281870 | Molding | HFTD Tier 3 | Distribution | 2015-09-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018321 | 407282389 | High Sign | HFTD Tier 2 | Distribution | 2015-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018322 | 407282394 | Molding | HFTD Tier 2 | Distribution | 2015-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018323 | 407282906 | Guy | HFTD Tier 3 | Distribution | 2015-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018324 | 407283742 | Guy | HFTD Tier 3 | Distribution | 2015-09-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018325 | 407286796 | Guy | HFTD Tier 3 | Distribution | 2015-09-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018326 | 407286896 | Vis Strips | HFTD Tier 3 | Distribution | 2015-09-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018327 | 407287136 | Molding | HFTD Tier 3 | Distribution | 2015-09-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018328 | 407290565 | Pole Tag | HFTD Tier 3 | Distribution | 2015-09-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018329 | 407290582 | Pole Tag | HFTD Tier 3 | Distribution | 2015-09-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018330 | 407293720 | High Sign | HFTD Tier 2 | Distribution | 2015-09-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018331 | 407297739 | Bond | HFTD Tier 3 | Distribution | 2015-09-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018332 | 407299959 | Bond | HFTD Tier 3 | Distribution | 2015-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018333 | 407301209 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018334 | 407301230 | Guy | HFTD Tier 3 | Distribution | 2015-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018335 | 407301240 | Guy | HFTD Tier 3 | Distribution | 2015-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018336 | 407302307 | Molding | HFTD Tier 3 | Distribution | 2015-09-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018337 | 407304969 | High Sign | HFTD Tier 3 | Distribution | 2015-09-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018338 | 407305027 | High Sign | HFTD Tier 3 | Distribution | 2015-09-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018339 | 407314843 | Molding | HFTD Tier 2 | Distribution | 2015-09-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018340 | 407317701 | High Sign | HFTD Tier 2 | Distribution | 2015-09-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018341 | 407320005 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-09-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018342 | 407320032 | Guy | HFTD Tier 3 | Distribution | 2015-09-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018343 | 407320458 | Bond | HFTD Tier 3 | Distribution | 2015-09-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018344 | 407320631 | Molding | HFTD Tier 3 | Distribution | 2015-09-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018345 | 407320934 | Bond | HFTD Tier 3 | Distribution | 2015-09-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018346 | 407325150 | Molding | HFTD Tier 3 | Distribution | 2015-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018347 | 407325409 | Pole Tag | HFTD Tier 3 | Distribution | 2015-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018348 | 407325560 | High Sign | HFTD Tier 2 | Distribution | 2015-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018349 | 407325665 | High Sign | HFTD Tier 3 | Distribution | 2015-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018350 | 407326508 | High Sign | HFTD Tier 3 | Distribution | 2015-09-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018351 | 407332590 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-09-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018352 | 407342495 | High Sign | HFTD Tier 3 | Distribution | 2015-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018353 | 407343936 | High Sign | HFTD Tier 2 | Distribution | 2015-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018354 | 407343940 | Pole Tag | HFTD Tier 3 | Distribution | 2015-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018355 | 407343998 | Molding | HFTD Tier 2 | Distribution | 2015-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018356 | 407344293 | High Sign | HFTD Tier 2 | Distribution | 2015-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018357 | 407344294 | High Sign | HFTD Tier 2 | Distribution | 2015-09-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018358 | 407346172 | Pole Tag | HFTD Tier 3 | Distribution | 2015-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018359 | 407346906 | Molding | HFTD Tier 2 | Distribution | 2015-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018360 | 407346916 | Guy | HFTD Tier 2 | Distribution | 2015-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018361 | 407348268 | Guy | HFTD Tier 2 | Distribution | 2015-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018362 | 407348323 | Guy | HFTD Tier 2 | Distribution | 2015-09-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018363 | 407350472 | Bond | HFTD Tier 3 | Distribution | 2015-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018364 | 407351337 | Guy | HFTD Tier 2 | Distribution | 2015-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018365 | 407351440 | Guy | HFTD Tier 2 | Distribution | 2015-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018366 | 407352452 | High Sign | HFTD Tier 2 | Distribution | 2015-09-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018367 | 407353708 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-10-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018368 | 407358074 | High Sign | HFTD Tier 2 | Distribution | 2015-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018369 | 407358099 | High Sign | HFTD Tier 2 | Distribution | 2015-10-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018370 | 407363837 | Molding | HFTD Tier 2 | Distribution | 2015-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018371 | 407364416 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018372 | 407367808 | Molding | HFTD Tier 2 | Distribution | 2015-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018373 | 407367817 | Molding | HFTD Tier 2 | Distribution | 2015-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018374 | 407367850 | Molding | HFTD Tier 2 | Distribution | 2015-10-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018375 | 407368742 | High Sign | HFTD Tier 3 | Distribution | 2015-10-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018376 | 407383240 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018377 | 407383250 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018378 | 407384442 | High Sign | HFTD Tier 2 | Distribution | 2015-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018379 | 407385938 | Molding | HFTD Tier 3 | Distribution | 2015-10-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018380 | 407386023 | Molding | HFTD Tier 3 | Distribution | 2015-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018381 | 407386070 | Molding | HFTD Tier 3 | Distribution | 2015-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018382 | 407386078 | High Sign | HFTD Tier 2 | Distribution | 2015-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018383 | 407386138 | High Sign | HFTD Tier 2 | Distribution | 2015-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018384 | 407386146 | High Sign | HFTD Tier 2 | Distribution | 2015-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018385 | 407386154 | High Sign | HFTD Tier 2 | Distribution | 2015-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018386 | 407386190 | High Sign | HFTD Tier 2 | Distribution | 2015-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018387 | 407386409 | Insulator | HFTD Tier 3 | Distribution | 2015-10-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018388 | 407388704 | Molding | HFTD Tier 3 | Distribution | 2015-10-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018389 | 407389395 | Guy | HFTD Tier 2 | Distribution | 2015-10-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018390 | 407389466 | High Sign | HFTD Tier 3 | Distribution | 2015-10-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018391 | 407390103 | Molding | HFTD Tier 2 | Distribution | 2015-10-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018392 | 407390717 | Molding | HFTD Tier 2 | Distribution | 2015-10-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018393 | 407392538 | Molding | HFTD Tier 2 | Distribution | 2015-10-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018394 | 407392563 | Molding | HFTD Tier 2 | Distribution | 2015-10-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018395 | 407394143 | Molding | HFTD Tier 2 | Distribution | 2015-10-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018396 | 407394655 | Guy | HFTD Tier 2 | Distribution | 2015-10-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018397 | 407398395 | Molding | HFTD Tier 3 | Distribution | 2015-10-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018398 | 407398796 | Molding | HFTD Tier 3 | Distribution | 2015-10-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018399 | 407399808 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-10-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018400 | 407400039 | High Sign | HFTD Tier 3 | Distribution | 2015-10-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018401 | 407402138 | Guy | HFTD Tier 3 | Distribution | 2015-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018402 | 407402993 | High Sign | HFTD Tier 2 | Distribution | 2015-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018403 | 407403213 | Molding | HFTD Tier 3 | Distribution | 2015-10-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018404 | 407403250 | Molding | HFTD Tier 3 | Distribution | 2015-10-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018405 | 407403959 | Guy | HFTD Tier 3 | Distribution | 2015-10-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018406 | 407408550 | Guy | HFTD Tier 3 | Distribution | 2015-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018407 | 407408860 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018408 | 407409744 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-10-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018409 | 407411750 | Guy | HFTD Tier 3 | Distribution | 2015-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018410 | 407411757 | High Sign | HFTD Tier 2 | Distribution | 2015-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018411 | 407412004 | Molding | HFTD Tier 3 | Distribution | 2015-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018412 | 407412320 | Guy | HFTD Tier 3 | Distribution | 2015-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018413 | 407412823 | Molding | HFTD Tier 3 | Distribution | 2015-10-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018414 | 407414745 | High Sign | HFTD Tier 3 | Distribution | 2015-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018415 | 407415888 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-10-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018416 | 407418815 | Pole step | HFTD Tier 3 | Distribution | 2015-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018417 | 407419509 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018418 | 407420033 | Riser/Conduit | HFTD Tier 3 | Distribution | 2015-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018419 | 407420444 | High Sign | HFTD Tier 3 | Distribution | 2015-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018420 | 407420471 | Pole step | HFTD Tier 3 | Distribution | 2015-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018421 | 407420485 | High Sign | HFTD Tier 3 | Distribution | 2015-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018422 | 407420490 | Pole step | HFTD Tier 3 | Distribution | 2015-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018423 | 407421033 | High Sign | HFTD Tier 3 | Distribution | 2015-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018424 | 407421060 | Molding | HFTD Tier 3 | Distribution | 2015-10-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018425 | 407427759 | Guy | HFTD Tier 2 | Distribution | 2015-10-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018426 | 407428058 | High Sign | HFTD Tier 2 | Distribution | 2015-10-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018427 | 407428071 | High Sign | HFTD Tier 2 | Distribution | 2015-10-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018428 | 407429886 | Pole step | HFTD Tier 3 | Distribution | 2015-11-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018429 | 407430073 | Pole step | HFTD Tier 3 | Distribution | 2015-11-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018430 | 407433516 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-11-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018431 | 407433910 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-11-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018432 | 407436397 | Pole step | HFTD Tier 3 | Distribution | 2015-11-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018433 | 407436520 | High Sign | HFTD Tier 3 | Distribution | 2015-11-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018434 | 407438136 | High Sign | HFTD Tier 3 | Distribution | 2015-11-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018435 | 407438137 | Pole step | HFTD Tier 3 | Distribution | 2015-11-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018436 | 407438149 | Pole step | HFTD Tier 3 | Distribution | 2015-11-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018437 | 407438179 | Pole step | HFTD Tier 3 | Distribution | 2015-11-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018438 | 407438301 | Guy | HFTD Tier 3 | Distribution | 2015-11-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018439 | 407439321 | Guy | HFTD Tier 3 | Distribution | 2015-11-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018440 | 407439530 | Guy | HFTD Tier 3 | Distribution | 2015-11-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018441 | 407439540 | High Sign | HFTD Tier 3 | Distribution | 2015-11-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018442 | 407440264 | High Sign | HFTD Tier 2 | Distribution | 2015-11-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018443 | 407440365 | Pole step | HFTD Tier 3 | Distribution | 2015-11-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018444 | 407445672 | Molding | HFTD Tier 3 | Distribution | 2015-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018445 | 407445993 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-11-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018446 | 407449360 | Guy | HFTD Tier 3 | Distribution | 2015-11-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018447 | 407452324 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018448 | 407453163 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018449 | 407454698 | Molding | HFTD Tier 3 | Distribution | 2015-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018450 | 407454777 | Guy | HFTD Tier 3 | Distribution | 2015-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018451 | 407454841 | Molding | HFTD Tier 3 | Distribution | 2015-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018452 | 407454855 | Guy | HFTD Tier 3 | Distribution | 2015-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018453 | 407454873 | High Sign | HFTD Tier 3 | Distribution | 2015-11-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018454 | 407456522 | Guy | HFTD Tier 3 | Distribution | 2015-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018455 | 407457137 | Molding | HFTD Tier 3 | Distribution | 2015-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018456 | 407457374 | Molding | HFTD Tier 3 | Distribution | 2015-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018457 | 407457380 | Guy | HFTD Tier 3 | Distribution | 2015-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018458 | 407457410 | Pole step | HFTD Tier 3 | Distribution | 2015-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018459 | 407457420 | Molding | HFTD Tier 3 | Distribution | 2015-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018460 | 407457421 | High Sign | HFTD Tier 3 | Distribution | 2015-11-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018461 | 407462116 | High Sign | HFTD Tier 2 | Distribution | 2015-11-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018462 | 407468340 | Guy Guard | HFTD Tier 3 | Distribution | 2015-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018463 | 407468740 | High Sign | HFTD Tier 3 | Distribution | 2015-11-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018464 | 407471283 | High Sign | HFTD Tier 3 | Distribution | 2015-11-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018465 | 407482641 | High Sign | HFTD Tier 3 | Distribution | 2015-12-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018466 | 407482828 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-12-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018467 | 407482953 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-12-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018468 | 407483298 | Pole step | HFTD Tier 3 | Distribution | 2015-12-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018469 | 407483338 | Molding | HFTD Tier 3 | Distribution | 2015-12-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018470 | 407487405 | Guy | HFTD Tier 3 | Distribution | 2015-12-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018471 | 407489177 | High Sign | HFTD Tier 3 | Distribution | 2015-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018472 | 407489232 | High Sign | HFTD Tier 3 | Distribution | 2015-12-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018473 | 407494199 | High Sign | HFTD Tier 3 | Distribution | 2015-12-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018474 | 407494316 | High Sign | HFTD Tier 3 | Distribution | 2015-12-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018475 | 407494351 | High Sign | HFTD Tier 3 | Distribution | 2015-12-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018476 | 407494352 | High Sign | HFTD Tier 3 | Distribution | 2015-12-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018477 | 407494361 | Molding | HFTD Tier 3 | Distribution | 2015-12-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018478 | 407494370 | Molding | HFTD Tier 3 | Distribution | 2015-12-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018479 | 407494371 | Molding | HFTD Tier 3 | Distribution | 2015-12-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018480 | 407494380 | Molding | HFTD Tier 3 | Distribution | 2015-12-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018481 | 407494381 | Molding | HFTD Tier 3 | Distribution | 2015-12-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018482 | 407496155 | Molding | HFTD Tier 3 | Distribution | 2015-12-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018483 | 407496220 | High Sign | HFTD Tier 3 | Distribution | 2015-12-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018484 | 407496221 | Molding | HFTD Tier 3 | Distribution | 2015-12-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018485 | 407512117 | Right of Way | HFTD Tier 2 | Transmission | 2015-12-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018486 | 407521190 | Molding | HFTD Tier 2 | Distribution | 2016-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018487 | 407521432 | High Sign | HFTD Tier 2 | Distribution | 2016-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018488 | 407521446 | High Sign | HFTD Tier 2 | Distribution | 2016-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018489 | 407521544 | High Sign | HFTD Tier 2 | Distribution | 2016-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018490 | 407521749 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018491 | 407521872 | High Sign | HFTD Tier 2 | Distribution | 2016-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018492 | 407521876 | Guy | HFTD Tier 3 | Distribution | 2016-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018493 | 407521884 | Guy | HFTD Tier 3 | Distribution | 2016-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018494 | 407521911 | Guy | HFTD Tier 3 | Distribution | 2016-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018495 | 407522001 | Molding | HFTD Tier 2 | Distribution | 2016-01-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018496 | 407522761 | Molding | HFTD Tier 2 | Distribution | 2016-01-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018497 | 407523861 | Molding | HFTD Tier 2 | Distribution | 2016-01-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018498 | 407524028 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-01-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018499 | 407524118 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-01-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018500 | 407525238 | High Sign | HFTD Tier 3 | Distribution | 2016-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018501 | 407525340 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018502 | 407525854 | Riser/Conduit | HFTD Tier 3 | Distribution | 2016-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018503 | 407525905 | Pole step | HFTD Tier 3 | Distribution | 2016-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018504 | 407526053 | High Sign | HFTD Tier 2 | Distribution | 2016-01-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018505 | 407526709 | Guy | HFTD Tier 3 | Distribution | 2016-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018506 | 407527140 | High Sign | HFTD Tier 3 | Distribution | 2016-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018507 | 407527153 | Guy | HFTD Tier 2 | Distribution | 2016-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018508 | 407527202 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018509 | 407527264 | High Sign | HFTD Tier 2 | Distribution | 2016-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018510 | 407527419 | Molding | HFTD Tier 3 | Distribution | 2016-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018511 | 407527435 | High Sign | HFTD Tier 3 | Distribution | 2016-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018512 | 407527454 | Molding | HFTD Tier 3 | Distribution | 2016-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018513 | 407527534 | High Sign | HFTD Tier 3 | Distribution | 2016-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018514 | 407527628 | Molding | HFTD Tier 3 | Distribution | 2016-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018515 | 407527674 | High Sign | HFTD Tier 3 | Distribution | 2016-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018516 | 407527675 | High Sign | HFTD Tier 3 | Distribution | 2016-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018517 | 407527701 | High Sign | HFTD Tier 2 | Distribution | 2016-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018518 | 407527805 | Guy | HFTD Tier 3 | Distribution | 2016-01-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018519 | 407529181 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018520 | 407529191 | High Sign | HFTD Tier 3 | Distribution | 2016-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018521 | 407529240 | Molding | HFTD Tier 2 | Distribution | 2016-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018522 | 407529396 | Guy | HFTD Tier 3 | Distribution | 2016-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018523 | 407529416 | High Sign | HFTD Tier 3 | Distribution | 2016-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018524 | 407529601 | Bond | HFTD Tier 3 | Distribution | 2016-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018525 | 407529795 | High Sign | HFTD Tier 3 | Distribution | 2016-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018526 | 407529863 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018527 | 407529881 | Molding | HFTD Tier 3 | Distribution | 2016-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018528 | 407529978 | Molding | HFTD Tier 2 | Distribution | 2016-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018529 | 407530101 | High Sign | HFTD Tier 2 | Distribution | 2016-01-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018530 | 407532072 | Termination | HFTD Tier 2 | Distribution | 2016-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018531 | 407532120 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018532 | 407532143 | High Sign | HFTD Tier 2 | Distribution | 2016-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018533 | 407532151 | Molding | HFTD Tier 2 | Distribution | 2016-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018534 | 407532165 | High Sign | HFTD Tier 3 | Distribution | 2016-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018535 | 407532167 | High Sign | HFTD Tier 2 | Distribution | 2016-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018536 | 407532254 | Molding | HFTD Tier 3 | Distribution | 2016-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018537 | 407532359 | Guy Guard | HFTD Tier 2 | Distribution | 2016-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018538 | 407532361 | Molding | HFTD Tier 3 | Distribution | 2016-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018539 | 407532465 | High Sign | HFTD Tier 3 | Distribution | 2016-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018540 | 407532529 | High Sign | HFTD Tier 2 | Distribution | 2016-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018541 | 407532670 | Molding | HFTD Tier 2 | Distribution | 2016-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018542 | 407532926 | Guy | HFTD Tier 2 | Distribution | 2016-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018543 | 407532973 | High Sign | HFTD Tier 2 | Distribution | 2016-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018544 | 407534107 | Guy | HFTD Tier 2 | Distribution | 2016-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018545 | 407534301 | High Sign | HFTD Tier 2 | Distribution | 2016-01-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018546 | 407534401 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018547 | 407534570 | Riser/Conduit | HFTD Tier 2 | Distribution | 2016-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018548 | 407534870 | Molding | HFTD Tier 3 | Distribution | 2016-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018549 | 407535399 | Guy | HFTD Tier 2 | Distribution | 2016-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018550 | 407535569 | High Sign | HFTD Tier 2 | Distribution | 2016-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018551 | 407535599 | High Sign | HFTD Tier 2 | Distribution | 2016-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018552 | 407535617 | High Sign | HFTD Tier 2 | Distribution | 2016-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018553 | 407535808 | Guy | HFTD Tier 2 | Distribution | 2016-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018554 | 407535827 | High Sign | HFTD Tier 3 | Distribution | 2016-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018555 | 407535861 | High Sign | HFTD Tier 3 | Distribution | 2016-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018556 | 407535962 | High Sign | HFTD Tier 2 | Distribution | 2016-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018557 | 407535994 | High Sign | HFTD Tier 2 | Distribution | 2016-01-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018558 | 407537876 | Guy | HFTD Tier 2 | Distribution | 2016-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018559 | 407537931 | High Sign | HFTD Tier 2 | Distribution | 2016-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018560 | 407538187 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018561 | 407538191 | Guy | HFTD Tier 3 | Distribution | 2016-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018562 | 407538444 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018563 | 407538534 | High Sign | HFTD Tier 3 | Distribution | 2016-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018564 | 407538594 | High Sign | HFTD Tier 2 | Distribution | 2016-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018565 | 407539164 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018566 | 407540066 | High Sign | HFTD Tier 2 | Distribution | 2016-01-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018567 | 407540669 | Molding | HFTD Tier 2 | Distribution | 2016-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018568 | 407540781 | Molding | HFTD Tier 2 | Distribution | 2016-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018569 | 407540867 | Guy | HFTD Tier 2 | Distribution | 2016-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018570 | 407541101 | High Sign | HFTD Tier 3 | Distribution | 2016-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018571 | 407541310 | High Sign | HFTD Tier 3 | Distribution | 2016-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018572 | 407541449 | High Sign | HFTD Tier 3 | Distribution | 2016-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018573 | 407541452 | High Sign | HFTD Tier 3 | Distribution | 2016-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018574 | 407541481 | High Sign | HFTD Tier 3 | Distribution | 2016-01-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018575 | 407543509 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018576 | 407543585 | High Sign | HFTD Tier 3 | Distribution | 2016-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018577 | 407543688 | Riser/Conduit | HFTD Tier 2 | Distribution | 2016-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018578 | 407544057 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018579 | 407544256 | Molding | HFTD Tier 3 | Distribution | 2016-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018580 | 407544292 | Molding | HFTD Tier 3 | Distribution | 2016-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018581 | 407544449 | High Sign | HFTD Tier 2 | Distribution | 2016-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018582 | 407544456 | Guy Guard | HFTD Tier 3 | Distribution | 2016-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018583 | 407544468 | Guy | HFTD Tier 3 | Distribution | 2016-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018584 | 407544512 | High Sign | HFTD Tier 2 | Distribution | 2016-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018585 | 407544518 | Molding | HFTD Tier 2 | Distribution | 2016-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018586 | 407544530 | High Sign | HFTD Tier 2 | Distribution | 2016-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018587 | 407544543 | High Sign | HFTD Tier 2 | Distribution | 2016-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018588 | 407544556 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018589 | 407544750 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-01-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018590 | 407546139 | Molding | HFTD Tier 3 | Distribution | 2016-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018591 | 407546340 | High Sign | HFTD Tier 3 | Distribution | 2016-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018592 | 407546354 | High Sign | HFTD Tier 3 | Distribution | 2016-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018593 | 407546367 | Molding | HFTD Tier 2 | Distribution | 2016-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018594 | 407546448 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018595 | 407546468 | High Sign | HFTD Tier 3 | Distribution | 2016-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018596 | 407546520 | High Sign | HFTD Tier 3 | Distribution | 2016-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018597 | 407546521 | Molding | HFTD Tier 3 | Distribution | 2016-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018598 | 407546534 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018599 | 407546622 | High Sign | HFTD Tier 3 | Distribution | 2016-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018600 | 407546732 | Molding | HFTD Tier 3 | Distribution | 2016-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018601 | 407546752 | Molding | HFTD Tier 3 | Distribution | 2016-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018602 | 407546780 | Guy | HFTD Tier 3 | Distribution | 2016-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018603 | 407546838 | Guy | HFTD Tier 3 | Distribution | 2016-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018604 | 407547192 | High Sign | HFTD Tier 3 | Distribution | 2016-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018605 | 407547357 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018606 | 407547500 | High Sign | HFTD Tier 2 | Distribution | 2016-01-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018607 | 407548789 | High Sign | HFTD Tier 3 | Distribution | 2016-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018608 | 407549123 | High Sign | HFTD Tier 2 | Distribution | 2016-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018609 | 407549129 | High Sign | HFTD Tier 2 | Distribution | 2016-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018610 | 407549219 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018611 | 407549270 | High Sign | HFTD Tier 3 | Distribution | 2016-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018612 | 407549277 | Molding | HFTD Tier 2 | Distribution | 2016-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018613 | 407549348 | High Sign | HFTD Tier 3 | Distribution | 2016-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018614 | 407549374 | Termination | HFTD Tier 2 | Distribution | 2016-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018615 | 407549737 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018616 | 407549738 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018617 | 407549918 | High Sign | HFTD Tier 2 | Distribution | 2016-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018618 | 407550138 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018619 | 407550162 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018620 | 407550191 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018621 | 407550323 | High Sign | HFTD Tier 2 | Distribution | 2016-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018622 | 407550324 | Guy | HFTD Tier 3 | Distribution | 2016-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018623 | 407550400 | High Sign | HFTD Tier 2 | Distribution | 2016-01-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018624 | 407552376 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018625 | 407552511 | Molding | HFTD Tier 3 | Distribution | 2016-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018626 | 407552535 | Guy | HFTD Tier 2 | Distribution | 2016-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018627 | 407552571 | Guy | HFTD Tier 2 | Distribution | 2016-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018628 | 407552674 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018629 | 407552677 | Molding | HFTD Tier 3 | Distribution | 2016-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018630 | 407552732 | Pole step | HFTD Tier 3 | Distribution | 2016-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018631 | 407552863 | Molding | HFTD Tier 2 | Distribution | 2016-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018632 | 407552948 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018633 | 407553444 | Molding | HFTD Tier 2 | Distribution | 2016-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018634 | 407553477 | High Sign | HFTD Tier 2 | Distribution | 2016-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018635 | 407553582 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018636 | 407553599 | High Sign | HFTD Tier 2 | Distribution | 2016-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018637 | 407554495 | Guy Guard | HFTD Tier 3 | Distribution | 2016-01-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018638 | 407555564 | High Sign | HFTD Tier 3 | Distribution | 2016-01-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018639 | 407555648 | Pole step | HFTD Tier 3 | Distribution | 2016-01-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018640 | 407555860 | High Sign | HFTD Tier 2 | Distribution | 2016-01-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018641 | 407555862 | Guy | HFTD Tier 2 | Distribution | 2016-01-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018642 | 407556029 | High Sign | HFTD Tier 2 | Distribution | 2016-01-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018643 | 407556035 | Guy | HFTD Tier 2 | Distribution | 2016-01-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018644 | 407556066 | Molding | HFTD Tier 2 | Distribution | 2016-01-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018645 | 407556094 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-01-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018646 | 407556105 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-01-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018647 | 407556131 | High Sign | HFTD Tier 3 | Distribution | 2016-01-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018648 | 407556141 | Molding | HFTD Tier 3 | Distribution | 2016-01-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018649 | 407556236 | High Sign | HFTD Tier 2 | Distribution | 2016-01-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018650 | 407556373 | High Sign | HFTD Tier 2 | Distribution | 2016-01-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018651 | 407556470 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-01-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018652 | 407556562 | Guy | HFTD Tier 3 | Distribution | 2016-01-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018653 | 407556570 | Molding | HFTD Tier 3 | Distribution | 2016-01-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018654 | 407556733 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-01-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018655 | 407556766 | High Sign | HFTD Tier 3 | Distribution | 2016-01-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018656 | 407556862 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-01-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018657 | 407558597 | High Sign | HFTD Tier 3 | Distribution | 2016-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018658 | 407558808 | High Sign | HFTD Tier 3 | Distribution | 2016-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018659 | 407558930 | Guy | HFTD Tier 3 | Distribution | 2016-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018660 | 407558959 | High Sign | HFTD Tier 2 | Distribution | 2016-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018661 | 407558991 | High Sign | HFTD Tier 3 | Distribution | 2016-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018662 | 407559240 | High Sign | HFTD Tier 3 | Distribution | 2016-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018663 | 407559264 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018664 | 407559369 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018665 | 407559383 | Pole step | HFTD Tier 2 | Distribution | 2016-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018666 | 407559634 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018667 | 407559667 | Guy | HFTD Tier 3 | Distribution | 2016-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018668 | 407559670 | Guy Guard | HFTD Tier 3 | Distribution | 2016-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018669 | 407559831 | Molding | HFTD Tier 3 | Distribution | 2016-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018670 | 407559891 | High Sign | HFTD Tier 3 | Distribution | 2016-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018671 | 407559976 | High Sign | HFTD Tier 3 | Distribution | 2016-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018672 | 407560114 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018673 | 407560175 | High Sign | HFTD Tier 3 | Distribution | 2016-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018674 | 407560238 | High Sign | HFTD Tier 3 | Distribution | 2016-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018675 | 407560284 | High Sign | HFTD Tier 2 | Distribution | 2016-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018676 | 407560420 | Molding | HFTD Tier 2 | Distribution | 2016-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018677 | 407560744 | Guy | HFTD Tier 3 | Distribution | 2016-01-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018678 | 407561825 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018679 | 407561857 | High Sign | HFTD Tier 2 | Distribution | 2016-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018680 | 407561931 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018681 | 407562011 | High Sign | HFTD Tier 2 | Distribution | 2016-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018682 | 407562081 | Guy | HFTD Tier 3 | Distribution | 2016-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018683 | 407562099 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018684 | 407562274 | High Sign | HFTD Tier 3 | Distribution | 2016-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018685 | 407562531 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018686 | 407562672 | High Sign | HFTD Tier 3 | Distribution | 2016-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018687 | 407562949 | High Sign | HFTD Tier 3 | Distribution | 2016-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018688 | 407562988 | High Sign | HFTD Tier 3 | Distribution | 2016-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018689 | 407563059 | Pole step | HFTD Tier 3 | Distribution | 2016-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018690 | 407563086 | Guy | HFTD Tier 3 | Distribution | 2016-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018691 | 407563244 | Molding | HFTD Tier 2 | Distribution | 2016-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018692 | 407563247 | Guy | HFTD Tier 2 | Distribution | 2016-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018693 | 407563273 | Molding | HFTD Tier 3 | Distribution | 2016-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018694 | 407563313 | Guy | HFTD Tier 2 | Distribution | 2016-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018695 | 407563334 | Guy | HFTD Tier 2 | Distribution | 2016-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018696 | 407563465 | High Sign | HFTD Tier 3 | Distribution | 2016-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018697 | 407564440 | Guy | HFTD Tier 3 | Distribution | 2016-01-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018698 | 407565075 | High Sign | HFTD Tier 2 | Distribution | 2016-01-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018699 | 407565679 | Molding | HFTD Tier 3 | Distribution | 2016-01-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018700 | 407565816 | Molding | HFTD Tier 3 | Distribution | 2016-01-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018701 | 407565819 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-01-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018702 | 407565843 | High Sign | HFTD Tier 2 | Distribution | 2016-01-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018703 | 407565852 | High Sign | HFTD Tier 2 | Distribution | 2016-01-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018704 | 407567736 | Guy Guard | HFTD Tier 3 | Distribution | 2016-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018705 | 407567767 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018706 | 407567934 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018707 | 407568049 | Guy | HFTD Tier 2 | Distribution | 2016-01-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018708 | 407569871 | Guy | HFTD Tier 2 | Distribution | 2016-01-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018709 | 407569950 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-01-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018710 | 407570051 | Molding | HFTD Tier 2 | Distribution | 2016-01-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018711 | 407570145 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-01-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018712 | 407570162 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-01-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018713 | 407571419 | Guy | HFTD Tier 2 | Distribution | 2016-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018714 | 407571424 | Molding | HFTD Tier 2 | Distribution | 2016-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018715 | 407571438 | High Sign | HFTD Tier 3 | Distribution | 2016-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018716 | 407571536 | Molding | HFTD Tier 3 | Distribution | 2016-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018717 | 407571775 | High Sign | HFTD Tier 2 | Distribution | 2016-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018718 | 407571796 | High Sign | HFTD Tier 3 | Distribution | 2016-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018719 | 407572175 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018720 | 407572241 | Molding | HFTD Tier 3 | Distribution | 2016-02-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018721 | 407573529 | Guy | HFTD Tier 3 | Distribution | 2016-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018722 | 407573562 | High Sign | HFTD Tier 3 | Distribution | 2016-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018723 | 407574081 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018724 | 407574115 | High Sign | HFTD Tier 2 | Distribution | 2016-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018725 | 407574461 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-02-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018726 | 407575970 | High Sign | HFTD Tier 3 | Distribution | 2016-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018727 | 407576054 | High Sign | HFTD Tier 3 | Distribution | 2016-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018728 | 407576202 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018729 | 407576255 | High Sign | HFTD Tier 3 | Distribution | 2016-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018730 | 407576258 | Guy | HFTD Tier 3 | Distribution | 2016-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018731 | 407576378 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018732 | 407576487 | Anchor | HFTD Tier 3 | Distribution | 2016-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018733 | 407576491 | High Sign | HFTD Tier 2 | Distribution | 2016-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018734 | 407576504 | Molding | HFTD Tier 3 | Distribution | 2016-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018735 | 407576509 | Molding | HFTD Tier 3 | Distribution | 2016-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018736 | 407576548 | High Sign | HFTD Tier 3 | Distribution | 2016-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018737 | 407576709 | High Sign | HFTD Tier 2 | Distribution | 2016-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018738 | 407576824 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018739 | 407576958 | Molding | HFTD Tier 3 | Distribution | 2016-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018740 | 407576959 | High Sign | HFTD Tier 3 | Distribution | 2016-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018741 | 407576971 | High Sign | HFTD Tier 2 | Distribution | 2016-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018742 | 407576976 | High Sign | HFTD Tier 2 | Distribution | 2016-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018743 | 407578386 | Guy Guard | HFTD Tier 3 | Distribution | 2016-02-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018744 | 407579175 | High Sign | HFTD Tier 3 | Distribution | 2016-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018745 | 407579255 | Guy | HFTD Tier 2 | Distribution | 2016-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018746 | 407579758 | High Sign | HFTD Tier 2 | Distribution | 2016-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018747 | 407579988 | High Sign | HFTD Tier 2 | Distribution | 2016-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018748 | 407580064 | Molding | HFTD Tier 2 | Distribution | 2016-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018749 | 407580281 | High Sign | HFTD Tier 2 | Distribution | 2016-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018750 | 407580382 | Molding | HFTD Tier 2 | Distribution | 2016-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018751 | 407580410 | High Sign | HFTD Tier 2 | Distribution | 2016-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018752 | 407580429 | Guy | HFTD Tier 2 | Distribution | 2016-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018753 | 407580434 | High Sign | HFTD Tier 3 | Distribution | 2016-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018754 | 407580683 | High Sign | HFTD Tier 2 | Distribution | 2016-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018755 | 407580765 | Molding | HFTD Tier 3 | Distribution | 2016-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018756 | 407580773 | Guy | HFTD Tier 2 | Distribution | 2016-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018757 | 407580792 | Guy Guard | HFTD Tier 2 | Distribution | 2016-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018758 | 407581093 | High Sign | HFTD Tier 2 | Distribution | 2016-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018759 | 407582154 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018760 | 407582245 | High Sign | HFTD Tier 2 | Distribution | 2016-02-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018761 | 407582725 | Molding | HFTD Tier 3 | Distribution | 2016-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018762 | 407582744 | High Sign | HFTD Tier 3 | Distribution | 2016-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018763 | 407583240 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018764 | 407583463 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018765 | 407583547 | Molding | HFTD Tier 3 | Distribution | 2016-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018766 | 407583552 | High Sign | HFTD Tier 3 | Distribution | 2016-02-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018767 | 407584506 | Pole step | HFTD Tier 3 | Distribution | 2016-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018768 | 407584875 | Molding | HFTD Tier 3 | Distribution | 2016-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018769 | 407584918 | Molding | HFTD Tier 3 | Distribution | 2016-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018770 | 407585017 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018771 | 407585097 | Molding | HFTD Tier 3 | Distribution | 2016-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018772 | 407585362 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018773 | 407585384 | Pole step | HFTD Tier 3 | Distribution | 2016-02-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018774 | 407586077 | Molding | HFTD Tier 3 | Distribution | 2016-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018775 | 407586613 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018776 | 407586655 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018777 | 407586717 | High Sign | HFTD Tier 2 | Distribution | 2016-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018778 | 407586763 | Guy Guard | HFTD Tier 2 | Distribution | 2016-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018779 | 407586804 | High Sign | HFTD Tier 2 | Distribution | 2016-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018780 | 407586891 | High Sign | HFTD Tier 2 | Distribution | 2016-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018781 | 407586949 | High Sign | HFTD Tier 2 | Distribution | 2016-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018782 | 407587054 | Pole step | HFTD Tier 2 | Distribution | 2016-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018783 | 407587056 | High Sign | HFTD Tier 3 | Distribution | 2016-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018784 | 407587067 | High Sign | HFTD Tier 3 | Distribution | 2016-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018785 | 407587085 | High Sign | HFTD Tier 3 | Distribution | 2016-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018786 | 407587133 | High Sign | HFTD Tier 3 | Distribution | 2016-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018787 | 407587152 | Guy | HFTD Tier 2 | Distribution | 2016-02-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018788 | 407588429 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018789 | 407588433 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018790 | 407588493 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018791 | 407588549 | Guy | HFTD Tier 2 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018792 | 407588606 | Molding | HFTD Tier 3 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018793 | 407588680 | High Sign | HFTD Tier 2 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018794 | 407588713 | Guy Guard | HFTD Tier 3 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018795 | 407588757 | Molding | HFTD Tier 2 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018796 | 407588922 | High Sign | HFTD Tier 2 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018797 | 407588935 | High Sign | HFTD Tier 2 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018798 | 407589098 | Molding | HFTD Tier 2 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018799 | 407589099 | Guy | HFTD Tier 3 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018800 | 407589219 | Insulator | HFTD Tier 2 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018801 | 407589301 | High Sign | HFTD Tier 3 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018802 | 407589327 | High Sign | HFTD Tier 3 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018803 | 407589422 | High Sign | HFTD Tier 3 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018804 | 407589447 | Molding | HFTD Tier 3 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018805 | 407589464 | Guy | HFTD Tier 2 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018806 | 407589485 | High Sign | HFTD Tier 2 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018807 | 407589555 | Molding | HFTD Tier 3 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018808 | 407589572 | Guy | HFTD Tier 3 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018809 | 407589620 | Molding | HFTD Tier 3 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018810 | 407589722 | High Sign | HFTD Tier 2 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018811 | 407590274 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018812 | 407591074 | Crossarm | HFTD Tier 2 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018813 | 407591506 | Anchor | HFTD Tier 3 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018814 | 407591519 | Anchor | HFTD Tier 3 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018815 | 407591569 | Guy | HFTD Tier 3 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018816 | 407591779 | High Sign | HFTD Tier 2 | Distribution | 2016-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018817 | 407592287 | Pole step | HFTD Tier 2 | Distribution | 2016-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018818 | 407592309 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018819 | 407592921 | Riser/Conduit | HFTD Tier 3 | Distribution | 2011-11-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018820 | 407592932 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-11-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018821 | 407593277 | Molding | HFTD Tier 3 | Distribution | 2016-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018822 | 407593284 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018823 | 407593300 | Molding | HFTD Tier 2 | Distribution | 2016-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018824 | 407593623 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018825 | 407593624 | Guy | HFTD Tier 3 | Distribution | 2016-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018826 | 407594776 | Guy | HFTD Tier 2 | Distribution | 2016-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018827 | 407595049 | Guy | HFTD Tier 2 | Distribution | 2016-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018828 | 407595931 | Molding | HFTD Tier 3 | Distribution | 2016-02-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018829 | 407596260 | High Sign | HFTD Tier 2 | Distribution | 2016-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018830 | 407596267 | Molding | HFTD Tier 3 | Distribution | 2016-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018831 | 407596337 | Molding | HFTD Tier 3 | Distribution | 2016-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018832 | 407596619 | High Sign | HFTD Tier 2 | Distribution | 2016-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018833 | 407596734 | High Sign | HFTD Tier 2 | Distribution | 2016-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018834 | 407596830 | High Sign | HFTD Tier 2 | Distribution | 2016-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018835 | 407596833 | Molding | HFTD Tier 3 | Distribution | 2016-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018836 | 407596997 | Molding | HFTD Tier 3 | Distribution | 2016-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018837 | 407596999 | High Sign | HFTD Tier 3 | Distribution | 2016-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018838 | 407597010 | Pole step | HFTD Tier 2 | Distribution | 2016-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018839 | 407597064 | High Sign | HFTD Tier 3 | Distribution | 2016-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018840 | 407597169 | High Sign | HFTD Tier 2 | Distribution | 2016-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018841 | 407597233 | Crossarm | HFTD Tier 2 | Distribution | 2016-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018842 | 407597433 | High Sign | HFTD Tier 3 | Distribution | 2016-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018843 | 407597475 | Guy | HFTD Tier 2 | Distribution | 2016-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018844 | 407597605 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018845 | 407597607 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018846 | 407598238 | Molding | HFTD Tier 2 | Distribution | 2016-02-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018847 | 407598853 | Molding | HFTD Tier 3 | Distribution | 2016-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018848 | 407599217 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018849 | 407599600 | Molding | HFTD Tier 3 | Distribution | 2016-02-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018850 | 407601308 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018851 | 407601328 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018852 | 407601372 | Guy | HFTD Tier 3 | Distribution | 2016-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018853 | 407601392 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018854 | 407601431 | High Sign | HFTD Tier 2 | Distribution | 2016-02-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018855 | 407601859 | Molding | HFTD Tier 3 | Distribution | 2016-02-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018856 | 407602406 | Guy Guard | HFTD Tier 3 | Distribution | 2016-02-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018857 | 407602703 | High Sign | HFTD Tier 2 | Distribution | 2016-02-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018858 | 407602733 | High Sign | HFTD Tier 2 | Distribution | 2016-02-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018859 | 407602812 | Molding | HFTD Tier 2 | Distribution | 2016-02-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018860 | 407602897 | High Sign | HFTD Tier 2 | Distribution | 2016-02-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018861 | 407602945 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-02-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018862 | 407603015 | Guy | HFTD Tier 2 | Distribution | 2016-02-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018863 | 407603071 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-02-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018864 | 407603261 | Termination | HFTD Tier 2 | Distribution | 2016-02-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018865 | 407603291 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-02-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018866 | 407603437 | Guy Guard | HFTD Tier 3 | Distribution | 2016-02-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018867 | 407603519 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-02-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018868 | 407603589 | Termination | HFTD Tier 2 | Distribution | 2016-02-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018869 | 407604099 | High Sign | HFTD Tier 2 | Distribution | 2016-02-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018870 | 407604283 | High Sign | HFTD Tier 2 | Distribution | 2016-02-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018871 | 407604635 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-02-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018872 | 407605316 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-02-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018873 | 407605545 | Guy | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018874 | 407605564 | Molding | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018875 | 407605671 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018876 | 407605761 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018877 | 407605860 | Guy | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018878 | 407606344 | Molding | HFTD Tier 3 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018879 | 407606376 | High Sign | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018880 | 407606621 | High Sign | HFTD Tier 3 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018881 | 407606676 | Guy | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018882 | 407606797 | High Sign | HFTD Tier 3 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018883 | 407607099 | High Sign | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018884 | 407607183 | Molding | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018885 | 407607834 | Pole step | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018886 | 407607846 | Riser/Conduit | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018887 | 407608694 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018888 | 407608708 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018889 | 407608752 | High Sign | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018890 | 407609026 | Molding | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018891 | 407609032 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018892 | 407609041 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018893 | 407609050 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018894 | 407609051 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018895 | 407609070 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018896 | 407609080 | Molding | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018897 | 407609081 | High Sign | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018898 | 407609745 | Cutout/Fuse | HFTD Tier 3 | Distribution | 2016-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018899 | 407609802 | Guy | HFTD Tier 3 | Distribution | 2016-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018900 | 407610237 | Guy | HFTD Tier 3 | Distribution | 2016-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018901 | 407610289 | Guy | HFTD Tier 3 | Distribution | 2016-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018902 | 407610343 | Guy | HFTD Tier 3 | Distribution | 2016-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018903 | 407610370 | Guy | HFTD Tier 3 | Distribution | 2016-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018904 | 407611135 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018905 | 407611829 | Guy | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018906 | 407611841 | Guy | HFTD Tier 3 | Distribution | 2016-02-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018907 | 407611912 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018908 | 407612074 | Guy | HFTD Tier 2 | Distribution | 2016-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018909 | 407612469 | High Sign | HFTD Tier 2 | Distribution | 2016-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018910 | 407612483 | Guy | HFTD Tier 3 | Distribution | 2016-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018911 | 407612520 | Guy | HFTD Tier 3 | Distribution | 2016-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018912 | 407612704 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018913 | 407612881 | Guy | HFTD Tier 3 | Distribution | 2016-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018914 | 407613105 | Pole step | HFTD Tier 3 | Distribution | 2016-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018915 | 407613382 | Guy | HFTD Tier 3 | Distribution | 2016-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018916 | 407613992 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-02-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018917 | 407614814 | Molding | HFTD Tier 3 | Distribution | 2016-02-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018918 | 407615870 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018919 | 407615894 | Guy | HFTD Tier 3 | Distribution | 2016-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018920 | 407615936 | Molding | HFTD Tier 2 | Distribution | 2016-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018921 | 407615972 | Guy | HFTD Tier 3 | Distribution | 2016-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018922 | 407616023 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018923 | 407616082 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018924 | 407616345 | High Sign | HFTD Tier 3 | Distribution | 2016-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018925 | 407617099 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018926 | 407617115 | High Sign | HFTD Tier 2 | Distribution | 2016-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018927 | 407617127 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-02-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018928 | 407617131 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-02-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018929 | 407617144 | Molding | HFTD Tier 2 | Distribution | 2016-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018930 | 407617162 | Guy Guard | HFTD Tier 3 | Distribution | 2016-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018931 | 407617215 | Ground | HFTD Tier 2 | Distribution | 2016-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018932 | 407617216 | Molding | HFTD Tier 2 | Distribution | 2016-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018933 | 407617230 | Molding | HFTD Tier 2 | Distribution | 2016-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018934 | 407617328 | Guy | HFTD Tier 3 | Distribution | 2016-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018935 | 407617397 | High Sign | HFTD Tier 3 | Distribution | 2016-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018936 | 407617413 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018937 | 407618229 | High Sign | HFTD Tier 3 | Distribution | 2016-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018938 | 407618534 | Guy | HFTD Tier 3 | Distribution | 2016-02-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018939 | 407618718 | Guy Guard | HFTD Tier 3 | Distribution | 2016-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018940 | 407618795 | Guy | HFTD Tier 3 | Distribution | 2016-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018941 | 407618828 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018942 | 407618888 | Guy | HFTD Tier 3 | Distribution | 2016-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018943 | 407619359 | High Sign | HFTD Tier 2 | Distribution | 2016-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018944 | 407619386 | Molding | HFTD Tier 3 | Distribution | 2016-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018945 | 407619500 | High Sign | HFTD Tier 2 | Distribution | 2016-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018946 | 407619543 | Molding | HFTD Tier 2 | Distribution | 2016-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018947 | 407620184 | Guy | HFTD Tier 2 | Distribution | 2016-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018948 | 407620199 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018949 | 407620242 | Pole step | HFTD Tier 2 | Distribution | 2016-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018950 | 407620267 | Molding | HFTD Tier 3 | Distribution | 2016-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018951 | 407620320 | High Sign | HFTD Tier 3 | Distribution | 2016-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018952 | 407620321 | High Sign | HFTD Tier 3 | Distribution | 2016-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018953 | 407620324 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018954 | 407620325 | High Sign | HFTD Tier 2 | Distribution | 2016-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018955 | 407620342 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018956 | 407620350 | Molding | HFTD Tier 3 | Distribution | 2016-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018957 | 407621347 | Guy | HFTD Tier 3 | Distribution | 2016-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018958 | 407621353 | Guy | HFTD Tier 3 | Distribution | 2016-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018959 | 407621410 | High Sign | HFTD Tier 3 | Distribution | 2016-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018960 | 407622148 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018961 | 407622224 | Molding | HFTD Tier 3 | Distribution | 2016-02-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018962 | 407622890 | High Sign | HFTD Tier 2 | Distribution | 2016-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018963 | 407623069 | High Sign | HFTD Tier 3 | Distribution | 2016-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018964 | 407623176 | Guy | HFTD Tier 3 | Distribution | 2016-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018965 | 407623582 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018966 | 407624400 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018967 | 407624401 | Guy | HFTD Tier 2 | Distribution | 2016-02-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018968 | 407625211 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018969 | 407625966 | High Sign | HFTD Tier 3 | Distribution | 2016-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018970 | 407626026 | High Sign | HFTD Tier 3 | Distribution | 2016-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018971 | 407626072 | Molding | HFTD Tier 3 | Distribution | 2016-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018972 | 407626372 | High Sign | HFTD Tier 3 | Distribution | 2016-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018973 | 407626375 | High Sign | HFTD Tier 2 | Distribution | 2016-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018974 | 407626481 | High Sign | HFTD Tier 3 | Distribution | 2016-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018975 | 407626735 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-02-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018976 | 407628029 | High Sign | HFTD Tier 3 | Distribution | 2016-02-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018977 | 407628049 | High Sign | HFTD Tier 3 | Distribution | 2016-02-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018978 | 407628246 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-02-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018979 | 407629333 | High Sign | HFTD Tier 3 | Distribution | 2016-02-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018980 | 407630525 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-02-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018981 | 407630770 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-02-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018982 | 407631374 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-02-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018983 | 407631904 | Molding | HFTD Tier 3 | Distribution | 2016-02-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018984 | 407632045 | High Sign | HFTD Tier 3 | Distribution | 2016-02-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018985 | 407632222 | Guy | HFTD Tier 3 | Distribution | 2016-02-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018986 | 407632334 | High Sign | HFTD Tier 2 | Distribution | 2016-02-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018987 | 407632385 | Molding | HFTD Tier 2 | Distribution | 2016-02-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018988 | 407632508 | Riser/Conduit | HFTD Tier 3 | Distribution | 2016-02-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018989 | 407632592 | Guy | HFTD Tier 3 | Distribution | 2016-02-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018990 | 407632684 | Molding | HFTD Tier 3 | Distribution | 2016-02-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018991 | 407632810 | Guy | HFTD Tier 2 | Distribution | 2016-02-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018992 | 407634059 | Guy | HFTD Tier 3 | Distribution | 2016-02-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018993 | 407634151 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-02-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018994 | 407634618 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-02-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018995 | 407634737 | High Sign | HFTD Tier 3 | Distribution | 2016-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018996 | 407634947 | High Sign | HFTD Tier 3 | Distribution | 2016-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018997 | 407635014 | High Sign | HFTD Tier 2 | Distribution | 2016-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018998 | 407635033 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130018999 | 407635059 | High Sign | HFTD Tier 2 | Distribution | 2016-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019000 | 407635209 | Guy | HFTD Tier 3 | Distribution | 2016-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019001 | 407635214 | High Sign | HFTD Tier 2 | Distribution | 2016-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019002 | 407635246 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019003 | 407635252 | Guy | HFTD Tier 3 | Distribution | 2016-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019004 | 407635284 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019005 | 407635316 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019006 | 407635352 | Molding | HFTD Tier 2 | Distribution | 2016-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019007 | 407635504 | Guy Guard | HFTD Tier 3 | Distribution | 2016-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019008 | 407635751 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019009 | 407636037 | High Sign | HFTD Tier 2 | Distribution | 2016-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019010 | 407636120 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019011 | 407636134 | Molding | HFTD Tier 3 | Distribution | 2016-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019012 | 407636267 | Guy Guard | HFTD Tier 3 | Distribution | 2016-03-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019013 | 407638268 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019014 | 407638465 | Guy | HFTD Tier 3 | Distribution | 2016-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019015 | 407638467 | Guy | HFTD Tier 3 | Distribution | 2016-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019016 | 407638468 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019017 | 407638509 | High Sign | HFTD Tier 2 | Distribution | 2016-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019018 | 407638560 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019019 | 407638603 | High Sign | HFTD Tier 2 | Distribution | 2016-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019020 | 407639012 | Molding | HFTD Tier 3 | Distribution | 2016-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019021 | 407639034 | High Sign | HFTD Tier 3 | Distribution | 2016-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019022 | 407639126 | High Sign | HFTD Tier 2 | Distribution | 2016-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019023 | 407639144 | High Sign | HFTD Tier 2 | Distribution | 2016-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019024 | 407639193 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-03-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019025 | 407641323 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019026 | 407641549 | High Sign | HFTD Tier 3 | Distribution | 2016-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019027 | 407641942 | High Sign | HFTD Tier 3 | Distribution | 2016-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019028 | 407642324 | Molding | HFTD Tier 3 | Distribution | 2016-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019029 | 407642541 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019030 | 407642818 | Molding | HFTD Tier 3 | Distribution | 2016-03-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019031 | 407645117 | High Sign | HFTD Tier 3 | Distribution | 2016-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019032 | 407645125 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019033 | 407645157 | Pole step | HFTD Tier 2 | Distribution | 2016-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019034 | 407645172 | High Sign | HFTD Tier 3 | Distribution | 2016-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019035 | 407645484 | Pole step | HFTD Tier 2 | Distribution | 2016-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019036 | 407645513 | High Sign | HFTD Tier 2 | Distribution | 2016-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019037 | 407645531 | Pole step | HFTD Tier 2 | Distribution | 2016-03-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019038 | 407647188 | Guy | HFTD Tier 3 | Distribution | 2016-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019039 | 407647226 | Guy | HFTD Tier 3 | Distribution | 2016-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019040 | 407647248 | High Sign | HFTD Tier 3 | Distribution | 2016-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019041 | 407647311 | Guy | HFTD Tier 3 | Distribution | 2016-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019042 | 407647576 | Guy Guard | HFTD Tier 2 | Distribution | 2016-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019043 | 407647579 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019044 | 407647612 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019045 | 407647616 | Guy | HFTD Tier 2 | Distribution | 2016-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019046 | 407647624 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019047 | 407647630 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019048 | 407647654 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019049 | 407647681 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-03-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019050 | 407648405 | High Sign | HFTD Tier 3 | Distribution | 2016-03-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019051 | 407648594 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-03-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019052 | 407649417 | Molding | HFTD Tier 3 | Distribution | 2016-03-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019053 | 407650958 | Guy | HFTD Tier 2 | Distribution | 2016-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019054 | 407651105 | Guy | HFTD Tier 3 | Distribution | 2016-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019055 | 407651789 | Guy | HFTD Tier 2 | Distribution | 2016-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019056 | 407651855 | Molding | HFTD Tier 2 | Distribution | 2016-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019057 | 407651856 | Guy | HFTD Tier 2 | Distribution | 2016-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019058 | 407651862 | Guy | HFTD Tier 2 | Distribution | 2016-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019059 | 407651885 | Molding | HFTD Tier 2 | Distribution | 2016-03-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019060 | 407653484 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019061 | 407654149 | Pole step | HFTD Tier 2 | Distribution | 2016-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019062 | 407654177 | Guy | HFTD Tier 2 | Distribution | 2016-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019063 | 407654189 | High Sign | HFTD Tier 3 | Distribution | 2016-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019064 | 407654198 | High Sign | HFTD Tier 3 | Distribution | 2016-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019065 | 407654234 | High Sign | HFTD Tier 2 | Distribution | 2016-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019066 | 407654291 | High Sign | HFTD Tier 2 | Distribution | 2016-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019067 | 407654349 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019068 | 407654421 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019069 | 407654649 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019070 | 407654681 | High Sign | HFTD Tier 3 | Distribution | 2016-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019071 | 407654738 | High Sign | HFTD Tier 2 | Distribution | 2016-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019072 | 407654797 | Guy | HFTD Tier 3 | Distribution | 2016-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019073 | 407655042 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-03-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019074 | 407656579 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019075 | 407656798 | High Sign | HFTD Tier 2 | Distribution | 2016-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019076 | 407657413 | Guy | HFTD Tier 3 | Distribution | 2016-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019077 | 407657458 | Molding | HFTD Tier 2 | Distribution | 2016-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019078 | 407657691 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019079 | 407657854 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-03-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019080 | 407659459 | Guy | HFTD Tier 3 | Distribution | 2016-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019081 | 407659625 | High Sign | HFTD Tier 3 | Distribution | 2016-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019082 | 407659651 | High Sign | HFTD Tier 3 | Distribution | 2016-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019083 | 407660386 | High Sign | HFTD Tier 3 | Distribution | 2016-03-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019084 | 407662015 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-03-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019085 | 407663786 | High Sign | HFTD Tier 3 | Distribution | 2016-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019086 | 407663958 | Molding | HFTD Tier 3 | Distribution | 2016-03-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019087 | 407665761 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019088 | 407665976 | Termination | HFTD Tier 2 | Distribution | 2016-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019089 | 407665984 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019090 | 407665987 | Guy Guard | HFTD Tier 3 | Distribution | 2016-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019091 | 407666374 | High Sign | HFTD Tier 3 | Distribution | 2016-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019092 | 407666783 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019093 | 407666792 | Molding | HFTD Tier 3 | Distribution | 2016-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019094 | 407666828 | Guy Guard | HFTD Tier 3 | Distribution | 2016-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019095 | 407666855 | High Sign | HFTD Tier 3 | Distribution | 2016-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019096 | 407667139 | Guy | HFTD Tier 2 | Distribution | 2016-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019097 | 407668848 | High Sign | HFTD Tier 2 | Distribution | 2016-03-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019098 | 407669370 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019099 | 407669689 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019100 | 407669894 | High Sign | HFTD Tier 3 | Distribution | 2016-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019101 | 407669898 | High Sign | HFTD Tier 3 | Distribution | 2016-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019102 | 407669916 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019103 | 407669928 | High Sign | HFTD Tier 3 | Distribution | 2016-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019104 | 407669947 | High Sign | HFTD Tier 3 | Distribution | 2016-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019105 | 407670036 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019106 | 407670069 | High Sign | HFTD Tier 3 | Distribution | 2016-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019107 | 407670084 | Guy Guard | HFTD Tier 2 | Distribution | 2016-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019108 | 407670092 | Guy | HFTD Tier 2 | Distribution | 2016-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019109 | 407670101 | Guy | HFTD Tier 2 | Distribution | 2016-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019110 | 407670267 | High Sign | HFTD Tier 3 | Distribution | 2016-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019111 | 407670309 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019112 | 407670344 | Riser/Conduit | HFTD Tier 3 | Distribution | 2016-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019113 | 407670353 | Pole step | HFTD Tier 3 | Distribution | 2016-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019114 | 407670719 | High Sign | HFTD Tier 2 | Distribution | 2016-03-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019115 | 407673433 | High Sign | HFTD Tier 2 | Distribution | 2016-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019116 | 407673625 | Guy | HFTD Tier 2 | Distribution | 2016-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019117 | 407673653 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019118 | 407673761 | Insulator | HFTD Tier 2 | Distribution | 2016-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019119 | 407673921 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019120 | 407675353 | Molding | HFTD Tier 3 | Distribution | 2016-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019121 | 407675694 | High Sign | HFTD Tier 3 | Distribution | 2016-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019122 | 407675732 | High Sign | HFTD Tier 3 | Distribution | 2016-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019123 | 407675740 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-03-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019124 | 407676413 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019125 | 407678414 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019126 | 407678440 | Molding | HFTD Tier 2 | Distribution | 2016-03-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019127 | 407679925 | High Sign | HFTD Tier 2 | Distribution | 2016-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019128 | 407679937 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019129 | 407681643 | Molding | HFTD Tier 3 | Distribution | 2016-03-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019130 | 407681735 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019131 | 407681744 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019132 | 407681758 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019133 | 407681779 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019134 | 407681790 | Guy Guard | HFTD Tier 3 | Distribution | 2016-03-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019135 | 407682132 | Guy | HFTD Tier 2 | Distribution | 2016-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019136 | 407682327 | Guy | HFTD Tier 2 | Distribution | 2016-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019137 | 407682449 | High Sign | HFTD Tier 3 | Distribution | 2016-03-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019138 | 407684895 | Guy | HFTD Tier 2 | Distribution | 2016-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019139 | 407684912 | Guy | HFTD Tier 2 | Distribution | 2016-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019140 | 407685119 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019141 | 407685232 | High Sign | HFTD Tier 2 | Distribution | 2016-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019142 | 407685244 | Guy | HFTD Tier 2 | Distribution | 2016-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019143 | 407685270 | Guy | HFTD Tier 2 | Distribution | 2016-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019144 | 407685397 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019145 | 407685807 | Guy Guard | HFTD Tier 3 | Distribution | 2016-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019146 | 407685901 | Molding | HFTD Tier 3 | Distribution | 2016-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019147 | 407685911 | High Sign | HFTD Tier 3 | Distribution | 2016-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019148 | 407687117 | Molding | HFTD Tier 3 | Distribution | 2016-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019149 | 407687131 | High Sign | HFTD Tier 3 | Distribution | 2016-03-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019150 | 407687665 | High Sign | HFTD Tier 2 | Distribution | 2016-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019151 | 407687775 | Guy | HFTD Tier 2 | Distribution | 2016-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019152 | 407687789 | Guy | HFTD Tier 2 | Distribution | 2016-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019153 | 407687827 | Insulator | HFTD Tier 2 | Distribution | 2016-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019154 | 407687839 | Guy Guard | HFTD Tier 3 | Distribution | 2016-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019155 | 407687857 | Insulator | HFTD Tier 2 | Distribution | 2016-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019156 | 407687880 | Guy Guard | HFTD Tier 3 | Distribution | 2016-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019157 | 407688515 | Molding | HFTD Tier 2 | Distribution | 2016-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019158 | 407688536 | Insulator | HFTD Tier 2 | Distribution | 2016-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019159 | 407688537 | Molding | HFTD Tier 2 | Distribution | 2016-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019160 | 407688571 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019161 | 407688613 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019162 | 407689937 | Vis Strips | HFTD Tier 3 | Distribution | 2016-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019163 | 407689963 | High Sign | HFTD Tier 2 | Distribution | 2016-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019164 | 407690396 | High Sign | HFTD Tier 2 | Distribution | 2016-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019165 | 407691133 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019166 | 407691171 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019167 | 407691901 | Guy Guard | HFTD Tier 3 | Distribution | 2016-03-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019168 | 407692555 | Molding | HFTD Tier 3 | Distribution | 2016-03-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019169 | 407693001 | Guy | HFTD Tier 2 | Distribution | 2016-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019170 | 407693041 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019171 | 407693186 | Guy | HFTD Tier 2 | Distribution | 2016-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019172 | 407693396 | High Sign | HFTD Tier 2 | Distribution | 2016-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019173 | 407693479 | High Sign | HFTD Tier 2 | Distribution | 2016-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019174 | 407694396 | High Sign | HFTD Tier 3 | Distribution | 2016-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019175 | 407694534 | High Sign | HFTD Tier 3 | Distribution | 2016-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019176 | 407694543 | Molding | HFTD Tier 3 | Distribution | 2016-03-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019177 | 407695616 | High Sign | HFTD Tier 2 | Distribution | 2016-03-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019178 | 407698065 | Molding | HFTD Tier 2 | Distribution | 2016-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019179 | 407698134 | High Sign | HFTD Tier 2 | Distribution | 2016-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019180 | 407698715 | High Sign | HFTD Tier 2 | Distribution | 2016-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019181 | 407698745 | Guy Guard | HFTD Tier 3 | Distribution | 2016-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019182 | 407699242 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019183 | 407700786 | High Sign | HFTD Tier 3 | Distribution | 2016-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019184 | 407700825 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019185 | 407700903 | High Sign | HFTD Tier 2 | Distribution | 2016-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019186 | 407701494 | Guy Guard | HFTD Tier 3 | Distribution | 2016-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019187 | 407701671 | Molding | HFTD Tier 2 | Distribution | 2016-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019188 | 407701682 | High Sign | HFTD Tier 2 | Distribution | 2016-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019189 | 407702882 | High Sign | HFTD Tier 3 | Distribution | 2016-03-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019190 | 407702889 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-03-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019191 | 407704135 | Molding | HFTD Tier 3 | Distribution | 2016-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019192 | 407704158 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-04-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019193 | 407706235 | High Sign | HFTD Tier 3 | Distribution | 2016-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019194 | 407706423 | Molding | HFTD Tier 2 | Distribution | 2016-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019195 | 407706430 | Molding | HFTD Tier 2 | Distribution | 2016-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019196 | 407706556 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019197 | 407706845 | High Sign | HFTD Tier 2 | Distribution | 2016-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019198 | 407706876 | Molding | HFTD Tier 2 | Distribution | 2016-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019199 | 407708803 | Anchor | HFTD Tier 3 | Distribution | 2016-04-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019200 | 407709371 | Molding | HFTD Tier 2 | Distribution | 2016-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019201 | 407709643 | Guy | HFTD Tier 3 | Distribution | 2016-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019202 | 407709673 | Molding | HFTD Tier 3 | Distribution | 2016-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019203 | 407709700 | Guy | HFTD Tier 2 | Distribution | 2016-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019204 | 407709712 | Insulator | HFTD Tier 2 | Distribution | 2016-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019205 | 407709721 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019206 | 407709726 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019207 | 407709735 | Molding | HFTD Tier 3 | Distribution | 2016-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019208 | 407709742 | Termination | HFTD Tier 2 | Distribution | 2016-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019209 | 407709761 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019210 | 407709795 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019211 | 407709959 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019212 | 407710034 | Insulator | HFTD Tier 2 | Distribution | 2016-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019213 | 407710091 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019214 | 407710195 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019215 | 407710378 | Guy | HFTD Tier 2 | Distribution | 2016-04-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019216 | 407712016 | Guy | HFTD Tier 2 | Distribution | 2016-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019217 | 407713119 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019218 | 407714410 | High Sign | HFTD Tier 2 | Distribution | 2016-04-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019219 | 407715265 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019220 | 407715439 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019221 | 407715450 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019222 | 407716187 | High Sign | HFTD Tier 3 | Distribution | 2016-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019223 | 407716226 | High Sign | HFTD Tier 3 | Distribution | 2016-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019224 | 407716402 | High Sign | HFTD Tier 2 | Distribution | 2016-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019225 | 407716408 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019226 | 407717702 | Guy | HFTD Tier 3 | Distribution | 2016-04-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019227 | 407718642 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-04-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019228 | 407718694 | High Sign | HFTD Tier 2 | Distribution | 2016-04-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019229 | 407719258 | Molding | HFTD Tier 2 | Distribution | 2016-04-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019230 | 407719732 | Guy | HFTD Tier 2 | Distribution | 2016-04-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019231 | 407722220 | Guy | HFTD Tier 3 | Distribution | 2016-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019232 | 407722482 | Riser/Conduit | HFTD Tier 2 | Distribution | 2016-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019233 | 407722514 | Guy Guard | HFTD Tier 3 | Distribution | 2016-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019234 | 407722534 | Molding | HFTD Tier 3 | Distribution | 2016-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019235 | 407722595 | High Sign | HFTD Tier 3 | Distribution | 2016-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019236 | 407722623 | High Sign | HFTD Tier 3 | Distribution | 2016-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019237 | 407722649 | High Sign | HFTD Tier 2 | Distribution | 2016-04-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019238 | 407724142 | Molding | HFTD Tier 3 | Distribution | 2016-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019239 | 407724368 | Pole step | HFTD Tier 2 | Distribution | 2016-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019240 | 407724675 | Guy | HFTD Tier 2 | Distribution | 2016-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019241 | 407724754 | Molding | HFTD Tier 2 | Distribution | 2016-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019242 | 407724898 | High Sign | HFTD Tier 2 | Distribution | 2016-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019243 | 407724953 | Molding | HFTD Tier 3 | Distribution | 2016-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019244 | 407725107 | Guy | HFTD Tier 3 | Distribution | 2016-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019245 | 407725221 | High Sign | HFTD Tier 2 | Distribution | 2016-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019246 | 407725306 | Guy | HFTD Tier 3 | Distribution | 2016-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019247 | 407725309 | Guy | HFTD Tier 3 | Distribution | 2016-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019248 | 407725502 | High Sign | HFTD Tier 3 | Distribution | 2016-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019249 | 407725503 | Molding | HFTD Tier 3 | Distribution | 2016-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019250 | 407725533 | Guy | HFTD Tier 3 | Distribution | 2016-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019251 | 407726717 | Pole step | HFTD Tier 3 | Distribution | 2016-04-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019252 | 407727869 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019253 | 407727942 | Guy | HFTD Tier 2 | Distribution | 2016-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019254 | 407728192 | Guy Guard | HFTD Tier 3 | Distribution | 2016-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019255 | 407728205 | Guy | HFTD Tier 3 | Distribution | 2016-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019256 | 407728325 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019257 | 407728330 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019258 | 407728377 | Guy | HFTD Tier 2 | Distribution | 2016-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019259 | 407728447 | Guy | HFTD Tier 3 | Distribution | 2016-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019260 | 407728531 | High Sign | HFTD Tier 3 | Distribution | 2016-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019261 | 407728532 | High Sign | HFTD Tier 3 | Distribution | 2016-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019262 | 407728733 | High Sign | HFTD Tier 3 | Distribution | 2016-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019263 | 407728735 | High Sign | HFTD Tier 3 | Distribution | 2016-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019264 | 407728799 | High Sign | HFTD Tier 3 | Distribution | 2016-04-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019265 | 407730071 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-04-13 | 1938-04-28 | 2 | Ignition Risk, no GO95 exception | [6 empty] | SCE | 2025 | 4
1130019266 | 407730927 | Guy | HFTD Tier 3 | Distribution | 2016-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019267 | 407730933 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019268 | 407731018 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019269 | 407731529 | Molding | HFTD Tier 2 | Distribution | 2016-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019270 | 407731867 | High Sign | HFTD Tier 3 | Distribution | 2016-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019271 | 407731968 | Molding | HFTD Tier 3 | Distribution | 2016-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019272 | 407731974 | Molding | HFTD Tier 3 | Distribution | 2016-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019273 | 407731985 | Molding | HFTD Tier 3 | Distribution | 2016-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019274 | 407732022 | High Sign | HFTD Tier 3 | Distribution | 2016-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019275 | 407732023 | Guy Guard | HFTD Tier 3 | Distribution | 2016-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019276 | 407732078 | Anchor | HFTD Tier 3 | Distribution | 2016-04-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019277 | 407734557 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019278 | 407734591 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019279 | 407734593 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-04-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019280 | 407737256 | Guy | HFTD Tier 2 | Distribution | 2016-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019281 | 407737274 | High Sign | HFTD Tier 2 | Distribution | 2016-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019282 | 407737998 | High Sign | HFTD Tier 3 | Distribution | 2016-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019283 | 407738211 | Guy | HFTD Tier 3 | Distribution | 2016-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019284 | 407738259 | High Sign | HFTD Tier 3 | Distribution | 2016-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019285 | 407738273 | High Sign | HFTD Tier 3 | Distribution | 2016-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019286 | 407739666 | High Sign | HFTD Tier 2 | Distribution | 2016-04-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019287 | 407740318 | Guy Guard | HFTD Tier 2 | Distribution | 2016-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019288 | 407740370 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019289 | 407740385 | Anchor | HFTD Tier 3 | Distribution | 2016-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019290 | 407740396 | High Sign | HFTD Tier 2 | Distribution | 2016-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019291 | 407740625 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019292 | 407740714 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019293 | 407740907 | High Sign | HFTD Tier 3 | Distribution | 2016-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019294 | 407741149 | High Sign | HFTD Tier 3 | Distribution | 2016-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019295 | 407742175 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019296 | 407742187 | High Sign | HFTD Tier 3 | Distribution | 2016-04-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019297 | 407743272 | High Sign | HFTD Tier 2 | Distribution | 2016-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019298 | 407743786 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019299 | 407743850 | Riser/Conduit | HFTD Tier 2 | Distribution | 2016-04-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019300 | 407745338 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019301 | 407746060 | Guy Guard | HFTD Tier 3 | Distribution | 2016-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019302 | 407749737 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019303 | 407749818 | High Sign | HFTD Tier 2 | Distribution | 2016-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019304 | 407750236 | High Sign | HFTD Tier 3 | Distribution | 2016-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019305 | 407750267 | Molding | HFTD Tier 3 | Distribution | 2016-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019306 | 407750284 | High Sign | HFTD Tier 3 | Distribution | 2016-04-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019307 | 407750677 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019308 | 407750860 | Riser/Conduit | HFTD Tier 2 | Distribution | 2016-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019309 | 407750884 | Guy | HFTD Tier 2 | Distribution | 2016-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019310 | 407753208 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-04-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019311 | 407753840 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019312 | 407754468 | High Sign | HFTD Tier 3 | Distribution | 2016-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019313 | 407754540 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019314 | 407756200 | Molding | HFTD Tier 3 | Distribution | 2016-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019315 | 407756238 | High Sign | HFTD Tier 3 | Distribution | 2016-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019316 | 407756641 | High Sign | HFTD Tier 3 | Distribution | 2016-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019317 | 407756673 | High Sign | HFTD Tier 3 | Distribution | 2016-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019318 | 407756674 | High Sign | HFTD Tier 3 | Distribution | 2016-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019319 | 407756691 | Riser/Conduit | HFTD Tier 3 | Distribution | 2016-04-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019320 | 407757013 | Guy Guard | HFTD Tier 2 | Distribution | 2016-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019321 | 407757169 | Guy Guard | HFTD Tier 3 | Distribution | 2016-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019322 | 407757824 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019323 | 407759322 | Molding | HFTD Tier 2 | Distribution | 2016-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019324 | 407759599 | Riser/Conduit | HFTD Tier 2 | Distribution | 2016-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019325 | 407759957 | Guy | HFTD Tier 3 | Distribution | 2016-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019326 | 407759965 | Molding | HFTD Tier 3 | Distribution | 2016-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019327 | 407759984 | Guy Guard | HFTD Tier 3 | Distribution | 2016-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019328 | 407760940 | High Sign | HFTD Tier 3 | Distribution | 2016-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019329 | 407761192 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019330 | 407761209 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019331 | 407761752 | Molding | HFTD Tier 3 | Distribution | 2016-04-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019332 | 407763304 | Guy | HFTD Tier 2 | Distribution | 2016-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019333 | 407763594 | High Sign | HFTD Tier 3 | Distribution | 2016-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019334 | 407763725 | Molding | HFTD Tier 2 | Distribution | 2016-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019335 | 407764218 | Guy Guard | HFTD Tier 2 | Distribution | 2016-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019336 | 407764257 | Insulator | HFTD Tier 2 | Distribution | 2016-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019337 | 407764352 | High Sign | HFTD Tier 2 | Distribution | 2016-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019338 | 407764366 | High Sign | HFTD Tier 2 | Distribution | 2016-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019339 | 407764371 | High Sign | HFTD Tier 2 | Distribution | 2016-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019340 | 407766641 | High Sign | HFTD Tier 2 | Distribution | 2016-04-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019341 | 407766935 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-04-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019342 | 407767373 | Molding | HFTD Tier 2 | Distribution | 2016-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019343 | 407767399 | High Sign | HFTD Tier 2 | Distribution | 2016-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019344 | 407767438 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019345 | 407768171 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-05-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019346 | 407769584 | Guy | HFTD Tier 3 | Distribution | 2016-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019347 | 407769620 | Bond | HFTD Tier 2 | Distribution | 2016-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019348 | 407769726 | High Sign | HFTD Tier 2 | Distribution | 2016-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019349 | 407769995 | Molding | HFTD Tier 2 | Distribution | 2016-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019350 | 407770647 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019351 | 407770694 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019352 | 407770785 | High Sign | HFTD Tier 3 | Distribution | 2016-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019353 | 407770786 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019354 | 407771245 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019355 | 407771433 | Molding | HFTD Tier 2 | Distribution | 2016-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019356 | 407771670 | Guy | HFTD Tier 2 | Distribution | 2016-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019357 | 407771933 | Insulator | HFTD Tier 2 | Distribution | 2016-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019358 | 407772036 | Guy | HFTD Tier 2 | Distribution | 2016-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019359 | 407772440 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019360 | 407772846 | Guy Guard | HFTD Tier 3 | Distribution | 2016-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019361 | 407772888 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019362 | 407773190 | Guy | HFTD Tier 2 | Distribution | 2016-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019363 | 407773492 | Molding | HFTD Tier 2 | Distribution | 2016-05-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019364 | 407777946 | High Sign | HFTD Tier 2 | Distribution | 2016-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019365 | 407777995 | High Sign | HFTD Tier 2 | Distribution | 2016-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019366 | 407778003 | High Sign | HFTD Tier 2 | Distribution | 2016-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019367 | 407778083 | High Sign | HFTD Tier 2 | Distribution | 2016-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019368 | 407778130 | High Sign | HFTD Tier 2 | Distribution | 2016-05-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019369 | 407779658 | Molding | HFTD Tier 2 | Distribution | 2016-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019370 | 407779663 | Termination | HFTD Tier 2 | Distribution | 2016-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019371 | 407779695 | Molding | HFTD Tier 2 | Distribution | 2016-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019372 | 407779701 | High Sign | HFTD Tier 2 | Distribution | 2016-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019373 | 407779702 | High Sign | HFTD Tier 2 | Distribution | 2016-04-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019374 | 407779728 | Molding | HFTD Tier 2 | Distribution | 2016-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019375 | 407779806 | High Sign | HFTD Tier 2 | Distribution | 2016-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019376 | 407779816 | High Sign | HFTD Tier 2 | Distribution | 2016-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019377 | 407779818 | High Sign | HFTD Tier 2 | Distribution | 2016-05-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019378 | 407779837 | High Sign | HFTD Tier 2 | Distribution | 2016-05-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019379 | 407779839 | High Sign | HFTD Tier 2 | Distribution | 2016-05-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019380 | 407779850 | High Sign | HFTD Tier 2 | Distribution | 2016-05-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019381 | 407779852 | High Sign | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019382 | 407779853 | High Sign | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019383 | 407779860 | High Sign | HFTD Tier 2 | Distribution | 2016-05-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019384 | 407779875 | High Sign | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019385 | 407779907 | High Sign | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019386 | 407779934 | High Sign | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019387 | 407779948 | High Sign | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019388 | 407779950 | High Sign | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019389 | 407779962 | High Sign | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019390 | 407780240 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019391 | 407780281 | High Sign | HFTD Tier 3 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019392 | 407780406 | High Sign | HFTD Tier 3 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019393 | 407780517 | High Sign | HFTD Tier 3 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019394 | 407780580 | Riser/Conduit | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019395 | 407780592 | Ground | HFTD Tier 3 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019396 | 407780757 | High Sign | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019397 | 407780766 | High Sign | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019398 | 407780785 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019399 | 407780786 | High Sign | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019400 | 407780792 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019401 | 407780805 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019402 | 407780823 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019403 | 407780824 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019404 | 407780833 | High Sign | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019405 | 407780873 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019406 | 407780894 | High Sign | HFTD Tier 3 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019407 | 407780907 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019408 | 407780914 | High Sign | HFTD Tier 3 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019409 | 407780959 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019410 | 407781005 | Guy | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019411 | 407781083 | Guy | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019412 | 407781090 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019413 | 407781095 | High Sign | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019414 | 407781930 | Guy | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019415 | 407782415 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019416 | 407782938 | Guy | HFTD Tier 3 | Distribution | 2016-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019417 | 407782981 | Guy | HFTD Tier 3 | Distribution | 2016-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019418 | 407783071 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019419 | 407783122 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019420 | 407783136 | Guy | HFTD Tier 2 | Distribution | 2016-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019421 | 407783638 | Guy | HFTD Tier 3 | Distribution | 2016-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019422 | 407783731 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019423 | 407783732 | Bond | HFTD Tier 3 | Distribution | 2016-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019424 | 407784032 | Molding | HFTD Tier 2 | Distribution | 2016-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019425 | 407784189 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019426 | 407784253 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019427 | 407784263 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019428 | 407784365 | Molding | HFTD Tier 3 | Distribution | 2016-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019429 | 407784394 | Guy Guard | HFTD Tier 3 | Distribution | 2016-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019430 | 407786081 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-05-10 | 1965-04-28 | 2 | Ignition Risk, no GO95 exception | [6 empty] | SCE | 2025 | 4
1130019431 | 407786188 | Molding | HFTD Tier 2 | Distribution | 2016-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019432 | 407786213 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019433 | 407786226 | High Sign | HFTD Tier 2 | Distribution | 2016-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019434 | 407786244 | High Sign | HFTD Tier 2 | Distribution | 2016-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019435 | 407786245 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019436 | 407786254 | Molding | HFTD Tier 2 | Distribution | 2016-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019437 | 407786271 | Guy | HFTD Tier 2 | Distribution | 2016-05-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019438 | 407786351 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019439 | 407786568 | Molding | HFTD Tier 3 | Distribution | 2016-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019440 | 407786647 | High Sign | HFTD Tier 3 | Distribution | 2016-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019441 | 407786702 | High Sign | HFTD Tier 3 | Distribution | 2016-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019442 | 407786797 | High Sign | HFTD Tier 3 | Distribution | 2016-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019443 | 407786823 | Molding | HFTD Tier 3 | Distribution | 2016-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019444 | 407787136 | Riser/Conduit | HFTD Tier 3 | Distribution | 2016-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019445 | 407787334 | Molding | HFTD Tier 3 | Distribution | 2016-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019446 | 407787496 | High Sign | HFTD Tier 3 | Distribution | 2016-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019447 | 407787511 | High Sign | HFTD Tier 3 | Distribution | 2016-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019448 | 407787517 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019449 | 407787534 | High Sign | HFTD Tier 3 | Distribution | 2016-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019450 | 407787952 | High Sign | HFTD Tier 2 | Distribution | 2016-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019451 | 407788154 | High Sign | HFTD Tier 2 | Distribution | 2016-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019452 | 407789295 | Molding | HFTD Tier 3 | Distribution | 2016-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019453 | 407789416 | High Sign | HFTD Tier 3 | Distribution | 2016-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019454 | 407789450 | Molding | HFTD Tier 3 | Distribution | 2016-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019455 | 407789970 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019456 | 407790160 | High Sign | HFTD Tier 3 | Distribution | 2016-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019457 | 407790289 | Vis Strips | HFTD Tier 2 | Distribution | 2016-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019458 | 407790293 | High Sign | HFTD Tier 3 | Distribution | 2016-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019459 | 407790294 | High Sign | HFTD Tier 2 | Distribution | 2016-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019460 | 407790304 | High Sign | HFTD Tier 2 | Distribution | 2016-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019461 | 407790331 | High Sign | HFTD Tier 3 | Distribution | 2016-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019462 | 407790343 | Vis Strips | HFTD Tier 2 | Distribution | 2016-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019463 | 407790450 | High Sign | HFTD Tier 2 | Distribution | 2016-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019464 | 407790504 | High Sign | HFTD Tier 3 | Distribution | 2016-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019465 | 407790567 | High Sign | HFTD Tier 2 | Distribution | 2016-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019466 | 407790581 | Vis Strips | HFTD Tier 3 | Distribution | 2016-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019467 | 407790754 | Molding | HFTD Tier 3 | Distribution | 2016-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019468 | 407790782 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019469 | 407790853 | Molding | HFTD Tier 3 | Distribution | 2016-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019470 | 407792019 | High Sign | HFTD Tier 2 | Distribution | 2016-05-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019471 | 407792114 | High Sign | HFTD Tier 2 | Distribution | 2016-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019472 | 407792132 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019473 | 407792144 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019474 | 407792230 | Molding | HFTD Tier 2 | Distribution | 2016-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019475 | 407792239 | High Sign | HFTD Tier 3 | Distribution | 2016-05-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019476 | 407796020 | High Sign | HFTD Tier 2 | Distribution | 2016-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019477 | 407796472 | Molding | HFTD Tier 3 | Distribution | 2016-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019478 | 407797071 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019479 | 407797079 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019480 | 407797157 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019481 | 407797217 | High Sign | HFTD Tier 2 | Distribution | 2016-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019482 | 407797311 | High Sign | HFTD Tier 2 | Distribution | 2016-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019483 | 407799001 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019484 | 407799606 | High Sign | HFTD Tier 3 | Distribution | 2016-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019485 | 407799614 | High Sign | HFTD Tier 3 | Distribution | 2016-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019486 | 407800203 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019487 | 407800254 | Pole step | HFTD Tier 3 | Distribution | 2016-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019488 | 407800294 | Molding | HFTD Tier 3 | Distribution | 2016-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019489 | 407800350 | High Sign | HFTD Tier 3 | Distribution | 2016-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019490 | 407800393 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019491 | 407800608 | Guy | HFTD Tier 2 | Distribution | 2016-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019492 | 407800763 | Molding | HFTD Tier 3 | Distribution | 2016-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019493 | 407800833 | High Sign | HFTD Tier 3 | Distribution | 2016-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019494 | 407800840 | Pole step | HFTD Tier 3 | Distribution | 2016-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019495 | 407800964 | High Sign | HFTD Tier 2 | Distribution | 2016-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019496 | 407801059 | Pole step | HFTD Tier 3 | Distribution | 2016-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019497 | 407801114 | Pole step | HFTD Tier 3 | Distribution | 2016-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019498 | 407801156 | High Sign | HFTD Tier 3 | Distribution | 2016-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019499 | 407801301 | High Sign | HFTD Tier 3 | Distribution | 2016-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019500 | 407802084 | Molding | HFTD Tier 2 | Distribution | 2016-05-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019501 | 407802120 | High Sign | HFTD Tier 2 | Distribution | 2016-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019502 | 407802121 | Molding | HFTD Tier 2 | Distribution | 2016-05-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019503 | 407802891 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019504 | 407802899 | High Sign | HFTD Tier 3 | Distribution | 2016-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019505 | 407803149 | Guy | HFTD Tier 2 | Distribution | 2016-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019506 | 407804854 | High Sign | HFTD Tier 3 | Distribution | 2016-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019507 | 407804959 | Molding | HFTD Tier 3 | Distribution | 2016-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019508 | 407805007 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019509 | 407805011 | High Sign | HFTD Tier 3 | Distribution | 2016-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019510 | 407805311 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019511 | 407805695 | Molding | HFTD Tier 3 | Distribution | 2016-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019512 | 407805735 | High Sign | HFTD Tier 3 | Distribution | 2016-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019513 | 407805924 | Molding | HFTD Tier 3 | Distribution | 2016-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019514 | 407805930 | Guy Guard | HFTD Tier 3 | Distribution | 2016-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019515 | 407805963 | Riser/Conduit | HFTD Tier 3 | Distribution | 2016-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019516 | 407806296 | High Sign | HFTD Tier 3 | Distribution | 2016-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019517 | 407806840 | High Sign | HFTD Tier 2 | Distribution | 2016-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019518 | 407807239 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019519 | 407808132 | Molding | HFTD Tier 2 | Distribution | 2016-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019520 | 407808160 | Molding | HFTD Tier 2 | Distribution | 2016-05-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019521 | 407808205 | High Sign | HFTD Tier 3 | Distribution | 2016-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019522 | 407808231 | Guy | HFTD Tier 2 | Distribution | 2016-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019523 | 407808295 | Molding | HFTD Tier 3 | Distribution | 2016-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019524 | 407808350 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019525 | 407808363 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019526 | 407809068 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-05-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019527 | 407809419 | High Sign | HFTD Tier 3 | Distribution | 2016-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019528 | 407809495 | High Sign | HFTD Tier 3 | Distribution | 2016-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019529 | 407809533 | High Sign | HFTD Tier 3 | Distribution | 2016-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019530 | 407809534 | Guy | HFTD Tier 3 | Distribution | 2016-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019531 | 407809541 | High Sign | HFTD Tier 3 | Distribution | 2016-05-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019532 | 407811383 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019533 | 407811837 | High Sign | HFTD Tier 2 | Distribution | 2016-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019534 | 407812958 | Guy | HFTD Tier 3 | Distribution | 2016-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019535 | 407816014 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019536 | 407816326 | Molding | HFTD Tier 2 | Distribution | 2016-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019537 | 407816437 | High Sign | HFTD Tier 2 | Distribution | 2016-05-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019538 | 407816442 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019539 | 407816460 | High Sign | HFTD Tier 2 | Distribution | 2016-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019540 | 407816536 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019541 | 407816549 | Molding | HFTD Tier 3 | Distribution | 2016-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019542 | 407816586 | Bond | HFTD Tier 3 | Distribution | 2016-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019543 | 407816592 | Riser/Conduit | HFTD Tier 3 | Distribution | 2016-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019544 | 407816594 | Molding | HFTD Tier 3 | Distribution | 2016-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019545 | 407816597 | Molding | HFTD Tier 3 | Distribution | 2016-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019546 | 407816602 | Bond | HFTD Tier 3 | Distribution | 2016-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019547 | 407817117 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-05-24 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019548 | 407817388 | High Sign | HFTD Tier 3 | Distribution | 2016-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019549 | 407817439 | High Sign | HFTD Tier 3 | Distribution | 2016-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019550 | 407817528 | Molding | HFTD Tier 3 | Distribution | 2016-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019551 | 407817537 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019552 | 407817608 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019553 | 407817611 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019554 | 407817853 | Insulator | HFTD Tier 2 | Distribution | 2016-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019555 | 407817949 | Molding | HFTD Tier 3 | Distribution | 2016-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019556 | 407817957 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019557 | 407818104 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019558 | 407818142 | Molding | HFTD Tier 2 | Distribution | 2016-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019559 | 407818317 | High Sign | HFTD Tier 2 | Distribution | 2016-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019560 | 407820189 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019561 | 407820304 | Riser/Conduit | HFTD Tier 2 | Distribution | 2016-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019562 | 407820340 | Molding | HFTD Tier 2 | Distribution | 2016-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019563 | 407820363 | Riser/Conduit | HFTD Tier 2 | Distribution | 2016-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019564 | 407820366 | Pole step | HFTD Tier 2 | Distribution | 2016-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019565 | 407820390 | High Sign | HFTD Tier 2 | Distribution | 2016-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019566 | 407820588 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-05-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019567 | 407824195 | Guy | HFTD Tier 3 | Distribution | 2016-05-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019568 | 407825576 | Guy | HFTD Tier 2 | Distribution | 2016-05-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019569 | 407826428 | Guy | HFTD Tier 3 | Distribution | 2016-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019570 | 407826664 | High Sign | HFTD Tier 3 | Distribution | 2016-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019571 | 407826675 | Guy | HFTD Tier 3 | Distribution | 2016-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019572 | 407827081 | Molding | HFTD Tier 3 | Distribution | 2016-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019573 | 407827194 | High Sign | HFTD Tier 2 | Distribution | 2016-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019574 | 407827382 | High Sign | HFTD Tier 3 | Distribution | 2016-05-31 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019575 | 407828681 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019576 | 407829095 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019577 | 407829660 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019578 | 407830556 | Molding | HFTD Tier 2 | Distribution | 2016-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019579 | 407830864 | Guy | HFTD Tier 3 | Distribution | 2016-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019580 | 407831463 | Guy | HFTD Tier 3 | Distribution | 2016-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019581 | 407831470 | Guy | HFTD Tier 3 | Distribution | 2016-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019582 | 407831471 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019583 | 407831491 | Guy | HFTD Tier 2 | Distribution | 2016-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019584 | 407831691 | High Sign | HFTD Tier 3 | Distribution | 2016-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019585 | 407831958 | Structure/Equip Itself | HFTD Tier 2 | Transmission | 2016-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019586 | 407831961 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019587 | 407831987 | Structure/Equip Itself | HFTD Tier 2 | Transmission | 2016-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019588 | 407831995 | Structure/Equip Itself | HFTD Tier 2 | Transmission | 2016-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019589 | 407832010 | Structure/Equip Itself | HFTD Tier 2 | Transmission | 2016-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019590 | 407832011 | Structure/Equip Itself | HFTD Tier 2 | Transmission | 2016-06-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019591 | 407832969 | Guy | HFTD Tier 3 | Distribution | 2016-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019592 | 407833593 | High Sign | HFTD Tier 3 | Distribution | 2016-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019593 | 407833650 | Molding | HFTD Tier 3 | Distribution | 2016-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019594 | 407835019 | Molding | HFTD Tier 2 | Distribution | 2016-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019595 | 407835115 | High Sign | HFTD Tier 3 | Distribution | 2016-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019596 | 407835401 | Molding | HFTD Tier 2 | Distribution | 2016-06-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019597 | 407838579 | Molding | HFTD Tier 2 | Distribution | 2016-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019598 | 407838597 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019599 | 407838637 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019600 | 407838731 | Molding | HFTD Tier 2 | Distribution | 2016-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019601 | 407838763 | High Sign | HFTD Tier 2 | Distribution | 2016-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019602 | 407838770 | Molding | HFTD Tier 2 | Distribution | 2016-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019603 | 407838786 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019604 | 407838805 | Molding | HFTD Tier 2 | Distribution | 2016-06-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019605 | 407839700 | Molding | HFTD Tier 2 | Distribution | 2016-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019606 | 407839782 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019607 | 407839914 | High Sign | HFTD Tier 3 | Distribution | 2016-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019608 | 407839924 | Bond | HFTD Tier 3 | Distribution | 2016-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019609 | 407839932 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019610 | 407839979 | High Sign | HFTD Tier 2 | Distribution | 2016-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019611 | 407841334 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019612 | 407841444 | Riser/Conduit | HFTD Tier 2 | Distribution | 2016-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019613 | 407841452 | Pole step | HFTD Tier 2 | Distribution | 2016-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019614 | 407842057 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019615 | 407842073 | Molding | HFTD Tier 2 | Distribution | 2016-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019616 | 407842437 | High Sign | HFTD Tier 2 | Distribution | 2016-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019617 | 407842467 | Guy | HFTD Tier 2 | Distribution | 2016-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019618 | 407842485 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019619 | 407842497 | Molding | HFTD Tier 2 | Distribution | 2016-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019620 | 407842835 | Molding | HFTD Tier 3 | Distribution | 2016-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019621 | 407842837 | Insulator | HFTD Tier 2 | Distribution | 2016-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019622 | 407842888 | Molding | HFTD Tier 3 | Distribution | 2016-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019623 | 407842889 | Molding | HFTD Tier 3 | Distribution | 2016-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019624 | 407842922 | High Sign | HFTD Tier 3 | Distribution | 2016-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019625 | 407842941 | Pole step | HFTD Tier 2 | Distribution | 2016-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019626 | 407842950 | High Sign | HFTD Tier 3 | Distribution | 2016-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019627 | 407845367 | High Sign | HFTD Tier 2 | Distribution | 2016-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019628 | 407845398 | High Sign | HFTD Tier 2 | Distribution | 2016-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019629 | 407845433 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019630 | 407845453 | High Sign | HFTD Tier 2 | Distribution | 2016-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019631 | 407845454 | High Sign | HFTD Tier 2 | Distribution | 2016-06-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019632 | 407845581 | High Sign | HFTD Tier 3 | Distribution | 2016-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019633 | 407845807 | Ground | HFTD Tier 3 | Distribution | 2016-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019634 | 407845923 | High Sign | HFTD Tier 3 | Distribution | 2016-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019635 | 407845960 | High Sign | HFTD Tier 3 | Distribution | 2016-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019636 | 407846419 | Guy | HFTD Tier 2 | Distribution | 2016-06-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019637 | 407846439 | High Sign | HFTD Tier 3 | Distribution | 2016-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019638 | 407846444 | High Sign | HFTD Tier 3 | Distribution | 2016-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019639 | 407846514 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019640 | 407848345 | Guy Guard | HFTD Tier 2 | Distribution | 2016-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019641 | 407848411 | High Sign | HFTD Tier 2 | Distribution | 2016-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019642 | 407849145 | Molding | HFTD Tier 2 | Distribution | 2016-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019643 | 407849152 | Molding | HFTD Tier 2 | Distribution | 2016-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019644 | 407849154 | High Sign | HFTD Tier 2 | Distribution | 2016-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019645 | 407849155 | Termination | HFTD Tier 2 | Distribution | 2016-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019646 | 407849166 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019647 | 407849171 | Molding | HFTD Tier 2 | Distribution | 2016-06-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019648 | 407849406 | Molding | HFTD Tier 2 | Distribution | 2016-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019649 | 407849488 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019650 | 407849667 | ID Markings | HFTD Tier 3 | Distribution | 2016-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019651 | 407849696 | High Sign | HFTD Tier 3 | Distribution | 2016-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019652 | 407849718 | High Sign | HFTD Tier 3 | Distribution | 2016-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019653 | 407849719 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019654 | 407850722 | Molding | HFTD Tier 2 | Distribution | 2016-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019655 | 407850823 | High Sign | HFTD Tier 2 | Distribution | 2016-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019656 | 407850967 | Vis Strips | HFTD Tier 2 | Distribution | 2016-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019657 | 407851005 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019658 | 407851123 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019659 | 407851191 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019660 | 407851304 | Molding | HFTD Tier 3 | Distribution | 2016-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019661 | 407852311 | Guy | HFTD Tier 3 | Distribution | 2016-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019662 | 407852317 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019663 | 407852355 | Molding | HFTD Tier 2 | Distribution | 2016-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019664 | 407852402 | High Sign | HFTD Tier 2 | Distribution | 2016-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019665 | 407853335 | High Sign | HFTD Tier 2 | Distribution | 2016-06-09 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019666 | 407853663 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019667 | 407853987 | High Sign | HFTD Tier 3 | Distribution | 2016-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019668 | 407853989 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-06-10 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019669 | 407854845 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019670 | 407855556 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019671 | 407855587 | High Sign | HFTD Tier 2 | Distribution | 2016-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019672 | 407855743 | Molding | HFTD Tier 2 | Distribution | 2016-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019673 | 407855844 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019674 | 407856087 | High Sign | HFTD Tier 2 | Distribution | 2016-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019675 | 407857385 | High Sign | HFTD Tier 2 | Distribution | 2016-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019676 | 407857395 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019677 | 407858203 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019678 | 407859832 | Molding | HFTD Tier 3 | Distribution | 2016-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019679 | 407860002 | High Sign | HFTD Tier 3 | Distribution | 2016-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019680 | 407860201 | Guy Guard | HFTD Tier 3 | Distribution | 2016-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019681 | 407860203 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019682 | 407860290 | Guy | HFTD Tier 3 | Distribution | 2016-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019683 | 407860315 | Guy | HFTD Tier 3 | Distribution | 2016-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019684 | 407860382 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019685 | 407860392 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019686 | 407860416 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019687 | 407860438 | High Sign | HFTD Tier 2 | Distribution | 2016-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019688 | 407860451 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019689 | 407860796 | Termination | HFTD Tier 2 | Distribution | 2016-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019690 | 407860818 | Molding | HFTD Tier 2 | Distribution | 2016-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019691 | 407860898 | Molding | HFTD Tier 2 | Distribution | 2016-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019692 | 407860926 | High Sign | HFTD Tier 3 | Distribution | 2016-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019693 | 407860939 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019694 | 407860953 | High Sign | HFTD Tier 2 | Distribution | 2016-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019695 | 407860989 | High Sign | HFTD Tier 3 | Distribution | 2016-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019696 | 407861074 | High Sign | HFTD Tier 3 | Distribution | 2016-06-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019697 | 407861697 | Guy | HFTD Tier 3 | Distribution | 2016-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019698 | 407861847 | Molding | HFTD Tier 2 | Distribution | 2016-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019699 | 407861879 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019700 | 407861953 | Guy Guard | HFTD Tier 3 | Distribution | 2016-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019701 | 407862297 | Guy | HFTD Tier 2 | Distribution | 2016-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019702 | 407862387 | High Sign | HFTD Tier 3 | Distribution | 2016-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019703 | 407863643 | High Sign | HFTD Tier 2 | Distribution | 2016-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019704 | 407863871 | Guy Guard | HFTD Tier 3 | Distribution | 2016-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019705 | 407863897 | High Sign | HFTD Tier 2 | Distribution | 2016-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019706 | 407863898 | High Sign | HFTD Tier 2 | Distribution | 2016-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019707 | 407863899 | High Sign | HFTD Tier 2 | Distribution | 2016-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019708 | 407863900 | High Sign | HFTD Tier 2 | Distribution | 2016-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019709 | 407864811 | High Sign | HFTD Tier 3 | Distribution | 2016-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019710 | 407864820 | High Sign | HFTD Tier 3 | Distribution | 2016-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019711 | 407864850 | High Sign | HFTD Tier 3 | Distribution | 2016-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019712 | 407865043 | High Sign | HFTD Tier 3 | Distribution | 2016-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019713 | 407865275 | High Sign | HFTD Tier 3 | Distribution | 2016-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019714 | 407865339 | Guy | HFTD Tier 2 | Distribution | 2016-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019715 | 407865381 | Guy Guard | HFTD Tier 2 | Distribution | 2016-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019716 | 407865412 | Guy Guard | HFTD Tier 2 | Distribution | 2016-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019717 | 407865420 | Guy | HFTD Tier 2 | Distribution | 2016-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019718 | 407865513 | High Sign | HFTD Tier 3 | Distribution | 2016-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019719 | 407865563 | High Sign | HFTD Tier 3 | Distribution | 2016-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019720 | 407865612 | Molding | HFTD Tier 3 | Distribution | 2016-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019721 | 407865722 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019722 | 407865746 | High Sign | HFTD Tier 3 | Distribution | 2016-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019723 | 407865765 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019724 | 407865875 | Guy | HFTD Tier 2 | Distribution | 2016-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019725 | 407866270 | High Sign | HFTD Tier 3 | Distribution | 2016-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019726 | 407866299 | High Sign | HFTD Tier 3 | Distribution | 2016-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019727 | 407866547 | High Sign | HFTD Tier 3 | Distribution | 2016-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019728 | 407866694 | High Sign | HFTD Tier 3 | Distribution | 2016-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019729 | 407866874 | Molding | HFTD Tier 3 | Distribution | 2016-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019730 | 407867288 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-16 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019731 | 407867306 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019732 | 407867645 | High Sign | HFTD Tier 3 | Distribution | 2016-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019733 | 407867704 | High Sign | HFTD Tier 3 | Distribution | 2016-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019734 | 407868557 | Molding | HFTD Tier 2 | Distribution | 2016-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019735 | 407868576 | High Sign | HFTD Tier 2 | Distribution | 2016-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019736 | 407868663 | High Sign | HFTD Tier 2 | Distribution | 2016-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019737 | 407868732 | High Sign | HFTD Tier 2 | Distribution | 2016-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019738 | 407868764 | High Sign | HFTD Tier 2 | Distribution | 2016-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019739 | 407868790 | High Sign | HFTD Tier 2 | Distribution | 2016-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019740 | 407868791 | High Sign | HFTD Tier 2 | Distribution | 2016-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019741 | 407869415 | Guy Guard | HFTD Tier 3 | Distribution | 2016-06-17 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019742 | 407870209 | Molding | HFTD Tier 2 | Distribution | 2016-06-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019743 | 407871135 | Guy | HFTD Tier 3 | Distribution | 2016-06-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019744 | 407871221 | Vis Strips | HFTD Tier 2 | Distribution | 2016-06-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019745 | 407871500 | Molding | HFTD Tier 3 | Distribution | 2016-06-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019746 | 407871893 | Guy Guard | HFTD Tier 2 | Distribution | 2016-06-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019747 | 407872034 | High Sign | HFTD Tier 2 | Distribution | 2016-06-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019748 | 407872035 | Guy Guard | HFTD Tier 3 | Distribution | 2016-06-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019749 | 407872043 | Pole step | HFTD Tier 2 | Distribution | 2016-06-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019750 | 407872117 | High Sign | HFTD Tier 3 | Distribution | 2016-06-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019751 | 407872229 | High Sign | HFTD Tier 2 | Distribution | 2016-06-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019752 | 407872268 | Guy | HFTD Tier 2 | Distribution | 2016-06-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019753 | 407872313 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019754 | 407873370 | High Sign | HFTD Tier 3 | Distribution | 2016-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019755 | 407873535 | Guy | HFTD Tier 3 | Distribution | 2016-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019756 | 407873614 | High Sign | HFTD Tier 3 | Distribution | 2016-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019757 | 407874065 | Molding | HFTD Tier 3 | Distribution | 2016-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019758 | 407874067 | Molding | HFTD Tier 3 | Distribution | 2016-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019759 | 407874165 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019760 | 407874169 | Molding | HFTD Tier 3 | Distribution | 2016-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019761 | 407874481 | Molding | HFTD Tier 3 | Distribution | 2016-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019762 | 407874644 | Guy Guard | HFTD Tier 3 | Distribution | 2016-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019763 | 407874658 | High Sign | HFTD Tier 3 | Distribution | 2016-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019764 | 407874687 | High Sign | HFTD Tier 3 | Distribution | 2016-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019765 | 407874848 | High Sign | HFTD Tier 2 | Distribution | 2016-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019766 | 407874894 | High Sign | HFTD Tier 2 | Distribution | 2016-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019767 | 407874915 | High Sign | HFTD Tier 2 | Distribution | 2016-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019768 | 407874980 | Guy Guard | HFTD Tier 3 | Distribution | 2016-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019769 | 407875078 | Guy | HFTD Tier 3 | Distribution | 2016-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019770 | 407875079 | Guy | HFTD Tier 3 | Distribution | 2016-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019771 | 407875109 | Guy | HFTD Tier 3 | Distribution | 2016-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019772 | 407875213 | Molding | HFTD Tier 3 | Distribution | 2016-06-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019773 | 407876332 | High Sign | HFTD Tier 3 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019774 | 407876334 | Guy | HFTD Tier 3 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019775 | 407876350 | Molding | HFTD Tier 3 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019776 | 407876371 | High Sign | HFTD Tier 3 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019777 | 407876383 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019778 | 407876470 | Riser/Conduit | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019779 | 407876682 | Guy | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019780 | 407876936 | Riser/Conduit | HFTD Tier 3 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019781 | 407877753 | Guy | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019782 | 407877884 | Guy Guard | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019783 | 407877923 | Guy Guard | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019784 | 407877946 | Guy Guard | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019785 | 407877947 | Guy | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019786 | 407877954 | Guy Guard | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019787 | 407877955 | Guy Guard | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019788 | 407877983 | Guy Guard | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019789 | 407877990 | Guy Guard | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019790 | 407877992 | Guy | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019791 | 407878000 | Guy | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019792 | 407878002 | Guy Guard | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019793 | 407878007 | Guy Guard | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019794 | 407878011 | Guy Guard | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019795 | 407878013 | Guy Guard | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019796 | 407878034 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019797 | 407878246 | Molding | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019798 | 407878368 | High Sign | HFTD Tier 3 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019799 | 407879009 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019800 | 407880026 | High Sign | HFTD Tier 3 | Distribution | 2016-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019801 | 407881030 | Guy | HFTD Tier 2 | Distribution | 2016-06-23 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019802 | 407881955 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019803 | 407881957 | Molding | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019804 | 407882004 | Molding | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019805 | 407882012 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019806 | 407882031 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019807 | 407882831 | High Sign | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019808 | 407884693 | Molding | HFTD Tier 2 | Distribution | 2016-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019809 | 407884702 | High Sign | HFTD Tier 2 | Distribution | 2016-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019810 | 407885938 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019811 | 407885991 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019812 | 407886033 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-06-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019813 | 407886036 | Guy | HFTD Tier 2 | Distribution | 2016-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019814 | 407886051 | Guy | HFTD Tier 2 | Distribution | 2016-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019815 | 407886077 | High Sign | HFTD Tier 2 | Distribution | 2016-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019816 | 407886175 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-06-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019817 | 407886515 | High Sign | HFTD Tier 3 | Distribution | 2016-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019818 | 407886640 | Guy | HFTD Tier 2 | Distribution | 2016-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019819 | 407886867 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019820 | 407886981 | Guy | HFTD Tier 3 | Distribution | 2016-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019821 | 407887175 | Guy Guard | HFTD Tier 3 | Distribution | 2016-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019822 | 407888262 | Guy Guard | HFTD Tier 3 | Distribution | 2016-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019823 | 407888286 | Riser/Conduit | HFTD Tier 3 | Distribution | 2016-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019824 | 407888489 | High Sign | HFTD Tier 3 | Distribution | 2016-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019825 | 407888616 | High Sign | HFTD Tier 3 | Distribution | 2016-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019826 | 407888617 | Molding | HFTD Tier 3 | Distribution | 2016-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019827 | 407888637 | Molding | HFTD Tier 3 | Distribution | 2016-06-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019828 | 407889299 | Termination | HFTD Tier 2 | Distribution | 2016-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019829 | 407889307 | Termination | HFTD Tier 2 | Distribution | 2016-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019830 | 407889503 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019831 | 407889715 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019832 | 407889744 | Molding | HFTD Tier 2 | Distribution | 2016-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019833 | 407890138 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019834 | 407890257 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019835 | 407890477 | Molding | HFTD Tier 3 | Distribution | 2016-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019836 | 407890507 | High Sign | HFTD Tier 3 | Distribution | 2016-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019837 | 407890534 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019838 | 407890646 | Molding | HFTD Tier 3 | Distribution | 2016-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019839 | 407892169 | High Sign | HFTD Tier 3 | Distribution | 2016-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019840 | 407892234 | High Sign | HFTD Tier 3 | Distribution | 2016-06-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019841 | 407893984 | Termination | HFTD Tier 2 | Distribution | 2016-06-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019842 | 407894063 | High Sign | HFTD Tier 2 | Distribution | 2016-06-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019843 | 407894072 | High Sign | HFTD Tier 2 | Distribution | 2016-06-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019844 | 407894341 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-06-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019845 | 407894348 | High Sign | HFTD Tier 3 | Distribution | 2016-06-29 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019846 | 407895292 | Molding | HFTD Tier 2 | Distribution | 2016-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019847 | 407895490 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019848 | 407895609 | Molding | HFTD Tier 2 | Distribution | 2016-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019849 | 407895626 | Ground | HFTD Tier 2 | Distribution | 2016-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019850 | 407895763 | Guy | HFTD Tier 3 | Distribution | 2016-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019851 | 407895866 | Guy | HFTD Tier 3 | Distribution | 2016-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019852 | 407895887 | Guy Guard | HFTD Tier 2 | Distribution | 2016-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019853 | 407896371 | High Sign | HFTD Tier 2 | Distribution | 2016-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019854 | 407897190 | High Sign | HFTD Tier 3 | Distribution | 2016-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019855 | 407897958 | High Sign | HFTD Tier 3 | Distribution | 2016-06-30 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019856 | 407898400 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-07-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019857 | 407903293 | Riser/Conduit | HFTD Tier 2 | Distribution | 2016-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019858 | 407903417 | Riser/Conduit | HFTD Tier 2 | Distribution | 2016-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019859 | 407903422 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019860 | 407904305 | Insulator | HFTD Tier 2 | Distribution | 2016-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019861 | 407904383 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019862 | 407904413 | High Sign | HFTD Tier 2 | Distribution | 2016-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019863 | 407904417 | Pole step | HFTD Tier 3 | Distribution | 2016-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019864 | 407904426 | High Sign | HFTD Tier 3 | Distribution | 2016-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019865 | 407904451 | Molding | HFTD Tier 3 | Distribution | 2016-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019866 | 407904498 | High Sign | HFTD Tier 3 | Distribution | 2016-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019867 | 407904686 | High Sign | HFTD Tier 3 | Distribution | 2016-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019868 | 407904744 | Guy | HFTD Tier 2 | Distribution | 2016-07-06 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019869 | 407907317 | Molding | HFTD Tier 2 | Distribution | 2016-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019870 | 407907451 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019871 | 407907759 | High Sign | HFTD Tier 3 | Distribution | 2016-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019872 | 407907788 | Molding | HFTD Tier 3 | Distribution | 2016-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019873 | 407907841 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019874 | 407907865 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019875 | 407907876 | High Sign | HFTD Tier 3 | Distribution | 2016-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019876 | 407907898 | Guy Guard | HFTD Tier 3 | Distribution | 2016-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019877 | 407907921 | High Sign | HFTD Tier 3 | Distribution | 2016-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019878 | 407908122 | Riser/Conduit | HFTD Tier 2 | Distribution | 2016-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019879 | 407908131 | Guy | HFTD Tier 2 | Distribution | 2016-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019880 | 407908146 | Molding | HFTD Tier 2 | Distribution | 2016-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019881 | 407909829 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019882 | 407909943 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019883 | 407910020 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019884 | 407910230 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019885 | 407910244 | High Sign | HFTD Tier 2 | Distribution | 2016-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019886 | 407910261 | Guy | HFTD Tier 2 | Distribution | 2016-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019887 | 407910599 | High Sign | HFTD Tier 3 | Distribution | 2016-07-07 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019888 | 407910737 | Guy | HFTD Tier 2 | Distribution | 2016-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019889 | 407910825 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019890 | 407910881 | Pole step | HFTD Tier 2 | Distribution | 2016-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019891 | 407911398 | Guy | HFTD Tier 3 | Distribution | 2016-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019892 | 407911471 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-07-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019893 | 407913449 | Insulator | HFTD Tier 2 | Distribution | 2016-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019894 | 407913518 | Molding | HFTD Tier 2 | Distribution | 2016-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019895 | 407913550 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019896 | 407913553 | Molding | HFTD Tier 2 | Distribution | 2016-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019897 | 407913582 | Pole step | HFTD Tier 2 | Distribution | 2016-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019898 | 407913640 | High Sign | HFTD Tier 2 | Distribution | 2016-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019899 | 407913797 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019900 | 407914429 | Pole step | HFTD Tier 3 | Distribution | 2016-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019901 | 407914567 | Pole step | HFTD Tier 3 | Distribution | 2016-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019902 | 407914589 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019903 | 407914591 | High Sign | HFTD Tier 3 | Distribution | 2016-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019904 | 407914600 | High Sign | HFTD Tier 3 | Distribution | 2016-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019905 | 407915616 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019906 | 407915623 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-07-11 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019907 | 407916609 | High Sign | HFTD Tier 3 | Distribution | 2016-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019908 | 407916630 | Guy | HFTD Tier 3 | Distribution | 2016-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019909 | 407916815 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019910 | 407916912 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019911 | 407917023 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019912 | 407917059 | Riser/Conduit | HFTD Tier 2 | Distribution | 2016-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019913 | 407917234 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019914 | 407917335 | High Sign | HFTD Tier 3 | Distribution | 2016-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019915 | 407917398 | Pole step | HFTD Tier 3 | Distribution | 2016-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019916 | 407917417 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019917 | 407917427 | Insulator | HFTD Tier 3 | Distribution | 2016-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019918 | 407917433 | Pole step | HFTD Tier 3 | Distribution | 2016-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019919 | 407917896 | High Sign | HFTD Tier 2 | Distribution | 2016-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019920 | 407918059 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019921 | 407918160 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019922 | 407918243 | Molding | HFTD Tier 2 | Distribution | 2016-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019923 | 407918434 | High Sign | HFTD Tier 3 | Distribution | 2016-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019924 | 407918555 | Molding | HFTD Tier 2 | Distribution | 2016-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019925 | 407918566 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019926 | 407918887 | Guy | HFTD Tier 3 | Distribution | 2016-07-12 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019927 | 407920816 | High Sign | HFTD Tier 3 | Distribution | 2016-07-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019928 | 407921945 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-07-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019929 | 407922086 | Molding | HFTD Tier 2 | Distribution | 2016-07-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019930 | 407922137 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-07-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019931 | 407922552 | High Sign | HFTD Tier 3 | Distribution | 2016-07-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019932 | 407922581 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-07-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019933 | 407923458 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-07-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019934 | 407923781 | Guy | HFTD Tier 2 | Distribution | 2016-07-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019935 | 407924066 | Guy | HFTD Tier 2 | Distribution | 2016-07-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019936 | 407924096 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-07-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019937 | 407924122 | Insulator | HFTD Tier 2 | Distribution | 2016-07-13 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019938 | 407924269 | High Sign | HFTD Tier 3 | Distribution | 2016-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019939 | 407924295 | High Sign | HFTD Tier 3 | Distribution | 2016-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019940 | 407924305 | High Sign | HFTD Tier 3 | Distribution | 2016-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019941 | 407924308 | Insulator | HFTD Tier 2 | Distribution | 2016-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019942 | 407924309 | High Sign | HFTD Tier 2 | Distribution | 2016-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019943 | 407924331 | Molding | HFTD Tier 3 | Distribution | 2016-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019944 | 407924368 | Guy Guard | HFTD Tier 3 | Distribution | 2016-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019945 | 407924587 | Pole step | HFTD Tier 2 | Distribution | 2016-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019946 | 407924637 | Molding | HFTD Tier 3 | Distribution | 2016-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019947 | 407924939 | Termination | HFTD Tier 2 | Distribution | 2016-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019948 | 407925002 | High Sign | HFTD Tier 2 | Distribution | 2016-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019949 | 407925688 | High Sign | HFTD Tier 2 | Distribution | 2016-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019950 | 407925761 | Guy | HFTD Tier 2 | Distribution | 2016-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019951 | 407925821 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019952 | 407925959 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019953 | 407926123 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019954 | 407926297 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019955 | 407926302 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019956 | 407926351 | Guy | HFTD Tier 2 | Distribution | 2016-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019957 | 407926829 | High Sign | HFTD Tier 3 | Distribution | 2016-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019958 | 407926854 | Guy | HFTD Tier 3 | Distribution | 2016-07-14 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019959 | 407928885 | Molding | HFTD Tier 2 | Distribution | 2016-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019960 | 407929212 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-07-15 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019961 | 407931215 | High Sign | HFTD Tier 3 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019962 | 407931238 | High Sign | HFTD Tier 3 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019963 | 407931242 | High Sign | HFTD Tier 3 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019964 | 407931251 | High Sign | HFTD Tier 3 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019965 | 407931292 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019966 | 407931300 | High Sign | HFTD Tier 3 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019967 | 407931310 | High Sign | HFTD Tier 3 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019968 | 407931322 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019969 | 407931328 | Molding | HFTD Tier 3 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019970 | 407931468 | High Sign | HFTD Tier 3 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019971 | 407931503 | High Sign | HFTD Tier 3 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019972 | 407931639 | High Sign | HFTD Tier 3 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019973 | 407931744 | Molding | HFTD Tier 3 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019974 | 407931780 | High Sign | HFTD Tier 3 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019975 | 407932127 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019976 | 407932189 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019977 | 407932197 | High Sign | HFTD Tier 2 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019978 | 407932222 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019979 | 407932762 | Pole step | HFTD Tier 3 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019980 | 407932797 | Pole step | HFTD Tier 3 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019981 | 407932810 | Molding | HFTD Tier 3 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019982 | 407932820 | Molding | HFTD Tier 3 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019983 | 407933696 | High Sign | HFTD Tier 3 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019984 | 407933733 | Pole step | HFTD Tier 2 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019985 | 407933761 | High Sign | HFTD Tier 2 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019986 | 407933771 | High Sign | HFTD Tier 3 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019987 | 407933919 | Guy | HFTD Tier 3 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019988 | 407934272 | High Sign | HFTD Tier 3 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019989 | 407934300 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019990 | 407934418 | Molding | HFTD Tier 2 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019991 | 407934463 | Guy Guard | HFTD Tier 3 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019992 | 407934469 | Molding | HFTD Tier 2 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019993 | 407934487 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019994 | 407934511 | Molding | HFTD Tier 2 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019995 | 407934521 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019996 | 407934844 | Molding | HFTD Tier 3 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019997 | 407934864 | High Sign | HFTD Tier 2 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019998 | 407935024 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130019999 | 407935025 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020000 | 407935036 | High Sign | HFTD Tier 2 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020001 | 407935038 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020002 | 407935101 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020003 | 407935206 | High Sign | HFTD Tier 3 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020004 | 407935238 | Molding | HFTD Tier 3 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020005 | 407935254 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020006 | 407935278 | High Sign | HFTD Tier 2 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020007 | 407935313 | High Sign | HFTD Tier 2 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020008 | 407935459 | High Sign | HFTD Tier 2 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020009 | 407936744 | Riser/Conduit | HFTD Tier 2 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020010 | 407936827 | Guy | HFTD Tier 2 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020011 | 407936835 | Guy Guard | HFTD Tier 2 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020012 | 407936863 | Guy | HFTD Tier 2 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020013 | 407937533 | High Sign | HFTD Tier 2 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020014 | 407937547 | Guy | HFTD Tier 2 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020015 | 407937669 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020016 | 407937672 | High Sign | HFTD Tier 2 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020017 | 407937676 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020018 | 407937700 | High Sign | HFTD Tier 2 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020019 | 407937801 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020020 | 407937808 | Molding | HFTD Tier 2 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020021 | 407937852 | Guy | HFTD Tier 2 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020022 | 407938106 | High Sign | HFTD Tier 2 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020023 | 407938175 | Molding | HFTD Tier 2 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020024 | 407938341 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020025 | 407938489 | Molding | HFTD Tier 2 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020026 | 407938755 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020027 | 407938760 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020028 | 407938872 | Guy | HFTD Tier 3 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020029 | 407938917 | Molding | HFTD Tier 3 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020030 | 407938940 | Guy | HFTD Tier 3 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020031 | 407938960 | Pole step | HFTD Tier 3 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020032 | 407939274 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020033 | 407939705 | Molding | HFTD Tier 2 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020034 | 407939947 | Guy | HFTD Tier 2 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020035 | 407939950 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020036 | 407940637 | High Sign | HFTD Tier 2 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020037 | 407940901 | Guy | HFTD Tier 3 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020038 | 407941065 | Molding | HFTD Tier 2 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020039 | 407941267 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020040 | 407941269 | High Sign | HFTD Tier 3 | Distribution | 2016-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020041 | 407941281 | High Sign | HFTD Tier 2 | Distribution | 2016-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020042 | 407941329 | Molding | HFTD Tier 3 | Distribution | 2016-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020043 | 407941411 | Guy | HFTD Tier 2 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020044 | 407941471 | High Sign | HFTD Tier 2 | Distribution | 2016-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020045 | 407941483 | High Sign | HFTD Tier 2 | Distribution | 2016-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020046 | 407941514 | High Sign | HFTD Tier 3 | Distribution | 2016-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020047 | 407941536 | High Sign | HFTD Tier 3 | Distribution | 2016-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020048 | 407941693 | High Sign | HFTD Tier 3 | Distribution | 2016-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020049 | 407941933 | Guy Guard | HFTD Tier 3 | Distribution | 2016-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020050 | 407942029 | High Sign | HFTD Tier 3 | Distribution | 2016-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020051 | 407942032 | Molding | HFTD Tier 2 | Distribution | 2016-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020052 | 407942163 | High Sign | HFTD Tier 2 | Distribution | 2016-07-21 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020053 | 407943432 | Molding | HFTD Tier 3 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020054 | 407943966 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020055 | 407944358 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020056 | 407945279 | High Sign | HFTD Tier 2 | Distribution | 2016-07-22 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020057 | 407947438 | Guy Guard | HFTD Tier 3 | Distribution | 2016-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020058 | 407947480 | Guy | HFTD Tier 3 | Distribution | 2016-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020059 | 407947692 | Guy | HFTD Tier 2 | Distribution | 2016-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020060 | 407948312 | Molding | HFTD Tier 3 | Distribution | 2016-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020061 | 407948341 | High Sign | HFTD Tier 3 | Distribution | 2016-07-25 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020062 | 407950551 | Guy Guard | HFTD Tier 2 | Distribution | 2016-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020063 | 407950828 | High Sign | HFTD Tier 3 | Distribution | 2016-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020064 | 407950907 | High Sign | HFTD Tier 3 | Distribution | 2016-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020065 | 407950921 | High Sign | HFTD Tier 3 | Distribution | 2016-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020066 | 407950941 | Guy | HFTD Tier 3 | Distribution | 2016-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020067 | 407950950 | High Sign | HFTD Tier 3 | Distribution | 2016-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020068 | 407952516 | High Sign | HFTD Tier 2 | Distribution | 2016-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020069 | 407952523 | High Sign | HFTD Tier 2 | Distribution | 2016-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020070 | 407952533 | High Sign | HFTD Tier 2 | Distribution | 2016-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020071 | 407952542 | Molding | HFTD Tier 2 | Distribution | 2016-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020072 | 407952921 | Molding | HFTD Tier 3 | Distribution | 2016-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020073 | 407952923 | Guy | HFTD Tier 3 | Distribution | 2016-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020074 | 407952985 | Molding | HFTD Tier 2 | Distribution | 2016-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020075 | 407953151 | High Sign | HFTD Tier 3 | Distribution | 2016-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020076 | 407953297 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020077 | 407953428 | Molding | HFTD Tier 3 | Distribution | 2016-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020078 | 407953465 | Guy | HFTD Tier 3 | Distribution | 2016-07-26 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020079 | 407954198 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020080 | 407954338 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020081 | 407954342 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020082 | 407954361 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020083 | 407954536 | Molding | HFTD Tier 3 | Distribution | 2016-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020084 | 407954678 | High Sign | HFTD Tier 3 | Distribution | 2016-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020085 | 407955196 | Molding | HFTD Tier 3 | Distribution | 2016-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020086 | 407955841 | High Sign | HFTD Tier 3 | Distribution | 2016-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020087 | 407955859 | High Sign | HFTD Tier 3 | Distribution | 2016-07-27 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020088 | 407958435 | Guy Guard | HFTD Tier 3 | Distribution | 2016-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020089 | 407958706 | Guy Guard | HFTD Tier 3 | Distribution | 2016-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020090 | 407963602 | Guy | HFTD Tier 3 | Distribution | 2016-08-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020091 | 407963762 | Molding | HFTD Tier 3 | Distribution | 2016-08-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020092 | 407964514 | High Sign | HFTD Tier 2 | Distribution | 2016-07-28 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020093 | 407964543 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-08-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020094 | 407964568 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-08-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020095 | 407964599 | High Sign | HFTD Tier 3 | Distribution | 2016-08-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020096 | 407964645 | High Sign | HFTD Tier 3 | Distribution | 2016-08-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020097 | 407964656 | Molding | HFTD Tier 3 | Distribution | 2016-08-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020098 | 407964658 | High Sign | HFTD Tier 3 | Distribution | 2016-08-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020099 | 407964659 | High Sign | HFTD Tier 3 | Distribution | 2016-08-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020100 | 407964665 | High Sign | HFTD Tier 3 | Distribution | 2016-08-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020101 | 407964694 | High Sign | HFTD Tier 3 | Distribution | 2016-08-01 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020102 | 407967197 | Molding | HFTD Tier 2 | Distribution | 2016-08-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020103 | 407969190 | High Sign | HFTD Tier 2 | Distribution | 2016-08-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020104 | 407970360 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-08-02 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020105 | 407970942 | High Sign | HFTD Tier 3 | Distribution | 2016-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020106 | 407971046 | High Sign | HFTD Tier 3 | Distribution | 2016-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020107 | 407971130 | High Sign | HFTD Tier 3 | Distribution | 2016-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020108 | 407971171 | Guy Guard | HFTD Tier 2 | Distribution | 2016-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020109 | 407971209 | Guy | HFTD Tier 2 | Distribution | 2016-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020110 | 407971220 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020111 | 407971267 | Termination | HFTD Tier 2 | Distribution | 2016-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020112 | 407971319 | Anchor | HFTD Tier 2 | Distribution | 2016-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020113 | 407971426 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020114 | 407971468 | Guy | HFTD Tier 2 | Distribution | 2016-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020115 | 407971514 | High Sign | HFTD Tier 3 | Distribution | 2016-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020116 | 407971525 | Guy | HFTD Tier 2 | Distribution | 2016-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020117 | 407971670 | Guy Guard | HFTD Tier 2 | Distribution | 2016-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020118 | 407971711 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020119 | 407971935 | Guy | HFTD Tier 3 | Distribution | 2016-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020120 | 407971993 | Guy | HFTD Tier 3 | Distribution | 2016-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020121 | 407972853 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020122 | 407972967 | High Sign | HFTD Tier 2 | Distribution | 2016-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020123 | 407974130 | Molding | HFTD Tier 2 | Distribution | 2016-08-03 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020124 | 407975015 | Pole step | HFTD Tier 2 | Distribution | 2016-08-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020125 | 407975129 | Guy | HFTD Tier 3 | Distribution | 2016-08-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020126 | 407975162 | High Sign | HFTD Tier 3 | Distribution | 2016-08-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020127 | 407975233 | High Sign | HFTD Tier 2 | Distribution | 2016-08-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020128 | 407977230 | High Sign | HFTD Tier 2 | Distribution | 2016-08-04 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020129 | 407978103 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020130 | 407978193 | Molding | HFTD Tier 2 | Distribution | 2016-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020131 | 407978524 | Molding | HFTD Tier 2 | Distribution | 2016-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020132 | 407978604 | Molding | HFTD Tier 2 | Distribution | 2016-08-05 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020133 | 407981954 | Molding | HFTD Tier 2 | Distribution | 2016-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4
1130020134 | 407982069 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-08-08 |  | 3 | Ignition Risk, no GO95 exception | [5 empty] | Due Date N/A | SCE | 2025 | 4