## Table 1
METRIC NUMBER | UTILITY ID | SUBMISSION DATE | WMP CATEGORY | WMP INITIATIVE | WMP ACTIVITY NAME | TARGET ID (IF MULTIPLE) | UTILITY MITIGATION ACTIVITY TRACKING ID (UMAT) | ACTIVITY CLASSIFICATION | ACTIVITY DESCRIPTION | ACTIVITY OBJECTIVE | WMP SECTION | RISK COMPONENT TARGETED | QUANT / QUAL | QUANT TARGET UNITS | MIDYEAR TARGET (YES / NO) | COMMENTS | BLANK MEANING | REPORTING YEAR | REPORTING QUARTER | QUANT YTD VALUE | QUAL YTD VALUE | STATUS | CORRECTIVE ACTIONS IF DELAYED
1010000000 | SCE | 2026-08-03 | Emergency Preparedness, Collaboration and Public Awareness | Public Outreach and Education Awareness Program | Wildfire Safety Community Meetings |  | DEP-1 | Program | Community meetings, primarily in SCE's HFRA, to share information about SCE’s WMP efforts | Share grid hardening, PSPS, and emergency preparedness updates, and highlight SCE's various programs, services, and resources. Also, receive direct feedback from meeting participants | 11.4.3.2 | Not applicable | Qualitative |  | No |  |  | 2026 | 2 |  | In Q2, SCE target was met. SCE hosted two virtual wildfire community safety meetings. | Completed
1010000001 | SCE | 2026-08-03 | Emergency Preparedness, Collaboration and Public Awareness | Emergency Preparedness Plan | SCE Emergency Response Training |  | DEP-2 | Program | Technical training programs that prepare employees to perform their jobs safely, comply with regulatory requirements and laws, maintain system reliability, and leverage new technology | Provide effective emergency response and restore service during and after a major event. | 11.2.1.2.3 | Not applicable | Qualitative |  | No |  |  | 2026 | 2 |  | In Q2, SCE met target. PSPS teams were qualified/re-qualified to maintain readiness. | Completed
1010000002 | SCE | 2026-08-03 | Emergency Preparedness, Collaboration and Public Awareness | Public Outreach and Education Awareness Program | Customer Research and Education |  | DEP-4 | Program | SCE develops surveys to capture customer feedback on SCE’s wildfire mitigation initiatives with a special emphasis on PSPS activities | Improve its understanding of how to reduce impacts of wildfires, PSPS, and wildfire mitigation work for its customers | 11.4.3.3 | Not applicable | Qualitative |  | No |  |  | 2026 | 2 |  | Through Q2, the PSPS tracking study analysis and reporting was finalized. Activity is in progress and on track to meet year-end target. | In Progress
1010000003 | SCE | 2026-08-03 | Emergency Preparedness, Collaboration and Public Awareness | External Collaboration and Coordination | Aerial Suppression |  | DEP-5 | Project | SCE funds up to four aerial firefighting helicopters, support personnel and equipment to bolster firefighting capabilities | Support fire suppression within SCE’s service area | 11.2.1.3 | Wildfire vulnerability | Qualitative |  | No |  |  | 2026 | 2 |  | In Q1, SCE target was met. 2026 funding agreements were executed. | Completed
1010000004 | SCE | 2026-08-03 | Grid Design, Operations, and Maintenance | Asset Inspections | Distribution HFRI Inspections (Ground and Aerial) |  | IN-1.1 | Program | Detailed inspections of distribution electric lines and equipment | Detect equipment anomalies and mitigate ignition risks that cannot be detected during compliance ‐ driven programs alone | 8.3.1.1 | Equipment ignition likelihood, Contact from vegetation ignition likelihood, Contact by object ignition | Quantitative | # of structures in HFRA | Yes | Aerial: 141554.0 Ground: 143584.0 |  | 2026 | 2 | 143584 |  | In Progress
1010000005 | SCE | 2026-08-03 | Grid Design, Operations, and Maintenance | Asset Inspections | Transmission HFRI Inspections (Ground and Aerial) |  | IN-1.2 | Program | Detailed inspections of transmission electric lines and equipment | Detect equipment anomalies and mitigate ignition risks that cannot be detected during compliance ‐ driven programs alone | 8.3.2.1 | Equipment ignition likelihood, Contact from vegetation ignition likelihood, Contact by object ignition | Quantitative | # of structures in HFRA | Yes | Aerial: 21594.0 Ground: 21036.0 |  | 2026 | 2 | 21036 |  | In Progress
1010000006 | SCE | 2026-08-03 | Grid Design, Operations, and Maintenance | Equipment Maintenance & Repair | Review Transmission and Distribution HFRI Inspection Survey |  | IN-10 | Project | Review transmission and distribution HFRI inspection survey | Review transmission and distribution HFRI inspections survey and revise as needed | 8.4 | Not applicable | Qualitative |  | No |  |  | 2026 | 2 |  | Through Q2, survey enhancements continue to be tested. Activity is in progress and on track to meet year-end target. | In Progress
1010000007 | SCE | 2026-08-03 | Grid Design, Operations, and Maintenance | Work Orders | Asset Work Order Reduction |  | IN-11 | Project | Work order reduction | Close P2 notifications in HFRA with ignition risk potential that are past due | 8.6 | Equipment ignition likelihood, Contact from vegetation ignition likelihood, Contact by object ignition | Qualitative |  | No |  |  | 2026 | 2 |  | Through Q2, SCE has closed 76% of past due notifications. Activity has exceeded year-end target. | Completed
1010000008 | SCE | 2026-08-03 | Grid Design, Operations, and Maintenance | Workforce Planning | Workforce Planning |  | IN-12 | Project | Review and implement a revised asset inspections training curriculum. | Review asset inspections training curriculum and revise, as necessary | 8.8 | Not applicable | Qualitative |  | No |  |  | 2026 | 2 |  | Through Q2, SCE Inspections training program / curriculum has been mapped. Activity remains in progress and on track to meet year-end target. | In Progress
1010000009 | SCE | 2026-08-03 | Grid Design, Operations, and Maintenance | Asset Inspections | Distribution Infrared (IR) Scanning |  | IN-3 | Program | Infrared inspections of distribution electric lines and equipment | Detect deteriorated connection points on electrical equipment such as conductors, insulators, splices or connectors that over time can lead to failures if left unmitigated and pose ignition risks | 8.3.3.1 | Equipment ignition likelihood | Quantitative | # of distribution circuit miles in HFRA | Yes |  |  | 2026 | 2 | 2742.54 |  | In Progress
1010000010 | SCE | 2026-08-03 | Grid Design, Operations, and Maintenance | Asset Inspections | Transmission Infrared and Corona Scanning |  | IN-4 | Program | Infrared inspections of transmission electric lines and equipment | Detect deteriorated connection points on electrical equipment such as conductors, insulators, splices or connectors that over time can lead to failures if left unmitigated and pose ignition risks | 8.3.4.1 | Equipment ignition likelihood | Quantitative | # of transmission circuit miles in HFRA | Yes |  |  | 2026 | 2 | 739 |  | In Progress
1010000011 | SCE | 2026-08-03 | Grid Design, Operations, and Maintenance | Asset Inspections | Generation HFRI Inspections |  | IN-5 | Program | Generation High Fire Risk-Informed Inspections and Remediations in HFRA | Identify potential ignition risks on generation-related assets and mitigate the ignition driver risks through system hardening | 8.3.5 | Equipment ignition likelihood, Contact from vegetation ignition likelihood, Contact by object ignition | Quantitative | generation related assets in HFRA | Yes |  |  | 2026 | 2 | 126 |  | In Progress
1010000012 | SCE | 2026-08-03 | Enterprise Systems | Enterprise Systems | Inspection and Maintenance Tools |  | IN-8 | Project | InspectForce is the centralized asset inspection product used for planning and executing inspections | Improves the effectiveness and speed of inspections, data quality and record accuracy, and helps ensure that information is available, accessible, and timely to support wildfire mitigation activities. | 12.2 | Not applicable | Qualitative |  | No |  |  | 2026 | 2 |  | Activity Through Q2, SCE has completed training to all initial users of the InspectForce software for distribution (ground-only) and 360° inspections (combined aerial and ground). Activity is in progress and on track to meet year-end target. | In Progress
1010000013 | SCE | 2026-08-03 | Emergency Preparedness, Collaboration and Public Awareness | Customer Support in Wildfire and PSPS Emergencies | Critical Care Backup Battery (CCBB) |  | PSPS-2 | Program | Supports all customers enrolled in Medical Baseline (MBL) that reside in a HFRA to provide a battery-powered portable backup solution | Allows eligible customers to operate critical medical equipment during power outages due to PSPS events or other emergencies | 11.5.1 | PSPS vulnerability | Qualitative |  | No |  |  | 2026 | 2 |  | Through Q2, 99% of eligible customers enrolled received batteries within 30 business days. Activity is in progress and on track to meet year-end target. | In Progress
1010000014 | SCE | 2026-08-03 | Emergency Preparedness, Collaboration and Public Awareness | Customer Support in Wildfire and PSPS Emergencies | Portable PowerStation and Generator Rebates |  | PSPS-3 | Program | Provides up to five $75 rebates to customers for purchasing a portable power station for their home or small business resiliency needs | Provide additional opportunities to increase customer resiliency | 11.5.2 | PSPS vulnerability | Qualitative |  | No |  |  | 2026 | 2 |  | Through Q2,100% of rebate claims were processed and distributed within 30 business days. Activity is in progress and on track to meet year-end target. | In Progress
1010000015 | SCE | 2026-08-03 | Enterprise Systems | Enterprise Systems | POI Model Asset Data Refresh |  | RM-1 | Project | Performs regular data synthesis and quality checks on each of these individual subcomponent models. | Refresh POI model with latest asset data | 12.2 | Not applicable | Qualitative |  | No |  |  | 2026 | 2 |  | Through Q2, kick off meeting was held and owners assigned to refresh respective POI models. Activity is in progress and on track to meet year-end target. | In Progress
1010000016 | SCE | 2026-08-03 | Situational Awareness and Forecasting | Grid Monitoring Systems | Early Fault Detection (EFD) |  | SA-11 | Project | EFD technology detects high frequency radio emissions that can occur from arcing or partial discharge conditions on the electric system. | EFD could potentially be used to monitor the overall health of the electric system which may inform operational decisions during high‐risk conditions. | 10.3.1.1 | Equipment ignition likelihood, Contact from vegetation ignition likelihood, Contact by object ignition | Quantitative | # of locations | No |  |  | 2026 | 2 | 103 |  | In Progress
1010000017 | SCE | 2026-08-03 | Situational Awareness and Forecasting | Weather Station Maintenance and Calibration | Weather Station Calibrations |  | SA-12 | Project | The various weather station instruments are cleaned, tightened, re-aligned, replaced, and otherwise maintained as needed during the calibration. | Calibrate SCE-owned weather stations to ensure operational functionality and accuracy | 10.5.5 | Not applicable | Quantitative | # of calibrations | No |  |  | 2026 | 2 | 1056 |  | In Progress
1010000018 | SCE | 2026-08-03 | Situational Awareness and Forecasting | Weather Station Maintenance and Calibration | Weather Station Calibration Procedures |  | SA-13 | Project | Reviews, updates, and consolidates procedures for weather station calibration. | Review, update, and consolidate program procedures for weather station calibration | 10.5.5 | Not applicable | Qualitative |  | No |  |  | 2026 | 2 |  | Through Q2, SCE held an in-person field operations technical training and reviewed weather station procedures. Activity is in progress and on track to meet year-end target. | In Progress
1010000019 | SCE | 2026-08-03 | Enterprise Systems | Grid Monitoring Systems | Distribution Open Phase Detection (DOPD) |  | SA-14 | Project | Evaluates DOPD integration with FAN technology and develop a strategy and implementation plan for the future DOPD program. | Evaluate DOPD integration with field area network (FAN) technology and develop future DOPD program strategy and implementation plan | 10.3.1.3 | Not applicable | Qualitative |  | No |  |  | 2026 | 2 |  | Through Q2, SCE established a test plan for lab evaluation and a schedule for lab testing. Activity is in progress and on track to meet year-end target. | In Progress
1010000020 | SCE | 2026-08-03 | Situational Awareness and Forecasting | Ignition Detection Systems | HD Camera AI Uptime |  | SA-15 | Project | Validates AI uptime on available cameras. | Validate AI uptime on available cameras four times a year | 10.4.1.1 | Not applicable | Quantitative | # of validations | No |  |  | 2026 | 2 | 2 |  | In Progress
1010000021 | SCE | 2026-08-03 | Situational Awareness and Forecasting | Weather Forecasting | Weather Model Verification |  | SA-16 | Project | Performs weather model verifications. | Perform four weather model verifications a year | 10.5 | Not applicable | Quantitative | # weather model verifications | No |  |  | 2026 | 2 | 2 |  | In Progress
1010000022 | SCE | 2026-08-03 | Situational Awareness and Forecasting | Environmental Monitoring Systems | Fuel Sampling |  | SA-17 | Project | Collects vegetation moisture observations to enhance wildfire situational awareness throughout the year. | Take ongoing fuel samples in designated areas of SCE's service territory to determine live and dead fuel moisture content | 10.2.1.2 | Not applicable | Quantitative | # of fuel samples | No |  |  | 2026 | 2 | 308 |  | In Progress
1010000023 | SCE | 2026-08-03 | Enterprise Systems | Ignition Detection Systems | HD Camera Improvement |  | SA-18 | Project | Develops and implement a long-term strategy to manage and enhance SCE’s camera system. | Develop long-term strategy to manage and identify opportunities to improve SCE’s camera system | 10.4 | Not applicable | Qualitative |  | No |  |  | 2026 | 2 |  | In Q2, SCE worked with its third-party research partner to assess the market for emerging technologies and opportunities to enhance the HD camera system. Activity is in progress and on track to meet year-end target. | In Progress
1010000024 | SCE | 2026-08-03 | Situational Awareness and Forecasting | Environmental Monitoring Systems | Weather Station Coverage |  | SA-19 | Project | Maintains a map of weather station coverage to evaluate potential future installations based on operational needs. | Continue to maintain a map of weather station point coverage for future evaluation of potential weather station installs, if there is an identified operational need. | 10.2.1.1 | Not applicable | Qualitative |  | No |  |  | 2026 | 2 |  | Through Q2, SCE continued to maintain a map of weather station point coverage for future evaluation of potential weather station installs. Activity is in progress and on track to meet year-end target. | In Progress
1010000025 | SCE | 2026-08-03 | Enterprise Systems | Weather Forecasting | Weather and Fuels Modeling |  | SA-3 | Program | Weather and fuels modeling including weather forecasts and historic weather data spanning the entire SCE service area | Maintain and enhance operational weather and fuel forecasting capabilities | 10.5 | Not applicable | Qualitative |  | No |  |  | 2026 | 2 |  | In Q2, the vendor work is proceeding as expected; SCE received a list of weather stations expected to have machine learning models built. Activity is in progress and on track to meet year-end target. | In Progress
1010000026 | SCE | 2026-08-03 | Grid Design, Operations, and Maintenance | Covered Conductor Installation | Covered Conductor |  | SH-1 | Program | Replaces existing bare wire with covered conductor (CC) and upgrade associated components to enhance safety and reliability. | Install covered conductor to reduce CFO, EFF and Wire-to-Wire risk on targeted circuits | 8.2.1.1 | Equipment ignition likelihood, Contact from vegetation ignition likelihood, Contact by object ignition, PSPS Likelihood | Quantitative | # of circuit miles | No |  |  | 2026 | 2 | 96 |  | In Progress
1010000027 | SCE | 2026-08-03 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Long Span Initiative |  | SH-14 | Program | Reduces the risk of conductor clash in high wind conditions for various distribution spans. | Implement select mitigations on identified long spans to reduce Wire to Wire risk | 8.2.5.1 | Equipment ignition likelihood, Contact from vegetation ignition likelihood, Contact by object ignition | Quantitative | # of spans | No |  |  | 2026 | 2 | 238 |  | In Progress
1010000028 | SCE | 2026-08-03 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Vibration Damper Retrofit |  | SH-16 | Program | Aims to stop wind-driven vibration (known as Aeolian vibration) that may lead to conductor abrasion or fatigue over time. | Install vibration dampers to reduce the effects of aeolian vibrations and extend the useful life of covered conductor | 8.2.1.2 | Equipment ignition likelihood, Contact from vegetation ignition likelihood, Contact by object ignition | Qualitative |  | No |  |  | 2026 | 2 |  | Through Q2, SCE has installed 280 of the remaining 310 retrofit vibration dampers on structures in HFRA. Activity is in progress and on track to meet year-end target. | In Progress
1010000029 | SCE | 2026-08-03 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Rapid Earth Fault Current Limiters (REFCL) - Ground Fault Neutralizer |  | SH-17 | Program | The Rapid Earth Fault Current Limiter (REFCL) initiative uses technology that detects ground faults as small as a half ampere on one phase of a threephase powerline. | Complete construction of REFCL Ground Fault Neutralizers at targeted substations | 8.2.6.1 | Equipment ignition likelihood, Contact from vegetation ignition likelihood, Contact by object ignition | Quantitative | completed construction at substation | No |  |  | 2026 | 2 | 2 |  | Completed
1010000030 | SCE | 2026-08-03 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Rapid Earth Fault Current Limiters (REFCL) - Grounding Conversions |  | SH-18 | Program | The REFCL Grounding Conversion (REFCL GC) applications act to reduce energy and ignition risk associated with single phase to ground faults. | Complete construction of REFCL grounding conversions at targeted locations | 8.2.6.2 | Equipment ignition likelihood, Contact from vegetation ignition likelihood, Contact by object ignition | Quantitative | completed construction at location | No |  |  | 2026 | 2 | 0 |  | In Progress
1010000031 | SCE | 2026-08-03 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Fire-resistant (FR) Wrap Expanded Deployment |  | SH-19 | Project | Installs FR wraps on unwrapped wood poles on a risk-prioritized basis in HFRA that are located within areas experiencing the highest frequency of burns. | Deploy fire resistant wraps on unprotected wood poles | 8.2.3.1 | Equipment ignition likelihood | Quantitative | # of fire-resistant wraps | No |  |  | 2026 | 2 | 14 |  | Delayed | After publication of new construction standards, partnered with internal partners to addressed its internal permitting hurdles, clearing the way for execution to start Continue meetings with internal stakeholders monthly for updates and address any potential obstacles
1010000032 | SCE | 2026-08-03 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Undergrounding Overhead Conductor |  | SH-2 | Program | Underground existing overhead power lines to minimize wildfire and PSPS risk by preventing contact with energized conductors and reducing ignition potential from equipment failures. | Underground previously overhead conductor to reduce likelihood of ignition | 8.2.2.1 | Equipment ignition likelihood, Contact from vegetation ignition likelihood, Contact by object ignition, PSPS Likelihood | Quantitative | OH circuit miles converted to UG | No |  |  | 2026 | 2 | 17 |  | In Progress
1010000033 | SCE | 2026-08-03 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Transmission Proactive Splice Shunting |  | SH-20 | Project | SCE plans to proactively remediate splices by shunting them to enhance redundancy, ensuring both physical and electrical load are supported. | Shunt splices on transmission conductor to reduce the likelihood of equipment failure | 8.2.6.4 | Equipment ignition likelihood | Quantitative | # of splice shuntings | No |  |  | 2026 | 2 | 186 |  | In Progress
1010000034 | SCE | 2026-08-03 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Remote Controlled Automatic Reclosers Settings Update |  | SH-5 | Program | Installs Remote Control Switches (RCS) and Remote Automatic Recloser (RAR) devices. | Install sectionalizing devices to increase circuit sectionalization | 8.2.8.1 | Equipment ignition likelihood, Contact from vegetation ignition likelihood, Contact by object ignition | Quantitative | # of RARs / RCSs installed and operationalized | No |  |  | 2026 | 2 | 7 |  | Completed
1010000035 | SCE | 2026-08-03 | Vegetation Management and Inspections | Vegetation Inspections | Hazard Tree Management Program |  | VM-1 | Program | Identifies trees that pose a risk to electric facilities based on the tree’s observed structural integrity and site conditions. | Inspect SCE's grid and prescribe mitigations for hazardous trees with strike potential within SCE's HFRA | 9.2.3 | Contact from vegetation ignition likelihood | Quantitative | circuit miles inspected | Yes |  |  | 2026 | 2 | 4344.92 |  | In Progress
1010000036 | SCE | 2026-08-03 | Vegetation Management and Inspections | Wood and Slash Management | Wood and Slash Contractor Management |  | VM-11 | Project | Evaluates debris management practices and improving contractual agreements with vendors where practical. | Review and identify potential updates to contract terms for debris management, with implementation contingent on contract execution timing | 9.5 | Not applicable | Qualitative |  | No |  |  | 2026 | 2 |  | Through Q2, SCE Vegetation Management system continues to utilize mandatory work management fields to document the removal method for all wood slash (debris) and mandatory QC fields to support sample-based verification activities. Activity is in progress and on track to meet year-end target. | In Progress
1010000037 | SCE | 2026-08-03 | Vegetation Management and Inspections | Workforce Planning | SCE VM Workforce Planning |  | VM-12 | Project | Partnership with educational institutes for SCE personnel to participate in professional seminars and webinars | Continue partnership with educational institutes for SCE personnel to participate in professional seminars and webinars | 9.13 | Not applicable | Qualitative |  | No |  |  | 2026 | 2 |  | Through Q2, SCE continued educational partnerships with local college for SCE personnel to take part in professional seminars and webinars. Activity is in progress and on track to meet year-end target. | In Progress
1010000038 | SCE | 2026-08-03 | Vegetation Management and Inspections | Integrated Vegetation Management | VM Treatment Methodologies |  | VM-13 | Project | SCE continues to evaluate, expand, and apply treatment methodologies across required vegetation management activities. | Continue to evaluate and expand treatment methodologies across required vegetation management activities | 9.7 | Not applicable | Qualitative |  | No |  |  | 2026 | 2 |  | Through Q2, SCE continued evaluating and advancing alternative vegetation treatment methodologies and technologies. Activity is in progress and on track to meet year-end target. | In Progress
1010000039 | SCE | 2026-08-03 | Vegetation Management and Inspections | Defensible Space | Expanded Clearances for Non-Energized Facilities |  | VM-14 | Project | SCE conducts field inspections of non-energized water conveyance generation facilities. | Implement field inspections of nonenergized water conveyance facilities and develop an expanded clearance treatment scope that can be implemented in 2027 and 2028 | 9.6 | Not applicable | Qualitative |  | No |  |  | 2026 | 2 |  | Through Q2, SCE developed an app to track inspections of non-energized water conveyance facilities to monitor treatment recommendations and completions for expanded clearance documentation. SCE has secured and awarded contracts for program implementation. Activity is in progress and on track to meet year-end target. | In Progress
1010000040 | SCE | 2026-08-03 | Vegetation Management and Inspections | Clearance | Transition from Ground-based Inspections to Remote Sensing to Perform a Portion of Inspections for Clearances from Distribution Lines |  | VM-15 | Project | Integrate new vegetation management technology/practice for line clearing. | Build core capabilities (crown segmentation and trim prescription) for Distribution to implement remote inspections and work prescription. | 9.2 | Not applicable | Qualitative |  | No |  |  | 2026 | 2 |  | Through Q2, SCE advanced implementation of transition from ground-based inspections to remote sensing by further developing and implementing work prescriptions derived from crown segmentation technology. Activity is in progress and on track to meet year-end target. | In Progress
1010000041 | SCE | 2026-08-03 | Vegetation Management and Inspections | Clearance | Transition from Ground-based Inspections to Remote Sensing to Perform a Portion of Inspections for Clearances from Transmission Lines |  | VM-16 | Project | Integrate new vegetation management technology/practice for line clearing. | Build core capabilities and operationalize remote sensing technology | 9.2 | Not applicable | Qualitative |  | No |  |  | 2026 | 2 |  | Through Q2, SCE Through Q2, SCE advanced implementation of transition from ground-based inspections to remote sensing by further developing and implementing work prescriptions derived from crown segmentation technology. Activity is in progress and on track to meet year-end target. | In Progress
1010000042 | SCE | 2026-08-03 | Vegetation Management and Inspections | Vegetation Management and Inspections | Effectiveness of Remote Sensing Pilot – Distribution |  | VM-17 | Project | Produce metrics for Distribution ground and remote sensing inspection efficacy. | Determine effectiveness of remote sensing technology | 9.2 | Not applicable | Qualitative |  | No |  |  | 2026 | 2 |  | Through Q2, SCE developed and operationalized dashboard that provides metrics to support measurement of alignment/misalignment between derived trim decisions for Distribution remote sensing inspections, Activity is in progress and on track to meet year-end target. | In Progress
1010000043 | SCE | 2026-08-03 | Vegetation Management and Inspections | Vegetation Management and Inspections | Effectiveness of Remote Sensing Pilot – Transmission |  | VM-18 | Project | Produce metrics for Transmission ground and remote sensing inspection efficacy. | Determine effectiveness of remote sensing technology | 9.2 | Not applicable | Qualitative |  | No |  |  | 2026 | 2 |  | Through Q2, SCE developed and operationalized dashboard that provide metrics for derived percentage alignment/misalignment and trim decisions. Activity is in progress and on track to meet year-end target. | In Progress
1010000044 | SCE | 2026-08-03 | Vegetation Management and Inspections | Vegetation management and inspections | Additional Structure Brushing |  | VM-2.1 | Program | SCE attempts to brush additional structures outside the State Responsibility Area in HFRA for risk mitigation | Inspect structures and perform clearance where necessary and feasible to reduce EFF Risk | 9.4.1.2 | Equipment ignition likelihood, Contact from vegetation ignition likelihood | Quantitative | # structures brushed | Yes |  |  | 2026 | 2 | 59685 |  | In Progress
1010000045 | SCE | 2026-08-03 | Vegetation Management and Inspections | Pole Clearing | Compliance Structure Brushing |  | VM-2.2 | Program | SCE removes vegetation around all Distribution poles and Transmission structures subject to PRC 4292 in State Responsibility Areas (SRA). | Inspect structures and perform clearance where necessary and feasible to reduce EFF Risk | 9.4.1.1 | Equipment ignition likelihood, Contact from vegetation ignition likelihood | Quantitative | # structures brushed | Yes |  |  | 2026 | 2 | 63801 |  | In Progress
1010000046 | SCE | 2026-08-03 | Vegetation Management and Inspections | Pole Clearing | Dead and Dying Tree Removal |  | VM-4 | Program | Patrols in HFRA to identify and remove dead, dying, or diseased trees affected by drought conditions and/or insect infestation. | Inspect SCE's grid and prescribe mitigation for dead and dying trees with strike potential within SCE's HFRA | 9.2.4 | Contact from vegetation ignition likelihood | Quantitative | circuit miles inspected | Yes |  |  | 2026 | 2 | 5092.16 |  | In Progress
1010000047 | SCE | 2026-08-03 | Enterprise Systems | Vegetation Management Enterprise System | Vegetation Work Management System |  | VM-6 | Project | Data Warehouse used for Routine Vegetation Management inspections and resulting mitigations | Monitor utilization of vegetation work management system and make enhancements as needed | 12.2 | Not applicable | Qualitative |  | No |  |  | 2026 | 2 |  | SCE completed training materials and train-the-trainer courses in Q1. Activity is ahead of schedule to meet year-end target. | In Progress
1010000048 | SCE | 2026-08-03 | Vegetation Management and Inspections | Vegetation management and inspections | Inspections for Vegetation Clearance from Distribution Lines |  | VM-7 | Program | Inspections for vegetation clearances from distribution lines aim to prevent vegetation from encroaching upon distribution assets | Inspect SCE's distribution system in HFRA and prescribe mitigation as needed to achieve clearance | 9.2.1 | Contact from vegetation ignition likelihood | Quantitative | % of circuit miles inspected in HFRA | Yes |  |  | 2026 | 2 | 0.68 |  | In Progress
1010000049 | SCE | 2026-08-03 | Vegetation Management and Inspections | Clearance | Inspections for Vegetation Clearance from Transmission Lines |  | VM-8 | Program | Transmission expanded line clearances to mitigate the risk of vegetation contact with energized conductors | Inspect SCE's Transmission system in HFRA and prescribe mitigation as needed to achieve clearance | 9.2.2 | Contact from vegetation ignition likelihood | Quantitative | % of circuit miles inspected in HFRA | Yes |  |  | 2026 | 2 | 0.6 |  | In Progress
Note on W1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Tina Luong @Felicia Martinez Tina, also, we need to have a status populated per the Guidelines else T1 will be rejected… Can you please advise?

## Table 2
METRIC NUMBER | METRIC TYPE | METRIC NAME | WIND WARNING STATUS | HFTD TIER | LINE TYPE | INSPECTION TYPE | INSPECTION METHOD | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1020000000 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | HFTD Tier 2 |  |  |  | Number of events | SCE notes tha the aggregate sum of all risk events is for those with ignition risk only and that these sums should not be expected to align with table 5 and 6 for total risk events. |  | SCE | 2026 | 2 | 0
1020000001 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | HFTD Tier 2 |  |  |  | Number of events | SCE notes tha the aggregate sum of all risk events is for those with ignition risk only and that these sums should not be expected to align with table 5 and 6 for total risk events. |  | SCE | 2026 | 2 | 2
1020000002 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events | SCE notes tha the aggregate sum of all risk events is for those with ignition risk only and that these sums should not be expected to align with table 5 and 6 for total risk events. |  | SCE | 2026 | 2 | 0
1020000003 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | HFTD Tier 2 |  |  |  | Number of events | SCE notes tha the aggregate sum of all risk events is for those with ignition risk only and that these sums should not be expected to align with table 5 and 6 for total risk events. |  | SCE | 2026 | 2 | 311
1020000004 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | HFTD Tier 3 |  |  |  | Number of events | SCE notes tha the aggregate sum of all risk events is for those with ignition risk only and that these sums should not be expected to align with table 5 and 6 for total risk events. |  | SCE | 2026 | 2 | 0
1020000005 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | HFTD Tier 3 |  |  |  | Number of events | SCE notes tha the aggregate sum of all risk events is for those with ignition risk only and that these sums should not be expected to align with table 5 and 6 for total risk events. |  | SCE | 2026 | 2 | 3
1020000006 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events | SCE notes tha the aggregate sum of all risk events is for those with ignition risk only and that these sums should not be expected to align with table 5 and 6 for total risk events. |  | SCE | 2026 | 2 | 0
1020000007 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | HFTD Tier 3 |  |  |  | Number of events | SCE notes tha the aggregate sum of all risk events is for those with ignition risk only and that these sums should not be expected to align with table 5 and 6 for total risk events. |  | SCE | 2026 | 2 | 406
1020000008 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | Non-HFTD |  |  |  | Number of events | SCE notes tha the aggregate sum of all risk events is for those with ignition risk only and that these sums should not be expected to align with table 5 and 6 for total risk events. |  | SCE | 2026 | 2 | 43
1020000009 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | Non-HFTD |  |  |  | Number of events | SCE notes tha the aggregate sum of all risk events is for those with ignition risk only and that these sums should not be expected to align with table 5 and 6 for total risk events. |  | SCE | 2026 | 2 | 15
1020000010 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | Non-HFTD |  |  |  | Number of events | SCE notes tha the aggregate sum of all risk events is for those with ignition risk only and that these sums should not be expected to align with table 5 and 6 for total risk events. |  | SCE | 2026 | 2 | 9
1020000011 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | Non-HFTD |  |  |  | Number of events | SCE notes tha the aggregate sum of all risk events is for those with ignition risk only and that these sums should not be expected to align with table 5 and 6 for total risk events. |  | SCE | 2026 | 2 | 3106
1020000012 | Risk Events | Number of wires down | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | SCE | 2026 | 2 | 0
1020000013 | Risk Events | Number of wires down | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | SCE | 2026 | 2 | 0
1020000014 | Risk Events | Number of wires down | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | SCE | 2026 | 2 | 0
1020000015 | Risk Events | Number of wires down | Neither | HFTD Tier 2 |  |  |  | Number of events | Note: A portion of this data includes "Unknown" HWW/RFW. |  | SCE | 2026 | 2 | 17
1020000016 | Risk Events | Number of wires down | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | SCE | 2026 | 2 | 0
1020000017 | Risk Events | Number of wires down | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | SCE | 2026 | 2 | 0
1020000018 | Risk Events | Number of wires down | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | SCE | 2026 | 2 | 0
1020000019 | Risk Events | Number of wires down | Neither | HFTD Tier 3 |  |  |  | Number of events | Note: A portion of this data includes "Unknown" HWW/RFW. |  | SCE | 2026 | 2 | 19
1020000020 | Risk Events | Number of wires down | RFW only | Non-HFTD |  |  |  | Number of events |  |  | SCE | 2026 | 2 | 3
1020000021 | Risk Events | Number of wires down | HWW only | Non-HFTD |  |  |  | Number of events |  |  | SCE | 2026 | 2 | 2
1020000022 | Risk Events | Number of wires down | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | SCE | 2026 | 2 | 1
1020000023 | Risk Events | Number of wires down | Neither | Non-HFTD |  |  |  | Number of events | Note: A portion of this data includes "Unknown" HFTD & "Unknown" HWW/RFW. |  | SCE | 2026 | 2 | 227
1020000024 | Risk Events | Number of outage events not caused by contact with vegetation | RFW only | HFTD Tier 2 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2026 | 2 | 0
1020000025 | Risk Events | Number of outage events not caused by contact with vegetation | HWW only | HFTD Tier 2 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2026 | 2 | 2
1020000026 | Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2026 | 2 | 0
1020000027 | Risk Events | Number of outage events not caused by contact with vegetation | Neither | HFTD Tier 2 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2026 | 2 | 290
1020000028 | Risk Events | Number of outage events not caused by contact with vegetation | RFW only | HFTD Tier 3 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2026 | 2 | 0
1020000029 | Risk Events | Number of outage events not caused by contact with vegetation | HWW only | HFTD Tier 3 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2026 | 2 | 2
1020000030 | Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2026 | 2 | 0
1020000031 | Risk Events | Number of outage events not caused by contact with vegetation | Neither | HFTD Tier 3 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2026 | 2 | 368
1020000032 | Risk Events | Number of outage events not caused by contact with vegetation | RFW only | Non-HFTD |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2026 | 2 | 33
1020000033 | Risk Events | Number of outage events not caused by contact with vegetation | HWW only | Non-HFTD |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2026 | 2 | 10
1020000034 | Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | Non-HFTD |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2026 | 2 | 8
1020000035 | Risk Events | Number of outage events not caused by contact with vegetation | Neither | Non-HFTD |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2026 | 2 | 2732
1020000036 | Risk Events | Number of outage events caused by contact with vegetation | RFW only | HFTD Tier 2 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2026 | 2 | 0
1020000037 | Risk Events | Number of outage events caused by contact with vegetation | HWW only | HFTD Tier 2 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2026 | 2 | 0
1020000038 | Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2026 | 2 | 0
1020000039 | Risk Events | Number of outage events caused by contact with vegetation | Neither | HFTD Tier 2 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2026 | 2 | 1
1020000040 | Risk Events | Number of outage events caused by contact with vegetation | RFW only | HFTD Tier 3 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2026 | 2 | 0
1020000041 | Risk Events | Number of outage events caused by contact with vegetation | HWW only | HFTD Tier 3 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2026 | 2 | 0
1020000042 | Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2026 | 2 | 0
1020000043 | Risk Events | Number of outage events caused by contact with vegetation | Neither | HFTD Tier 3 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2026 | 2 | 7
1020000044 | Risk Events | Number of outage events caused by contact with vegetation | RFW only | Non-HFTD |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2026 | 2 | 0
1020000045 | Risk Events | Number of outage events caused by contact with vegetation | HWW only | Non-HFTD |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2026 | 2 | 1
1020000046 | Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | Non-HFTD |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2026 | 2 | 0
1020000047 | Risk Events | Number of outage events caused by contact with vegetation | Neither | Non-HFTD |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2026 | 2 | 23
1020000048 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | HFTD Tier 2 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2026 | 2 | 0
1020000049 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | HFTD Tier 2 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2026 | 2 | 0
1020000050 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2026 | 2 | 0
1020000051 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | HFTD Tier 2 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2026 | 2 | 2
1020000052 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | HFTD Tier 3 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2026 | 2 | 0
1020000053 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | HFTD Tier 3 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2026 | 2 | 1
1020000054 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2026 | 2 | 0
1020000055 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | HFTD Tier 3 |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2026 | 2 | 6
1020000056 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | Non-HFTD |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2026 | 2 | 6
1020000057 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | Non-HFTD |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2026 | 2 | 1
1020000058 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | Non-HFTD |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2026 | 2 | 0
1020000059 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | Non-HFTD |  |  |  | Number of events | SCE interprets these Outages to be a subset of the metric above which captures those Risk Events that have the potential to cause ignition only, as such, these are subset of those reported on Table 5. |  | SCE | 2026 | 2 | 103
1020000060 | Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 2 | Distribution |  |  | days |  |  | SCE | 2026 | 2 | 42
1020000061 | Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | days |  |  | SCE | 2026 | 2 | 190
1020000062 | Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 3 | Distribution |  |  | days |  |  | SCE | 2026 | 2 | 37
1020000063 | Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | days |  |  | SCE | 2026 | 2 | 106
1020000064 | Time between vegetation inspection finding and resulting trimming activity | Median time |  | Non-HFTD | Distribution |  |  | days |  |  | SCE | 2026 | 2 | 39
1020000065 | Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | days |  |  | SCE | 2026 | 2 | 98
1020000066 | Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 2 | Transmission |  |  | days |  |  | SCE | 2026 | 2 | 63
1020000067 | Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | days |  |  | SCE | 2026 | 2 | 335
1020000068 | Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 3 | Transmission |  |  | days |  |  | SCE | 2026 | 2 | 55
1020000069 | Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | days |  |  | SCE | 2026 | 2 | 425
1020000070 | Time between vegetation inspection finding and resulting trimming activity | Median time |  | Non-HFTD | Transmission |  |  | days |  |  | SCE | 2026 | 2 | 39
1020000071 | Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | days |  |  | SCE | 2026 | 2 | 103
1020000072 | Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours |  |  | SCE | 2026 | 2 | 1
1020000073 | Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours |  |  | SCE | 2026 | 2 | 6
1020000074 | Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours |  |  | SCE | 2026 | 2 | 1
1020000075 | Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours |  |  | SCE | 2026 | 2 | 5.5
1020000076 | Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000077 | Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000078 | Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours |  |  | SCE | 2026 | 2 | 0
1020000079 | Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours |  |  | SCE | 2026 | 2 | 0
1020000080 | Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours |  |  | SCE | 2026 | 2 | 0
1020000081 | Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours |  |  | SCE | 2026 | 2 | 0
1020000082 | Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000083 | Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000084 | Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours |  |  | SCE | 2026 | 2 | 271
1020000085 | Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours |  |  | SCE | 2026 | 2 | 1008
1020000086 | Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours |  |  | SCE | 2026 | 2 | 113
1020000087 | Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours |  |  | SCE | 2026 | 2 | 903
1020000088 | Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000089 | Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000090 | Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours |  |  | SCE | 2026 | 2 | 318
1020000091 | Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours |  |  | SCE | 2026 | 2 | 1825
1020000092 | Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours |  |  | SCE | 2026 | 2 | 200.5
1020000093 | Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours |  |  | SCE | 2026 | 2 | 2041
1020000094 | Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000095 | Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000096 | Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours |  |  | SCE | 2026 | 2 | 848
1020000097 | Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours |  |  | SCE | 2026 | 2 | 6568
1020000098 | Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours |  |  | SCE | 2026 | 2 | 609
1020000099 | Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours |  |  | SCE | 2026 | 2 | 4214
1020000100 | Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000101 | Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000102 | Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours |  |  | SCE | 2026 | 2 | 1017
1020000103 | Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours |  |  | SCE | 2026 | 2 | 2088
1020000104 | Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours |  |  | SCE | 2026 | 2 | 1810
1020000105 | Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours |  |  | SCE | 2026 | 2 | 2667
1020000106 | Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000107 | Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000108 | Vegetation management work orders | Number of vegetation management open work orders (total) | [5 empty] | Number of orders | Routine |  | SCE | 2026 | 2 | 66785
1020000109 | Vegetation management work orders | Number of vegetation management past due work orders (total) | [5 empty] | Number of orders | Routine - For Veg Past Due WOs, SCE reports the number of open work points in 6a that have exceeded internal targets of 30 days <Regulatory Clearance Distance (RCD) and 90 days between RCD and Trigger Clearance Distance (TCD). |  | SCE | 2026 | 2 | 19979
1020000110 | Asset management work orders | Number of asset management open work orders (total) | [5 empty] | Number of orders |  |  | SCE | 2026 | 2 | 148890
1020000111 | Asset management work orders | Number of asset management past due work orders (total) | [5 empty] | Number of orders |  |  | SCE | 2026 | 2 | 5624
1020000112 | Response Time | Response time to locked open circuit breaker | [5 empty] | Hours | For metric 8a, data for crew response time to a locked circuit breaker incident is not readily availableis not currently available as SCE does not make it mandatory to track arrival time of the crew for instances not involving hazard conditions such as 911 or wire down calls. Documentation takes time away from restoring customers and therefore not tracked for other purposesSCE will continue to review the available information in its outage systems to provide this information in a future filing. Currently, aAny average on a quarterly basisquarterly data would not reflect only 911 and wire down events and is not a good representation of our overall true response time. | Metric Not Available at this Time. | SCE | 2026 | 2
1020000113 | Fatalities and injuries due to utility-related ignitions | Fatalities due to utility-related ignitions (total) | [5 empty] | Number of fatalities | The information provided in conjunction with all of the “utility-ignited” wildfire statistics in tables 1-13 should not be construed as an admission of any wrongdoing or liability by SCE or concession that the wildfire was actually caused by SCE equipment. SCE is required to submit an Electric Safety Incident Report when certain criteria are met, including any allegation that an incident is attributed to SCE equipment, even if there is no evidence supporting such allegation. SCE further notes that the damages metrics provided may be tracked by other agencies and thus, SCE does not guarantee the accuracy of such information. Additionally, in many instances the cause of wildfires are still under investigation and even where an Authority Having Jurisdiction (AHJ) has issued a report on the cause, SCE may dispute the conclusions of such report. |  | SCE | 2026 | 2 | 0
1020000114 | Fatalities and injuries due to utility-related ignitions | Injuries due to utility-related ignitions (total) | [5 empty] | Number of injuries | The information provided in conjunction with all of the “utility-ignited” wildfire statistics in tables 1-13 should not be construed as an admission of any wrongdoing or liability by SCE or concession that the wildfire was actually caused by SCE equipment. SCE is required to submit an Electric Safety Incident Report when certain criteria are met, including any allegation that an incident is attributed to SCE equipment, even if there is no evidence supporting such allegation. SCE further notes that the damages metrics provided may be tracked by other agencies and thus, SCE does not guarantee the accuracy of such information. Additionally, in many instances the cause of wildfires are still under investigation and even where an Authority Having Jurisdiction (AHJ) has issued a report on the cause, SCE may dispute the conclusions of such report. |  | SCE | 2026 | 2 | 0
1020000115 | Value of assets destroyed by utility-related ignitions, listed by asset type | Value of assets destroyed by utility-related ignitions (total) | [5 empty] | Dollars | The information provided in conjunction with all of the “utility-ignited” wildfire statistics in tables 1-13 should not be construed as an admission of any wrongdoing or liability by SCE or concession that the wildfire was actually caused by SCE equipment. SCE is required to submit an Electric Safety Incident Report when certain criteria are met, including any allegation that an incident is attributed to SCE equipment, even if there is no evidence supporting such allegation. SCE further notes that the damages metrics provided may be tracked by other agencies and thus, SCE does not guarantee the accuracy of such information. Additionally, in many instances the cause of wildfires are still under investigation and even where an Authority Having Jurisdiction (AHJ) has issued a report on the cause, SCE may dispute the conclusions of such report. Ignition costs include only those repair WOs that have been closed by time of report out. Additional costs may still be pending. Updated estimates of these costs may be provided in SCE/EIX quarterly financial statements, where applicable. |  | SCE | 2026 | 2 | 38318.29
1020000116 | Structures damaged or destroyed by utility-related ignitions | Number of structures destroyed by utility-related ignitions (total) | [5 empty] | Number of structures | The information provided in conjunction with all of the “utility-ignited” wildfire statistics in tables 1-13 should not be construed as an admission of any wrongdoing or liability by SCE or concession that the wildfire was actually caused by SCE equipment. SCE is required to submit an Electric Safety Incident Report when certain criteria are met, including any allegation that an incident is attributed to SCE equipment, even if there is no evidence supporting such allegation. SCE further notes that the damages metrics provided may be tracked by other agencies and thus, SCE does not guarantee the accuracy of such information. Additionally, in many instances the cause of wildfires are still under investigation and even where an Authority Having Jurisdiction (AHJ) has issued a report on the cause, SCE may dispute the conclusions of such report. |  | SCE | 2026 | 2 | 0
1020000117 | Structures damaged or destroyed by utility-related ignitions | Critical infrastructure damaged/destroyed by utility-related ignitions (total) | [5 empty] | Number of structures |  | Data point is not currently tracked. | SCE | 2026 | 2
1020000118 | Acreage burned by utility-ignited wildfires | Acreage burned by utility-ignited wildfires | [5 empty] | Acres | The information provided in conjunction with all of the “utility-ignited” wildfire statistics in tables 1-13 should not be construed as an admission of any wrongdoing or liability by SCE or concession that the wildfire was actually caused by SCE equipment. SCE is required to submit an Electric Safety Incident Report when certain criteria are met, including any allegation that an incident is attributed to SCE equipment, even if there is no evidence supporting such allegation. SCE further notes that the damages metrics provided may be tracked by other agencies and thus, SCE does not guarantee the accuracy of such information. Additionally, in many instances the cause of wildfires are still under investigation and even where an Authority Having Jurisdiction (AHJ) has issued a report on the cause, SCE may dispute the conclusions of such report. |  | SCE | 2026 | 2 | 1248.96
1020000119 | Number of utility-related ignitions | Number of ignitions | RFW only | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | SCE | 2026 | 2 | 0
1020000120 | Number of utility-related ignitions | Number of ignitions | HWW only | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | SCE | 2026 | 2 | 0
1020000121 | Number of utility-related ignitions | Number of ignitions | HWW & RFW | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | SCE | 2026 | 2 | 0
1020000122 | Number of utility-related ignitions | Number of ignitions | Neither | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | SCE | 2026 | 2 | 1
1020000123 | Number of utility-related ignitions | Number of ignitions | RFW only | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | SCE | 2026 | 2 | 0
1020000124 | Number of utility-related ignitions | Number of ignitions | HWW only | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | SCE | 2026 | 2 | 0
1020000125 | Number of utility-related ignitions | Number of ignitions | HWW & RFW | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | SCE | 2026 | 2 | 0
1020000126 | Number of utility-related ignitions | Number of ignitions | Neither | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | SCE | 2026 | 2 | 6
1020000127 | Number of utility-related ignitions | Number of ignitions | RFW only | Non-HFTD |  |  |  | Number of ignitions |  |  | SCE | 2026 | 2 | 1
1020000128 | Number of utility-related ignitions | Number of ignitions | HWW only | Non-HFTD |  |  |  | Number of ignitions |  |  | SCE | 2026 | 2 | 1
1020000129 | Number of utility-related ignitions | Number of ignitions | HWW & RFW | Non-HFTD |  |  |  | Number of ignitions |  |  | SCE | 2026 | 2 | 0
1020000130 | Number of utility-related ignitions | Number of ignitions | Neither | Non-HFTD |  |  |  | Number of ignitions |  |  | SCE | 2026 | 2 | 21
1020000131 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000132 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000133 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000134 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000135 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SCE | 2026 | 2 | 25235
1020000136 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | SCE Dist Aerial inspections completed using drone. Aerial only used for "Hard To Access" structures. |  | SCE | 2026 | 2 | 0
1020000137 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000138 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SCE | 2026 | 2 | 25711
1020000139 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000140 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | SCE's Dist IR Scan uses Aerial (helicopter) for HFTD "Hard to Access" structures only. |  | SCE | 2026 | 2 | 0
1020000141 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000142 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SCE | 2026 | 2 | 59371
1020000143 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000144 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000145 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000146 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000147 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. |  | SCE | 2026 | 2 | 855.4621
1020000148 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility | SCE Dist Aerial inspections completed using drone. Aerial only used for "Hard To Access" structures. SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. |  | SCE | 2026 | 2 | 0
1020000149 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000150 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. |  | SCE | 2026 | 2 | 871.5984
1020000151 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000152 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility | SCE's Dist IR Scan uses Aerial (helicopter) for HFTD "Hard to Access" structures only. SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. |  | SCE | 2026 | 2 | 0
1020000153 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000154 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. |  | SCE | 2026 | 2 | 648
1020000155 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000156 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000157 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000158 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000159 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000160 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000161 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000162 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 46
1020000163 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000164 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000165 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000166 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 2
1020000167 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000168 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000169 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000170 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000171 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 13
1020000172 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000173 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000174 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 6364
1020000175 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000176 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000177 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000178 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 3
1020000179 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000180 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000181 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000182 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000183 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000184 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000185 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000186 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 4502
1020000187 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000188 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000189 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000190 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000191 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000192 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000193 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000194 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000195 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SCE | 2026 | 2 | 48214
1020000196 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | SCE Dist Aerial inspections completed using drone. Aerial only used for "Hard To Access" structures. |  | SCE | 2026 | 2 | 0
1020000197 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000198 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SCE | 2026 | 2 | 48270
1020000199 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000200 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | SCE's Dist IR Scan uses Aerial (helicopter) for HFTD "Hard to Access" structures only. |  | SCE | 2026 | 2 | 0
1020000201 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000202 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SCE | 2026 | 2 | 87502
1020000203 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000204 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000205 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000206 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000207 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. |  | SCE | 2026 | 2 | 1634.4462
1020000208 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility | SCE Dist Aerial inspections completed using drone. Aerial only used for "Hard To Access" structures. SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspection |  | SCE | 2026 | 2 | 0
1020000209 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000210 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. |  | SCE | 2026 | 2 | 1636.3446
1020000211 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000212 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility | SCE's Dist IR Scan uses Aerial (helicopter) for HFTD "Hard to Access" structures only. SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requ |  | SCE | 2026 | 2 | 0
1020000213 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000214 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. |  | SCE | 2026 | 2 | 2095
1020000215 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000216 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000217 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000218 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000219 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000220 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000221 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000222 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 63
1020000223 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000224 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000225 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000226 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 1
1020000227 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000228 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000229 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000230 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000231 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 76
1020000232 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000233 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000234 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 12012
1020000235 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000236 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000237 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000238 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 10
1020000239 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000240 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000241 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000242 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000243 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000244 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000245 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000246 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 7740
1020000247 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000248 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000249 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000250 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000251 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000252 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000253 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000254 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000255 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE Dist Aerial completed in HFRA only | SCE | 2026 | 2
1020000256 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | SCE Dist Aerial inspections completed using drone. Aerial only used for "Hard To Access" structures. | SCE Dist Aerial inspections completed using drone. Aerial only used for "Hard To Access" structures. | SCE | 2026 | 2
1020000257 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000258 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000259 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000260 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE's Dist IR Scan uses Aerial (helicopter) for HFTD "Hard to Access" structures only. | SCE | 2026 | 2
1020000261 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000262 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000263 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000264 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000265 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000266 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000267 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | SCE Dist Aerial completed in HFRA only | SCE | 2026 | 2
1020000268 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  | SCE Dist Aerial inspections completed using drone. Aerial only used for "Hard To Access" structures. | SCE | 2026 | 2
1020000269 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000270 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000271 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000272 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000273 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000274 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000275 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000276 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000277 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000278 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000279 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000280 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000281 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000282 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000283 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000284 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000285 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000286 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000287 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000288 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000289 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000290 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000291 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000292 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000293 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000294 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000295 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000296 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000297 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000298 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000299 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000300 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000301 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000302 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000303 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000304 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000305 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000306 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000307 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000308 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000309 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000310 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000311 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000312 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000313 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000314 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000315 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SCE | 2026 | 2 | 7264
1020000316 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | SCE Trans Detailed inspections use Aerial (helicopter) for "Hard to Access" structures only. |  | SCE | 2026 | 2 | 0
1020000317 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000318 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SCE | 2026 | 2 | 5962
1020000319 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000320 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SCE | 2026 | 2 | 823
1020000321 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000322 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000323 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000324 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000325 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000326 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000327 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. |  | SCE | 2026 | 2 | 862.4198
1020000328 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility | SCE Trans Detailed inspections use Aerial (helicopter) for "Hard to Access" structures only. SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. |  | SCE | 2026 | 2 | 0
1020000329 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000330 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. |  | SCE | 2026 | 2 | 707.8396
1020000331 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000332 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. |  | SCE | 2026 | 2 | 18
1020000333 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000334 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000335 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000336 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000337 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000338 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000339 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000340 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000341 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000342 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000343 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000344 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000345 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000346 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000347 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000348 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000349 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000350 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000351 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 130
1020000352 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000353 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000354 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 245
1020000355 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000356 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000357 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000358 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000359 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000360 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000361 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000362 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000363 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000364 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000365 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000366 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 278
1020000367 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000368 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000369 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000370 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000371 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000372 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000373 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000374 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000375 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SCE | 2026 | 2 | 5413
1020000376 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | SCE Trans Detailed inspections use Aerial (helicopter) for "Hard to Access" structures only. |  | SCE | 2026 | 2 | 0
1020000377 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000378 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SCE | 2026 | 2 | 6381
1020000379 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000380 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SCE | 2026 | 2 | 6939
1020000381 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000382 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000383 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000384 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000385 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000386 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000387 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. |  | SCE | 2026 | 2 | 642.6595
1020000388 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility | SCE Trans Detailed inspections use Aerial (helicopter) for "Hard to Access" structures only. SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in th |  | SCE | 2026 | 2 | 0
1020000389 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000390 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. |  | SCE | 2026 | 2 | 757.5855
1020000391 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000392 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility | SCE tracks completed inspections by tracking the counts of assets inspected instead of tracking by circuit miles. In order to present completed inspections in the requested format, SCE used a calculated average span length multiplied by the number of structures inspected. |  | SCE | 2026 | 2 | 530
1020000393 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000394 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000395 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000396 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000397 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000398 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000399 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000400 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000401 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000402 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000403 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000404 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000405 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000406 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000407 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000408 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000409 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000410 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000411 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 50
1020000412 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000413 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000414 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 122
1020000415 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000416 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000417 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000418 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000419 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000420 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000421 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000422 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000423 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000424 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000425 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000426 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 275
1020000427 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000428 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000429 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000430 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | SCE | 2026 | 2 | 0
1020000431 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000432 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000433 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000434 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000435 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE Trans Aerial inspection is HFTD only | SCE | 2026 | 2
1020000436 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE Trans Aerial inspection is HFTD only | SCE | 2026 | 2
1020000437 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000438 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000439 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000440 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE Trans IR scan is HFTD only | SCE | 2026 | 2
1020000441 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000442 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000443 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000444 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000445 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000446 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000447 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | SCE Trans Aerial inspection is HFTD only | SCE | 2026 | 2
1020000448 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  | SCE Trans Aerial inspection is HFTD only | SCE | 2026 | 2
1020000449 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000450 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000451 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000452 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | SCE Trans IR scan is HFTD only | SCE | 2026 | 2
1020000453 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000454 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000455 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000456 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000457 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000458 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000459 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000460 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000461 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000462 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000463 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000464 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000465 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000466 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000467 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000468 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000469 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000470 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000471 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000472 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000473 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000474 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000475 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000476 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000477 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000478 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000479 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000480 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000481 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000482 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000483 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000484 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000485 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000486 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000487 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000488 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000489 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | SCE does not track this inspection type by this inspection method. | SCE | 2026 | 2
1020000490 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000491 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000492 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000493 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000494 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000495 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000496 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000497 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000498 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 44
1020000499 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000500 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000501 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000502 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000503 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000504 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000505 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000506 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000507 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 45
1020000508 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000509 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000510 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 5274
1020000511 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000512 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000513 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000514 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 5
1020000515 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000516 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000517 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000518 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000519 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 1
1020000520 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000521 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000522 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 2494
1020000523 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000524 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000525 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000526 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000527 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000528 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000529 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000530 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000531 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000532 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000533 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000534 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 64
1020000535 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000536 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000537 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000538 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 1
1020000539 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000540 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000541 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000542 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000543 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 85
1020000544 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000545 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000546 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 9951
1020000547 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000548 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000549 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000550 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 2
1020000551 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000552 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000553 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000554 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000555 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 8
1020000556 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000557 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000558 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 3832
1020000559 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000560 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000561 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000562 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000563 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000564 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000565 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000566 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000567 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000568 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000569 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000570 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000571 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000572 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000573 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000574 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000575 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000576 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000577 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000578 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000579 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000580 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000581 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000582 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000583 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000584 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000585 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000586 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000587 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000588 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000589 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000590 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000591 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000592 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000593 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000594 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000595 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000596 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000597 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000598 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000599 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000600 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000601 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000602 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000603 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000604 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000605 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000606 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000607 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000608 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000609 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000610 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000611 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000612 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000613 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000614 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000615 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 123
1020000616 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000617 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000618 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 102
1020000619 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000620 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000621 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000622 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000623 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000624 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000625 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000626 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000627 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 17
1020000628 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000629 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000630 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 45
1020000631 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000632 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000633 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000634 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000635 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000636 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000637 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000638 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000639 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000640 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000641 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000642 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000643 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000644 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000645 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000646 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000647 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000648 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000649 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000650 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000651 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 80
1020000652 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000653 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000654 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 77
1020000655 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000656 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000657 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000658 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 1
1020000659 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000660 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000661 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000662 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000663 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 36
1020000664 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000665 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000666 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 96
1020000667 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000668 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000669 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000670 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SCE | 2026 | 2 | 0
1020000671 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000672 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000673 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000674 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000675 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000676 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000677 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000678 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000679 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000680 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000681 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000682 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000683 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000684 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000685 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000686 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000687 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000688 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000689 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000690 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000691 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000692 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000693 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000694 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000695 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000696 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000697 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000698 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000699 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000700 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000701 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000702 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000703 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000704 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000705 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | SCE does not track this insepction type by this inspection method | SCE | 2026 | 2
1020000706 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  | Non-HFTD notifications are no longer tracked for QDR | SCE | 2026 | 2
1020000707 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000708 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000709 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000710 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SCE | 2026 | 2 | 73300
1020000711 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000712 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000713 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000714 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SCE | 2026 | 2 | 649
1020000715 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000716 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000717 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000718 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SCE | 2026 | 2 | 1
1020000719 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000720 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000721 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000722 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SCE | 2026 | 2 | 851
1020000723 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000724 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000725 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000726 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SCE | 2026 | 2 | 154094
1020000727 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000728 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000729 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000730 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SCE | 2026 | 2 | 1495
1020000731 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000732 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000733 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000734 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SCE | 2026 | 2 | 2
1020000735 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000736 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000737 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000738 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SCE | 2026 | 2 | 1686
1020000739 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000740 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000741 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000742 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SCE | 2026 | 2 | 223301
1020000743 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000744 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000745 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000746 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SCE | 2026 | 2 | 5718
1020000747 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000748 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000749 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000750 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SCE | 2026 | 2 | 6
1020000751 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000752 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000753 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000754 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SCE | 2026 | 2 | 2534
1020000755 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000756 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000757 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000758 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SCE | 2026 | 2 | 15232
1020000759 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000760 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000761 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000762 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SCE | 2026 | 2 | 17
1020000763 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000764 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000765 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000766 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SCE | 2026 | 2 | 0
1020000767 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000768 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000769 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000770 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SCE | 2026 | 2 | 126
1020000771 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000772 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000773 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000774 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SCE | 2026 | 2 | 17655
1020000775 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000776 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000777 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000778 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SCE | 2026 | 2 | 7
1020000779 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000780 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000781 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000782 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SCE | 2026 | 2 | 2
1020000783 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000784 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000785 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000786 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SCE | 2026 | 2 | 394
1020000787 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000788 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000789 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000790 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SCE | 2026 | 2 | 23367
1020000791 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000792 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000793 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000794 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SCE | 2026 | 2 | 55
1020000795 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000796 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000797 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000798 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SCE | 2026 | 2 | 1
1020000799 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000800 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000801 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | SCE does not track Veg inspections using Drone, Aerial, or LiDAR. | SCE | 2026 | 2
1020000802 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SCE | 2026 | 2 | 514
1020000803 | Community outreach metrics | % of customers notified of evacuation in evacuation zone of a utility-ignited wildfire | [5 empty] | Percentage of customers notified of evacuation | SCE has no jurisdiction over evacuation orders. SCE diligently requested and followed up with local governments and law enforcement, and was only able to obtain information from one county. Even then, the information provided included high-level estimations of evacuation counts estimated by the local government and law enforcement entity for a limited amount of fires. Because of this, SCE is unable to obtain the requested data, analyze it, and report on evacuation related requirements in this table. SCE anticipates this to be a recurring challenge going forward. | SCE does not track this metric. | SCE | 2026 | 2

## Table 3
METRIC NUMBER | METRIC | DEFINITION | PURPOSE | ASSUMPTIONS MADE TO CONNECT METRIC TO PURPOSE | THIRD-PARTY VALIDATION (IF ANY) | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1030000000 | 1. Number of CPUC reportable ignitions in HFRA | Count of the number of CPUC reportable ignitions in HFRA | To measure changes in rate of ignitions between years | Factors outside of SCE's control (e.g., wind, live fuel moisture) have a significant effect on CPUC reportable ignition counts in HFRA. | Annual submission of CPUC reportable ignition totals to CPUC | # of ignitions |  |  | SCE | 2026 | 2 | 7
1030000001 | 2. Number of wire downs in HFRA | Count of the number of wire downs in HFRA | To measure changes in rate of wire down events which are a pre-cursor both ignition and safety events | Number of wire down incidents in HFRA based on cause. These metrics may help to provide insight on controllable and uncontrollable risks or help plan future activities to focus on a particular type of fault or outage that may be of wildfire risk. | Deep-dive audits of select portions of utility grid | # of wiredowns |  |  | SCE | 2026 | 2 | 36
1030000002 | 3. Number of outages in HFRA | Count of the number of outages in HFRA | To measure changes in rate of fault events which are a pre-cursor both ignition and safety events. | Number of faults in HFRA based on cause. These metrics may help to provide insight on controllable and uncontrollable risks or help plan future activities to focus on a particular type of fault or outage that may be of wildfire risk. | Deep-dive audits of select portions of utility grid | # of outages |  |  | SCE | 2026 | 2 | 670
1030000003 | 4. # of asset management ignition risk-related work orders that are past due (excluding GO95 exceptions) | Count of the total past due T&D ignition risk work orders, excluding GO95 exceptions | To meaure the past due asset-related work orders that have ignition risk and are not subject to GO95 exceptions | This metric will help track past due work order that are related to wildfire risk mitigation and that are largely within the utility's control for addressing. |  | # of work orders |  |  | SCE | 2026 | 2 | 705
1030000004 | 5. Number of Tree-Caused Circuit Interruptions (TCCIs) in HFRA (ODRM data) | Count of TCCIs in HFRA | To measure trends in how vegetation is causing risk events when contacting overhead circuitry in HFRA | Vegetation that comes into contact with energized circuits can cause a circuit interruption (e.g., fault), however there may be cases with vegetation comes into contact with SCE infrastructure and no fault occurs. |  | # of interruptions |  |  | SCE | 2026 | 2 | 2
1030000005 | 6. Number of trees inspected where at least some vegetation was found in a non-compliant condition in HFRA - Routine | Count of instances in HFRA where vegetation found in non-compliant condition through Routine Line Clearing programs | To meaure the extent to which vegetation exists in non-compliant condition | Routine Line Clearing activities will identify instances in which vegetation exists in a non-compliant condition |  | # of trees |  |  | SCE | 2026 | 2 | 3057
1030000006 | 7. Frequency of PSPS events (total) | Count of PSPS events in which de-energization has occurred | To measure trends in how many de-energization events occur each year | Metric does not account for the normalization of weather, fuel conditions, etc., year over year. Actual performance in each year will be driven by weather and fuel conditions experienced in those years and may vary from prior year and future year projected figures. | CPUC compliance reporting (e.g., PSPS Post-Event Reports, Post Season Reports) | # of events | SCE uses a 2020-2022 PSPS event average to forecast 2023-2025 events. SCE does not forecast a reduction in events from the 2020-2022 average as overall circuit scope reduction may not reduce event count |  | SCE | 2026 | 2 | 2
1030000007 | 8. Scope of PSPS events (total) | Count of circuit de-energized | To meaure trends in how may circuits are de-energized due to PSPS events | Metric does not account for the normalization of weather, fuel conditions, etc., year over year. Actual performance in each year will be driven by weather and fuel conditions experienced in those years and may vary from prior year and future year projected figures. | CPUC compliance reporting (e.g., PSPS Post-Event Reports, Post Season Reports) | # of circuits | Forecast reductions are derived from applying SCE's 2023 reduction forecast to 2020-2022 averages across each future year. |  | SCE | 2026 | 2 | 7
1030000008 | 9. Duration of PSPS (total) | Customer hours de-energized due to PSPS | To measure trends in the amount of customer hours de-energized due to PSPS | Metric does not account for the normalization of weather, fuel conditions, etc., year over year. Actual performance in each year will be driven by weather and fuel conditions experienced in those years and may vary from prior year and future year projected figures. | CPUC compliance reporting (e.g., PSPS Post-Event Reports, Post Season Reports) | # of hours | Forecast reductions are derived from applying SCE's 2023 reduction forecast to 2020-2022 averages across each future year. |  | SCE | 2026 | 2 | 13085.28
1030000009 | 10. # of customers impacted by PSPS | Count of customers de-enrgized due to PSPS | To measure trends in the number of customers de-energized due to PSPS | Metric does not account for the normalization of weather, fuel conditions, etc., year over year. Actual performance in each year will be driven by weather and fuel conditions experienced in those years and may vary from prior year and future year projected figures. | CPUC compliance reporting (e.g., PSPS Post-Event Reports, Post Season Reports) | # of customers | Forecast reductions are derived from applying SCE's 2023 reduction forecast to 2020-2022 averages across each future year. |  | SCE | 2026 | 2 | 750
1030000010 | 11a. Customer recall of SCE wildfire and preparedness communications - System Wide | The percentage of surveyed customers across SCE's service area who responded that they recalled communications from SCE about the threat of wildfire and how they can prepare for them. | To help measure the effectiveness of its community outreach and engagement activities by measuring customer awareness of SCE’s wildfire messaging and customer wildfire and PSPS programs and services. | Results can be impacted by volume of PSPS events experienced per year, level of marketing and outreach to customers, severity of fire season, and other factors. | In-Language Wildfire Mitigation / PSPS Communications Effectiveness Survey | % | The survey that generates these results is performed twice annually, once once toward the start of Q3 and once toward the end of Q4. Therefore, figures are not provided for Q1 or Q2. |  | SCE | 2026 | 2 | 0
1030000011 | 11b. Customer recall of SCE wildfire and preparedness communications - HFRA only | The percentage of surveyed customers across SCE's HFRA who responded that they recalled communications from SCE about the threat of wildfire and how they can prepare for them. | To help measure the effectiveness of its community outreach and engagement activities by measuring customer awareness of SCE’s wildfire messaging and customer wildfire and PSPS programs and services. | Results can be impacted by volume of PSPS events experienced per year, level of marketing and outreach to customers, severity of fire season, and other factors. | In-Language Wildfire Mitigation / PSPS Communications Effectiveness Survey | % | The survey that generates these results is performed twice annually, once once toward the start of Q3 and once toward the end of Q4. Therefore, figures are not provided for Q1 or Q2. |  | SCE | 2026 | 2 | 0

## Table 4
METRIC NUMBER | METRIC TYPE | METRIC NAME | LINE TYPE | HFTD TIER | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1040000000 | Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | HFTD Tier 2 | Red flag warning overhead circuit mile days |  |  | SCE | 2026 | 2 | 976.9253
1040000001 | Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | HFTD Tier 3 | Red flag warning overhead circuit mile days |  |  | SCE | 2026 | 2 | 893.8422
1040000002 | Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | Non-HFTD | Red flag warning overhead circuit mile days |  |  | SCE | 2026 | 2 | 30729.321
1040000003 | Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | HFTD Tier 2 | Red flag warning overhead circuit mile days |  |  | SCE | 2026 | 2 | 524.6307
1040000004 | Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | HFTD Tier 3 | Red flag warning overhead circuit mile days |  |  | SCE | 2026 | 2 | 163.033
1040000005 | Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | Non-HFTD | Red flag warning overhead circuit mile days |  |  | SCE | 2026 | 2 | 10042.8944
1040000006 | Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | HFTD Tier 2 | High Wind Warning overhead circuit mile days |  |  | SCE | 2026 | 2 | 765.7343
1040000007 | Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | HFTD Tier 3 | High Wind Warning overhead circuit mile days |  |  | SCE | 2026 | 2 | 395.041
1040000008 | Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | Non-HFTD | High Wind Warning overhead circuit mile days |  |  | SCE | 2026 | 2 | 2799.4774
1040000009 | Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | HFTD Tier 2 | High Wind Warning overhead circuit mile days |  |  | SCE | 2026 | 2 | 978.9445
1040000010 | Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | HFTD Tier 3 | High Wind Warning overhead circuit mile days |  |  | SCE | 2026 | 2 | 304.4492
1040000011 | Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | Non-HFTD | High Wind Warning overhead circuit mile days |  |  | SCE | 2026 | 2 | 2532.9005
1040000012 | Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | HFTD Tier 2 | High wind warning and red flag warning overhead circuit mile days |  |  | SCE | 2026 | 2 | 216.3667
1040000013 | Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | HFTD Tier 3 | High wind warning and red flag warning overhead circuit mile days |  |  | SCE | 2026 | 2 | 214.0776
1040000014 | Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | Non-HFTD | High wind warning and red flag warning overhead circuit mile days |  |  | SCE | 2026 | 2 | 2628.6331
1040000015 | Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | HFTD Tier 2 | High wind warning and red flag warning overhead circuit mile days |  |  | SCE | 2026 | 2 | 165.2025
1040000016 | Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | HFTD Tier 3 | High wind warning and red flag warning overhead circuit mile days |  |  | SCE | 2026 | 2 | 121.2417
1040000017 | Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | Non-HFTD | High wind warning and red flag warning overhead circuit mile days |  |  | SCE | 2026 | 2 | 1054.5084
1040000018 | Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | HFTD Tier 2 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | SCE | 2026 | 2 | 8388.9266
1040000019 | Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | HFTD Tier 3 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | SCE | 2026 | 2 | 10680.2274
1040000020 | Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | Non-HFTD | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | SCE | 2026 | 2 | 2730.978
1040000021 | Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | HFTD Tier 2 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | SCE | 2026 | 2 | 3675.1115
1040000022 | Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | HFTD Tier 3 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | SCE | 2026 | 2 | 2950.2051
1040000023 | Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | Non-HFTD | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | SCE | 2026 | 2 | 0.0042556

## Table 5
METRIC NUMBER | METRIC TYPE | METRIC NAME | RISK EVENT DRIVER | LINE TYPE | HFTD TIER | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1050000000 | Fire | Wire down event | Fire | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 15
1050000001 | Fire | Wire down event | Fire | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 1
1050000002 | Fire | Wire down event | Fire | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000003 | Fire | Wire down event | Fire | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000004 | Fire | Wire down event | Fire | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000005 | Fire | Wire down event | Fire | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000006 | Contact from object | Wire down event | Animal contact | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 14
1050000007 | Contact from object | Wire down event | Animal contact | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000008 | Contact from object | Wire down event | Animal contact | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000009 | Contact from object | Wire down event | Animal contact | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000010 | Contact from object | Wire down event | Animal contact | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000011 | Contact from object | Wire down event | Animal contact | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000012 | Contact from object | Wire down event | Balloon contact | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 12
1050000013 | Contact from object | Wire down event | Balloon contact | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000014 | Contact from object | Wire down event | Balloon contact | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000015 | Contact from object | Wire down event | Balloon contact | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000016 | Contact from object | Wire down event | Balloon contact | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000017 | Contact from object | Wire down event | Balloon contact | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000018 | Contact from object | Wire down event | Land vehicle contact | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 79
1050000019 | Contact from object | Wire down event | Land vehicle contact | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 6
1050000020 | Contact from object | Wire down event | Land vehicle contact | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 5
1050000021 | Contact from object | Wire down event | Land vehicle contact | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000022 | Contact from object | Wire down event | Land vehicle contact | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000023 | Contact from object | Wire down event | Land vehicle contact | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000024 | Contact from object | Wire down event | Aircraft vehicle contact | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000025 | Contact from object | Wire down event | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000026 | Contact from object | Wire down event | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000027 | Contact from object | Wire down event | Aircraft vehicle contact | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000028 | Contact from object | Wire down event | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000029 | Contact from object | Wire down event | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000030 | Contact from object | Wire down event | 3rd party contact | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 7
1050000031 | Contact from object | Wire down event | 3rd party contact | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000032 | Contact from object | Wire down event | 3rd party contact | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 1
1050000033 | Contact from object | Wire down event | 3rd party contact | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000034 | Contact from object | Wire down event | 3rd party contact | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000035 | Contact from object | Wire down event | 3rd party contact | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000036 | Contact from object | Wire down event | Other (contact from object) | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 9
1050000037 | Contact from object | Wire down event | Other (contact from object) | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000038 | Contact from object | Wire down event | Other (contact from object) | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000039 | Contact from object | Wire down event | Other (contact from object) | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000040 | Contact from object | Wire down event | Other (contact from object) | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000041 | Contact from object | Wire down event | Other (contact from object) | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000042 | Contact from object | Wire down event | Unknown (contact from object) | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000043 | Contact from object | Wire down event | Unknown (contact from object) | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000044 | Contact from object | Wire down event | Unknown (contact from object) | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000045 | Contact from object | Wire down event | Unknown (contact from object) | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000046 | Contact from object | Wire down event | Unknown (contact from object) | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000047 | Contact from object | Wire down event | Unknown (contact from object) | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000048 | Vegetation contact | Wire down event | Uncategorized / other (vegetation contact) | Distribution | Non-HFTD | # risk events | A portion of this data may include "Unknown" HFTD. |  | SCE | 2026 | 2 | 9
1050000049 | Vegetation contact | Wire down event | Uncategorized / other (vegetation contact) | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 2
1050000050 | Vegetation contact | Wire down event | Uncategorized / other (vegetation contact) | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 8
1050000051 | Vegetation contact | Wire down event | Uncategorized / other (vegetation contact) | Transmission | Non-HFTD | # risk events | A portion of this data may include "Unknown" HFTD. |  | SCE | 2026 | 2 | 0
1050000052 | Vegetation contact | Wire down event | Uncategorized / other (vegetation contact) | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000053 | Vegetation contact | Wire down event | Uncategorized / other (vegetation contact) | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000054 | Vegetation contact | Wire down event | Grow-in | Distribution | Non-HFTD | # risk events | A portion of this data may include "Unknown" HFTD. |  | SCE | 2026 | 2 | 10
1050000055 | Vegetation contact | Wire down event | Grow-in | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000056 | Vegetation contact | Wire down event | Grow-in | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 1
1050000057 | Vegetation contact | Wire down event | Grow-in | Transmission | Non-HFTD | # risk events | A portion of this data may include "Unknown" HFTD. |  | SCE | 2026 | 2 | 0
1050000058 | Vegetation contact | Wire down event | Grow-in | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000059 | Vegetation contact | Wire down event | Grow-in | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000060 | Vegetation contact | Wire down event | Blow-in | Distribution | Non-HFTD | # risk events | A portion of this data may include "Unknown" HFTD. |  | SCE | 2026 | 2 | 1
1050000061 | Vegetation contact | Wire down event | Blow-in | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000062 | Vegetation contact | Wire down event | Blow-in | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000063 | Vegetation contact | Wire down event | Blow-in | Transmission | Non-HFTD | # risk events | A portion of this data may include "Unknown" HFTD. |  | SCE | 2026 | 2 | 0
1050000064 | Vegetation contact | Wire down event | Blow-in | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000065 | Vegetation contact | Wire down event | Blow-in | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000066 | Vegetation contact | Wire down event | Trunk failure | Distribution | Non-HFTD | # risk events | A portion of this data may include "Unknown" HFTD. |  | SCE | 2026 | 2 | 0
1050000067 | Vegetation contact | Wire down event | Trunk failure | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000068 | Vegetation contact | Wire down event | Trunk failure | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000069 | Vegetation contact | Wire down event | Trunk failure | Transmission | Non-HFTD | # risk events | A portion of this data may include "Unknown" HFTD. |  | SCE | 2026 | 2 | 0
1050000070 | Vegetation contact | Wire down event | Trunk failure | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000071 | Vegetation contact | Wire down event | Trunk failure | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000072 | Vegetation contact | Wire down event | Root failure | Distribution | Non-HFTD | # risk events | A portion of this data may include "Unknown" HFTD. |  | SCE | 2026 | 2 | 0
1050000073 | Vegetation contact | Wire down event | Root failure | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000074 | Vegetation contact | Wire down event | Root failure | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000075 | Vegetation contact | Wire down event | Root failure | Transmission | Non-HFTD | # risk events | A portion of this data may include "Unknown" HFTD. |  | SCE | 2026 | 2 | 0
1050000076 | Vegetation contact | Wire down event | Root failure | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000077 | Vegetation contact | Wire down event | Root failure | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000078 | Vegetation contact | Wire down event | Detached frond / limb / bark | Distribution | Non-HFTD | # risk events | A portion of this data may include "Unknown" HFTD. |  | SCE | 2026 | 2 | 6
1050000079 | Vegetation contact | Wire down event | Detached frond / limb / bark | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000080 | Vegetation contact | Wire down event | Detached frond / limb / bark | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000081 | Vegetation contact | Wire down event | Detached frond / limb / bark | Transmission | Non-HFTD | # risk events | A portion of this data may include "Unknown" HFTD. |  | SCE | 2026 | 2 | 0
1050000082 | Vegetation contact | Wire down event | Detached frond / limb / bark | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000083 | Vegetation contact | Wire down event | Detached frond / limb / bark | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000084 | Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 1
1050000085 | Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000086 | Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000087 | Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000088 | Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000089 | Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000090 | Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000091 | Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000092 | Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000093 | Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000094 | Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000095 | Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000096 | Equipment / facility failure or damage | Wire down event | Conductor | Distribution | Non-HFTD | # risk events | A portion of this data may include "Unknown" HFTD. |  | SCE | 2026 | 2 | 24
1050000097 | Equipment / facility failure or damage | Wire down event | Conductor | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 3
1050000098 | Equipment / facility failure or damage | Wire down event | Conductor | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 1
1050000099 | Equipment / facility failure or damage | Wire down event | Conductor | Transmission | Non-HFTD | # risk events | A portion of this data may include "Unknown" HFTD. |  | SCE | 2026 | 2 | 0
1050000100 | Equipment / facility failure or damage | Wire down event | Conductor | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000101 | Equipment / facility failure or damage | Wire down event | Conductor | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000102 | Equipment / facility failure or damage | Wire down event | Connection device | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 19
1050000103 | Equipment / facility failure or damage | Wire down event | Connection device | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 2
1050000104 | Equipment / facility failure or damage | Wire down event | Connection device | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 2
1050000105 | Equipment / facility failure or damage | Wire down event | Connection device | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000106 | Equipment / facility failure or damage | Wire down event | Connection device | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000107 | Equipment / facility failure or damage | Wire down event | Connection device | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000108 | Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 2
1050000109 | Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000110 | Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000111 | Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000112 | Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000113 | Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000114 | Equipment / facility failure or damage | Wire down event | Fuse | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000115 | Equipment / facility failure or damage | Wire down event | Fuse | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000116 | Equipment / facility failure or damage | Wire down event | Fuse | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000117 | Equipment / facility failure or damage | Wire down event | Fuse | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000118 | Equipment / facility failure or damage | Wire down event | Fuse | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000119 | Equipment / facility failure or damage | Wire down event | Fuse | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000120 | Equipment / facility failure or damage | Wire down event | Cutout | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000121 | Equipment / facility failure or damage | Wire down event | Cutout | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000122 | Equipment / facility failure or damage | Wire down event | Cutout | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000123 | Equipment / facility failure or damage | Wire down event | Cutout | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000124 | Equipment / facility failure or damage | Wire down event | Cutout | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000125 | Equipment / facility failure or damage | Wire down event | Cutout | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000126 | Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 1
1050000127 | Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000128 | Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000129 | Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000130 | Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000131 | Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000132 | Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 1
1050000133 | Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000134 | Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000135 | Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000136 | Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000137 | Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000138 | Equipment / facility failure or damage | Wire down event | Pole | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000139 | Equipment / facility failure or damage | Wire down event | Pole | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000140 | Equipment / facility failure or damage | Wire down event | Pole | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000141 | Equipment / facility failure or damage | Wire down event | Pole | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000142 | Equipment / facility failure or damage | Wire down event | Pole | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 1
1050000143 | Equipment / facility failure or damage | Wire down event | Pole | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000144 | Equipment / facility failure or damage | Wire down event | Recloser | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000145 | Equipment / facility failure or damage | Wire down event | Recloser | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000146 | Equipment / facility failure or damage | Wire down event | Recloser | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000147 | Equipment / facility failure or damage | Wire down event | Recloser | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000148 | Equipment / facility failure or damage | Wire down event | Recloser | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000149 | Equipment / facility failure or damage | Wire down event | Recloser | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000150 | Equipment / facility failure or damage | Wire down event | Relay | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000151 | Equipment / facility failure or damage | Wire down event | Relay | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000152 | Equipment / facility failure or damage | Wire down event | Relay | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000153 | Equipment / facility failure or damage | Wire down event | Relay | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000154 | Equipment / facility failure or damage | Wire down event | Relay | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000155 | Equipment / facility failure or damage | Wire down event | Relay | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000156 | Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000157 | Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000158 | Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000159 | Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000160 | Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000161 | Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000162 | Equipment / facility failure or damage | Wire down event | Splice | Distribution | Non-HFTD | # risk events | A portion of this data may include "Unknown" HFTD. |  | SCE | 2026 | 2 | 2
1050000163 | Equipment / facility failure or damage | Wire down event | Splice | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 2
1050000164 | Equipment / facility failure or damage | Wire down event | Splice | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 1
1050000165 | Equipment / facility failure or damage | Wire down event | Splice | Transmission | Non-HFTD | # risk events | A portion of this data may include "Unknown" HFTD. |  | SCE | 2026 | 2 | 0
1050000166 | Equipment / facility failure or damage | Wire down event | Splice | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000167 | Equipment / facility failure or damage | Wire down event | Splice | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000168 | Equipment / facility failure or damage | Wire down event | Switch | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000169 | Equipment / facility failure or damage | Wire down event | Switch | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000170 | Equipment / facility failure or damage | Wire down event | Switch | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000171 | Equipment / facility failure or damage | Wire down event | Switch | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000172 | Equipment / facility failure or damage | Wire down event | Switch | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000173 | Equipment / facility failure or damage | Wire down event | Switch | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000174 | Equipment / facility failure or damage | Wire down event | Tap | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000175 | Equipment / facility failure or damage | Wire down event | Tap | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000176 | Equipment / facility failure or damage | Wire down event | Tap | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000177 | Equipment / facility failure or damage | Wire down event | Tap | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000178 | Equipment / facility failure or damage | Wire down event | Tap | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000179 | Equipment / facility failure or damage | Wire down event | Tap | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000180 | Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000181 | Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000182 | Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000183 | Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000184 | Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000185 | Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000186 | Equipment / facility failure or damage | Wire down event | Transformer | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000187 | Equipment / facility failure or damage | Wire down event | Transformer | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000188 | Equipment / facility failure or damage | Wire down event | Transformer | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000189 | Equipment / facility failure or damage | Wire down event | Transformer | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000190 | Equipment / facility failure or damage | Wire down event | Transformer | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000191 | Equipment / facility failure or damage | Wire down event | Transformer | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000192 | Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000193 | Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000194 | Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000195 | Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000196 | Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000197 | Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000198 | Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000199 | Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000200 | Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000201 | Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000202 | Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000203 | Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000204 | Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 3
1050000205 | Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000206 | Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000207 | Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000208 | Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000209 | Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000210 | Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 4
1050000211 | Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000212 | Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000213 | Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000214 | Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000215 | Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000216 | Contamination | Wire down event | Contamination | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000217 | Contamination | Wire down event | Contamination | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000218 | Contamination | Wire down event | Contamination | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000219 | Contamination | Wire down event | Contamination | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000220 | Contamination | Wire down event | Contamination | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000221 | Contamination | Wire down event | Contamination | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000222 | Vandalism / theft | Wire down event | Vandalism / theft | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 7
1050000223 | Vandalism / theft | Wire down event | Vandalism / theft | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000224 | Vandalism / theft | Wire down event | Vandalism / theft | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000225 | Vandalism / theft | Wire down event | Vandalism / theft | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 1
1050000226 | Vandalism / theft | Wire down event | Vandalism / theft | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000227 | Vandalism / theft | Wire down event | Vandalism / theft | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000228 | Lightning | Wire down event | Lightning | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000229 | Lightning | Wire down event | Lightning | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000230 | Lightning | Wire down event | Lightning | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000231 | Lightning | Wire down event | Lightning | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000232 | Lightning | Wire down event | Lightning | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000233 | Lightning | Wire down event | Lightning | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000234 | Unknown | Wire down event | Unknown (unknown) | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 3
1050000235 | Unknown | Wire down event | Unknown (unknown) | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000236 | Unknown | Wire down event | Unknown (unknown) | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000237 | Unknown | Wire down event | Unknown (unknown) | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000238 | Unknown | Wire down event | Unknown (unknown) | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000239 | Unknown | Wire down event | Unknown (unknown) | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000240 | Other | Wire down event | Other (other) | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 3
1050000241 | Other | Wire down event | Other (other) | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000242 | Other | Wire down event | Other (other) | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000243 | Other | Wire down event | Other (other) | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000244 | Other | Wire down event | Other (other) | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000245 | Other | Wire down event | Other (other) | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000246 | Dig-in | Unplanned Outage | Dig-in | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 16
1050000247 | Dig-in | Unplanned Outage | Dig-in | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 2
1050000248 | Dig-in | Unplanned Outage | Dig-in | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 2
1050000249 | Dig-in | Unplanned Outage | Dig-in | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000250 | Dig-in | Unplanned Outage | Dig-in | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000251 | Dig-in | Unplanned Outage | Dig-in | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000252 | Fire | Unplanned Outage | Fire | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 28
1050000253 | Fire | Unplanned Outage | Fire | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 3
1050000254 | Fire | Unplanned Outage | Fire | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 3
1050000255 | Fire | Unplanned Outage | Fire | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 2
1050000256 | Fire | Unplanned Outage | Fire | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000257 | Fire | Unplanned Outage | Fire | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000258 | Contact from object | Unplanned Outage | Animal contact | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 164
1050000259 | Contact from object | Unplanned Outage | Animal contact | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 20
1050000260 | Contact from object | Unplanned Outage | Animal contact | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 46
1050000261 | Contact from object | Unplanned Outage | Animal contact | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 6
1050000262 | Contact from object | Unplanned Outage | Animal contact | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000263 | Contact from object | Unplanned Outage | Animal contact | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000264 | Contact from object | Unplanned Outage | Balloon contact | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 164
1050000265 | Contact from object | Unplanned Outage | Balloon contact | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 2
1050000266 | Contact from object | Unplanned Outage | Balloon contact | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 4
1050000267 | Contact from object | Unplanned Outage | Balloon contact | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 2
1050000268 | Contact from object | Unplanned Outage | Balloon contact | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000269 | Contact from object | Unplanned Outage | Balloon contact | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000270 | Contact from object | Unplanned Outage | Land vehicle contact | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 127
1050000271 | Contact from object | Unplanned Outage | Land vehicle contact | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 10
1050000272 | Contact from object | Unplanned Outage | Land vehicle contact | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 9
1050000273 | Contact from object | Unplanned Outage | Land vehicle contact | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 5
1050000274 | Contact from object | Unplanned Outage | Land vehicle contact | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000275 | Contact from object | Unplanned Outage | Land vehicle contact | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000276 | Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000277 | Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000278 | Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000279 | Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000280 | Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000281 | Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000282 | Contact from object | Unplanned Outage | 3rd party contact | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 17
1050000283 | Contact from object | Unplanned Outage | 3rd party contact | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000284 | Contact from object | Unplanned Outage | 3rd party contact | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000285 | Contact from object | Unplanned Outage | 3rd party contact | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000286 | Contact from object | Unplanned Outage | 3rd party contact | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000287 | Contact from object | Unplanned Outage | 3rd party contact | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000288 | Contact from object | Unplanned Outage | Other (contact from object) | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 38
1050000289 | Contact from object | Unplanned Outage | Other (contact from object) | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 3
1050000290 | Contact from object | Unplanned Outage | Other (contact from object) | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 3
1050000291 | Contact from object | Unplanned Outage | Other (contact from object) | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 1
1050000292 | Contact from object | Unplanned Outage | Other (contact from object) | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000293 | Contact from object | Unplanned Outage | Other (contact from object) | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000294 | Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000295 | Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000296 | Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000297 | Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000298 | Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000299 | Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000300 | Vegetation contact | Unplanned Outage | Uncategorized / other (vegetation contact) | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000301 | Vegetation contact | Unplanned Outage | Uncategorized / other (vegetation contact) | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000302 | Vegetation contact | Unplanned Outage | Uncategorized / other (vegetation contact) | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000303 | Vegetation contact | Unplanned Outage | Uncategorized / other (vegetation contact) | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000304 | Vegetation contact | Unplanned Outage | Uncategorized / other (vegetation contact) | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000305 | Vegetation contact | Unplanned Outage | Uncategorized / other (vegetation contact) | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000306 | Vegetation contact | Unplanned Outage | Grow-in | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 6
1050000307 | Vegetation contact | Unplanned Outage | Grow-in | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000308 | Vegetation contact | Unplanned Outage | Grow-in | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 1
1050000309 | Vegetation contact | Unplanned Outage | Grow-in | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000310 | Vegetation contact | Unplanned Outage | Grow-in | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000311 | Vegetation contact | Unplanned Outage | Grow-in | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000312 | Vegetation contact | Unplanned Outage | Blow-in | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 17
1050000313 | Vegetation contact | Unplanned Outage | Blow-in | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 1
1050000314 | Vegetation contact | Unplanned Outage | Blow-in | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 6
1050000315 | Vegetation contact | Unplanned Outage | Blow-in | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 1
1050000316 | Vegetation contact | Unplanned Outage | Blow-in | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000317 | Vegetation contact | Unplanned Outage | Blow-in | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000318 | Vegetation contact | Unplanned Outage | Trunk failure | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000319 | Vegetation contact | Unplanned Outage | Trunk failure | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000320 | Vegetation contact | Unplanned Outage | Trunk failure | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000321 | Vegetation contact | Unplanned Outage | Trunk failure | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000322 | Vegetation contact | Unplanned Outage | Trunk failure | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000323 | Vegetation contact | Unplanned Outage | Trunk failure | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000324 | Vegetation contact | Unplanned Outage | Root failure | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000325 | Vegetation contact | Unplanned Outage | Root failure | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000326 | Vegetation contact | Unplanned Outage | Root failure | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000327 | Vegetation contact | Unplanned Outage | Root failure | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000328 | Vegetation contact | Unplanned Outage | Root failure | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000329 | Vegetation contact | Unplanned Outage | Root failure | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000330 | Vegetation contact | Unplanned Outage | Detached frond / limb / bark | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000331 | Vegetation contact | Unplanned Outage | Detached frond / limb / bark | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000332 | Vegetation contact | Unplanned Outage | Detached frond / limb / bark | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000333 | Vegetation contact | Unplanned Outage | Detached frond / limb / bark | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000334 | Vegetation contact | Unplanned Outage | Detached frond / limb / bark | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000335 | Vegetation contact | Unplanned Outage | Detached frond / limb / bark | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000336 | Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 2
1050000337 | Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000338 | Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000339 | Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000340 | Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000341 | Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000342 | Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 7
1050000343 | Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000344 | Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000345 | Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000346 | Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000347 | Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000348 | Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 168
1050000349 | Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 20
1050000350 | Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 9
1050000351 | Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 4
1050000352 | Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000353 | Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000354 | Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 153
1050000355 | Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 23
1050000356 | Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 21
1050000357 | Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 2
1050000358 | Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000359 | Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000360 | Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 146
1050000361 | Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 8
1050000362 | Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 9
1050000363 | Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000364 | Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000365 | Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000366 | Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 163
1050000367 | Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 26
1050000368 | Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 25
1050000369 | Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000370 | Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000371 | Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000372 | Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000373 | Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000374 | Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000375 | Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000376 | Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000377 | Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000378 | Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 16
1050000379 | Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 4
1050000380 | Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000381 | Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 2
1050000382 | Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000383 | Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000384 | Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 18
1050000385 | Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 4
1050000386 | Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000387 | Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000388 | Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000389 | Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000390 | Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 65
1050000391 | Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 6
1050000392 | Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 12
1050000393 | Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 4
1050000394 | Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000395 | Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000396 | Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000397 | Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000398 | Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000399 | Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000400 | Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000401 | Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000402 | Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000403 | Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000404 | Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000405 | Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000406 | Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000407 | Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000408 | Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000409 | Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000410 | Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000411 | Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000412 | Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000413 | Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000414 | Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000415 | Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000416 | Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000417 | Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000418 | Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000419 | Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000420 | Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 19
1050000421 | Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 1
1050000422 | Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 3
1050000423 | Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 1
1050000424 | Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000425 | Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000426 | Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000427 | Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000428 | Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000429 | Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000430 | Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000431 | Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000432 | Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000433 | Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000434 | Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000435 | Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000436 | Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000437 | Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000438 | Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 292
1050000439 | Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 40
1050000440 | Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 56
1050000441 | Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000442 | Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000443 | Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000444 | Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000445 | Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000446 | Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000447 | Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000448 | Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000449 | Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000450 | Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000451 | Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000452 | Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000453 | Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000454 | Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000455 | Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000456 | Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 18
1050000457 | Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 8
1050000458 | Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 9
1050000459 | Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 4
1050000460 | Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000461 | Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000462 | Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 2
1050000463 | Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000464 | Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000465 | Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000466 | Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000467 | Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000468 | Contamination | Unplanned Outage | Contamination | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000469 | Contamination | Unplanned Outage | Contamination | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000470 | Contamination | Unplanned Outage | Contamination | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000471 | Contamination | Unplanned Outage | Contamination | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 4
1050000472 | Contamination | Unplanned Outage | Contamination | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000473 | Contamination | Unplanned Outage | Contamination | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000474 | Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 13
1050000475 | Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000476 | Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000477 | Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000478 | Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000479 | Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000480 | Lightning | Unplanned Outage | Lightning | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 9
1050000481 | Lightning | Unplanned Outage | Lightning | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000482 | Lightning | Unplanned Outage | Lightning | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 4
1050000483 | Lightning | Unplanned Outage | Lightning | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 1
1050000484 | Lightning | Unplanned Outage | Lightning | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000485 | Lightning | Unplanned Outage | Lightning | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000486 | Government agency request | Unplanned Outage | Government agency request | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 3
1050000487 | Government agency request | Unplanned Outage | Government agency request | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 2
1050000488 | Government agency request | Unplanned Outage | Government agency request | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 1
1050000489 | Government agency request | Unplanned Outage | Government agency request | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 1
1050000490 | Government agency request | Unplanned Outage | Government agency request | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000491 | Government agency request | Unplanned Outage | Government agency request | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000492 | Customer request | Unplanned Outage | Customer request | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000493 | Customer request | Unplanned Outage | Customer request | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000494 | Customer request | Unplanned Outage | Customer request | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000495 | Customer request | Unplanned Outage | Customer request | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 0
1050000496 | Customer request | Unplanned Outage | Customer request | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000497 | Customer request | Unplanned Outage | Customer request | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 0
1050000498 | Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 555
1050000499 | Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 66
1050000500 | Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 138
1050000501 | Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 9
1050000502 | Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 1
1050000503 | Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 2
1050000504 | Unknown | Unplanned Outage | Unknown (unknown) | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 279
1050000505 | Unknown | Unplanned Outage | Unknown (unknown) | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 34
1050000506 | Unknown | Unplanned Outage | Unknown (unknown) | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 29
1050000507 | Unknown | Unplanned Outage | Unknown (unknown) | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 40
1050000508 | Unknown | Unplanned Outage | Unknown (unknown) | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 1
1050000509 | Unknown | Unplanned Outage | Unknown (unknown) | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 4
1050000510 | Other | Unplanned Outage | Other (other) | Distribution | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 741
1050000511 | Other | Unplanned Outage | Other (other) | Distribution | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 70
1050000512 | Other | Unplanned Outage | Other (other) | Distribution | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 116
1050000513 | Other | Unplanned Outage | Other (other) | Transmission | Non-HFTD | # risk events |  |  | SCE | 2026 | 2 | 40
1050000514 | Other | Unplanned Outage | Other (other) | Transmission | HFTD Tier 2 | # risk events |  |  | SCE | 2026 | 2 | 7
1050000515 | Other | Unplanned Outage | Other (other) | Transmission | HFTD Tier 3 | # risk events |  |  | SCE | 2026 | 2 | 6

## Table 6
METRIC NUMBER | METRIC TYPE | IGNITION DRIVER | LINE TYPE | HFTD TIER | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1060000000 | Dig-in | Dig-in | Distribution | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000001 | Dig-in | Dig-in | Distribution | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000002 | Dig-in | Dig-in | Distribution | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000003 | Dig-in | Dig-in | Transmission | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000004 | Dig-in | Dig-in | Transmission | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000005 | Dig-in | Dig-in | Transmission | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000006 | Contact from object | Animal contact | Distribution | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 5
1060000007 | Contact from object | Animal contact | Distribution | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000008 | Contact from object | Animal contact | Distribution | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 3
1060000009 | Contact from object | Animal contact | Transmission | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 1
1060000010 | Contact from object | Animal contact | Transmission | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000011 | Contact from object | Animal contact | Transmission | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 2
1060000012 | Contact from object | Balloon contact | Distribution | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 4
1060000013 | Contact from object | Balloon contact | Distribution | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000014 | Contact from object | Balloon contact | Distribution | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000015 | Contact from object | Balloon contact | Transmission | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000016 | Contact from object | Balloon contact | Transmission | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 1
1060000017 | Contact from object | Balloon contact | Transmission | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000018 | Contact from object | Land vehicle contact | Distribution | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 2
1060000019 | Contact from object | Land vehicle contact | Distribution | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000020 | Contact from object | Land vehicle contact | Distribution | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000021 | Contact from object | Land vehicle contact | Transmission | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000022 | Contact from object | Land vehicle contact | Transmission | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000023 | Contact from object | Land vehicle contact | Transmission | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000024 | Contact from object | Aircraft vehicle contact | Distribution | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000025 | Contact from object | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000026 | Contact from object | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000027 | Contact from object | Aircraft vehicle contact | Transmission | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000028 | Contact from object | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000029 | Contact from object | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000030 | Contact from object | 3rd party facility | Distribution | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000031 | Contact from object | 3rd party facility | Distribution | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000032 | Contact from object | 3rd party facility | Distribution | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000033 | Contact from object | 3rd party facility | Transmission | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000034 | Contact from object | 3rd party facility | Transmission | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000035 | Contact from object | 3rd party facility | Transmission | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000036 | Contact from object | Unknown (contact from object) | Distribution | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000037 | Contact from object | Unknown (contact from object) | Distribution | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000038 | Contact from object | Unknown (contact from object) | Distribution | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000039 | Contact from object | Unknown (contact from object) | Transmission | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000040 | Contact from object | Unknown (contact from object) | Transmission | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000041 | Contact from object | Unknown (contact from object) | Transmission | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000042 | Contact from object | Other (contact from object) | Distribution | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 2
1060000043 | Contact from object | Other (contact from object) | Distribution | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000044 | Contact from object | Other (contact from object) | Distribution | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000045 | Contact from object | Other (contact from object) | Transmission | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000046 | Contact from object | Other (contact from object) | Transmission | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000047 | Contact from object | Other (contact from object) | Transmission | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000048 | Vegetation contact | Uncategorized / other (vegetation contact) | Distribution | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000049 | Vegetation contact | Uncategorized / other (vegetation contact) | Distribution | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000050 | Vegetation contact | Uncategorized / other (vegetation contact) | Distribution | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000051 | Vegetation contact | Uncategorized / other (vegetation contact) | Transmission | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000052 | Vegetation contact | Uncategorized / other (vegetation contact) | Transmission | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000053 | Vegetation contact | Uncategorized / other (vegetation contact) | Transmission | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000054 | Vegetation contact | Grow-in | Distribution | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000055 | Vegetation contact | Grow-in | Distribution | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000056 | Vegetation contact | Grow-in | Distribution | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000057 | Vegetation contact | Grow-in | Transmission | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000058 | Vegetation contact | Grow-in | Transmission | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000059 | Vegetation contact | Grow-in | Transmission | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000060 | Vegetation contact | Blow-in | Distribution | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000061 | Vegetation contact | Blow-in | Distribution | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000062 | Vegetation contact | Blow-in | Distribution | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000063 | Vegetation contact | Blow-in | Transmission | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000064 | Vegetation contact | Blow-in | Transmission | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000065 | Vegetation contact | Blow-in | Transmission | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000066 | Vegetation contact | Trunk failure | Distribution | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000067 | Vegetation contact | Trunk failure | Distribution | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000068 | Vegetation contact | Trunk failure | Distribution | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000069 | Vegetation contact | Trunk failure | Transmission | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000070 | Vegetation contact | Trunk failure | Transmission | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000071 | Vegetation contact | Trunk failure | Transmission | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000072 | Vegetation contact | Root failure | Distribution | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000073 | Vegetation contact | Root failure | Distribution | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000074 | Vegetation contact | Root failure | Distribution | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000075 | Vegetation contact | Root failure | Transmission | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000076 | Vegetation contact | Root failure | Transmission | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000077 | Vegetation contact | Root failure | Transmission | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000078 | Vegetation contact | Detached frond / limb / bark | Distribution | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 1
1060000079 | Vegetation contact | Detached frond / limb / bark | Distribution | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000080 | Vegetation contact | Detached frond / limb / bark | Distribution | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000081 | Vegetation contact | Detached frond / limb / bark | Transmission | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000082 | Vegetation contact | Detached frond / limb / bark | Transmission | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000083 | Vegetation contact | Detached frond / limb / bark | Transmission | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000084 | Equipment / facility failure or damage | Anchor / guy | Distribution | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000085 | Equipment / facility failure or damage | Anchor / guy | Distribution | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000086 | Equipment / facility failure or damage | Anchor / guy | Distribution | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000087 | Equipment / facility failure or damage | Anchor / guy | Transmission | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000088 | Equipment / facility failure or damage | Anchor / guy | Transmission | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000089 | Equipment / facility failure or damage | Anchor / guy | Transmission | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000090 | Equipment / facility failure or damage | Capacitor bank | Distribution | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 1
1060000091 | Equipment / facility failure or damage | Capacitor bank | Distribution | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000092 | Equipment / facility failure or damage | Capacitor bank | Distribution | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000093 | Equipment / facility failure or damage | Capacitor bank | Transmission | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000094 | Equipment / facility failure or damage | Capacitor bank | Transmission | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000095 | Equipment / facility failure or damage | Capacitor bank | Transmission | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000096 | Equipment / facility failure or damage | Conductor | Distribution | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 1
1060000097 | Equipment / facility failure or damage | Conductor | Distribution | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000098 | Equipment / facility failure or damage | Conductor | Distribution | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000099 | Equipment / facility failure or damage | Conductor | Transmission | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000100 | Equipment / facility failure or damage | Conductor | Transmission | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000101 | Equipment / facility failure or damage | Conductor | Transmission | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000102 | Equipment / facility failure or damage | Connection device | Distribution | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000103 | Equipment / facility failure or damage | Connection device | Distribution | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000104 | Equipment / facility failure or damage | Connection device | Distribution | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000105 | Equipment / facility failure or damage | Connection device | Transmission | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000106 | Equipment / facility failure or damage | Connection device | Transmission | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000107 | Equipment / facility failure or damage | Connection device | Transmission | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000108 | Equipment / facility failure or damage | Crossarm | Distribution | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000109 | Equipment / facility failure or damage | Crossarm | Distribution | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000110 | Equipment / facility failure or damage | Crossarm | Distribution | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000111 | Equipment / facility failure or damage | Crossarm | Transmission | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000112 | Equipment / facility failure or damage | Crossarm | Transmission | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000113 | Equipment / facility failure or damage | Crossarm | Transmission | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000114 | Equipment / facility failure or damage | Fuse | Distribution | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000115 | Equipment / facility failure or damage | Fuse | Distribution | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000116 | Equipment / facility failure or damage | Fuse | Distribution | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000117 | Equipment / facility failure or damage | Fuse | Transmission | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000118 | Equipment / facility failure or damage | Fuse | Transmission | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000119 | Equipment / facility failure or damage | Fuse | Transmission | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000120 | Equipment / facility failure or damage | Cutout | Distribution | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000121 | Equipment / facility failure or damage | Cutout | Distribution | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000122 | Equipment / facility failure or damage | Cutout | Distribution | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000123 | Equipment / facility failure or damage | Cutout | Transmission | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000124 | Equipment / facility failure or damage | Cutout | Transmission | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000125 | Equipment / facility failure or damage | Cutout | Transmission | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000126 | Equipment / facility failure or damage | Insulator and bushing | Distribution | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000127 | Equipment / facility failure or damage | Insulator and bushing | Distribution | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000128 | Equipment / facility failure or damage | Insulator and bushing | Distribution | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000129 | Equipment / facility failure or damage | Insulator and bushing | Transmission | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000130 | Equipment / facility failure or damage | Insulator and bushing | Transmission | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000131 | Equipment / facility failure or damage | Insulator and bushing | Transmission | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000132 | Equipment / facility failure or damage | Lightning arrester | Distribution | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000133 | Equipment / facility failure or damage | Lightning arrester | Distribution | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000134 | Equipment / facility failure or damage | Lightning arrester | Distribution | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000135 | Equipment / facility failure or damage | Lightning arrester | Transmission | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000136 | Equipment / facility failure or damage | Lightning arrester | Transmission | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000137 | Equipment / facility failure or damage | Lightning arrester | Transmission | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000138 | Equipment / facility failure or damage | Pole | Distribution | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000139 | Equipment / facility failure or damage | Pole | Distribution | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000140 | Equipment / facility failure or damage | Pole | Distribution | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000141 | Equipment / facility failure or damage | Pole | Transmission | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000142 | Equipment / facility failure or damage | Pole | Transmission | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000143 | Equipment / facility failure or damage | Pole | Transmission | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000144 | Equipment / facility failure or damage | Recloser | Distribution | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000145 | Equipment / facility failure or damage | Recloser | Distribution | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000146 | Equipment / facility failure or damage | Recloser | Distribution | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000147 | Equipment / facility failure or damage | Recloser | Transmission | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000148 | Equipment / facility failure or damage | Recloser | Transmission | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000149 | Equipment / facility failure or damage | Recloser | Transmission | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000150 | Equipment / facility failure or damage | Relay | Distribution | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000151 | Equipment / facility failure or damage | Relay | Distribution | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000152 | Equipment / facility failure or damage | Relay | Distribution | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000153 | Equipment / facility failure or damage | Relay | Transmission | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000154 | Equipment / facility failure or damage | Relay | Transmission | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000155 | Equipment / facility failure or damage | Relay | Transmission | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000156 | Equipment / facility failure or damage | Sectionalizer | Distribution | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000157 | Equipment / facility failure or damage | Sectionalizer | Distribution | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000158 | Equipment / facility failure or damage | Sectionalizer | Distribution | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000159 | Equipment / facility failure or damage | Sectionalizer | Transmission | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000160 | Equipment / facility failure or damage | Sectionalizer | Transmission | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000161 | Equipment / facility failure or damage | Sectionalizer | Transmission | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000162 | Equipment / facility failure or damage | Splice | Distribution | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000163 | Equipment / facility failure or damage | Splice | Distribution | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000164 | Equipment / facility failure or damage | Splice | Distribution | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000165 | Equipment / facility failure or damage | Splice | Transmission | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000166 | Equipment / facility failure or damage | Splice | Transmission | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000167 | Equipment / facility failure or damage | Splice | Transmission | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000168 | Equipment / facility failure or damage | Switch | Distribution | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000169 | Equipment / facility failure or damage | Switch | Distribution | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000170 | Equipment / facility failure or damage | Switch | Distribution | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000171 | Equipment / facility failure or damage | Switch | Transmission | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000172 | Equipment / facility failure or damage | Switch | Transmission | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000173 | Equipment / facility failure or damage | Switch | Transmission | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000174 | Equipment / facility failure or damage | Tap | Distribution | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000175 | Equipment / facility failure or damage | Tap | Distribution | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000176 | Equipment / facility failure or damage | Tap | Distribution | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000177 | Equipment / facility failure or damage | Tap | Transmission | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000178 | Equipment / facility failure or damage | Tap | Transmission | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000179 | Equipment / facility failure or damage | Tap | Transmission | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000180 | Equipment / facility failure or damage | Tie wire | Distribution | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000181 | Equipment / facility failure or damage | Tie wire | Distribution | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000182 | Equipment / facility failure or damage | Tie wire | Distribution | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000183 | Equipment / facility failure or damage | Tie wire | Transmission | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000184 | Equipment / facility failure or damage | Tie wire | Transmission | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000185 | Equipment / facility failure or damage | Tie wire | Transmission | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000186 | Equipment / facility failure or damage | Transformer | Distribution | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000187 | Equipment / facility failure or damage | Transformer | Distribution | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000188 | Equipment / facility failure or damage | Transformer | Distribution | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000189 | Equipment / facility failure or damage | Transformer | Transmission | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000190 | Equipment / facility failure or damage | Transformer | Transmission | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000191 | Equipment / facility failure or damage | Transformer | Transmission | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000192 | Equipment / facility failure or damage | Voltage regulator / booster | Distribution | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000193 | Equipment / facility failure or damage | Voltage regulator / booster | Distribution | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000194 | Equipment / facility failure or damage | Voltage regulator / booster | Distribution | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000195 | Equipment / facility failure or damage | Voltage regulator / booster | Transmission | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000196 | Equipment / facility failure or damage | Voltage regulator / booster | Transmission | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000197 | Equipment / facility failure or damage | Voltage regulator / booster | Transmission | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000198 | Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000199 | Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000200 | Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000201 | Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000202 | Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000203 | Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000204 | Equipment / facility failure or damage | Other (equipment failure) | Distribution | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 1
1060000205 | Equipment / facility failure or damage | Other (equipment failure) | Distribution | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000206 | Equipment / facility failure or damage | Other (equipment failure) | Distribution | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000207 | Equipment / facility failure or damage | Other (equipment failure) | Transmission | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000208 | Equipment / facility failure or damage | Other (equipment failure) | Transmission | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000209 | Equipment / facility failure or damage | Other (equipment failure) | Transmission | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000210 | Wire-to-wire contact | Wire-to-wire contact | Distribution | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 1
1060000211 | Wire-to-wire contact | Wire-to-wire contact | Distribution | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000212 | Wire-to-wire contact | Wire-to-wire contact | Distribution | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000213 | Wire-to-wire contact | Wire-to-wire contact | Transmission | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000214 | Wire-to-wire contact | Wire-to-wire contact | Transmission | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000215 | Wire-to-wire contact | Wire-to-wire contact | Transmission | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000216 | Contamination | Contamination | Distribution | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000217 | Contamination | Contamination | Distribution | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000218 | Contamination | Contamination | Distribution | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000219 | Contamination | Contamination | Transmission | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000220 | Contamination | Contamination | Transmission | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000221 | Contamination | Contamination | Transmission | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000222 | Protective device operation | Protective device operation | Distribution | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000223 | Protective device operation | Protective device operation | Distribution | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000224 | Protective device operation | Protective device operation | Distribution | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000225 | Protective device operation | Protective device operation | Transmission | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000226 | Protective device operation | Protective device operation | Transmission | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000227 | Protective device operation | Protective device operation | Transmission | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000228 | Vandalism / theft | Vandalism / theft | Distribution | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 1
1060000229 | Vandalism / theft | Vandalism / theft | Distribution | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000230 | Vandalism / theft | Vandalism / theft | Distribution | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 1
1060000231 | Vandalism / theft | Vandalism / theft | Transmission | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000232 | Vandalism / theft | Vandalism / theft | Transmission | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000233 | Vandalism / theft | Vandalism / theft | Transmission | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000234 | Lightning | Lightning | Distribution | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000235 | Lightning | Lightning | Distribution | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000236 | Lightning | Lightning | Distribution | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000237 | Lightning | Lightning | Transmission | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000238 | Lightning | Lightning | Transmission | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000239 | Lightning | Lightning | Transmission | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000240 | Unknown | Unknown (unknown) | Distribution | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 2
1060000241 | Unknown | Unknown (unknown) | Distribution | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000242 | Unknown | Unknown (unknown) | Distribution | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000243 | Unknown | Unknown (unknown) | Transmission | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000244 | Unknown | Unknown (unknown) | Transmission | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000245 | Unknown | Unknown (unknown) | Transmission | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000246 | Other | Other (other) | Distribution | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 1
1060000247 | Other | Other (other) | Distribution | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000248 | Other | Other (other) | Distribution | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000249 | Other | Other (other) | Transmission | Non-HFTD | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000250 | Other | Other (other) | Transmission | HFTD Tier 2 | # ignitions |  |  | SCE | 2026 | 2 | 0
1060000251 | Other | Other (other) | Transmission | HFTD Tier 3 | # ignitions |  |  | SCE | 2026 | 2 | 0

## Table 7
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1070000000 | Overhead circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 3383
1070000001 | Overhead circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 12770
1070000002 | Overhead circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 2760
1070000003 | Overhead circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 6398
1070000004 | Overhead circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 468
1070000005 | Overhead circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 2308
1070000006 | Overhead circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 565
1070000007 | Overhead circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 383
1070000008 | Overhead circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 1022
1070000009 | Overhead circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 799
1070000010 | Overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 220
1070000011 | Overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 786
1070000012 | Overhead circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 743
1070000013 | Overhead circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 158
1070000014 | Overhead circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 2548
1070000015 | Overhead circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 1529
1070000016 | Overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 149
1070000017 | Overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 348
1070000018 | Overhead circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 479
1070000019 | Overhead circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 2684
1070000020 | Overhead circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 268
1070000021 | Overhead circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 2323
1070000022 | Overhead circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 37
1070000023 | Overhead circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 2008
1070000024 | Overhead circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 190
1070000025 | Overhead circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 217
1070000026 | Overhead circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 255
1070000027 | Overhead circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 727
1070000028 | Overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 32
1070000029 | Overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 550
1070000030 | Overhead circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 238
1070000031 | Overhead circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 201
1070000032 | Overhead circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 424
1070000033 | Overhead circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 1268
1070000034 | Overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 22
1070000035 | Overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 249
1070000036 | Underground circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 6160
1070000037 | Underground circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 13464
1070000038 | Underground circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 1633
1070000039 | Underground circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 2419
1070000040 | Underground circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 58
1070000041 | Underground circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 242
1070000042 | Underground circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 1198
1070000043 | Underground circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 660
1070000044 | Underground circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 813
1070000045 | Underground circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 377
1070000046 | Underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 36
1070000047 | Underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 110
1070000048 | Underground circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 1914
1070000049 | Underground circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 291
1070000050 | Underground circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 1654
1070000051 | Underground circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 471
1070000052 | Underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 16
1070000053 | Underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 61
1070000054 | Underground circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 15
1070000055 | Underground circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 232
1070000056 | Underground circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 1
1070000057 | Underground circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 47
1070000058 | Underground circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 0
1070000059 | Underground circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 17
1070000060 | Underground circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 7
1070000061 | Underground circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 6
1070000062 | Underground circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 1
1070000063 | Underground circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 5
1070000064 | Underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 0
1070000065 | Underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 0
1070000066 | Underground circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 16
1070000067 | Underground circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 11
1070000068 | Underground circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 7
1070000069 | Underground circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 10
1070000070 | Underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 0
1070000071 | Underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 0
1070000072 | Critical facilities |  | Non-HFTD | Urban | WUI | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 11646
1070000073 | Critical facilities |  | Non-HFTD | Urban | Non-WUI | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 50256
1070000074 | Critical facilities |  | Non-HFTD | Rural | WUI | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 3215
1070000075 | Critical facilities |  | Non-HFTD | Rural | Non-WUI | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 7104
1070000076 | Critical facilities |  | Non-HFTD | Highly rural | WUI | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 230
1070000077 | Critical facilities |  | Non-HFTD | Highly rural | Non-WUI | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 988
1070000078 | Critical facilities |  | HFTD Tier 2 | Urban | WUI | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 1889
1070000079 | Critical facilities |  | HFTD Tier 2 | Urban | Non-WUI | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 1536
1070000080 | Critical facilities |  | HFTD Tier 2 | Rural | WUI | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 1253
1070000081 | Critical facilities |  | HFTD Tier 2 | Rural | Non-WUI | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 888
1070000082 | Critical facilities |  | HFTD Tier 2 | Highly rural | WUI | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 160
1070000083 | Critical facilities |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 419
1070000084 | Critical facilities |  | HFTD Tier 3 | Urban | WUI | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 3326
1070000085 | Critical facilities |  | HFTD Tier 3 | Urban | Non-WUI | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 882
1070000086 | Critical facilities |  | HFTD Tier 3 | Rural | WUI | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 3376
1070000087 | Critical facilities |  | HFTD Tier 3 | Rural | Non-WUI | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 1592
1070000088 | Critical facilities |  | HFTD Tier 3 | Highly rural | WUI | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 122
1070000089 | Critical facilities |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of critical facilities | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 177
1070000090 | Residential customers |  | Non-HFTD | Urban | WUI | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 855830
1070000091 | Residential customers |  | Non-HFTD | Urban | Non-WUI | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 2689569
1070000092 | Residential customers |  | Non-HFTD | Rural | WUI | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 175658
1070000093 | Residential customers |  | Non-HFTD | Rural | Non-WUI | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 89983
1070000094 | Residential customers |  | Non-HFTD | Highly rural | WUI | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 8554
1070000095 | Residential customers |  | Non-HFTD | Highly rural | Non-WUI | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 3656
1070000096 | Residential customers |  | HFTD Tier 2 | Urban | WUI | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 111212
1070000097 | Residential customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 51991
1070000098 | Residential customers |  | HFTD Tier 2 | Rural | WUI | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 71415
1070000099 | Residential customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 12003
1070000100 | Residential customers |  | HFTD Tier 2 | Highly rural | WUI | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 5544
1070000101 | Residential customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 2250
1070000102 | Residential customers |  | HFTD Tier 3 | Urban | WUI | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 225321
1070000103 | Residential customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 8460
1070000104 | Residential customers |  | HFTD Tier 3 | Rural | WUI | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 145007
1070000105 | Residential customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 9209
1070000106 | Residential customers |  | HFTD Tier 3 | Highly rural | WUI | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 5181
1070000107 | Residential customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of residential customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 791
1070000108 | Commercial customers |  | Non-HFTD | Urban | WUI | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 66429
1070000109 | Commercial customers |  | Non-HFTD | Urban | Non-WUI | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 391117
1070000110 | Commercial customers |  | Non-HFTD | Rural | WUI | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 14400
1070000111 | Commercial customers |  | Non-HFTD | Rural | Non-WUI | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 44700
1070000112 | Commercial customers |  | Non-HFTD | Highly rural | WUI | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 786
1070000113 | Commercial customers |  | Non-HFTD | Highly rural | Non-WUI | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 2395
1070000114 | Commercial customers |  | HFTD Tier 2 | Urban | WUI | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 7150
1070000115 | Commercial customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 5958
1070000116 | Commercial customers |  | HFTD Tier 2 | Rural | WUI | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 4730
1070000117 | Commercial customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 2531
1070000118 | Commercial customers |  | HFTD Tier 2 | Highly rural | WUI | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 595
1070000119 | Commercial customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 990
1070000120 | Commercial customers |  | HFTD Tier 3 | Urban | WUI | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 20522
1070000121 | Commercial customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 8440
1070000122 | Commercial customers |  | HFTD Tier 3 | Rural | WUI | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 12871
1070000123 | Commercial customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 6506
1070000124 | Commercial customers |  | HFTD Tier 3 | Highly rural | WUI | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 366
1070000125 | Commercial customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of commercial customers | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 466
1070000126 | AFN customers |  | Non-HFTD | Urban | WUI | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 336775
1070000127 | AFN customers |  | Non-HFTD | Urban | Non-WUI | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 1092802
1070000128 | AFN customers |  | Non-HFTD | Rural | WUI | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 69534
1070000129 | AFN customers |  | Non-HFTD | Rural | Non-WUI | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 37598
1070000130 | AFN customers |  | Non-HFTD | Highly rural | WUI | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 2993
1070000131 | AFN customers |  | Non-HFTD | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 1160
1070000132 | AFN customers |  | HFTD Tier 2 | Urban | WUI | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 33579
1070000133 | AFN customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 13506
1070000134 | AFN customers |  | HFTD Tier 2 | Rural | WUI | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 22567
1070000135 | AFN customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 3466
1070000136 | AFN customers |  | HFTD Tier 2 | Highly rural | WUI | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 1471
1070000137 | AFN customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 761
1070000138 | AFN customers |  | HFTD Tier 3 | Urban | WUI | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 61503
1070000139 | AFN customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 2148
1070000140 | AFN customers |  | HFTD Tier 3 | Rural | WUI | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 39005
1070000141 | AFN customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 2605
1070000142 | AFN customers |  | HFTD Tier 3 | Highly rural | WUI | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 1812
1070000143 | AFN customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 257
1070000144 | Substations |  | Non-HFTD | Urban | WUI | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 66
1070000145 | Substations |  | Non-HFTD | Urban | Non-WUI | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 391
1070000146 | Substations |  | Non-HFTD | Rural | WUI | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 24
1070000147 | Substations |  | Non-HFTD | Rural | Non-WUI | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 244
1070000148 | Substations |  | Non-HFTD | Highly rural | WUI | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 6
1070000149 | Substations |  | Non-HFTD | Highly rural | Non-WUI | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 126
1070000150 | Substations |  | HFTD Tier 2 | Urban | WUI | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 11
1070000151 | Substations |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 17
1070000152 | Substations |  | HFTD Tier 2 | Rural | WUI | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 12
1070000153 | Substations |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 38
1070000154 | Substations |  | HFTD Tier 2 | Highly rural | WUI | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 5
1070000155 | Substations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 33
1070000156 | Substations |  | HFTD Tier 3 | Urban | WUI | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 17
1070000157 | Substations |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 9
1070000158 | Substations |  | HFTD Tier 3 | Rural | WUI | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 22
1070000159 | Substations |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 42
1070000160 | Substations |  | HFTD Tier 3 | Highly rural | WUI | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 1
1070000161 | Substations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 5
1070000162 | Weather stations |  | Non-HFTD | Urban | WUI | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 79
1070000163 | Weather stations |  | Non-HFTD | Urban | Non-WUI | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 52
1070000164 | Weather stations |  | Non-HFTD | Rural | WUI | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 51
1070000165 | Weather stations |  | Non-HFTD | Rural | Non-WUI | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 35
1070000166 | Weather stations |  | Non-HFTD | Highly rural | WUI | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 0
1070000167 | Weather stations |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 19
1070000168 | Weather stations |  | HFTD Tier 2 | Urban | WUI | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 132
1070000169 | Weather stations |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 102
1070000170 | Weather stations |  | HFTD Tier 2 | Rural | WUI | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 136
1070000171 | Weather stations |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 193
1070000172 | Weather stations |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 25
1070000173 | Weather stations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 144
1070000174 | Weather stations |  | HFTD Tier 3 | Urban | WUI | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 130
1070000175 | Weather stations |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 58
1070000176 | Weather stations |  | HFTD Tier 3 | Rural | WUI | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 374
1070000177 | Weather stations |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 400
1070000178 | Weather stations |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 15
1070000179 | Weather stations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations | It is important to note that GIS models are updated frequently to reflect changes within SCE’s service area and for data clean‐up. SCE does not have the ability to analyze and calculate information in previous years since the GIS data is dynamic and cannot be pulled retroactively. Accordingly, while SCE has provided data on a quarterly basis starting with 2022, SCE is still conducting quality control review of all the data and will correct any errors once its review is complete. |  | SCE | 2026 | 2 | 75

## Table 8
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1080000000 | Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | -4
1080000001 | Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | -11
1080000002 | Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 1
1080000003 | Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000004 | Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000005 | Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 1
1080000006 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | -2
1080000007 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | -3
1080000008 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | -3
1080000009 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000010 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | -1
1080000011 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | -1
1080000012 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | -2
1080000013 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000014 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | -6
1080000015 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | -5
1080000016 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | -1
1080000017 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000018 | Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000019 | Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000020 | Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000021 | Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 1
1080000022 | Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000023 | Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000024 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000025 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000026 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000027 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000028 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000029 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000030 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000031 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000032 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000033 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000034 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000035 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000036 | Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 15
1080000037 | Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 35
1080000038 | Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 8
1080000039 | Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 21
1080000040 | Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 1
1080000041 | Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 1
1080000042 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 6
1080000043 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 5
1080000044 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 6
1080000045 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 8
1080000046 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000047 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 1
1080000048 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 3
1080000049 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000050 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 6
1080000051 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 5
1080000052 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000053 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | -1
1080000054 | Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000055 | Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000056 | Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000057 | Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000058 | Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000059 | Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000060 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000061 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000062 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000063 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000064 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000065 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000066 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000067 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000068 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000069 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000070 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000071 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000072 | Net addition (or removal) - Substations |  | Non-HFTD | Urban | WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000073 | Net addition (or removal) - Substations |  | Non-HFTD | Urban | Non-WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | -1
1080000074 | Net addition (or removal) - Substations |  | Non-HFTD | Rural | WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000075 | Net addition (or removal) - Substations |  | Non-HFTD | Rural | Non-WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000076 | Net addition (or removal) - Substations |  | Non-HFTD | Highly rural | WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000077 | Net addition (or removal) - Substations |  | Non-HFTD | Highly rural | Non-WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000078 | Net addition (or removal) - Substations |  | HFTD Tier 2 | Urban | WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000079 | Net addition (or removal) - Substations |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000080 | Net addition (or removal) - Substations |  | HFTD Tier 2 | Rural | WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000081 | Net addition (or removal) - Substations |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000082 | Net addition (or removal) - Substations |  | HFTD Tier 2 | Highly rural | WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000083 | Net addition (or removal) - Substations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000084 | Net addition (or removal) - Substations |  | HFTD Tier 3 | Urban | WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000085 | Net addition (or removal) - Substations |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000086 | Net addition (or removal) - Substations |  | HFTD Tier 3 | Rural | WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000087 | Net addition (or removal) - Substations |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000088 | Net addition (or removal) - Substations |  | HFTD Tier 3 | Highly rural | WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000089 | Net addition (or removal) - Substations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000090 | Net addition (or removal) - Weather stations |  | Non-HFTD | Urban | WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000091 | Net addition (or removal) - Weather stations |  | Non-HFTD | Urban | Non-WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 1
1080000092 | Net addition (or removal) - Weather stations |  | Non-HFTD | Rural | WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 1
1080000093 | Net addition (or removal) - Weather stations |  | Non-HFTD | Rural | Non-WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000094 | Net addition (or removal) - Weather stations |  | Non-HFTD | Highly rural | WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000095 | Net addition (or removal) - Weather stations |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000096 | Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Urban | WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000097 | Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 2
1080000098 | Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Rural | WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000099 | Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000100 | Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000101 | Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 1
1080000102 | Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Urban | WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000103 | Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000104 | Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Rural | WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000105 | Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 1
1080000106 | Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1080000107 | Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0

## Table 9
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1090000000 | Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Urban | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0.02
1090000001 | Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0.81
1090000002 | Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 3.72
1090000003 | Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 18.59
1090000004 | Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1090000005 | Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1090000006 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1090000007 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1090000008 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1090000009 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0.07
1090000010 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1090000011 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1090000012 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 9.05
1090000013 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0.29
1090000014 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1090000015 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1090000016 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1090000017 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1090000018 | Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Urban | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. | Metric Not tracked/available at this Time. | SCE | 2026 | 2
1090000019 | Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. | Metric Not tracked/available at this Time. | SCE | 2026 | 2
1090000020 | Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. | Metric Not tracked/available at this Time. | SCE | 2026 | 2
1090000021 | Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. | Metric Not tracked/available at this Time. | SCE | 2026 | 2
1090000022 | Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. | Metric Not tracked/available at this Time. | SCE | 2026 | 2
1090000023 | Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. | Metric Not tracked/available at this Time. | SCE | 2026 | 2
1090000024 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. | Metric Not tracked/available at this Time. | SCE | 2026 | 2
1090000025 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. | Metric Not tracked/available at this Time. | SCE | 2026 | 2
1090000026 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. | Metric Not tracked/available at this Time. | SCE | 2026 | 2
1090000027 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. | Metric Not tracked/available at this Time. | SCE | 2026 | 2
1090000028 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. | Metric Not tracked/available at this Time. | SCE | 2026 | 2
1090000029 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. | Metric Not tracked/available at this Time. | SCE | 2026 | 2
1090000030 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. | Metric Not tracked/available at this Time. | SCE | 2026 | 2
1090000031 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. | Metric Not tracked/available at this Time. | SCE | 2026 | 2
1090000032 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. | Metric Not tracked/available at this Time. | SCE | 2026 | 2
1090000033 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. | Metric Not tracked/available at this Time. | SCE | 2026 | 2
1090000034 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. | Metric Not tracked/available at this Time. | SCE | 2026 | 2
1090000035 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. | Metric Not tracked/available at this Time. | SCE | 2026 | 2
1090000036 | Number of substations upgraded |  | Non-HFTD | Urban | WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 1
1090000037 | Number of substations upgraded |  | Non-HFTD | Urban | Non-WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 6
1090000038 | Number of substations upgraded |  | Non-HFTD | Rural | WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 1
1090000039 | Number of substations upgraded |  | Non-HFTD | Rural | Non-WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 3
1090000040 | Number of substations upgraded |  | Non-HFTD | Highly rural | WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1090000041 | Number of substations upgraded |  | Non-HFTD | Highly rural | Non-WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1090000042 | Number of substations upgraded |  | HFTD Tier 2 | Urban | WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1090000043 | Number of substations upgraded |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1090000044 | Number of substations upgraded |  | HFTD Tier 2 | Rural | WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1090000045 | Number of substations upgraded |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1090000046 | Number of substations upgraded |  | HFTD Tier 2 | Highly rural | WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1090000047 | Number of substations upgraded |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1090000048 | Number of substations upgraded |  | HFTD Tier 3 | Urban | WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1090000049 | Number of substations upgraded |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1090000050 | Number of substations upgraded |  | HFTD Tier 3 | Rural | WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1090000051 | Number of substations upgraded |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1090000052 | Number of substations upgraded |  | HFTD Tier 3 | Highly rural | WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1090000053 | Number of substations upgraded |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1090000054 | Number of weather stations with hardware upgraded |  | Non-HFTD | Urban | WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 2
1090000055 | Number of weather stations with hardware upgraded |  | Non-HFTD | Urban | Non-WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 1
1090000056 | Number of weather stations with hardware upgraded |  | Non-HFTD | Rural | WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1090000057 | Number of weather stations with hardware upgraded |  | Non-HFTD | Rural | Non-WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1090000058 | Number of weather stations with hardware upgraded |  | Non-HFTD | Highly rural | WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1090000059 | Number of weather stations with hardware upgraded |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1090000060 | Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Urban | WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1090000061 | Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1090000062 | Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Rural | WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1090000063 | Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 1
1090000064 | Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1090000065 | Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1090000066 | Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Urban | WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1090000067 | Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 1
1090000068 | Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Rural | WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 3
1090000069 | Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 1
1090000070 | Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0
1090000071 | Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations | SCE provides equipment addition, removal and upgrade data where available. In some instances, the exact circuit and/or geospatial locational data and line lengths required are not available. This is due in part to detailed designs not yet completed for certain infrastructure projects. SCE is working internally to begin incorporating the geospatial data needed to provide these data points for future submissions. |  | SCE | 2026 | 2 | 0

## Table 10
METRIC NUMBER | METRIC TYPE | METRIC NAME | WIND WARNING STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1100000000 | Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | RFW only | Number of events |  |  | SCE | 2026 | 2 | 1
1100000001 | Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | HWW only | Number of events |  |  | SCE | 2026 | 2 | 0
1100000002 | Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | HWW & RFW | Number of events |  |  | SCE | 2026 | 2 | 0
1100000003 | Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | Neither | Number of events |  |  | SCE | 2026 | 2 | 1
1100000004 | Recent use of PSPS and fast-trip | Scope of PSPS events (total) | RFW only | Circuit-events, measured in number of events multiplied by number of circuits de-energized | SCE interprets this line item as de-energized circuit count. If one circuit is de-energized in subsequent events, the circuit count would be two. |  | SCE | 2026 | 2 | 1
1100000005 | Recent use of PSPS and fast-trip | Scope of PSPS events (total) | HWW only | Circuit-events, measured in number of events multiplied by number of circuits de-energized | SCE interprets this line item as de-energized circuit count. If one circuit is de-energized in subsequent events, the circuit count would be two. |  | SCE | 2026 | 2 | 0
1100000006 | Recent use of PSPS and fast-trip | Scope of PSPS events (total) | HWW & RFW | Circuit-events, measured in number of events multiplied by number of circuits de-energized | SCE interprets this line item as de-energized circuit count. If one circuit is de-energized in subsequent events, the circuit count would be two. |  | SCE | 2026 | 2 | 0
1100000007 | Recent use of PSPS and fast-trip | Scope of PSPS events (total) | Neither | Circuit-events, measured in number of events multiplied by number of circuits de-energized | SCE interprets this line item as de-energized circuit count. If one circuit is de-energized in subsequent events, the circuit count would be two. |  | SCE | 2026 | 2 | 6
1100000008 | Recent use of PSPS and fast-trip | Duration of PSPS events (total) | RFW only | Customer hours |  |  | SCE | 2026 | 2 | 2254.88
1100000009 | Recent use of PSPS and fast-trip | Duration of PSPS events (total) | HWW only | Customer hours |  |  | SCE | 2026 | 2 | 0
1100000010 | Recent use of PSPS and fast-trip | Duration of PSPS events (total) | HWW & RFW | Customer hours |  |  | SCE | 2026 | 2 | 0
1100000011 | Recent use of PSPS and fast-trip | Duration of PSPS events (total) | Neither | Customer hours |  |  | SCE | 2026 | 2 | 10830.4
1100000012 | Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | RFW only | Number of events | Fast curve (FC) events are outages where FC settings were enabled on HFRA circuits and not solely where outages were due to FC. |  | SCE | 2026 | 2 | 1
1100000013 | Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | HWW only | Number of events | Fast curve (FC) events are outages where FC settings were enabled on HFRA circuits and not solely where outages were due to FC. |  | SCE | 2026 | 2 | 1
1100000014 | Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | HWW & RFW | Number of events | Fast curve (FC) events are outages where FC settings were enabled on HFRA circuits and not solely where outages were due to FC. |  | SCE | 2026 | 2 | 0
1100000015 | Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | Neither | Number of events | Fast curve (FC) events are outages where FC settings were enabled on HFRA circuits and not solely where outages were due to FC. |  | SCE | 2026 | 2 | 201
1100000016 | Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | RFW only | Circuit mile days | Data for fast curve is a mix of on and off signals. While the matching of outages to Fast curve enablement was consistent, the switching caused issues with days being counted as a Fast curve day. Code has been adjusted to accurately capture the day as a fast curve day |  | SCE | 2026 | 2 | 9808.85
1100000017 | Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | HWW only | Circuit mile days | Data for fast curve is a mix of on and off signals. While the matching of outages to Fast curve enablement was consistent, the switching caused issues with days being counted as a Fast curve day. Code has been adjusted to accurately capture the day as a fast curve day |  | SCE | 2026 | 2 | 2769.81
1100000018 | Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | HWW & RFW | Circuit mile days | Data for fast curve is a mix of on and off signals. While the matching of outages to Fast curve enablement was consistent, the switching caused issues with days being counted as a Fast curve day. Code has been adjusted to accurately capture the day as a fast curve day |  | SCE | 2026 | 2 | 2204.55
1100000019 | Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | Neither | Circuit mile days | Data for fast curve is a mix of on and off signals. While the matching of outages to Fast curve enablement was consistent, the switching caused issues with days being counted as a Fast curve day. Code has been adjusted to accurately capture the day as a fast curve day |  | SCE | 2026 | 2 | 1426068.48
1100000020 | Customer hours of PSPS and other outages | Customer hours of planned outages including PSPS (total) |  | Customer hours | Customer Hours of Interruption for Planned Outages (Customers interrupted multiplied by Hours of Interruption). Antcipate data related to planned outages will change as SCE finishes an enhancement project to improve planned outage reporting. |  | SCE | 2026 | 2 | 1812591.5756
1100000021 | Customer hours of PSPS and other outages | Customer hours of unplanned outages, not including PSPS or fast-trip (total) |  | Customer hours |  |  | SCE | 2026 | 2 | 1859963.9989
1100000022 | Customer hours of PSPS and other outages | Customer hours of unplanned outages resulting from fast-trip |  | Customer hours | Fast curve (FC) events are outages where FC settings were enabled on HFRA circuits and not solely where outages were due to FC. Customer hours are customer hours of interruption (customers multiplied by their duration) |  | SCE | 2026 | 2 | 474142
1100000023 | Customer hours of PSPS and other outages | System Average Interruption Duration Index (SAIDI) (including PSPS) |  | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served | Includes both planned and unplanned outages. Data is subject to change. |  | SCE | 2026 | 2 | 20.9273
1100000024 | Customer hours of PSPS and other outages | System Average Interruption Duration Index (SAIDI) (excluding PSPS) |  | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served | Includes both planned and unplanned outages. Data is subject to change. |  | SCE | 2026 | 2 | 20.8055
1100000025 | Customer hours of PSPS and other outages | System Average Interruption Frequency Index (SAIFI) (including PSPS) |  | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) | Includes both planned and unplanned outages. Data is subject to change. |  | SCE | 2026 | 2 | 0.22161
1100000026 | Customer hours of PSPS and other outages | System Average Interruption Frequency Index (SAIFI) (excluding PSPS) |  | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) | Includes both planned and unplanned outages. Data is subject to change. |  | SCE | 2026 | 2 | 0.22133
1100000027 | Critical infrastructure impacted by PSPS | Critical infrastructure impacted by PSPS |  | Number of critical infrastructure (in accordance with D.19-05-042) locations impacted multiplied by hours offline | This number is the total number of Critical Infrastructure customers impacted (de-energized) by a PSPS event |  | SCE | 2026 | 2 | 23
1100000028 | Community outreach of PSPS metrics | # of customers impacted by PSPS |  | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | SCE | 2026 | 2 | 750
1100000029 | Community outreach of PSPS metrics | # of medical baseline customers impacted by PSPS |  | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | SCE | 2026 | 2 | 13
1100000030 | Community outreach of PSPS metrics | # of customers notified prior to initiation of PSPS event |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) | This number is the total number of customers sent pre-event notification (adv Int, Int, Update, Expected) for a potential PSPS de-energization. |  | SCE | 2026 | 2 | 3033
1100000031 | Community outreach of PSPS metrics | # of medical baseline customers notified prior to initiation of PSPS event |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) | This number is the total number of MBL customers sent pre-event notification (adv Int, Int, Update, Expected) for a potential PSPS de-energization. |  | SCE | 2026 | 2 | 96
1100000032 | Community outreach of PSPS metrics | # of customers notified prior to a PSPS event impacting them |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) | This number is the total number of customers impacted (de-energized) by a PSPS event. NOTE: This is a subset number of K40. De-energized customers who were notified pre-event (adv int, int, update, expected) |  | SCE | 2026 | 2 | 750
1100000033 | Community outreach of PSPS metrics | # of medical baseline customers notified prior to a PSPS event impacting them |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) | This number is the total number of MBL customers impacted (de-energized) by a PSPS event. NOTE: This is a subset number of K41. De-energized MBL customers who were notified pre-event (adv int, int, update, expected) |  | SCE | 2026 | 2 | 13
1100000034 | Other PSPS metrics | Number of PSPS events in which a notification was sent but no de-energization occurred |  | Number of events |  |  | SCE | 2026 | 2 | 0
1100000035 | Other PSPS metrics | Average number of customers located on de-energized circuit |  | Number of customers | Sum total of all de-energized customers / total number of de-energized circuits. |  | SCE | 2026 | 2 | 124.67
1100000036 | Other PSPS metrics | Customer hours of PSPS per RFW OH circuit mile day |  | Customer hours per RFW OH circuit mile day in time period |  |  | SCE | 2026 | 2 | 4.61
1100000037 | Other PSPS metrics | Customer hours of PSPS per HWW OH circuit mile day |  | Customer hours per HWW OH circuit mile day in time period |  |  | SCE | 2026 | 2 | 0
1100000038 | Other PSPS metrics | Customer hours of PSPS per high FPIOH circuit mile day |  | Customer hours per FPI OH circuit mile day in time period |  |  | SCE | 2026 | 2 | 0.01
1100000039 | Other PSPS metrics | Median time between de-energization, due to PSPS, and inspection of a circuit segment |  | hours | De-en to prep-to-restore time (=MEDIAN,[ARRAY]) |  | SCE | 2026 | 2 | 31.63
1100000040 | Other PSPS metrics | 95 percentile of time between de-energization, due to PSPS, and inspection of a circuit segment |  | hours | De-en to prep-to-restore time (0.95) (=PERCENTILE.INC,[ARRAY]) |  | SCE | 2026 | 2 | 34.05
1100000041 | Other PSPS metrics | Median time between de-energization, due to fast-trip, and inspection of a circuit segment |  | hours | Fast curve (FC) events are outages where FC settings were enabled on HFRA circuits and not solely where outages were due to FC. Median time of entire outage durations instead of inspection on circuit-segment |  | SCE | 2026 | 2 | 4.3
1100000042 | Other PSPS metrics | 95 percentile of time between de-energization, due to fast-trip, and inspection of a circuit segment |  | hours | Fast curve (FC) events are outages where FC settings were enabled on HFRA circuits and not solely where outages were due to FC. 95th percentile of entire outage durations instead of inspection on circuit-segment. 5% of durations are above value |  | SCE | 2026 | 2 | 20.2
1100000043 | Other PSPS metrics | Number of risk events occurring on a de-energized circuit |  | Number of risk events |  |  | SCE | 2026 | 2 | 0

## Table 12
METRIC NUMBER | WORK ORDER NUMBER | EQUIPMENT TYPE | HFTD TIER | LINE TYPE | DATE OPENED | DUE DATE | GO 95 RULE 18 PRIORITY | UTILITY SPECIFIC REPAIR PRIORITY | DATE REINSPECTED | DATE MODIFIED | DUE DATE AFTER REINSPECTED OR MODIFIED | GO 95 RULE 18 PRIORITY AFTER REINSPECTED OR MODIFIED | REASON FOR REINSPECTION | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER
1120000000 | 400199120 | High Sign | HFTD Tier 2 | Distribution | 1999-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000001 | 400918837 | High Sign | HFTD Tier 2 | Distribution | 1999-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000002 | 400953636 | High Sign | HFTD Tier 2 | Distribution | 1999-09-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000003 | 400753288 | High Sign | HFTD Tier 2 | Distribution | 1999-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000004 | 400955035 | High Sign | HFTD Tier 2 | Distribution | 1999-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000005 | 400976137 | High Sign | HFTD Tier 2 | Distribution | 1999-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000006 | 400562536 | High Sign | HFTD Tier 2 | Distribution | 1999-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000007 | 400832005 | High Sign | HFTD Tier 2 | Distribution | 1999-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000008 | 400956923 | High Sign | HFTD Tier 2 | Distribution | 1999-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000009 | 400310846 | Molding | HFTD Tier 2 | Distribution | 1999-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000010 | 400325638 | Molding | HFTD Tier 2 | Distribution | 1999-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000011 | 400133266 | Molding | HFTD Tier 2 | Distribution | 1999-09-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000012 | 400316511 | Molding | HFTD Tier 2 | Distribution | 1999-09-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000013 | 400669796 | High Sign | HFTD Tier 2 | Distribution | 1999-09-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000014 | 400799687 | High Sign | HFTD Tier 2 | Distribution | 1999-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000015 | 400040194 | High Sign | HFTD Tier 2 | Distribution | 2000-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000016 | 400477095 | High Sign | HFTD Tier 2 | Distribution | 2000-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000017 | 400132182 | Molding | HFTD Tier 3 | Distribution | 2000-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000018 | 400062498 | High Sign | HFTD Tier 3 | Distribution | 2000-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000019 | 400352042 | High Sign | HFTD Tier 3 | Distribution | 2000-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000020 | 400410823 | High Sign | HFTD Tier 3 | Distribution | 2000-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000021 | 400436090 | High Sign | HFTD Tier 3 | Distribution | 2000-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000022 | 400046268 | High Sign | HFTD Tier 3 | Distribution | 2000-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000023 | 400027192 | High Sign | HFTD Tier 3 | Distribution | 2000-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000024 | 400338629 | High Sign | HFTD Tier 3 | Distribution | 2000-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000025 | 400065621 | Molding | HFTD Tier 3 | Distribution | 2000-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000026 | 400610861 | Molding | HFTD Tier 3 | Distribution | 2000-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000027 | 400044534 | Molding | HFTD Tier 2 | Distribution | 2000-10-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000028 | 400117442 | Molding | HFTD Tier 3 | Distribution | 2000-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000029 | 400357121 | Molding | HFTD Tier 3 | Distribution | 2000-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000030 | 400377737 | Molding | HFTD Tier 3 | Distribution | 2000-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000031 | 400444428 | High Sign | HFTD Tier 2 | Distribution | 2000-12-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000032 | 400023974 | Molding | HFTD Tier 3 | Distribution | 2001-01-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000033 | 400056039 | Molding | HFTD Tier 2 | Distribution | 2001-01-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000034 | 400059297 | Molding | HFTD Tier 2 | Distribution | 2001-01-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000035 | 400066870 | Molding | HFTD Tier 2 | Distribution | 2001-01-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000036 | 400078310 | Molding | HFTD Tier 3 | Distribution | 2001-01-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000037 | 400206553 | High Sign | HFTD Tier 2 | Distribution | 2001-01-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000038 | 400211465 | High Sign | HFTD Tier 2 | Distribution | 2001-01-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000039 | 400225503 | High Sign | HFTD Tier 3 | Distribution | 2001-01-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000040 | 400279211 | High Sign | HFTD Tier 2 | Distribution | 2001-01-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000041 | 400370214 | High Sign | HFTD Tier 2 | Distribution | 2001-01-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000042 | 400478562 | Hardware/Framing | HFTD Tier 3 | Distribution | 2001-01-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000043 | 400555213 | High Sign | HFTD Tier 3 | Distribution | 2001-01-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000044 | 400566353 | High Sign | HFTD Tier 3 | Distribution | 2001-01-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000045 | 400337124 | Molding | HFTD Tier 2 | Distribution | 2001-01-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000046 | 400337498 | Molding | HFTD Tier 2 | Distribution | 2001-01-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000047 | 400399984 | High Sign | HFTD Tier 2 | Distribution | 2001-01-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000048 | 400476708 | Molding | HFTD Tier 2 | Distribution | 2001-01-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000049 | 400848529 | High Sign | HFTD Tier 3 | Distribution | 2001-01-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000050 | 400235189 | Molding | HFTD Tier 2 | Distribution | 2001-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000051 | 400238071 | Molding | HFTD Tier 2 | Distribution | 2001-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000052 | 400253127 | High Sign | HFTD Tier 2 | Distribution | 2001-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000053 | 400431830 | High Sign | HFTD Tier 3 | Distribution | 2001-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000054 | 400508837 | High Sign | HFTD Tier 3 | Distribution | 2001-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000055 | 400998343 | Cable/Conductor | HFTD Tier 3 | Distribution | 2001-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000056 | 400802078 | Guy | HFTD Tier 3 | Distribution | 2001-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000057 | 400237017 | Molding | HFTD Tier 2 | Distribution | 2001-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000058 | 400239233 | Molding | HFTD Tier 2 | Distribution | 2001-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000059 | 400308330 | High Sign | HFTD Tier 2 | Distribution | 2001-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000060 | 400093624 | High Sign | HFTD Tier 2 | Distribution | 2001-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000061 | 400235705 | Molding | HFTD Tier 2 | Distribution | 2001-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000062 | 400235831 | Molding | HFTD Tier 2 | Distribution | 2001-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000063 | 400239503 | Molding | HFTD Tier 2 | Distribution | 2001-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000064 | 400239844 | Molding | HFTD Tier 2 | Distribution | 2001-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000065 | 400241810 | Molding | HFTD Tier 2 | Distribution | 2001-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000066 | 400241825 | Molding | HFTD Tier 2 | Distribution | 2001-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000067 | 400252141 | High Sign | HFTD Tier 2 | Distribution | 2001-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000068 | 400252841 | High Sign | HFTD Tier 2 | Distribution | 2001-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000069 | 400254116 | High Sign | HFTD Tier 2 | Distribution | 2001-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000070 | 400258712 | High Sign | HFTD Tier 2 | Distribution | 2001-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000071 | 400386095 | Molding | HFTD Tier 2 | Distribution | 2001-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000072 | 400392879 | Molding | HFTD Tier 2 | Distribution | 2001-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000073 | 400396183 | Molding | HFTD Tier 2 | Distribution | 2001-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000074 | 400609692 | High Sign | HFTD Tier 3 | Distribution | 2001-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000075 | 401006692 | High Sign | HFTD Tier 3 | Distribution | 2001-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000076 | 401006693 | Molding | HFTD Tier 3 | Distribution | 2001-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000077 | 400641855 | Cable/Conductor | HFTD Tier 2 | Distribution | 2001-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000078 | 400802879 | High Sign | HFTD Tier 2 | Distribution | 2001-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000079 | 400781916 | High Sign | HFTD Tier 2 | Distribution | 2001-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000080 | 400792118 | High Sign | HFTD Tier 3 | Distribution | 2001-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000081 | 400979703 | High Sign | HFTD Tier 3 | Distribution | 2001-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000082 | 400980154 | High Sign | HFTD Tier 3 | Distribution | 2001-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000083 | 400983429 | High Sign | HFTD Tier 3 | Distribution | 2001-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000084 | 400030878 | Molding | HFTD Tier 3 | Distribution | 2001-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000085 | 400048119 | Molding | HFTD Tier 2 | Distribution | 2001-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000086 | 400064004 | High Sign | HFTD Tier 2 | Distribution | 2001-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000087 | 400110593 | High Sign | HFTD Tier 2 | Distribution | 2001-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000088 | 400185064 | Molding | HFTD Tier 2 | Distribution | 2001-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000089 | 400236864 | Molding | HFTD Tier 2 | Distribution | 2001-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000090 | 400243520 | High Sign | HFTD Tier 2 | Distribution | 2001-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000091 | 400330014 | Molding | HFTD Tier 2 | Distribution | 2001-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000092 | 400347601 | Molding | HFTD Tier 2 | Distribution | 2001-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000093 | 400730363 | High Sign | HFTD Tier 3 | Distribution | 2001-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000094 | 400816018 | High Sign | HFTD Tier 3 | Distribution | 2001-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000095 | 400208504 | High Sign | HFTD Tier 3 | Distribution | 2001-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000096 | 400512452 | High Sign | HFTD Tier 2 | Distribution | 2001-04-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000097 | 400520482 | High Sign | HFTD Tier 3 | Distribution | 2001-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000098 | 400526329 | High Sign | HFTD Tier 3 | Distribution | 2001-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000099 | 400205159 | High Sign | HFTD Tier 2 | Distribution | 2001-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000100 | 400699182 | High Sign | HFTD Tier 3 | Distribution | 2001-07-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000101 | 400043863 | Molding | HFTD Tier 3 | Distribution | 2001-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000102 | 400104401 | High Sign | HFTD Tier 3 | Distribution | 2001-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000103 | 400105320 | Molding | HFTD Tier 3 | Distribution | 2001-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000104 | 400206803 | Molding | HFTD Tier 2 | Distribution | 2001-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000105 | 400237127 | Molding | HFTD Tier 3 | Distribution | 2001-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000106 | 400446072 | High Sign | HFTD Tier 3 | Distribution | 2001-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000107 | 400817037 | High Sign | HFTD Tier 3 | Distribution | 2001-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000108 | 400955216 | High Sign | HFTD Tier 3 | Distribution | 2001-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000109 | 400955346 | Molding | HFTD Tier 3 | Distribution | 2001-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000110 | 400956916 | Molding | HFTD Tier 3 | Distribution | 2001-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000111 | 400969966 | Molding | HFTD Tier 3 | Distribution | 2001-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000112 | 401006618 | High Sign | HFTD Tier 3 | Distribution | 2001-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000113 | 401006619 | Molding | HFTD Tier 3 | Distribution | 2001-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000114 | 400913773 | Molding | HFTD Tier 3 | Distribution | 2001-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000115 | 400741133 | Hardware/Framing | HFTD Tier 2 | Distribution | 2001-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000116 | 400538411 | High Sign | HFTD Tier 3 | Distribution | 2001-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000117 | 400125507 | Molding | HFTD Tier 3 | Distribution | 2001-08-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000118 | 400803320 | High Sign | HFTD Tier 3 | Distribution | 2001-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000119 | 400940537 | High Sign | HFTD Tier 3 | Distribution | 2001-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000120 | 400579678 | High Sign | HFTD Tier 3 | Distribution | 2001-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000121 | 400718927 | Molding | HFTD Tier 3 | Distribution | 2001-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000122 | 400748122 | Molding | HFTD Tier 3 | Distribution | 2001-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000123 | 400749772 | High Sign | HFTD Tier 3 | Distribution | 2001-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000124 | 400804013 | High Sign | HFTD Tier 3 | Distribution | 2001-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000125 | 400806834 | High Sign | HFTD Tier 3 | Distribution | 2001-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000126 | 400860186 | High Sign | HFTD Tier 2 | Distribution | 2001-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000127 | 400866946 | High Sign | HFTD Tier 2 | Distribution | 2001-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000128 | 400943494 | High Sign | HFTD Tier 3 | Distribution | 2001-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000129 | 400967484 | High Sign | HFTD Tier 2 | Distribution | 2001-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000130 | 400968246 | High Sign | HFTD Tier 2 | Distribution | 2001-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000131 | 400969507 | High Sign | HFTD Tier 2 | Distribution | 2001-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000132 | 400970129 | High Sign | HFTD Tier 2 | Distribution | 2001-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000133 | 400977647 | High Sign | HFTD Tier 2 | Distribution | 2001-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000134 | 400977752 | High Sign | HFTD Tier 2 | Distribution | 2001-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000135 | 400978067 | High Sign | HFTD Tier 2 | Distribution | 2001-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000136 | 400704891 | Molding | HFTD Tier 3 | Distribution | 2001-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000137 | 400861158 | High Sign | HFTD Tier 3 | Distribution | 2001-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000138 | 400861587 | High Sign | HFTD Tier 3 | Distribution | 2001-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000139 | 400868114 | High Sign | HFTD Tier 3 | Distribution | 2001-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000140 | 400869662 | High Sign | HFTD Tier 3 | Distribution | 2001-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000141 | 400870296 | High Sign | HFTD Tier 2 | Distribution | 2001-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000142 | 400873315 | High Sign | HFTD Tier 3 | Distribution | 2001-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000143 | 400942648 | High Sign | HFTD Tier 3 | Distribution | 2001-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000144 | 400970301 | High Sign | HFTD Tier 3 | Distribution | 2001-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000145 | 400972461 | High Sign | HFTD Tier 3 | Distribution | 2001-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000146 | 400973383 | High Sign | HFTD Tier 3 | Distribution | 2001-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000147 | 400977682 | High Sign | HFTD Tier 3 | Distribution | 2001-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000148 | 400978006 | High Sign | HFTD Tier 2 | Distribution | 2001-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000149 | 400659642 | Molding | HFTD Tier 2 | Distribution | 2001-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000150 | 400808694 | Molding | HFTD Tier 2 | Distribution | 2001-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000151 | 401001192 | Cable/Conductor | HFTD Tier 2 | Distribution | 2001-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000152 | 400867857 | Molding | HFTD Tier 2 | Distribution | 2001-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000153 | 400877805 | High Sign | HFTD Tier 2 | Distribution | 2001-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000154 | 400921053 | High Sign | HFTD Tier 2 | Distribution | 2001-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000155 | 400924569 | Molding | HFTD Tier 2 | Distribution | 2001-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000156 | 400105476 | High Sign | HFTD Tier 3 | Distribution | 2001-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000157 | 400110893 | High Sign | HFTD Tier 3 | Distribution | 2001-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000158 | 400139675 | High Sign | HFTD Tier 2 | Distribution | 2001-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000159 | 400147423 | High Sign | HFTD Tier 3 | Distribution | 2001-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000160 | 400170252 | High Sign | HFTD Tier 3 | Distribution | 2001-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000161 | 400171394 | High Sign | HFTD Tier 3 | Distribution | 2001-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000162 | 400867031 | Insulator | HFTD Tier 2 | Distribution | 2001-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000163 | 400151421 | High Sign | HFTD Tier 3 | Distribution | 2001-08-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000164 | 400156054 | High Sign | HFTD Tier 3 | Distribution | 2001-08-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000165 | 400156058 | High Sign | HFTD Tier 3 | Distribution | 2001-08-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000166 | 400161452 | High Sign | HFTD Tier 3 | Distribution | 2001-08-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000167 | 400572472 | High Sign | HFTD Tier 3 | Distribution | 2001-08-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000168 | 400174269 | Molding | HFTD Tier 2 | Distribution | 2001-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000169 | 400336903 | Molding | HFTD Tier 3 | Distribution | 2001-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000170 | 400856286 | Molding | HFTD Tier 3 | Distribution | 2001-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000171 | 400916341 | High Sign | HFTD Tier 3 | Distribution | 2001-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000172 | 400974622 | Molding | HFTD Tier 3 | Distribution | 2001-08-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000173 | 400222014 | High Sign | HFTD Tier 3 | Distribution | 2001-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000174 | 400889516 | Molding | HFTD Tier 3 | Distribution | 2001-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000175 | 400890026 | Molding | HFTD Tier 3 | Distribution | 2001-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000176 | 400893698 | Molding | HFTD Tier 3 | Distribution | 2001-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000177 | 400896220 | Molding | HFTD Tier 3 | Distribution | 2001-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000178 | 400975405 | High Sign | HFTD Tier 3 | Distribution | 2001-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000179 | 400976968 | High Sign | HFTD Tier 2 | Distribution | 2001-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000180 | 400979094 | High Sign | HFTD Tier 3 | Distribution | 2001-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000181 | 400233507 | High Sign | HFTD Tier 2 | Distribution | 2001-08-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000182 | 400560598 | Hardware/Framing | HFTD Tier 3 | Distribution | 2001-08-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000183 | 400891729 | High Sign | HFTD Tier 3 | Distribution | 2001-08-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000184 | 400975579 | Molding | HFTD Tier 3 | Distribution | 2001-08-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000185 | 400976375 | Molding | HFTD Tier 3 | Distribution | 2001-08-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000186 | 400976523 | High Sign | HFTD Tier 3 | Distribution | 2001-08-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000187 | 400976740 | High Sign | HFTD Tier 3 | Distribution | 2001-08-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000188 | 400976987 | High Sign | HFTD Tier 3 | Distribution | 2001-08-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000189 | 400979251 | High Sign | HFTD Tier 3 | Distribution | 2001-08-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000190 | 400229589 | High Sign | HFTD Tier 3 | Distribution | 2001-08-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000191 | 400229677 | High Sign | HFTD Tier 2 | Distribution | 2001-08-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000192 | 400240920 | High Sign | HFTD Tier 3 | Distribution | 2001-08-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000193 | 400243524 | High Sign | HFTD Tier 3 | Distribution | 2001-08-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000194 | 400246515 | High Sign | HFTD Tier 2 | Distribution | 2001-08-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000195 | 400170044 | High Sign | HFTD Tier 2 | Distribution | 2001-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000196 | 400177057 | Hardware/Framing | HFTD Tier 2 | Distribution | 2001-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000197 | 400213479 | High Sign | HFTD Tier 2 | Distribution | 2001-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000198 | 400724531 | High Sign | HFTD Tier 3 | Distribution | 2001-09-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000199 | 400729793 | Hardware/Framing | HFTD Tier 3 | Distribution | 2001-09-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000200 | 400249373 | High Sign | HFTD Tier 2 | Distribution | 2001-09-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000201 | 400574877 | High Sign | HFTD Tier 2 | Distribution | 2001-09-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000202 | 400633588 | High Sign | HFTD Tier 2 | Distribution | 2001-09-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000203 | 400737924 | Guy | HFTD Tier 2 | Distribution | 2001-09-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000204 | 401006580 | High Sign | HFTD Tier 3 | Distribution | 2001-09-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000205 | 400977320 | Molding | HFTD Tier 3 | Distribution | 2001-09-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000206 | 400010692 | High Sign | HFTD Tier 3 | Distribution | 2001-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000207 | 400010946 | Crossarm | HFTD Tier 3 | Distribution | 2001-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000208 | 400011159 | High Sign | HFTD Tier 3 | Distribution | 2001-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000209 | 400011439 | High Sign | HFTD Tier 3 | Distribution | 2001-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000210 | 400194332 | High Sign | HFTD Tier 2 | Distribution | 2001-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000211 | 400194580 | High Sign | HFTD Tier 2 | Distribution | 2001-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000212 | 400236262 | High Sign | HFTD Tier 2 | Distribution | 2001-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000213 | 400265707 | High Sign | HFTD Tier 2 | Distribution | 2001-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000214 | 400380557 | High Sign | HFTD Tier 3 | Distribution | 2001-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000215 | 400445082 | Molding | HFTD Tier 3 | Distribution | 2001-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000216 | 400463716 | High Sign | HFTD Tier 3 | Distribution | 2001-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000217 | 400504740 | Crossarm | HFTD Tier 3 | Distribution | 2001-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000218 | 400976616 | Molding | HFTD Tier 3 | Distribution | 2001-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000219 | 400977016 | Molding | HFTD Tier 3 | Distribution | 2001-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000220 | 400977017 | High Sign | HFTD Tier 3 | Distribution | 2001-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000221 | 400900921 | High Sign | HFTD Tier 2 | Distribution | 2001-09-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000222 | 400977466 | High Sign | HFTD Tier 2 | Distribution | 2001-09-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000223 | 401006625 | Molding | HFTD Tier 2 | Distribution | 2001-09-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000224 | 400577802 | Molding | HFTD Tier 3 | Distribution | 2001-09-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000225 | 400911259 | Molding | HFTD Tier 3 | Distribution | 2001-09-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000226 | 400979606 | High Sign | HFTD Tier 3 | Distribution | 2001-09-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000227 | 400979964 | High Sign | HFTD Tier 3 | Distribution | 2001-09-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000228 | 400980007 | High Sign | HFTD Tier 3 | Distribution | 2001-09-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000229 | 400980024 | Molding | HFTD Tier 3 | Distribution | 2001-09-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000230 | 400980073 | Molding | HFTD Tier 3 | Distribution | 2001-09-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000231 | 400608935 | Molding | HFTD Tier 3 | Distribution | 2001-09-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000232 | 400267159 | High Sign | HFTD Tier 2 | Distribution | 2001-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000233 | 400424904 | High Sign | HFTD Tier 3 | Distribution | 2001-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000234 | 400440149 | Molding | HFTD Tier 3 | Distribution | 2001-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000235 | 400443874 | High Sign | HFTD Tier 3 | Distribution | 2001-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000236 | 400580492 | High Sign | HFTD Tier 3 | Distribution | 2001-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000237 | 400581446 | High Sign | HFTD Tier 3 | Distribution | 2001-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000238 | 400587241 | High Sign | HFTD Tier 3 | Distribution | 2001-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000239 | 400654319 | High Sign | HFTD Tier 3 | Distribution | 2001-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000240 | 400914535 | High Sign | HFTD Tier 3 | Distribution | 2001-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000241 | 400917261 | Molding | HFTD Tier 3 | Distribution | 2001-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000242 | 400917265 | High Sign | HFTD Tier 3 | Distribution | 2001-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000243 | 400918261 | High Sign | HFTD Tier 3 | Distribution | 2001-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000244 | 400956905 | High Sign | HFTD Tier 3 | Distribution | 2001-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000245 | 400977564 | High Sign | HFTD Tier 3 | Distribution | 2001-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000246 | 400980335 | Molding | HFTD Tier 3 | Distribution | 2001-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000247 | 413847903 | Molding | HFTD Tier 3 | Distribution | 2001-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000248 | 400221021 | High Sign | HFTD Tier 2 | Distribution | 2001-09-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000249 | 400275175 | High Sign | HFTD Tier 2 | Distribution | 2001-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000250 | 400297260 | High Sign | HFTD Tier 2 | Distribution | 2001-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000251 | 400299570 | High Sign | HFTD Tier 3 | Distribution | 2001-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000252 | 400920948 | High Sign | HFTD Tier 3 | Distribution | 2001-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000253 | 400237882 | High Sign | HFTD Tier 2 | Distribution | 2001-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000254 | 400312283 | High Sign | HFTD Tier 2 | Distribution | 2001-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000255 | 400315198 | High Sign | HFTD Tier 2 | Distribution | 2001-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000256 | 400330996 | High Sign | HFTD Tier 2 | Distribution | 2001-09-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000257 | 401003953 | Cable/Conductor | HFTD Tier 2 | Distribution | 2001-09-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000258 | 400252213 | High Sign | HFTD Tier 2 | Distribution | 2001-09-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000259 | 400254691 | High Sign | HFTD Tier 2 | Distribution | 2001-09-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000260 | 400824418 | Molding | HFTD Tier 3 | Distribution | 2001-09-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000261 | 400929443 | High Sign | HFTD Tier 3 | Distribution | 2001-09-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000262 | 400931538 | Molding | HFTD Tier 3 | Distribution | 2001-09-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000263 | 400980659 | Molding | HFTD Tier 3 | Distribution | 2001-09-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000264 | 400980838 | High Sign | HFTD Tier 3 | Distribution | 2001-09-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000265 | 400328411 | High Sign | HFTD Tier 3 | Distribution | 2001-09-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000266 | 400689388 | High Sign | HFTD Tier 2 | Distribution | 2001-09-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000267 | 400689702 | Molding | HFTD Tier 2 | Distribution | 2001-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000268 | 400327216 | High Sign | HFTD Tier 2 | Distribution | 2001-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000269 | 400612729 | High Sign | HFTD Tier 3 | Distribution | 2001-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000270 | 400930963 | Hardware/Framing | HFTD Tier 3 | Distribution | 2001-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000271 | 400981879 | Molding | HFTD Tier 3 | Distribution | 2001-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000272 | 400357182 | High Sign | HFTD Tier 2 | Distribution | 2001-09-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000273 | 400360720 | High Sign | HFTD Tier 2 | Distribution | 2001-09-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000274 | 400852098 | High Sign | HFTD Tier 3 | Distribution | 2001-09-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000275 | 400946131 | High Sign | HFTD Tier 3 | Distribution | 2001-09-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000276 | 400980981 | Molding | HFTD Tier 3 | Distribution | 2001-09-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000277 | 400981120 | Guy | HFTD Tier 3 | Distribution | 2001-09-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000278 | 400982293 | Molding | HFTD Tier 3 | Distribution | 2001-09-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000279 | 400982436 | High Sign | HFTD Tier 3 | Distribution | 2001-09-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000280 | 401006657 | High Sign | HFTD Tier 3 | Distribution | 2001-09-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000281 | 400418021 | Molding | HFTD Tier 3 | Distribution | 2001-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000282 | 400813602 | Molding | HFTD Tier 3 | Distribution | 2001-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000283 | 400867479 | Molding | HFTD Tier 3 | Distribution | 2001-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000284 | 400868648 | Molding | HFTD Tier 3 | Distribution | 2001-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000285 | 400872117 | High Sign | HFTD Tier 3 | Distribution | 2001-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000286 | 400945900 | Molding | HFTD Tier 3 | Distribution | 2001-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000287 | 400951357 | Molding | HFTD Tier 3 | Distribution | 2001-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000288 | 400981210 | Molding | HFTD Tier 3 | Distribution | 2001-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000289 | 400981381 | Molding | HFTD Tier 3 | Distribution | 2001-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000290 | 400981525 | Molding | HFTD Tier 3 | Distribution | 2001-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000291 | 400981610 | Molding | HFTD Tier 3 | Distribution | 2001-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000292 | 400982572 | Molding | HFTD Tier 3 | Distribution | 2001-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000293 | 401006626 | High Sign | HFTD Tier 3 | Distribution | 2001-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000294 | 401006627 | Molding | HFTD Tier 3 | Distribution | 2001-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000295 | 401006644 | High Sign | HFTD Tier 2 | Distribution | 2001-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000296 | 400418376 | High Sign | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000297 | 400420087 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000298 | 400421773 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000299 | 400421787 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000300 | 400423668 | High Sign | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000301 | 400428871 | High Sign | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000302 | 400448912 | High Sign | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000303 | 400450406 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000304 | 400452667 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000305 | 400453910 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000306 | 400454755 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000307 | 400619162 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000308 | 400619235 | High Sign | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000309 | 400621456 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000310 | 400627539 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000311 | 400685830 | High Sign | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000312 | 400737620 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000313 | 400851479 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000314 | 400852505 | High Sign | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000315 | 400872127 | High Sign | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000316 | 400880343 | High Sign | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000317 | 400881393 | High Sign | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000318 | 400881444 | High Sign | HFTD Tier 2 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000319 | 400929494 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000320 | 400931842 | High Sign | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000321 | 400931886 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000322 | 400933184 | Hardware/Framing | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000323 | 400934554 | High Sign | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000324 | 400934558 | High Sign | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000325 | 400938020 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000326 | 400981779 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000327 | 400981936 | High Sign | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000328 | 400981943 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000329 | 400982008 | High Sign | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000330 | 400982077 | High Sign | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000331 | 400982110 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000332 | 400982248 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000333 | 400982254 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000334 | 400983446 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000335 | 400983616 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000336 | 401006566 | Guy | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000337 | 401006583 | High Sign | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000338 | 401006584 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000339 | 401006707 | High Sign | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000340 | 401006709 | Molding | HFTD Tier 3 | Distribution | 2001-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000341 | 400037979 | Molding | HFTD Tier 3 | Distribution | 2001-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000342 | 400687140 | High Sign | HFTD Tier 3 | Distribution | 2001-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000343 | 400693932 | High Sign | HFTD Tier 2 | Distribution | 2001-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000344 | 400883847 | High Sign | HFTD Tier 3 | Distribution | 2001-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000345 | 400894406 | Molding | HFTD Tier 3 | Distribution | 2001-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000346 | 400896013 | High Sign | HFTD Tier 3 | Distribution | 2001-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000347 | 400896058 | High Sign | HFTD Tier 2 | Distribution | 2001-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000348 | 400941059 | High Sign | HFTD Tier 3 | Distribution | 2001-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000349 | 400942170 | High Sign | HFTD Tier 3 | Distribution | 2001-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000350 | 400420310 | Molding | HFTD Tier 3 | Distribution | 2001-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000351 | 400431204 | Molding | HFTD Tier 3 | Distribution | 2001-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000352 | 400446652 | Molding | HFTD Tier 3 | Distribution | 2001-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000353 | 400447414 | Molding | HFTD Tier 3 | Distribution | 2001-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000354 | 400449322 | High Sign | HFTD Tier 3 | Distribution | 2001-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000355 | 400451237 | High Sign | HFTD Tier 3 | Distribution | 2001-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000356 | 400566350 | Molding | HFTD Tier 3 | Distribution | 2001-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000357 | 400886873 | Molding | HFTD Tier 3 | Distribution | 2001-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000358 | 400896068 | Molding | HFTD Tier 3 | Distribution | 2001-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000359 | 400956690 | High Sign | HFTD Tier 3 | Distribution | 2001-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000360 | 400957986 | High Sign | HFTD Tier 3 | Distribution | 2001-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000361 | 400982204 | High Sign | HFTD Tier 3 | Distribution | 2001-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000362 | 400982490 | Molding | HFTD Tier 3 | Distribution | 2001-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000363 | 400984146 | High Sign | HFTD Tier 3 | Distribution | 2001-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000364 | 400043787 | High Sign | HFTD Tier 2 | Distribution | 2001-10-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000365 | 400047306 | Molding | HFTD Tier 2 | Distribution | 2001-10-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000366 | 400056603 | High Sign | HFTD Tier 2 | Distribution | 2001-10-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000367 | 400431353 | Molding | HFTD Tier 3 | Distribution | 2001-10-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000368 | 400580239 | High Sign | HFTD Tier 2 | Distribution | 2001-10-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000369 | 400640945 | High Sign | HFTD Tier 2 | Distribution | 2001-10-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000370 | 400640993 | Riser/Conduit | HFTD Tier 2 | Distribution | 2001-10-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000371 | 400690052 | Molding | HFTD Tier 2 | Distribution | 2001-10-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000372 | 400765368 | High Sign | HFTD Tier 2 | Distribution | 2001-10-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000373 | 400767555 | Molding | HFTD Tier 2 | Distribution | 2001-10-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000374 | 401006520 | Molding | HFTD Tier 3 | Distribution | 2001-10-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000375 | 400504625 | Molding | HFTD Tier 3 | Distribution | 2001-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000376 | 401006002 | High Sign | HFTD Tier 2 | Distribution | 2001-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000377 | 401006003 | Molding | HFTD Tier 2 | Distribution | 2001-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000378 | 401006558 | High Sign | HFTD Tier 3 | Distribution | 2001-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000379 | 400569135 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000380 | 400569612 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000381 | 400570387 | Molding | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000382 | 400570443 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000383 | 400575080 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000384 | 400577033 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000385 | 400577487 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000386 | 400577593 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000387 | 400586368 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000388 | 400589938 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000389 | 400815119 | Cable/Conductor | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000390 | 400890196 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000391 | 400891885 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000392 | 400898114 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000393 | 400900735 | Cable/Conductor | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000394 | 400902041 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000395 | 400907747 | Insulator | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000396 | 400957512 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000397 | 400959783 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000398 | 400960711 | Molding | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000399 | 400961109 | Molding | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000400 | 400961660 | Cable/Conductor | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000401 | 400962329 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000402 | 400962416 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000403 | 400982607 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000404 | 400982649 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000405 | 400982688 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000406 | 400982796 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000407 | 400982879 | High Sign | HFTD Tier 3 | Distribution | 2001-10-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000408 | 400929757 | High Sign | HFTD Tier 3 | Distribution | 2001-10-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000409 | 400908273 | High Sign | HFTD Tier 3 | Distribution | 2001-10-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000410 | 400799108 | High Sign | HFTD Tier 2 | Distribution | 2001-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000411 | 400908360 | High Sign | HFTD Tier 3 | Distribution | 2001-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000412 | 401003209 | High Sign | HFTD Tier 2 | Distribution | 2001-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000413 | 400278002 | Molding | HFTD Tier 2 | Distribution | 2001-10-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000414 | 400573271 | High Sign | HFTD Tier 2 | Distribution | 2001-10-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000415 | 400950815 | Molding | HFTD Tier 2 | Distribution | 2001-10-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000416 | 400427261 | Molding | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000417 | 400427377 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000418 | 400599271 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000419 | 400601527 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000420 | 400605580 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000421 | 400607524 | Molding | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000422 | 400607801 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000423 | 400616225 | Molding | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000424 | 400643497 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000425 | 400650374 | Cable/Conductor | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000426 | 400659495 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000427 | 400659550 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000428 | 400664832 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000429 | 400665344 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000430 | 400665403 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000431 | 400668056 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000432 | 400669021 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000433 | 400671442 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000434 | 400672306 | Cable/Conductor | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000435 | 400945815 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000436 | 400945905 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000437 | 400945929 | Molding | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000438 | 400946317 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000439 | 400946320 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000440 | 400946978 | Cable/Conductor | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000441 | 400947086 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000442 | 400947110 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000443 | 400949244 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000444 | 400949767 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000445 | 400949865 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000446 | 400973415 | Molding | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000447 | 400973420 | Molding | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000448 | 400973430 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000449 | 400973799 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000450 | 400973804 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000451 | 400974226 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000452 | 400975011 | Cable/Conductor | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000453 | 400975310 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000454 | 400975318 | Molding | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000455 | 400975469 | High Sign | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000456 | 400975559 | Molding | HFTD Tier 3 | Distribution | 2001-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000457 | 400451706 | Hardware/Framing | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000458 | 400454107 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000459 | 400459853 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000460 | 400463059 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000461 | 400558775 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000462 | 400570400 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000463 | 400599565 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000464 | 400605598 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000465 | 400606635 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000466 | 400610041 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000467 | 400612533 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000468 | 400624879 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000469 | 400626460 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000470 | 400633404 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000471 | 400635676 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000472 | 400635780 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000473 | 400635785 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000474 | 400635789 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000475 | 400636830 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000476 | 400638664 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000477 | 400640894 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000478 | 400641014 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000479 | 400644098 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000480 | 400645670 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000481 | 400646794 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000482 | 400646798 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000483 | 400646849 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000484 | 400650471 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000485 | 400650476 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000486 | 400651850 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000487 | 400681602 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000488 | 400682501 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000489 | 400692961 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000490 | 400693977 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000491 | 400694032 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000492 | 400696161 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000493 | 400715344 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000494 | 400718595 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000495 | 400848453 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000496 | 400906712 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000497 | 400953617 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000498 | 400953893 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000499 | 400955133 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000500 | 400955160 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000501 | 400955258 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000502 | 400955690 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000503 | 400955711 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000504 | 400955716 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000505 | 400956857 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000506 | 400957226 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000507 | 400957252 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000508 | 400958678 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000509 | 400960192 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000510 | 400977292 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000511 | 400977331 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000512 | 400977351 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000513 | 400977480 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000514 | 400977531 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000515 | 400977534 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000516 | 400977830 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000517 | 400977834 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000518 | 400977917 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000519 | 400977998 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000520 | 400978142 | High Sign | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000521 | 401001195 | Cable/Conductor | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000522 | 401001197 | Cable/Conductor | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000523 | 401001198 | Cable/Conductor | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000524 | 401001202 | Cable/Conductor | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000525 | 401006484 | Molding | HFTD Tier 3 | Distribution | 2001-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000526 | 400677867 | High Sign | HFTD Tier 3 | Distribution | 2001-10-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000527 | 400741216 | Guy | HFTD Tier 3 | Distribution | 2001-10-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000528 | 400759386 | High Sign | HFTD Tier 3 | Distribution | 2001-10-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000529 | 400770707 | High Sign | HFTD Tier 3 | Distribution | 2001-10-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000530 | 400941469 | Guy | HFTD Tier 3 | Distribution | 2001-10-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000531 | 400942258 | High Sign | HFTD Tier 2 | Distribution | 2001-10-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000532 | 400942723 | Molding | HFTD Tier 3 | Distribution | 2001-10-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000533 | 400943411 | Molding | HFTD Tier 2 | Distribution | 2001-10-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000534 | 400956896 | High Sign | HFTD Tier 3 | Distribution | 2001-10-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000535 | 400504131 | Molding | HFTD Tier 3 | Distribution | 2001-10-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000536 | 400504315 | Molding | HFTD Tier 3 | Distribution | 2001-10-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000537 | 400612545 | Molding | HFTD Tier 2 | Distribution | 2001-10-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000538 | 400612631 | High Sign | HFTD Tier 2 | Distribution | 2001-10-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000539 | 400615800 | Molding | HFTD Tier 3 | Distribution | 2001-10-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000540 | 400617014 | Molding | HFTD Tier 3 | Distribution | 2001-10-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000541 | 400619065 | Molding | HFTD Tier 3 | Distribution | 2001-10-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000542 | 400620298 | High Sign | HFTD Tier 3 | Distribution | 2001-10-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000543 | 400625423 | Guy | HFTD Tier 3 | Distribution | 2001-10-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000544 | 400751702 | High Sign | HFTD Tier 3 | Distribution | 2001-10-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000545 | 400993857 | Cable/Conductor | HFTD Tier 3 | Distribution | 2001-10-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000546 | 400461162 | High Sign | HFTD Tier 3 | Distribution | 2001-11-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000547 | 400497930 | Molding | HFTD Tier 3 | Distribution | 2001-11-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000548 | 400011500 | High Sign | HFTD Tier 3 | Distribution | 2001-11-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000549 | 400560247 | High Sign | HFTD Tier 3 | Distribution | 2001-11-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000550 | 400564117 | High Sign | HFTD Tier 3 | Distribution | 2001-11-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000551 | 400573016 | Molding | HFTD Tier 2 | Distribution | 2001-11-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000552 | 400746378 | High Sign | HFTD Tier 2 | Distribution | 2001-11-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000553 | 400753042 | Riser/Conduit | HFTD Tier 2 | Distribution | 2001-11-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000554 | 400908036 | Molding | HFTD Tier 2 | Distribution | 2001-11-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000555 | 400591490 | Molding | HFTD Tier 2 | Distribution | 2001-11-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000556 | 400676544 | Molding | HFTD Tier 3 | Distribution | 2001-11-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000557 | 400693546 | Molding | HFTD Tier 2 | Distribution | 2001-11-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000558 | 400655624 | Molding | HFTD Tier 3 | Distribution | 2001-11-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000559 | 400657948 | Molding | HFTD Tier 3 | Distribution | 2001-11-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000560 | 400499745 | Molding | HFTD Tier 2 | Distribution | 2001-11-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000561 | 400553062 | Molding | HFTD Tier 2 | Distribution | 2001-11-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000562 | 400957373 | Insulator | HFTD Tier 3 | Distribution | 2001-11-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000563 | 400959585 | High Sign | HFTD Tier 2 | Distribution | 2001-11-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000564 | 401006054 | High Sign | HFTD Tier 2 | Distribution | 2001-11-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000565 | 401006641 | High Sign | HFTD Tier 3 | Distribution | 2001-11-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000566 | 401006642 | Molding | HFTD Tier 3 | Distribution | 2001-11-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000567 | 400710594 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2001-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000568 | 401006633 | High Sign | HFTD Tier 3 | Distribution | 2001-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000569 | 400575035 | Guy | HFTD Tier 3 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000570 | 400693270 | High Sign | HFTD Tier 2 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000571 | 400725219 | Molding | HFTD Tier 2 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000572 | 400738583 | Molding | HFTD Tier 3 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000573 | 400742510 | Molding | HFTD Tier 3 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000574 | 400789614 | High Sign | HFTD Tier 3 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000575 | 400858143 | Molding | HFTD Tier 3 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000576 | 400867580 | High Sign | HFTD Tier 3 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000577 | 400868325 | High Sign | HFTD Tier 3 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000578 | 400871437 | High Sign | HFTD Tier 3 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000579 | 400923784 | High Sign | HFTD Tier 2 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000580 | 400929502 | High Sign | HFTD Tier 2 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000581 | 400977324 | High Sign | HFTD Tier 3 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000582 | 400979699 | Molding | HFTD Tier 3 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000583 | 400979795 | High Sign | HFTD Tier 3 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000584 | 400981612 | High Sign | HFTD Tier 3 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000585 | 400983017 | Molding | HFTD Tier 3 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000586 | 400983209 | Molding | HFTD Tier 3 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000587 | 400983210 | High Sign | HFTD Tier 3 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000588 | 400983214 | High Sign | HFTD Tier 3 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000589 | 401006579 | Molding | HFTD Tier 3 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000590 | 401006664 | Molding | HFTD Tier 3 | Distribution | 2001-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000591 | 400467542 | High Sign | HFTD Tier 3 | Distribution | 2001-11-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000592 | 401003794 | High Sign | HFTD Tier 3 | Distribution | 2001-11-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000593 | 401006542 | High Sign | HFTD Tier 3 | Distribution | 2001-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000594 | 400460100 | Molding | HFTD Tier 3 | Distribution | 2001-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000595 | 400477721 | Molding | HFTD Tier 3 | Distribution | 2001-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000596 | 400607230 | High Sign | HFTD Tier 3 | Distribution | 2001-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000597 | 400631166 | Insulator | HFTD Tier 2 | Distribution | 2001-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000598 | 400906359 | High Sign | HFTD Tier 2 | Distribution | 2001-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000599 | 400914639 | Molding | HFTD Tier 2 | Distribution | 2001-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000600 | 400963232 | Molding | HFTD Tier 3 | Distribution | 2001-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000601 | 400964218 | Molding | HFTD Tier 3 | Distribution | 2001-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000602 | 400993420 | Cable/Conductor | HFTD Tier 2 | Distribution | 2001-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000603 | 400035680 | Molding | HFTD Tier 3 | Distribution | 2001-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000604 | 400481300 | High Sign | HFTD Tier 2 | Distribution | 2001-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000605 | 400580925 | Molding | HFTD Tier 3 | Distribution | 2001-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000606 | 400591083 | High Sign | HFTD Tier 3 | Distribution | 2001-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000607 | 400656586 | High Sign | HFTD Tier 3 | Distribution | 2001-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000608 | 400705742 | High Sign | HFTD Tier 3 | Distribution | 2001-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000609 | 400710228 | High Sign | HFTD Tier 3 | Distribution | 2001-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000610 | 400712976 | Molding | HFTD Tier 3 | Distribution | 2001-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000611 | 400763841 | High Sign | HFTD Tier 3 | Distribution | 2001-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000612 | 400815463 | Molding | HFTD Tier 3 | Distribution | 2001-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000613 | 400938914 | High Sign | HFTD Tier 3 | Distribution | 2001-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000614 | 400944098 | High Sign | HFTD Tier 3 | Distribution | 2001-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000615 | 400944113 | High Sign | HFTD Tier 3 | Distribution | 2001-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000616 | 400960832 | High Sign | HFTD Tier 3 | Distribution | 2001-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000617 | 400962845 | Molding | HFTD Tier 3 | Distribution | 2001-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000618 | 400547189 | Molding | HFTD Tier 2 | Distribution | 2001-11-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000619 | 400453494 | Molding | HFTD Tier 3 | Distribution | 2001-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000620 | 400703947 | High Sign | HFTD Tier 3 | Distribution | 2001-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000621 | 400705816 | Molding | HFTD Tier 3 | Distribution | 2001-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000622 | 400935655 | High Sign | HFTD Tier 3 | Distribution | 2001-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000623 | 400939214 | Molding | HFTD Tier 3 | Distribution | 2001-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000624 | 400962287 | Molding | HFTD Tier 3 | Distribution | 2001-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000625 | 400964658 | Molding | HFTD Tier 3 | Distribution | 2001-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000626 | 400964663 | High Sign | HFTD Tier 3 | Distribution | 2001-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000627 | 400540707 | High Sign | HFTD Tier 2 | Distribution | 2001-11-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000628 | 400607693 | High Sign | HFTD Tier 3 | Distribution | 2001-11-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000629 | 400616220 | Molding | HFTD Tier 3 | Distribution | 2001-11-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000630 | 400721335 | Molding | HFTD Tier 3 | Distribution | 2001-11-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000631 | 400840581 | Riser/Conduit | HFTD Tier 3 | Distribution | 2001-11-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000632 | 400942632 | High Sign | HFTD Tier 3 | Distribution | 2001-11-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000633 | 400943383 | High Sign | HFTD Tier 3 | Distribution | 2001-11-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000634 | 400966932 | Molding | HFTD Tier 3 | Distribution | 2001-11-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000635 | 400966937 | Molding | HFTD Tier 3 | Distribution | 2001-11-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000636 | 401006679 | High Sign | HFTD Tier 3 | Distribution | 2001-11-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000637 | 401006680 | Molding | HFTD Tier 3 | Distribution | 2001-11-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000638 | 400551440 | Molding | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000639 | 400570268 | Molding | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000640 | 400574777 | Molding | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000641 | 400584765 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000642 | 400587253 | Molding | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000643 | 400590389 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000644 | 400590405 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000645 | 400590437 | High Sign | HFTD Tier 2 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000646 | 400599638 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000647 | 400599682 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000648 | 400601140 | Molding | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000649 | 400607294 | Molding | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000650 | 400630742 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000651 | 400632394 | Molding | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000652 | 400636996 | Molding | HFTD Tier 2 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000653 | 400643636 | Molding | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000654 | 400645158 | Molding | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000655 | 400648078 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000656 | 400652687 | Molding | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000657 | 400657248 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000658 | 400699248 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000659 | 400704788 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000660 | 400713538 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000661 | 400714856 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000662 | 400717143 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000663 | 400718004 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000664 | 400719509 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000665 | 400719581 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000666 | 400719657 | Molding | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000667 | 400721071 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000668 | 400721226 | Molding | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000669 | 400723424 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000670 | 400724402 | Molding | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000671 | 400724495 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000672 | 400725349 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000673 | 400725769 | High Sign | HFTD Tier 2 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000674 | 400726004 | ID Markings | HFTD Tier 2 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000675 | 400726844 | Molding | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000676 | 400732395 | High Sign | HFTD Tier 2 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000677 | 400733641 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000678 | 400733656 | High Sign | HFTD Tier 2 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000679 | 400734804 | High Sign | HFTD Tier 2 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000680 | 400764211 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000681 | 400802350 | High Sign | HFTD Tier 2 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000682 | 400803489 | High Sign | HFTD Tier 2 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000683 | 400819464 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000684 | 400822218 | High Sign | HFTD Tier 2 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000685 | 400832302 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000686 | 400833224 | Molding | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000687 | 400858103 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000688 | 400859563 | Molding | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000689 | 400869506 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000690 | 400875150 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000691 | 400878172 | High Sign | HFTD Tier 2 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000692 | 400878216 | Molding | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000693 | 400880428 | High Sign | HFTD Tier 2 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000694 | 400891805 | High Sign | HFTD Tier 2 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000695 | 400934398 | Molding | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000696 | 400935257 | High Sign | HFTD Tier 2 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000697 | 400936066 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000698 | 400937470 | High Sign | HFTD Tier 2 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000699 | 400937982 | High Sign | HFTD Tier 2 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000700 | 400939199 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000701 | 400939527 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000702 | 400941598 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000703 | 400942112 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000704 | 400942689 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000705 | 400943025 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000706 | 400943453 | Molding | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000707 | 400945869 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000708 | 400947174 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000709 | 400947513 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000710 | 400947518 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000711 | 400953006 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000712 | 400953016 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000713 | 400954223 | Molding | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000714 | 400965971 | High Sign | HFTD Tier 3 | Distribution | 2001-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000715 | 400075704 | High Sign | HFTD Tier 3 | Distribution | 2001-11-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000716 | 400079297 | High Sign | HFTD Tier 3 | Distribution | 2001-11-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000717 | 400096013 | Molding | HFTD Tier 3 | Distribution | 2001-11-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000718 | 400098636 | High Sign | HFTD Tier 3 | Distribution | 2001-11-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000719 | 400563636 | Molding | HFTD Tier 3 | Distribution | 2001-11-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000720 | 400024219 | High Sign | HFTD Tier 2 | Distribution | 2001-11-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000721 | 400722872 | High Sign | HFTD Tier 2 | Distribution | 2001-11-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000722 | 400874281 | High Sign | HFTD Tier 2 | Distribution | 2001-11-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000723 | 400878566 | High Sign | HFTD Tier 2 | Distribution | 2001-11-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000724 | 401006082 | Guy | HFTD Tier 2 | Distribution | 2001-11-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000725 | 400528011 | High Sign | HFTD Tier 3 | Distribution | 2001-11-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000726 | 400757674 | High Sign | HFTD Tier 3 | Distribution | 2001-11-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000727 | 400017029 | Molding | HFTD Tier 2 | Distribution | 2001-11-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000728 | 400204835 | High Sign | HFTD Tier 3 | Distribution | 2001-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000729 | 400480998 | High Sign | HFTD Tier 3 | Distribution | 2001-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000730 | 400802914 | High Sign | HFTD Tier 3 | Distribution | 2001-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000731 | 400847286 | High Sign | HFTD Tier 3 | Distribution | 2001-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000732 | 400848283 | High Sign | HFTD Tier 3 | Distribution | 2001-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000733 | 400898857 | High Sign | HFTD Tier 3 | Distribution | 2001-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000734 | 400902614 | High Sign | HFTD Tier 3 | Distribution | 2001-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000735 | 400902825 | High Sign | HFTD Tier 3 | Distribution | 2001-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000736 | 400057206 | High Sign | HFTD Tier 2 | Distribution | 2001-12-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000737 | 400115149 | Molding | HFTD Tier 2 | Distribution | 2001-12-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000738 | 400020821 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000739 | 400021550 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000740 | 400024878 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000741 | 400551457 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000742 | 400664386 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000743 | 400697321 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000744 | 400697357 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000745 | 400698474 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000746 | 400703959 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000747 | 400703992 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000748 | 400704901 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000749 | 400704987 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000750 | 400706399 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000751 | 400706426 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000752 | 400706442 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000753 | 400707222 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000754 | 400707238 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000755 | 400707281 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000756 | 400708111 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000757 | 400709003 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000758 | 400709073 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000759 | 400710548 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000760 | 400713688 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000761 | 400716299 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000762 | 400717173 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000763 | 400718687 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000764 | 400721010 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000765 | 400723613 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000766 | 400766919 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000767 | 400768222 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000768 | 400768260 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000769 | 400768709 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000770 | 400769287 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000771 | 400770290 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000772 | 400770303 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000773 | 400770317 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000774 | 400770340 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000775 | 400771045 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000776 | 400771633 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000777 | 400772170 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000778 | 400772945 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000779 | 400773801 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000780 | 400774318 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000781 | 400779238 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000782 | 400784661 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000783 | 400880346 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000784 | 400882354 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000785 | 400884694 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000786 | 400892643 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000787 | 400893332 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000788 | 400893396 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000789 | 400895593 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000790 | 400895647 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000791 | 400897691 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000792 | 400897741 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000793 | 400897782 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000794 | 400900872 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000795 | 400902841 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000796 | 400903759 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000797 | 400904161 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000798 | 400907587 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000799 | 400907632 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000800 | 400907637 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000801 | 400907743 | Cable/Conductor | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000802 | 400940289 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000803 | 400969738 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000804 | 400969753 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000805 | 400969758 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000806 | 400969799 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000807 | 400970034 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000808 | 400970583 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000809 | 400970593 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000810 | 400970620 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000811 | 400971296 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000812 | 400971713 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000813 | 400971729 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000814 | 400971964 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000815 | 400971975 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000816 | 400972199 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000817 | 400972596 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000818 | 400972606 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000819 | 400972611 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000820 | 400972620 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000821 | 400972857 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000822 | 400973271 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000823 | 400973281 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000824 | 400973491 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000825 | 400973600 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000826 | 400973784 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000827 | 400974190 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000828 | 400974480 | Molding | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000829 | 400975100 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000830 | 400975112 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000831 | 401001199 | Cable/Conductor | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000832 | 401006482 | High Sign | HFTD Tier 3 | Distribution | 2001-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000833 | 400082170 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000834 | 400110503 | Hardware/Framing | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000835 | 400113544 | High Sign | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000836 | 400529156 | Molding | HFTD Tier 3 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000837 | 400562132 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000838 | 400563273 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000839 | 400566379 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000840 | 400566517 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000841 | 400569814 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000842 | 400569834 | High Sign | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000843 | 400572183 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000844 | 400573315 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000845 | 400574110 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000846 | 400575576 | High Sign | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000847 | 400593309 | High Sign | HFTD Tier 3 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000848 | 400624578 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000849 | 400626763 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000850 | 400633207 | High Sign | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000851 | 400633999 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000852 | 400636243 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000853 | 400638641 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000854 | 400640077 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000855 | 400641234 | High Sign | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000856 | 400644925 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000857 | 400645132 | High Sign | HFTD Tier 3 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000858 | 400649186 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000859 | 400654461 | Molding | HFTD Tier 3 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000860 | 400680253 | Molding | HFTD Tier 3 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000861 | 400719337 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000862 | 400719392 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000863 | 400725107 | High Sign | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000864 | 400726183 | High Sign | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000865 | 400726906 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000866 | 400727991 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000867 | 400728642 | High Sign | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000868 | 400728668 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000869 | 400730059 | High Sign | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000870 | 400731321 | Molding | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000871 | 400734494 | High Sign | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000872 | 400794865 | High Sign | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000873 | 400794904 | High Sign | HFTD Tier 3 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000874 | 400794908 | High Sign | HFTD Tier 3 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000875 | 400943099 | High Sign | HFTD Tier 2 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000876 | 400968068 | Molding | HFTD Tier 3 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000877 | 400968083 | Molding | HFTD Tier 3 | Distribution | 2001-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000878 | 400084288 | High Sign | HFTD Tier 2 | Distribution | 2001-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000879 | 400497746 | Molding | HFTD Tier 2 | Distribution | 2001-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000880 | 400588461 | Molding | HFTD Tier 3 | Distribution | 2001-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000881 | 400591366 | Molding | HFTD Tier 3 | Distribution | 2001-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000882 | 400691685 | High Sign | HFTD Tier 3 | Distribution | 2001-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000883 | 400698538 | High Sign | HFTD Tier 3 | Distribution | 2001-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000884 | 400699407 | Molding | HFTD Tier 3 | Distribution | 2001-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000885 | 400810643 | High Sign | HFTD Tier 3 | Distribution | 2001-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000886 | 400817502 | Molding | HFTD Tier 3 | Distribution | 2001-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000887 | 400967226 | Molding | HFTD Tier 3 | Distribution | 2001-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000888 | 400967231 | High Sign | HFTD Tier 3 | Distribution | 2001-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000889 | 400967957 | High Sign | HFTD Tier 3 | Distribution | 2001-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000890 | 400968368 | High Sign | HFTD Tier 3 | Distribution | 2001-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000891 | 400969187 | High Sign | HFTD Tier 3 | Distribution | 2001-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000892 | 400969216 | High Sign | HFTD Tier 3 | Distribution | 2001-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000893 | 400969489 | High Sign | HFTD Tier 3 | Distribution | 2001-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000894 | 400983925 | Molding | HFTD Tier 3 | Distribution | 2001-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000895 | 400999359 | Cable/Conductor | HFTD Tier 3 | Distribution | 2001-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000896 | 401006099 | Molding | HFTD Tier 3 | Distribution | 2001-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000897 | 400390403 | High Sign | HFTD Tier 2 | Distribution | 2001-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000898 | 400584896 | High Sign | HFTD Tier 3 | Distribution | 2001-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000899 | 400098009 | High Sign | HFTD Tier 2 | Distribution | 2001-12-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000900 | 400138716 | High Sign | HFTD Tier 2 | Distribution | 2001-12-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000901 | 400502524 | High Sign | HFTD Tier 2 | Distribution | 2001-12-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000902 | 400544025 | Hardware/Framing | HFTD Tier 2 | Distribution | 2001-12-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000903 | 400553020 | High Sign | HFTD Tier 2 | Distribution | 2001-12-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000904 | 400904180 | Hardware/Framing | HFTD Tier 2 | Distribution | 2001-12-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000905 | 400973093 | Molding | HFTD Tier 2 | Distribution | 2001-12-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000906 | 400998123 | Cable/Conductor | HFTD Tier 3 | Distribution | 2001-12-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000907 | 400321595 | High Sign | HFTD Tier 3 | Distribution | 2001-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000908 | 400564057 | High Sign | HFTD Tier 3 | Distribution | 2001-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000909 | 400581429 | High Sign | HFTD Tier 3 | Distribution | 2001-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000910 | 400589893 | Molding | HFTD Tier 3 | Distribution | 2001-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000911 | 400591581 | High Sign | HFTD Tier 3 | Distribution | 2001-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000912 | 400651218 | Molding | HFTD Tier 3 | Distribution | 2001-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000913 | 400657706 | Molding | HFTD Tier 3 | Distribution | 2001-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000914 | 400661690 | High Sign | HFTD Tier 3 | Distribution | 2001-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000915 | 400701900 | High Sign | HFTD Tier 3 | Distribution | 2001-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000916 | 400715165 | Cable/Conductor | HFTD Tier 3 | Distribution | 2001-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000917 | 400717184 | High Sign | HFTD Tier 3 | Distribution | 2001-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000918 | 400755950 | Riser/Conduit | HFTD Tier 3 | Distribution | 2001-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000919 | 400757387 | High Sign | HFTD Tier 3 | Distribution | 2001-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000920 | 400769425 | Molding | HFTD Tier 3 | Distribution | 2001-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000921 | 400954366 | Molding | HFTD Tier 3 | Distribution | 2001-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000922 | 400963471 | Guy | HFTD Tier 3 | Distribution | 2001-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000923 | 400971793 | High Sign | HFTD Tier 3 | Distribution | 2001-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000924 | 401004253 | High Sign | HFTD Tier 2 | Distribution | 2001-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000925 | 401006608 | High Sign | HFTD Tier 3 | Distribution | 2001-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000926 | 400027955 | Molding | HFTD Tier 2 | Distribution | 2001-12-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000927 | 400165287 | High Sign | HFTD Tier 2 | Distribution | 2001-12-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000928 | 400119246 | High Sign | HFTD Tier 2 | Distribution | 2001-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000929 | 400510635 | High Sign | HFTD Tier 2 | Distribution | 2001-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000930 | 400654769 | Molding | HFTD Tier 3 | Distribution | 2001-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000931 | 400662719 | High Sign | HFTD Tier 3 | Distribution | 2001-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000932 | 400725899 | Molding | HFTD Tier 3 | Distribution | 2001-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000933 | 400726888 | High Sign | HFTD Tier 3 | Distribution | 2001-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000934 | 400731734 | High Sign | HFTD Tier 3 | Distribution | 2001-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000935 | 400999476 | Cable/Conductor | HFTD Tier 3 | Distribution | 2001-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000936 | 401006652 | High Sign | HFTD Tier 3 | Distribution | 2001-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000937 | 400106620 | Molding | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000938 | 400150426 | High Sign | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000939 | 400152173 | High Sign | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000940 | 400157103 | High Sign | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000941 | 400172497 | High Sign | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000942 | 400174364 | High Sign | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000943 | 400588367 | High Sign | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000944 | 400589428 | Molding | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000945 | 400591255 | Molding | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000946 | 400594068 | Molding | HFTD Tier 3 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000947 | 400594115 | High Sign | HFTD Tier 3 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000948 | 400656395 | Hardware/Framing | HFTD Tier 3 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000949 | 400665145 | Molding | HFTD Tier 3 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000950 | 400723719 | Molding | HFTD Tier 3 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000951 | 400725508 | Hardware/Framing | HFTD Tier 3 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000952 | 400731485 | Molding | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000953 | 400761013 | High Sign | HFTD Tier 3 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000954 | 400767075 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000955 | 400769562 | Molding | HFTD Tier 3 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000956 | 400775632 | High Sign | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000957 | 400818914 | High Sign | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000958 | 400826210 | High Sign | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000959 | 400854965 | Molding | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000960 | 400855634 | Molding | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000961 | 400856602 | High Sign | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000962 | 400861607 | Guy | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000963 | 400861834 | High Sign | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000964 | 400868833 | Molding | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000965 | 400882310 | Molding | HFTD Tier 3 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000966 | 400914909 | Molding | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000967 | 400931504 | High Sign | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000968 | 400933018 | High Sign | HFTD Tier 2 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000969 | 413834632 | High Sign | HFTD Tier 3 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000970 | 413838344 | High Sign | HFTD Tier 3 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000971 | 413838345 | Molding | HFTD Tier 3 | Distribution | 2001-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000972 | 400584920 | Molding | HFTD Tier 3 | Distribution | 2001-12-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000973 | 400773019 | High Sign | HFTD Tier 3 | Distribution | 2001-12-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000974 | 400024907 | Molding | HFTD Tier 3 | Distribution | 2001-12-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000975 | 400619134 | Molding | HFTD Tier 3 | Distribution | 2001-12-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000976 | 400645050 | High Sign | HFTD Tier 2 | Distribution | 2001-12-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000977 | 400659615 | Molding | HFTD Tier 3 | Distribution | 2001-12-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000978 | 400711629 | High Sign | HFTD Tier 3 | Distribution | 2001-12-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000979 | 400724993 | High Sign | HFTD Tier 3 | Distribution | 2001-12-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000980 | 400734051 | High Sign | HFTD Tier 2 | Distribution | 2001-12-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000981 | 400737037 | High Sign | HFTD Tier 2 | Distribution | 2001-12-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000982 | 400784724 | High Sign | HFTD Tier 3 | Distribution | 2001-12-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000983 | 400786292 | High Sign | HFTD Tier 3 | Distribution | 2001-12-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000984 | 400836635 | High Sign | HFTD Tier 2 | Distribution | 2001-12-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000985 | 400876171 | High Sign | HFTD Tier 2 | Distribution | 2001-12-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000986 | 400914629 | High Sign | HFTD Tier 3 | Distribution | 2001-12-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000987 | 401006672 | High Sign | HFTD Tier 3 | Distribution | 2001-12-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000988 | 401006674 | High Sign | HFTD Tier 3 | Distribution | 2001-12-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000989 | 413829867 | Molding | HFTD Tier 3 | Distribution | 2001-12-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000990 | 400037905 | Molding | HFTD Tier 2 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000991 | 400106015 | High Sign | HFTD Tier 2 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000992 | 400559393 | Molding | HFTD Tier 2 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000993 | 400565866 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000994 | 400619924 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000995 | 400621243 | Hardware/Framing | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000996 | 400643286 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000997 | 400647799 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000998 | 400648821 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120000999 | 400650726 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001000 | 400661726 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001001 | 400666374 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001002 | 400667414 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001003 | 400667522 | Molding | HFTD Tier 2 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001004 | 400668432 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001005 | 400669784 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001006 | 400671260 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001007 | 400672113 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001008 | 400672422 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001009 | 400672441 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001010 | 400672502 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001011 | 400673200 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001012 | 400673227 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001013 | 400674335 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001014 | 400674353 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001015 | 400675251 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001016 | 400675269 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001017 | 400676470 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001018 | 400676486 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001019 | 400677205 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001020 | 400681858 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001021 | 400683253 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001022 | 400683568 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001023 | 400683597 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001024 | 400684657 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001025 | 400684746 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001026 | 400685108 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001027 | 400687773 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001028 | 400688003 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001029 | 400688863 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001030 | 400690069 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001031 | 400690117 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001032 | 400691092 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001033 | 400693716 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001034 | 400694751 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001035 | 400695595 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001036 | 400701543 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001037 | 400739714 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001038 | 400741230 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001039 | 400741476 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001040 | 400742039 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001041 | 400742055 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001042 | 400742606 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001043 | 400742631 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001044 | 400742641 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001045 | 400742830 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001046 | 400742868 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001047 | 400743709 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001048 | 400743947 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001049 | 400743988 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001050 | 400746619 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001051 | 400746647 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001052 | 400746873 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001053 | 400751084 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001054 | 400751825 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001055 | 400753693 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001056 | 400754441 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001057 | 400755734 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001058 | 400756651 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001059 | 400756730 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001060 | 400758315 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001061 | 400760096 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001062 | 400760125 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001063 | 400760801 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001064 | 400762886 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001065 | 400782334 | Hardware/Framing | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001066 | 400852697 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001067 | 400853803 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001068 | 400853861 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001069 | 400853866 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001070 | 400856073 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001071 | 400856125 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001072 | 400856128 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001073 | 400856163 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001074 | 400858897 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001075 | 400859002 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001076 | 400859008 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001077 | 400862069 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001078 | 400863307 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001079 | 400863398 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001080 | 400864770 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001081 | 400866271 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001082 | 400866279 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001083 | 400866323 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001084 | 400867205 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001085 | 400868533 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001086 | 400868824 | Insulator | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001087 | 400872443 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001088 | 400872742 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001089 | 400872747 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001090 | 400876024 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001091 | 400878798 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001092 | 400878945 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001093 | 400880236 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001094 | 400881029 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001095 | 400884348 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001096 | 400884599 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001097 | 400886056 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001098 | 400887503 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001099 | 400893138 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001100 | 400904442 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001101 | 400943335 | Molding | HFTD Tier 2 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001102 | 400958223 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001103 | 400959945 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001104 | 400959970 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001105 | 400960332 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001106 | 400960687 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001107 | 400961308 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001108 | 400961323 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001109 | 400961333 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001110 | 400961671 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001111 | 400961677 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001112 | 400961864 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001113 | 400962158 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001114 | 400962690 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001115 | 400962699 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001116 | 400962714 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001117 | 400962723 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001118 | 400964553 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001119 | 400964558 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001120 | 400964830 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001121 | 400965340 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001122 | 400965533 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001123 | 400965650 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001124 | 400965950 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001125 | 400967869 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001126 | 400968295 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001127 | 400968326 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001128 | 400968568 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001129 | 400969433 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001130 | 400969717 | Molding | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001131 | 400969732 | High Sign | HFTD Tier 3 | Distribution | 2001-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001132 | 400163123 | High Sign | HFTD Tier 3 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001133 | 400558604 | High Sign | HFTD Tier 3 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001134 | 400558821 | Hardware/Framing | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001135 | 400567823 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001136 | 400569724 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001137 | 400578040 | Hardware/Framing | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001138 | 400582878 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001139 | 400585862 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001140 | 400587289 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001141 | 400588971 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001142 | 400592361 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001143 | 400597172 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001144 | 400597189 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001145 | 400597255 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001146 | 400602621 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001147 | 400620153 | High Sign | HFTD Tier 3 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001148 | 400633095 | Molding | HFTD Tier 3 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001149 | 400638464 | Molding | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001150 | 400641788 | Molding | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001151 | 400679768 | Molding | HFTD Tier 3 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001152 | 400686889 | Molding | HFTD Tier 3 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001153 | 400778493 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001154 | 400810278 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001155 | 400811065 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001156 | 400812484 | Molding | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001157 | 400815151 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001158 | 400822724 | Molding | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001159 | 400825404 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001160 | 400825608 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001161 | 400834613 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001162 | 400835348 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001163 | 400835392 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001164 | 400837799 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001165 | 400837907 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001166 | 400838737 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001167 | 400839008 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001168 | 400839754 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001169 | 400839827 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001170 | 400839843 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001171 | 400840893 | Molding | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001172 | 400842296 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001173 | 400848787 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001174 | 400864669 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001175 | 400868733 | Hardware/Framing | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001176 | 400874182 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001177 | 400874199 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001178 | 400876267 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001179 | 400880682 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001180 | 400880753 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001181 | 400881584 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001182 | 400882964 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001183 | 400883708 | Molding | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001184 | 400884101 | Molding | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001185 | 400885079 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001186 | 400891602 | High Sign | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001187 | 400951391 | Molding | HFTD Tier 2 | Distribution | 2001-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001188 | 400583032 | High Sign | HFTD Tier 3 | Distribution | 2001-12-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001189 | 401006595 | Molding | HFTD Tier 3 | Distribution | 2001-12-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001190 | 401006596 | High Sign | HFTD Tier 3 | Distribution | 2001-12-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001191 | 400130055 | High Sign | HFTD Tier 3 | Distribution | 2001-12-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001192 | 400130749 | High Sign | HFTD Tier 3 | Distribution | 2001-12-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001193 | 400150612 | High Sign | HFTD Tier 3 | Distribution | 2001-12-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001194 | 400151882 | High Sign | HFTD Tier 3 | Distribution | 2001-12-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001195 | 400152401 | High Sign | HFTD Tier 3 | Distribution | 2001-12-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001196 | 400391832 | High Sign | HFTD Tier 3 | Distribution | 2001-12-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001197 | 400595710 | High Sign | HFTD Tier 2 | Distribution | 2001-12-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001198 | 400604162 | High Sign | HFTD Tier 2 | Distribution | 2001-12-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001199 | 400809724 | High Sign | HFTD Tier 3 | Distribution | 2001-12-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001200 | 400814561 | Guy | HFTD Tier 3 | Distribution | 2001-12-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001201 | 400825884 | Guy | HFTD Tier 2 | Distribution | 2001-12-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001202 | 400624233 | High Sign | HFTD Tier 3 | Distribution | 2001-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001203 | 400689013 | Cable/Conductor | HFTD Tier 3 | Distribution | 2001-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001204 | 400692492 | Hardware/Framing | HFTD Tier 3 | Distribution | 2001-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001205 | 400699061 | Molding | HFTD Tier 3 | Distribution | 2001-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001206 | 400699881 | Molding | HFTD Tier 3 | Distribution | 2001-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001207 | 400702143 | Guy | HFTD Tier 3 | Distribution | 2001-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001208 | 400730336 | High Sign | HFTD Tier 3 | Distribution | 2001-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001209 | 400736173 | High Sign | HFTD Tier 3 | Distribution | 2001-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001210 | 400749663 | High Sign | HFTD Tier 2 | Distribution | 2001-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001211 | 400749752 | High Sign | HFTD Tier 3 | Distribution | 2001-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001212 | 400782724 | Molding | HFTD Tier 2 | Distribution | 2001-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001213 | 400816347 | High Sign | HFTD Tier 3 | Distribution | 2001-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001214 | 400898616 | Molding | HFTD Tier 3 | Distribution | 2001-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001215 | 400906551 | Insulator | HFTD Tier 3 | Distribution | 2001-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001216 | 400940341 | High Sign | HFTD Tier 3 | Distribution | 2001-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001217 | 400999696 | Cable/Conductor | HFTD Tier 3 | Distribution | 2001-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001218 | 401006621 | Molding | HFTD Tier 3 | Distribution | 2001-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001219 | 400674261 | High Sign | HFTD Tier 3 | Distribution | 2001-12-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001220 | 400793762 | High Sign | HFTD Tier 2 | Distribution | 2001-12-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001221 | 400829302 | Molding | HFTD Tier 2 | Distribution | 2001-12-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001222 | 400906937 | Molding | HFTD Tier 2 | Distribution | 2001-12-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001223 | 400916990 | High Sign | HFTD Tier 2 | Distribution | 2001-12-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001224 | 400976825 | High Sign | HFTD Tier 2 | Distribution | 2001-12-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001225 | 400065080 | Cable/Conductor | HFTD Tier 2 | Distribution | 2002-01-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001226 | 400581315 | Guy | HFTD Tier 2 | Distribution | 2002-01-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001227 | 400712750 | High Sign | HFTD Tier 2 | Distribution | 2002-01-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001228 | 400725438 | High Sign | HFTD Tier 2 | Distribution | 2002-01-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001229 | 400828423 | Guy | HFTD Tier 2 | Distribution | 2002-01-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001230 | 400831232 | High Sign | HFTD Tier 2 | Distribution | 2002-01-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001231 | 400836327 | Insulator | HFTD Tier 3 | Distribution | 2002-01-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001232 | 400907213 | High Sign | HFTD Tier 2 | Distribution | 2002-01-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001233 | 401006173 | Molding | HFTD Tier 2 | Distribution | 2002-01-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001234 | 400730878 | High Sign | HFTD Tier 3 | Distribution | 2002-01-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001235 | 400734657 | High Sign | HFTD Tier 3 | Distribution | 2002-01-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001236 | 400883996 | High Sign | HFTD Tier 3 | Distribution | 2002-01-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001237 | 401006695 | Hardware/Framing | HFTD Tier 3 | Distribution | 2002-01-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001238 | 400149815 | High Sign | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001239 | 400549041 | High Sign | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001240 | 400553962 | Crossarm | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001241 | 400555805 | High Sign | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001242 | 400560353 | High Sign | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001243 | 400561319 | High Sign | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001244 | 400561345 | High Sign | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001245 | 400563262 | High Sign | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001246 | 400590668 | Molding | HFTD Tier 2 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001247 | 400598059 | Molding | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001248 | 400599737 | High Sign | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001249 | 400605943 | High Sign | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001250 | 400611794 | High Sign | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001251 | 400615978 | Molding | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001252 | 400617272 | Molding | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001253 | 400617754 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001254 | 400619823 | High Sign | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001255 | 400621229 | High Sign | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001256 | 400622218 | High Sign | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001257 | 400630006 | High Sign | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001258 | 400672252 | High Sign | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001259 | 400737660 | High Sign | HFTD Tier 2 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001260 | 400910778 | Molding | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001261 | 400929702 | High Sign | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001262 | 400963662 | High Sign | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001263 | 401005691 | High Sign | HFTD Tier 2 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001264 | 401006498 | High Sign | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001265 | 401006571 | High Sign | HFTD Tier 2 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001266 | 401006572 | Molding | HFTD Tier 2 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001267 | 401006594 | High Sign | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001268 | 401006597 | Molding | HFTD Tier 3 | Distribution | 2002-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001269 | 400607553 | Riser/Conduit | HFTD Tier 2 | Distribution | 2002-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001270 | 400776426 | Molding | HFTD Tier 2 | Distribution | 2002-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001271 | 400825047 | Molding | HFTD Tier 2 | Distribution | 2002-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001272 | 400080158 | High Sign | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001273 | 400081578 | Molding | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001274 | 400106458 | Guy | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001275 | 400111447 | High Sign | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001276 | 400549774 | Molding | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001277 | 400552253 | Molding | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001278 | 400558406 | High Sign | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001279 | 400573542 | Molding | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001280 | 400587465 | Molding | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001281 | 400607494 | High Sign | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001282 | 400611729 | High Sign | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001283 | 400613573 | Molding | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001284 | 400624166 | High Sign | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001285 | 400637655 | High Sign | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001286 | 400700199 | High Sign | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001287 | 400701156 | High Sign | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001288 | 400744587 | Molding | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001289 | 400804471 | High Sign | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001290 | 400806776 | High Sign | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001291 | 400874036 | High Sign | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001292 | 400927064 | High Sign | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001293 | 400931147 | High Sign | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001294 | 400938380 | Insulator | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001295 | 400940865 | Molding | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001296 | 400947293 | High Sign | HFTD Tier 3 | Distribution | 2002-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001297 | 400548229 | High Sign | HFTD Tier 3 | Distribution | 2002-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001298 | 400642257 | High Sign | HFTD Tier 2 | Distribution | 2002-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001299 | 400761434 | Molding | HFTD Tier 3 | Distribution | 2002-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001300 | 400810954 | Molding | HFTD Tier 3 | Distribution | 2002-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001301 | 400847473 | High Sign | HFTD Tier 2 | Distribution | 2002-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001302 | 400871350 | Hardware/Framing | HFTD Tier 3 | Distribution | 2002-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001303 | 400642770 | Molding | HFTD Tier 3 | Distribution | 2002-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001304 | 400657111 | High Sign | HFTD Tier 3 | Distribution | 2002-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001305 | 400676710 | High Sign | HFTD Tier 3 | Distribution | 2002-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001306 | 400684258 | High Sign | HFTD Tier 3 | Distribution | 2002-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001307 | 400722780 | Ground | HFTD Tier 3 | Distribution | 2002-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001308 | 400766834 | Molding | HFTD Tier 3 | Distribution | 2002-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001309 | 401005875 | Hardware/Framing | HFTD Tier 3 | Distribution | 2002-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001310 | 401005876 | Molding | HFTD Tier 3 | Distribution | 2002-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001311 | 400767303 | Insulator | HFTD Tier 2 | Distribution | 2002-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001312 | 400794733 | High Sign | HFTD Tier 3 | Distribution | 2002-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001313 | 400615833 | Insulator | HFTD Tier 2 | Distribution | 2002-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001314 | 400723876 | High Sign | HFTD Tier 3 | Distribution | 2002-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001315 | 400741460 | Insulator | HFTD Tier 2 | Distribution | 2002-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001316 | 400728099 | High Sign | HFTD Tier 3 | Distribution | 2002-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001317 | 400199047 | Molding | HFTD Tier 2 | Distribution | 2002-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001318 | 400199071 | Molding | HFTD Tier 2 | Distribution | 2002-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001319 | 400199938 | Molding | HFTD Tier 2 | Distribution | 2002-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001320 | 400711158 | Molding | HFTD Tier 2 | Distribution | 2002-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001321 | 400720146 | High Sign | HFTD Tier 2 | Distribution | 2002-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001322 | 400752652 | Molding | HFTD Tier 2 | Distribution | 2002-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001323 | 400767640 | Molding | HFTD Tier 2 | Distribution | 2002-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001324 | 400805102 | Molding | HFTD Tier 2 | Distribution | 2002-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001325 | 400808711 | Molding | HFTD Tier 2 | Distribution | 2002-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001326 | 400813064 | Molding | HFTD Tier 2 | Distribution | 2002-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001327 | 400825938 | Molding | HFTD Tier 2 | Distribution | 2002-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001328 | 400831390 | Molding | HFTD Tier 2 | Distribution | 2002-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001329 | 400836527 | Molding | HFTD Tier 2 | Distribution | 2002-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001330 | 400843449 | High Sign | HFTD Tier 2 | Distribution | 2002-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001331 | 400845520 | High Sign | HFTD Tier 2 | Distribution | 2002-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001332 | 400846568 | Molding | HFTD Tier 2 | Distribution | 2002-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001333 | 400849867 | High Sign | HFTD Tier 2 | Distribution | 2002-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001334 | 400999774 | Cable/Conductor | HFTD Tier 2 | Distribution | 2002-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001335 | 401003970 | High Sign | HFTD Tier 3 | Distribution | 2002-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001336 | 401006197 | Molding | HFTD Tier 2 | Distribution | 2002-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001337 | 400790469 | Molding | HFTD Tier 2 | Distribution | 2002-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001338 | 400793630 | High Sign | HFTD Tier 2 | Distribution | 2002-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001339 | 400808415 | High Sign | HFTD Tier 2 | Distribution | 2002-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001340 | 400811428 | High Sign | HFTD Tier 2 | Distribution | 2002-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001341 | 400813118 | Molding | HFTD Tier 2 | Distribution | 2002-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001342 | 400891687 | Molding | HFTD Tier 2 | Distribution | 2002-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001343 | 400208295 | High Sign | HFTD Tier 3 | Distribution | 2002-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001344 | 400653750 | High Sign | HFTD Tier 3 | Distribution | 2002-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001345 | 400655093 | Molding | HFTD Tier 2 | Distribution | 2002-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001346 | 400658514 | High Sign | HFTD Tier 2 | Distribution | 2002-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001347 | 400717407 | High Sign | HFTD Tier 2 | Distribution | 2002-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001348 | 400789840 | High Sign | HFTD Tier 2 | Distribution | 2002-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001349 | 400802502 | High Sign | HFTD Tier 2 | Distribution | 2002-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001350 | 400811222 | Molding | HFTD Tier 3 | Distribution | 2002-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001351 | 400815757 | High Sign | HFTD Tier 2 | Distribution | 2002-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001352 | 400816183 | High Sign | HFTD Tier 2 | Distribution | 2002-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001353 | 400825103 | High Sign | HFTD Tier 2 | Distribution | 2002-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001354 | 400827230 | High Sign | HFTD Tier 3 | Distribution | 2002-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001355 | 400867112 | High Sign | HFTD Tier 3 | Distribution | 2002-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001356 | 400871395 | High Sign | HFTD Tier 2 | Distribution | 2002-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001357 | 400871416 | High Sign | HFTD Tier 3 | Distribution | 2002-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001358 | 400875041 | High Sign | HFTD Tier 2 | Distribution | 2002-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001359 | 400886888 | Molding | HFTD Tier 3 | Distribution | 2002-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001360 | 400027724 | High Sign | HFTD Tier 2 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001361 | 400055899 | Molding | HFTD Tier 2 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001362 | 400059636 | High Sign | HFTD Tier 2 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001363 | 400601236 | Molding | HFTD Tier 2 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001364 | 400639029 | High Sign | HFTD Tier 3 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001365 | 400643445 | High Sign | HFTD Tier 3 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001366 | 400657133 | Riser/Conduit | HFTD Tier 3 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001367 | 400683431 | Hardware/Framing | HFTD Tier 3 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001368 | 400774080 | High Sign | HFTD Tier 3 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001369 | 400779055 | High Sign | HFTD Tier 3 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001370 | 400779124 | High Sign | HFTD Tier 3 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001371 | 400780415 | Molding | HFTD Tier 3 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001372 | 400781453 | Molding | HFTD Tier 3 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001373 | 400782130 | Molding | HFTD Tier 3 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001374 | 400782132 | High Sign | HFTD Tier 3 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001375 | 400826523 | Molding | HFTD Tier 2 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001376 | 400830004 | High Sign | HFTD Tier 3 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001377 | 400850303 | High Sign | HFTD Tier 2 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001378 | 400854254 | High Sign | HFTD Tier 3 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001379 | 400877377 | High Sign | HFTD Tier 3 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001380 | 400939150 | High Sign | HFTD Tier 3 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001381 | 400999756 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001382 | 401001206 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001383 | 401006159 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001384 | 401517620 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2002-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001385 | 400803781 | High Sign | HFTD Tier 3 | Distribution | 2002-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001386 | 400808728 | High Sign | HFTD Tier 3 | Distribution | 2002-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001387 | 400827848 | High Sign | HFTD Tier 3 | Distribution | 2002-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001388 | 400862122 | High Sign | HFTD Tier 3 | Distribution | 2002-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001389 | 400878583 | High Sign | HFTD Tier 3 | Distribution | 2002-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001390 | 400937273 | Molding | HFTD Tier 3 | Distribution | 2002-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001391 | 400999658 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-01-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001392 | 400302827 | High Sign | HFTD Tier 3 | Distribution | 2002-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001393 | 401006689 | High Sign | HFTD Tier 3 | Distribution | 2002-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001394 | 400082563 | Hardware/Framing | HFTD Tier 2 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001395 | 400084490 | Molding | HFTD Tier 2 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001396 | 400103999 | Molding | HFTD Tier 2 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001397 | 400107252 | Insulator | HFTD Tier 2 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001398 | 400109384 | Molding | HFTD Tier 2 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001399 | 400187588 | High Sign | HFTD Tier 3 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001400 | 400188188 | High Sign | HFTD Tier 3 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001401 | 400188211 | Molding | HFTD Tier 3 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001402 | 400189686 | High Sign | HFTD Tier 3 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001403 | 400545257 | High Sign | HFTD Tier 3 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001404 | 400547802 | High Sign | HFTD Tier 3 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001405 | 400548709 | High Sign | HFTD Tier 3 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001406 | 400579572 | Molding | HFTD Tier 2 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001407 | 400579626 | Molding | HFTD Tier 2 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001408 | 400591364 | High Sign | HFTD Tier 2 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001409 | 400603480 | Molding | HFTD Tier 3 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001410 | 400606418 | High Sign | HFTD Tier 3 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001411 | 400611311 | High Sign | HFTD Tier 3 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001412 | 400629593 | High Sign | HFTD Tier 3 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001413 | 400633416 | Molding | HFTD Tier 3 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001414 | 400635256 | High Sign | HFTD Tier 3 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001415 | 400659260 | High Sign | HFTD Tier 3 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001416 | 400670569 | Insulator | HFTD Tier 3 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001417 | 400671771 | High Sign | HFTD Tier 3 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001418 | 400824406 | High Sign | HFTD Tier 2 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001419 | 400844312 | High Sign | HFTD Tier 2 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001420 | 400845317 | High Sign | HFTD Tier 3 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001421 | 400862347 | High Sign | HFTD Tier 2 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001422 | 400877191 | High Sign | HFTD Tier 2 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001423 | 400887741 | Guy | HFTD Tier 2 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001424 | 400899510 | High Sign | HFTD Tier 2 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001425 | 400924584 | High Sign | HFTD Tier 2 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001426 | 401006593 | High Sign | HFTD Tier 3 | Distribution | 2002-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001427 | 400547179 | High Sign | HFTD Tier 3 | Distribution | 2002-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001428 | 400564183 | Molding | HFTD Tier 3 | Distribution | 2002-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001429 | 400794667 | Molding | HFTD Tier 3 | Distribution | 2002-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001430 | 400148137 | Hardware/Framing | HFTD Tier 2 | Distribution | 2002-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001431 | 400166140 | Hardware/Framing | HFTD Tier 2 | Distribution | 2002-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001432 | 400670317 | High Sign | HFTD Tier 2 | Distribution | 2002-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001433 | 400671779 | High Sign | HFTD Tier 2 | Distribution | 2002-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001434 | 400724797 | High Sign | HFTD Tier 2 | Distribution | 2002-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001435 | 400727364 | High Sign | HFTD Tier 2 | Distribution | 2002-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001436 | 400898804 | High Sign | HFTD Tier 2 | Distribution | 2002-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001437 | 400902083 | High Sign | HFTD Tier 2 | Distribution | 2002-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001438 | 400603435 | High Sign | HFTD Tier 3 | Distribution | 2002-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001439 | 400616901 | Molding | HFTD Tier 2 | Distribution | 2002-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001440 | 400621715 | High Sign | HFTD Tier 2 | Distribution | 2002-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001441 | 400626449 | Insulator | HFTD Tier 2 | Distribution | 2002-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001442 | 400700206 | Insulator | HFTD Tier 2 | Distribution | 2002-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001443 | 400701920 | High Sign | HFTD Tier 2 | Distribution | 2002-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001444 | 400702279 | High Sign | HFTD Tier 2 | Distribution | 2002-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001445 | 400725415 | High Sign | HFTD Tier 2 | Distribution | 2002-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001446 | 400741865 | High Sign | HFTD Tier 2 | Distribution | 2002-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001447 | 400745603 | Hardware/Framing | HFTD Tier 2 | Distribution | 2002-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001448 | 400164076 | Guy | HFTD Tier 3 | Distribution | 2002-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001449 | 400165547 | High Sign | HFTD Tier 3 | Distribution | 2002-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001450 | 400166168 | High Sign | HFTD Tier 3 | Distribution | 2002-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001451 | 400599256 | High Sign | HFTD Tier 3 | Distribution | 2002-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001452 | 400605788 | High Sign | HFTD Tier 3 | Distribution | 2002-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001453 | 400606678 | High Sign | HFTD Tier 2 | Distribution | 2002-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001454 | 400607885 | High Sign | HFTD Tier 3 | Distribution | 2002-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001455 | 400611424 | High Sign | HFTD Tier 3 | Distribution | 2002-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001456 | 400659310 | High Sign | HFTD Tier 3 | Distribution | 2002-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001457 | 400661851 | High Sign | HFTD Tier 2 | Distribution | 2002-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001458 | 400673233 | High Sign | HFTD Tier 3 | Distribution | 2002-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001459 | 400673539 | High Sign | HFTD Tier 2 | Distribution | 2002-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001460 | 400675352 | High Sign | HFTD Tier 3 | Distribution | 2002-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001461 | 400675395 | High Sign | HFTD Tier 3 | Distribution | 2002-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001462 | 400677344 | High Sign | HFTD Tier 3 | Distribution | 2002-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001463 | 400678766 | High Sign | HFTD Tier 3 | Distribution | 2002-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001464 | 400679117 | High Sign | HFTD Tier 3 | Distribution | 2002-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001465 | 400722226 | High Sign | HFTD Tier 2 | Distribution | 2002-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001466 | 400723708 | High Sign | HFTD Tier 3 | Distribution | 2002-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001467 | 400724752 | High Sign | HFTD Tier 2 | Distribution | 2002-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001468 | 400680010 | Molding | HFTD Tier 3 | Distribution | 2002-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001469 | 400691350 | High Sign | HFTD Tier 3 | Distribution | 2002-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001470 | 400698968 | High Sign | HFTD Tier 2 | Distribution | 2002-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001471 | 400704882 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001472 | 400708382 | High Sign | HFTD Tier 3 | Distribution | 2002-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001473 | 400750096 | High Sign | HFTD Tier 2 | Distribution | 2002-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001474 | 400541530 | Molding | HFTD Tier 3 | Distribution | 2002-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001475 | 400562115 | Hardware/Framing | HFTD Tier 3 | Distribution | 2002-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001476 | 400565505 | Hardware/Framing | HFTD Tier 3 | Distribution | 2002-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001477 | 400582380 | Molding | HFTD Tier 3 | Distribution | 2002-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001478 | 400711432 | High Sign | HFTD Tier 3 | Distribution | 2002-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001479 | 400717174 | Molding | HFTD Tier 3 | Distribution | 2002-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001480 | 400719130 | Molding | HFTD Tier 3 | Distribution | 2002-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001481 | 400764393 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001482 | 400767702 | Molding | HFTD Tier 3 | Distribution | 2002-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001483 | 400779878 | High Sign | HFTD Tier 3 | Distribution | 2002-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001484 | 400874221 | Molding | HFTD Tier 3 | Distribution | 2002-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001485 | 400876615 | Molding | HFTD Tier 3 | Distribution | 2002-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001486 | 400881606 | Molding | HFTD Tier 2 | Distribution | 2002-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001487 | 400909789 | High Sign | HFTD Tier 3 | Distribution | 2002-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001488 | 400932299 | Molding | HFTD Tier 3 | Distribution | 2002-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001489 | 401006038 | High Sign | HFTD Tier 3 | Distribution | 2002-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001490 | 401006039 | Molding | HFTD Tier 3 | Distribution | 2002-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001491 | 400871573 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001492 | 400899515 | High Sign | HFTD Tier 3 | Distribution | 2002-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001493 | 400169655 | High Sign | HFTD Tier 2 | Distribution | 2002-02-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001494 | 400536367 | Hardware/Framing | HFTD Tier 3 | Distribution | 2002-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001495 | 400566492 | High Sign | HFTD Tier 2 | Distribution | 2002-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001496 | 400567408 | High Sign | HFTD Tier 2 | Distribution | 2002-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001497 | 400784822 | High Sign | HFTD Tier 2 | Distribution | 2002-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001498 | 400788954 | Insulator | HFTD Tier 2 | Distribution | 2002-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001499 | 400790542 | High Sign | HFTD Tier 2 | Distribution | 2002-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001500 | 400830346 | Molding | HFTD Tier 2 | Distribution | 2002-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001501 | 400840380 | High Sign | HFTD Tier 3 | Distribution | 2002-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001502 | 400871930 | Guy | HFTD Tier 3 | Distribution | 2002-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001503 | 400890531 | Guy | HFTD Tier 3 | Distribution | 2002-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001504 | 400691294 | Molding | HFTD Tier 2 | Distribution | 2002-02-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001505 | 400722912 | High Sign | HFTD Tier 3 | Distribution | 2002-02-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001506 | 400848336 | High Sign | HFTD Tier 2 | Distribution | 2002-02-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001507 | 400186715 | Guy | HFTD Tier 2 | Distribution | 2002-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001508 | 400190963 | Guy | HFTD Tier 2 | Distribution | 2002-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001509 | 400191446 | Guy | HFTD Tier 2 | Distribution | 2002-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001510 | 400628884 | Molding | HFTD Tier 2 | Distribution | 2002-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001511 | 400636979 | Hardware/Framing | HFTD Tier 2 | Distribution | 2002-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001512 | 400722861 | Riser/Conduit | HFTD Tier 2 | Distribution | 2002-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001513 | 400722877 | Guy | HFTD Tier 2 | Distribution | 2002-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001514 | 400732238 | Molding | HFTD Tier 2 | Distribution | 2002-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001515 | 400754459 | Hardware/Framing | HFTD Tier 2 | Distribution | 2002-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001516 | 401006245 | High Sign | HFTD Tier 3 | Distribution | 2002-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001517 | 401006246 | Molding | HFTD Tier 3 | Distribution | 2002-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001518 | 401006635 | High Sign | HFTD Tier 3 | Distribution | 2002-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001519 | 401006681 | High Sign | HFTD Tier 3 | Distribution | 2002-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001520 | 400278390 | Molding | HFTD Tier 3 | Distribution | 2002-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001521 | 400585599 | High Sign | HFTD Tier 3 | Distribution | 2002-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001522 | 400626802 | High Sign | HFTD Tier 2 | Distribution | 2002-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001523 | 400626834 | High Sign | HFTD Tier 3 | Distribution | 2002-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001524 | 400748259 | High Sign | HFTD Tier 3 | Distribution | 2002-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001525 | 400774091 | High Sign | HFTD Tier 3 | Distribution | 2002-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001526 | 400195332 | Molding | HFTD Tier 3 | Distribution | 2002-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001527 | 400597836 | High Sign | HFTD Tier 3 | Distribution | 2002-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001528 | 400603498 | Molding | HFTD Tier 3 | Distribution | 2002-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001529 | 400603945 | Molding | HFTD Tier 3 | Distribution | 2002-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001530 | 400609336 | Molding | HFTD Tier 3 | Distribution | 2002-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001531 | 400657478 | High Sign | HFTD Tier 3 | Distribution | 2002-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001532 | 400664052 | High Sign | HFTD Tier 3 | Distribution | 2002-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001533 | 400665044 | High Sign | HFTD Tier 3 | Distribution | 2002-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001534 | 400690929 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001535 | 400691711 | Molding | HFTD Tier 3 | Distribution | 2002-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001536 | 400691730 | High Sign | HFTD Tier 3 | Distribution | 2002-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001537 | 400725133 | High Sign | HFTD Tier 3 | Distribution | 2002-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001538 | 400726801 | High Sign | HFTD Tier 3 | Distribution | 2002-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001539 | 400613211 | High Sign | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001540 | 400613231 | High Sign | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001541 | 400616469 | Molding | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001542 | 400624767 | Molding | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001543 | 400686040 | Molding | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001544 | 400687505 | High Sign | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001545 | 400687522 | High Sign | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001546 | 400687549 | Molding | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001547 | 400690172 | Molding | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001548 | 400690554 | High Sign | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001549 | 400707794 | High Sign | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001550 | 400713958 | High Sign | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001551 | 400713983 | High Sign | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001552 | 400714567 | High Sign | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001553 | 400716121 | High Sign | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001554 | 400717621 | High Sign | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001555 | 400729032 | High Sign | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001556 | 400729127 | High Sign | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001557 | 400736383 | High Sign | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001558 | 400738942 | High Sign | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001559 | 400765689 | Molding | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001560 | 400782827 | Molding | HFTD Tier 2 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001561 | 400817345 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001562 | 400629124 | Molding | HFTD Tier 2 | Distribution | 2002-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001563 | 400867968 | Molding | HFTD Tier 3 | Distribution | 2002-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001564 | 400870179 | Molding | HFTD Tier 2 | Distribution | 2002-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001565 | 400883392 | Molding | HFTD Tier 2 | Distribution | 2002-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001566 | 400623744 | Molding | HFTD Tier 2 | Distribution | 2002-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001567 | 400637566 | Molding | HFTD Tier 2 | Distribution | 2002-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001568 | 400771798 | High Sign | HFTD Tier 2 | Distribution | 2002-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001569 | 400774945 | High Sign | HFTD Tier 2 | Distribution | 2002-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001570 | 400856865 | Molding | HFTD Tier 2 | Distribution | 2002-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001571 | 400868618 | Cable/Conductor | HFTD Tier 2 | Distribution | 2002-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001572 | 400868678 | High Sign | HFTD Tier 2 | Distribution | 2002-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001573 | 400249914 | Guy | HFTD Tier 2 | Distribution | 2002-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001574 | 400278638 | High Sign | HFTD Tier 2 | Distribution | 2002-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001575 | 400643334 | High Sign | HFTD Tier 3 | Distribution | 2002-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001576 | 400643417 | High Sign | HFTD Tier 3 | Distribution | 2002-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001577 | 400669942 | Cable/Conductor | HFTD Tier 2 | Distribution | 2002-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001578 | 400735098 | Molding | HFTD Tier 3 | Distribution | 2002-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001579 | 400761986 | Molding | HFTD Tier 3 | Distribution | 2002-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001580 | 400811353 | Guy | HFTD Tier 2 | Distribution | 2002-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001581 | 400926144 | Guy | HFTD Tier 2 | Distribution | 2002-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001582 | 400613159 | Cable/Conductor | HFTD Tier 2 | Distribution | 2002-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001583 | 400632469 | High Sign | HFTD Tier 2 | Distribution | 2002-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001584 | 400667352 | Molding | HFTD Tier 2 | Distribution | 2002-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001585 | 400694589 | Molding | HFTD Tier 2 | Distribution | 2002-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001586 | 400712419 | Molding | HFTD Tier 2 | Distribution | 2002-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001587 | 400783322 | Molding | HFTD Tier 2 | Distribution | 2002-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001588 | 400786342 | Molding | HFTD Tier 2 | Distribution | 2002-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001589 | 400855746 | Molding | HFTD Tier 2 | Distribution | 2002-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001590 | 400880318 | High Sign | HFTD Tier 2 | Distribution | 2002-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001591 | 400914748 | Hardware/Framing | HFTD Tier 2 | Distribution | 2002-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001592 | 400968526 | High Sign | HFTD Tier 2 | Distribution | 2002-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001593 | 400969726 | High Sign | HFTD Tier 2 | Distribution | 2002-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001594 | 400636587 | Riser/Conduit | HFTD Tier 3 | Distribution | 2002-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001595 | 400877175 | Molding | HFTD Tier 3 | Distribution | 2002-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001596 | 401006489 | High Sign | HFTD Tier 3 | Distribution | 2002-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001597 | 400272027 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001598 | 400666853 | High Sign | HFTD Tier 3 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001599 | 400672970 | High Sign | HFTD Tier 3 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001600 | 400722809 | High Sign | HFTD Tier 2 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001601 | 400745986 | High Sign | HFTD Tier 3 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001602 | 400751062 | High Sign | HFTD Tier 3 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001603 | 400756231 | High Sign | HFTD Tier 3 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001604 | 400757680 | High Sign | HFTD Tier 3 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001605 | 400761418 | Molding | HFTD Tier 3 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001606 | 400762798 | High Sign | HFTD Tier 3 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001607 | 400764151 | High Sign | HFTD Tier 3 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001608 | 400764744 | High Sign | HFTD Tier 3 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001609 | 400764814 | High Sign | HFTD Tier 3 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001610 | 400767763 | High Sign | HFTD Tier 3 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001611 | 400771175 | High Sign | HFTD Tier 3 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001612 | 400771203 | Hardware/Framing | HFTD Tier 3 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001613 | 400779137 | High Sign | HFTD Tier 3 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001614 | 400835898 | High Sign | HFTD Tier 2 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001615 | 400837374 | High Sign | HFTD Tier 2 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001616 | 401006067 | High Sign | HFTD Tier 2 | Distribution | 2002-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001617 | 400204572 | Molding | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001618 | 400539781 | High Sign | HFTD Tier 2 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001619 | 400545278 | High Sign | HFTD Tier 2 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001620 | 400559427 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001621 | 400560607 | Molding | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001622 | 400560691 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001623 | 400560721 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001624 | 400566784 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001625 | 400567618 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001626 | 400572831 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001627 | 400573596 | High Sign | HFTD Tier 2 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001628 | 400574364 | Molding | HFTD Tier 2 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001629 | 400576008 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001630 | 400582270 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001631 | 400583083 | Molding | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001632 | 400586641 | Guy | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001633 | 400587234 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001634 | 400588359 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001635 | 400589677 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001636 | 400613274 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001637 | 400616006 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001638 | 400616969 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001639 | 400621306 | Molding | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001640 | 400624760 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001641 | 400625447 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001642 | 400627327 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001643 | 400627749 | Molding | HFTD Tier 2 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001644 | 400632325 | Molding | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001645 | 400639338 | Guy | HFTD Tier 2 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001646 | 400640675 | High Sign | HFTD Tier 2 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001647 | 400645255 | High Sign | HFTD Tier 2 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001648 | 400646704 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001649 | 400646747 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001650 | 400651222 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001651 | 400657871 | Molding | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001652 | 400660193 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001653 | 400661321 | Molding | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001654 | 400662419 | Molding | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001655 | 400662437 | Molding | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001656 | 400665707 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001657 | 400666214 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001658 | 400666903 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001659 | 400671095 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001660 | 400672019 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001661 | 400675407 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001662 | 400679729 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001663 | 400682513 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001664 | 400682532 | Molding | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001665 | 400683528 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001666 | 400684947 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001667 | 400708376 | Molding | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001668 | 400749189 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001669 | 400760763 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001670 | 400760819 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001671 | 400761826 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001672 | 400761880 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001673 | 400763779 | Molding | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001674 | 400770881 | Molding | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001675 | 400773134 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001676 | 400774116 | Molding | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001677 | 400838909 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001678 | 400839879 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001679 | 400842337 | Molding | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001680 | 400845380 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001681 | 400846943 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001682 | 400850173 | Molding | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001683 | 400852262 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001684 | 400854517 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001685 | 400854643 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001686 | 400854684 | Molding | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001687 | 400854700 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001688 | 400867485 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001689 | 400868250 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001690 | 400868603 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001691 | 400873795 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001692 | 400876247 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001693 | 400877138 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001694 | 400886590 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001695 | 400887639 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001696 | 400887699 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001697 | 400889149 | Molding | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001698 | 400890334 | Molding | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001699 | 400891417 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001700 | 400892021 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001701 | 400895191 | Molding | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001702 | 400895232 | Guy | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001703 | 400897520 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001704 | 400906886 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001705 | 400911276 | Molding | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001706 | 400920096 | Molding | HFTD Tier 2 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001707 | 400985700 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001708 | 400994017 | Cable/Conductor | HFTD Tier 2 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001709 | 401003106 | High Sign | HFTD Tier 2 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001710 | 401005894 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001711 | 401005895 | High Sign | HFTD Tier 3 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001712 | 401005916 | High Sign | HFTD Tier 2 | Distribution | 2002-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001713 | 400185665 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001714 | 400185690 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001715 | 400185864 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001716 | 400185988 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001717 | 400201558 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001718 | 400203490 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001719 | 400204400 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001720 | 400205302 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001721 | 400399954 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001722 | 400407521 | Molding | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001723 | 400503143 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001724 | 400596504 | High Sign | HFTD Tier 3 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001725 | 400653368 | High Sign | HFTD Tier 3 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001726 | 400658361 | Molding | HFTD Tier 3 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001727 | 400661761 | Insulator | HFTD Tier 3 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001728 | 400839356 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001729 | 400895820 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001730 | 400895862 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001731 | 400897297 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001732 | 400899948 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001733 | 400925134 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001734 | 400930654 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001735 | 400933851 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001736 | 400935352 | Hardware/Framing | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001737 | 400935383 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001738 | 400937310 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001739 | 400938771 | High Sign | HFTD Tier 2 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001740 | 400999522 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001741 | 400576324 | High Sign | HFTD Tier 2 | Distribution | 2002-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001742 | 400602151 | High Sign | HFTD Tier 2 | Distribution | 2002-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001743 | 400631232 | High Sign | HFTD Tier 2 | Distribution | 2002-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001744 | 400733668 | Molding | HFTD Tier 2 | Distribution | 2002-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001745 | 400816200 | Molding | HFTD Tier 2 | Distribution | 2002-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001746 | 400821659 | Molding | HFTD Tier 2 | Distribution | 2002-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001747 | 400822543 | Molding | HFTD Tier 2 | Distribution | 2002-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001748 | 400843112 | High Sign | HFTD Tier 2 | Distribution | 2002-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001749 | 400846018 | Molding | HFTD Tier 2 | Distribution | 2002-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001750 | 400847635 | Molding | HFTD Tier 2 | Distribution | 2002-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001751 | 400864485 | Molding | HFTD Tier 2 | Distribution | 2002-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001752 | 400887496 | High Sign | HFTD Tier 2 | Distribution | 2002-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001753 | 400906683 | High Sign | HFTD Tier 2 | Distribution | 2002-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001754 | 400576431 | Molding | HFTD Tier 3 | Distribution | 2002-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001755 | 400582259 | Molding | HFTD Tier 3 | Distribution | 2002-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001756 | 400583047 | High Sign | HFTD Tier 3 | Distribution | 2002-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001757 | 400621637 | High Sign | HFTD Tier 3 | Distribution | 2002-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001758 | 400626387 | High Sign | HFTD Tier 3 | Distribution | 2002-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001759 | 400629032 | High Sign | HFTD Tier 3 | Distribution | 2002-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001760 | 400932147 | Molding | HFTD Tier 3 | Distribution | 2002-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001761 | 400935675 | Molding | HFTD Tier 3 | Distribution | 2002-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001762 | 400935703 | High Sign | HFTD Tier 3 | Distribution | 2002-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001763 | 400936631 | Molding | HFTD Tier 3 | Distribution | 2002-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001764 | 400848759 | Molding | HFTD Tier 2 | Distribution | 2002-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001765 | 400555710 | High Sign | HFTD Tier 3 | Distribution | 2002-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001766 | 400604961 | High Sign | HFTD Tier 2 | Distribution | 2002-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001767 | 400610024 | High Sign | HFTD Tier 3 | Distribution | 2002-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001768 | 400783659 | High Sign | HFTD Tier 3 | Distribution | 2002-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001769 | 400792123 | High Sign | HFTD Tier 2 | Distribution | 2002-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001770 | 400793003 | Molding | HFTD Tier 3 | Distribution | 2002-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001771 | 400794396 | High Sign | HFTD Tier 2 | Distribution | 2002-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001772 | 400848142 | High Sign | HFTD Tier 3 | Distribution | 2002-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001773 | 400856604 | High Sign | HFTD Tier 2 | Distribution | 2002-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001774 | 400870648 | High Sign | HFTD Tier 3 | Distribution | 2002-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001775 | 400872953 | High Sign | HFTD Tier 2 | Distribution | 2002-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001776 | 400879402 | High Sign | HFTD Tier 2 | Distribution | 2002-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001777 | 400886727 | High Sign | HFTD Tier 2 | Distribution | 2002-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001778 | 400899798 | High Sign | HFTD Tier 2 | Distribution | 2002-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001779 | 400913723 | High Sign | HFTD Tier 3 | Distribution | 2002-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001780 | 400922115 | High Sign | HFTD Tier 3 | Distribution | 2002-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001781 | 400959175 | High Sign | HFTD Tier 2 | Distribution | 2002-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001782 | 401006632 | High Sign | HFTD Tier 3 | Distribution | 2002-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001783 | 400661662 | High Sign | HFTD Tier 2 | Distribution | 2002-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001784 | 400939989 | Molding | HFTD Tier 3 | Distribution | 2002-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001785 | 400085008 | High Sign | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001786 | 400291821 | Molding | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001787 | 400618102 | High Sign | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001788 | 400619210 | High Sign | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001789 | 400643778 | High Sign | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001790 | 400646013 | Molding | HFTD Tier 2 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001791 | 400648853 | High Sign | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001792 | 400652890 | High Sign | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001793 | 400653747 | High Sign | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001794 | 400678357 | Molding | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001795 | 400702939 | High Sign | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001796 | 400707011 | Molding | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001797 | 400716362 | High Sign | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001798 | 400726640 | High Sign | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001799 | 400745151 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001800 | 400873898 | High Sign | HFTD Tier 2 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001801 | 400880968 | Molding | HFTD Tier 2 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001802 | 400899261 | High Sign | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001803 | 400924453 | High Sign | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001804 | 400934059 | Insulator | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001805 | 400959953 | Molding | HFTD Tier 2 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001806 | 400999722 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001807 | 400999750 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001808 | 401001077 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001809 | 400531925 | High Sign | HFTD Tier 3 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001810 | 400532866 | Molding | HFTD Tier 3 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001811 | 400532907 | High Sign | HFTD Tier 2 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001812 | 400604091 | Riser/Conduit | HFTD Tier 2 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001813 | 400608283 | High Sign | HFTD Tier 3 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001814 | 400615717 | Molding | HFTD Tier 2 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001815 | 400641096 | Molding | HFTD Tier 2 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001816 | 400664007 | High Sign | HFTD Tier 3 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001817 | 400689015 | Molding | HFTD Tier 2 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001818 | 400693279 | High Sign | HFTD Tier 3 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001819 | 400694575 | Molding | HFTD Tier 2 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001820 | 400698434 | Molding | HFTD Tier 2 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001821 | 400715139 | Molding | HFTD Tier 2 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001822 | 400799875 | High Sign | HFTD Tier 3 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001823 | 400850062 | High Sign | HFTD Tier 2 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001824 | 400852639 | Molding | HFTD Tier 3 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001825 | 400862753 | High Sign | HFTD Tier 2 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001826 | 400864111 | High Sign | HFTD Tier 2 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001827 | 400865026 | High Sign | HFTD Tier 2 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001828 | 400867974 | Cable/Conductor | HFTD Tier 2 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001829 | 400875030 | High Sign | HFTD Tier 3 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001830 | 400876469 | High Sign | HFTD Tier 3 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001831 | 400878265 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001832 | 400883813 | High Sign | HFTD Tier 3 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001833 | 400885637 | Insulator | HFTD Tier 3 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001834 | 400886598 | Molding | HFTD Tier 2 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001835 | 400892439 | Molding | HFTD Tier 3 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001836 | 400897065 | High Sign | HFTD Tier 3 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001837 | 400898770 | High Sign | HFTD Tier 3 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001838 | 400900815 | High Sign | HFTD Tier 2 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001839 | 400903035 | High Sign | HFTD Tier 2 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001840 | 400908419 | Molding | HFTD Tier 2 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001841 | 400926642 | Riser/Conduit | HFTD Tier 2 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001842 | 400931165 | Molding | HFTD Tier 2 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001843 | 400969542 | High Sign | HFTD Tier 2 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001844 | 400985451 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001845 | 401006703 | High Sign | HFTD Tier 2 | Distribution | 2002-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001846 | 400611727 | High Sign | HFTD Tier 2 | Distribution | 2002-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001847 | 400623376 | High Sign | HFTD Tier 3 | Distribution | 2002-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001848 | 400679505 | High Sign | HFTD Tier 2 | Distribution | 2002-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001849 | 400692913 | Molding | HFTD Tier 2 | Distribution | 2002-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001850 | 400726950 | Molding | HFTD Tier 2 | Distribution | 2002-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001851 | 400770247 | Guy | HFTD Tier 2 | Distribution | 2002-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001852 | 400772312 | High Sign | HFTD Tier 2 | Distribution | 2002-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001853 | 400798693 | Hardware/Framing | HFTD Tier 3 | Distribution | 2002-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001854 | 400821718 | Molding | HFTD Tier 3 | Distribution | 2002-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001855 | 400878471 | Molding | HFTD Tier 2 | Distribution | 2002-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001856 | 400879783 | High Sign | HFTD Tier 3 | Distribution | 2002-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001857 | 400166548 | High Sign | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001858 | 400192363 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001859 | 400196359 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001860 | 400217094 | Guy | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001861 | 400218634 | Molding | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001862 | 400221984 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001863 | 400223226 | High Sign | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001864 | 400544781 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001865 | 400552113 | Molding | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001866 | 400554031 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001867 | 400556896 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001868 | 400556925 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001869 | 400562841 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001870 | 400564947 | Molding | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001871 | 400572453 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001872 | 400573485 | Molding | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001873 | 400576159 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001874 | 400608664 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001875 | 400613459 | Insulator | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001876 | 400616312 | Molding | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001877 | 400616612 | Molding | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001878 | 400619125 | Molding | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001879 | 400626553 | Molding | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001880 | 400647485 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001881 | 400662260 | High Sign | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001882 | 400662352 | High Sign | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001883 | 400668245 | High Sign | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001884 | 400668306 | High Sign | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001885 | 400671814 | High Sign | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001886 | 400726751 | Molding | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001887 | 400727461 | Molding | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001888 | 400730912 | High Sign | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001889 | 400730942 | Molding | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001890 | 400736555 | Molding | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001891 | 400739572 | High Sign | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001892 | 400746099 | High Sign | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001893 | 400747613 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001894 | 400749681 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001895 | 400750235 | High Sign | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001896 | 400759939 | High Sign | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001897 | 400762561 | High Sign | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001898 | 400795765 | High Sign | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001899 | 400805017 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001900 | 400856763 | High Sign | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001901 | 400861031 | High Sign | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001902 | 400864557 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001903 | 400865593 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001904 | 400868825 | High Sign | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001905 | 400876153 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001906 | 400881030 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001907 | 400884986 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001908 | 400885005 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001909 | 400899144 | High Sign | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001910 | 400900616 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001911 | 400900995 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001912 | 400904410 | Molding | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001913 | 400909050 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001914 | 400910106 | High Sign | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001915 | 400910952 | High Sign | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001916 | 400911110 | Molding | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001917 | 400912566 | Molding | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001918 | 400912643 | Molding | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001919 | 400927386 | High Sign | HFTD Tier 2 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001920 | 401588293 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001921 | 400538305 | High Sign | HFTD Tier 3 | Distribution | 2002-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001922 | 400545117 | Molding | HFTD Tier 3 | Distribution | 2002-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001923 | 400570857 | Molding | HFTD Tier 3 | Distribution | 2002-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001924 | 400593474 | High Sign | HFTD Tier 3 | Distribution | 2002-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001925 | 400624697 | High Sign | HFTD Tier 3 | Distribution | 2002-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001926 | 400673468 | High Sign | HFTD Tier 3 | Distribution | 2002-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001927 | 400676619 | High Sign | HFTD Tier 3 | Distribution | 2002-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001928 | 400795259 | High Sign | HFTD Tier 3 | Distribution | 2002-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001929 | 400802858 | Molding | HFTD Tier 3 | Distribution | 2002-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001930 | 400864749 | Molding | HFTD Tier 3 | Distribution | 2002-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001931 | 400875308 | High Sign | HFTD Tier 3 | Distribution | 2002-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001932 | 400878399 | High Sign | HFTD Tier 3 | Distribution | 2002-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001933 | 401003198 | High Sign | HFTD Tier 2 | Distribution | 2002-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001934 | 400566728 | Guy | HFTD Tier 3 | Distribution | 2002-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001935 | 400567757 | Guy | HFTD Tier 3 | Distribution | 2002-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001936 | 400569127 | Molding | HFTD Tier 3 | Distribution | 2002-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001937 | 400574120 | Guy | HFTD Tier 3 | Distribution | 2002-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001938 | 400624156 | Guy | HFTD Tier 3 | Distribution | 2002-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001939 | 400624209 | Guy | HFTD Tier 3 | Distribution | 2002-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001940 | 400626001 | Molding | HFTD Tier 3 | Distribution | 2002-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001941 | 400632593 | Guy | HFTD Tier 3 | Distribution | 2002-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001942 | 400633462 | Guy | HFTD Tier 3 | Distribution | 2002-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001943 | 400636782 | Guy | HFTD Tier 3 | Distribution | 2002-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001944 | 400666431 | High Sign | HFTD Tier 3 | Distribution | 2002-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001945 | 400670265 | High Sign | HFTD Tier 3 | Distribution | 2002-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001946 | 400705850 | Molding | HFTD Tier 2 | Distribution | 2002-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001947 | 400705865 | Molding | HFTD Tier 2 | Distribution | 2002-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001948 | 400705956 | Guy | HFTD Tier 2 | Distribution | 2002-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001949 | 400707460 | Molding | HFTD Tier 2 | Distribution | 2002-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001950 | 400794185 | Molding | HFTD Tier 2 | Distribution | 2002-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001951 | 400862855 | High Sign | HFTD Tier 2 | Distribution | 2002-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001952 | 400038237 | High Sign | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001953 | 400528055 | Guy | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001954 | 400582532 | High Sign | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001955 | 400602818 | High Sign | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001956 | 400607257 | High Sign | HFTD Tier 2 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001957 | 400634648 | High Sign | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001958 | 400636181 | High Sign | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001959 | 400706710 | High Sign | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001960 | 400708239 | Guy | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001961 | 400709077 | Guy | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001962 | 400709448 | High Sign | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001963 | 400710526 | High Sign | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001964 | 400714382 | High Sign | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001965 | 400720306 | High Sign | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001966 | 400745502 | High Sign | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001967 | 400746960 | High Sign | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001968 | 400749395 | High Sign | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001969 | 400802047 | High Sign | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001970 | 400803973 | High Sign | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001971 | 400806827 | Guy | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001972 | 400879837 | High Sign | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001973 | 400893827 | High Sign | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001974 | 400897006 | High Sign | HFTD Tier 3 | Distribution | 2002-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001975 | 400140157 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001976 | 400632542 | High Sign | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001977 | 400648374 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001978 | 400648418 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001979 | 400655349 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001980 | 400655367 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001981 | 400656295 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001982 | 400658811 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001983 | 400660055 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001984 | 400664305 | High Sign | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001985 | 400664351 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001986 | 400666993 | High Sign | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001987 | 400667009 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001988 | 400668204 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001989 | 400668220 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001990 | 400669376 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001991 | 400705953 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001992 | 400707519 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001993 | 400709728 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001994 | 400718024 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001995 | 400718051 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001996 | 400719114 | High Sign | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001997 | 400823928 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001998 | 400883896 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120001999 | 400912639 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002000 | 400912656 | High Sign | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002001 | 400920874 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002002 | 400920901 | High Sign | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002003 | 400921294 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002004 | 400923882 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002005 | 400925029 | High Sign | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002006 | 400931188 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002007 | 400939746 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002008 | 400939776 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002009 | 400940898 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002010 | 400942254 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002011 | 400942716 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002012 | 400945672 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002013 | 400946413 | Guy | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002014 | 401006691 | Molding | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002015 | 401006701 | High Sign | HFTD Tier 3 | Distribution | 2002-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002016 | 400746626 | High Sign | HFTD Tier 2 | Distribution | 2002-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002017 | 400601992 | High Sign | HFTD Tier 2 | Distribution | 2002-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002018 | 400732946 | High Sign | HFTD Tier 2 | Distribution | 2002-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002019 | 400743701 | High Sign | HFTD Tier 2 | Distribution | 2002-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002020 | 400883796 | Molding | HFTD Tier 3 | Distribution | 2002-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002021 | 400388671 | High Sign | HFTD Tier 2 | Distribution | 2002-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002022 | 400510126 | High Sign | HFTD Tier 2 | Distribution | 2002-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002023 | 400678929 | High Sign | HFTD Tier 2 | Distribution | 2002-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002024 | 400681681 | High Sign | HFTD Tier 2 | Distribution | 2002-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002025 | 400681717 | Molding | HFTD Tier 2 | Distribution | 2002-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002026 | 400687840 | Molding | HFTD Tier 2 | Distribution | 2002-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002027 | 400731104 | High Sign | HFTD Tier 2 | Distribution | 2002-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002028 | 400732268 | Molding | HFTD Tier 2 | Distribution | 2002-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002029 | 400922334 | High Sign | HFTD Tier 2 | Distribution | 2002-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002030 | 400926809 | High Sign | HFTD Tier 2 | Distribution | 2002-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002031 | 400530622 | High Sign | HFTD Tier 2 | Distribution | 2002-04-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002032 | 400761721 | High Sign | HFTD Tier 2 | Distribution | 2002-04-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002033 | 400861232 | High Sign | HFTD Tier 2 | Distribution | 2002-04-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002034 | 400242290 | Molding | HFTD Tier 2 | Distribution | 2002-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002035 | 400244973 | High Sign | HFTD Tier 3 | Distribution | 2002-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002036 | 400257418 | Molding | HFTD Tier 2 | Distribution | 2002-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002037 | 400260430 | Molding | HFTD Tier 2 | Distribution | 2002-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002038 | 400260443 | High Sign | HFTD Tier 2 | Distribution | 2002-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002039 | 400262223 | Molding | HFTD Tier 2 | Distribution | 2002-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002040 | 400267934 | Molding | HFTD Tier 2 | Distribution | 2002-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002041 | 400348165 | Molding | HFTD Tier 2 | Distribution | 2002-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002042 | 400357433 | Molding | HFTD Tier 2 | Distribution | 2002-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002043 | 400910598 | Molding | HFTD Tier 2 | Distribution | 2002-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002044 | 400640526 | Molding | HFTD Tier 2 | Distribution | 2002-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002045 | 400935719 | High Sign | HFTD Tier 2 | Distribution | 2002-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002046 | 401006733 | High Sign | HFTD Tier 3 | Distribution | 2002-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002047 | 400887575 | High Sign | HFTD Tier 3 | Distribution | 2002-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002048 | 400891105 | Molding | HFTD Tier 3 | Distribution | 2002-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002049 | 400897514 | Hardware/Framing | HFTD Tier 3 | Distribution | 2002-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002050 | 400763619 | Molding | HFTD Tier 3 | Distribution | 2002-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002051 | 400210337 | High Sign | HFTD Tier 3 | Distribution | 2002-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002052 | 400244265 | Molding | HFTD Tier 2 | Distribution | 2002-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002053 | 400605206 | Molding | HFTD Tier 3 | Distribution | 2002-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002054 | 400605485 | Molding | HFTD Tier 3 | Distribution | 2002-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002055 | 400614713 | Molding | HFTD Tier 3 | Distribution | 2002-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002056 | 400711659 | High Sign | HFTD Tier 3 | Distribution | 2002-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002057 | 400768204 | High Sign | HFTD Tier 3 | Distribution | 2002-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002058 | 400820506 | High Sign | HFTD Tier 3 | Distribution | 2002-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002059 | 400856366 | High Sign | HFTD Tier 3 | Distribution | 2002-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002060 | 400923014 | Molding | HFTD Tier 2 | Distribution | 2002-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002061 | 400684498 | High Sign | HFTD Tier 3 | Distribution | 2002-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002062 | 400689829 | Guy | HFTD Tier 3 | Distribution | 2002-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002063 | 400948139 | High Sign | HFTD Tier 3 | Distribution | 2002-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002064 | 400611039 | High Sign | HFTD Tier 2 | Distribution | 2002-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002065 | 400626673 | High Sign | HFTD Tier 2 | Distribution | 2002-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002066 | 400766223 | High Sign | HFTD Tier 3 | Distribution | 2002-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002067 | 400885458 | Molding | HFTD Tier 3 | Distribution | 2002-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002068 | 400913404 | Molding | HFTD Tier 3 | Distribution | 2002-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002069 | 400577889 | High Sign | HFTD Tier 3 | Distribution | 2002-04-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002070 | 400999649 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002071 | 401006559 | High Sign | HFTD Tier 3 | Distribution | 2002-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002072 | 400742934 | High Sign | HFTD Tier 3 | Distribution | 2002-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002073 | 400829840 | High Sign | HFTD Tier 3 | Distribution | 2002-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002074 | 400591953 | Molding | HFTD Tier 3 | Distribution | 2002-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002075 | 400620272 | High Sign | HFTD Tier 3 | Distribution | 2002-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002076 | 400786906 | Molding | HFTD Tier 2 | Distribution | 2002-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002077 | 400807390 | Guy | HFTD Tier 3 | Distribution | 2002-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002078 | 400884737 | High Sign | HFTD Tier 3 | Distribution | 2002-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002079 | 400886443 | Molding | HFTD Tier 3 | Distribution | 2002-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002080 | 400893290 | High Sign | HFTD Tier 3 | Distribution | 2002-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002081 | 400927680 | High Sign | HFTD Tier 3 | Distribution | 2002-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002082 | 400933025 | Guy | HFTD Tier 3 | Distribution | 2002-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002083 | 400938333 | Guy | HFTD Tier 3 | Distribution | 2002-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002084 | 400999496 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002085 | 400654059 | High Sign | HFTD Tier 3 | Distribution | 2002-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002086 | 400927148 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2002-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002087 | 400205854 | Molding | HFTD Tier 2 | Distribution | 2002-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002088 | 400762716 | Molding | HFTD Tier 2 | Distribution | 2002-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002089 | 400771656 | Molding | HFTD Tier 2 | Distribution | 2002-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002090 | 400836018 | Molding | HFTD Tier 2 | Distribution | 2002-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002091 | 400836203 | High Sign | HFTD Tier 2 | Distribution | 2002-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002092 | 400836900 | Ground | HFTD Tier 2 | Distribution | 2002-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002093 | 400849197 | High Sign | HFTD Tier 2 | Distribution | 2002-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002094 | 401466126 | Molding | HFTD Tier 2 | Distribution | 2002-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002095 | 400564897 | Molding | HFTD Tier 2 | Distribution | 2002-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002096 | 401001204 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002097 | 401006582 | Molding | HFTD Tier 3 | Distribution | 2002-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002098 | 400937398 | Molding | HFTD Tier 3 | Distribution | 2002-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002099 | 401001203 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002100 | 400766014 | Molding | HFTD Tier 2 | Distribution | 2002-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002101 | 400966494 | High Sign | HFTD Tier 2 | Distribution | 2002-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002102 | 400356095 | Guy | HFTD Tier 2 | Distribution | 2002-05-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002103 | 400363996 | Molding | HFTD Tier 2 | Distribution | 2002-05-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002104 | 400413055 | Guy | HFTD Tier 2 | Distribution | 2002-05-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002105 | 400537234 | Guy | HFTD Tier 3 | Distribution | 2002-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002106 | 400538703 | Molding | HFTD Tier 3 | Distribution | 2002-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002107 | 400548656 | High Sign | HFTD Tier 3 | Distribution | 2002-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002108 | 400600518 | High Sign | HFTD Tier 3 | Distribution | 2002-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002109 | 400779275 | Molding | HFTD Tier 3 | Distribution | 2002-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002110 | 400892224 | High Sign | HFTD Tier 3 | Distribution | 2002-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002111 | 400936251 | High Sign | HFTD Tier 3 | Distribution | 2002-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002112 | 400962736 | High Sign | HFTD Tier 3 | Distribution | 2002-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002113 | 400985769 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002114 | 400720552 | High Sign | HFTD Tier 2 | Distribution | 2002-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002115 | 400797477 | Molding | HFTD Tier 2 | Distribution | 2002-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002116 | 400553747 | High Sign | HFTD Tier 2 | Distribution | 2002-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002117 | 400563621 | Molding | HFTD Tier 2 | Distribution | 2002-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002118 | 400619505 | High Sign | HFTD Tier 2 | Distribution | 2002-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002119 | 400696730 | Molding | HFTD Tier 2 | Distribution | 2002-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002120 | 400705889 | Molding | HFTD Tier 2 | Distribution | 2002-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002121 | 400709501 | High Sign | HFTD Tier 2 | Distribution | 2002-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002122 | 400709565 | Hardware/Framing | HFTD Tier 2 | Distribution | 2002-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002123 | 400710516 | High Sign | HFTD Tier 2 | Distribution | 2002-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002124 | 400957555 | High Sign | HFTD Tier 2 | Distribution | 2002-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002125 | 400637650 | High Sign | HFTD Tier 2 | Distribution | 2002-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002126 | 400805477 | High Sign | HFTD Tier 2 | Distribution | 2002-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002127 | 400878146 | High Sign | HFTD Tier 2 | Distribution | 2002-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002128 | 400541224 | Molding | HFTD Tier 2 | Distribution | 2002-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002129 | 400545713 | Molding | HFTD Tier 2 | Distribution | 2002-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002130 | 400565757 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002131 | 400697916 | Hardware/Framing | HFTD Tier 2 | Distribution | 2002-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002132 | 400739653 | High Sign | HFTD Tier 2 | Distribution | 2002-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002133 | 400745602 | High Sign | HFTD Tier 2 | Distribution | 2002-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002134 | 400848584 | Molding | HFTD Tier 2 | Distribution | 2002-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002135 | 400872673 | Molding | HFTD Tier 3 | Distribution | 2002-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002136 | 400955207 | Insulator | HFTD Tier 3 | Distribution | 2002-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002137 | 400955227 | Molding | HFTD Tier 2 | Distribution | 2002-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002138 | 400993136 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002139 | 400741997 | Guy | HFTD Tier 2 | Distribution | 2002-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002140 | 400750048 | Molding | HFTD Tier 2 | Distribution | 2002-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002141 | 400664746 | High Sign | HFTD Tier 3 | Distribution | 2002-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002142 | 400882158 | High Sign | HFTD Tier 3 | Distribution | 2002-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002143 | 400270299 | Cable/Conductor | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002144 | 400313708 | Molding | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002145 | 400530858 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002146 | 400534856 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002147 | 400535663 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002148 | 400536254 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002149 | 400536286 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002150 | 400536812 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002151 | 400538521 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002152 | 400539441 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002153 | 400539972 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002154 | 400541605 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002155 | 400541667 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002156 | 400543417 | High Sign | HFTD Tier 3 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002157 | 400635934 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002158 | 400638286 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002159 | 400639329 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002160 | 400640119 | Guy | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002161 | 400642669 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002162 | 400644683 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002163 | 400649542 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002164 | 400649635 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002165 | 400650577 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002166 | 400650605 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002167 | 400651440 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002168 | 400652447 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002169 | 400652475 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002170 | 400652990 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002171 | 400653096 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002172 | 400653962 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002173 | 400654025 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002174 | 400656041 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002175 | 400656087 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002176 | 400660995 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002177 | 400661089 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002178 | 400662071 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002179 | 400663314 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002180 | 400689039 | Molding | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002181 | 400699064 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002182 | 400706005 | Cable/Conductor | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002183 | 400772502 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002184 | 400777403 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002185 | 400779551 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002186 | 400780159 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002187 | 400780880 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002188 | 400781358 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002189 | 400783090 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002190 | 400784570 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002191 | 400786588 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002192 | 400790210 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002193 | 400790250 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002194 | 400790300 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002195 | 400790884 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002196 | 400791733 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002197 | 400791913 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002198 | 400792107 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002199 | 400792130 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002200 | 400794060 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002201 | 400794113 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002202 | 400833403 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002203 | 400933304 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002204 | 400933538 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002205 | 400933550 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002206 | 400935005 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002207 | 400935435 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002208 | 400935748 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002209 | 400937196 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002210 | 400937712 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002211 | 400937719 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002212 | 400939083 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002213 | 400941257 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002214 | 400941273 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002215 | 400942029 | Molding | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002216 | 400942391 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002217 | 400942519 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002218 | 400942883 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002219 | 400942925 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002220 | 400943252 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002221 | 400945343 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002222 | 400948690 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002223 | 400948692 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002224 | 400968572 | Molding | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002225 | 400968767 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002226 | 400970087 | High Sign | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002227 | 400992075 | Cable/Conductor | HFTD Tier 2 | Distribution | 2002-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002228 | 400640567 | High Sign | HFTD Tier 2 | Distribution | 2002-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002229 | 400640631 | High Sign | HFTD Tier 2 | Distribution | 2002-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002230 | 400646254 | High Sign | HFTD Tier 3 | Distribution | 2002-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002231 | 400649445 | Ground | HFTD Tier 2 | Distribution | 2002-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002232 | 400718575 | High Sign | HFTD Tier 2 | Distribution | 2002-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002233 | 400728274 | High Sign | HFTD Tier 2 | Distribution | 2002-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002234 | 400787481 | Molding | HFTD Tier 2 | Distribution | 2002-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002235 | 400827833 | High Sign | HFTD Tier 2 | Distribution | 2002-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002236 | 400836431 | Molding | HFTD Tier 2 | Distribution | 2002-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002237 | 400843634 | High Sign | HFTD Tier 3 | Distribution | 2002-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002238 | 400957246 | High Sign | HFTD Tier 2 | Distribution | 2002-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002239 | 400958090 | Molding | HFTD Tier 2 | Distribution | 2002-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002240 | 400959897 | High Sign | HFTD Tier 2 | Distribution | 2002-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002241 | 401006570 | High Sign | HFTD Tier 3 | Distribution | 2002-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002242 | 400908670 | High Sign | HFTD Tier 3 | Distribution | 2002-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002243 | 400586042 | High Sign | HFTD Tier 3 | Distribution | 2002-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002244 | 400592302 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002245 | 400607505 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002246 | 400639203 | High Sign | HFTD Tier 3 | Distribution | 2002-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002247 | 400656798 | Insulator | HFTD Tier 2 | Distribution | 2002-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002248 | 400658894 | Cable/Conductor | HFTD Tier 2 | Distribution | 2002-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002249 | 400662231 | High Sign | HFTD Tier 3 | Distribution | 2002-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002250 | 400701988 | High Sign | HFTD Tier 3 | Distribution | 2002-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002251 | 400712436 | Molding | HFTD Tier 2 | Distribution | 2002-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002252 | 400805805 | Insulator | HFTD Tier 2 | Distribution | 2002-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002253 | 400831864 | High Sign | HFTD Tier 3 | Distribution | 2002-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002254 | 400841430 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002255 | 400846136 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002256 | 400926216 | High Sign | HFTD Tier 3 | Distribution | 2002-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002257 | 400956273 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002258 | 400996379 | Cable/Conductor | HFTD Tier 2 | Distribution | 2002-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002259 | 400998602 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002260 | 400998703 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002261 | 400999255 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002262 | 400999308 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002263 | 400593116 | High Sign | HFTD Tier 2 | Distribution | 2002-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002264 | 400596837 | High Sign | HFTD Tier 2 | Distribution | 2002-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002265 | 400688001 | High Sign | HFTD Tier 2 | Distribution | 2002-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002266 | 400947381 | Molding | HFTD Tier 2 | Distribution | 2002-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002267 | 400724709 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002268 | 400985904 | Cable/Conductor | HFTD Tier 3 | Distribution | 2002-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002269 | 400962764 | Molding | HFTD Tier 2 | Distribution | 2002-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002270 | 400610109 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002271 | 400611506 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002272 | 400613363 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002273 | 400614313 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002274 | 400616197 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002275 | 400616917 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002276 | 400616945 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002277 | 400617042 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002278 | 400619309 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002279 | 400665726 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002280 | 400665753 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002281 | 400671137 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002282 | 400672223 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002283 | 400674808 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002284 | 400674838 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002285 | 400786856 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002286 | 400788767 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002287 | 400788796 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002288 | 400791192 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002289 | 400795306 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002290 | 400849822 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002291 | 400851701 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002292 | 400851718 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002293 | 400852066 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002294 | 400852844 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002295 | 400854787 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002296 | 400854803 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002297 | 400855764 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002298 | 400861313 | High Sign | HFTD Tier 2 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002299 | 401006694 | Hardware/Framing | HFTD Tier 3 | Distribution | 2002-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002300 | 400376028 | High Sign | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002301 | 400379391 | Insulator | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002302 | 400379408 | High Sign | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002303 | 400379921 | Molding | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002304 | 400380860 | High Sign | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002305 | 400382253 | High Sign | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002306 | 400382284 | High Sign | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002307 | 400382834 | High Sign | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002308 | 400383323 | Molding | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002309 | 400384178 | High Sign | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002310 | 400387632 | High Sign | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002311 | 400388613 | Molding | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002312 | 400389143 | Molding | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002313 | 400392838 | Molding | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002314 | 400395086 | High Sign | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002315 | 400396946 | High Sign | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002316 | 400396973 | Molding | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002317 | 400398141 | High Sign | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002318 | 400400395 | High Sign | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002319 | 400540905 | Molding | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002320 | 400592391 | Molding | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002321 | 400594728 | High Sign | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002322 | 400631803 | Molding | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002323 | 400708494 | Molding | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002324 | 400769633 | Molding | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002325 | 400773371 | Molding | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002326 | 400774656 | High Sign | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002327 | 400779758 | Molding | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002328 | 400808543 | Molding | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002329 | 400810398 | Molding | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002330 | 400900661 | Molding | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002331 | 400902787 | Molding | HFTD Tier 2 | Distribution | 2002-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002332 | 400645808 | High Sign | HFTD Tier 2 | Distribution | 2002-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002333 | 400735056 | High Sign | HFTD Tier 2 | Distribution | 2002-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002334 | 400829982 | High Sign | HFTD Tier 3 | Distribution | 2002-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002335 | 400864110 | High Sign | HFTD Tier 2 | Distribution | 2002-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002336 | 400865587 | High Sign | HFTD Tier 2 | Distribution | 2002-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002337 | 400924041 | Hardware/Framing | HFTD Tier 3 | Distribution | 2002-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002338 | 401006516 | High Sign | HFTD Tier 3 | Distribution | 2002-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002339 | 400640010 | High Sign | HFTD Tier 2 | Distribution | 2002-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002340 | 400596329 | High Sign | HFTD Tier 3 | Distribution | 2002-08-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002341 | 400624942 | Molding | HFTD Tier 3 | Distribution | 2002-08-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002342 | 400878223 | Hardware/Framing | HFTD Tier 3 | Distribution | 2002-08-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002343 | 400540803 | High Sign | HFTD Tier 2 | Distribution | 2002-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002344 | 400851490 | Molding | HFTD Tier 2 | Distribution | 2002-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002345 | 400901964 | Molding | HFTD Tier 2 | Distribution | 2002-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002346 | 401006683 | High Sign | HFTD Tier 3 | Distribution | 2002-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002347 | 401005300 | Molding | HFTD Tier 2 | Distribution | 2002-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002348 | 400755822 | Guy | HFTD Tier 3 | Distribution | 2002-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002349 | 400727604 | High Sign | HFTD Tier 2 | Distribution | 2002-09-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002350 | 400730104 | High Sign | HFTD Tier 2 | Distribution | 2002-09-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002351 | 400734860 | High Sign | HFTD Tier 2 | Distribution | 2002-09-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002352 | 400899572 | High Sign | HFTD Tier 2 | Distribution | 2002-09-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002353 | 401005959 | High Sign | HFTD Tier 2 | Distribution | 2002-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002354 | 400881307 | Molding | HFTD Tier 3 | Distribution | 2002-09-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002355 | 400818650 | Molding | HFTD Tier 3 | Distribution | 2002-09-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002356 | 401006560 | Molding | HFTD Tier 3 | Distribution | 2002-09-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002357 | 401006561 | High Sign | HFTD Tier 3 | Distribution | 2002-09-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002358 | 400644310 | High Sign | HFTD Tier 3 | Distribution | 2002-09-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002359 | 400343939 | Molding | HFTD Tier 2 | Distribution | 2002-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002360 | 400358708 | Molding | HFTD Tier 2 | Distribution | 2002-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002361 | 400822756 | Molding | HFTD Tier 2 | Distribution | 2002-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002362 | 400901969 | High Sign | HFTD Tier 2 | Distribution | 2002-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002363 | 400774401 | Molding | HFTD Tier 2 | Distribution | 2003-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002364 | 400755486 | Molding | HFTD Tier 2 | Distribution | 2003-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002365 | 400529571 | Molding | HFTD Tier 2 | Distribution | 2003-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002366 | 400583898 | High Sign | HFTD Tier 2 | Distribution | 2003-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002367 | 400686326 | High Sign | HFTD Tier 2 | Distribution | 2003-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002368 | 400606546 | Molding | HFTD Tier 2 | Distribution | 2003-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002369 | 400737139 | Hardware/Framing | HFTD Tier 3 | Distribution | 2003-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002370 | 400705466 | Molding | HFTD Tier 2 | Distribution | 2003-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002371 | 400710048 | High Sign | HFTD Tier 2 | Distribution | 2003-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002372 | 400557925 | High Sign | HFTD Tier 2 | Distribution | 2003-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002373 | 400785454 | High Sign | HFTD Tier 2 | Distribution | 2003-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002374 | 400553294 | Molding | HFTD Tier 2 | Distribution | 2003-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002375 | 400620398 | Molding | HFTD Tier 2 | Distribution | 2003-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002376 | 400719390 | High Sign | HFTD Tier 2 | Distribution | 2003-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002377 | 400719417 | Molding | HFTD Tier 2 | Distribution | 2003-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002378 | 400788510 | Molding | HFTD Tier 2 | Distribution | 2003-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002379 | 400575102 | High Sign | HFTD Tier 2 | Distribution | 2003-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002380 | 400575130 | High Sign | HFTD Tier 2 | Distribution | 2003-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002381 | 400798911 | Molding | HFTD Tier 2 | Distribution | 2003-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002382 | 400576941 | Molding | HFTD Tier 2 | Distribution | 2003-04-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002383 | 400727627 | High Sign | HFTD Tier 2 | Distribution | 2003-04-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002384 | 400798925 | High Sign | HFTD Tier 2 | Distribution | 2003-04-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002385 | 400736330 | High Sign | HFTD Tier 2 | Distribution | 2003-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002386 | 400748891 | Cable/Conductor | HFTD Tier 3 | Distribution | 2003-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002387 | 400891520 | Insulator | HFTD Tier 3 | Distribution | 2003-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002388 | 400864604 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2003-05-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002389 | 400770900 | High Sign | HFTD Tier 3 | Distribution | 2003-05-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002390 | 400546811 | Molding | HFTD Tier 3 | Distribution | 2003-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002391 | 400812141 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2003-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002392 | 400557704 | High Sign | HFTD Tier 3 | Distribution | 2003-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002393 | 400559544 | High Sign | HFTD Tier 3 | Distribution | 2003-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002394 | 400819757 | Molding | HFTD Tier 3 | Distribution | 2003-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002395 | 400813979 | High Sign | HFTD Tier 2 | Distribution | 2003-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002396 | 400290884 | Guy | HFTD Tier 3 | Distribution | 2003-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002397 | 400447750 | Molding | HFTD Tier 3 | Distribution | 2003-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002398 | 400675980 | High Sign | HFTD Tier 3 | Distribution | 2003-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002399 | 400688339 | Cable/Conductor | HFTD Tier 3 | Distribution | 2003-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002400 | 400713233 | Molding | HFTD Tier 3 | Distribution | 2003-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002401 | 400787100 | Molding | HFTD Tier 3 | Distribution | 2003-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002402 | 400789120 | Cable/Conductor | HFTD Tier 3 | Distribution | 2003-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002403 | 400932002 | Molding | HFTD Tier 3 | Distribution | 2003-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002404 | 400985399 | Cable/Conductor | HFTD Tier 3 | Distribution | 2003-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002405 | 400924275 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2003-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002406 | 400985421 | Cable/Conductor | HFTD Tier 3 | Distribution | 2003-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002407 | 400985422 | Cable/Conductor | HFTD Tier 3 | Distribution | 2003-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002408 | 400985945 | Cable/Conductor | HFTD Tier 3 | Distribution | 2003-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002409 | 400549156 | Molding | HFTD Tier 3 | Distribution | 2003-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002410 | 400550916 | Molding | HFTD Tier 3 | Distribution | 2003-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002411 | 400550944 | Molding | HFTD Tier 3 | Distribution | 2003-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002412 | 400672482 | High Sign | HFTD Tier 3 | Distribution | 2003-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002413 | 400597528 | Molding | HFTD Tier 3 | Distribution | 2003-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002414 | 400689932 | Cable/Conductor | HFTD Tier 3 | Distribution | 2003-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002415 | 400897306 | Molding | HFTD Tier 3 | Distribution | 2003-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002416 | 400918564 | Molding | HFTD Tier 3 | Distribution | 2003-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002417 | 401006487 | Guy | HFTD Tier 3 | Distribution | 2003-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002418 | 400889079 | Molding | HFTD Tier 3 | Distribution | 2003-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002419 | 400668550 | Guy | HFTD Tier 3 | Distribution | 2003-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002420 | 400357963 | High Sign | HFTD Tier 3 | Distribution | 2003-06-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002421 | 400588119 | Molding | HFTD Tier 3 | Distribution | 2003-06-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002422 | 400619329 | Cable/Conductor | HFTD Tier 3 | Distribution | 2003-06-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002423 | 400620023 | High Sign | HFTD Tier 3 | Distribution | 2003-06-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002424 | 400734570 | High Sign | HFTD Tier 3 | Distribution | 2003-06-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002425 | 400734881 | Molding | HFTD Tier 3 | Distribution | 2003-06-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002426 | 400889753 | Molding | HFTD Tier 3 | Distribution | 2003-06-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002427 | 400343208 | Guy | HFTD Tier 3 | Distribution | 2003-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002428 | 400345238 | High Sign | HFTD Tier 3 | Distribution | 2003-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002429 | 400347051 | Guy | HFTD Tier 3 | Distribution | 2003-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002430 | 400363792 | Molding | HFTD Tier 3 | Distribution | 2003-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002431 | 400624065 | High Sign | HFTD Tier 3 | Distribution | 2003-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002432 | 400626996 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2003-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002433 | 400737384 | Molding | HFTD Tier 3 | Distribution | 2003-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002434 | 400300311 | High Sign | HFTD Tier 3 | Distribution | 2003-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002435 | 400587746 | Guy | HFTD Tier 3 | Distribution | 2003-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002436 | 400589737 | Molding | HFTD Tier 3 | Distribution | 2003-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002437 | 400596979 | Molding | HFTD Tier 3 | Distribution | 2003-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002438 | 400678023 | High Sign | HFTD Tier 3 | Distribution | 2003-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002439 | 400829823 | Molding | HFTD Tier 3 | Distribution | 2003-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002440 | 400833236 | Molding | HFTD Tier 3 | Distribution | 2003-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002441 | 400883365 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2003-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002442 | 400872611 | Molding | HFTD Tier 3 | Distribution | 2003-07-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002443 | 400874195 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2003-07-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002444 | 400875259 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2003-07-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002445 | 400345202 | Guy | HFTD Tier 3 | Distribution | 2003-07-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002446 | 400349013 | Guy | HFTD Tier 3 | Distribution | 2003-07-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002447 | 400828260 | High Sign | HFTD Tier 3 | Distribution | 2003-07-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002448 | 400734458 | Molding | HFTD Tier 3 | Distribution | 2003-07-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002449 | 400124057 | High Sign | HFTD Tier 2 | Distribution | 2003-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002450 | 400377728 | Molding | HFTD Tier 3 | Distribution | 2003-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002451 | 400536051 | Molding | HFTD Tier 3 | Distribution | 2003-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002452 | 400745728 | Molding | HFTD Tier 3 | Distribution | 2003-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002453 | 400775432 | Molding | HFTD Tier 3 | Distribution | 2003-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002454 | 400851746 | Hardware/Framing | HFTD Tier 3 | Distribution | 2003-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002455 | 400507402 | Cable/Conductor | HFTD Tier 3 | Distribution | 2003-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002456 | 400748652 | Molding | HFTD Tier 3 | Distribution | 2003-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002457 | 400304910 | High Sign | HFTD Tier 3 | Distribution | 2003-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002458 | 400353450 | Molding | HFTD Tier 3 | Distribution | 2003-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002459 | 400742029 | High Sign | HFTD Tier 3 | Distribution | 2003-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002460 | 400745784 | High Sign | HFTD Tier 3 | Distribution | 2003-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002461 | 400777264 | Molding | HFTD Tier 3 | Distribution | 2003-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002462 | 400734806 | High Sign | HFTD Tier 3 | Distribution | 2003-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002463 | 400843017 | Molding | HFTD Tier 3 | Distribution | 2003-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002464 | 400124871 | High Sign | HFTD Tier 2 | Distribution | 2003-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002465 | 400366975 | High Sign | HFTD Tier 3 | Distribution | 2003-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002466 | 411571260 | High Sign | HFTD Tier 3 | Distribution | 2003-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002467 | 400727710 | High Sign | HFTD Tier 3 | Distribution | 2003-07-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002468 | 400934012 | High Sign | HFTD Tier 3 | Distribution | 2003-07-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002469 | 400787150 | Cable/Conductor | HFTD Tier 3 | Distribution | 2003-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002470 | 400378561 | High Sign | HFTD Tier 3 | Distribution | 2003-08-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002471 | 400380529 | High Sign | HFTD Tier 3 | Distribution | 2003-08-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002472 | 400538735 | High Sign | HFTD Tier 3 | Distribution | 2003-08-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002473 | 400541972 | Guy | HFTD Tier 3 | Distribution | 2003-08-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002474 | 400929601 | Molding | HFTD Tier 3 | Distribution | 2003-08-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002475 | 400318030 | High Sign | HFTD Tier 3 | Distribution | 2003-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002476 | 400845171 | High Sign | HFTD Tier 3 | Distribution | 2003-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002477 | 400842201 | High Sign | HFTD Tier 2 | Distribution | 2003-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002478 | 400336644 | Guy | HFTD Tier 3 | Distribution | 2003-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002479 | 400358132 | Molding | HFTD Tier 2 | Distribution | 2003-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002480 | 400360216 | Molding | HFTD Tier 2 | Distribution | 2003-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002481 | 400378682 | Molding | HFTD Tier 3 | Distribution | 2003-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002482 | 400379906 | High Sign | HFTD Tier 3 | Distribution | 2003-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002483 | 400443032 | Molding | HFTD Tier 2 | Distribution | 2003-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002484 | 400454456 | Molding | HFTD Tier 3 | Distribution | 2003-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002485 | 400456793 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2003-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002486 | 400631405 | Guy | HFTD Tier 3 | Distribution | 2003-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002487 | 400640657 | High Sign | HFTD Tier 3 | Distribution | 2003-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002488 | 400657463 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2003-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002489 | 400669629 | Molding | HFTD Tier 3 | Distribution | 2003-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002490 | 400794809 | Hardware/Framing | HFTD Tier 2 | Distribution | 2003-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002491 | 400807871 | High Sign | HFTD Tier 2 | Distribution | 2003-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002492 | 400877026 | Molding | HFTD Tier 3 | Distribution | 2003-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002493 | 400404945 | High Sign | HFTD Tier 2 | Distribution | 2003-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002494 | 400656564 | Molding | HFTD Tier 2 | Distribution | 2003-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002495 | 400811880 | Molding | HFTD Tier 2 | Distribution | 2003-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002496 | 400875879 | Molding | HFTD Tier 3 | Distribution | 2003-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002497 | 400352397 | High Sign | HFTD Tier 2 | Distribution | 2003-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002498 | 400352419 | High Sign | HFTD Tier 2 | Distribution | 2003-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002499 | 400354274 | High Sign | HFTD Tier 2 | Distribution | 2003-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002500 | 400356140 | High Sign | HFTD Tier 2 | Distribution | 2003-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002501 | 400445565 | Molding | HFTD Tier 2 | Distribution | 2003-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002502 | 400451015 | High Sign | HFTD Tier 2 | Distribution | 2003-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002503 | 400629607 | High Sign | HFTD Tier 2 | Distribution | 2003-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002504 | 400630315 | High Sign | HFTD Tier 2 | Distribution | 2003-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002505 | 400631333 | High Sign | HFTD Tier 2 | Distribution | 2003-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002506 | 400634638 | High Sign | HFTD Tier 2 | Distribution | 2003-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002507 | 400640517 | Guy | HFTD Tier 2 | Distribution | 2003-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002508 | 400829098 | Molding | HFTD Tier 3 | Distribution | 2003-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002509 | 400845217 | High Sign | HFTD Tier 2 | Distribution | 2003-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002510 | 400847154 | Guy | HFTD Tier 2 | Distribution | 2003-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002511 | 400849812 | High Sign | HFTD Tier 2 | Distribution | 2003-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002512 | 400851671 | High Sign | HFTD Tier 2 | Distribution | 2003-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002513 | 400853521 | High Sign | HFTD Tier 2 | Distribution | 2003-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002514 | 401470447 | High Sign | HFTD Tier 2 | Distribution | 2003-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002515 | 400376601 | High Sign | HFTD Tier 3 | Distribution | 2003-08-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002516 | 400383237 | High Sign | HFTD Tier 3 | Distribution | 2003-08-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002517 | 400480809 | High Sign | HFTD Tier 3 | Distribution | 2003-08-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002518 | 400670997 | Riser/Conduit | HFTD Tier 3 | Distribution | 2003-08-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002519 | 400671053 | Insulator | HFTD Tier 3 | Distribution | 2003-08-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002520 | 400850839 | Hardware/Framing | HFTD Tier 3 | Distribution | 2003-08-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002521 | 400886493 | Molding | HFTD Tier 3 | Distribution | 2003-08-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002522 | 400371599 | High Sign | HFTD Tier 3 | Distribution | 2003-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002523 | 400371637 | High Sign | HFTD Tier 3 | Distribution | 2003-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002524 | 400373874 | Molding | HFTD Tier 3 | Distribution | 2003-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002525 | 400460629 | Guy | HFTD Tier 3 | Distribution | 2003-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002526 | 400462886 | Guy | HFTD Tier 3 | Distribution | 2003-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002527 | 400653169 | Hardware/Framing | HFTD Tier 3 | Distribution | 2003-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002528 | 400870899 | High Sign | HFTD Tier 3 | Distribution | 2003-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002529 | 400647156 | Molding | HFTD Tier 3 | Distribution | 2003-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002530 | 400699090 | High Sign | HFTD Tier 3 | Distribution | 2003-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002531 | 400761757 | Hardware/Framing | HFTD Tier 3 | Distribution | 2003-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002532 | 400535453 | Molding | HFTD Tier 2 | Distribution | 2003-08-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002533 | 400539788 | Hardware/Framing | HFTD Tier 3 | Distribution | 2003-08-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002534 | 400740556 | Molding | HFTD Tier 2 | Distribution | 2003-08-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002535 | 400577716 | Ground | HFTD Tier 3 | Distribution | 2003-08-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002536 | 400307737 | High Sign | HFTD Tier 2 | Distribution | 2003-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002537 | 400581565 | High Sign | HFTD Tier 2 | Distribution | 2003-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002538 | 400695759 | High Sign | HFTD Tier 2 | Distribution | 2003-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002539 | 400790244 | Hardware/Framing | HFTD Tier 3 | Distribution | 2003-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002540 | 400799296 | High Sign | HFTD Tier 2 | Distribution | 2003-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002541 | 400590734 | High Sign | HFTD Tier 2 | Distribution | 2003-09-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002542 | 400592640 | High Sign | HFTD Tier 2 | Distribution | 2003-09-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002543 | 400813232 | Molding | HFTD Tier 2 | Distribution | 2003-09-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002544 | 400346615 | High Sign | HFTD Tier 2 | Distribution | 2003-09-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002545 | 400487801 | High Sign | HFTD Tier 3 | Distribution | 2003-09-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002546 | 400612920 | High Sign | HFTD Tier 2 | Distribution | 2003-09-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002547 | 400727355 | Molding | HFTD Tier 2 | Distribution | 2003-09-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002548 | 400818454 | Molding | HFTD Tier 3 | Distribution | 2003-09-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002549 | 400827259 | Molding | HFTD Tier 2 | Distribution | 2003-09-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002550 | 400644714 | High Sign | HFTD Tier 2 | Distribution | 2003-09-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002551 | 400660454 | Hardware/Framing | HFTD Tier 3 | Distribution | 2003-09-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002552 | 400844932 | High Sign | HFTD Tier 3 | Distribution | 2003-09-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002553 | 400852831 | Molding | HFTD Tier 2 | Distribution | 2003-09-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002554 | 400359240 | High Sign | HFTD Tier 2 | Distribution | 2003-09-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002555 | 400377863 | High Sign | HFTD Tier 2 | Distribution | 2003-09-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002556 | 400627868 | High Sign | HFTD Tier 2 | Distribution | 2003-09-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002557 | 400392372 | High Sign | HFTD Tier 2 | Distribution | 2003-09-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002558 | 400406674 | High Sign | HFTD Tier 2 | Distribution | 2003-09-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002559 | 400442075 | High Sign | HFTD Tier 2 | Distribution | 2003-09-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002560 | 400651045 | High Sign | HFTD Tier 2 | Distribution | 2003-09-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002561 | 400656811 | Molding | HFTD Tier 2 | Distribution | 2003-09-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002562 | 400663535 | High Sign | HFTD Tier 2 | Distribution | 2003-09-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002563 | 400774701 | High Sign | HFTD Tier 2 | Distribution | 2003-09-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002564 | 400860250 | Molding | HFTD Tier 2 | Distribution | 2003-09-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002565 | 400669377 | Molding | HFTD Tier 2 | Distribution | 2003-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002566 | 400687623 | Molding | HFTD Tier 2 | Distribution | 2003-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002567 | 400781994 | Molding | HFTD Tier 3 | Distribution | 2003-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002568 | 400790192 | Molding | HFTD Tier 3 | Distribution | 2003-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002569 | 400804142 | Molding | HFTD Tier 2 | Distribution | 2003-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002570 | 400440499 | High Sign | HFTD Tier 2 | Distribution | 2003-09-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002571 | 400684220 | High Sign | HFTD Tier 3 | Distribution | 2003-09-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002572 | 400712473 | High Sign | HFTD Tier 2 | Distribution | 2003-09-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002573 | 400805896 | High Sign | HFTD Tier 3 | Distribution | 2003-09-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002574 | 400917434 | Guy | HFTD Tier 2 | Distribution | 2003-09-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002575 | 400447662 | High Sign | HFTD Tier 2 | Distribution | 2003-09-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002576 | 400911812 | High Sign | HFTD Tier 2 | Distribution | 2003-09-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002577 | 400297386 | Hardware/Framing | HFTD Tier 3 | Distribution | 2003-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002578 | 400804821 | High Sign | HFTD Tier 3 | Distribution | 2003-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002579 | 400823639 | High Sign | HFTD Tier 2 | Distribution | 2003-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002580 | 400923196 | High Sign | HFTD Tier 2 | Distribution | 2003-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002581 | 400011371 | High Sign | HFTD Tier 3 | Distribution | 2003-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002582 | 400870638 | Molding | HFTD Tier 3 | Distribution | 2003-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002583 | 400010580 | High Sign | HFTD Tier 3 | Distribution | 2003-09-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002584 | 400884871 | Riser/Conduit | HFTD Tier 2 | Distribution | 2003-09-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002585 | 400506325 | Molding | HFTD Tier 2 | Distribution | 2003-09-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002586 | 400758840 | Molding | HFTD Tier 2 | Distribution | 2003-09-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002587 | 400435697 | Molding | HFTD Tier 3 | Distribution | 2003-09-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002588 | 400515746 | Cable/Conductor | HFTD Tier 2 | Distribution | 2003-09-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002589 | 400522089 | Molding | HFTD Tier 3 | Distribution | 2003-09-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002590 | 400919889 | Hardware/Framing | HFTD Tier 3 | Distribution | 2003-09-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002591 | 400357023 | High Sign | HFTD Tier 3 | Distribution | 2003-09-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002592 | 400528713 | High Sign | HFTD Tier 2 | Distribution | 2003-09-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002593 | 400795469 | Molding | HFTD Tier 3 | Distribution | 2003-09-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002594 | 400585676 | Molding | HFTD Tier 3 | Distribution | 2003-09-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002595 | 400587314 | Molding | HFTD Tier 3 | Distribution | 2003-09-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002596 | 400295181 | High Sign | HFTD Tier 2 | Distribution | 2003-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002597 | 400302703 | High Sign | HFTD Tier 2 | Distribution | 2003-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002598 | 400311442 | Molding | HFTD Tier 2 | Distribution | 2003-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002599 | 400390409 | High Sign | HFTD Tier 2 | Distribution | 2003-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002600 | 400392028 | High Sign | HFTD Tier 2 | Distribution | 2003-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002601 | 400427207 | Molding | HFTD Tier 3 | Distribution | 2003-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002602 | 400574029 | High Sign | HFTD Tier 2 | Distribution | 2003-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002603 | 400805722 | High Sign | HFTD Tier 2 | Distribution | 2003-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002604 | 400334228 | Molding | HFTD Tier 3 | Distribution | 2003-09-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002605 | 400335052 | Molding | HFTD Tier 2 | Distribution | 2003-09-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002606 | 400338992 | Molding | HFTD Tier 2 | Distribution | 2003-09-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002607 | 400482286 | Molding | HFTD Tier 2 | Distribution | 2003-09-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002608 | 400836556 | High Sign | HFTD Tier 3 | Distribution | 2003-09-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002609 | 400623506 | Molding | HFTD Tier 2 | Distribution | 2003-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002610 | 400834542 | Molding | HFTD Tier 2 | Distribution | 2003-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002611 | 400985214 | Cable/Conductor | HFTD Tier 2 | Distribution | 2003-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002612 | 400514269 | Molding | HFTD Tier 3 | Distribution | 2003-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002613 | 400309658 | Molding | HFTD Tier 2 | Distribution | 2003-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002614 | 400414164 | High Sign | HFTD Tier 3 | Distribution | 2003-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002615 | 400510058 | High Sign | HFTD Tier 3 | Distribution | 2003-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002616 | 400513581 | High Sign | HFTD Tier 2 | Distribution | 2003-10-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002617 | 400009810 | Molding | HFTD Tier 2 | Distribution | 2003-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002618 | 400010119 | Molding | HFTD Tier 2 | Distribution | 2003-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002619 | 400010465 | Molding | HFTD Tier 2 | Distribution | 2003-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002620 | 400011438 | Molding | HFTD Tier 2 | Distribution | 2003-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002621 | 400011643 | Molding | HFTD Tier 2 | Distribution | 2003-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002622 | 400011928 | High Sign | HFTD Tier 2 | Distribution | 2003-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002623 | 400012538 | Molding | HFTD Tier 2 | Distribution | 2003-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002624 | 400016482 | Molding | HFTD Tier 2 | Distribution | 2003-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002625 | 400296826 | Ground | HFTD Tier 2 | Distribution | 2003-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002626 | 400296852 | High Sign | HFTD Tier 2 | Distribution | 2003-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002627 | 400350961 | High Sign | HFTD Tier 2 | Distribution | 2003-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002628 | 400350984 | High Sign | HFTD Tier 2 | Distribution | 2003-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002629 | 400352521 | Molding | HFTD Tier 2 | Distribution | 2003-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002630 | 400354871 | High Sign | HFTD Tier 2 | Distribution | 2003-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002631 | 400523678 | High Sign | HFTD Tier 2 | Distribution | 2003-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002632 | 400525373 | Molding | HFTD Tier 2 | Distribution | 2003-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002633 | 400526150 | Molding | HFTD Tier 2 | Distribution | 2003-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002634 | 400527227 | Molding | HFTD Tier 2 | Distribution | 2003-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002635 | 400527250 | Molding | HFTD Tier 2 | Distribution | 2003-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002636 | 400930201 | High Sign | HFTD Tier 3 | Distribution | 2003-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002637 | 400328432 | High Sign | HFTD Tier 2 | Distribution | 2003-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002638 | 400359889 | Guy | HFTD Tier 3 | Distribution | 2003-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002639 | 400361540 | Guy | HFTD Tier 3 | Distribution | 2003-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002640 | 400363883 | Riser/Conduit | HFTD Tier 3 | Distribution | 2003-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002641 | 400370083 | High Sign | HFTD Tier 3 | Distribution | 2003-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002642 | 400463779 | Molding | HFTD Tier 3 | Distribution | 2003-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002643 | 400578474 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2003-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002644 | 400992501 | Cable/Conductor | HFTD Tier 3 | Distribution | 2003-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002645 | 400340976 | Guy | HFTD Tier 3 | Distribution | 2003-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002646 | 400403520 | Guy | HFTD Tier 3 | Distribution | 2003-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002647 | 400536966 | Molding | HFTD Tier 2 | Distribution | 2003-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002648 | 401468014 | High Sign | HFTD Tier 3 | Distribution | 2003-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002649 | 400420225 | Molding | HFTD Tier 2 | Distribution | 2003-10-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002650 | 400368921 | High Sign | HFTD Tier 3 | Distribution | 2003-10-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002651 | 400370919 | High Sign | HFTD Tier 2 | Distribution | 2003-10-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002652 | 400426014 | High Sign | HFTD Tier 2 | Distribution | 2003-10-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002653 | 400433900 | High Sign | HFTD Tier 3 | Distribution | 2003-10-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002654 | 400497851 | Molding | HFTD Tier 3 | Distribution | 2003-10-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002655 | 400604820 | High Sign | HFTD Tier 2 | Distribution | 2003-10-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002656 | 400606596 | Cable/Conductor | HFTD Tier 2 | Distribution | 2003-10-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002657 | 400608936 | Molding | HFTD Tier 3 | Distribution | 2003-10-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002658 | 400468984 | High Sign | HFTD Tier 2 | Distribution | 2003-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002659 | 400470240 | High Sign | HFTD Tier 2 | Distribution | 2003-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002660 | 400472207 | High Sign | HFTD Tier 2 | Distribution | 2003-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002661 | 400397519 | Molding | HFTD Tier 2 | Distribution | 2003-10-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002662 | 400432602 | High Sign | HFTD Tier 2 | Distribution | 2003-10-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002663 | 400471220 | High Sign | HFTD Tier 2 | Distribution | 2003-10-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002664 | 400472742 | Riser/Conduit | HFTD Tier 2 | Distribution | 2003-10-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002665 | 400533081 | High Sign | HFTD Tier 2 | Distribution | 2003-10-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002666 | 400533723 | High Sign | HFTD Tier 2 | Distribution | 2003-10-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002667 | 400647069 | High Sign | HFTD Tier 3 | Distribution | 2003-10-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002668 | 400650020 | High Sign | HFTD Tier 2 | Distribution | 2003-10-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002669 | 400295538 | High Sign | HFTD Tier 2 | Distribution | 2003-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002670 | 400296611 | Molding | HFTD Tier 2 | Distribution | 2003-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002671 | 400297872 | Molding | HFTD Tier 2 | Distribution | 2003-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002672 | 400297941 | Molding | HFTD Tier 2 | Distribution | 2003-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002673 | 400502469 | Molding | HFTD Tier 3 | Distribution | 2003-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002674 | 400504822 | Molding | HFTD Tier 2 | Distribution | 2003-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002675 | 400509448 | Molding | HFTD Tier 2 | Distribution | 2003-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002676 | 400588153 | Molding | HFTD Tier 2 | Distribution | 2003-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002677 | 401609135 | Cable/Conductor | HFTD Tier 3 | Distribution | 2003-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002678 | 400294419 | High Sign | HFTD Tier 3 | Distribution | 2003-10-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002679 | 400460437 | Guy | HFTD Tier 3 | Distribution | 2003-10-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002680 | 400460482 | High Sign | HFTD Tier 2 | Distribution | 2003-10-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002681 | 400503002 | High Sign | HFTD Tier 3 | Distribution | 2003-10-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002682 | 400506032 | Molding | HFTD Tier 2 | Distribution | 2003-10-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002683 | 400509409 | High Sign | HFTD Tier 3 | Distribution | 2003-10-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002684 | 400315906 | Molding | HFTD Tier 2 | Distribution | 2003-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002685 | 400321375 | High Sign | HFTD Tier 2 | Distribution | 2003-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002686 | 400481353 | Molding | HFTD Tier 2 | Distribution | 2003-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002687 | 400618477 | High Sign | HFTD Tier 2 | Distribution | 2003-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002688 | 400342170 | Molding | HFTD Tier 2 | Distribution | 2003-10-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002689 | 400383861 | Molding | HFTD Tier 3 | Distribution | 2003-10-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002690 | 400494035 | Molding | HFTD Tier 2 | Distribution | 2003-10-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002691 | 400515679 | High Sign | HFTD Tier 2 | Distribution | 2003-10-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002692 | 400517452 | Molding | HFTD Tier 2 | Distribution | 2003-10-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002693 | 400518429 | High Sign | HFTD Tier 2 | Distribution | 2003-10-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002694 | 400642563 | High Sign | HFTD Tier 2 | Distribution | 2003-10-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002695 | 400646169 | High Sign | HFTD Tier 3 | Distribution | 2003-10-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002696 | 400353485 | High Sign | HFTD Tier 2 | Distribution | 2003-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002697 | 400358535 | Molding | HFTD Tier 2 | Distribution | 2003-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002698 | 400365128 | High Sign | HFTD Tier 2 | Distribution | 2003-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002699 | 400497900 | Molding | HFTD Tier 2 | Distribution | 2003-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002700 | 400501818 | Molding | HFTD Tier 2 | Distribution | 2003-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002701 | 400501841 | Molding | HFTD Tier 2 | Distribution | 2003-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002702 | 400506434 | High Sign | HFTD Tier 2 | Distribution | 2003-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002703 | 400664758 | High Sign | HFTD Tier 2 | Distribution | 2003-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002704 | 400675695 | High Sign | HFTD Tier 2 | Distribution | 2003-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002705 | 400683157 | Molding | HFTD Tier 2 | Distribution | 2003-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002706 | 400015628 | Riser/Conduit | HFTD Tier 3 | Distribution | 2003-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002707 | 400374014 | High Sign | HFTD Tier 2 | Distribution | 2003-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002708 | 400379033 | High Sign | HFTD Tier 2 | Distribution | 2003-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002709 | 400508220 | Molding | HFTD Tier 2 | Distribution | 2003-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002710 | 400508229 | Molding | HFTD Tier 2 | Distribution | 2003-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002711 | 400521001 | Molding | HFTD Tier 2 | Distribution | 2003-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002712 | 400529337 | High Sign | HFTD Tier 3 | Distribution | 2003-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002713 | 400539775 | High Sign | HFTD Tier 2 | Distribution | 2003-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002714 | 400299943 | Molding | HFTD Tier 2 | Distribution | 2003-10-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002715 | 400514885 | High Sign | HFTD Tier 2 | Distribution | 2003-10-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002716 | 400543123 | Molding | HFTD Tier 2 | Distribution | 2003-10-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002717 | 400526047 | Guy | HFTD Tier 3 | Distribution | 2003-10-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002718 | 400526080 | Cable/Conductor | HFTD Tier 3 | Distribution | 2003-10-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002719 | 400526558 | Molding | HFTD Tier 2 | Distribution | 2003-10-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002720 | 400535327 | High Sign | HFTD Tier 3 | Distribution | 2003-10-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002721 | 400533902 | High Sign | HFTD Tier 2 | Distribution | 2003-10-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002722 | 400318385 | High Sign | HFTD Tier 2 | Distribution | 2003-11-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002723 | 400325955 | Riser/Conduit | HFTD Tier 2 | Distribution | 2003-11-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002724 | 400329412 | Molding | HFTD Tier 2 | Distribution | 2003-11-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002725 | 400426101 | High Sign | HFTD Tier 2 | Distribution | 2003-11-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002726 | 400565942 | High Sign | HFTD Tier 2 | Distribution | 2003-11-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002727 | 400609201 | High Sign | HFTD Tier 2 | Distribution | 2003-11-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002728 | 400375161 | Molding | HFTD Tier 3 | Distribution | 2003-11-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002729 | 400383619 | Hardware/Framing | HFTD Tier 3 | Distribution | 2003-11-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002730 | 400578593 | High Sign | HFTD Tier 2 | Distribution | 2003-11-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002731 | 400015103 | Molding | HFTD Tier 3 | Distribution | 2003-11-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002732 | 400641704 | High Sign | HFTD Tier 2 | Distribution | 2003-11-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002733 | 400653332 | High Sign | HFTD Tier 2 | Distribution | 2003-11-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002734 | 400681363 | Riser/Conduit | HFTD Tier 3 | Distribution | 2003-11-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002735 | 403046700 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2003-11-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002736 | 400058703 | High Sign | HFTD Tier 2 | Distribution | 2003-11-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002737 | 400381183 | Molding | HFTD Tier 2 | Distribution | 2003-11-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002738 | 400381875 | Molding | HFTD Tier 2 | Distribution | 2003-11-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002739 | 400428815 | High Sign | HFTD Tier 2 | Distribution | 2003-11-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002740 | 400618340 | Guy | HFTD Tier 2 | Distribution | 2003-11-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002741 | 400629190 | High Sign | HFTD Tier 2 | Distribution | 2003-11-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002742 | 400676817 | High Sign | HFTD Tier 2 | Distribution | 2003-11-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002743 | 400679260 | High Sign | HFTD Tier 2 | Distribution | 2003-11-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002744 | 400305356 | High Sign | HFTD Tier 3 | Distribution | 2003-11-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002745 | 400383284 | Molding | HFTD Tier 3 | Distribution | 2003-11-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002746 | 400410144 | High Sign | HFTD Tier 3 | Distribution | 2003-11-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002747 | 400467070 | Molding | HFTD Tier 3 | Distribution | 2003-11-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002748 | 400635523 | Molding | HFTD Tier 3 | Distribution | 2003-11-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002749 | 400691629 | High Sign | HFTD Tier 2 | Distribution | 2003-11-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002750 | 400059414 | High Sign | HFTD Tier 2 | Distribution | 2003-11-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002751 | 400049255 | Molding | HFTD Tier 2 | Distribution | 2003-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002752 | 400050897 | Molding | HFTD Tier 2 | Distribution | 2003-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002753 | 400694745 | Riser/Conduit | HFTD Tier 2 | Distribution | 2003-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002754 | 400706813 | Molding | HFTD Tier 2 | Distribution | 2003-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002755 | 400080747 | High Sign | HFTD Tier 2 | Distribution | 2003-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002756 | 400639897 | High Sign | HFTD Tier 2 | Distribution | 2003-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002757 | 400689810 | High Sign | HFTD Tier 2 | Distribution | 2003-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002758 | 400699274 | Molding | HFTD Tier 2 | Distribution | 2003-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002759 | 403046690 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2003-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002760 | 400023118 | Hardware/Framing | HFTD Tier 2 | Distribution | 2003-11-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002761 | 400070396 | Molding | HFTD Tier 3 | Distribution | 2003-11-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002762 | 400081184 | Guy | HFTD Tier 2 | Distribution | 2003-11-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002763 | 400326207 | Molding | HFTD Tier 2 | Distribution | 2003-11-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002764 | 400453060 | Molding | HFTD Tier 2 | Distribution | 2003-11-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002765 | 400651136 | Molding | HFTD Tier 2 | Distribution | 2003-11-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002766 | 400699645 | Hardware/Framing | HFTD Tier 3 | Distribution | 2003-11-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002767 | 400703686 | Molding | HFTD Tier 3 | Distribution | 2003-11-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002768 | 400055202 | Molding | HFTD Tier 2 | Distribution | 2003-11-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002769 | 400114341 | High Sign | HFTD Tier 3 | Distribution | 2003-11-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002770 | 400160229 | High Sign | HFTD Tier 3 | Distribution | 2003-11-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002771 | 400308113 | High Sign | HFTD Tier 3 | Distribution | 2003-11-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002772 | 400323874 | High Sign | HFTD Tier 2 | Distribution | 2003-11-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002773 | 400478514 | Molding | HFTD Tier 3 | Distribution | 2003-11-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002774 | 400482685 | Molding | HFTD Tier 3 | Distribution | 2003-11-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002775 | 400511185 | High Sign | HFTD Tier 2 | Distribution | 2003-11-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002776 | 400512034 | High Sign | HFTD Tier 2 | Distribution | 2003-11-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002777 | 400022014 | High Sign | HFTD Tier 2 | Distribution | 2003-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002778 | 400046130 | High Sign | HFTD Tier 3 | Distribution | 2003-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002779 | 400051736 | Molding | HFTD Tier 2 | Distribution | 2003-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002780 | 400132351 | High Sign | HFTD Tier 2 | Distribution | 2003-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002781 | 400143899 | Molding | HFTD Tier 2 | Distribution | 2003-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002782 | 400185508 | Molding | HFTD Tier 2 | Distribution | 2003-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002783 | 400517315 | Molding | HFTD Tier 2 | Distribution | 2003-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002784 | 400520850 | High Sign | HFTD Tier 2 | Distribution | 2003-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002785 | 403046562 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2003-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002786 | 403046566 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2003-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002787 | 403046795 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2003-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002788 | 400048895 | Molding | HFTD Tier 2 | Distribution | 2003-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002789 | 400057909 | High Sign | HFTD Tier 3 | Distribution | 2003-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002790 | 400086366 | Molding | HFTD Tier 2 | Distribution | 2003-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002791 | 400150402 | High Sign | HFTD Tier 2 | Distribution | 2003-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002792 | 400344840 | High Sign | HFTD Tier 2 | Distribution | 2003-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002793 | 400348860 | High Sign | HFTD Tier 2 | Distribution | 2003-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002794 | 400354174 | Cable/Conductor | HFTD Tier 3 | Distribution | 2003-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002795 | 400515564 | High Sign | HFTD Tier 2 | Distribution | 2003-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002796 | 400123156 | High Sign | HFTD Tier 2 | Distribution | 2003-11-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002797 | 400176983 | High Sign | HFTD Tier 3 | Distribution | 2003-11-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002798 | 400351827 | Guy | HFTD Tier 2 | Distribution | 2003-11-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002799 | 400359449 | High Sign | HFTD Tier 3 | Distribution | 2003-11-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002800 | 400523296 | High Sign | HFTD Tier 3 | Distribution | 2003-11-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002801 | 400247761 | Molding | HFTD Tier 3 | Distribution | 2003-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002802 | 400387706 | Molding | HFTD Tier 2 | Distribution | 2003-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002803 | 400530153 | Molding | HFTD Tier 2 | Distribution | 2003-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002804 | 400045631 | High Sign | HFTD Tier 2 | Distribution | 2003-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002805 | 400393941 | Molding | HFTD Tier 2 | Distribution | 2003-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002806 | 400403178 | High Sign | HFTD Tier 2 | Distribution | 2003-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002807 | 400406344 | High Sign | HFTD Tier 2 | Distribution | 2003-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002808 | 400427810 | Molding | HFTD Tier 3 | Distribution | 2003-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002809 | 400534271 | High Sign | HFTD Tier 2 | Distribution | 2003-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002810 | 400534284 | High Sign | HFTD Tier 2 | Distribution | 2003-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002811 | 400535809 | Molding | HFTD Tier 2 | Distribution | 2003-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002812 | 400540882 | Molding | HFTD Tier 2 | Distribution | 2003-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002813 | 400547763 | Molding | HFTD Tier 2 | Distribution | 2003-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002814 | 403046084 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2003-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002815 | 400199745 | High Sign | HFTD Tier 2 | Distribution | 2003-11-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002816 | 400203016 | High Sign | HFTD Tier 2 | Distribution | 2003-11-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002817 | 400209323 | Molding | HFTD Tier 2 | Distribution | 2003-11-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002818 | 400209347 | High Sign | HFTD Tier 2 | Distribution | 2003-11-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002819 | 400536222 | High Sign | HFTD Tier 2 | Distribution | 2003-11-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002820 | 400546982 | High Sign | HFTD Tier 2 | Distribution | 2003-11-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002821 | 400547718 | Molding | HFTD Tier 2 | Distribution | 2003-11-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002822 | 400551076 | High Sign | HFTD Tier 2 | Distribution | 2003-11-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002823 | 400225229 | Molding | HFTD Tier 2 | Distribution | 2003-11-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002824 | 400415770 | Molding | HFTD Tier 2 | Distribution | 2003-11-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002825 | 400451203 | High Sign | HFTD Tier 2 | Distribution | 2003-11-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002826 | 400451228 | High Sign | HFTD Tier 2 | Distribution | 2003-11-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002827 | 400560043 | High Sign | HFTD Tier 2 | Distribution | 2003-11-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002828 | 400163905 | High Sign | HFTD Tier 2 | Distribution | 2003-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002829 | 400167277 | Molding | HFTD Tier 3 | Distribution | 2003-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002830 | 400176022 | High Sign | HFTD Tier 3 | Distribution | 2003-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002831 | 400183962 | Guy | HFTD Tier 2 | Distribution | 2003-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002832 | 400190282 | Guy | HFTD Tier 2 | Distribution | 2003-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002833 | 400191571 | Guy | HFTD Tier 2 | Distribution | 2003-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002834 | 400252811 | High Sign | HFTD Tier 3 | Distribution | 2003-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002835 | 400259568 | Guy | HFTD Tier 2 | Distribution | 2003-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002836 | 400263396 | Guy | HFTD Tier 2 | Distribution | 2003-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002837 | 400264462 | Guy | HFTD Tier 2 | Distribution | 2003-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002838 | 400437319 | High Sign | HFTD Tier 2 | Distribution | 2003-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002839 | 400463415 | Guy | HFTD Tier 2 | Distribution | 2003-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002840 | 400466249 | Guy | HFTD Tier 2 | Distribution | 2003-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002841 | 400608015 | Molding | HFTD Tier 2 | Distribution | 2003-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002842 | 400608035 | Molding | HFTD Tier 2 | Distribution | 2003-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002843 | 400608398 | Guy | HFTD Tier 2 | Distribution | 2003-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002844 | 400611903 | Guy | HFTD Tier 2 | Distribution | 2003-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002845 | 400181176 | Molding | HFTD Tier 2 | Distribution | 2003-11-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002846 | 400251810 | Molding | HFTD Tier 2 | Distribution | 2003-11-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002847 | 400263789 | High Sign | HFTD Tier 2 | Distribution | 2003-11-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002848 | 400463952 | High Sign | HFTD Tier 2 | Distribution | 2003-11-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002849 | 400611614 | High Sign | HFTD Tier 2 | Distribution | 2003-11-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002850 | 400611795 | Molding | HFTD Tier 2 | Distribution | 2003-11-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002851 | 403046691 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2003-11-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002852 | 400202965 | Molding | HFTD Tier 2 | Distribution | 2003-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002853 | 400204425 | Molding | HFTD Tier 2 | Distribution | 2003-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002854 | 400279116 | High Sign | HFTD Tier 2 | Distribution | 2003-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002855 | 400626047 | High Sign | HFTD Tier 2 | Distribution | 2003-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002856 | 400029874 | Molding | HFTD Tier 3 | Distribution | 2003-11-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002857 | 400038921 | Riser/Conduit | HFTD Tier 3 | Distribution | 2003-11-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002858 | 400226130 | Insulator | HFTD Tier 2 | Distribution | 2003-11-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002859 | 400304311 | Insulator | HFTD Tier 2 | Distribution | 2003-11-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002860 | 400304338 | High Sign | HFTD Tier 2 | Distribution | 2003-11-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002861 | 400487206 | High Sign | HFTD Tier 2 | Distribution | 2003-11-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002862 | 400490178 | Molding | HFTD Tier 3 | Distribution | 2003-11-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002863 | 400811786 | Hardware/Framing | HFTD Tier 3 | Distribution | 2003-11-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002864 | 400034047 | Molding | HFTD Tier 2 | Distribution | 2003-11-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002865 | 400247625 | High Sign | HFTD Tier 2 | Distribution | 2003-11-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002866 | 400319322 | High Sign | HFTD Tier 2 | Distribution | 2003-11-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002867 | 400320422 | High Sign | HFTD Tier 2 | Distribution | 2003-11-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002868 | 400324869 | Molding | HFTD Tier 2 | Distribution | 2003-11-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002869 | 400492953 | High Sign | HFTD Tier 2 | Distribution | 2003-11-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002870 | 400661649 | High Sign | HFTD Tier 2 | Distribution | 2003-11-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002871 | 400245217 | High Sign | HFTD Tier 2 | Distribution | 2003-11-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002872 | 400279925 | High Sign | HFTD Tier 2 | Distribution | 2003-11-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002873 | 400332629 | High Sign | HFTD Tier 2 | Distribution | 2003-11-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002874 | 400503633 | High Sign | HFTD Tier 3 | Distribution | 2003-11-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002875 | 400271163 | Molding | HFTD Tier 3 | Distribution | 2003-11-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002876 | 400357546 | High Sign | HFTD Tier 3 | Distribution | 2003-11-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002877 | 400373512 | High Sign | HFTD Tier 3 | Distribution | 2003-11-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002878 | 400049970 | High Sign | HFTD Tier 3 | Distribution | 2003-11-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002879 | 400200248 | High Sign | HFTD Tier 3 | Distribution | 2003-11-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002880 | 400444782 | Molding | HFTD Tier 3 | Distribution | 2003-11-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002881 | 400056232 | High Sign | HFTD Tier 3 | Distribution | 2003-11-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002882 | 400019575 | Hardware/Framing | HFTD Tier 3 | Distribution | 2003-11-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002883 | 400020069 | High Sign | HFTD Tier 3 | Distribution | 2003-11-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002884 | 400020118 | Molding | HFTD Tier 3 | Distribution | 2003-11-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002885 | 400019625 | Molding | HFTD Tier 3 | Distribution | 2003-12-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002886 | 400039138 | Molding | HFTD Tier 3 | Distribution | 2003-12-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002887 | 400421456 | High Sign | HFTD Tier 3 | Distribution | 2003-12-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002888 | 400524404 | High Sign | HFTD Tier 3 | Distribution | 2003-12-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002889 | 400583741 | Molding | HFTD Tier 2 | Distribution | 2003-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002890 | 400114234 | High Sign | HFTD Tier 3 | Distribution | 2003-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002891 | 400127744 | Molding | HFTD Tier 2 | Distribution | 2003-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002892 | 400128489 | Riser/Conduit | HFTD Tier 2 | Distribution | 2003-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002893 | 400498386 | High Sign | HFTD Tier 2 | Distribution | 2003-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002894 | 400547042 | Guy | HFTD Tier 3 | Distribution | 2003-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002895 | 400392758 | High Sign | HFTD Tier 2 | Distribution | 2003-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002896 | 400490860 | High Sign | HFTD Tier 2 | Distribution | 2003-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002897 | 400498380 | High Sign | HFTD Tier 2 | Distribution | 2003-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002898 | 400052015 | High Sign | HFTD Tier 2 | Distribution | 2003-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002899 | 400091242 | High Sign | HFTD Tier 3 | Distribution | 2003-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002900 | 400075807 | Cable/Conductor | HFTD Tier 3 | Distribution | 2003-12-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002901 | 400196068 | Molding | HFTD Tier 3 | Distribution | 2003-12-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002902 | 400646398 | Molding | HFTD Tier 3 | Distribution | 2003-12-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002903 | 400045386 | Molding | HFTD Tier 3 | Distribution | 2003-12-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002904 | 400217473 | Molding | HFTD Tier 3 | Distribution | 2003-12-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002905 | 400211201 | High Sign | HFTD Tier 2 | Distribution | 2003-12-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002906 | 400652330 | Molding | HFTD Tier 3 | Distribution | 2003-12-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002907 | 400655553 | Molding | HFTD Tier 3 | Distribution | 2003-12-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002908 | 400232423 | Molding | HFTD Tier 3 | Distribution | 2003-12-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002909 | 400255033 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2003-12-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002910 | 400468537 | Molding | HFTD Tier 3 | Distribution | 2003-12-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002911 | 400471568 | Molding | HFTD Tier 3 | Distribution | 2003-12-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002912 | 400674343 | Riser/Conduit | HFTD Tier 3 | Distribution | 2003-12-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002913 | 400117437 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2003-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002914 | 400125668 | Molding | HFTD Tier 3 | Distribution | 2003-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002915 | 400694241 | High Sign | HFTD Tier 3 | Distribution | 2003-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002916 | 400248793 | Molding | HFTD Tier 3 | Distribution | 2003-12-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002917 | 400701292 | Guy | HFTD Tier 2 | Distribution | 2003-12-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002918 | 400034855 | High Sign | HFTD Tier 2 | Distribution | 2003-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002919 | 400143683 | High Sign | HFTD Tier 2 | Distribution | 2003-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002920 | 400147349 | High Sign | HFTD Tier 2 | Distribution | 2003-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002921 | 400150871 | High Sign | HFTD Tier 3 | Distribution | 2003-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002922 | 400258550 | High Sign | HFTD Tier 2 | Distribution | 2003-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002923 | 400262348 | High Sign | HFTD Tier 2 | Distribution | 2003-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002924 | 400263491 | High Sign | HFTD Tier 2 | Distribution | 2003-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002925 | 400497392 | Guy | HFTD Tier 2 | Distribution | 2003-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002926 | 400703665 | High Sign | HFTD Tier 2 | Distribution | 2003-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002927 | 400710781 | High Sign | HFTD Tier 2 | Distribution | 2003-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002928 | 400277824 | Molding | HFTD Tier 3 | Distribution | 2003-12-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002929 | 400284886 | Molding | HFTD Tier 3 | Distribution | 2003-12-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002930 | 400077201 | High Sign | HFTD Tier 2 | Distribution | 2003-12-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002931 | 400079671 | Guy | HFTD Tier 2 | Distribution | 2003-12-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002932 | 400079700 | High Sign | HFTD Tier 2 | Distribution | 2003-12-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002933 | 400093766 | High Sign | HFTD Tier 2 | Distribution | 2003-12-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002934 | 400096894 | Guy | HFTD Tier 2 | Distribution | 2003-12-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002935 | 400097816 | High Sign | HFTD Tier 2 | Distribution | 2003-12-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002936 | 400178210 | High Sign | HFTD Tier 3 | Distribution | 2003-12-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002937 | 400184904 | High Sign | HFTD Tier 3 | Distribution | 2003-12-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002938 | 400195853 | High Sign | HFTD Tier 2 | Distribution | 2003-12-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002939 | 400198046 | High Sign | HFTD Tier 2 | Distribution | 2003-12-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002940 | 400033888 | Molding | HFTD Tier 2 | Distribution | 2003-12-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002941 | 400139719 | High Sign | HFTD Tier 3 | Distribution | 2003-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002942 | 400223799 | Molding | HFTD Tier 3 | Distribution | 2003-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002943 | 400223872 | Molding | HFTD Tier 3 | Distribution | 2003-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002944 | 400162752 | Guy | HFTD Tier 3 | Distribution | 2003-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002945 | 400232807 | Molding | HFTD Tier 3 | Distribution | 2003-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002946 | 400249639 | Molding | HFTD Tier 3 | Distribution | 2003-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002947 | 400346771 | Hardware/Framing | HFTD Tier 3 | Distribution | 2003-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002948 | 400356186 | Guy | HFTD Tier 3 | Distribution | 2003-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002949 | 400133330 | Molding | HFTD Tier 3 | Distribution | 2003-12-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002950 | 400266914 | Molding | HFTD Tier 3 | Distribution | 2003-12-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002951 | 400195168 | Molding | HFTD Tier 3 | Distribution | 2003-12-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002952 | 400197384 | Molding | HFTD Tier 3 | Distribution | 2003-12-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002953 | 400282064 | High Sign | HFTD Tier 3 | Distribution | 2003-12-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002954 | 400395970 | Molding | HFTD Tier 3 | Distribution | 2003-12-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002955 | 400483937 | High Sign | HFTD Tier 3 | Distribution | 2003-12-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002956 | 400485502 | Molding | HFTD Tier 3 | Distribution | 2003-12-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002957 | 400046010 | Molding | HFTD Tier 3 | Distribution | 2003-12-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002958 | 400283836 | High Sign | HFTD Tier 3 | Distribution | 2003-12-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002959 | 400220922 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-01-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002960 | 400334191 | Crossarm | HFTD Tier 3 | Distribution | 2004-01-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002961 | 400443814 | Molding | HFTD Tier 3 | Distribution | 2004-01-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002962 | 400462911 | High Sign | HFTD Tier 3 | Distribution | 2004-01-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002963 | 400363611 | High Sign | HFTD Tier 2 | Distribution | 2004-01-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002964 | 400478116 | Guy | HFTD Tier 3 | Distribution | 2004-01-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002965 | 400482102 | Crossarm | HFTD Tier 3 | Distribution | 2004-01-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002966 | 400059027 | High Sign | HFTD Tier 3 | Distribution | 2004-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002967 | 400256180 | High Sign | HFTD Tier 2 | Distribution | 2004-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002968 | 400361871 | Molding | HFTD Tier 2 | Distribution | 2004-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002969 | 400482083 | High Sign | HFTD Tier 3 | Distribution | 2004-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002970 | 400483066 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002971 | 400270604 | High Sign | HFTD Tier 3 | Distribution | 2004-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002972 | 400365045 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002973 | 400390091 | High Sign | HFTD Tier 2 | Distribution | 2004-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002974 | 400494854 | High Sign | HFTD Tier 3 | Distribution | 2004-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002975 | 400037328 | High Sign | HFTD Tier 3 | Distribution | 2004-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002976 | 400139602 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002977 | 400141674 | Molding | HFTD Tier 3 | Distribution | 2004-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002978 | 400410141 | High Sign | HFTD Tier 3 | Distribution | 2004-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002979 | 400415892 | High Sign | HFTD Tier 3 | Distribution | 2004-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002980 | 400419948 | High Sign | HFTD Tier 3 | Distribution | 2004-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002981 | 400422708 | Guy | HFTD Tier 3 | Distribution | 2004-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002982 | 400493267 | Molding | HFTD Tier 3 | Distribution | 2004-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002983 | 400494277 | High Sign | HFTD Tier 3 | Distribution | 2004-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002984 | 400099600 | High Sign | HFTD Tier 2 | Distribution | 2004-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002985 | 400102663 | High Sign | HFTD Tier 2 | Distribution | 2004-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002986 | 400341513 | High Sign | HFTD Tier 2 | Distribution | 2004-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002987 | 400046609 | High Sign | HFTD Tier 2 | Distribution | 2004-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002988 | 400405294 | Molding | HFTD Tier 3 | Distribution | 2004-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002989 | 400455325 | High Sign | HFTD Tier 2 | Distribution | 2004-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002990 | 400061410 | Molding | HFTD Tier 2 | Distribution | 2004-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002991 | 400139579 | High Sign | HFTD Tier 3 | Distribution | 2004-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002992 | 400043237 | Molding | HFTD Tier 2 | Distribution | 2004-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002993 | 400089849 | Molding | HFTD Tier 3 | Distribution | 2004-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002994 | 400231925 | Molding | HFTD Tier 3 | Distribution | 2004-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002995 | 400406513 | High Sign | HFTD Tier 3 | Distribution | 2004-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002996 | 400435090 | Guy | HFTD Tier 3 | Distribution | 2004-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002997 | 400043576 | Molding | HFTD Tier 2 | Distribution | 2004-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002998 | 400103320 | High Sign | HFTD Tier 3 | Distribution | 2004-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120002999 | 400218850 | High Sign | HFTD Tier 3 | Distribution | 2004-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003000 | 400491310 | High Sign | HFTD Tier 3 | Distribution | 2004-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003001 | 400213966 | High Sign | HFTD Tier 2 | Distribution | 2004-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003002 | 400235886 | High Sign | HFTD Tier 3 | Distribution | 2004-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003003 | 400250355 | High Sign | HFTD Tier 2 | Distribution | 2004-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003004 | 400478624 | Molding | HFTD Tier 2 | Distribution | 2004-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003005 | 400031631 | High Sign | HFTD Tier 3 | Distribution | 2004-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003006 | 400039681 | High Sign | HFTD Tier 2 | Distribution | 2004-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003007 | 400152596 | High Sign | HFTD Tier 3 | Distribution | 2004-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003008 | 400152774 | Molding | HFTD Tier 3 | Distribution | 2004-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003009 | 400233031 | Molding | HFTD Tier 3 | Distribution | 2004-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003010 | 400480248 | High Sign | HFTD Tier 3 | Distribution | 2004-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003011 | 400078111 | High Sign | HFTD Tier 3 | Distribution | 2004-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003012 | 400078304 | Riser/Conduit | HFTD Tier 3 | Distribution | 2004-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003013 | 400290228 | Molding | HFTD Tier 3 | Distribution | 2004-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003014 | 400290256 | High Sign | HFTD Tier 3 | Distribution | 2004-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003015 | 400299697 | Molding | HFTD Tier 3 | Distribution | 2004-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003016 | 400342765 | Molding | HFTD Tier 3 | Distribution | 2004-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003017 | 401002497 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003018 | 400121591 | Molding | HFTD Tier 3 | Distribution | 2004-01-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003019 | 400125233 | Molding | HFTD Tier 3 | Distribution | 2004-01-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003020 | 400130486 | High Sign | HFTD Tier 3 | Distribution | 2004-01-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003021 | 400196100 | Molding | HFTD Tier 3 | Distribution | 2004-01-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003022 | 400204208 | Molding | HFTD Tier 3 | Distribution | 2004-01-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003023 | 400208868 | High Sign | HFTD Tier 3 | Distribution | 2004-01-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003024 | 400240493 | Molding | HFTD Tier 3 | Distribution | 2004-01-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003025 | 400134032 | Molding | HFTD Tier 2 | Distribution | 2004-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003026 | 400251190 | Riser/Conduit | HFTD Tier 3 | Distribution | 2004-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003027 | 400141571 | Molding | HFTD Tier 3 | Distribution | 2004-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003028 | 400143560 | Molding | HFTD Tier 3 | Distribution | 2004-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003029 | 400167841 | Molding | HFTD Tier 2 | Distribution | 2004-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003030 | 400171094 | High Sign | HFTD Tier 3 | Distribution | 2004-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003031 | 400179186 | High Sign | HFTD Tier 3 | Distribution | 2004-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003032 | 400179766 | Molding | HFTD Tier 2 | Distribution | 2004-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003033 | 400259463 | Riser/Conduit | HFTD Tier 3 | Distribution | 2004-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003034 | 400373232 | High Sign | HFTD Tier 3 | Distribution | 2004-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003035 | 400379203 | Molding | HFTD Tier 3 | Distribution | 2004-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003036 | 400393535 | Molding | HFTD Tier 3 | Distribution | 2004-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003037 | 400416277 | High Sign | HFTD Tier 3 | Distribution | 2004-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003038 | 400089905 | High Sign | HFTD Tier 3 | Distribution | 2004-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003039 | 400170068 | High Sign | HFTD Tier 3 | Distribution | 2004-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003040 | 400173513 | Molding | HFTD Tier 2 | Distribution | 2004-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003041 | 400178144 | High Sign | HFTD Tier 2 | Distribution | 2004-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003042 | 400299335 | Molding | HFTD Tier 2 | Distribution | 2004-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003043 | 400312807 | Molding | HFTD Tier 2 | Distribution | 2004-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003044 | 400314962 | Guy | HFTD Tier 2 | Distribution | 2004-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003045 | 400401334 | High Sign | HFTD Tier 2 | Distribution | 2004-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003046 | 400402413 | Riser/Conduit | HFTD Tier 2 | Distribution | 2004-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003047 | 400057845 | High Sign | HFTD Tier 3 | Distribution | 2004-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003048 | 400210701 | High Sign | HFTD Tier 2 | Distribution | 2004-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003049 | 400220262 | Molding | HFTD Tier 3 | Distribution | 2004-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003050 | 400245428 | High Sign | HFTD Tier 2 | Distribution | 2004-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003051 | 400247047 | High Sign | HFTD Tier 2 | Distribution | 2004-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003052 | 400297729 | Riser/Conduit | HFTD Tier 3 | Distribution | 2004-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003053 | 400297783 | High Sign | HFTD Tier 3 | Distribution | 2004-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003054 | 400479644 | Molding | HFTD Tier 3 | Distribution | 2004-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003055 | 400489026 | High Sign | HFTD Tier 2 | Distribution | 2004-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003056 | 400189377 | High Sign | HFTD Tier 2 | Distribution | 2004-02-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003057 | 400219149 | Molding | HFTD Tier 2 | Distribution | 2004-02-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003058 | 400220326 | Molding | HFTD Tier 3 | Distribution | 2004-02-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003059 | 400356613 | Molding | HFTD Tier 2 | Distribution | 2004-02-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003060 | 400366202 | High Sign | HFTD Tier 2 | Distribution | 2004-02-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003061 | 400373308 | High Sign | HFTD Tier 3 | Distribution | 2004-02-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003062 | 400486455 | High Sign | HFTD Tier 2 | Distribution | 2004-02-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003063 | 400494473 | High Sign | HFTD Tier 2 | Distribution | 2004-02-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003064 | 400066589 | Molding | HFTD Tier 3 | Distribution | 2004-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003065 | 400185453 | Ground | HFTD Tier 2 | Distribution | 2004-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003066 | 400211822 | Guy | HFTD Tier 3 | Distribution | 2004-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003067 | 400221223 | High Sign | HFTD Tier 2 | Distribution | 2004-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003068 | 400226184 | Molding | HFTD Tier 2 | Distribution | 2004-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003069 | 400478356 | Molding | HFTD Tier 3 | Distribution | 2004-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003070 | 400481664 | Molding | HFTD Tier 2 | Distribution | 2004-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003071 | 400223528 | Molding | HFTD Tier 2 | Distribution | 2004-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003072 | 400228199 | High Sign | HFTD Tier 2 | Distribution | 2004-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003073 | 400230131 | Molding | HFTD Tier 2 | Distribution | 2004-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003074 | 400249245 | High Sign | HFTD Tier 2 | Distribution | 2004-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003075 | 400488430 | Molding | HFTD Tier 2 | Distribution | 2004-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003076 | 400039460 | Guy | HFTD Tier 3 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003077 | 400078888 | High Sign | HFTD Tier 2 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003078 | 400099055 | Molding | HFTD Tier 2 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003079 | 400100201 | High Sign | HFTD Tier 2 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003080 | 400101543 | High Sign | HFTD Tier 2 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003081 | 400247964 | Guy | HFTD Tier 3 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003082 | 400261768 | High Sign | HFTD Tier 3 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003083 | 400282502 | High Sign | HFTD Tier 2 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003084 | 400284151 | High Sign | HFTD Tier 2 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003085 | 400284164 | Molding | HFTD Tier 2 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003086 | 400294718 | High Sign | HFTD Tier 2 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003087 | 400304249 | High Sign | HFTD Tier 2 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003088 | 400308560 | Molding | HFTD Tier 2 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003089 | 400310670 | Molding | HFTD Tier 2 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003090 | 400312656 | Molding | HFTD Tier 2 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003091 | 400318677 | High Sign | HFTD Tier 2 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003092 | 400374323 | High Sign | HFTD Tier 2 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003093 | 400428049 | High Sign | HFTD Tier 2 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003094 | 400430230 | High Sign | HFTD Tier 2 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003095 | 400430260 | High Sign | HFTD Tier 2 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003096 | 400433208 | High Sign | HFTD Tier 2 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003097 | 400434344 | High Sign | HFTD Tier 2 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003098 | 400500237 | Molding | HFTD Tier 2 | Distribution | 2004-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003099 | 400089097 | Insulator | HFTD Tier 3 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003100 | 400114553 | High Sign | HFTD Tier 3 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003101 | 400130402 | High Sign | HFTD Tier 2 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003102 | 400279985 | Molding | HFTD Tier 3 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003103 | 400308528 | Molding | HFTD Tier 3 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003104 | 400311457 | Molding | HFTD Tier 3 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003105 | 400312708 | High Sign | HFTD Tier 2 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003106 | 400316142 | Guy | HFTD Tier 3 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003107 | 400318504 | High Sign | HFTD Tier 2 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003108 | 400321489 | Molding | HFTD Tier 2 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003109 | 400326127 | High Sign | HFTD Tier 3 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003110 | 400326209 | High Sign | HFTD Tier 2 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003111 | 400326233 | High Sign | HFTD Tier 2 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003112 | 400342620 | Guy | HFTD Tier 3 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003113 | 400345295 | Crossarm | HFTD Tier 3 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003114 | 400353432 | Molding | HFTD Tier 2 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003115 | 400360085 | High Sign | HFTD Tier 2 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003116 | 400422883 | Molding | HFTD Tier 3 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003117 | 400446419 | High Sign | HFTD Tier 3 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003118 | 400452629 | Guy | HFTD Tier 3 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003119 | 400464921 | Molding | HFTD Tier 3 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003120 | 400464971 | Molding | HFTD Tier 2 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003121 | 400465098 | High Sign | HFTD Tier 2 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003122 | 400467739 | High Sign | HFTD Tier 2 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003123 | 400467778 | High Sign | HFTD Tier 2 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003124 | 400470024 | Molding | HFTD Tier 2 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003125 | 400470038 | Molding | HFTD Tier 2 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003126 | 400470086 | High Sign | HFTD Tier 2 | Distribution | 2004-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003127 | 400048768 | High Sign | HFTD Tier 2 | Distribution | 2004-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003128 | 400052280 | High Sign | HFTD Tier 2 | Distribution | 2004-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003129 | 400059703 | Molding | HFTD Tier 3 | Distribution | 2004-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003130 | 400088058 | Guy | HFTD Tier 3 | Distribution | 2004-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003131 | 400093418 | Molding | HFTD Tier 3 | Distribution | 2004-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003132 | 400194296 | Molding | HFTD Tier 2 | Distribution | 2004-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003133 | 400325643 | High Sign | HFTD Tier 2 | Distribution | 2004-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003134 | 400329024 | High Sign | HFTD Tier 2 | Distribution | 2004-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003135 | 400375549 | Molding | HFTD Tier 2 | Distribution | 2004-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003136 | 400378294 | Molding | HFTD Tier 2 | Distribution | 2004-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003137 | 400407967 | High Sign | HFTD Tier 2 | Distribution | 2004-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003138 | 400410360 | High Sign | HFTD Tier 2 | Distribution | 2004-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003139 | 400417903 | High Sign | HFTD Tier 3 | Distribution | 2004-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003140 | 400420146 | High Sign | HFTD Tier 2 | Distribution | 2004-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003141 | 400420172 | High Sign | HFTD Tier 2 | Distribution | 2004-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003142 | 400054139 | Molding | HFTD Tier 2 | Distribution | 2004-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003143 | 400153675 | High Sign | HFTD Tier 3 | Distribution | 2004-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003144 | 400158196 | High Sign | HFTD Tier 3 | Distribution | 2004-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003145 | 400367826 | High Sign | HFTD Tier 3 | Distribution | 2004-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003146 | 400037652 | High Sign | HFTD Tier 3 | Distribution | 2004-02-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003147 | 400147536 | Molding | HFTD Tier 2 | Distribution | 2004-02-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003148 | 400222630 | High Sign | HFTD Tier 3 | Distribution | 2004-02-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003149 | 400398329 | Molding | HFTD Tier 2 | Distribution | 2004-02-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003150 | 400405172 | High Sign | HFTD Tier 3 | Distribution | 2004-02-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003151 | 400418065 | High Sign | HFTD Tier 2 | Distribution | 2004-02-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003152 | 400439170 | High Sign | HFTD Tier 3 | Distribution | 2004-02-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003153 | 400385971 | Molding | HFTD Tier 2 | Distribution | 2004-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003154 | 400423833 | Molding | HFTD Tier 3 | Distribution | 2004-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003155 | 400103808 | Molding | HFTD Tier 3 | Distribution | 2004-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003156 | 400122438 | Hardware/Framing | HFTD Tier 3 | Distribution | 2004-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003157 | 400297463 | High Sign | HFTD Tier 2 | Distribution | 2004-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003158 | 400438157 | Molding | HFTD Tier 3 | Distribution | 2004-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003159 | 400447882 | Guy | HFTD Tier 3 | Distribution | 2004-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003160 | 400050208 | High Sign | HFTD Tier 2 | Distribution | 2004-02-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003161 | 400070580 | Molding | HFTD Tier 2 | Distribution | 2004-02-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003162 | 400100997 | Molding | HFTD Tier 3 | Distribution | 2004-02-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003163 | 400305843 | High Sign | HFTD Tier 2 | Distribution | 2004-02-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003164 | 400309877 | Guy | HFTD Tier 3 | Distribution | 2004-02-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003165 | 400315173 | Molding | HFTD Tier 3 | Distribution | 2004-02-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003166 | 400315876 | High Sign | HFTD Tier 2 | Distribution | 2004-02-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003167 | 400327659 | Molding | HFTD Tier 2 | Distribution | 2004-02-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003168 | 400478798 | High Sign | HFTD Tier 2 | Distribution | 2004-02-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003169 | 400482486 | High Sign | HFTD Tier 2 | Distribution | 2004-02-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003170 | 400492471 | Guy | HFTD Tier 3 | Distribution | 2004-02-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003171 | 403047145 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-02-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003172 | 400126120 | High Sign | HFTD Tier 3 | Distribution | 2004-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003173 | 400345009 | High Sign | HFTD Tier 2 | Distribution | 2004-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003174 | 400109861 | Molding | HFTD Tier 2 | Distribution | 2004-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003175 | 400356763 | High Sign | HFTD Tier 2 | Distribution | 2004-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003176 | 400437864 | Guy | HFTD Tier 3 | Distribution | 2004-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003177 | 400474887 | High Sign | HFTD Tier 3 | Distribution | 2004-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003178 | 400062395 | High Sign | HFTD Tier 2 | Distribution | 2004-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003179 | 400066527 | Molding | HFTD Tier 2 | Distribution | 2004-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003180 | 400242289 | High Sign | HFTD Tier 2 | Distribution | 2004-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003181 | 400031909 | High Sign | HFTD Tier 2 | Distribution | 2004-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003182 | 400077755 | High Sign | HFTD Tier 3 | Distribution | 2004-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003183 | 400082429 | High Sign | HFTD Tier 3 | Distribution | 2004-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003184 | 400096352 | Molding | HFTD Tier 3 | Distribution | 2004-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003185 | 400096379 | Molding | HFTD Tier 3 | Distribution | 2004-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003186 | 400102890 | High Sign | HFTD Tier 3 | Distribution | 2004-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003187 | 400122076 | Molding | HFTD Tier 3 | Distribution | 2004-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003188 | 400357741 | High Sign | HFTD Tier 2 | Distribution | 2004-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003189 | 400595266 | Molding | HFTD Tier 2 | Distribution | 2004-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003190 | 400077754 | Molding | HFTD Tier 2 | Distribution | 2004-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003191 | 400105216 | High Sign | HFTD Tier 3 | Distribution | 2004-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003192 | 400459530 | Molding | HFTD Tier 2 | Distribution | 2004-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003193 | 400463184 | Molding | HFTD Tier 2 | Distribution | 2004-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003194 | 400045899 | Molding | HFTD Tier 2 | Distribution | 2004-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003195 | 400050433 | High Sign | HFTD Tier 2 | Distribution | 2004-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003196 | 400055455 | Guy | HFTD Tier 3 | Distribution | 2004-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003197 | 400096805 | High Sign | HFTD Tier 2 | Distribution | 2004-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003198 | 400146828 | High Sign | HFTD Tier 3 | Distribution | 2004-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003199 | 400220454 | Riser/Conduit | HFTD Tier 2 | Distribution | 2004-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003200 | 400372146 | High Sign | HFTD Tier 2 | Distribution | 2004-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003201 | 400378215 | High Sign | HFTD Tier 2 | Distribution | 2004-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003202 | 400461234 | High Sign | HFTD Tier 2 | Distribution | 2004-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003203 | 400479398 | Guy | HFTD Tier 2 | Distribution | 2004-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003204 | 400119159 | High Sign | HFTD Tier 2 | Distribution | 2004-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003205 | 400122491 | High Sign | HFTD Tier 2 | Distribution | 2004-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003206 | 400122804 | Molding | HFTD Tier 2 | Distribution | 2004-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003207 | 400125363 | High Sign | HFTD Tier 2 | Distribution | 2004-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003208 | 400163567 | High Sign | HFTD Tier 2 | Distribution | 2004-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003209 | 400168144 | High Sign | HFTD Tier 3 | Distribution | 2004-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003210 | 400381594 | Molding | HFTD Tier 3 | Distribution | 2004-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003211 | 400443052 | High Sign | HFTD Tier 2 | Distribution | 2004-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003212 | 400453762 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2004-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003213 | 400455384 | High Sign | HFTD Tier 2 | Distribution | 2004-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003214 | 400455459 | High Sign | HFTD Tier 2 | Distribution | 2004-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003215 | 400476941 | High Sign | HFTD Tier 3 | Distribution | 2004-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003216 | 400480578 | High Sign | HFTD Tier 2 | Distribution | 2004-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003217 | 400510233 | High Sign | HFTD Tier 3 | Distribution | 2004-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003218 | 400548171 | High Sign | HFTD Tier 2 | Distribution | 2004-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003219 | 400122464 | High Sign | HFTD Tier 2 | Distribution | 2004-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003220 | 400172526 | Molding | HFTD Tier 2 | Distribution | 2004-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003221 | 400183727 | High Sign | HFTD Tier 2 | Distribution | 2004-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003222 | 400277329 | Molding | HFTD Tier 3 | Distribution | 2004-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003223 | 400047201 | Guy | HFTD Tier 3 | Distribution | 2004-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003224 | 400286790 | Hardware/Framing | HFTD Tier 3 | Distribution | 2004-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003225 | 400102308 | Molding | HFTD Tier 2 | Distribution | 2004-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003226 | 400296010 | Molding | HFTD Tier 3 | Distribution | 2004-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003227 | 400374618 | Molding | HFTD Tier 3 | Distribution | 2004-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003228 | 400440233 | High Sign | HFTD Tier 3 | Distribution | 2004-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003229 | 400181353 | High Sign | HFTD Tier 3 | Distribution | 2004-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003230 | 400402531 | Molding | HFTD Tier 2 | Distribution | 2004-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003231 | 400476111 | High Sign | HFTD Tier 3 | Distribution | 2004-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003232 | 400286695 | Molding | HFTD Tier 3 | Distribution | 2004-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003233 | 400534604 | Guy | HFTD Tier 3 | Distribution | 2004-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003234 | 400538370 | Guy | HFTD Tier 3 | Distribution | 2004-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003235 | 400299563 | Molding | HFTD Tier 3 | Distribution | 2004-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003236 | 400516361 | Molding | HFTD Tier 3 | Distribution | 2004-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003237 | 400478493 | Molding | HFTD Tier 3 | Distribution | 2004-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003238 | 400955464 | High Sign | HFTD Tier 3 | Distribution | 2004-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003239 | 400403391 | High Sign | HFTD Tier 3 | Distribution | 2004-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003240 | 400405429 | High Sign | HFTD Tier 3 | Distribution | 2004-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003241 | 400405453 | High Sign | HFTD Tier 3 | Distribution | 2004-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003242 | 400405468 | High Sign | HFTD Tier 3 | Distribution | 2004-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003243 | 400407240 | High Sign | HFTD Tier 3 | Distribution | 2004-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003244 | 400477102 | Molding | HFTD Tier 2 | Distribution | 2004-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003245 | 400515993 | Molding | HFTD Tier 2 | Distribution | 2004-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003246 | 400125599 | High Sign | HFTD Tier 2 | Distribution | 2004-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003247 | 400454359 | Molding | HFTD Tier 2 | Distribution | 2004-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003248 | 400459648 | High Sign | HFTD Tier 2 | Distribution | 2004-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003249 | 400031726 | High Sign | HFTD Tier 2 | Distribution | 2004-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003250 | 400057573 | Molding | HFTD Tier 2 | Distribution | 2004-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003251 | 400102008 | Molding | HFTD Tier 3 | Distribution | 2004-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003252 | 400124235 | Molding | HFTD Tier 2 | Distribution | 2004-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003253 | 400132009 | High Sign | HFTD Tier 2 | Distribution | 2004-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003254 | 400203447 | Molding | HFTD Tier 2 | Distribution | 2004-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003255 | 400431586 | Molding | HFTD Tier 3 | Distribution | 2004-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003256 | 400473592 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2004-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003257 | 400587515 | High Sign | HFTD Tier 2 | Distribution | 2004-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003258 | 400463909 | Molding | HFTD Tier 3 | Distribution | 2004-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003259 | 400542354 | Guy | HFTD Tier 3 | Distribution | 2004-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003260 | 400542673 | Molding | HFTD Tier 2 | Distribution | 2004-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003261 | 400031752 | High Sign | HFTD Tier 2 | Distribution | 2004-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003262 | 400061176 | Molding | HFTD Tier 2 | Distribution | 2004-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003263 | 400063063 | Molding | HFTD Tier 2 | Distribution | 2004-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003264 | 400485292 | Molding | HFTD Tier 2 | Distribution | 2004-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003265 | 400507746 | Guy | HFTD Tier 2 | Distribution | 2004-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003266 | 400531012 | High Sign | HFTD Tier 3 | Distribution | 2004-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003267 | 400591403 | High Sign | HFTD Tier 2 | Distribution | 2004-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003268 | 400146580 | High Sign | HFTD Tier 3 | Distribution | 2004-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003269 | 400482588 | High Sign | HFTD Tier 3 | Distribution | 2004-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003270 | 400485320 | Molding | HFTD Tier 2 | Distribution | 2004-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003271 | 400040403 | High Sign | HFTD Tier 3 | Distribution | 2004-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003272 | 400045474 | Guy | HFTD Tier 3 | Distribution | 2004-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003273 | 400087061 | High Sign | HFTD Tier 2 | Distribution | 2004-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003274 | 400087852 | Ground | HFTD Tier 2 | Distribution | 2004-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003275 | 400200330 | Molding | HFTD Tier 2 | Distribution | 2004-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003276 | 400201474 | Molding | HFTD Tier 2 | Distribution | 2004-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003277 | 400205047 | High Sign | HFTD Tier 2 | Distribution | 2004-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003278 | 400213591 | Guy | HFTD Tier 2 | Distribution | 2004-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003279 | 400218249 | High Sign | HFTD Tier 2 | Distribution | 2004-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003280 | 400218274 | High Sign | HFTD Tier 2 | Distribution | 2004-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003281 | 400377078 | High Sign | HFTD Tier 2 | Distribution | 2004-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003282 | 400388370 | High Sign | HFTD Tier 2 | Distribution | 2004-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003283 | 400517023 | Molding | HFTD Tier 2 | Distribution | 2004-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003284 | 400557737 | High Sign | HFTD Tier 2 | Distribution | 2004-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003285 | 400578229 | High Sign | HFTD Tier 3 | Distribution | 2004-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003286 | 400586132 | High Sign | HFTD Tier 3 | Distribution | 2004-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003287 | 400041487 | High Sign | HFTD Tier 2 | Distribution | 2004-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003288 | 400045385 | High Sign | HFTD Tier 3 | Distribution | 2004-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003289 | 400052050 | High Sign | HFTD Tier 3 | Distribution | 2004-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003290 | 400115249 | High Sign | HFTD Tier 2 | Distribution | 2004-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003291 | 400215885 | Molding | HFTD Tier 3 | Distribution | 2004-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003292 | 400215910 | High Sign | HFTD Tier 3 | Distribution | 2004-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003293 | 400281280 | Molding | HFTD Tier 2 | Distribution | 2004-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003294 | 400514116 | High Sign | HFTD Tier 3 | Distribution | 2004-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003295 | 400558182 | High Sign | HFTD Tier 2 | Distribution | 2004-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003296 | 400562237 | High Sign | HFTD Tier 2 | Distribution | 2004-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003297 | 400066511 | Molding | HFTD Tier 3 | Distribution | 2004-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003298 | 400116975 | High Sign | HFTD Tier 3 | Distribution | 2004-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003299 | 400117003 | Molding | HFTD Tier 3 | Distribution | 2004-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003300 | 400117335 | High Sign | HFTD Tier 2 | Distribution | 2004-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003301 | 400342700 | Guy | HFTD Tier 3 | Distribution | 2004-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003302 | 400344651 | High Sign | HFTD Tier 3 | Distribution | 2004-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003303 | 400526045 | High Sign | HFTD Tier 3 | Distribution | 2004-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003304 | 400582587 | Guy | HFTD Tier 3 | Distribution | 2004-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003305 | 400087913 | High Sign | HFTD Tier 3 | Distribution | 2004-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003306 | 400095868 | High Sign | HFTD Tier 2 | Distribution | 2004-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003307 | 400099516 | High Sign | HFTD Tier 3 | Distribution | 2004-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003308 | 400105970 | High Sign | HFTD Tier 2 | Distribution | 2004-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003309 | 400106561 | High Sign | HFTD Tier 2 | Distribution | 2004-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003310 | 400131826 | Molding | HFTD Tier 2 | Distribution | 2004-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003311 | 400133286 | Molding | HFTD Tier 3 | Distribution | 2004-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003312 | 400133472 | Molding | HFTD Tier 3 | Distribution | 2004-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003313 | 400134341 | High Sign | HFTD Tier 3 | Distribution | 2004-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003314 | 400258452 | High Sign | HFTD Tier 3 | Distribution | 2004-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003315 | 400265163 | High Sign | HFTD Tier 3 | Distribution | 2004-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003316 | 400286092 | High Sign | HFTD Tier 2 | Distribution | 2004-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003317 | 400540599 | High Sign | HFTD Tier 3 | Distribution | 2004-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003318 | 400543165 | Molding | HFTD Tier 3 | Distribution | 2004-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003319 | 400131689 | High Sign | HFTD Tier 3 | Distribution | 2004-04-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003320 | 400136887 | Molding | HFTD Tier 3 | Distribution | 2004-04-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003321 | 400309196 | High Sign | HFTD Tier 2 | Distribution | 2004-04-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003322 | 400321397 | Guy | HFTD Tier 3 | Distribution | 2004-04-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003323 | 400325446 | Insulator | HFTD Tier 2 | Distribution | 2004-04-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003324 | 400344433 | Insulator | HFTD Tier 2 | Distribution | 2004-04-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003325 | 400361061 | Hardware/Framing | HFTD Tier 3 | Distribution | 2004-04-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003326 | 400054448 | High Sign | HFTD Tier 3 | Distribution | 2004-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003327 | 400158391 | High Sign | HFTD Tier 3 | Distribution | 2004-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003328 | 400161665 | High Sign | HFTD Tier 3 | Distribution | 2004-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003329 | 400168388 | Molding | HFTD Tier 2 | Distribution | 2004-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003330 | 400327923 | High Sign | HFTD Tier 3 | Distribution | 2004-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003331 | 400328796 | High Sign | HFTD Tier 2 | Distribution | 2004-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003332 | 400331560 | Molding | HFTD Tier 3 | Distribution | 2004-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003333 | 400333438 | High Sign | HFTD Tier 2 | Distribution | 2004-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003334 | 400335802 | Molding | HFTD Tier 3 | Distribution | 2004-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003335 | 400343796 | Molding | HFTD Tier 3 | Distribution | 2004-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003336 | 400346209 | High Sign | HFTD Tier 3 | Distribution | 2004-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003337 | 400346230 | Guy | HFTD Tier 3 | Distribution | 2004-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003338 | 400347293 | High Sign | HFTD Tier 2 | Distribution | 2004-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003339 | 400354100 | High Sign | HFTD Tier 3 | Distribution | 2004-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003340 | 400992266 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003341 | 400071283 | Molding | HFTD Tier 3 | Distribution | 2004-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003342 | 400166366 | Molding | HFTD Tier 3 | Distribution | 2004-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003343 | 400206636 | Molding | HFTD Tier 2 | Distribution | 2004-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003344 | 400214629 | Guy | HFTD Tier 2 | Distribution | 2004-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003345 | 400313640 | Molding | HFTD Tier 2 | Distribution | 2004-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003346 | 400357376 | High Sign | HFTD Tier 3 | Distribution | 2004-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003347 | 400372407 | High Sign | HFTD Tier 3 | Distribution | 2004-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003348 | 400485746 | Molding | HFTD Tier 2 | Distribution | 2004-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003349 | 400944164 | Guy | HFTD Tier 3 | Distribution | 2004-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003350 | 400196692 | High Sign | HFTD Tier 3 | Distribution | 2004-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003351 | 400204150 | Molding | HFTD Tier 3 | Distribution | 2004-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003352 | 400212624 | Molding | HFTD Tier 2 | Distribution | 2004-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003353 | 400365967 | Guy | HFTD Tier 3 | Distribution | 2004-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003354 | 400369229 | High Sign | HFTD Tier 3 | Distribution | 2004-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003355 | 400399780 | High Sign | HFTD Tier 2 | Distribution | 2004-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003356 | 400410064 | Molding | HFTD Tier 2 | Distribution | 2004-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003357 | 400426435 | High Sign | HFTD Tier 2 | Distribution | 2004-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003358 | 400488414 | Molding | HFTD Tier 2 | Distribution | 2004-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003359 | 400125821 | Guy | HFTD Tier 3 | Distribution | 2004-04-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003360 | 400177033 | High Sign | HFTD Tier 2 | Distribution | 2004-04-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003361 | 400180705 | Molding | HFTD Tier 2 | Distribution | 2004-04-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003362 | 400276810 | High Sign | HFTD Tier 2 | Distribution | 2004-04-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003363 | 400419553 | Molding | HFTD Tier 3 | Distribution | 2004-04-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003364 | 400434164 | High Sign | HFTD Tier 3 | Distribution | 2004-04-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003365 | 400450466 | Molding | HFTD Tier 2 | Distribution | 2004-04-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003366 | 400453585 | High Sign | HFTD Tier 2 | Distribution | 2004-04-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003367 | 400144241 | High Sign | HFTD Tier 3 | Distribution | 2004-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003368 | 400152361 | Molding | HFTD Tier 2 | Distribution | 2004-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003369 | 400240823 | Molding | HFTD Tier 3 | Distribution | 2004-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003370 | 400253492 | Molding | HFTD Tier 2 | Distribution | 2004-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003371 | 400255413 | High Sign | HFTD Tier 2 | Distribution | 2004-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003372 | 400421259 | High Sign | HFTD Tier 2 | Distribution | 2004-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003373 | 400427191 | High Sign | HFTD Tier 3 | Distribution | 2004-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003374 | 403047058 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003375 | 400145699 | Molding | HFTD Tier 3 | Distribution | 2004-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003376 | 400186238 | Guy | HFTD Tier 3 | Distribution | 2004-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003377 | 400187570 | High Sign | HFTD Tier 3 | Distribution | 2004-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003378 | 400221515 | High Sign | HFTD Tier 2 | Distribution | 2004-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003379 | 400285912 | High Sign | HFTD Tier 2 | Distribution | 2004-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003380 | 400301748 | Hardware/Framing | HFTD Tier 2 | Distribution | 2004-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003381 | 400450130 | Molding | HFTD Tier 3 | Distribution | 2004-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003382 | 400458115 | High Sign | HFTD Tier 3 | Distribution | 2004-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003383 | 400127967 | High Sign | HFTD Tier 3 | Distribution | 2004-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003384 | 400201686 | High Sign | HFTD Tier 3 | Distribution | 2004-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003385 | 400205197 | Molding | HFTD Tier 3 | Distribution | 2004-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003386 | 400236674 | High Sign | HFTD Tier 2 | Distribution | 2004-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003387 | 400238269 | Molding | HFTD Tier 2 | Distribution | 2004-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003388 | 400241614 | High Sign | HFTD Tier 2 | Distribution | 2004-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003389 | 400337937 | Molding | HFTD Tier 2 | Distribution | 2004-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003390 | 400481164 | Guy | HFTD Tier 3 | Distribution | 2004-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003391 | 400493018 | High Sign | HFTD Tier 2 | Distribution | 2004-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003392 | 400504689 | High Sign | HFTD Tier 2 | Distribution | 2004-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003393 | 400508584 | Molding | HFTD Tier 2 | Distribution | 2004-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003394 | 400509224 | High Sign | HFTD Tier 2 | Distribution | 2004-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003395 | 400039373 | Molding | HFTD Tier 2 | Distribution | 2004-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003396 | 400040345 | Guy | HFTD Tier 2 | Distribution | 2004-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003397 | 400197006 | High Sign | HFTD Tier 3 | Distribution | 2004-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003398 | 400230641 | Molding | HFTD Tier 2 | Distribution | 2004-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003399 | 400344753 | Molding | HFTD Tier 2 | Distribution | 2004-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003400 | 400366742 | High Sign | HFTD Tier 2 | Distribution | 2004-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003401 | 400483023 | Hardware/Framing | HFTD Tier 2 | Distribution | 2004-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003402 | 400484175 | Molding | HFTD Tier 3 | Distribution | 2004-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003403 | 400121864 | Molding | HFTD Tier 2 | Distribution | 2004-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003404 | 400137020 | Riser/Conduit | HFTD Tier 2 | Distribution | 2004-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003405 | 400141913 | High Sign | HFTD Tier 2 | Distribution | 2004-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003406 | 400146372 | Molding | HFTD Tier 2 | Distribution | 2004-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003407 | 400230681 | Molding | HFTD Tier 2 | Distribution | 2004-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003408 | 400277430 | Molding | HFTD Tier 3 | Distribution | 2004-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003409 | 400322596 | High Sign | HFTD Tier 2 | Distribution | 2004-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003410 | 400332449 | High Sign | HFTD Tier 2 | Distribution | 2004-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003411 | 400342799 | Molding | HFTD Tier 2 | Distribution | 2004-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003412 | 400581359 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003413 | 401000317 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003414 | 401705589 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003415 | 400276180 | Molding | HFTD Tier 3 | Distribution | 2004-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003416 | 400517481 | Molding | HFTD Tier 2 | Distribution | 2004-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003417 | 400106545 | High Sign | HFTD Tier 3 | Distribution | 2004-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003418 | 400107429 | Molding | HFTD Tier 3 | Distribution | 2004-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003419 | 400266882 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003420 | 400267809 | Riser/Conduit | HFTD Tier 3 | Distribution | 2004-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003421 | 400335010 | High Sign | HFTD Tier 2 | Distribution | 2004-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003422 | 400414732 | High Sign | HFTD Tier 2 | Distribution | 2004-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003423 | 400442422 | Molding | HFTD Tier 2 | Distribution | 2004-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003424 | 400444737 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2004-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003425 | 400484004 | High Sign | HFTD Tier 3 | Distribution | 2004-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003426 | 400554259 | Molding | HFTD Tier 2 | Distribution | 2004-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003427 | 400581391 | Molding | HFTD Tier 2 | Distribution | 2004-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003428 | 400140161 | Hardware/Framing | HFTD Tier 2 | Distribution | 2004-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003429 | 400418028 | High Sign | HFTD Tier 2 | Distribution | 2004-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003430 | 400029634 | High Sign | HFTD Tier 2 | Distribution | 2004-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003431 | 400029666 | Molding | HFTD Tier 3 | Distribution | 2004-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003432 | 400072089 | High Sign | HFTD Tier 2 | Distribution | 2004-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003433 | 400078484 | High Sign | HFTD Tier 2 | Distribution | 2004-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003434 | 400079831 | Hardware/Framing | HFTD Tier 2 | Distribution | 2004-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003435 | 400082670 | High Sign | HFTD Tier 2 | Distribution | 2004-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003436 | 400082724 | High Sign | HFTD Tier 3 | Distribution | 2004-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003437 | 400083053 | Molding | HFTD Tier 3 | Distribution | 2004-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003438 | 400088294 | High Sign | HFTD Tier 2 | Distribution | 2004-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003439 | 400183729 | Molding | HFTD Tier 2 | Distribution | 2004-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003440 | 400191821 | Molding | HFTD Tier 3 | Distribution | 2004-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003441 | 400198544 | High Sign | HFTD Tier 2 | Distribution | 2004-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003442 | 400359734 | Guy | HFTD Tier 2 | Distribution | 2004-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003443 | 400389420 | High Sign | HFTD Tier 2 | Distribution | 2004-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003444 | 400484674 | High Sign | HFTD Tier 2 | Distribution | 2004-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003445 | 400497871 | Molding | HFTD Tier 3 | Distribution | 2004-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003446 | 400499052 | High Sign | HFTD Tier 2 | Distribution | 2004-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003447 | 400999023 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003448 | 400072045 | High Sign | HFTD Tier 2 | Distribution | 2004-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003449 | 400078430 | High Sign | HFTD Tier 2 | Distribution | 2004-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003450 | 400082697 | Molding | HFTD Tier 2 | Distribution | 2004-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003451 | 400088312 | High Sign | HFTD Tier 3 | Distribution | 2004-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003452 | 400088593 | Insulator | HFTD Tier 3 | Distribution | 2004-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003453 | 400196125 | Hardware/Framing | HFTD Tier 2 | Distribution | 2004-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003454 | 400380669 | High Sign | HFTD Tier 2 | Distribution | 2004-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003455 | 400386308 | Molding | HFTD Tier 2 | Distribution | 2004-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003456 | 400386363 | High Sign | HFTD Tier 2 | Distribution | 2004-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003457 | 400401122 | Molding | HFTD Tier 3 | Distribution | 2004-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003458 | 400497822 | Guy | HFTD Tier 2 | Distribution | 2004-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003459 | 400499087 | High Sign | HFTD Tier 3 | Distribution | 2004-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003460 | 400126568 | Crossarm | HFTD Tier 2 | Distribution | 2004-04-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003461 | 400183704 | High Sign | HFTD Tier 2 | Distribution | 2004-04-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003462 | 400187768 | High Sign | HFTD Tier 2 | Distribution | 2004-04-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003463 | 400380696 | High Sign | HFTD Tier 2 | Distribution | 2004-04-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003464 | 400382569 | High Sign | HFTD Tier 2 | Distribution | 2004-04-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003465 | 400386338 | High Sign | HFTD Tier 2 | Distribution | 2004-04-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003466 | 400494726 | High Sign | HFTD Tier 2 | Distribution | 2004-04-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003467 | 400497096 | Molding | HFTD Tier 2 | Distribution | 2004-04-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003468 | 400498389 | High Sign | HFTD Tier 2 | Distribution | 2004-04-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003469 | 400043275 | High Sign | HFTD Tier 2 | Distribution | 2004-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003470 | 400101639 | High Sign | HFTD Tier 2 | Distribution | 2004-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003471 | 400146464 | Molding | HFTD Tier 3 | Distribution | 2004-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003472 | 400157618 | Molding | HFTD Tier 3 | Distribution | 2004-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003473 | 400157671 | Molding | HFTD Tier 3 | Distribution | 2004-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003474 | 400287380 | Molding | HFTD Tier 2 | Distribution | 2004-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003475 | 400406370 | Molding | HFTD Tier 3 | Distribution | 2004-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003476 | 400417599 | Insulator | HFTD Tier 2 | Distribution | 2004-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003477 | 400464581 | Molding | HFTD Tier 3 | Distribution | 2004-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003478 | 400493953 | Molding | HFTD Tier 2 | Distribution | 2004-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003479 | 401005994 | High Sign | HFTD Tier 3 | Distribution | 2004-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003480 | 400110790 | Molding | HFTD Tier 3 | Distribution | 2004-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003481 | 400132517 | High Sign | HFTD Tier 3 | Distribution | 2004-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003482 | 400160449 | High Sign | HFTD Tier 3 | Distribution | 2004-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003483 | 400181997 | Molding | HFTD Tier 3 | Distribution | 2004-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003484 | 400240830 | High Sign | HFTD Tier 3 | Distribution | 2004-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003485 | 400246209 | High Sign | HFTD Tier 3 | Distribution | 2004-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003486 | 400285656 | Molding | HFTD Tier 3 | Distribution | 2004-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003487 | 400442329 | High Sign | HFTD Tier 3 | Distribution | 2004-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003488 | 400844638 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003489 | 400038425 | High Sign | HFTD Tier 3 | Distribution | 2004-04-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003490 | 400173084 | Molding | HFTD Tier 3 | Distribution | 2004-04-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003491 | 400178756 | Molding | HFTD Tier 3 | Distribution | 2004-04-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003492 | 400441284 | Molding | HFTD Tier 2 | Distribution | 2004-04-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003493 | 400054840 | High Sign | HFTD Tier 3 | Distribution | 2004-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003494 | 400120682 | Molding | HFTD Tier 2 | Distribution | 2004-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003495 | 400131215 | Molding | HFTD Tier 2 | Distribution | 2004-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003496 | 400131479 | Molding | HFTD Tier 2 | Distribution | 2004-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003497 | 400147199 | Molding | HFTD Tier 3 | Distribution | 2004-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003498 | 400151264 | Molding | HFTD Tier 2 | Distribution | 2004-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003499 | 400176308 | Molding | HFTD Tier 3 | Distribution | 2004-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003500 | 400194531 | Molding | HFTD Tier 3 | Distribution | 2004-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003501 | 400327207 | High Sign | HFTD Tier 3 | Distribution | 2004-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003502 | 400398715 | High Sign | HFTD Tier 3 | Distribution | 2004-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003503 | 400493787 | Molding | HFTD Tier 2 | Distribution | 2004-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003504 | 400053858 | Molding | HFTD Tier 2 | Distribution | 2004-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003505 | 400055896 | High Sign | HFTD Tier 2 | Distribution | 2004-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003506 | 400059448 | Molding | HFTD Tier 2 | Distribution | 2004-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003507 | 400191239 | Molding | HFTD Tier 3 | Distribution | 2004-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003508 | 400217736 | High Sign | HFTD Tier 3 | Distribution | 2004-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003509 | 400223459 | High Sign | HFTD Tier 2 | Distribution | 2004-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003510 | 400227408 | High Sign | HFTD Tier 3 | Distribution | 2004-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003511 | 400233799 | High Sign | HFTD Tier 2 | Distribution | 2004-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003512 | 400302359 | Molding | HFTD Tier 3 | Distribution | 2004-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003513 | 400317589 | High Sign | HFTD Tier 2 | Distribution | 2004-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003514 | 400319818 | High Sign | HFTD Tier 2 | Distribution | 2004-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003515 | 400041520 | Molding | HFTD Tier 2 | Distribution | 2004-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003516 | 400042663 | High Sign | HFTD Tier 2 | Distribution | 2004-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003517 | 400048432 | High Sign | HFTD Tier 2 | Distribution | 2004-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003518 | 400078390 | High Sign | HFTD Tier 3 | Distribution | 2004-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003519 | 400093835 | High Sign | HFTD Tier 2 | Distribution | 2004-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003520 | 400093861 | High Sign | HFTD Tier 2 | Distribution | 2004-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003521 | 400139812 | Hardware/Framing | HFTD Tier 2 | Distribution | 2004-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003522 | 400153016 | Molding | HFTD Tier 3 | Distribution | 2004-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003523 | 400210711 | High Sign | HFTD Tier 2 | Distribution | 2004-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003524 | 400214880 | Molding | HFTD Tier 2 | Distribution | 2004-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003525 | 400243900 | High Sign | HFTD Tier 3 | Distribution | 2004-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003526 | 400342349 | High Sign | HFTD Tier 3 | Distribution | 2004-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003527 | 400369076 | Molding | HFTD Tier 2 | Distribution | 2004-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003528 | 400459212 | Ground | HFTD Tier 2 | Distribution | 2004-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003529 | 400151408 | Molding | HFTD Tier 3 | Distribution | 2004-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003530 | 400189670 | Molding | HFTD Tier 3 | Distribution | 2004-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003531 | 400212505 | High Sign | HFTD Tier 2 | Distribution | 2004-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003532 | 400216938 | Molding | HFTD Tier 2 | Distribution | 2004-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003533 | 400240885 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003534 | 400254433 | Molding | HFTD Tier 3 | Distribution | 2004-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003535 | 400320636 | High Sign | HFTD Tier 3 | Distribution | 2004-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003536 | 400320662 | High Sign | HFTD Tier 3 | Distribution | 2004-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003537 | 400327046 | Molding | HFTD Tier 3 | Distribution | 2004-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003538 | 400329381 | Molding | HFTD Tier 2 | Distribution | 2004-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003539 | 400333325 | High Sign | HFTD Tier 2 | Distribution | 2004-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003540 | 400045638 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003541 | 400326038 | Molding | HFTD Tier 3 | Distribution | 2004-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003542 | 400394543 | High Sign | HFTD Tier 2 | Distribution | 2004-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003543 | 400417905 | High Sign | HFTD Tier 3 | Distribution | 2004-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003544 | 400135480 | Molding | HFTD Tier 3 | Distribution | 2004-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003545 | 400151267 | Molding | HFTD Tier 2 | Distribution | 2004-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003546 | 400219768 | Molding | HFTD Tier 3 | Distribution | 2004-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003547 | 400253559 | High Sign | HFTD Tier 2 | Distribution | 2004-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003548 | 400262772 | Molding | HFTD Tier 3 | Distribution | 2004-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003549 | 400310028 | Molding | HFTD Tier 2 | Distribution | 2004-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003550 | 400318487 | High Sign | HFTD Tier 3 | Distribution | 2004-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003551 | 400321527 | Molding | HFTD Tier 3 | Distribution | 2004-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003552 | 400323865 | High Sign | HFTD Tier 3 | Distribution | 2004-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003553 | 400324360 | Molding | HFTD Tier 3 | Distribution | 2004-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003554 | 400326997 | Molding | HFTD Tier 3 | Distribution | 2004-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003555 | 400396234 | High Sign | HFTD Tier 2 | Distribution | 2004-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003556 | 400398496 | High Sign | HFTD Tier 3 | Distribution | 2004-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003557 | 400414346 | High Sign | HFTD Tier 2 | Distribution | 2004-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003558 | 400486965 | Molding | HFTD Tier 3 | Distribution | 2004-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003559 | 400140994 | Molding | HFTD Tier 2 | Distribution | 2004-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003560 | 400159923 | Molding | HFTD Tier 2 | Distribution | 2004-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003561 | 400169393 | High Sign | HFTD Tier 2 | Distribution | 2004-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003562 | 400268841 | Molding | HFTD Tier 2 | Distribution | 2004-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003563 | 400426933 | High Sign | HFTD Tier 2 | Distribution | 2004-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003564 | 400136269 | High Sign | HFTD Tier 3 | Distribution | 2004-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003565 | 400184720 | High Sign | HFTD Tier 2 | Distribution | 2004-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003566 | 400302246 | High Sign | HFTD Tier 2 | Distribution | 2004-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003567 | 400302525 | High Sign | HFTD Tier 2 | Distribution | 2004-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003568 | 400348679 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003569 | 400367545 | Molding | HFTD Tier 2 | Distribution | 2004-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003570 | 400461456 | High Sign | HFTD Tier 2 | Distribution | 2004-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003571 | 400468372 | Guy | HFTD Tier 2 | Distribution | 2004-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003572 | 400314995 | High Sign | HFTD Tier 3 | Distribution | 2004-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003573 | 400315963 | Guy | HFTD Tier 2 | Distribution | 2004-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003574 | 400477186 | Molding | HFTD Tier 2 | Distribution | 2004-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003575 | 400030776 | Molding | HFTD Tier 2 | Distribution | 2004-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003576 | 400055487 | High Sign | HFTD Tier 2 | Distribution | 2004-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003577 | 400230679 | Insulator | HFTD Tier 2 | Distribution | 2004-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003578 | 400351218 | Molding | HFTD Tier 2 | Distribution | 2004-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003579 | 400393270 | Guy | HFTD Tier 3 | Distribution | 2004-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003580 | 400396307 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003581 | 400406416 | Molding | HFTD Tier 2 | Distribution | 2004-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003582 | 400424990 | Guy | HFTD Tier 2 | Distribution | 2004-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003583 | 400985379 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003584 | 403047255 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2004-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003585 | 400273748 | High Sign | HFTD Tier 2 | Distribution | 2004-05-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003586 | 400283941 | High Sign | HFTD Tier 2 | Distribution | 2004-05-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003587 | 400286626 | Insulator | HFTD Tier 2 | Distribution | 2004-05-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003588 | 400307063 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-05-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003589 | 400397142 | Guy | HFTD Tier 2 | Distribution | 2004-05-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003590 | 400429798 | Molding | HFTD Tier 2 | Distribution | 2004-05-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003591 | 400464305 | High Sign | HFTD Tier 2 | Distribution | 2004-05-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003592 | 400465850 | High Sign | HFTD Tier 2 | Distribution | 2004-05-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003593 | 400488206 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-05-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003594 | 400489856 | Molding | HFTD Tier 2 | Distribution | 2004-05-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003595 | 400078425 | Molding | HFTD Tier 2 | Distribution | 2004-05-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003596 | 400082776 | Guy | HFTD Tier 2 | Distribution | 2004-05-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003597 | 400084964 | High Sign | HFTD Tier 2 | Distribution | 2004-05-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003598 | 400270140 | High Sign | HFTD Tier 2 | Distribution | 2004-05-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003599 | 400271185 | High Sign | HFTD Tier 2 | Distribution | 2004-05-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003600 | 400293327 | Molding | HFTD Tier 2 | Distribution | 2004-05-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003601 | 400105959 | High Sign | HFTD Tier 2 | Distribution | 2004-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003602 | 400118253 | Insulator | HFTD Tier 2 | Distribution | 2004-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003603 | 400125127 | Hardware/Framing | HFTD Tier 2 | Distribution | 2004-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003604 | 400128031 | Insulator | HFTD Tier 2 | Distribution | 2004-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003605 | 400128089 | Insulator | HFTD Tier 2 | Distribution | 2004-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003606 | 400130591 | Insulator | HFTD Tier 2 | Distribution | 2004-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003607 | 400130658 | Molding | HFTD Tier 2 | Distribution | 2004-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003608 | 400333255 | Insulator | HFTD Tier 2 | Distribution | 2004-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003609 | 400443405 | Insulator | HFTD Tier 2 | Distribution | 2004-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003610 | 400458098 | Molding | HFTD Tier 2 | Distribution | 2004-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003611 | 400584368 | High Sign | HFTD Tier 2 | Distribution | 2004-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003612 | 400028860 | Insulator | HFTD Tier 2 | Distribution | 2004-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003613 | 400069253 | Molding | HFTD Tier 3 | Distribution | 2004-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003614 | 400128074 | Molding | HFTD Tier 2 | Distribution | 2004-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003615 | 400142323 | High Sign | HFTD Tier 2 | Distribution | 2004-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003616 | 400144549 | Molding | HFTD Tier 2 | Distribution | 2004-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003617 | 400159378 | High Sign | HFTD Tier 3 | Distribution | 2004-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003618 | 400159409 | Molding | HFTD Tier 2 | Distribution | 2004-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003619 | 400159431 | High Sign | HFTD Tier 2 | Distribution | 2004-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003620 | 400168387 | Molding | HFTD Tier 2 | Distribution | 2004-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003621 | 400325102 | Insulator | HFTD Tier 2 | Distribution | 2004-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003622 | 400330378 | Insulator | HFTD Tier 2 | Distribution | 2004-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003623 | 400441608 | High Sign | HFTD Tier 2 | Distribution | 2004-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003624 | 400453636 | Insulator | HFTD Tier 2 | Distribution | 2004-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003625 | 400458060 | Insulator | HFTD Tier 2 | Distribution | 2004-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003626 | 400498493 | High Sign | HFTD Tier 2 | Distribution | 2004-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003627 | 400028409 | Molding | HFTD Tier 3 | Distribution | 2004-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003628 | 400049800 | Molding | HFTD Tier 3 | Distribution | 2004-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003629 | 400091211 | High Sign | HFTD Tier 2 | Distribution | 2004-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003630 | 400166361 | High Sign | HFTD Tier 2 | Distribution | 2004-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003631 | 400169496 | High Sign | HFTD Tier 2 | Distribution | 2004-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003632 | 400350304 | Molding | HFTD Tier 2 | Distribution | 2004-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003633 | 400468830 | High Sign | HFTD Tier 2 | Distribution | 2004-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003634 | 400481601 | Molding | HFTD Tier 2 | Distribution | 2004-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003635 | 400495619 | Molding | HFTD Tier 2 | Distribution | 2004-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003636 | 400056277 | High Sign | HFTD Tier 2 | Distribution | 2004-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003637 | 400067412 | High Sign | HFTD Tier 2 | Distribution | 2004-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003638 | 400082649 | High Sign | HFTD Tier 2 | Distribution | 2004-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003639 | 400083932 | High Sign | HFTD Tier 2 | Distribution | 2004-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003640 | 400116033 | Hardware/Framing | HFTD Tier 2 | Distribution | 2004-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003641 | 400118375 | High Sign | HFTD Tier 2 | Distribution | 2004-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003642 | 400122540 | Riser/Conduit | HFTD Tier 3 | Distribution | 2004-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003643 | 400125054 | High Sign | HFTD Tier 3 | Distribution | 2004-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003644 | 400179988 | High Sign | HFTD Tier 2 | Distribution | 2004-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003645 | 400183817 | High Sign | HFTD Tier 2 | Distribution | 2004-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003646 | 400185570 | Molding | HFTD Tier 2 | Distribution | 2004-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003647 | 400206858 | High Sign | HFTD Tier 3 | Distribution | 2004-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003648 | 400211751 | High Sign | HFTD Tier 2 | Distribution | 2004-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003649 | 400414419 | High Sign | HFTD Tier 2 | Distribution | 2004-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003650 | 400419807 | High Sign | HFTD Tier 3 | Distribution | 2004-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003651 | 400114567 | Molding | HFTD Tier 2 | Distribution | 2004-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003652 | 400123672 | High Sign | HFTD Tier 2 | Distribution | 2004-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003653 | 400231034 | Molding | HFTD Tier 2 | Distribution | 2004-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003654 | 400261296 | Molding | HFTD Tier 2 | Distribution | 2004-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003655 | 400455210 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003656 | 400985222 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003657 | 400114549 | Molding | HFTD Tier 2 | Distribution | 2004-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003658 | 400123642 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003659 | 400138203 | High Sign | HFTD Tier 3 | Distribution | 2004-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003660 | 400254831 | Molding | HFTD Tier 2 | Distribution | 2004-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003661 | 400361134 | Molding | HFTD Tier 2 | Distribution | 2004-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003662 | 400365693 | High Sign | HFTD Tier 2 | Distribution | 2004-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003663 | 400096441 | Molding | HFTD Tier 3 | Distribution | 2004-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003664 | 400145631 | Molding | HFTD Tier 3 | Distribution | 2004-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003665 | 400152304 | Guy | HFTD Tier 2 | Distribution | 2004-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003666 | 400162155 | Hardware/Framing | HFTD Tier 2 | Distribution | 2004-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003667 | 400195617 | Insulator | HFTD Tier 3 | Distribution | 2004-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003668 | 400226915 | High Sign | HFTD Tier 2 | Distribution | 2004-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003669 | 400231755 | High Sign | HFTD Tier 3 | Distribution | 2004-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003670 | 400460257 | Insulator | HFTD Tier 2 | Distribution | 2004-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003671 | 400461714 | Hardware/Framing | HFTD Tier 2 | Distribution | 2004-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003672 | 400047158 | High Sign | HFTD Tier 3 | Distribution | 2004-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003673 | 400057437 | High Sign | HFTD Tier 3 | Distribution | 2004-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003674 | 400113881 | High Sign | HFTD Tier 2 | Distribution | 2004-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003675 | 400121130 | Molding | HFTD Tier 3 | Distribution | 2004-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003676 | 400162814 | Guy | HFTD Tier 3 | Distribution | 2004-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003677 | 400166740 | Molding | HFTD Tier 3 | Distribution | 2004-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003678 | 400169332 | Molding | HFTD Tier 3 | Distribution | 2004-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003679 | 400174319 | Guy | HFTD Tier 3 | Distribution | 2004-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003680 | 400205053 | Guy | HFTD Tier 3 | Distribution | 2004-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003681 | 400210890 | High Sign | HFTD Tier 3 | Distribution | 2004-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003682 | 400213577 | Guy | HFTD Tier 3 | Distribution | 2004-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003683 | 400243905 | High Sign | HFTD Tier 2 | Distribution | 2004-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003684 | 400246900 | High Sign | HFTD Tier 2 | Distribution | 2004-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003685 | 400255415 | Molding | HFTD Tier 2 | Distribution | 2004-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003686 | 400288529 | High Sign | HFTD Tier 3 | Distribution | 2004-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003687 | 400472179 | High Sign | HFTD Tier 3 | Distribution | 2004-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003688 | 400123592 | High Sign | HFTD Tier 2 | Distribution | 2004-05-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003689 | 400177030 | High Sign | HFTD Tier 2 | Distribution | 2004-05-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003690 | 400182039 | High Sign | HFTD Tier 2 | Distribution | 2004-05-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003691 | 400182066 | Molding | HFTD Tier 3 | Distribution | 2004-05-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003692 | 400188560 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-05-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003693 | 400257334 | High Sign | HFTD Tier 2 | Distribution | 2004-05-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003694 | 400264094 | High Sign | HFTD Tier 2 | Distribution | 2004-05-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003695 | 400039502 | High Sign | HFTD Tier 2 | Distribution | 2004-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003696 | 400057329 | Molding | HFTD Tier 2 | Distribution | 2004-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003697 | 400144754 | Molding | HFTD Tier 3 | Distribution | 2004-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003698 | 400149962 | Molding | HFTD Tier 3 | Distribution | 2004-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003699 | 400152178 | High Sign | HFTD Tier 2 | Distribution | 2004-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003700 | 400164813 | Molding | HFTD Tier 2 | Distribution | 2004-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003701 | 400190994 | Molding | HFTD Tier 2 | Distribution | 2004-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003702 | 400197965 | High Sign | HFTD Tier 2 | Distribution | 2004-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003703 | 400280535 | High Sign | HFTD Tier 2 | Distribution | 2004-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003704 | 400281386 | High Sign | HFTD Tier 3 | Distribution | 2004-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003705 | 400285329 | High Sign | HFTD Tier 2 | Distribution | 2004-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003706 | 400289573 | High Sign | HFTD Tier 2 | Distribution | 2004-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003707 | 401460260 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003708 | 401461506 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003709 | 400064339 | Molding | HFTD Tier 3 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003710 | 400065180 | High Sign | HFTD Tier 2 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003711 | 400066371 | Molding | HFTD Tier 2 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003712 | 400067142 | High Sign | HFTD Tier 3 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003713 | 400067188 | High Sign | HFTD Tier 2 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003714 | 400070737 | Guy | HFTD Tier 2 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003715 | 400084126 | High Sign | HFTD Tier 2 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003716 | 400182198 | Molding | HFTD Tier 2 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003717 | 400204390 | High Sign | HFTD Tier 2 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003718 | 400214512 | Molding | HFTD Tier 3 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003719 | 400218504 | High Sign | HFTD Tier 2 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003720 | 400220373 | High Sign | HFTD Tier 3 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003721 | 400223159 | Molding | HFTD Tier 3 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003722 | 400306793 | Molding | HFTD Tier 3 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003723 | 400307648 | Molding | HFTD Tier 3 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003724 | 400309488 | High Sign | HFTD Tier 3 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003725 | 400312350 | Molding | HFTD Tier 3 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003726 | 400986311 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003727 | 401468648 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003728 | 400074933 | High Sign | HFTD Tier 3 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003729 | 400077078 | High Sign | HFTD Tier 3 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003730 | 400188811 | High Sign | HFTD Tier 2 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003731 | 400189874 | Molding | HFTD Tier 3 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003732 | 400216901 | Molding | HFTD Tier 3 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003733 | 400216926 | High Sign | HFTD Tier 3 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003734 | 400218603 | Molding | HFTD Tier 3 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003735 | 400219640 | Molding | HFTD Tier 3 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003736 | 400220349 | High Sign | HFTD Tier 2 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003737 | 400224349 | High Sign | HFTD Tier 3 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003738 | 400234890 | Guy | HFTD Tier 2 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003739 | 400314522 | Molding | HFTD Tier 3 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003740 | 400316326 | High Sign | HFTD Tier 2 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003741 | 400316352 | Molding | HFTD Tier 2 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003742 | 400320244 | High Sign | HFTD Tier 3 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003743 | 400320270 | Molding | HFTD Tier 3 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003744 | 400320669 | High Sign | HFTD Tier 2 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003745 | 400324694 | Molding | HFTD Tier 3 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003746 | 400343344 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003747 | 400437786 | Riser/Conduit | HFTD Tier 2 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003748 | 401462884 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003749 | 401464346 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003750 | 401466217 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003751 | 401468634 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003752 | 400110207 | High Sign | HFTD Tier 2 | Distribution | 2004-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003753 | 400116919 | Molding | HFTD Tier 2 | Distribution | 2004-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003754 | 400120049 | Molding | HFTD Tier 2 | Distribution | 2004-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003755 | 400121462 | High Sign | HFTD Tier 2 | Distribution | 2004-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003756 | 400236639 | Molding | HFTD Tier 2 | Distribution | 2004-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003757 | 400239452 | High Sign | HFTD Tier 2 | Distribution | 2004-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003758 | 400265200 | Molding | HFTD Tier 2 | Distribution | 2004-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003759 | 400272469 | Guy | HFTD Tier 2 | Distribution | 2004-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003760 | 400347679 | Guy | HFTD Tier 3 | Distribution | 2004-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003761 | 400351127 | High Sign | HFTD Tier 3 | Distribution | 2004-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003762 | 400378472 | High Sign | HFTD Tier 2 | Distribution | 2004-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003763 | 400386231 | High Sign | HFTD Tier 2 | Distribution | 2004-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003764 | 400434695 | High Sign | HFTD Tier 2 | Distribution | 2004-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003765 | 400135502 | High Sign | HFTD Tier 2 | Distribution | 2004-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003766 | 400153846 | Molding | HFTD Tier 2 | Distribution | 2004-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003767 | 400247392 | High Sign | HFTD Tier 2 | Distribution | 2004-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003768 | 400247416 | High Sign | HFTD Tier 2 | Distribution | 2004-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003769 | 400249488 | High Sign | HFTD Tier 2 | Distribution | 2004-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003770 | 400250274 | High Sign | HFTD Tier 2 | Distribution | 2004-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003771 | 400266041 | High Sign | HFTD Tier 2 | Distribution | 2004-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003772 | 400268836 | Molding | HFTD Tier 2 | Distribution | 2004-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003773 | 400279393 | High Sign | HFTD Tier 2 | Distribution | 2004-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003774 | 400282676 | High Sign | HFTD Tier 2 | Distribution | 2004-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003775 | 400284622 | High Sign | HFTD Tier 2 | Distribution | 2004-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003776 | 400288988 | High Sign | HFTD Tier 2 | Distribution | 2004-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003777 | 400389913 | High Sign | HFTD Tier 2 | Distribution | 2004-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003778 | 400401020 | High Sign | HFTD Tier 2 | Distribution | 2004-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003779 | 400402151 | Molding | HFTD Tier 2 | Distribution | 2004-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003780 | 400415224 | High Sign | HFTD Tier 2 | Distribution | 2004-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003781 | 400433571 | Insulator | HFTD Tier 2 | Distribution | 2004-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003782 | 400162118 | High Sign | HFTD Tier 2 | Distribution | 2004-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003783 | 400176947 | High Sign | HFTD Tier 2 | Distribution | 2004-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003784 | 400270921 | High Sign | HFTD Tier 2 | Distribution | 2004-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003785 | 400308805 | High Sign | HFTD Tier 2 | Distribution | 2004-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003786 | 400310264 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003787 | 400417647 | High Sign | HFTD Tier 2 | Distribution | 2004-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003788 | 400988570 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003789 | 401003616 | Guy | HFTD Tier 2 | Distribution | 2004-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003790 | 401467407 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003791 | 401468213 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003792 | 400020716 | High Sign | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003793 | 400040831 | High Sign | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003794 | 400044439 | High Sign | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003795 | 400171741 | High Sign | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003796 | 400175223 | Molding | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003797 | 400198648 | High Sign | HFTD Tier 3 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003798 | 400232171 | Molding | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003799 | 400246229 | High Sign | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003800 | 400257157 | Molding | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003801 | 400259242 | High Sign | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003802 | 400272925 | Molding | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003803 | 400283800 | High Sign | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003804 | 400284681 | Molding | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003805 | 400315266 | High Sign | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003806 | 400348701 | High Sign | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003807 | 400364521 | High Sign | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003808 | 400377143 | Molding | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003809 | 400384227 | High Sign | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003810 | 400411878 | High Sign | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003811 | 400423159 | High Sign | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003812 | 400423221 | High Sign | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003813 | 400494544 | High Sign | HFTD Tier 2 | Distribution | 2004-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003814 | 400190583 | High Sign | HFTD Tier 3 | Distribution | 2004-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003815 | 400199881 | High Sign | HFTD Tier 2 | Distribution | 2004-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003816 | 400205894 | High Sign | HFTD Tier 2 | Distribution | 2004-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003817 | 400257194 | Molding | HFTD Tier 2 | Distribution | 2004-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003818 | 400273745 | Molding | HFTD Tier 2 | Distribution | 2004-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003819 | 400338952 | High Sign | HFTD Tier 2 | Distribution | 2004-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003820 | 400350711 | High Sign | HFTD Tier 2 | Distribution | 2004-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003821 | 400354618 | Molding | HFTD Tier 2 | Distribution | 2004-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003822 | 400377198 | Molding | HFTD Tier 2 | Distribution | 2004-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003823 | 400988809 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003824 | 400036414 | High Sign | HFTD Tier 2 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003825 | 400039626 | High Sign | HFTD Tier 2 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003826 | 400040875 | High Sign | HFTD Tier 3 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003827 | 400043332 | High Sign | HFTD Tier 2 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003828 | 400206963 | High Sign | HFTD Tier 2 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003829 | 400217885 | High Sign | HFTD Tier 3 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003830 | 400226377 | Guy | HFTD Tier 3 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003831 | 400230429 | Guy | HFTD Tier 3 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003832 | 400259197 | High Sign | HFTD Tier 2 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003833 | 400259219 | High Sign | HFTD Tier 2 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003834 | 400333039 | Molding | HFTD Tier 2 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003835 | 400333087 | Molding | HFTD Tier 3 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003836 | 400335175 | Molding | HFTD Tier 2 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003837 | 400338039 | High Sign | HFTD Tier 3 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003838 | 400340914 | High Sign | HFTD Tier 3 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003839 | 400348403 | Guy | HFTD Tier 3 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003840 | 400355855 | Molding | HFTD Tier 2 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003841 | 400358706 | Guy | HFTD Tier 3 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003842 | 400364467 | High Sign | HFTD Tier 3 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003843 | 400367095 | High Sign | HFTD Tier 2 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003844 | 400405483 | High Sign | HFTD Tier 2 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003845 | 400410766 | High Sign | HFTD Tier 2 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003846 | 400423823 | Guy | HFTD Tier 3 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003847 | 400477710 | High Sign | HFTD Tier 3 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003848 | 400478375 | High Sign | HFTD Tier 2 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003849 | 400486106 | Guy | HFTD Tier 2 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003850 | 400490241 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003851 | 401470749 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003852 | 401472493 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003853 | 400019945 | Molding | HFTD Tier 2 | Distribution | 2004-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003854 | 400028330 | High Sign | HFTD Tier 2 | Distribution | 2004-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003855 | 400028568 | High Sign | HFTD Tier 2 | Distribution | 2004-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003856 | 400045261 | High Sign | HFTD Tier 2 | Distribution | 2004-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003857 | 400045285 | High Sign | HFTD Tier 2 | Distribution | 2004-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003858 | 400048645 | High Sign | HFTD Tier 2 | Distribution | 2004-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003859 | 400051099 | High Sign | HFTD Tier 2 | Distribution | 2004-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003860 | 400053094 | High Sign | HFTD Tier 2 | Distribution | 2004-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003861 | 400106640 | Molding | HFTD Tier 3 | Distribution | 2004-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003862 | 400197689 | Molding | HFTD Tier 2 | Distribution | 2004-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003863 | 400201844 | Molding | HFTD Tier 2 | Distribution | 2004-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003864 | 400251314 | High Sign | HFTD Tier 2 | Distribution | 2004-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003865 | 400366577 | High Sign | HFTD Tier 2 | Distribution | 2004-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003866 | 400370374 | Insulator | HFTD Tier 2 | Distribution | 2004-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003867 | 400381822 | Molding | HFTD Tier 2 | Distribution | 2004-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003868 | 400398452 | High Sign | HFTD Tier 2 | Distribution | 2004-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003869 | 400406308 | High Sign | HFTD Tier 2 | Distribution | 2004-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003870 | 400406521 | Molding | HFTD Tier 2 | Distribution | 2004-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003871 | 403047062 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003872 | 400085523 | High Sign | HFTD Tier 2 | Distribution | 2004-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003873 | 400168074 | Molding | HFTD Tier 3 | Distribution | 2004-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003874 | 400417617 | High Sign | HFTD Tier 2 | Distribution | 2004-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003875 | 401469903 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003876 | 401472113 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003877 | 400157432 | Molding | HFTD Tier 2 | Distribution | 2004-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003878 | 400058635 | High Sign | HFTD Tier 2 | Distribution | 2004-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003879 | 400066621 | High Sign | HFTD Tier 2 | Distribution | 2004-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003880 | 400080971 | High Sign | HFTD Tier 2 | Distribution | 2004-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003881 | 400086506 | Molding | HFTD Tier 2 | Distribution | 2004-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003882 | 400134984 | Molding | HFTD Tier 2 | Distribution | 2004-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003883 | 400136111 | Molding | HFTD Tier 2 | Distribution | 2004-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003884 | 400243320 | Molding | HFTD Tier 2 | Distribution | 2004-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003885 | 400246890 | Molding | HFTD Tier 2 | Distribution | 2004-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003886 | 400255351 | High Sign | HFTD Tier 2 | Distribution | 2004-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003887 | 400256843 | High Sign | HFTD Tier 2 | Distribution | 2004-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003888 | 400438258 | High Sign | HFTD Tier 3 | Distribution | 2004-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003889 | 400059752 | High Sign | HFTD Tier 2 | Distribution | 2004-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003890 | 400082177 | Molding | HFTD Tier 2 | Distribution | 2004-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003891 | 400086572 | Molding | HFTD Tier 2 | Distribution | 2004-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003892 | 400146058 | Molding | HFTD Tier 3 | Distribution | 2004-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003893 | 400149459 | Hardware/Framing | HFTD Tier 3 | Distribution | 2004-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003894 | 400159386 | High Sign | HFTD Tier 3 | Distribution | 2004-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003895 | 400162099 | Molding | HFTD Tier 3 | Distribution | 2004-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003896 | 400162875 | Molding | HFTD Tier 2 | Distribution | 2004-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003897 | 400171468 | Riser/Conduit | HFTD Tier 2 | Distribution | 2004-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003898 | 400250316 | High Sign | HFTD Tier 2 | Distribution | 2004-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003899 | 400345911 | Insulator | HFTD Tier 2 | Distribution | 2004-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003900 | 400350156 | Hardware/Framing | HFTD Tier 3 | Distribution | 2004-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003901 | 400353946 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003902 | 400451288 | High Sign | HFTD Tier 2 | Distribution | 2004-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003903 | 400451311 | High Sign | HFTD Tier 2 | Distribution | 2004-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003904 | 400454450 | High Sign | HFTD Tier 2 | Distribution | 2004-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003905 | 401472564 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003906 | 401474239 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003907 | 401477931 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003908 | 400162341 | High Sign | HFTD Tier 2 | Distribution | 2004-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003909 | 400189464 | Molding | HFTD Tier 2 | Distribution | 2004-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003910 | 400193573 | Molding | HFTD Tier 2 | Distribution | 2004-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003911 | 400222452 | High Sign | HFTD Tier 3 | Distribution | 2004-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003912 | 400248868 | High Sign | HFTD Tier 2 | Distribution | 2004-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003913 | 400358765 | Insulator | HFTD Tier 2 | Distribution | 2004-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003914 | 400361907 | High Sign | HFTD Tier 2 | Distribution | 2004-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003915 | 400393031 | Molding | HFTD Tier 3 | Distribution | 2004-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003916 | 400433236 | Guy | HFTD Tier 3 | Distribution | 2004-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003917 | 400460868 | Hardware/Framing | HFTD Tier 3 | Distribution | 2004-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003918 | 400483802 | Molding | HFTD Tier 2 | Distribution | 2004-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003919 | 400483825 | Molding | HFTD Tier 2 | Distribution | 2004-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003920 | 400484139 | Insulator | HFTD Tier 2 | Distribution | 2004-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003921 | 400023607 | Molding | HFTD Tier 3 | Distribution | 2004-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003922 | 400036458 | High Sign | HFTD Tier 3 | Distribution | 2004-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003923 | 400063452 | Molding | HFTD Tier 2 | Distribution | 2004-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003924 | 400088661 | High Sign | HFTD Tier 2 | Distribution | 2004-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003925 | 400188699 | Hardware/Framing | HFTD Tier 2 | Distribution | 2004-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003926 | 400256805 | Molding | HFTD Tier 2 | Distribution | 2004-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003927 | 400064707 | High Sign | HFTD Tier 3 | Distribution | 2004-06-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003928 | 400201893 | Hardware/Framing | HFTD Tier 2 | Distribution | 2004-06-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003929 | 400403927 | Molding | HFTD Tier 2 | Distribution | 2004-06-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003930 | 400406372 | Hardware/Framing | HFTD Tier 2 | Distribution | 2004-06-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003931 | 400116474 | High Sign | HFTD Tier 2 | Distribution | 2004-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003932 | 400126403 | Molding | HFTD Tier 3 | Distribution | 2004-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003933 | 400197925 | Molding | HFTD Tier 2 | Distribution | 2004-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003934 | 400230714 | Molding | HFTD Tier 2 | Distribution | 2004-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003935 | 400417310 | Molding | HFTD Tier 2 | Distribution | 2004-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003936 | 400417332 | High Sign | HFTD Tier 2 | Distribution | 2004-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003937 | 400420344 | High Sign | HFTD Tier 2 | Distribution | 2004-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003938 | 400108242 | Guy | HFTD Tier 3 | Distribution | 2004-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003939 | 400149816 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003940 | 400143555 | Guy | HFTD Tier 3 | Distribution | 2004-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003941 | 400291624 | High Sign | HFTD Tier 3 | Distribution | 2004-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003942 | 400428233 | Guy | HFTD Tier 3 | Distribution | 2004-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003943 | 400112101 | Guy | HFTD Tier 3 | Distribution | 2004-06-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003944 | 400420212 | High Sign | HFTD Tier 3 | Distribution | 2004-06-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003945 | 400060110 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003946 | 400082825 | Molding | HFTD Tier 3 | Distribution | 2004-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003947 | 400115238 | Molding | HFTD Tier 3 | Distribution | 2004-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003948 | 400315245 | Guy | HFTD Tier 3 | Distribution | 2004-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003949 | 403046971 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003950 | 400230928 | High Sign | HFTD Tier 3 | Distribution | 2004-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003951 | 400387455 | Molding | HFTD Tier 2 | Distribution | 2004-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003952 | 400453338 | Molding | HFTD Tier 3 | Distribution | 2004-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003953 | 400148369 | Molding | HFTD Tier 2 | Distribution | 2004-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003954 | 400193888 | Molding | HFTD Tier 3 | Distribution | 2004-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003955 | 400239898 | High Sign | HFTD Tier 3 | Distribution | 2004-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003956 | 400280118 | High Sign | HFTD Tier 2 | Distribution | 2004-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003957 | 400288239 | High Sign | HFTD Tier 2 | Distribution | 2004-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003958 | 400294153 | High Sign | HFTD Tier 2 | Distribution | 2004-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003959 | 400299839 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2004-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003960 | 400310414 | High Sign | HFTD Tier 3 | Distribution | 2004-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003961 | 400023866 | Guy | HFTD Tier 3 | Distribution | 2004-07-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003962 | 400275056 | Molding | HFTD Tier 3 | Distribution | 2004-07-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003963 | 400297995 | Molding | HFTD Tier 3 | Distribution | 2004-07-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003964 | 400300228 | High Sign | HFTD Tier 2 | Distribution | 2004-07-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003965 | 401492307 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-07-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003966 | 400293304 | High Sign | HFTD Tier 3 | Distribution | 2004-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003967 | 400326685 | Guy | HFTD Tier 3 | Distribution | 2004-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003968 | 400342254 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003969 | 400374719 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003970 | 400234594 | High Sign | HFTD Tier 3 | Distribution | 2004-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003971 | 400237618 | Molding | HFTD Tier 3 | Distribution | 2004-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003972 | 400350356 | Guy | HFTD Tier 3 | Distribution | 2004-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003973 | 400120071 | Guy | HFTD Tier 3 | Distribution | 2004-07-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003974 | 400206983 | High Sign | HFTD Tier 3 | Distribution | 2004-07-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003975 | 400213508 | Molding | HFTD Tier 3 | Distribution | 2004-07-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003976 | 400454596 | High Sign | HFTD Tier 3 | Distribution | 2004-07-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003977 | 400470808 | Molding | HFTD Tier 3 | Distribution | 2004-07-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003978 | 400140135 | Molding | HFTD Tier 3 | Distribution | 2004-07-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003979 | 400203393 | High Sign | HFTD Tier 2 | Distribution | 2004-07-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003980 | 400289667 | Molding | HFTD Tier 2 | Distribution | 2004-07-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003981 | 400101398 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003982 | 400376865 | Molding | HFTD Tier 2 | Distribution | 2004-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003983 | 400405374 | Molding | HFTD Tier 2 | Distribution | 2004-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003984 | 400421197 | Molding | HFTD Tier 2 | Distribution | 2004-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003985 | 400150391 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2004-07-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003986 | 400169034 | Molding | HFTD Tier 2 | Distribution | 2004-07-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003987 | 400171011 | Molding | HFTD Tier 2 | Distribution | 2004-07-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003988 | 400173365 | Molding | HFTD Tier 2 | Distribution | 2004-07-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003989 | 400198969 | Insulator | HFTD Tier 2 | Distribution | 2004-07-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003990 | 400343372 | Molding | HFTD Tier 2 | Distribution | 2004-07-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003991 | 400353258 | High Sign | HFTD Tier 2 | Distribution | 2004-07-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003992 | 400356031 | Molding | HFTD Tier 2 | Distribution | 2004-07-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003993 | 400405881 | Molding | HFTD Tier 2 | Distribution | 2004-07-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003994 | 400425236 | Molding | HFTD Tier 2 | Distribution | 2004-07-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003995 | 400434195 | High Sign | HFTD Tier 2 | Distribution | 2004-07-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003996 | 400057428 | High Sign | HFTD Tier 2 | Distribution | 2004-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003997 | 400190304 | High Sign | HFTD Tier 2 | Distribution | 2004-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003998 | 400347872 | Molding | HFTD Tier 2 | Distribution | 2004-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120003999 | 400363587 | High Sign | HFTD Tier 3 | Distribution | 2004-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004000 | 400405313 | High Sign | HFTD Tier 3 | Distribution | 2004-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004001 | 400420915 | High Sign | HFTD Tier 2 | Distribution | 2004-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004002 | 400449043 | High Sign | HFTD Tier 3 | Distribution | 2004-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004003 | 400458886 | High Sign | HFTD Tier 3 | Distribution | 2004-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004004 | 400463298 | High Sign | HFTD Tier 3 | Distribution | 2004-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004005 | 400487973 | High Sign | HFTD Tier 3 | Distribution | 2004-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004006 | 400358578 | High Sign | HFTD Tier 2 | Distribution | 2004-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004007 | 400369899 | High Sign | HFTD Tier 2 | Distribution | 2004-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004008 | 403047072 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004009 | 400203827 | High Sign | HFTD Tier 3 | Distribution | 2004-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004010 | 400210926 | Molding | HFTD Tier 2 | Distribution | 2004-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004011 | 400223761 | High Sign | HFTD Tier 3 | Distribution | 2004-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004012 | 400226426 | High Sign | HFTD Tier 3 | Distribution | 2004-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004013 | 400228193 | High Sign | HFTD Tier 2 | Distribution | 2004-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004014 | 400228206 | High Sign | HFTD Tier 3 | Distribution | 2004-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004015 | 400229839 | High Sign | HFTD Tier 3 | Distribution | 2004-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004016 | 400229852 | High Sign | HFTD Tier 3 | Distribution | 2004-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004017 | 400230584 | High Sign | HFTD Tier 3 | Distribution | 2004-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004018 | 400406390 | High Sign | HFTD Tier 3 | Distribution | 2004-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004019 | 400446657 | High Sign | HFTD Tier 3 | Distribution | 2004-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004020 | 400467317 | High Sign | HFTD Tier 3 | Distribution | 2004-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004021 | 400472682 | High Sign | HFTD Tier 3 | Distribution | 2004-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004022 | 400473696 | High Sign | HFTD Tier 3 | Distribution | 2004-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004023 | 400477485 | High Sign | HFTD Tier 3 | Distribution | 2004-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004024 | 400477495 | High Sign | HFTD Tier 3 | Distribution | 2004-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004025 | 400484773 | Guy | HFTD Tier 3 | Distribution | 2004-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004026 | 400487503 | High Sign | HFTD Tier 3 | Distribution | 2004-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004027 | 400488991 | High Sign | HFTD Tier 3 | Distribution | 2004-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004028 | 400489736 | High Sign | HFTD Tier 3 | Distribution | 2004-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004029 | 400053971 | High Sign | HFTD Tier 3 | Distribution | 2004-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004030 | 400087436 | Molding | HFTD Tier 3 | Distribution | 2004-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004031 | 400018771 | High Sign | HFTD Tier 2 | Distribution | 2004-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004032 | 400029263 | Molding | HFTD Tier 2 | Distribution | 2004-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004033 | 400055699 | High Sign | HFTD Tier 2 | Distribution | 2004-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004034 | 400060974 | Molding | HFTD Tier 3 | Distribution | 2004-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004035 | 400259227 | Molding | HFTD Tier 2 | Distribution | 2004-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004036 | 400274085 | High Sign | HFTD Tier 2 | Distribution | 2004-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004037 | 400464011 | Molding | HFTD Tier 2 | Distribution | 2004-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004038 | 400013888 | High Sign | HFTD Tier 3 | Distribution | 2004-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004039 | 400053181 | Molding | HFTD Tier 2 | Distribution | 2004-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004040 | 400053198 | High Sign | HFTD Tier 2 | Distribution | 2004-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004041 | 400054045 | High Sign | HFTD Tier 2 | Distribution | 2004-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004042 | 400058376 | High Sign | HFTD Tier 2 | Distribution | 2004-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004043 | 400060894 | Molding | HFTD Tier 3 | Distribution | 2004-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004044 | 400062995 | Molding | HFTD Tier 3 | Distribution | 2004-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004045 | 400076536 | Molding | HFTD Tier 2 | Distribution | 2004-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004046 | 400077920 | Hardware/Framing | HFTD Tier 3 | Distribution | 2004-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004047 | 400081389 | High Sign | HFTD Tier 3 | Distribution | 2004-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004048 | 400272424 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004049 | 400307266 | High Sign | HFTD Tier 3 | Distribution | 2004-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004050 | 400315336 | Molding | HFTD Tier 2 | Distribution | 2004-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004051 | 400319669 | Molding | HFTD Tier 3 | Distribution | 2004-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004052 | 400458564 | Molding | HFTD Tier 2 | Distribution | 2004-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004053 | 400483759 | Molding | HFTD Tier 3 | Distribution | 2004-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004054 | 400486785 | High Sign | HFTD Tier 2 | Distribution | 2004-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004055 | 400033212 | Molding | HFTD Tier 3 | Distribution | 2004-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004056 | 400052344 | Guy | HFTD Tier 3 | Distribution | 2004-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004057 | 400096169 | High Sign | HFTD Tier 3 | Distribution | 2004-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004058 | 400098740 | Molding | HFTD Tier 2 | Distribution | 2004-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004059 | 400100180 | High Sign | HFTD Tier 3 | Distribution | 2004-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004060 | 400111751 | Hardware/Framing | HFTD Tier 3 | Distribution | 2004-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004061 | 400145725 | High Sign | HFTD Tier 3 | Distribution | 2004-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004062 | 400301695 | High Sign | HFTD Tier 3 | Distribution | 2004-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004063 | 400349419 | Hardware/Framing | HFTD Tier 3 | Distribution | 2004-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004064 | 400351790 | High Sign | HFTD Tier 3 | Distribution | 2004-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004065 | 400482190 | High Sign | HFTD Tier 3 | Distribution | 2004-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004066 | 400018890 | Molding | HFTD Tier 2 | Distribution | 2004-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004067 | 400020280 | Guy | HFTD Tier 2 | Distribution | 2004-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004068 | 400023112 | Guy | HFTD Tier 2 | Distribution | 2004-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004069 | 400024440 | Molding | HFTD Tier 3 | Distribution | 2004-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004070 | 400026521 | High Sign | HFTD Tier 2 | Distribution | 2004-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004071 | 400113839 | Molding | HFTD Tier 3 | Distribution | 2004-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004072 | 400118717 | High Sign | HFTD Tier 3 | Distribution | 2004-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004073 | 400334351 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2004-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004074 | 400335422 | Molding | HFTD Tier 3 | Distribution | 2004-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004075 | 400340305 | Molding | HFTD Tier 2 | Distribution | 2004-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004076 | 400080253 | Molding | HFTD Tier 3 | Distribution | 2004-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004077 | 400141714 | Hardware/Framing | HFTD Tier 3 | Distribution | 2004-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004078 | 400404938 | High Sign | HFTD Tier 3 | Distribution | 2004-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004079 | 403047065 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004080 | 403047295 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004081 | 400197772 | Guy | HFTD Tier 3 | Distribution | 2004-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004082 | 400203850 | Molding | HFTD Tier 3 | Distribution | 2004-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004083 | 400207004 | Molding | HFTD Tier 3 | Distribution | 2004-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004084 | 400372439 | Insulator | HFTD Tier 2 | Distribution | 2004-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004085 | 400069056 | High Sign | HFTD Tier 3 | Distribution | 2004-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004086 | 400123646 | Molding | HFTD Tier 3 | Distribution | 2004-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004087 | 400173495 | High Sign | HFTD Tier 2 | Distribution | 2004-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004088 | 400248427 | High Sign | HFTD Tier 3 | Distribution | 2004-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004089 | 400259322 | Hardware/Framing | HFTD Tier 3 | Distribution | 2004-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004090 | 400265180 | High Sign | HFTD Tier 3 | Distribution | 2004-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004091 | 400079436 | High Sign | HFTD Tier 2 | Distribution | 2004-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004092 | 400170700 | Molding | HFTD Tier 2 | Distribution | 2004-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004093 | 400183481 | High Sign | HFTD Tier 2 | Distribution | 2004-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004094 | 400197747 | High Sign | HFTD Tier 3 | Distribution | 2004-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004095 | 400019897 | High Sign | HFTD Tier 3 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004096 | 400019907 | High Sign | HFTD Tier 3 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004097 | 400021618 | High Sign | HFTD Tier 3 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004098 | 400023110 | High Sign | HFTD Tier 3 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004099 | 400024246 | High Sign | HFTD Tier 3 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004100 | 400024253 | High Sign | HFTD Tier 3 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004101 | 400139120 | Molding | HFTD Tier 2 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004102 | 400163458 | Molding | HFTD Tier 3 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004103 | 400165263 | High Sign | HFTD Tier 3 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004104 | 400167913 | High Sign | HFTD Tier 3 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004105 | 400167936 | High Sign | HFTD Tier 3 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004106 | 400169918 | High Sign | HFTD Tier 3 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004107 | 400231970 | High Sign | HFTD Tier 3 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004108 | 400231986 | High Sign | HFTD Tier 3 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004109 | 400233824 | High Sign | HFTD Tier 3 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004110 | 400235409 | High Sign | HFTD Tier 3 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004111 | 400235434 | High Sign | HFTD Tier 3 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004112 | 400238016 | High Sign | HFTD Tier 3 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004113 | 400239659 | High Sign | HFTD Tier 3 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004114 | 400239683 | High Sign | HFTD Tier 3 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004115 | 400240889 | High Sign | HFTD Tier 3 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004116 | 401524151 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004117 | 400146486 | Guy | HFTD Tier 3 | Distribution | 2004-08-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004118 | 400148252 | Guy | HFTD Tier 3 | Distribution | 2004-08-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004119 | 400220972 | Molding | HFTD Tier 3 | Distribution | 2004-08-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004120 | 400222872 | Guy | HFTD Tier 2 | Distribution | 2004-08-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004121 | 400222887 | Guy | HFTD Tier 3 | Distribution | 2004-08-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004122 | 400222900 | High Sign | HFTD Tier 2 | Distribution | 2004-08-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004123 | 400026308 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004124 | 400026329 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004125 | 400026339 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004126 | 400032162 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004127 | 400032759 | Guy | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004128 | 400035000 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004129 | 400035016 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004130 | 400182389 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004131 | 400184753 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004132 | 400184767 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004133 | 400186901 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004134 | 400186933 | Guy | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004135 | 400189311 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004136 | 400247706 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004137 | 400247718 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004138 | 400249565 | Molding | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004139 | 400250354 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004140 | 400250375 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004141 | 400251796 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004142 | 400253726 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004143 | 400253750 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004144 | 400253967 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004145 | 400255286 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004146 | 400256475 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004147 | 400257922 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004148 | 400259663 | High Sign | HFTD Tier 3 | Distribution | 2004-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004149 | 400162678 | Molding | HFTD Tier 3 | Distribution | 2004-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004150 | 400221895 | Molding | HFTD Tier 2 | Distribution | 2004-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004151 | 400319439 | High Sign | HFTD Tier 2 | Distribution | 2004-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004152 | 400380404 | Molding | HFTD Tier 3 | Distribution | 2004-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004153 | 400388379 | Molding | HFTD Tier 3 | Distribution | 2004-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004154 | 403048843 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004155 | 400096674 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004156 | 400096732 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004157 | 400096746 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004158 | 400099626 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004159 | 400099673 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004160 | 400099689 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004161 | 400100925 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004162 | 400100970 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004163 | 400100996 | Guy | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004164 | 400104004 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004165 | 400104048 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004166 | 400104071 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004167 | 400247518 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004168 | 400247552 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004169 | 400247566 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004170 | 400250183 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004171 | 400250231 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004172 | 400251612 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004173 | 400251633 | Guy | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004174 | 400253760 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004175 | 400253799 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004176 | 400298019 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004177 | 400305840 | Molding | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004178 | 400306086 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004179 | 400306115 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004180 | 400308685 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004181 | 400309613 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004182 | 400309629 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004183 | 400310567 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004184 | 400311582 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004185 | 400311715 | Guy | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004186 | 400311768 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004187 | 400312641 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004188 | 400312682 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004189 | 400313038 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004190 | 400313943 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004191 | 400313970 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004192 | 400315324 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004193 | 400315351 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004194 | 400315392 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004195 | 400318857 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004196 | 400318905 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004197 | 400318919 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004198 | 400379223 | Molding | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004199 | 401737122 | High Sign | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004200 | 401737420 | Insulator | HFTD Tier 3 | Distribution | 2004-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004201 | 400388273 | Molding | HFTD Tier 2 | Distribution | 2004-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004202 | 400353174 | Molding | HFTD Tier 2 | Distribution | 2004-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004203 | 400355409 | Molding | HFTD Tier 2 | Distribution | 2004-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004204 | 400343574 | High Sign | HFTD Tier 3 | Distribution | 2004-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004205 | 400347128 | Riser/Conduit | HFTD Tier 2 | Distribution | 2004-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004206 | 400305870 | High Sign | HFTD Tier 3 | Distribution | 2004-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004207 | 400312353 | High Sign | HFTD Tier 3 | Distribution | 2004-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004208 | 400379632 | High Sign | HFTD Tier 3 | Distribution | 2004-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004209 | 400380304 | Molding | HFTD Tier 3 | Distribution | 2004-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004210 | 400380332 | Molding | HFTD Tier 2 | Distribution | 2004-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004211 | 400382765 | Molding | HFTD Tier 3 | Distribution | 2004-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004212 | 400390506 | Molding | HFTD Tier 3 | Distribution | 2004-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004213 | 400364541 | Guy | HFTD Tier 3 | Distribution | 2004-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004214 | 400416073 | Molding | HFTD Tier 3 | Distribution | 2004-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004215 | 400013010 | Molding | HFTD Tier 3 | Distribution | 2004-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004216 | 400034268 | High Sign | HFTD Tier 3 | Distribution | 2004-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004217 | 400051476 | Molding | HFTD Tier 3 | Distribution | 2004-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004218 | 400059019 | High Sign | HFTD Tier 3 | Distribution | 2004-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004219 | 400059088 | High Sign | HFTD Tier 3 | Distribution | 2004-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004220 | 400385789 | High Sign | HFTD Tier 2 | Distribution | 2004-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004221 | 400428357 | High Sign | HFTD Tier 3 | Distribution | 2004-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004222 | 400041483 | High Sign | HFTD Tier 3 | Distribution | 2004-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004223 | 400315180 | Molding | HFTD Tier 2 | Distribution | 2004-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004224 | 400384992 | High Sign | HFTD Tier 3 | Distribution | 2004-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004225 | 400029117 | High Sign | HFTD Tier 3 | Distribution | 2004-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004226 | 400066433 | Molding | HFTD Tier 2 | Distribution | 2004-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004227 | 400201976 | High Sign | HFTD Tier 2 | Distribution | 2004-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004228 | 400270285 | Molding | HFTD Tier 3 | Distribution | 2004-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004229 | 400303829 | High Sign | HFTD Tier 2 | Distribution | 2004-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004230 | 400450122 | Molding | HFTD Tier 3 | Distribution | 2004-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004231 | 400016288 | High Sign | HFTD Tier 3 | Distribution | 2004-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004232 | 400016624 | High Sign | HFTD Tier 3 | Distribution | 2004-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004233 | 400017673 | High Sign | HFTD Tier 3 | Distribution | 2004-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004234 | 400018655 | High Sign | HFTD Tier 3 | Distribution | 2004-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004235 | 400033627 | High Sign | HFTD Tier 3 | Distribution | 2004-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004236 | 400036094 | Molding | HFTD Tier 3 | Distribution | 2004-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004237 | 400074891 | High Sign | HFTD Tier 2 | Distribution | 2004-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004238 | 400271769 | High Sign | HFTD Tier 3 | Distribution | 2004-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004239 | 400274229 | High Sign | HFTD Tier 3 | Distribution | 2004-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004240 | 400275532 | Molding | HFTD Tier 3 | Distribution | 2004-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004241 | 400277232 | Molding | HFTD Tier 3 | Distribution | 2004-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004242 | 400454263 | Molding | HFTD Tier 3 | Distribution | 2004-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004243 | 400457395 | High Sign | HFTD Tier 3 | Distribution | 2004-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004244 | 400457472 | High Sign | HFTD Tier 3 | Distribution | 2004-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004245 | 400040370 | High Sign | HFTD Tier 3 | Distribution | 2004-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004246 | 400042405 | High Sign | HFTD Tier 2 | Distribution | 2004-08-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004247 | 400473436 | Molding | HFTD Tier 3 | Distribution | 2004-08-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004248 | 400015734 | Riser/Conduit | HFTD Tier 3 | Distribution | 2004-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004249 | 400020862 | High Sign | HFTD Tier 3 | Distribution | 2004-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004250 | 400061255 | High Sign | HFTD Tier 3 | Distribution | 2004-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004251 | 400108475 | High Sign | HFTD Tier 2 | Distribution | 2004-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004252 | 400034354 | High Sign | HFTD Tier 3 | Distribution | 2004-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004253 | 400078933 | Guy | HFTD Tier 2 | Distribution | 2004-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004254 | 400098203 | Molding | HFTD Tier 3 | Distribution | 2004-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004255 | 400120996 | High Sign | HFTD Tier 3 | Distribution | 2004-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004256 | 400213628 | High Sign | HFTD Tier 2 | Distribution | 2004-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004257 | 400340213 | Molding | HFTD Tier 2 | Distribution | 2004-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004258 | 400343529 | High Sign | HFTD Tier 3 | Distribution | 2004-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004259 | 400346672 | Molding | HFTD Tier 3 | Distribution | 2004-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004260 | 400373668 | High Sign | HFTD Tier 3 | Distribution | 2004-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004261 | 400414105 | Hardware/Framing | HFTD Tier 2 | Distribution | 2004-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004262 | 400114045 | Riser/Conduit | HFTD Tier 3 | Distribution | 2004-08-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004263 | 400125357 | Hardware/Framing | HFTD Tier 3 | Distribution | 2004-08-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004264 | 401555293 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-08-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004265 | 400114511 | Guy | HFTD Tier 2 | Distribution | 2004-08-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004266 | 400147435 | High Sign | HFTD Tier 2 | Distribution | 2004-08-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004267 | 400440297 | Riser/Conduit | HFTD Tier 3 | Distribution | 2004-08-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004268 | 400141949 | High Sign | HFTD Tier 2 | Distribution | 2004-08-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004269 | 400227453 | Guy | HFTD Tier 3 | Distribution | 2004-08-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004270 | 400142643 | Molding | HFTD Tier 3 | Distribution | 2004-08-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004271 | 400156702 | High Sign | HFTD Tier 2 | Distribution | 2004-08-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004272 | 400162450 | Molding | HFTD Tier 2 | Distribution | 2004-08-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004273 | 400185052 | Molding | HFTD Tier 2 | Distribution | 2004-08-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004274 | 400231350 | High Sign | HFTD Tier 2 | Distribution | 2004-08-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004275 | 400413314 | High Sign | HFTD Tier 2 | Distribution | 2004-08-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004276 | 400432853 | High Sign | HFTD Tier 2 | Distribution | 2004-08-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004277 | 403047573 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-08-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004278 | 400043047 | High Sign | HFTD Tier 2 | Distribution | 2004-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004279 | 400046527 | High Sign | HFTD Tier 2 | Distribution | 2004-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004280 | 400231295 | Hardware/Framing | HFTD Tier 2 | Distribution | 2004-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004281 | 400257242 | Molding | HFTD Tier 2 | Distribution | 2004-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004282 | 400046599 | Guy | HFTD Tier 2 | Distribution | 2004-09-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004283 | 400047406 | Molding | HFTD Tier 2 | Distribution | 2004-09-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004284 | 401005578 | High Sign | HFTD Tier 3 | Distribution | 2004-09-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004285 | 400023604 | High Sign | HFTD Tier 3 | Distribution | 2004-09-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004286 | 400245664 | Molding | HFTD Tier 3 | Distribution | 2004-09-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004287 | 403046022 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-09-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004288 | 400026149 | High Sign | HFTD Tier 3 | Distribution | 2004-09-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004289 | 400236427 | High Sign | HFTD Tier 3 | Distribution | 2004-09-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004290 | 400074563 | Molding | HFTD Tier 2 | Distribution | 2004-09-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004291 | 400252963 | High Sign | HFTD Tier 3 | Distribution | 2004-09-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004292 | 400261091 | High Sign | HFTD Tier 3 | Distribution | 2004-09-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004293 | 400125881 | High Sign | HFTD Tier 3 | Distribution | 2004-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004294 | 400127998 | High Sign | HFTD Tier 3 | Distribution | 2004-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004295 | 400308351 | Riser/Conduit | HFTD Tier 3 | Distribution | 2004-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004296 | 400312717 | High Sign | HFTD Tier 3 | Distribution | 2004-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004297 | 400336698 | Molding | HFTD Tier 3 | Distribution | 2004-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004298 | 400340960 | Molding | HFTD Tier 3 | Distribution | 2004-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004299 | 400326438 | High Sign | HFTD Tier 3 | Distribution | 2004-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004300 | 400326466 | High Sign | HFTD Tier 2 | Distribution | 2004-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004301 | 400334118 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004302 | 400337396 | High Sign | HFTD Tier 3 | Distribution | 2004-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004303 | 400337423 | High Sign | HFTD Tier 2 | Distribution | 2004-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004304 | 400337478 | High Sign | HFTD Tier 2 | Distribution | 2004-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004305 | 400132278 | Guy | HFTD Tier 3 | Distribution | 2004-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004306 | 400135618 | High Sign | HFTD Tier 3 | Distribution | 2004-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004307 | 400189193 | High Sign | HFTD Tier 2 | Distribution | 2004-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004308 | 400394630 | Molding | HFTD Tier 2 | Distribution | 2004-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004309 | 400144662 | Guy | HFTD Tier 2 | Distribution | 2004-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004310 | 400151973 | Molding | HFTD Tier 3 | Distribution | 2004-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004311 | 400247969 | High Sign | HFTD Tier 3 | Distribution | 2004-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004312 | 400309517 | Molding | HFTD Tier 2 | Distribution | 2004-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004313 | 400333463 | Molding | HFTD Tier 3 | Distribution | 2004-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004314 | 400335694 | Insulator | HFTD Tier 2 | Distribution | 2004-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004315 | 400342284 | High Sign | HFTD Tier 2 | Distribution | 2004-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004316 | 400345693 | Molding | HFTD Tier 2 | Distribution | 2004-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004317 | 400459015 | Molding | HFTD Tier 3 | Distribution | 2004-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004318 | 400188257 | High Sign | HFTD Tier 2 | Distribution | 2004-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004319 | 400333102 | High Sign | HFTD Tier 2 | Distribution | 2004-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004320 | 400354167 | High Sign | HFTD Tier 2 | Distribution | 2004-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004321 | 400366594 | Molding | HFTD Tier 3 | Distribution | 2004-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004322 | 400387265 | Molding | HFTD Tier 2 | Distribution | 2004-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004323 | 401581612 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004324 | 400183698 | Molding | HFTD Tier 2 | Distribution | 2004-09-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004325 | 400353800 | High Sign | HFTD Tier 3 | Distribution | 2004-09-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004326 | 400364164 | Molding | HFTD Tier 3 | Distribution | 2004-09-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004327 | 400373194 | High Sign | HFTD Tier 3 | Distribution | 2004-09-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004328 | 400388991 | Molding | HFTD Tier 3 | Distribution | 2004-09-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004329 | 400261350 | Molding | HFTD Tier 3 | Distribution | 2004-09-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004330 | 400108664 | Ground | HFTD Tier 3 | Distribution | 2004-09-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004331 | 400153221 | Guy | HFTD Tier 3 | Distribution | 2004-09-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004332 | 400162537 | Molding | HFTD Tier 3 | Distribution | 2004-09-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004333 | 400227617 | Guy | HFTD Tier 3 | Distribution | 2004-09-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004334 | 400415440 | Molding | HFTD Tier 3 | Distribution | 2004-09-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004335 | 400425464 | High Sign | HFTD Tier 3 | Distribution | 2004-09-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004336 | 400439752 | Molding | HFTD Tier 3 | Distribution | 2004-09-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004337 | 400015028 | Molding | HFTD Tier 3 | Distribution | 2004-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004338 | 400022326 | High Sign | HFTD Tier 3 | Distribution | 2004-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004339 | 400041232 | High Sign | HFTD Tier 3 | Distribution | 2004-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004340 | 400106618 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004341 | 400116564 | High Sign | HFTD Tier 3 | Distribution | 2004-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004342 | 400153928 | Molding | HFTD Tier 3 | Distribution | 2004-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004343 | 400301131 | High Sign | HFTD Tier 3 | Distribution | 2004-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004344 | 400311946 | High Sign | HFTD Tier 3 | Distribution | 2004-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004345 | 400450381 | High Sign | HFTD Tier 3 | Distribution | 2004-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004346 | 400467422 | Molding | HFTD Tier 3 | Distribution | 2004-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004347 | 400012970 | High Sign | HFTD Tier 3 | Distribution | 2004-09-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004348 | 400029776 | Molding | HFTD Tier 3 | Distribution | 2004-09-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004349 | 400114197 | Molding | HFTD Tier 3 | Distribution | 2004-09-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004350 | 400150958 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-09-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004351 | 400258864 | High Sign | HFTD Tier 3 | Distribution | 2004-09-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004352 | 400258888 | High Sign | HFTD Tier 3 | Distribution | 2004-09-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004353 | 400261526 | High Sign | HFTD Tier 3 | Distribution | 2004-09-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004354 | 400308131 | High Sign | HFTD Tier 3 | Distribution | 2004-09-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004355 | 400442447 | Molding | HFTD Tier 3 | Distribution | 2004-09-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004356 | 400444973 | High Sign | HFTD Tier 3 | Distribution | 2004-09-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004357 | 400447383 | High Sign | HFTD Tier 3 | Distribution | 2004-09-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004358 | 400461658 | High Sign | HFTD Tier 3 | Distribution | 2004-09-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004359 | 400465119 | High Sign | HFTD Tier 3 | Distribution | 2004-09-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004360 | 400472554 | High Sign | HFTD Tier 3 | Distribution | 2004-09-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004361 | 400016417 | High Sign | HFTD Tier 3 | Distribution | 2004-09-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004362 | 400018477 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2004-09-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004363 | 400048973 | High Sign | HFTD Tier 3 | Distribution | 2004-09-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004364 | 400052745 | High Sign | HFTD Tier 3 | Distribution | 2004-09-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004365 | 400314338 | High Sign | HFTD Tier 3 | Distribution | 2004-09-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004366 | 400036965 | Guy | HFTD Tier 3 | Distribution | 2004-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004367 | 400038489 | High Sign | HFTD Tier 3 | Distribution | 2004-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004368 | 400065314 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004369 | 400071949 | High Sign | HFTD Tier 3 | Distribution | 2004-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004370 | 400075276 | High Sign | HFTD Tier 3 | Distribution | 2004-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004371 | 400247770 | High Sign | HFTD Tier 3 | Distribution | 2004-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004372 | 400250128 | Molding | HFTD Tier 3 | Distribution | 2004-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004373 | 400251722 | Molding | HFTD Tier 3 | Distribution | 2004-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004374 | 400260552 | Molding | HFTD Tier 3 | Distribution | 2004-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004375 | 400825804 | Riser/Conduit | HFTD Tier 3 | Distribution | 2004-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004376 | 400894851 | High Sign | HFTD Tier 3 | Distribution | 2004-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004377 | 400066573 | High Sign | HFTD Tier 3 | Distribution | 2004-09-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004378 | 400077267 | Molding | HFTD Tier 3 | Distribution | 2004-09-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004379 | 400109748 | Molding | HFTD Tier 3 | Distribution | 2004-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004380 | 400116321 | High Sign | HFTD Tier 3 | Distribution | 2004-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004381 | 400160686 | High Sign | HFTD Tier 3 | Distribution | 2004-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004382 | 400165778 | High Sign | HFTD Tier 2 | Distribution | 2004-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004383 | 400411071 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004384 | 400420805 | High Sign | HFTD Tier 2 | Distribution | 2004-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004385 | 400439680 | High Sign | HFTD Tier 3 | Distribution | 2004-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004386 | 400024220 | Crossarm | HFTD Tier 3 | Distribution | 2004-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004387 | 400083694 | Guy | HFTD Tier 3 | Distribution | 2004-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004388 | 400114267 | Molding | HFTD Tier 3 | Distribution | 2004-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004389 | 400158001 | Molding | HFTD Tier 2 | Distribution | 2004-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004390 | 400254339 | Molding | HFTD Tier 3 | Distribution | 2004-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004391 | 400384376 | High Sign | HFTD Tier 3 | Distribution | 2004-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004392 | 400465696 | Molding | HFTD Tier 3 | Distribution | 2004-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004393 | 400124162 | Molding | HFTD Tier 2 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004394 | 400134442 | High Sign | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004395 | 400137603 | High Sign | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004396 | 400139572 | High Sign | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004397 | 400145855 | High Sign | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004398 | 400167325 | Molding | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004399 | 400172599 | Molding | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004400 | 400174098 | High Sign | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004401 | 400180733 | Molding | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004402 | 400185224 | High Sign | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004403 | 400185288 | High Sign | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004404 | 400186971 | Molding | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004405 | 400237871 | High Sign | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004406 | 400254974 | Molding | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004407 | 400267374 | Molding | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004408 | 400415662 | High Sign | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004409 | 400425717 | Molding | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004410 | 400437744 | High Sign | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004411 | 400439627 | Molding | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004412 | 400441822 | High Sign | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004413 | 400441975 | High Sign | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004414 | 400465709 | High Sign | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004415 | 400472698 | High Sign | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004416 | 401006452 | High Sign | HFTD Tier 3 | Distribution | 2004-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004417 | 400020804 | Insulator | HFTD Tier 2 | Distribution | 2004-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004418 | 400026540 | Insulator | HFTD Tier 3 | Distribution | 2004-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004419 | 400030613 | Molding | HFTD Tier 3 | Distribution | 2004-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004420 | 400192839 | High Sign | HFTD Tier 2 | Distribution | 2004-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004421 | 400197632 | Molding | HFTD Tier 2 | Distribution | 2004-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004422 | 400212541 | Molding | HFTD Tier 3 | Distribution | 2004-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004423 | 400232739 | Molding | HFTD Tier 3 | Distribution | 2004-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004424 | 400237047 | Molding | HFTD Tier 2 | Distribution | 2004-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004425 | 400247558 | High Sign | HFTD Tier 3 | Distribution | 2004-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004426 | 400256612 | Molding | HFTD Tier 3 | Distribution | 2004-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004427 | 400257099 | High Sign | HFTD Tier 3 | Distribution | 2004-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004428 | 400260783 | Molding | HFTD Tier 3 | Distribution | 2004-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004429 | 400265924 | Hardware/Framing | HFTD Tier 3 | Distribution | 2004-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004430 | 400268395 | Molding | HFTD Tier 3 | Distribution | 2004-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004431 | 400274314 | Ground | HFTD Tier 3 | Distribution | 2004-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004432 | 400309072 | High Sign | HFTD Tier 3 | Distribution | 2004-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004433 | 400365202 | Molding | HFTD Tier 3 | Distribution | 2004-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004434 | 400458273 | Crossarm | HFTD Tier 3 | Distribution | 2004-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004435 | 400210736 | Molding | HFTD Tier 3 | Distribution | 2004-10-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004436 | 400323418 | Molding | HFTD Tier 3 | Distribution | 2004-10-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004437 | 400201772 | Molding | HFTD Tier 3 | Distribution | 2004-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004438 | 400251333 | High Sign | HFTD Tier 3 | Distribution | 2004-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004439 | 400024252 | High Sign | HFTD Tier 3 | Distribution | 2004-10-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004440 | 400234291 | Riser/Conduit | HFTD Tier 2 | Distribution | 2004-10-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004441 | 400239605 | Molding | HFTD Tier 3 | Distribution | 2004-10-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004442 | 400241075 | Hardware/Framing | HFTD Tier 3 | Distribution | 2004-10-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004443 | 400250517 | High Sign | HFTD Tier 3 | Distribution | 2004-10-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004444 | 400250542 | Molding | HFTD Tier 3 | Distribution | 2004-10-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004445 | 400343866 | Molding | HFTD Tier 3 | Distribution | 2004-10-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004446 | 403047523 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-10-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004447 | 400119786 | High Sign | HFTD Tier 2 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004448 | 400130891 | High Sign | HFTD Tier 2 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004449 | 400134231 | High Sign | HFTD Tier 3 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004450 | 400138115 | High Sign | HFTD Tier 2 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004451 | 400138193 | High Sign | HFTD Tier 3 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004452 | 400159703 | High Sign | HFTD Tier 3 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004453 | 400159841 | Molding | HFTD Tier 3 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004454 | 400164403 | High Sign | HFTD Tier 3 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004455 | 400166521 | Molding | HFTD Tier 3 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004456 | 400182694 | High Sign | HFTD Tier 2 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004457 | 400185260 | High Sign | HFTD Tier 2 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004458 | 400245290 | Molding | HFTD Tier 3 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004459 | 400268951 | High Sign | HFTD Tier 2 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004460 | 400276585 | High Sign | HFTD Tier 2 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004461 | 400279224 | High Sign | HFTD Tier 2 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004462 | 400280206 | High Sign | HFTD Tier 2 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004463 | 400305447 | Molding | HFTD Tier 3 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004464 | 400309933 | High Sign | HFTD Tier 3 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004465 | 400316895 | Guy | HFTD Tier 3 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004466 | 400318201 | High Sign | HFTD Tier 2 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004467 | 400320716 | High Sign | HFTD Tier 2 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004468 | 400329953 | Molding | HFTD Tier 2 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004469 | 400333220 | High Sign | HFTD Tier 2 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004470 | 400342986 | High Sign | HFTD Tier 3 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004471 | 400344521 | High Sign | HFTD Tier 2 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004472 | 400348319 | Molding | HFTD Tier 2 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004473 | 400351075 | High Sign | HFTD Tier 2 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004474 | 400363068 | High Sign | HFTD Tier 3 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004475 | 400367786 | High Sign | HFTD Tier 3 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004476 | 400386636 | High Sign | HFTD Tier 2 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004477 | 400389112 | High Sign | HFTD Tier 2 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004478 | 400390677 | Ground | HFTD Tier 3 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004479 | 400393829 | High Sign | HFTD Tier 3 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004480 | 400397556 | High Sign | HFTD Tier 3 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004481 | 400414441 | High Sign | HFTD Tier 2 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004482 | 400414510 | High Sign | HFTD Tier 2 | Distribution | 2004-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004483 | 400145612 | High Sign | HFTD Tier 3 | Distribution | 2004-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004484 | 400146929 | High Sign | HFTD Tier 3 | Distribution | 2004-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004485 | 400239891 | Molding | HFTD Tier 3 | Distribution | 2004-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004486 | 400259126 | Molding | HFTD Tier 3 | Distribution | 2004-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004487 | 400260649 | High Sign | HFTD Tier 3 | Distribution | 2004-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004488 | 400272758 | High Sign | HFTD Tier 3 | Distribution | 2004-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004489 | 400273886 | Molding | HFTD Tier 3 | Distribution | 2004-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004490 | 400280281 | High Sign | HFTD Tier 3 | Distribution | 2004-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004491 | 400280306 | High Sign | HFTD Tier 3 | Distribution | 2004-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004492 | 400281539 | Molding | HFTD Tier 3 | Distribution | 2004-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004493 | 400285260 | Hardware/Framing | HFTD Tier 3 | Distribution | 2004-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004494 | 400290234 | Insulator | HFTD Tier 3 | Distribution | 2004-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004495 | 400334286 | High Sign | HFTD Tier 2 | Distribution | 2004-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004496 | 400337627 | High Sign | HFTD Tier 2 | Distribution | 2004-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004497 | 400367991 | High Sign | HFTD Tier 3 | Distribution | 2004-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004498 | 400389086 | High Sign | HFTD Tier 2 | Distribution | 2004-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004499 | 400409768 | High Sign | HFTD Tier 2 | Distribution | 2004-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004500 | 403047433 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2004-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004501 | 400126475 | High Sign | HFTD Tier 2 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004502 | 400135444 | High Sign | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004503 | 400137241 | Molding | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004504 | 400137295 | High Sign | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004505 | 400138089 | High Sign | HFTD Tier 2 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004506 | 400139297 | Molding | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004507 | 400141098 | High Sign | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004508 | 400145552 | Molding | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004509 | 400151448 | High Sign | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004510 | 400235323 | High Sign | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004511 | 400238751 | Molding | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004512 | 400240060 | Molding | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004513 | 400264090 | Molding | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004514 | 400277063 | Molding | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004515 | 400281453 | High Sign | HFTD Tier 2 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004516 | 400282422 | High Sign | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004517 | 400283775 | High Sign | HFTD Tier 2 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004518 | 400284773 | High Sign | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004519 | 400285149 | High Sign | HFTD Tier 2 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004520 | 400286204 | Molding | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004521 | 400287642 | High Sign | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004522 | 400287666 | High Sign | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004523 | 400290178 | High Sign | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004524 | 400291953 | High Sign | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004525 | 400295911 | High Sign | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004526 | 400341194 | High Sign | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004527 | 400341239 | High Sign | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004528 | 400343794 | High Sign | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004529 | 400348303 | High Sign | HFTD Tier 2 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004530 | 400361799 | Molding | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004531 | 400362873 | High Sign | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004532 | 400365314 | High Sign | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004533 | 400367885 | High Sign | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004534 | 400367938 | High Sign | HFTD Tier 3 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004535 | 400388815 | Molding | HFTD Tier 2 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004536 | 400401910 | High Sign | HFTD Tier 2 | Distribution | 2004-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004537 | 400152623 | High Sign | HFTD Tier 2 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004538 | 400152650 | High Sign | HFTD Tier 2 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004539 | 400154982 | High Sign | HFTD Tier 2 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004540 | 400155202 | High Sign | HFTD Tier 2 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004541 | 400157325 | High Sign | HFTD Tier 2 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004542 | 400179592 | High Sign | HFTD Tier 2 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004543 | 400295984 | High Sign | HFTD Tier 2 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004544 | 400296538 | High Sign | HFTD Tier 2 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004545 | 400326185 | Molding | HFTD Tier 2 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004546 | 400344386 | High Sign | HFTD Tier 2 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004547 | 400347864 | High Sign | HFTD Tier 2 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004548 | 400350591 | High Sign | HFTD Tier 2 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004549 | 400354693 | High Sign | HFTD Tier 3 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004550 | 400357283 | Hardware/Framing | HFTD Tier 3 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004551 | 400370250 | High Sign | HFTD Tier 3 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004552 | 400372138 | High Sign | HFTD Tier 2 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004553 | 400372944 | High Sign | HFTD Tier 2 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004554 | 400377139 | High Sign | HFTD Tier 2 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004555 | 400378075 | High Sign | HFTD Tier 2 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004556 | 400378811 | High Sign | HFTD Tier 2 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004557 | 400378946 | High Sign | HFTD Tier 2 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004558 | 400378971 | High Sign | HFTD Tier 2 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004559 | 400391720 | Molding | HFTD Tier 3 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004560 | 400394084 | High Sign | HFTD Tier 3 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004561 | 400394112 | High Sign | HFTD Tier 3 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004562 | 400396923 | High Sign | HFTD Tier 3 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004563 | 400396975 | Molding | HFTD Tier 3 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004564 | 400401503 | High Sign | HFTD Tier 2 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004565 | 400417252 | High Sign | HFTD Tier 3 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004566 | 400427635 | Molding | HFTD Tier 3 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004567 | 400435995 | Molding | HFTD Tier 3 | Distribution | 2004-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004568 | 400282360 | High Sign | HFTD Tier 3 | Distribution | 2004-10-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004569 | 400192957 | Molding | HFTD Tier 2 | Distribution | 2004-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004570 | 400224126 | High Sign | HFTD Tier 3 | Distribution | 2004-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004571 | 400226912 | High Sign | HFTD Tier 3 | Distribution | 2004-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004572 | 400226999 | High Sign | HFTD Tier 3 | Distribution | 2004-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004573 | 400228684 | High Sign | HFTD Tier 3 | Distribution | 2004-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004574 | 400230623 | High Sign | HFTD Tier 3 | Distribution | 2004-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004575 | 400368908 | Guy | HFTD Tier 2 | Distribution | 2004-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004576 | 400395919 | Molding | HFTD Tier 2 | Distribution | 2004-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004577 | 400428559 | Molding | HFTD Tier 3 | Distribution | 2004-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004578 | 400431417 | High Sign | HFTD Tier 3 | Distribution | 2004-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004579 | 400436017 | High Sign | HFTD Tier 2 | Distribution | 2004-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004580 | 400462503 | High Sign | HFTD Tier 3 | Distribution | 2004-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004581 | 400462601 | High Sign | HFTD Tier 3 | Distribution | 2004-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004582 | 400224085 | Molding | HFTD Tier 3 | Distribution | 2004-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004583 | 400226937 | High Sign | HFTD Tier 3 | Distribution | 2004-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004584 | 400230682 | High Sign | HFTD Tier 3 | Distribution | 2004-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004585 | 400383411 | High Sign | HFTD Tier 3 | Distribution | 2004-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004586 | 400387849 | High Sign | HFTD Tier 3 | Distribution | 2004-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004587 | 400391354 | Molding | HFTD Tier 3 | Distribution | 2004-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004588 | 400397323 | Molding | HFTD Tier 3 | Distribution | 2004-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004589 | 400409627 | High Sign | HFTD Tier 2 | Distribution | 2004-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004590 | 400416513 | Molding | HFTD Tier 2 | Distribution | 2004-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004591 | 400428491 | High Sign | HFTD Tier 3 | Distribution | 2004-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004592 | 400433572 | High Sign | HFTD Tier 3 | Distribution | 2004-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004593 | 400444328 | High Sign | HFTD Tier 2 | Distribution | 2004-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004594 | 400456102 | High Sign | HFTD Tier 3 | Distribution | 2004-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004595 | 400458977 | Molding | HFTD Tier 3 | Distribution | 2004-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004596 | 400462567 | High Sign | HFTD Tier 3 | Distribution | 2004-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004597 | 400012051 | Guy | HFTD Tier 3 | Distribution | 2004-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004598 | 400080988 | Molding | HFTD Tier 3 | Distribution | 2004-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004599 | 400082425 | Molding | HFTD Tier 3 | Distribution | 2004-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004600 | 400353016 | High Sign | HFTD Tier 3 | Distribution | 2004-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004601 | 400358315 | High Sign | HFTD Tier 3 | Distribution | 2004-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004602 | 400406517 | Guy | HFTD Tier 3 | Distribution | 2004-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004603 | 400445563 | Molding | HFTD Tier 3 | Distribution | 2004-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004604 | 400458618 | Molding | HFTD Tier 2 | Distribution | 2004-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004605 | 400017527 | Guy | HFTD Tier 3 | Distribution | 2004-10-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004606 | 400018527 | High Sign | HFTD Tier 2 | Distribution | 2004-10-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004607 | 400287018 | High Sign | HFTD Tier 2 | Distribution | 2004-10-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004608 | 400430341 | Molding | HFTD Tier 3 | Distribution | 2004-10-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004609 | 400741808 | High Sign | HFTD Tier 2 | Distribution | 2004-10-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004610 | 400885998 | High Sign | HFTD Tier 2 | Distribution | 2004-10-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004611 | 400012947 | High Sign | HFTD Tier 3 | Distribution | 2004-10-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004612 | 400044795 | High Sign | HFTD Tier 2 | Distribution | 2004-10-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004613 | 400047296 | Molding | HFTD Tier 3 | Distribution | 2004-10-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004614 | 400294870 | High Sign | HFTD Tier 2 | Distribution | 2004-10-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004615 | 400053297 | High Sign | HFTD Tier 2 | Distribution | 2004-10-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004616 | 400335194 | High Sign | HFTD Tier 2 | Distribution | 2004-10-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004617 | 400412712 | Guy | HFTD Tier 2 | Distribution | 2004-10-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004618 | 400056106 | High Sign | HFTD Tier 2 | Distribution | 2004-10-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004619 | 400251929 | Molding | HFTD Tier 3 | Distribution | 2004-10-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004620 | 400089437 | Molding | HFTD Tier 3 | Distribution | 2004-10-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004621 | 400042327 | Molding | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004622 | 400046171 | High Sign | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004623 | 400079604 | High Sign | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004624 | 400079631 | Molding | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004625 | 400087969 | High Sign | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004626 | 400088016 | High Sign | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004627 | 400106023 | Molding | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004628 | 400106941 | High Sign | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004629 | 400124476 | Molding | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004630 | 400124503 | Molding | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004631 | 400124677 | High Sign | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004632 | 400124692 | High Sign | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004633 | 400127702 | Molding | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004634 | 400129675 | High Sign | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004635 | 400129853 | Molding | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004636 | 400131606 | High Sign | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004637 | 400147552 | High Sign | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004638 | 400147577 | Molding | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004639 | 400148559 | High Sign | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004640 | 400152060 | High Sign | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004641 | 400249111 | Molding | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004642 | 400272548 | Molding | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004643 | 400273718 | High Sign | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004644 | 400276699 | Molding | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004645 | 400288970 | High Sign | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004646 | 400291391 | Molding | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004647 | 400385573 | High Sign | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004648 | 400386908 | High Sign | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004649 | 400389663 | Molding | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004650 | 400390247 | High Sign | HFTD Tier 3 | Distribution | 2004-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004651 | 400129912 | High Sign | HFTD Tier 3 | Distribution | 2004-10-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004652 | 400169340 | Molding | HFTD Tier 2 | Distribution | 2004-10-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004653 | 400205170 | Molding | HFTD Tier 2 | Distribution | 2004-10-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004654 | 400206577 | High Sign | HFTD Tier 3 | Distribution | 2004-10-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004655 | 400224848 | High Sign | HFTD Tier 2 | Distribution | 2004-10-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004656 | 400282862 | High Sign | HFTD Tier 2 | Distribution | 2004-10-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004657 | 400005887 | High Sign | HFTD Tier 3 | Distribution | 2004-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004658 | 400210149 | High Sign | HFTD Tier 3 | Distribution | 2004-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004659 | 400207313 | High Sign | HFTD Tier 3 | Distribution | 2004-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004660 | 400255673 | High Sign | HFTD Tier 3 | Distribution | 2004-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004661 | 400007687 | Molding | HFTD Tier 3 | Distribution | 2004-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004662 | 400180134 | Molding | HFTD Tier 3 | Distribution | 2004-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004663 | 400216770 | High Sign | HFTD Tier 3 | Distribution | 2004-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004664 | 400216785 | Molding | HFTD Tier 3 | Distribution | 2004-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004665 | 400218978 | Molding | HFTD Tier 3 | Distribution | 2004-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004666 | 400221539 | Hardware/Framing | HFTD Tier 3 | Distribution | 2004-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004667 | 400246379 | Molding | HFTD Tier 3 | Distribution | 2004-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004668 | 400247819 | High Sign | HFTD Tier 3 | Distribution | 2004-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004669 | 400254256 | High Sign | HFTD Tier 3 | Distribution | 2004-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004670 | 400254330 | High Sign | HFTD Tier 3 | Distribution | 2004-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004671 | 400259143 | High Sign | HFTD Tier 3 | Distribution | 2004-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004672 | 400261476 | Molding | HFTD Tier 3 | Distribution | 2004-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004673 | 400263649 | High Sign | HFTD Tier 3 | Distribution | 2004-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004674 | 400280864 | Molding | HFTD Tier 3 | Distribution | 2004-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004675 | 400243758 | Molding | HFTD Tier 2 | Distribution | 2004-10-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004676 | 401001200 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-10-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004677 | 400010656 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-11-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004678 | 400036849 | High Sign | HFTD Tier 3 | Distribution | 2004-11-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004679 | 400305524 | Guy | HFTD Tier 3 | Distribution | 2004-11-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004680 | 400020679 | Molding | HFTD Tier 2 | Distribution | 2004-11-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004681 | 400026560 | High Sign | HFTD Tier 2 | Distribution | 2004-11-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004682 | 400069934 | High Sign | HFTD Tier 3 | Distribution | 2004-11-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004683 | 400332303 | High Sign | HFTD Tier 3 | Distribution | 2004-11-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004684 | 400991462 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-11-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004685 | 400367582 | High Sign | HFTD Tier 3 | Distribution | 2004-11-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004686 | 400390004 | Crossarm | HFTD Tier 3 | Distribution | 2004-11-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004687 | 400038734 | Molding | HFTD Tier 2 | Distribution | 2004-11-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004688 | 400006534 | Insulator | HFTD Tier 3 | Distribution | 2004-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004689 | 400007482 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2004-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004690 | 400007483 | High Sign | HFTD Tier 3 | Distribution | 2004-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004691 | 400007566 | High Sign | HFTD Tier 3 | Distribution | 2004-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004692 | 400095578 | Molding | HFTD Tier 3 | Distribution | 2004-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004693 | 400127223 | High Sign | HFTD Tier 3 | Distribution | 2004-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004694 | 400129818 | Molding | HFTD Tier 3 | Distribution | 2004-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004695 | 400269914 | Molding | HFTD Tier 3 | Distribution | 2004-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004696 | 400271247 | Molding | HFTD Tier 3 | Distribution | 2004-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004697 | 400294068 | High Sign | HFTD Tier 3 | Distribution | 2004-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004698 | 400296542 | Molding | HFTD Tier 3 | Distribution | 2004-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004699 | 400474276 | High Sign | HFTD Tier 3 | Distribution | 2004-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004700 | 400006536 | High Sign | HFTD Tier 3 | Distribution | 2004-11-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004701 | 400007350 | Ground | HFTD Tier 3 | Distribution | 2004-11-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004702 | 400468586 | Molding | HFTD Tier 3 | Distribution | 2004-11-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004703 | 400005640 | High Sign | HFTD Tier 3 | Distribution | 2004-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004704 | 400006050 | Guy | HFTD Tier 2 | Distribution | 2004-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004705 | 400111407 | High Sign | HFTD Tier 3 | Distribution | 2004-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004706 | 400471143 | Guy | HFTD Tier 2 | Distribution | 2004-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004707 | 400008348 | High Sign | HFTD Tier 2 | Distribution | 2004-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004708 | 400020901 | Molding | HFTD Tier 2 | Distribution | 2004-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004709 | 400022704 | Molding | HFTD Tier 2 | Distribution | 2004-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004710 | 400048801 | High Sign | HFTD Tier 2 | Distribution | 2004-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004711 | 400341317 | Molding | HFTD Tier 3 | Distribution | 2004-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004712 | 400008013 | High Sign | HFTD Tier 3 | Distribution | 2004-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004713 | 400050384 | Molding | HFTD Tier 3 | Distribution | 2004-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004714 | 400053851 | Molding | HFTD Tier 2 | Distribution | 2004-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004715 | 400191379 | Molding | HFTD Tier 3 | Distribution | 2004-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004716 | 400349381 | High Sign | HFTD Tier 3 | Distribution | 2004-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004717 | 400145421 | High Sign | HFTD Tier 3 | Distribution | 2004-11-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004718 | 400008216 | Molding | HFTD Tier 3 | Distribution | 2004-11-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004719 | 400009285 | High Sign | HFTD Tier 2 | Distribution | 2004-11-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004720 | 400037185 | Molding | HFTD Tier 2 | Distribution | 2004-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004721 | 400101234 | Molding | HFTD Tier 3 | Distribution | 2004-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004722 | 400033327 | Molding | HFTD Tier 3 | Distribution | 2004-11-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004723 | 400341392 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-11-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004724 | 400026025 | High Sign | HFTD Tier 3 | Distribution | 2004-11-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004725 | 400181886 | Insulator | HFTD Tier 2 | Distribution | 2004-11-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004726 | 401006565 | High Sign | HFTD Tier 3 | Distribution | 2004-11-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004727 | 400018496 | High Sign | HFTD Tier 3 | Distribution | 2004-11-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004728 | 400018572 | High Sign | HFTD Tier 3 | Distribution | 2004-11-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004729 | 400024110 | High Sign | HFTD Tier 3 | Distribution | 2004-11-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004730 | 400058655 | Molding | HFTD Tier 3 | Distribution | 2004-11-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004731 | 400058722 | Ground | HFTD Tier 3 | Distribution | 2004-11-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004732 | 400064354 | Molding | HFTD Tier 3 | Distribution | 2004-11-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004733 | 400162419 | High Sign | HFTD Tier 3 | Distribution | 2004-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004734 | 400192444 | Hardware/Framing | HFTD Tier 2 | Distribution | 2004-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004735 | 400212676 | Molding | HFTD Tier 2 | Distribution | 2004-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004736 | 400881425 | Molding | HFTD Tier 2 | Distribution | 2004-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004737 | 400010888 | High Sign | HFTD Tier 3 | Distribution | 2004-12-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004738 | 400011311 | High Sign | HFTD Tier 3 | Distribution | 2004-12-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004739 | 400028304 | High Sign | HFTD Tier 3 | Distribution | 2004-12-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004740 | 400093840 | Hardware/Framing | HFTD Tier 2 | Distribution | 2004-12-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004741 | 400094883 | High Sign | HFTD Tier 2 | Distribution | 2004-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004742 | 400096696 | High Sign | HFTD Tier 2 | Distribution | 2004-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004743 | 400453370 | High Sign | HFTD Tier 2 | Distribution | 2004-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004744 | 400055150 | High Sign | HFTD Tier 3 | Distribution | 2004-12-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004745 | 400058089 | Molding | HFTD Tier 3 | Distribution | 2004-12-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004746 | 400254965 | High Sign | HFTD Tier 2 | Distribution | 2004-12-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004747 | 400254976 | High Sign | HFTD Tier 2 | Distribution | 2004-12-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004748 | 400507127 | High Sign | HFTD Tier 3 | Distribution | 2004-12-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004749 | 400075567 | Molding | HFTD Tier 3 | Distribution | 2004-12-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004750 | 400123830 | High Sign | HFTD Tier 2 | Distribution | 2004-12-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004751 | 400205185 | High Sign | HFTD Tier 3 | Distribution | 2004-12-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004752 | 400283639 | Molding | HFTD Tier 2 | Distribution | 2004-12-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004753 | 400318181 | High Sign | HFTD Tier 2 | Distribution | 2004-12-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004754 | 400020978 | Molding | HFTD Tier 3 | Distribution | 2004-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004755 | 400022053 | Molding | HFTD Tier 3 | Distribution | 2004-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004756 | 400141601 | High Sign | HFTD Tier 3 | Distribution | 2004-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004757 | 400156384 | Molding | HFTD Tier 3 | Distribution | 2004-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004758 | 400321806 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004759 | 400332017 | Molding | HFTD Tier 3 | Distribution | 2004-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004760 | 400339960 | Molding | HFTD Tier 3 | Distribution | 2004-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004761 | 400341049 | Molding | HFTD Tier 3 | Distribution | 2004-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004762 | 400344888 | Molding | HFTD Tier 3 | Distribution | 2004-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004763 | 400140557 | High Sign | HFTD Tier 2 | Distribution | 2004-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004764 | 400321058 | Molding | HFTD Tier 3 | Distribution | 2004-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004765 | 400430168 | Molding | HFTD Tier 2 | Distribution | 2004-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004766 | 401006690 | High Sign | HFTD Tier 3 | Distribution | 2004-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004767 | 400091686 | Molding | HFTD Tier 3 | Distribution | 2004-12-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004768 | 400149503 | Molding | HFTD Tier 3 | Distribution | 2004-12-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004769 | 400273053 | Guy | HFTD Tier 3 | Distribution | 2004-12-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004770 | 400320231 | High Sign | HFTD Tier 2 | Distribution | 2004-12-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004771 | 400339215 | Molding | HFTD Tier 3 | Distribution | 2004-12-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004772 | 400202320 | Riser/Conduit | HFTD Tier 3 | Distribution | 2004-12-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004773 | 400308060 | High Sign | HFTD Tier 3 | Distribution | 2004-12-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004774 | 400320646 | Cable/Conductor | HFTD Tier 3 | Distribution | 2004-12-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004775 | 400374155 | Guy | HFTD Tier 3 | Distribution | 2004-12-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004776 | 400379523 | Molding | HFTD Tier 3 | Distribution | 2004-12-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004777 | 400257945 | Molding | HFTD Tier 2 | Distribution | 2004-12-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004778 | 400305737 | Molding | HFTD Tier 2 | Distribution | 2004-12-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004779 | 400413666 | High Sign | HFTD Tier 3 | Distribution | 2004-12-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004780 | 400450393 | Molding | HFTD Tier 2 | Distribution | 2004-12-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004781 | 400406314 | Molding | HFTD Tier 3 | Distribution | 2004-12-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004782 | 400314481 | Molding | HFTD Tier 2 | Distribution | 2004-12-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004783 | 400479748 | Molding | HFTD Tier 3 | Distribution | 2004-12-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004784 | 401594450 | Cable/Conductor | HFTD Tier 2 | Distribution | 2004-12-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004785 | 400006775 | Hardware/Framing | HFTD Tier 2 | Distribution | 2005-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004786 | 400006923 | Molding | HFTD Tier 2 | Distribution | 2005-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004787 | 401599978 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004788 | 400008453 | High Sign | HFTD Tier 2 | Distribution | 2005-01-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004789 | 400517053 | Hardware/Framing | HFTD Tier 3 | Distribution | 2005-01-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004790 | 401004207 | High Sign | HFTD Tier 2 | Distribution | 2005-01-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004791 | 400394017 | High Sign | HFTD Tier 2 | Distribution | 2005-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004792 | 400429955 | High Sign | HFTD Tier 2 | Distribution | 2005-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004793 | 400451970 | High Sign | HFTD Tier 2 | Distribution | 2005-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004794 | 400459378 | Molding | HFTD Tier 2 | Distribution | 2005-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004795 | 400523699 | High Sign | HFTD Tier 2 | Distribution | 2005-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004796 | 400544158 | Molding | HFTD Tier 2 | Distribution | 2005-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004797 | 400546671 | Molding | HFTD Tier 2 | Distribution | 2005-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004798 | 400065476 | High Sign | HFTD Tier 2 | Distribution | 2005-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004799 | 400483853 | Molding | HFTD Tier 2 | Distribution | 2005-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004800 | 403047884 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2005-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004801 | 403047940 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2005-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004802 | 400022580 | Molding | HFTD Tier 2 | Distribution | 2005-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004803 | 400028598 | Riser/Conduit | HFTD Tier 2 | Distribution | 2005-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004804 | 400050955 | Molding | HFTD Tier 2 | Distribution | 2005-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004805 | 400160935 | Molding | HFTD Tier 2 | Distribution | 2005-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004806 | 400194453 | Molding | HFTD Tier 2 | Distribution | 2005-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004807 | 400510008 | High Sign | HFTD Tier 2 | Distribution | 2005-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004808 | 400534844 | High Sign | HFTD Tier 2 | Distribution | 2005-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004809 | 400535048 | Riser/Conduit | HFTD Tier 2 | Distribution | 2005-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004810 | 400011169 | Molding | HFTD Tier 2 | Distribution | 2005-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004811 | 400049635 | Molding | HFTD Tier 2 | Distribution | 2005-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004812 | 400052157 | Molding | HFTD Tier 3 | Distribution | 2005-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004813 | 400054531 | Guy | HFTD Tier 2 | Distribution | 2005-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004814 | 400065666 | High Sign | HFTD Tier 3 | Distribution | 2005-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004815 | 400066967 | High Sign | HFTD Tier 2 | Distribution | 2005-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004816 | 400113871 | High Sign | HFTD Tier 2 | Distribution | 2005-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004817 | 400124459 | Insulator | HFTD Tier 3 | Distribution | 2005-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004818 | 400202252 | Molding | HFTD Tier 3 | Distribution | 2005-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004819 | 400206809 | Molding | HFTD Tier 2 | Distribution | 2005-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004820 | 400206837 | Molding | HFTD Tier 3 | Distribution | 2005-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004821 | 400232833 | Guy | HFTD Tier 2 | Distribution | 2005-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004822 | 400559529 | High Sign | HFTD Tier 3 | Distribution | 2005-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004823 | 400035391 | Molding | HFTD Tier 2 | Distribution | 2005-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004824 | 400084428 | Molding | HFTD Tier 3 | Distribution | 2005-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004825 | 400042893 | Riser/Conduit | HFTD Tier 2 | Distribution | 2005-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004826 | 400084820 | Molding | HFTD Tier 2 | Distribution | 2005-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004827 | 400121042 | Molding | HFTD Tier 2 | Distribution | 2005-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004828 | 400011377 | Hardware/Framing | HFTD Tier 2 | Distribution | 2005-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004829 | 400043936 | Molding | HFTD Tier 2 | Distribution | 2005-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004830 | 400088730 | Molding | HFTD Tier 2 | Distribution | 2005-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004831 | 400110402 | Hardware/Framing | HFTD Tier 2 | Distribution | 2005-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004832 | 400110431 | Molding | HFTD Tier 2 | Distribution | 2005-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004833 | 400162107 | Riser/Conduit | HFTD Tier 2 | Distribution | 2005-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004834 | 400336531 | Molding | HFTD Tier 2 | Distribution | 2005-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004835 | 403046046 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004836 | 403047733 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004837 | 400011075 | Molding | HFTD Tier 3 | Distribution | 2005-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004838 | 400017400 | Guy | HFTD Tier 3 | Distribution | 2005-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004839 | 400049190 | Molding | HFTD Tier 3 | Distribution | 2005-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004840 | 400056711 | Molding | HFTD Tier 3 | Distribution | 2005-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004841 | 400085253 | Molding | HFTD Tier 3 | Distribution | 2005-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004842 | 400089173 | Molding | HFTD Tier 3 | Distribution | 2005-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004843 | 400089240 | Molding | HFTD Tier 3 | Distribution | 2005-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004844 | 400090010 | High Sign | HFTD Tier 3 | Distribution | 2005-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004845 | 400090032 | Molding | HFTD Tier 3 | Distribution | 2005-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004846 | 400135848 | Molding | HFTD Tier 2 | Distribution | 2005-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004847 | 400154807 | Cable/Conductor | HFTD Tier 2 | Distribution | 2005-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004848 | 400174714 | Molding | HFTD Tier 2 | Distribution | 2005-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004849 | 400402437 | High Sign | HFTD Tier 3 | Distribution | 2005-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004850 | 403046063 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004851 | 403046095 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004852 | 403046097 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004853 | 403046153 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004854 | 400052116 | High Sign | HFTD Tier 2 | Distribution | 2005-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004855 | 400209989 | Molding | HFTD Tier 2 | Distribution | 2005-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004856 | 400215074 | Molding | HFTD Tier 2 | Distribution | 2005-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004857 | 400357230 | Molding | HFTD Tier 2 | Distribution | 2005-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004858 | 403046057 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004859 | 403046107 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004860 | 403046198 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004861 | 400204073 | Molding | HFTD Tier 2 | Distribution | 2005-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004862 | 400236909 | High Sign | HFTD Tier 2 | Distribution | 2005-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004863 | 400296409 | High Sign | HFTD Tier 2 | Distribution | 2005-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004864 | 400299156 | Guy | HFTD Tier 2 | Distribution | 2005-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004865 | 400067223 | High Sign | HFTD Tier 3 | Distribution | 2005-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004866 | 400098694 | Molding | HFTD Tier 3 | Distribution | 2005-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004867 | 403046064 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004868 | 403046156 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004869 | 403046195 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004870 | 403046210 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004871 | 403046263 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004872 | 400248197 | High Sign | HFTD Tier 2 | Distribution | 2005-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004873 | 403046061 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004874 | 403046100 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004875 | 400297176 | High Sign | HFTD Tier 3 | Distribution | 2005-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004876 | 400437128 | High Sign | HFTD Tier 3 | Distribution | 2005-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004877 | 400377791 | Cable/Conductor | HFTD Tier 2 | Distribution | 2005-02-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004878 | 400032823 | Molding | HFTD Tier 3 | Distribution | 2005-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004879 | 400350544 | High Sign | HFTD Tier 3 | Distribution | 2005-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004880 | 400465639 | High Sign | HFTD Tier 3 | Distribution | 2005-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004881 | 400507068 | High Sign | HFTD Tier 3 | Distribution | 2005-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004882 | 400054337 | High Sign | HFTD Tier 3 | Distribution | 2005-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004883 | 400062984 | Hardware/Framing | HFTD Tier 3 | Distribution | 2005-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004884 | 400457912 | Molding | HFTD Tier 3 | Distribution | 2005-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004885 | 400490086 | Molding | HFTD Tier 2 | Distribution | 2005-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004886 | 403046337 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004887 | 400073128 | Molding | HFTD Tier 3 | Distribution | 2005-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004888 | 400465425 | Molding | HFTD Tier 3 | Distribution | 2005-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004889 | 400468174 | Molding | HFTD Tier 3 | Distribution | 2005-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004890 | 400468954 | Molding | HFTD Tier 3 | Distribution | 2005-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004891 | 400473058 | Molding | HFTD Tier 3 | Distribution | 2005-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004892 | 400492456 | Molding | HFTD Tier 3 | Distribution | 2005-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004893 | 400510142 | Riser/Conduit | HFTD Tier 3 | Distribution | 2005-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004894 | 400531582 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004895 | 400158213 | Molding | HFTD Tier 3 | Distribution | 2005-02-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004896 | 400299635 | Molding | HFTD Tier 3 | Distribution | 2005-02-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004897 | 400526639 | Molding | HFTD Tier 3 | Distribution | 2005-02-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004898 | 400540775 | Cable/Conductor | HFTD Tier 3 | Distribution | 2005-02-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004899 | 400034482 | Molding | HFTD Tier 3 | Distribution | 2005-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004900 | 400227476 | Guy | HFTD Tier 3 | Distribution | 2005-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004901 | 400229343 | Molding | HFTD Tier 3 | Distribution | 2005-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004902 | 400082226 | Molding | HFTD Tier 2 | Distribution | 2005-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004903 | 400112085 | Molding | HFTD Tier 2 | Distribution | 2005-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004904 | 400119908 | Molding | HFTD Tier 2 | Distribution | 2005-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004905 | 400167862 | High Sign | HFTD Tier 2 | Distribution | 2005-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004906 | 400123380 | Molding | HFTD Tier 3 | Distribution | 2005-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004907 | 400324445 | Molding | HFTD Tier 3 | Distribution | 2005-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004908 | 400067870 | High Sign | HFTD Tier 2 | Distribution | 2005-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004909 | 400103438 | High Sign | HFTD Tier 2 | Distribution | 2005-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004910 | 400525127 | Molding | HFTD Tier 2 | Distribution | 2005-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004911 | 400069765 | Molding | HFTD Tier 2 | Distribution | 2005-02-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004912 | 400361837 | High Sign | HFTD Tier 3 | Distribution | 2005-02-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004913 | 400391921 | Molding | HFTD Tier 2 | Distribution | 2005-02-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004914 | 400422922 | High Sign | HFTD Tier 2 | Distribution | 2005-02-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004915 | 400526055 | Molding | HFTD Tier 2 | Distribution | 2005-02-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004916 | 400536492 | Cable/Conductor | HFTD Tier 3 | Distribution | 2005-02-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004917 | 400186337 | Guy | HFTD Tier 3 | Distribution | 2005-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004918 | 400355128 | Molding | HFTD Tier 3 | Distribution | 2005-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004919 | 400068642 | High Sign | HFTD Tier 2 | Distribution | 2005-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004920 | 400289648 | High Sign | HFTD Tier 3 | Distribution | 2005-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004921 | 400339912 | High Sign | HFTD Tier 2 | Distribution | 2005-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004922 | 400376271 | Molding | HFTD Tier 2 | Distribution | 2005-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004923 | 400445346 | Molding | HFTD Tier 3 | Distribution | 2005-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004924 | 400452271 | Molding | HFTD Tier 3 | Distribution | 2005-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004925 | 400122488 | Riser/Conduit | HFTD Tier 3 | Distribution | 2005-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004926 | 400249875 | Molding | HFTD Tier 3 | Distribution | 2005-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004927 | 400250288 | Molding | HFTD Tier 3 | Distribution | 2005-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004928 | 400262693 | High Sign | HFTD Tier 3 | Distribution | 2005-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004929 | 400444370 | Riser/Conduit | HFTD Tier 3 | Distribution | 2005-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004930 | 400458877 | High Sign | HFTD Tier 3 | Distribution | 2005-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004931 | 400509660 | High Sign | HFTD Tier 2 | Distribution | 2005-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004932 | 400131278 | High Sign | HFTD Tier 2 | Distribution | 2005-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004933 | 400249904 | Guy | HFTD Tier 3 | Distribution | 2005-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004934 | 400250283 | High Sign | HFTD Tier 3 | Distribution | 2005-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004935 | 400257148 | Guy | HFTD Tier 3 | Distribution | 2005-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004936 | 400261893 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004937 | 400267474 | High Sign | HFTD Tier 2 | Distribution | 2005-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004938 | 400433108 | Molding | HFTD Tier 3 | Distribution | 2005-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004939 | 400436329 | Molding | HFTD Tier 3 | Distribution | 2005-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004940 | 400450947 | High Sign | HFTD Tier 2 | Distribution | 2005-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004941 | 400061731 | Molding | HFTD Tier 2 | Distribution | 2005-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004942 | 400063509 | Molding | HFTD Tier 3 | Distribution | 2005-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004943 | 400097709 | Guy | HFTD Tier 3 | Distribution | 2005-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004944 | 400109774 | Molding | HFTD Tier 3 | Distribution | 2005-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004945 | 400111615 | Molding | HFTD Tier 2 | Distribution | 2005-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004946 | 400113309 | Molding | HFTD Tier 2 | Distribution | 2005-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004947 | 400133469 | Molding | HFTD Tier 3 | Distribution | 2005-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004948 | 400134410 | Molding | HFTD Tier 2 | Distribution | 2005-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004949 | 400134437 | Molding | HFTD Tier 2 | Distribution | 2005-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004950 | 400315751 | High Sign | HFTD Tier 3 | Distribution | 2005-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004951 | 400340058 | Molding | HFTD Tier 2 | Distribution | 2005-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004952 | 400481838 | Guy | HFTD Tier 3 | Distribution | 2005-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004953 | 400494198 | High Sign | HFTD Tier 3 | Distribution | 2005-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004954 | 400497032 | High Sign | HFTD Tier 3 | Distribution | 2005-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004955 | 400324678 | Molding | HFTD Tier 2 | Distribution | 2005-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004956 | 400354881 | High Sign | HFTD Tier 2 | Distribution | 2005-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004957 | 400500540 | Molding | HFTD Tier 2 | Distribution | 2005-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004958 | 400515882 | High Sign | HFTD Tier 2 | Distribution | 2005-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004959 | 400522031 | Molding | HFTD Tier 2 | Distribution | 2005-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004960 | 400541862 | Molding | HFTD Tier 3 | Distribution | 2005-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004961 | 400411121 | Molding | HFTD Tier 3 | Distribution | 2005-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004962 | 400573076 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004963 | 400436092 | High Sign | HFTD Tier 3 | Distribution | 2005-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004964 | 400440044 | Riser/Conduit | HFTD Tier 2 | Distribution | 2005-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004965 | 400555239 | Molding | HFTD Tier 3 | Distribution | 2005-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004966 | 400048246 | Guy | HFTD Tier 3 | Distribution | 2005-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004967 | 400051578 | Guy | HFTD Tier 3 | Distribution | 2005-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004968 | 400061939 | High Sign | HFTD Tier 2 | Distribution | 2005-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004969 | 400064688 | High Sign | HFTD Tier 2 | Distribution | 2005-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004970 | 400066061 | Molding | HFTD Tier 2 | Distribution | 2005-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004971 | 400067806 | Molding | HFTD Tier 2 | Distribution | 2005-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004972 | 400070544 | Molding | HFTD Tier 2 | Distribution | 2005-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004973 | 400086670 | Molding | HFTD Tier 3 | Distribution | 2005-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004974 | 400427472 | High Sign | HFTD Tier 2 | Distribution | 2005-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004975 | 400434613 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2005-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004976 | 400435255 | Guy | HFTD Tier 2 | Distribution | 2005-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004977 | 400463344 | Guy | HFTD Tier 3 | Distribution | 2005-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004978 | 400478367 | Guy | HFTD Tier 3 | Distribution | 2005-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004979 | 400482276 | Guy | HFTD Tier 3 | Distribution | 2005-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004980 | 400606871 | Molding | HFTD Tier 2 | Distribution | 2005-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004981 | 400615336 | Guy | HFTD Tier 3 | Distribution | 2005-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004982 | 400055402 | Molding | HFTD Tier 2 | Distribution | 2005-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004983 | 400070514 | High Sign | HFTD Tier 2 | Distribution | 2005-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004984 | 400072973 | Guy | HFTD Tier 2 | Distribution | 2005-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004985 | 400075230 | Guy | HFTD Tier 2 | Distribution | 2005-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004986 | 400109125 | Molding | HFTD Tier 3 | Distribution | 2005-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004987 | 400135575 | Molding | HFTD Tier 3 | Distribution | 2005-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004988 | 400309159 | Guy | HFTD Tier 3 | Distribution | 2005-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004989 | 400309189 | Molding | HFTD Tier 3 | Distribution | 2005-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004990 | 400428429 | Molding | HFTD Tier 2 | Distribution | 2005-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004991 | 400433109 | High Sign | HFTD Tier 2 | Distribution | 2005-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004992 | 400461817 | High Sign | HFTD Tier 2 | Distribution | 2005-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004993 | 400494902 | Guy | HFTD Tier 3 | Distribution | 2005-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004994 | 400500846 | Guy | HFTD Tier 3 | Distribution | 2005-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004995 | 400507008 | Guy | HFTD Tier 3 | Distribution | 2005-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004996 | 400055333 | High Sign | HFTD Tier 2 | Distribution | 2005-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004997 | 400061877 | Molding | HFTD Tier 2 | Distribution | 2005-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004998 | 400065992 | Molding | HFTD Tier 2 | Distribution | 2005-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120004999 | 400070444 | High Sign | HFTD Tier 2 | Distribution | 2005-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005000 | 400108321 | Riser/Conduit | HFTD Tier 3 | Distribution | 2005-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005001 | 400121507 | Molding | HFTD Tier 3 | Distribution | 2005-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005002 | 400306874 | High Sign | HFTD Tier 3 | Distribution | 2005-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005003 | 400360027 | High Sign | HFTD Tier 3 | Distribution | 2005-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005004 | 400421357 | High Sign | HFTD Tier 2 | Distribution | 2005-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005005 | 400427532 | Molding | HFTD Tier 2 | Distribution | 2005-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005006 | 400432241 | Molding | HFTD Tier 2 | Distribution | 2005-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005007 | 400495853 | Ground | HFTD Tier 3 | Distribution | 2005-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005008 | 400497985 | Riser/Conduit | HFTD Tier 3 | Distribution | 2005-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005009 | 400521911 | Molding | HFTD Tier 3 | Distribution | 2005-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005010 | 401003224 | High Sign | HFTD Tier 3 | Distribution | 2005-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005011 | 400023404 | High Sign | HFTD Tier 3 | Distribution | 2005-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005012 | 400025581 | High Sign | HFTD Tier 3 | Distribution | 2005-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005013 | 400073403 | Molding | HFTD Tier 2 | Distribution | 2005-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005014 | 400112989 | Molding | HFTD Tier 3 | Distribution | 2005-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005015 | 400141706 | Guy | HFTD Tier 3 | Distribution | 2005-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005016 | 400376432 | High Sign | HFTD Tier 3 | Distribution | 2005-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005017 | 400380850 | High Sign | HFTD Tier 3 | Distribution | 2005-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005018 | 400380871 | High Sign | HFTD Tier 3 | Distribution | 2005-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005019 | 400391709 | Molding | HFTD Tier 3 | Distribution | 2005-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005020 | 400512008 | Molding | HFTD Tier 3 | Distribution | 2005-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005021 | 400560974 | Ground | HFTD Tier 3 | Distribution | 2005-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005022 | 401002494 | Cable/Conductor | HFTD Tier 3 | Distribution | 2005-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005023 | 400089622 | Molding | HFTD Tier 2 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005024 | 400122659 | Riser/Conduit | HFTD Tier 3 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005025 | 400123299 | Molding | HFTD Tier 2 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005026 | 400124754 | Molding | HFTD Tier 2 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005027 | 400168691 | Molding | HFTD Tier 2 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005028 | 400360942 | Guy | HFTD Tier 3 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005029 | 400365891 | Molding | HFTD Tier 3 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005030 | 400369477 | Molding | HFTD Tier 3 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005031 | 400373210 | Guy | HFTD Tier 3 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005032 | 400468575 | Molding | HFTD Tier 3 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005033 | 400523761 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005034 | 400523771 | Cable/Conductor | HFTD Tier 3 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005035 | 400529587 | Guy | HFTD Tier 3 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005036 | 400529608 | Guy | HFTD Tier 3 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005037 | 400548219 | Molding | HFTD Tier 3 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005038 | 400551465 | High Sign | HFTD Tier 3 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005039 | 400561939 | Molding | HFTD Tier 3 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005040 | 400737940 | Molding | HFTD Tier 3 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005041 | 400741053 | High Sign | HFTD Tier 3 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005042 | 400742101 | Guy | HFTD Tier 3 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005043 | 400747302 | High Sign | HFTD Tier 3 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005044 | 400756556 | High Sign | HFTD Tier 3 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005045 | 413823452 | Molding | HFTD Tier 3 | Distribution | 2005-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005046 | 400115851 | Hardware/Framing | HFTD Tier 3 | Distribution | 2005-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005047 | 400124823 | Molding | HFTD Tier 3 | Distribution | 2005-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005048 | 400430826 | Guy | HFTD Tier 3 | Distribution | 2005-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005049 | 400442546 | Guy | HFTD Tier 3 | Distribution | 2005-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005050 | 400455699 | Molding | HFTD Tier 3 | Distribution | 2005-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005051 | 400464116 | High Sign | HFTD Tier 3 | Distribution | 2005-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005052 | 403048249 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005053 | 400126686 | High Sign | HFTD Tier 3 | Distribution | 2005-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005054 | 400170782 | Molding | HFTD Tier 2 | Distribution | 2005-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005055 | 400492758 | Molding | HFTD Tier 2 | Distribution | 2005-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005056 | 400044691 | High Sign | HFTD Tier 3 | Distribution | 2005-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005057 | 400494990 | High Sign | HFTD Tier 2 | Distribution | 2005-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005058 | 400125470 | Molding | HFTD Tier 3 | Distribution | 2005-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005059 | 400144253 | Hardware/Framing | HFTD Tier 3 | Distribution | 2005-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005060 | 400158347 | Molding | HFTD Tier 3 | Distribution | 2005-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005061 | 400176778 | Molding | HFTD Tier 3 | Distribution | 2005-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005062 | 400198133 | High Sign | HFTD Tier 2 | Distribution | 2005-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005063 | 400200198 | Molding | HFTD Tier 2 | Distribution | 2005-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005064 | 400351370 | Cable/Conductor | HFTD Tier 3 | Distribution | 2005-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005065 | 400373563 | High Sign | HFTD Tier 2 | Distribution | 2005-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005066 | 400465865 | High Sign | HFTD Tier 3 | Distribution | 2005-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005067 | 400467145 | Molding | HFTD Tier 3 | Distribution | 2005-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005068 | 400488988 | Molding | HFTD Tier 3 | Distribution | 2005-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005069 | 400508270 | Molding | HFTD Tier 2 | Distribution | 2005-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005070 | 401457147 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005071 | 400133774 | Hardware/Framing | HFTD Tier 3 | Distribution | 2005-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005072 | 400144545 | Hardware/Framing | HFTD Tier 3 | Distribution | 2005-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005073 | 400205631 | High Sign | HFTD Tier 3 | Distribution | 2005-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005074 | 400210379 | Molding | HFTD Tier 3 | Distribution | 2005-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005075 | 400210811 | High Sign | HFTD Tier 3 | Distribution | 2005-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005076 | 400213020 | Molding | HFTD Tier 3 | Distribution | 2005-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005077 | 400223305 | High Sign | HFTD Tier 3 | Distribution | 2005-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005078 | 400236418 | High Sign | HFTD Tier 3 | Distribution | 2005-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005079 | 400391609 | High Sign | HFTD Tier 3 | Distribution | 2005-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005080 | 400391639 | High Sign | HFTD Tier 3 | Distribution | 2005-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005081 | 400518953 | Molding | HFTD Tier 3 | Distribution | 2005-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005082 | 400090940 | Molding | HFTD Tier 3 | Distribution | 2005-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005083 | 400130595 | Molding | HFTD Tier 3 | Distribution | 2005-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005084 | 400143566 | Molding | HFTD Tier 3 | Distribution | 2005-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005085 | 400198753 | Molding | HFTD Tier 3 | Distribution | 2005-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005086 | 400206931 | Guy | HFTD Tier 3 | Distribution | 2005-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005087 | 400210447 | Molding | HFTD Tier 3 | Distribution | 2005-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005088 | 400210756 | Molding | HFTD Tier 3 | Distribution | 2005-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005089 | 400234661 | High Sign | HFTD Tier 3 | Distribution | 2005-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005090 | 400386984 | High Sign | HFTD Tier 3 | Distribution | 2005-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005091 | 400387043 | Molding | HFTD Tier 3 | Distribution | 2005-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005092 | 400391579 | Guy | HFTD Tier 3 | Distribution | 2005-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005093 | 400409817 | Molding | HFTD Tier 3 | Distribution | 2005-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005094 | 400428944 | High Sign | HFTD Tier 2 | Distribution | 2005-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005095 | 400429925 | Molding | HFTD Tier 2 | Distribution | 2005-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005096 | 400564626 | Molding | HFTD Tier 2 | Distribution | 2005-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005097 | 400234720 | Molding | HFTD Tier 3 | Distribution | 2005-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005098 | 400244494 | Molding | HFTD Tier 3 | Distribution | 2005-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005099 | 400281471 | High Sign | HFTD Tier 3 | Distribution | 2005-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005100 | 400341316 | High Sign | HFTD Tier 3 | Distribution | 2005-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005101 | 400350858 | Molding | HFTD Tier 3 | Distribution | 2005-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005102 | 400500590 | Guy | HFTD Tier 3 | Distribution | 2005-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005103 | 400531507 | High Sign | HFTD Tier 3 | Distribution | 2005-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005104 | 400136520 | Molding | HFTD Tier 2 | Distribution | 2005-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005105 | 400145696 | Molding | HFTD Tier 3 | Distribution | 2005-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005106 | 400624589 | Molding | HFTD Tier 3 | Distribution | 2005-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005107 | 400134911 | Molding | HFTD Tier 2 | Distribution | 2005-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005108 | 400300446 | High Sign | HFTD Tier 3 | Distribution | 2005-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005109 | 400350494 | Riser/Conduit | HFTD Tier 3 | Distribution | 2005-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005110 | 400368706 | Ground | HFTD Tier 3 | Distribution | 2005-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005111 | 400372422 | Cable/Conductor | HFTD Tier 3 | Distribution | 2005-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005112 | 400394010 | Molding | HFTD Tier 3 | Distribution | 2005-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005113 | 400398487 | Molding | HFTD Tier 3 | Distribution | 2005-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005114 | 400409342 | Molding | HFTD Tier 3 | Distribution | 2005-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005115 | 400501606 | Molding | HFTD Tier 3 | Distribution | 2005-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005116 | 400663074 | Molding | HFTD Tier 2 | Distribution | 2005-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005117 | 400664421 | Molding | HFTD Tier 3 | Distribution | 2005-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005118 | 400687414 | Molding | HFTD Tier 3 | Distribution | 2005-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005119 | 400687467 | Molding | HFTD Tier 3 | Distribution | 2005-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005120 | 400139527 | Molding | HFTD Tier 3 | Distribution | 2005-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005121 | 400340252 | Molding | HFTD Tier 3 | Distribution | 2005-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005122 | 400383600 | Molding | HFTD Tier 3 | Distribution | 2005-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005123 | 400386358 | Molding | HFTD Tier 3 | Distribution | 2005-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005124 | 400387367 | High Sign | HFTD Tier 3 | Distribution | 2005-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005125 | 400387398 | Molding | HFTD Tier 3 | Distribution | 2005-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005126 | 400406685 | High Sign | HFTD Tier 3 | Distribution | 2005-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005127 | 400494021 | Molding | HFTD Tier 3 | Distribution | 2005-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005128 | 400496860 | Molding | HFTD Tier 3 | Distribution | 2005-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005129 | 400507463 | Riser/Conduit | HFTD Tier 3 | Distribution | 2005-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005130 | 400509590 | Molding | HFTD Tier 3 | Distribution | 2005-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005131 | 400520441 | Molding | HFTD Tier 3 | Distribution | 2005-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005132 | 400639469 | Molding | HFTD Tier 3 | Distribution | 2005-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005133 | 400671332 | High Sign | HFTD Tier 3 | Distribution | 2005-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005134 | 400704005 | Molding | HFTD Tier 3 | Distribution | 2005-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005135 | 401457456 | Cable/Conductor | HFTD Tier 2 | Distribution | 2005-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005136 | 400387448 | Molding | HFTD Tier 3 | Distribution | 2005-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005137 | 400393393 | Molding | HFTD Tier 3 | Distribution | 2005-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005138 | 400393771 | Cable/Conductor | HFTD Tier 3 | Distribution | 2005-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005139 | 400403652 | Molding | HFTD Tier 3 | Distribution | 2005-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005140 | 400403681 | Molding | HFTD Tier 3 | Distribution | 2005-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005141 | 400409087 | Molding | HFTD Tier 3 | Distribution | 2005-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005142 | 400418646 | Molding | HFTD Tier 3 | Distribution | 2005-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005143 | 400517473 | Molding | HFTD Tier 3 | Distribution | 2005-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005144 | 400704000 | Guy | HFTD Tier 3 | Distribution | 2005-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005145 | 400704700 | Molding | HFTD Tier 3 | Distribution | 2005-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005146 | 400708166 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005147 | 400722000 | High Sign | HFTD Tier 2 | Distribution | 2005-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005148 | 400403744 | Molding | HFTD Tier 3 | Distribution | 2005-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005149 | 400413946 | Molding | HFTD Tier 3 | Distribution | 2005-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005150 | 400414088 | Molding | HFTD Tier 3 | Distribution | 2005-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005151 | 400418475 | Molding | HFTD Tier 3 | Distribution | 2005-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005152 | 400452432 | Molding | HFTD Tier 3 | Distribution | 2005-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005153 | 400453735 | High Sign | HFTD Tier 3 | Distribution | 2005-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005154 | 400523316 | Hardware/Framing | HFTD Tier 3 | Distribution | 2005-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005155 | 400550696 | Molding | HFTD Tier 3 | Distribution | 2005-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005156 | 400736570 | Riser/Conduit | HFTD Tier 3 | Distribution | 2005-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005157 | 400752974 | Molding | HFTD Tier 3 | Distribution | 2005-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005158 | 400058623 | Molding | HFTD Tier 3 | Distribution | 2005-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005159 | 400058680 | Molding | HFTD Tier 3 | Distribution | 2005-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005160 | 400456251 | Molding | HFTD Tier 3 | Distribution | 2005-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005161 | 400458100 | High Sign | HFTD Tier 3 | Distribution | 2005-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005162 | 400476868 | High Sign | HFTD Tier 3 | Distribution | 2005-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005163 | 400488196 | High Sign | HFTD Tier 3 | Distribution | 2005-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005164 | 400580997 | High Sign | HFTD Tier 3 | Distribution | 2005-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005165 | 400167226 | Molding | HFTD Tier 3 | Distribution | 2005-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005166 | 400391458 | High Sign | HFTD Tier 2 | Distribution | 2005-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005167 | 400497834 | Molding | HFTD Tier 3 | Distribution | 2005-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005168 | 400525578 | Riser/Conduit | HFTD Tier 3 | Distribution | 2005-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005169 | 400655164 | Molding | HFTD Tier 3 | Distribution | 2005-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005170 | 400670073 | High Sign | HFTD Tier 3 | Distribution | 2005-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005171 | 400021605 | Molding | HFTD Tier 3 | Distribution | 2005-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005172 | 400154692 | Molding | HFTD Tier 3 | Distribution | 2005-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005173 | 400156068 | Molding | HFTD Tier 3 | Distribution | 2005-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005174 | 400481559 | High Sign | HFTD Tier 3 | Distribution | 2005-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005175 | 400506297 | Molding | HFTD Tier 2 | Distribution | 2005-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005176 | 400524673 | Molding | HFTD Tier 2 | Distribution | 2005-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005177 | 400554822 | Molding | HFTD Tier 2 | Distribution | 2005-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005178 | 400558174 | Molding | HFTD Tier 2 | Distribution | 2005-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005179 | 400709877 | Molding | HFTD Tier 2 | Distribution | 2005-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005180 | 400028939 | High Sign | HFTD Tier 3 | Distribution | 2005-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005181 | 400032232 | Guy | HFTD Tier 3 | Distribution | 2005-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005182 | 400034777 | High Sign | HFTD Tier 3 | Distribution | 2005-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005183 | 400042796 | High Sign | HFTD Tier 3 | Distribution | 2005-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005184 | 400101779 | Molding | HFTD Tier 3 | Distribution | 2005-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005185 | 400115333 | Molding | HFTD Tier 3 | Distribution | 2005-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005186 | 400116858 | Guy | HFTD Tier 3 | Distribution | 2005-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005187 | 400119509 | Molding | HFTD Tier 3 | Distribution | 2005-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005188 | 400120124 | Molding | HFTD Tier 3 | Distribution | 2005-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005189 | 400141828 | Molding | HFTD Tier 3 | Distribution | 2005-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005190 | 400142497 | Molding | HFTD Tier 3 | Distribution | 2005-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005191 | 400144817 | Molding | HFTD Tier 3 | Distribution | 2005-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005192 | 400153366 | Molding | HFTD Tier 3 | Distribution | 2005-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005193 | 400153490 | Molding | HFTD Tier 3 | Distribution | 2005-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005194 | 400156617 | Molding | HFTD Tier 3 | Distribution | 2005-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005195 | 400159467 | Molding | HFTD Tier 3 | Distribution | 2005-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005196 | 400553126 | Molding | HFTD Tier 3 | Distribution | 2005-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005197 | 400558252 | High Sign | HFTD Tier 2 | Distribution | 2005-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005198 | 400738957 | High Sign | HFTD Tier 3 | Distribution | 2005-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005199 | 400749474 | High Sign | HFTD Tier 3 | Distribution | 2005-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005200 | 403048664 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005201 | 400079347 | High Sign | HFTD Tier 3 | Distribution | 2005-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005202 | 400753081 | Molding | HFTD Tier 3 | Distribution | 2005-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005203 | 400233103 | Molding | HFTD Tier 3 | Distribution | 2005-04-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005204 | 400084857 | High Sign | HFTD Tier 2 | Distribution | 2005-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005205 | 400154963 | High Sign | HFTD Tier 2 | Distribution | 2005-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005206 | 400157392 | Molding | HFTD Tier 3 | Distribution | 2005-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005207 | 400200109 | Guy | HFTD Tier 2 | Distribution | 2005-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005208 | 400286570 | High Sign | HFTD Tier 3 | Distribution | 2005-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005209 | 400333546 | High Sign | HFTD Tier 2 | Distribution | 2005-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005210 | 400339617 | Guy | HFTD Tier 2 | Distribution | 2005-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005211 | 400344485 | High Sign | HFTD Tier 2 | Distribution | 2005-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005212 | 400082529 | High Sign | HFTD Tier 2 | Distribution | 2005-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005213 | 400493323 | High Sign | HFTD Tier 3 | Distribution | 2005-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005214 | 400145649 | Riser/Conduit | HFTD Tier 3 | Distribution | 2005-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005215 | 400190135 | Molding | HFTD Tier 2 | Distribution | 2005-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005216 | 400361535 | High Sign | HFTD Tier 3 | Distribution | 2005-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005217 | 400231713 | Insulator | HFTD Tier 2 | Distribution | 2005-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005218 | 400368763 | High Sign | HFTD Tier 3 | Distribution | 2005-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005219 | 400389464 | High Sign | HFTD Tier 3 | Distribution | 2005-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005220 | 400247900 | High Sign | HFTD Tier 3 | Distribution | 2005-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005221 | 400000734 | Insulator | HFTD Tier 2 | Transmission | 2005-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005222 | 400134641 | Molding | HFTD Tier 3 | Distribution | 2005-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005223 | 400332519 | Molding | HFTD Tier 3 | Distribution | 2005-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005224 | 400516107 | Molding | HFTD Tier 3 | Distribution | 2005-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005225 | 401006783 | Molding | HFTD Tier 3 | Distribution | 2005-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005226 | 401006785 | High Sign | HFTD Tier 3 | Distribution | 2005-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005227 | 400498104 | Riser/Conduit | HFTD Tier 3 | Distribution | 2005-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005228 | 400512083 | High Sign | HFTD Tier 2 | Distribution | 2005-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005229 | 400405714 | Molding | HFTD Tier 2 | Distribution | 2005-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005230 | 400524599 | Molding | HFTD Tier 3 | Distribution | 2005-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005231 | 400548054 | Molding | HFTD Tier 3 | Distribution | 2005-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005232 | 400064048 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2005-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005233 | 400428941 | Molding | HFTD Tier 3 | Distribution | 2005-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005234 | 401006502 | Molding | HFTD Tier 3 | Distribution | 2005-04-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005235 | 400083332 | High Sign | HFTD Tier 3 | Distribution | 2005-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005236 | 400591654 | Molding | HFTD Tier 3 | Distribution | 2005-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005237 | 400269680 | High Sign | HFTD Tier 2 | Distribution | 2005-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005238 | 400531099 | Molding | HFTD Tier 2 | Distribution | 2005-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005239 | 400531859 | High Sign | HFTD Tier 2 | Distribution | 2005-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005240 | 400713691 | Molding | HFTD Tier 2 | Distribution | 2005-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005241 | 400139682 | Molding | HFTD Tier 3 | Distribution | 2005-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005242 | 400736733 | Molding | HFTD Tier 3 | Distribution | 2005-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005243 | 401006670 | High Sign | HFTD Tier 3 | Distribution | 2005-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005244 | 400043103 | Molding | HFTD Tier 2 | Distribution | 2005-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005245 | 400060000 | Bond | HFTD Tier 2 | Distribution | 2005-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005246 | 401464313 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005247 | 400094731 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005248 | 400114879 | Molding | HFTD Tier 3 | Distribution | 2005-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005249 | 400318466 | High Sign | HFTD Tier 3 | Distribution | 2005-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005250 | 400373798 | Guy | HFTD Tier 3 | Distribution | 2005-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005251 | 400069807 | Molding | HFTD Tier 2 | Distribution | 2005-05-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005252 | 400081026 | High Sign | HFTD Tier 2 | Distribution | 2005-05-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005253 | 400126781 | Molding | HFTD Tier 3 | Distribution | 2005-05-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005254 | 400300100 | Molding | HFTD Tier 2 | Distribution | 2005-05-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005255 | 400371342 | Cable/Conductor | HFTD Tier 3 | Distribution | 2005-05-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005256 | 400666522 | Riser/Conduit | HFTD Tier 2 | Distribution | 2005-05-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005257 | 400184095 | High Sign | HFTD Tier 2 | Distribution | 2005-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005258 | 400419561 | Molding | HFTD Tier 2 | Distribution | 2005-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005259 | 400491889 | High Sign | HFTD Tier 2 | Distribution | 2005-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005260 | 400232676 | Guy | HFTD Tier 2 | Distribution | 2005-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005261 | 400235034 | High Sign | HFTD Tier 2 | Distribution | 2005-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005262 | 400243432 | High Sign | HFTD Tier 2 | Distribution | 2005-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005263 | 400244677 | Guy | HFTD Tier 2 | Distribution | 2005-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005264 | 400266957 | High Sign | HFTD Tier 2 | Distribution | 2005-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005265 | 400269021 | High Sign | HFTD Tier 2 | Distribution | 2005-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005266 | 400281329 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2005-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005267 | 400294832 | High Sign | HFTD Tier 2 | Distribution | 2005-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005268 | 400298005 | High Sign | HFTD Tier 2 | Distribution | 2005-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005269 | 400301645 | High Sign | HFTD Tier 2 | Distribution | 2005-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005270 | 400498419 | Guy | HFTD Tier 2 | Distribution | 2005-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005271 | 401478688 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2005-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005272 | 400058923 | High Sign | HFTD Tier 2 | Distribution | 2005-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005273 | 400066904 | High Sign | HFTD Tier 2 | Distribution | 2005-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005274 | 400076527 | High Sign | HFTD Tier 2 | Distribution | 2005-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005275 | 400182161 | Molding | HFTD Tier 2 | Distribution | 2005-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005276 | 400185011 | Guy | HFTD Tier 3 | Distribution | 2005-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005277 | 400222962 | Molding | HFTD Tier 2 | Distribution | 2005-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005278 | 400236875 | Guy | HFTD Tier 3 | Distribution | 2005-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005279 | 400283870 | High Sign | HFTD Tier 2 | Distribution | 2005-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005280 | 400298563 | Molding | HFTD Tier 2 | Distribution | 2005-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005281 | 400415555 | High Sign | HFTD Tier 2 | Distribution | 2005-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005282 | 400471152 | High Sign | HFTD Tier 2 | Distribution | 2005-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005283 | 400473813 | High Sign | HFTD Tier 2 | Distribution | 2005-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005284 | 400474135 | High Sign | HFTD Tier 2 | Distribution | 2005-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005285 | 400477015 | High Sign | HFTD Tier 2 | Distribution | 2005-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005286 | 400480438 | Molding | HFTD Tier 2 | Distribution | 2005-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005287 | 400491766 | High Sign | HFTD Tier 2 | Distribution | 2005-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005288 | 400491826 | High Sign | HFTD Tier 2 | Distribution | 2005-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005289 | 400141461 | High Sign | HFTD Tier 2 | Distribution | 2005-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005290 | 400236173 | High Sign | HFTD Tier 2 | Distribution | 2005-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005291 | 400241118 | High Sign | HFTD Tier 2 | Distribution | 2005-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005292 | 400244441 | High Sign | HFTD Tier 2 | Distribution | 2005-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005293 | 400268934 | Molding | HFTD Tier 3 | Distribution | 2005-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005294 | 400274563 | High Sign | HFTD Tier 3 | Distribution | 2005-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005295 | 400277374 | High Sign | HFTD Tier 2 | Distribution | 2005-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005296 | 400278474 | High Sign | HFTD Tier 2 | Distribution | 2005-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005297 | 400301800 | High Sign | HFTD Tier 2 | Distribution | 2005-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005298 | 400499646 | Guy | HFTD Tier 2 | Distribution | 2005-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005299 | 400500852 | High Sign | HFTD Tier 2 | Distribution | 2005-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005300 | 400054118 | High Sign | HFTD Tier 2 | Distribution | 2005-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005301 | 400247083 | High Sign | HFTD Tier 2 | Distribution | 2005-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005302 | 400260110 | High Sign | HFTD Tier 2 | Distribution | 2005-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005303 | 400260118 | High Sign | HFTD Tier 2 | Distribution | 2005-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005304 | 400302712 | High Sign | HFTD Tier 2 | Distribution | 2005-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005305 | 400306162 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2005-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005306 | 400310871 | High Sign | HFTD Tier 2 | Distribution | 2005-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005307 | 400313566 | High Sign | HFTD Tier 2 | Distribution | 2005-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005308 | 400451615 | High Sign | HFTD Tier 2 | Distribution | 2005-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005309 | 400458652 | High Sign | HFTD Tier 2 | Distribution | 2005-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005310 | 400466964 | High Sign | HFTD Tier 2 | Distribution | 2005-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005311 | 400470990 | High Sign | HFTD Tier 2 | Distribution | 2005-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005312 | 400499804 | Molding | HFTD Tier 2 | Distribution | 2005-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005313 | 400503622 | High Sign | HFTD Tier 2 | Distribution | 2005-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005314 | 400562886 | Guy | HFTD Tier 2 | Distribution | 2005-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005315 | 403048567 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2005-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005316 | 400526003 | High Sign | HFTD Tier 3 | Distribution | 2005-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005317 | 400165366 | Molding | HFTD Tier 2 | Distribution | 2005-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005318 | 400278214 | High Sign | HFTD Tier 2 | Distribution | 2005-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005319 | 400295054 | Molding | HFTD Tier 3 | Distribution | 2005-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005320 | 400331550 | Guy | HFTD Tier 2 | Distribution | 2005-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005321 | 400521436 | High Sign | HFTD Tier 2 | Distribution | 2005-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005322 | 400145408 | High Sign | HFTD Tier 2 | Distribution | 2005-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005323 | 400292087 | Guy | HFTD Tier 2 | Distribution | 2005-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005324 | 400366964 | High Sign | HFTD Tier 2 | Distribution | 2005-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005325 | 400392811 | High Sign | HFTD Tier 2 | Distribution | 2005-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005326 | 400332668 | Riser/Conduit | HFTD Tier 3 | Distribution | 2005-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005327 | 400365011 | Molding | HFTD Tier 3 | Distribution | 2005-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005328 | 400394345 | High Sign | HFTD Tier 2 | Distribution | 2005-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005329 | 400424745 | Molding | HFTD Tier 2 | Distribution | 2005-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005330 | 400546083 | High Sign | HFTD Tier 3 | Distribution | 2005-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005331 | 400550607 | Ground | HFTD Tier 3 | Distribution | 2005-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005332 | 400021384 | High Sign | HFTD Tier 3 | Distribution | 2005-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005333 | 400026732 | High Sign | HFTD Tier 3 | Distribution | 2005-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005334 | 400090493 | Molding | HFTD Tier 2 | Distribution | 2005-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005335 | 400227093 | Molding | HFTD Tier 2 | Distribution | 2005-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005336 | 400265556 | High Sign | HFTD Tier 2 | Distribution | 2005-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005337 | 400391850 | Molding | HFTD Tier 3 | Distribution | 2005-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005338 | 400428514 | Guy | HFTD Tier 3 | Distribution | 2005-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005339 | 400451868 | High Sign | HFTD Tier 2 | Distribution | 2005-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005340 | 400458056 | Molding | HFTD Tier 3 | Distribution | 2005-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005341 | 400079053 | High Sign | HFTD Tier 3 | Distribution | 2005-05-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005342 | 400383304 | High Sign | HFTD Tier 3 | Distribution | 2005-05-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005343 | 400388742 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-05-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005344 | 400390771 | Molding | HFTD Tier 3 | Distribution | 2005-05-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005345 | 400427563 | High Sign | HFTD Tier 3 | Distribution | 2005-05-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005346 | 400439660 | High Sign | HFTD Tier 3 | Distribution | 2005-05-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005347 | 400448259 | Guy | HFTD Tier 3 | Distribution | 2005-05-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005348 | 400103256 | Guy | HFTD Tier 3 | Distribution | 2005-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005349 | 400460043 | High Sign | HFTD Tier 3 | Distribution | 2005-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005350 | 400184665 | High Sign | HFTD Tier 2 | Distribution | 2005-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005351 | 400482944 | Molding | HFTD Tier 2 | Distribution | 2005-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005352 | 400458748 | Molding | HFTD Tier 3 | Distribution | 2005-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005353 | 400069444 | High Sign | HFTD Tier 3 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005354 | 400075991 | High Sign | HFTD Tier 3 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005355 | 400076022 | High Sign | HFTD Tier 3 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005356 | 400076054 | High Sign | HFTD Tier 3 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005357 | 400187530 | High Sign | HFTD Tier 2 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005358 | 400191222 | High Sign | HFTD Tier 2 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005359 | 400193714 | Molding | HFTD Tier 2 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005360 | 400266748 | High Sign | HFTD Tier 3 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005361 | 400270643 | High Sign | HFTD Tier 3 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005362 | 400445921 | High Sign | HFTD Tier 3 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005363 | 400452303 | Molding | HFTD Tier 2 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005364 | 400492186 | Molding | HFTD Tier 3 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005365 | 400493115 | Molding | HFTD Tier 2 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005366 | 400498003 | High Sign | HFTD Tier 2 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005367 | 400509854 | Molding | HFTD Tier 2 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005368 | 400526313 | Molding | HFTD Tier 2 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005369 | 400532963 | High Sign | HFTD Tier 3 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005370 | 400534841 | High Sign | HFTD Tier 3 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005371 | 400537565 | High Sign | HFTD Tier 3 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005372 | 400538136 | High Sign | HFTD Tier 3 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005373 | 400553780 | High Sign | HFTD Tier 3 | Distribution | 2005-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005374 | 400022889 | High Sign | HFTD Tier 3 | Distribution | 2005-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005375 | 400059034 | High Sign | HFTD Tier 2 | Distribution | 2005-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005376 | 400062029 | High Sign | HFTD Tier 2 | Distribution | 2005-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005377 | 400076522 | High Sign | HFTD Tier 3 | Distribution | 2005-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005378 | 400093109 | High Sign | HFTD Tier 3 | Distribution | 2005-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005379 | 400163243 | High Sign | HFTD Tier 3 | Distribution | 2005-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005380 | 400176259 | High Sign | HFTD Tier 3 | Distribution | 2005-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005381 | 400191341 | Molding | HFTD Tier 2 | Distribution | 2005-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005382 | 400269597 | High Sign | HFTD Tier 3 | Distribution | 2005-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005383 | 400274651 | High Sign | HFTD Tier 3 | Distribution | 2005-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005384 | 400475599 | High Sign | HFTD Tier 3 | Distribution | 2005-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005385 | 400492182 | High Sign | HFTD Tier 2 | Distribution | 2005-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005386 | 400517887 | High Sign | HFTD Tier 3 | Distribution | 2005-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005387 | 400519128 | High Sign | HFTD Tier 3 | Distribution | 2005-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005388 | 400522310 | High Sign | HFTD Tier 3 | Distribution | 2005-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005389 | 400532942 | High Sign | HFTD Tier 3 | Distribution | 2005-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005390 | 400539250 | High Sign | HFTD Tier 3 | Distribution | 2005-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005391 | 400117925 | Molding | HFTD Tier 2 | Distribution | 2005-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005392 | 400190263 | Molding | HFTD Tier 3 | Distribution | 2005-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005393 | 403048663 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2005-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005394 | 400051489 | High Sign | HFTD Tier 2 | Distribution | 2005-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005395 | 400274211 | High Sign | HFTD Tier 2 | Distribution | 2005-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005396 | 400071476 | Molding | HFTD Tier 3 | Distribution | 2005-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005397 | 400453488 | Molding | HFTD Tier 2 | Distribution | 2005-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005398 | 403048570 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2005-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005399 | 400139631 | Molding | HFTD Tier 2 | Distribution | 2005-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005400 | 400362232 | Molding | HFTD Tier 2 | Distribution | 2005-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005401 | 400998323 | Cable/Conductor | HFTD Tier 2 | Distribution | 2005-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005402 | 400181936 | High Sign | HFTD Tier 3 | Distribution | 2005-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005403 | 400258232 | High Sign | HFTD Tier 2 | Distribution | 2005-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005404 | 400265915 | Molding | HFTD Tier 2 | Distribution | 2005-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005405 | 400320239 | High Sign | HFTD Tier 2 | Distribution | 2005-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005406 | 400406403 | Riser/Conduit | HFTD Tier 3 | Distribution | 2005-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005407 | 400197393 | High Sign | HFTD Tier 3 | Distribution | 2005-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005408 | 400192827 | Molding | HFTD Tier 2 | Distribution | 2005-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005409 | 400218043 | Molding | HFTD Tier 2 | Distribution | 2005-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005410 | 400256216 | Molding | HFTD Tier 3 | Distribution | 2005-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005411 | 400381401 | Molding | HFTD Tier 2 | Distribution | 2005-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005412 | 400461148 | High Sign | HFTD Tier 3 | Distribution | 2005-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005413 | 400499748 | Molding | HFTD Tier 3 | Distribution | 2005-06-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005414 | 400348600 | Molding | HFTD Tier 3 | Distribution | 2005-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005415 | 400349774 | High Sign | HFTD Tier 3 | Distribution | 2005-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005416 | 400553904 | Molding | HFTD Tier 3 | Distribution | 2005-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005417 | 400555567 | Molding | HFTD Tier 3 | Distribution | 2005-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005418 | 400296396 | Hardware/Framing | HFTD Tier 3 | Distribution | 2005-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005419 | 400355890 | High Sign | HFTD Tier 3 | Distribution | 2005-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005420 | 400200658 | Molding | HFTD Tier 2 | Distribution | 2005-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005421 | 400349744 | Guy | HFTD Tier 2 | Distribution | 2005-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005422 | 400192000 | Molding | HFTD Tier 2 | Distribution | 2005-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005423 | 400194980 | High Sign | HFTD Tier 3 | Distribution | 2005-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005424 | 400436843 | High Sign | HFTD Tier 3 | Distribution | 2005-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005425 | 400394485 | Molding | HFTD Tier 2 | Distribution | 2005-06-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005426 | 400398165 | Guy | HFTD Tier 2 | Distribution | 2005-06-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005427 | 400633347 | Molding | HFTD Tier 3 | Distribution | 2005-06-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005428 | 400089235 | High Sign | HFTD Tier 3 | Distribution | 2005-06-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005429 | 400479201 | Molding | HFTD Tier 3 | Distribution | 2005-06-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005430 | 400170819 | High Sign | HFTD Tier 3 | Distribution | 2005-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005431 | 400496292 | High Sign | HFTD Tier 3 | Distribution | 2005-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005432 | 400325337 | Molding | HFTD Tier 2 | Distribution | 2005-06-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005433 | 403048881 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2005-06-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005434 | 400266497 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2005-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005435 | 400034121 | High Sign | HFTD Tier 3 | Distribution | 2005-07-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005436 | 400537169 | Guy | HFTD Tier 3 | Distribution | 2005-07-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005437 | 400027776 | Molding | HFTD Tier 2 | Distribution | 2005-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005438 | 400266451 | Molding | HFTD Tier 2 | Distribution | 2005-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005439 | 400239584 | Molding | HFTD Tier 2 | Distribution | 2005-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005440 | 400306955 | Molding | HFTD Tier 2 | Distribution | 2005-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005441 | 400329072 | High Sign | HFTD Tier 3 | Distribution | 2005-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005442 | 400532526 | Molding | HFTD Tier 2 | Distribution | 2005-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005443 | 400534816 | Molding | HFTD Tier 2 | Distribution | 2005-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005444 | 400035192 | High Sign | HFTD Tier 2 | Distribution | 2005-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005445 | 400551035 | Molding | HFTD Tier 2 | Distribution | 2005-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005446 | 400076156 | Molding | HFTD Tier 2 | Distribution | 2005-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005447 | 400113511 | Molding | HFTD Tier 2 | Distribution | 2005-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005448 | 400120501 | Guy | HFTD Tier 2 | Distribution | 2005-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005449 | 400122427 | Molding | HFTD Tier 2 | Distribution | 2005-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005450 | 400199619 | High Sign | HFTD Tier 2 | Distribution | 2005-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005451 | 400215580 | High Sign | HFTD Tier 2 | Distribution | 2005-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005452 | 400217118 | Molding | HFTD Tier 2 | Distribution | 2005-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005453 | 400242105 | High Sign | HFTD Tier 2 | Distribution | 2005-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005454 | 400243596 | Molding | HFTD Tier 2 | Distribution | 2005-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005455 | 400280575 | High Sign | HFTD Tier 2 | Distribution | 2005-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005456 | 400078011 | High Sign | HFTD Tier 2 | Distribution | 2005-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005457 | 400105123 | Guy | HFTD Tier 2 | Distribution | 2005-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005458 | 400126178 | High Sign | HFTD Tier 2 | Distribution | 2005-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005459 | 400291383 | Guy | HFTD Tier 2 | Distribution | 2005-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005460 | 400291415 | Molding | HFTD Tier 2 | Distribution | 2005-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005461 | 400163491 | Molding | HFTD Tier 2 | Distribution | 2005-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005462 | 400166882 | High Sign | HFTD Tier 2 | Distribution | 2005-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005463 | 400140495 | High Sign | HFTD Tier 2 | Distribution | 2005-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005464 | 400176095 | High Sign | HFTD Tier 3 | Distribution | 2005-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005465 | 400224465 | Molding | HFTD Tier 3 | Distribution | 2005-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005466 | 400352071 | High Sign | HFTD Tier 2 | Distribution | 2005-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005467 | 400354019 | Molding | HFTD Tier 3 | Distribution | 2005-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005468 | 400193480 | High Sign | HFTD Tier 3 | Distribution | 2005-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005469 | 400209751 | Molding | HFTD Tier 2 | Distribution | 2005-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005470 | 400249455 | Molding | HFTD Tier 2 | Distribution | 2005-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005471 | 400365686 | Guy | HFTD Tier 3 | Distribution | 2005-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005472 | 400179977 | High Sign | HFTD Tier 2 | Distribution | 2005-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005473 | 400183656 | High Sign | HFTD Tier 2 | Distribution | 2005-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005474 | 400187292 | High Sign | HFTD Tier 2 | Distribution | 2005-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005475 | 400229970 | High Sign | HFTD Tier 2 | Distribution | 2005-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005476 | 400242830 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005477 | 400392682 | Guy | HFTD Tier 2 | Distribution | 2005-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005478 | 400406551 | High Sign | HFTD Tier 2 | Distribution | 2005-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005479 | 400185928 | High Sign | HFTD Tier 2 | Distribution | 2005-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005480 | 400203343 | High Sign | HFTD Tier 2 | Distribution | 2005-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005481 | 400241941 | Guy | HFTD Tier 2 | Distribution | 2005-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005482 | 400246453 | High Sign | HFTD Tier 3 | Distribution | 2005-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005483 | 400252164 | Molding | HFTD Tier 2 | Distribution | 2005-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005484 | 400418472 | Cable/Conductor | HFTD Tier 2 | Distribution | 2005-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005485 | 400422099 | High Sign | HFTD Tier 2 | Distribution | 2005-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005486 | 400489430 | Molding | HFTD Tier 3 | Distribution | 2005-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005487 | 400496714 | High Sign | HFTD Tier 3 | Distribution | 2005-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005488 | 400190687 | High Sign | HFTD Tier 2 | Distribution | 2005-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005489 | 400219836 | High Sign | HFTD Tier 2 | Distribution | 2005-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005490 | 400235505 | High Sign | HFTD Tier 2 | Distribution | 2005-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005491 | 400253021 | High Sign | HFTD Tier 2 | Distribution | 2005-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005492 | 400257264 | High Sign | HFTD Tier 2 | Distribution | 2005-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005493 | 400443358 | High Sign | HFTD Tier 2 | Distribution | 2005-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005494 | 400308481 | High Sign | HFTD Tier 2 | Distribution | 2005-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005495 | 401472301 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005496 | 400233459 | High Sign | HFTD Tier 2 | Distribution | 2005-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005497 | 400234704 | Guy | HFTD Tier 2 | Distribution | 2005-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005498 | 400243046 | Molding | HFTD Tier 2 | Distribution | 2005-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005499 | 400292661 | Molding | HFTD Tier 2 | Distribution | 2005-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005500 | 400243676 | High Sign | HFTD Tier 3 | Distribution | 2005-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005501 | 400252952 | Molding | HFTD Tier 2 | Distribution | 2005-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005502 | 400263296 | Molding | HFTD Tier 2 | Distribution | 2005-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005503 | 400315400 | Molding | HFTD Tier 2 | Distribution | 2005-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005504 | 400337329 | High Sign | HFTD Tier 2 | Distribution | 2005-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005505 | 400482164 | High Sign | HFTD Tier 2 | Distribution | 2005-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005506 | 400232608 | High Sign | HFTD Tier 2 | Distribution | 2005-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005507 | 400275860 | High Sign | HFTD Tier 2 | Distribution | 2005-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005508 | 400277197 | High Sign | HFTD Tier 2 | Distribution | 2005-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005509 | 400280460 | High Sign | HFTD Tier 3 | Distribution | 2005-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005510 | 400331852 | High Sign | HFTD Tier 2 | Distribution | 2005-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005511 | 400333684 | High Sign | HFTD Tier 2 | Distribution | 2005-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005512 | 400340092 | High Sign | HFTD Tier 2 | Distribution | 2005-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005513 | 400348036 | High Sign | HFTD Tier 2 | Distribution | 2005-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005514 | 400357458 | High Sign | HFTD Tier 2 | Distribution | 2005-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005515 | 400361963 | High Sign | HFTD Tier 2 | Distribution | 2005-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005516 | 400490372 | High Sign | HFTD Tier 2 | Distribution | 2005-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005517 | 400495267 | High Sign | HFTD Tier 3 | Distribution | 2005-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005518 | 400500615 | High Sign | HFTD Tier 3 | Distribution | 2005-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005519 | 400188814 | Molding | HFTD Tier 2 | Distribution | 2005-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005520 | 400237389 | High Sign | HFTD Tier 3 | Distribution | 2005-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005521 | 400241106 | Molding | HFTD Tier 3 | Distribution | 2005-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005522 | 400257725 | Molding | HFTD Tier 2 | Distribution | 2005-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005523 | 400258953 | High Sign | HFTD Tier 3 | Distribution | 2005-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005524 | 400298313 | High Sign | HFTD Tier 2 | Distribution | 2005-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005525 | 400306802 | High Sign | HFTD Tier 2 | Distribution | 2005-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005526 | 400316395 | High Sign | HFTD Tier 2 | Distribution | 2005-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005527 | 400377878 | High Sign | HFTD Tier 2 | Distribution | 2005-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005528 | 400379614 | High Sign | HFTD Tier 2 | Distribution | 2005-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005529 | 400383914 | High Sign | HFTD Tier 2 | Distribution | 2005-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005530 | 400391091 | High Sign | HFTD Tier 2 | Distribution | 2005-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005531 | 400394974 | High Sign | HFTD Tier 2 | Distribution | 2005-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005532 | 400515762 | High Sign | HFTD Tier 2 | Distribution | 2005-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005533 | 400517599 | High Sign | HFTD Tier 2 | Distribution | 2005-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005534 | 403045985 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005535 | 400372951 | High Sign | HFTD Tier 2 | Distribution | 2005-07-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005536 | 400382642 | High Sign | HFTD Tier 2 | Distribution | 2005-07-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005537 | 400395034 | High Sign | HFTD Tier 2 | Distribution | 2005-07-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005538 | 400360288 | Guy | HFTD Tier 3 | Distribution | 2005-08-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005539 | 400432387 | Guy | HFTD Tier 3 | Distribution | 2005-08-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005540 | 400538075 | Guy | HFTD Tier 3 | Distribution | 2005-08-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005541 | 400029939 | Molding | HFTD Tier 3 | Distribution | 2005-08-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005542 | 400352282 | Molding | HFTD Tier 3 | Distribution | 2005-08-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005543 | 400428197 | Molding | HFTD Tier 3 | Distribution | 2005-08-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005544 | 400433251 | Molding | HFTD Tier 3 | Distribution | 2005-08-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005545 | 400435480 | High Sign | HFTD Tier 3 | Distribution | 2005-08-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005546 | 400437207 | High Sign | HFTD Tier 2 | Distribution | 2005-08-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005547 | 400441385 | High Sign | HFTD Tier 3 | Distribution | 2005-08-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005548 | 400538014 | High Sign | HFTD Tier 3 | Distribution | 2005-08-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005549 | 400554349 | Molding | HFTD Tier 3 | Distribution | 2005-08-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005550 | 400486204 | Molding | HFTD Tier 2 | Distribution | 2005-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005551 | 400414550 | High Sign | HFTD Tier 2 | Distribution | 2005-08-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005552 | 400417050 | High Sign | HFTD Tier 2 | Distribution | 2005-08-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005553 | 400478002 | High Sign | HFTD Tier 2 | Distribution | 2005-08-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005554 | 400494938 | High Sign | HFTD Tier 3 | Distribution | 2005-08-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005555 | 400496254 | Guy | HFTD Tier 3 | Distribution | 2005-08-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005556 | 400394358 | Crossarm | HFTD Tier 3 | Distribution | 2005-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005557 | 400522969 | Molding | HFTD Tier 3 | Distribution | 2005-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005558 | 400526209 | Molding | HFTD Tier 3 | Distribution | 2005-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005559 | 400527346 | Molding | HFTD Tier 3 | Distribution | 2005-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005560 | 400075899 | High Sign | HFTD Tier 3 | Distribution | 2005-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005561 | 400457098 | High Sign | HFTD Tier 3 | Distribution | 2005-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005562 | 400476338 | Molding | HFTD Tier 2 | Distribution | 2005-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005563 | 400522999 | High Sign | HFTD Tier 3 | Distribution | 2005-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005564 | 400524290 | Molding | HFTD Tier 3 | Distribution | 2005-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005565 | 400199303 | High Sign | HFTD Tier 2 | Distribution | 2005-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005566 | 400207709 | High Sign | HFTD Tier 3 | Distribution | 2005-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005567 | 400468058 | Guy | HFTD Tier 2 | Distribution | 2005-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005568 | 400516305 | High Sign | HFTD Tier 2 | Distribution | 2005-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005569 | 400520330 | High Sign | HFTD Tier 2 | Distribution | 2005-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005570 | 400215842 | Molding | HFTD Tier 3 | Distribution | 2005-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005571 | 400492944 | Cable/Conductor | HFTD Tier 3 | Distribution | 2005-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005572 | 400502231 | Molding | HFTD Tier 3 | Distribution | 2005-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005573 | 400502956 | Molding | HFTD Tier 2 | Distribution | 2005-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005574 | 400531111 | Molding | HFTD Tier 2 | Distribution | 2005-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005575 | 400531605 | Guy | HFTD Tier 3 | Distribution | 2005-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005576 | 400547363 | Molding | HFTD Tier 3 | Distribution | 2005-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005577 | 400242575 | High Sign | HFTD Tier 2 | Distribution | 2005-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005578 | 400516342 | Molding | HFTD Tier 3 | Distribution | 2005-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005579 | 400200601 | High Sign | HFTD Tier 2 | Distribution | 2005-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005580 | 400189859 | Molding | HFTD Tier 3 | Distribution | 2005-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005581 | 400513887 | Molding | HFTD Tier 3 | Distribution | 2005-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005582 | 400593314 | Cable/Conductor | HFTD Tier 2 | Distribution | 2005-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005583 | 400970466 | Molding | HFTD Tier 2 | Distribution | 2005-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005584 | 400045303 | High Sign | HFTD Tier 3 | Distribution | 2005-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005585 | 400046347 | High Sign | HFTD Tier 3 | Distribution | 2005-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005586 | 400048963 | Molding | HFTD Tier 3 | Distribution | 2005-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005587 | 400053176 | Molding | HFTD Tier 3 | Distribution | 2005-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005588 | 400060220 | Molding | HFTD Tier 3 | Distribution | 2005-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005589 | 400069249 | Molding | HFTD Tier 3 | Distribution | 2005-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005590 | 400089965 | Molding | HFTD Tier 3 | Distribution | 2005-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005591 | 400207611 | Molding | HFTD Tier 3 | Distribution | 2005-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005592 | 400212555 | Molding | HFTD Tier 3 | Distribution | 2005-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005593 | 400214040 | High Sign | HFTD Tier 3 | Distribution | 2005-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005594 | 400515120 | High Sign | HFTD Tier 3 | Distribution | 2005-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005595 | 400518111 | Guy | HFTD Tier 3 | Distribution | 2005-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005596 | 400112886 | High Sign | HFTD Tier 3 | Distribution | 2005-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005597 | 400748280 | High Sign | HFTD Tier 2 | Distribution | 2005-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005598 | 400023251 | High Sign | HFTD Tier 3 | Distribution | 2005-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005599 | 400112153 | High Sign | HFTD Tier 3 | Distribution | 2005-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005600 | 400118536 | Guy | HFTD Tier 3 | Distribution | 2005-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005601 | 400153286 | Molding | HFTD Tier 3 | Distribution | 2005-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005602 | 400247664 | High Sign | HFTD Tier 3 | Distribution | 2005-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005603 | 400309897 | Hardware/Framing | HFTD Tier 3 | Distribution | 2005-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005604 | 400085476 | Molding | HFTD Tier 2 | Distribution | 2005-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005605 | 400117157 | Insulator | HFTD Tier 2 | Distribution | 2005-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005606 | 400132767 | High Sign | HFTD Tier 3 | Distribution | 2005-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005607 | 400133369 | High Sign | HFTD Tier 3 | Distribution | 2005-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005608 | 400140528 | Molding | HFTD Tier 3 | Distribution | 2005-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005609 | 400145700 | Molding | HFTD Tier 2 | Distribution | 2005-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005610 | 400275035 | High Sign | HFTD Tier 3 | Distribution | 2005-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005611 | 400548723 | Molding | HFTD Tier 2 | Distribution | 2005-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005612 | 400146102 | Molding | HFTD Tier 2 | Distribution | 2005-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005613 | 400227268 | Molding | HFTD Tier 2 | Distribution | 2005-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005614 | 400427826 | Molding | HFTD Tier 3 | Distribution | 2005-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005615 | 400454335 | Molding | HFTD Tier 2 | Distribution | 2005-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005616 | 400292088 | High Sign | HFTD Tier 2 | Distribution | 2005-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005617 | 400344225 | High Sign | HFTD Tier 2 | Distribution | 2005-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005618 | 400281524 | High Sign | HFTD Tier 2 | Distribution | 2005-08-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005619 | 400229914 | Molding | HFTD Tier 2 | Distribution | 2005-08-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005620 | 400235074 | High Sign | HFTD Tier 2 | Distribution | 2005-08-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005621 | 400183037 | Molding | HFTD Tier 2 | Distribution | 2005-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005622 | 400402055 | High Sign | HFTD Tier 2 | Distribution | 2005-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005623 | 400234063 | High Sign | HFTD Tier 2 | Distribution | 2005-08-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005624 | 400240721 | High Sign | HFTD Tier 2 | Distribution | 2005-08-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005625 | 400259589 | High Sign | HFTD Tier 2 | Distribution | 2005-08-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005626 | 400277149 | Molding | HFTD Tier 2 | Distribution | 2005-08-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005627 | 400279611 | Molding | HFTD Tier 2 | Distribution | 2005-08-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005628 | 400414065 | High Sign | HFTD Tier 2 | Distribution | 2005-08-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005629 | 400429951 | High Sign | HFTD Tier 2 | Distribution | 2005-08-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005630 | 400207146 | Molding | HFTD Tier 2 | Distribution | 2005-08-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005631 | 400282549 | Molding | HFTD Tier 2 | Distribution | 2005-08-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005632 | 400442104 | Molding | HFTD Tier 2 | Distribution | 2005-08-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005633 | 400194429 | Molding | HFTD Tier 2 | Distribution | 2005-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005634 | 400266630 | High Sign | HFTD Tier 3 | Distribution | 2005-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005635 | 400325307 | High Sign | HFTD Tier 3 | Distribution | 2005-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005636 | 401478399 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005637 | 400327329 | Guy | HFTD Tier 3 | Distribution | 2005-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005638 | 400470489 | Molding | HFTD Tier 3 | Distribution | 2005-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005639 | 400287435 | High Sign | HFTD Tier 3 | Distribution | 2005-09-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005640 | 400336076 | Molding | HFTD Tier 3 | Distribution | 2005-09-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005641 | 400343561 | Cable/Conductor | HFTD Tier 3 | Distribution | 2005-09-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005642 | 400492698 | Molding | HFTD Tier 2 | Distribution | 2005-09-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005643 | 400500146 | Molding | HFTD Tier 3 | Distribution | 2005-09-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005644 | 400281902 | High Sign | HFTD Tier 2 | Distribution | 2005-09-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005645 | 400302131 | High Sign | HFTD Tier 3 | Distribution | 2005-09-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005646 | 400383398 | High Sign | HFTD Tier 3 | Distribution | 2005-09-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005647 | 400400491 | Guy | HFTD Tier 3 | Distribution | 2005-09-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005648 | 400348492 | Molding | HFTD Tier 2 | Distribution | 2005-09-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005649 | 400349077 | Molding | HFTD Tier 3 | Distribution | 2005-09-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005650 | 400350285 | High Sign | HFTD Tier 2 | Distribution | 2005-09-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005651 | 400418641 | Molding | HFTD Tier 3 | Distribution | 2005-09-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005652 | 400462345 | Riser/Conduit | HFTD Tier 3 | Distribution | 2005-09-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005653 | 400535067 | Molding | HFTD Tier 3 | Distribution | 2005-09-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005654 | 400536036 | Molding | HFTD Tier 3 | Distribution | 2005-09-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005655 | 400539885 | Guy | HFTD Tier 2 | Distribution | 2005-09-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005656 | 400068408 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005657 | 400076497 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005658 | 400143397 | Guy | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005659 | 400144429 | High Sign | HFTD Tier 3 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005660 | 400146209 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005661 | 400147982 | Molding | HFTD Tier 3 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005662 | 400148040 | High Sign | HFTD Tier 3 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005663 | 400156084 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005664 | 400156200 | High Sign | HFTD Tier 3 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005665 | 400332541 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005666 | 400343300 | High Sign | HFTD Tier 3 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005667 | 400344378 | Molding | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005668 | 400347043 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005669 | 400355127 | Guy | HFTD Tier 3 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005670 | 400357948 | Riser/Conduit | HFTD Tier 3 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005671 | 400398371 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005672 | 400398401 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005673 | 400399274 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005674 | 400401542 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005675 | 400405276 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005676 | 400410947 | Insulator | HFTD Tier 3 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005677 | 400411551 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005678 | 400415493 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005679 | 400419244 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005680 | 400424838 | Molding | HFTD Tier 3 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005681 | 400470049 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005682 | 400481656 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005683 | 400482294 | High Sign | HFTD Tier 3 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005684 | 400486172 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005685 | 400488239 | Guy | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005686 | 400490337 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005687 | 400491784 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005688 | 400520124 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005689 | 400520660 | Molding | HFTD Tier 3 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005690 | 400521370 | High Sign | HFTD Tier 3 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005691 | 400522003 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005692 | 400523342 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005693 | 400524881 | Molding | HFTD Tier 3 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005694 | 400537802 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005695 | 400539401 | High Sign | HFTD Tier 2 | Distribution | 2005-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005696 | 400092842 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005697 | 400139040 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005698 | 400142342 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005699 | 400143223 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005700 | 400143252 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005701 | 400143318 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005702 | 400143342 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005703 | 400147334 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005704 | 400147428 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005705 | 400147465 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005706 | 400147490 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005707 | 400455445 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005708 | 400481615 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005709 | 400484543 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005710 | 400486702 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005711 | 400486731 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005712 | 400489070 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005713 | 400510678 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005714 | 400517073 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005715 | 400517113 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005716 | 400517124 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005717 | 400518233 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005718 | 400518236 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005719 | 400518262 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005720 | 400519175 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005721 | 400520103 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005722 | 400520114 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005723 | 400520690 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005724 | 400528748 | Molding | HFTD Tier 3 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005725 | 400532826 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005726 | 400532855 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005727 | 400535012 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005728 | 400535061 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005729 | 400535092 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005730 | 400535122 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005731 | 400537041 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005732 | 400537682 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005733 | 400537773 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005734 | 400540142 | High Sign | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005735 | 400540233 | Molding | HFTD Tier 2 | Distribution | 2005-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005736 | 400095754 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005737 | 400111567 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005738 | 400111630 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005739 | 400111952 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005740 | 400116791 | Insulator | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005741 | 400119749 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005742 | 400120032 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005743 | 400121921 | Molding | HFTD Tier 3 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005744 | 400122315 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005745 | 400123537 | Molding | HFTD Tier 3 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005746 | 400123906 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005747 | 400123935 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005748 | 400167515 | Molding | HFTD Tier 3 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005749 | 400183604 | Insulator | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005750 | 400183839 | High Sign | HFTD Tier 3 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005751 | 400262725 | Molding | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005752 | 400446893 | Hardware/Framing | HFTD Tier 3 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005753 | 400461679 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005754 | 400467998 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005755 | 400478547 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005756 | 400482965 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005757 | 400484361 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005758 | 400489050 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005759 | 400508542 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005760 | 400509071 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005761 | 400510228 | Hardware/Framing | HFTD Tier 3 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005762 | 400510698 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005763 | 400518253 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005764 | 400519586 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005765 | 400520281 | Guy | HFTD Tier 3 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005766 | 400523447 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005767 | 400524010 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005768 | 400524746 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005769 | 400525427 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005770 | 400525738 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005771 | 400526626 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005772 | 400529093 | Molding | HFTD Tier 3 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005773 | 400532551 | Molding | HFTD Tier 3 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005774 | 400540174 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005775 | 400545597 | High Sign | HFTD Tier 3 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005776 | 400553365 | Hardware/Framing | HFTD Tier 3 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005777 | 400940371 | High Sign | HFTD Tier 2 | Distribution | 2005-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005778 | 400038629 | High Sign | HFTD Tier 2 | Distribution | 2005-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005779 | 400159172 | High Sign | HFTD Tier 2 | Distribution | 2005-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005780 | 400192721 | High Sign | HFTD Tier 2 | Distribution | 2005-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005781 | 400503093 | High Sign | HFTD Tier 2 | Distribution | 2005-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005782 | 400509366 | High Sign | HFTD Tier 3 | Distribution | 2005-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005783 | 400546511 | High Sign | HFTD Tier 3 | Distribution | 2005-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005784 | 400744111 | High Sign | HFTD Tier 2 | Distribution | 2005-09-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005785 | 400898012 | Molding | HFTD Tier 2 | Distribution | 2005-09-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005786 | 400179774 | High Sign | HFTD Tier 2 | Distribution | 2005-09-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005787 | 400503839 | High Sign | HFTD Tier 2 | Distribution | 2005-09-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005788 | 400506671 | Guy | HFTD Tier 2 | Distribution | 2005-09-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005789 | 400509970 | Molding | HFTD Tier 3 | Distribution | 2005-09-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005790 | 400511228 | High Sign | HFTD Tier 2 | Distribution | 2005-09-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005791 | 400535671 | High Sign | HFTD Tier 2 | Distribution | 2005-09-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005792 | 400540143 | High Sign | HFTD Tier 2 | Distribution | 2005-09-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005793 | 400540173 | High Sign | HFTD Tier 2 | Distribution | 2005-09-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005794 | 400540204 | High Sign | HFTD Tier 2 | Distribution | 2005-09-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005795 | 400543615 | High Sign | HFTD Tier 3 | Distribution | 2005-09-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005796 | 400549531 | High Sign | HFTD Tier 2 | Distribution | 2005-09-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005797 | 400557328 | High Sign | HFTD Tier 2 | Distribution | 2005-09-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005798 | 400065697 | High Sign | HFTD Tier 3 | Distribution | 2005-09-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005799 | 400070051 | High Sign | HFTD Tier 3 | Distribution | 2005-09-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005800 | 400197610 | Molding | HFTD Tier 2 | Distribution | 2005-09-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005801 | 400204593 | Molding | HFTD Tier 3 | Distribution | 2005-09-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005802 | 400222891 | High Sign | HFTD Tier 3 | Distribution | 2005-09-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005803 | 400521111 | High Sign | HFTD Tier 3 | Distribution | 2005-09-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005804 | 400536894 | High Sign | HFTD Tier 3 | Distribution | 2005-09-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005805 | 400592825 | Molding | HFTD Tier 2 | Distribution | 2005-09-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005806 | 400595859 | High Sign | HFTD Tier 3 | Distribution | 2005-09-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005807 | 401481425 | Cable/Conductor | HFTD Tier 2 | Distribution | 2005-09-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005808 | 400058685 | Molding | HFTD Tier 2 | Distribution | 2005-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005809 | 400068978 | High Sign | HFTD Tier 2 | Distribution | 2005-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005810 | 400079448 | High Sign | HFTD Tier 2 | Distribution | 2005-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005811 | 400279704 | Molding | HFTD Tier 3 | Distribution | 2005-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005812 | 400384361 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005813 | 400531476 | Guy | HFTD Tier 3 | Distribution | 2005-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005814 | 400547129 | High Sign | HFTD Tier 3 | Distribution | 2005-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005815 | 400553302 | High Sign | HFTD Tier 3 | Distribution | 2005-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005816 | 400595852 | Molding | HFTD Tier 2 | Distribution | 2005-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005817 | 400597108 | High Sign | HFTD Tier 2 | Distribution | 2005-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005818 | 400603538 | Molding | HFTD Tier 2 | Distribution | 2005-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005819 | 400627753 | High Sign | HFTD Tier 3 | Distribution | 2005-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005820 | 400027600 | High Sign | HFTD Tier 3 | Distribution | 2005-09-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005821 | 400077315 | High Sign | HFTD Tier 2 | Distribution | 2005-09-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005822 | 400235107 | High Sign | HFTD Tier 2 | Distribution | 2005-09-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005823 | 400534939 | Riser/Conduit | HFTD Tier 2 | Distribution | 2005-09-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005824 | 400548819 | Molding | HFTD Tier 2 | Distribution | 2005-09-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005825 | 400643478 | Molding | HFTD Tier 3 | Distribution | 2005-09-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005826 | 400267993 | Molding | HFTD Tier 3 | Distribution | 2005-09-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005827 | 400280959 | Guy | HFTD Tier 3 | Distribution | 2005-09-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005828 | 400292208 | Molding | HFTD Tier 2 | Distribution | 2005-09-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005829 | 400562538 | High Sign | HFTD Tier 3 | Distribution | 2005-09-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005830 | 400037343 | Molding | HFTD Tier 2 | Distribution | 2005-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005831 | 400057390 | High Sign | HFTD Tier 2 | Distribution | 2005-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005832 | 400071390 | Guy | HFTD Tier 3 | Distribution | 2005-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005833 | 400073578 | High Sign | HFTD Tier 3 | Distribution | 2005-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005834 | 400074680 | Molding | HFTD Tier 3 | Distribution | 2005-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005835 | 400077842 | High Sign | HFTD Tier 3 | Distribution | 2005-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005836 | 400122130 | High Sign | HFTD Tier 2 | Distribution | 2005-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005837 | 400149113 | Guy | HFTD Tier 3 | Distribution | 2005-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005838 | 400161699 | Molding | HFTD Tier 3 | Distribution | 2005-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005839 | 400312342 | Guy | HFTD Tier 3 | Distribution | 2005-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005840 | 400317393 | Guy | HFTD Tier 3 | Distribution | 2005-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005841 | 400680256 | High Sign | HFTD Tier 3 | Distribution | 2005-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005842 | 400685114 | High Sign | HFTD Tier 3 | Distribution | 2005-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005843 | 400686503 | Molding | HFTD Tier 3 | Distribution | 2005-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005844 | 400688397 | High Sign | HFTD Tier 3 | Distribution | 2005-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005845 | 400055523 | Hardware/Framing | HFTD Tier 2 | Distribution | 2005-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005846 | 400057339 | Guy | HFTD Tier 3 | Distribution | 2005-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005847 | 400094410 | High Sign | HFTD Tier 2 | Distribution | 2005-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005848 | 400179233 | High Sign | HFTD Tier 2 | Distribution | 2005-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005849 | 400310072 | Molding | HFTD Tier 2 | Distribution | 2005-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005850 | 400312281 | High Sign | HFTD Tier 2 | Distribution | 2005-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005851 | 400674025 | High Sign | HFTD Tier 2 | Distribution | 2005-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005852 | 400101059 | High Sign | HFTD Tier 2 | Distribution | 2005-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005853 | 400107411 | Cable/Conductor | HFTD Tier 3 | Distribution | 2005-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005854 | 400115349 | High Sign | HFTD Tier 3 | Distribution | 2005-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005855 | 400115440 | High Sign | HFTD Tier 2 | Distribution | 2005-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005856 | 400197116 | High Sign | HFTD Tier 3 | Distribution | 2005-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005857 | 400353585 | High Sign | HFTD Tier 2 | Distribution | 2005-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005858 | 400387222 | Molding | HFTD Tier 3 | Distribution | 2005-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005859 | 400430970 | Molding | HFTD Tier 3 | Distribution | 2005-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005860 | 400696752 | Molding | HFTD Tier 3 | Distribution | 2005-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005861 | 400718334 | High Sign | HFTD Tier 3 | Distribution | 2005-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005862 | 400728115 | High Sign | HFTD Tier 2 | Distribution | 2005-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005863 | 400730180 | High Sign | HFTD Tier 3 | Distribution | 2005-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005864 | 400104549 | High Sign | HFTD Tier 2 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005865 | 400125139 | Cable/Conductor | HFTD Tier 3 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005866 | 400129471 | Cable/Conductor | HFTD Tier 3 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005867 | 400135249 | Molding | HFTD Tier 3 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005868 | 400153570 | Molding | HFTD Tier 3 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005869 | 400157660 | High Sign | HFTD Tier 3 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005870 | 400177056 | High Sign | HFTD Tier 3 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005871 | 400189265 | Molding | HFTD Tier 3 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005872 | 400201359 | Molding | HFTD Tier 2 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005873 | 400202608 | High Sign | HFTD Tier 3 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005874 | 400203502 | Guy | HFTD Tier 3 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005875 | 400207297 | High Sign | HFTD Tier 3 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005876 | 400363243 | Molding | HFTD Tier 3 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005877 | 400381378 | High Sign | HFTD Tier 3 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005878 | 400710348 | High Sign | HFTD Tier 2 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005879 | 400717606 | High Sign | HFTD Tier 2 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005880 | 400730407 | Guy | HFTD Tier 2 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005881 | 400736267 | High Sign | HFTD Tier 3 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005882 | 400738631 | High Sign | HFTD Tier 3 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005883 | 400778188 | Molding | HFTD Tier 3 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005884 | 400783572 | Molding | HFTD Tier 3 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005885 | 400783576 | Molding | HFTD Tier 3 | Distribution | 2005-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005886 | 400144080 | High Sign | HFTD Tier 2 | Distribution | 2005-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005887 | 400213744 | High Sign | HFTD Tier 3 | Distribution | 2005-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005888 | 400215108 | High Sign | HFTD Tier 2 | Distribution | 2005-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005889 | 400217838 | High Sign | HFTD Tier 2 | Distribution | 2005-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005890 | 400224822 | High Sign | HFTD Tier 2 | Distribution | 2005-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005891 | 400320840 | Molding | HFTD Tier 3 | Distribution | 2005-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005892 | 400387363 | High Sign | HFTD Tier 2 | Distribution | 2005-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005893 | 400428854 | Molding | HFTD Tier 3 | Distribution | 2005-10-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005894 | 400768026 | Molding | HFTD Tier 3 | Distribution | 2005-10-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005895 | 400782111 | High Sign | HFTD Tier 3 | Distribution | 2005-10-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005896 | 400178803 | Cable/Conductor | HFTD Tier 3 | Distribution | 2005-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005897 | 400270333 | Guy | HFTD Tier 3 | Distribution | 2005-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005898 | 400296938 | High Sign | HFTD Tier 3 | Distribution | 2005-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005899 | 400796291 | High Sign | HFTD Tier 3 | Distribution | 2005-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005900 | 400187474 | Molding | HFTD Tier 3 | Distribution | 2005-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005901 | 400275866 | Guy | HFTD Tier 3 | Distribution | 2005-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005902 | 400310102 | High Sign | HFTD Tier 3 | Distribution | 2005-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005903 | 400320305 | Molding | HFTD Tier 2 | Distribution | 2005-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005904 | 400445467 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005905 | 400454945 | High Sign | HFTD Tier 3 | Distribution | 2005-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005906 | 400459656 | High Sign | HFTD Tier 2 | Distribution | 2005-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005907 | 400465230 | High Sign | HFTD Tier 3 | Distribution | 2005-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005908 | 400788757 | Molding | HFTD Tier 3 | Distribution | 2005-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005909 | 400807836 | High Sign | HFTD Tier 3 | Distribution | 2005-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005910 | 400246667 | High Sign | HFTD Tier 3 | Distribution | 2005-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005911 | 400278393 | Molding | HFTD Tier 2 | Distribution | 2005-10-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005912 | 400364356 | High Sign | HFTD Tier 3 | Distribution | 2005-10-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005913 | 400263172 | Molding | HFTD Tier 3 | Distribution | 2005-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005914 | 400278488 | Molding | HFTD Tier 3 | Distribution | 2005-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005915 | 400298891 | Molding | HFTD Tier 2 | Distribution | 2005-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005916 | 400409436 | Molding | HFTD Tier 2 | Distribution | 2005-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005917 | 400502190 | High Sign | HFTD Tier 3 | Distribution | 2005-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005918 | 400515086 | Guy | HFTD Tier 3 | Distribution | 2005-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005919 | 400515198 | High Sign | HFTD Tier 3 | Distribution | 2005-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005920 | 400522091 | Molding | HFTD Tier 2 | Distribution | 2005-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005921 | 400523388 | Molding | HFTD Tier 2 | Distribution | 2005-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005922 | 400850689 | Insulator | HFTD Tier 2 | Distribution | 2005-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005923 | 400873055 | High Sign | HFTD Tier 2 | Distribution | 2005-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005924 | 400896332 | Molding | HFTD Tier 2 | Distribution | 2005-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005925 | 400284004 | Guy | HFTD Tier 3 | Distribution | 2005-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005926 | 400409516 | Molding | HFTD Tier 2 | Distribution | 2005-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005927 | 400411496 | Molding | HFTD Tier 2 | Distribution | 2005-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005928 | 400898508 | Molding | HFTD Tier 2 | Distribution | 2005-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005929 | 400900920 | Molding | HFTD Tier 2 | Distribution | 2005-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005930 | 400994780 | Cable/Conductor | HFTD Tier 2 | Distribution | 2005-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005931 | 400415678 | Molding | HFTD Tier 3 | Distribution | 2005-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005932 | 400355360 | High Sign | HFTD Tier 3 | Distribution | 2005-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005933 | 400259186 | Molding | HFTD Tier 3 | Distribution | 2005-10-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005934 | 400333432 | Molding | HFTD Tier 3 | Distribution | 2005-10-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005935 | 400336969 | Molding | HFTD Tier 3 | Distribution | 2005-10-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005936 | 400562098 | High Sign | HFTD Tier 3 | Distribution | 2005-10-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005937 | 400366263 | High Sign | HFTD Tier 2 | Distribution | 2005-10-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005938 | 400399182 | Guy | HFTD Tier 3 | Distribution | 2005-10-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005939 | 400467819 | Molding | HFTD Tier 2 | Distribution | 2005-10-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005940 | 400591446 | Guy | HFTD Tier 3 | Distribution | 2005-10-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005941 | 400384542 | Molding | HFTD Tier 3 | Distribution | 2005-10-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005942 | 400470625 | High Sign | HFTD Tier 2 | Distribution | 2005-10-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005943 | 400495763 | High Sign | HFTD Tier 3 | Distribution | 2005-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005944 | 400581650 | High Sign | HFTD Tier 3 | Distribution | 2005-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005945 | 400952264 | Guy | HFTD Tier 3 | Distribution | 2005-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005946 | 400434187 | High Sign | HFTD Tier 2 | Distribution | 2005-10-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005947 | 400509611 | High Sign | HFTD Tier 2 | Distribution | 2005-10-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005948 | 400628139 | Molding | HFTD Tier 2 | Distribution | 2005-10-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005949 | 400654882 | High Sign | HFTD Tier 3 | Distribution | 2005-10-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005950 | 400963771 | Molding | HFTD Tier 3 | Distribution | 2005-10-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005951 | 400965642 | Molding | HFTD Tier 2 | Distribution | 2005-10-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005952 | 400445799 | Molding | HFTD Tier 3 | Distribution | 2005-10-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005953 | 400963784 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-10-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005954 | 400477923 | Molding | HFTD Tier 3 | Distribution | 2005-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005955 | 400533634 | Molding | HFTD Tier 3 | Distribution | 2005-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005956 | 400702741 | Molding | HFTD Tier 3 | Distribution | 2005-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005957 | 400040545 | Molding | HFTD Tier 3 | Distribution | 2005-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005958 | 400042515 | Molding | HFTD Tier 3 | Distribution | 2005-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005959 | 400058485 | High Sign | HFTD Tier 3 | Distribution | 2005-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005960 | 400295344 | Molding | HFTD Tier 3 | Distribution | 2005-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005961 | 400504568 | Hardware/Framing | HFTD Tier 2 | Distribution | 2005-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005962 | 400696503 | Molding | HFTD Tier 2 | Distribution | 2005-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005963 | 400701575 | Molding | HFTD Tier 2 | Distribution | 2005-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005964 | 400724777 | Molding | HFTD Tier 3 | Distribution | 2005-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005965 | 400125437 | Molding | HFTD Tier 2 | Distribution | 2005-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005966 | 400129717 | Molding | HFTD Tier 2 | Distribution | 2005-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005967 | 400295375 | Molding | HFTD Tier 2 | Distribution | 2005-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005968 | 400744371 | High Sign | HFTD Tier 3 | Distribution | 2005-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005969 | 400320974 | Molding | HFTD Tier 2 | Distribution | 2005-10-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005970 | 400348694 | Molding | HFTD Tier 2 | Distribution | 2005-11-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005971 | 400632537 | Guy | HFTD Tier 3 | Distribution | 2005-11-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005972 | 400637385 | Guy | HFTD Tier 3 | Distribution | 2005-11-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005973 | 400769137 | Guy | HFTD Tier 3 | Distribution | 2005-11-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005974 | 400141810 | Molding | HFTD Tier 3 | Distribution | 2005-11-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005975 | 400142008 | Guy | HFTD Tier 2 | Distribution | 2005-11-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005976 | 400154343 | High Sign | HFTD Tier 3 | Distribution | 2005-11-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005977 | 400160980 | High Sign | HFTD Tier 3 | Distribution | 2005-11-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005978 | 400169837 | Molding | HFTD Tier 3 | Distribution | 2005-11-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005979 | 400172570 | Molding | HFTD Tier 2 | Distribution | 2005-11-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005980 | 400575824 | High Sign | HFTD Tier 3 | Distribution | 2005-11-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005981 | 400584003 | Molding | HFTD Tier 3 | Distribution | 2005-11-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005982 | 400599871 | Molding | HFTD Tier 2 | Distribution | 2005-11-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005983 | 400652709 | High Sign | HFTD Tier 2 | Distribution | 2005-11-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005984 | 400682272 | Molding | HFTD Tier 3 | Distribution | 2005-11-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005985 | 400788711 | Riser/Conduit | HFTD Tier 3 | Distribution | 2005-11-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005986 | 400187590 | Molding | HFTD Tier 2 | Distribution | 2005-11-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005987 | 400195592 | Molding | HFTD Tier 2 | Distribution | 2005-11-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005988 | 400351392 | Guy | HFTD Tier 3 | Distribution | 2005-11-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005989 | 400614818 | High Sign | HFTD Tier 2 | Distribution | 2005-11-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005990 | 400617355 | Molding | HFTD Tier 2 | Distribution | 2005-11-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005991 | 400620173 | Molding | HFTD Tier 2 | Distribution | 2005-11-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005992 | 400675788 | Guy | HFTD Tier 2 | Distribution | 2005-11-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005993 | 400792478 | High Sign | HFTD Tier 2 | Distribution | 2005-11-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005994 | 400972092 | Molding | HFTD Tier 3 | Distribution | 2005-11-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005995 | 400185373 | High Sign | HFTD Tier 2 | Distribution | 2005-11-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005996 | 400191681 | Guy | HFTD Tier 2 | Distribution | 2005-11-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005997 | 400211253 | Molding | HFTD Tier 3 | Distribution | 2005-11-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005998 | 400607475 | Molding | HFTD Tier 2 | Distribution | 2005-11-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120005999 | 400633519 | Cable/Conductor | HFTD Tier 3 | Distribution | 2005-11-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006000 | 400811704 | Molding | HFTD Tier 2 | Distribution | 2005-11-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006001 | 400821195 | Molding | HFTD Tier 2 | Distribution | 2005-11-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006002 | 403048772 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-11-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006003 | 400216883 | High Sign | HFTD Tier 3 | Distribution | 2005-11-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006004 | 400653717 | Molding | HFTD Tier 3 | Distribution | 2005-11-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006005 | 400220750 | Guy | HFTD Tier 2 | Distribution | 2005-11-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006006 | 400837966 | Guy | HFTD Tier 2 | Distribution | 2005-11-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006007 | 400761225 | High Sign | HFTD Tier 3 | Distribution | 2005-11-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006008 | 400879495 | High Sign | HFTD Tier 3 | Distribution | 2005-11-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006009 | 400883684 | Riser/Conduit | HFTD Tier 3 | Distribution | 2005-11-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006010 | 400891452 | High Sign | HFTD Tier 3 | Distribution | 2005-11-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006011 | 400253429 | Molding | HFTD Tier 3 | Distribution | 2005-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006012 | 400256194 | Molding | HFTD Tier 3 | Distribution | 2005-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006013 | 400886829 | Molding | HFTD Tier 3 | Distribution | 2005-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006014 | 400802552 | Molding | HFTD Tier 3 | Distribution | 2005-11-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006015 | 400804764 | Hardware/Framing | HFTD Tier 3 | Distribution | 2005-11-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006016 | 400912149 | Riser/Conduit | HFTD Tier 3 | Distribution | 2005-11-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006017 | 400937204 | Hardware/Framing | HFTD Tier 3 | Distribution | 2005-11-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006018 | 403048805 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-11-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006019 | 400949861 | Guy | HFTD Tier 3 | Distribution | 2005-11-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006020 | 400751792 | Molding | HFTD Tier 2 | Distribution | 2005-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006021 | 401004148 | Hardware/Framing | HFTD Tier 2 | Distribution | 2005-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006022 | 401004149 | High Sign | HFTD Tier 2 | Distribution | 2005-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006023 | 400766130 | Molding | HFTD Tier 3 | Distribution | 2005-11-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006024 | 400842524 | Molding | HFTD Tier 2 | Distribution | 2005-11-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006025 | 400949157 | Guy | HFTD Tier 3 | Distribution | 2005-11-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006026 | 403048812 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-11-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006027 | 400286006 | Molding | HFTD Tier 3 | Distribution | 2005-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006028 | 400397831 | High Sign | HFTD Tier 2 | Distribution | 2005-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006029 | 400408387 | Guy | HFTD Tier 3 | Distribution | 2005-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006030 | 400856652 | High Sign | HFTD Tier 2 | Distribution | 2005-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006031 | 400877535 | High Sign | HFTD Tier 2 | Distribution | 2005-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006032 | 400383273 | High Sign | HFTD Tier 3 | Distribution | 2005-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006033 | 400787965 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006034 | 400954975 | Molding | HFTD Tier 2 | Distribution | 2005-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006035 | 400967178 | Molding | HFTD Tier 3 | Distribution | 2005-11-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006036 | 400970235 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-11-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006037 | 400970614 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-11-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006038 | 400483016 | Molding | HFTD Tier 2 | Distribution | 2005-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006039 | 400494025 | Molding | HFTD Tier 3 | Distribution | 2005-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006040 | 400569967 | High Sign | HFTD Tier 2 | Distribution | 2005-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006041 | 400863206 | Molding | HFTD Tier 2 | Distribution | 2005-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006042 | 400963868 | Molding | HFTD Tier 3 | Distribution | 2005-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006043 | 400506916 | Molding | HFTD Tier 2 | Distribution | 2005-11-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006044 | 400894438 | High Sign | HFTD Tier 2 | Distribution | 2005-11-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006045 | 401486475 | Cable/Conductor | HFTD Tier 2 | Distribution | 2005-11-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006046 | 400974449 | Guy | HFTD Tier 2 | Distribution | 2005-11-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006047 | 400515708 | High Sign | HFTD Tier 2 | Distribution | 2005-11-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006048 | 400622461 | Molding | HFTD Tier 3 | Distribution | 2005-11-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006049 | 400645482 | High Sign | HFTD Tier 2 | Distribution | 2005-11-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006050 | 400643017 | High Sign | HFTD Tier 2 | Distribution | 2005-11-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006051 | 400769188 | High Sign | HFTD Tier 3 | Distribution | 2005-11-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006052 | 400971690 | Guy | HFTD Tier 3 | Distribution | 2005-11-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006053 | 400975720 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-11-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006054 | 400548175 | Molding | HFTD Tier 2 | Distribution | 2005-11-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006055 | 400771613 | Guy | HFTD Tier 3 | Distribution | 2005-11-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006056 | 400544875 | Molding | HFTD Tier 3 | Distribution | 2005-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006057 | 400602768 | Molding | HFTD Tier 3 | Distribution | 2005-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006058 | 400695821 | Molding | HFTD Tier 3 | Distribution | 2005-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006059 | 400698531 | Molding | HFTD Tier 3 | Distribution | 2005-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006060 | 400949705 | Molding | HFTD Tier 3 | Distribution | 2005-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006061 | 400960167 | Molding | HFTD Tier 3 | Distribution | 2005-12-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006062 | 400644095 | High Sign | HFTD Tier 3 | Distribution | 2005-12-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006063 | 400649618 | Molding | HFTD Tier 3 | Distribution | 2005-12-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006064 | 400739558 | Molding | HFTD Tier 3 | Distribution | 2005-12-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006065 | 400960344 | Molding | HFTD Tier 3 | Distribution | 2005-12-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006066 | 400960745 | High Sign | HFTD Tier 3 | Distribution | 2005-12-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006067 | 400550907 | Cable/Conductor | HFTD Tier 2 | Distribution | 2005-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006068 | 400556944 | High Sign | HFTD Tier 2 | Distribution | 2005-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006069 | 400549257 | Hardware/Framing | HFTD Tier 2 | Distribution | 2005-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006070 | 400563010 | High Sign | HFTD Tier 2 | Distribution | 2005-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006071 | 400566407 | High Sign | HFTD Tier 2 | Distribution | 2005-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006072 | 400627649 | Hardware/Framing | HFTD Tier 2 | Distribution | 2005-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006073 | 400648239 | High Sign | HFTD Tier 2 | Distribution | 2005-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006074 | 400655370 | Molding | HFTD Tier 3 | Distribution | 2005-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006075 | 400714147 | Molding | HFTD Tier 2 | Distribution | 2005-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006076 | 400954635 | Molding | HFTD Tier 2 | Distribution | 2005-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006077 | 400617239 | High Sign | HFTD Tier 3 | Distribution | 2005-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006078 | 400682503 | Molding | HFTD Tier 2 | Distribution | 2005-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006079 | 400752885 | Guy | HFTD Tier 2 | Distribution | 2005-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006080 | 400754078 | High Sign | HFTD Tier 3 | Distribution | 2005-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006081 | 400767536 | Molding | HFTD Tier 3 | Distribution | 2005-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006082 | 400584552 | High Sign | HFTD Tier 3 | Distribution | 2005-12-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006083 | 400656388 | Guy | HFTD Tier 3 | Distribution | 2005-12-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006084 | 400661533 | High Sign | HFTD Tier 3 | Distribution | 2005-12-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006085 | 400681553 | Hardware/Framing | HFTD Tier 2 | Distribution | 2005-12-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006086 | 400709181 | High Sign | HFTD Tier 3 | Distribution | 2005-12-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006087 | 400715408 | Molding | HFTD Tier 2 | Distribution | 2005-12-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006088 | 400720164 | Molding | HFTD Tier 3 | Distribution | 2005-12-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006089 | 400760004 | High Sign | HFTD Tier 2 | Distribution | 2005-12-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006090 | 400782117 | Riser/Conduit | HFTD Tier 2 | Distribution | 2005-12-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006091 | 400784758 | Molding | HFTD Tier 3 | Distribution | 2005-12-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006092 | 400974566 | High Sign | HFTD Tier 3 | Distribution | 2005-12-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006093 | 400985433 | Cable/Conductor | HFTD Tier 3 | Distribution | 2005-12-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006094 | 400342451 | Molding | HFTD Tier 2 | Distribution | 2005-12-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006095 | 400342477 | Molding | HFTD Tier 2 | Distribution | 2005-12-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006096 | 400357873 | Molding | HFTD Tier 2 | Distribution | 2005-12-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006097 | 400392434 | Molding | HFTD Tier 2 | Distribution | 2005-12-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006098 | 400621706 | Molding | HFTD Tier 2 | Distribution | 2005-12-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006099 | 400972992 | Cable/Conductor | HFTD Tier 2 | Distribution | 2005-12-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006100 | 400973494 | Molding | HFTD Tier 2 | Distribution | 2005-12-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006101 | 403046006 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2005-12-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006102 | 403046237 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2005-12-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006103 | 400791012 | High Sign | HFTD Tier 3 | Distribution | 2005-12-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006104 | 400800652 | High Sign | HFTD Tier 3 | Distribution | 2005-12-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006105 | 400806634 | High Sign | HFTD Tier 3 | Distribution | 2005-12-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006106 | 400812876 | Molding | HFTD Tier 3 | Distribution | 2005-12-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006107 | 400580495 | High Sign | HFTD Tier 2 | Distribution | 2005-12-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006108 | 400665555 | Molding | HFTD Tier 2 | Distribution | 2005-12-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006109 | 400677522 | High Sign | HFTD Tier 3 | Distribution | 2005-12-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006110 | 401000110 | Cable/Conductor | HFTD Tier 2 | Distribution | 2005-12-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006111 | 400309229 | Riser/Conduit | HFTD Tier 2 | Distribution | 2005-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006112 | 400347963 | Molding | HFTD Tier 2 | Distribution | 2005-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006113 | 400762559 | Molding | HFTD Tier 2 | Distribution | 2005-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006114 | 400767485 | Molding | HFTD Tier 2 | Distribution | 2005-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006115 | 400816663 | High Sign | HFTD Tier 3 | Distribution | 2005-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006116 | 400818270 | Molding | HFTD Tier 2 | Distribution | 2005-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006117 | 400823990 | High Sign | HFTD Tier 3 | Distribution | 2005-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006118 | 400799306 | High Sign | HFTD Tier 3 | Distribution | 2005-12-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006119 | 400860706 | High Sign | HFTD Tier 3 | Distribution | 2005-12-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006120 | 400371750 | High Sign | HFTD Tier 3 | Distribution | 2005-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006121 | 400634857 | High Sign | HFTD Tier 3 | Distribution | 2005-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006122 | 400637265 | High Sign | HFTD Tier 3 | Distribution | 2005-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006123 | 400706760 | Molding | HFTD Tier 2 | Distribution | 2005-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006124 | 400706825 | High Sign | HFTD Tier 3 | Distribution | 2005-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006125 | 400709597 | High Sign | HFTD Tier 3 | Distribution | 2005-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006126 | 400709652 | High Sign | HFTD Tier 3 | Distribution | 2005-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006127 | 400725968 | High Sign | HFTD Tier 3 | Distribution | 2005-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006128 | 400790422 | Molding | HFTD Tier 2 | Distribution | 2005-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006129 | 400824468 | High Sign | HFTD Tier 3 | Distribution | 2005-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006130 | 400824503 | High Sign | HFTD Tier 3 | Distribution | 2005-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006131 | 400912900 | Molding | HFTD Tier 3 | Distribution | 2005-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006132 | 400950665 | Molding | HFTD Tier 3 | Distribution | 2005-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006133 | 400746075 | High Sign | HFTD Tier 3 | Distribution | 2005-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006134 | 400815856 | Molding | HFTD Tier 2 | Distribution | 2005-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006135 | 400953352 | Molding | HFTD Tier 3 | Distribution | 2005-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006136 | 400665406 | Molding | HFTD Tier 2 | Distribution | 2005-12-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006137 | 400667775 | Molding | HFTD Tier 2 | Distribution | 2005-12-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006138 | 400767480 | Guy | HFTD Tier 2 | Distribution | 2005-12-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006139 | 400735474 | High Sign | HFTD Tier 2 | Distribution | 2005-12-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006140 | 400741909 | Guy | HFTD Tier 3 | Distribution | 2005-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006141 | 400874252 | Ground | HFTD Tier 3 | Distribution | 2005-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006142 | 400954354 | Molding | HFTD Tier 2 | Distribution | 2005-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006143 | 400842873 | Molding | HFTD Tier 2 | Distribution | 2005-12-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006144 | 400865940 | Molding | HFTD Tier 3 | Distribution | 2005-12-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006145 | 400883779 | High Sign | HFTD Tier 3 | Distribution | 2005-12-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006146 | 400919766 | Molding | HFTD Tier 3 | Distribution | 2005-12-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006147 | 400924595 | High Sign | HFTD Tier 2 | Distribution | 2005-12-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006148 | 400940949 | High Sign | HFTD Tier 3 | Distribution | 2005-12-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006149 | 400959347 | High Sign | HFTD Tier 3 | Distribution | 2005-12-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006150 | 400964887 | Molding | HFTD Tier 3 | Distribution | 2005-12-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006151 | 400970359 | Molding | HFTD Tier 3 | Distribution | 2005-12-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006152 | 401006504 | Hardware/Framing | HFTD Tier 3 | Distribution | 2005-12-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006153 | 401006505 | Molding | HFTD Tier 3 | Distribution | 2005-12-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006154 | 401491352 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-12-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006155 | 400793559 | High Sign | HFTD Tier 3 | Distribution | 2005-12-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006156 | 400892509 | Molding | HFTD Tier 3 | Distribution | 2005-12-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006157 | 400950614 | High Sign | HFTD Tier 2 | Distribution | 2005-12-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006158 | 400954969 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2005-12-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006159 | 400809067 | Molding | HFTD Tier 3 | Distribution | 2005-12-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006160 | 400902602 | Molding | HFTD Tier 3 | Distribution | 2005-12-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006161 | 400914261 | High Sign | HFTD Tier 3 | Distribution | 2005-12-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006162 | 400970762 | High Sign | HFTD Tier 3 | Distribution | 2005-12-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006163 | 400331188 | High Sign | HFTD Tier 3 | Distribution | 2005-12-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006164 | 400642406 | Molding | HFTD Tier 3 | Distribution | 2005-12-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006165 | 400827544 | High Sign | HFTD Tier 2 | Distribution | 2005-12-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006166 | 400856709 | High Sign | HFTD Tier 3 | Distribution | 2005-12-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006167 | 400960806 | Molding | HFTD Tier 3 | Distribution | 2005-12-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006168 | 400412457 | High Sign | HFTD Tier 2 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006169 | 400557216 | High Sign | HFTD Tier 3 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006170 | 400565053 | High Sign | HFTD Tier 2 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006171 | 400570447 | High Sign | HFTD Tier 3 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006172 | 400571748 | High Sign | HFTD Tier 3 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006173 | 400825165 | High Sign | HFTD Tier 2 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006174 | 400827549 | High Sign | HFTD Tier 2 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006175 | 400829896 | High Sign | HFTD Tier 2 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006176 | 400834087 | Molding | HFTD Tier 3 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006177 | 400923539 | High Sign | HFTD Tier 2 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006178 | 400925568 | High Sign | HFTD Tier 2 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006179 | 400929621 | High Sign | HFTD Tier 2 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006180 | 400930074 | High Sign | HFTD Tier 2 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006181 | 400930714 | High Sign | HFTD Tier 2 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006182 | 400931639 | High Sign | HFTD Tier 3 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006183 | 400932959 | High Sign | HFTD Tier 2 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006184 | 400941989 | High Sign | HFTD Tier 3 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006185 | 400943030 | High Sign | HFTD Tier 2 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006186 | 400943499 | High Sign | HFTD Tier 2 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006187 | 400943540 | Molding | HFTD Tier 3 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006188 | 400958832 | High Sign | HFTD Tier 2 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006189 | 400961144 | Guy | HFTD Tier 2 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006190 | 400963147 | High Sign | HFTD Tier 3 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006191 | 400963153 | Molding | HFTD Tier 3 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006192 | 400964307 | High Sign | HFTD Tier 2 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006193 | 400975231 | High Sign | HFTD Tier 2 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006194 | 400975240 | High Sign | HFTD Tier 2 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006195 | 400975870 | High Sign | HFTD Tier 2 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006196 | 400975878 | Molding | HFTD Tier 2 | Distribution | 2005-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006197 | 400591442 | High Sign | HFTD Tier 2 | Distribution | 2005-12-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006198 | 400593057 | High Sign | HFTD Tier 2 | Distribution | 2005-12-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006199 | 400597688 | High Sign | HFTD Tier 2 | Distribution | 2005-12-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006200 | 400606160 | High Sign | HFTD Tier 3 | Distribution | 2005-12-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006201 | 400867688 | High Sign | HFTD Tier 2 | Distribution | 2005-12-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006202 | 400869820 | High Sign | HFTD Tier 2 | Distribution | 2005-12-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006203 | 400870136 | High Sign | HFTD Tier 2 | Distribution | 2005-12-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006204 | 400874257 | High Sign | HFTD Tier 3 | Distribution | 2005-12-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006205 | 400946755 | Molding | HFTD Tier 3 | Distribution | 2005-12-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006206 | 400947278 | Molding | HFTD Tier 3 | Distribution | 2005-12-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006207 | 400949379 | High Sign | HFTD Tier 2 | Distribution | 2005-12-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006208 | 400951187 | High Sign | HFTD Tier 2 | Distribution | 2005-12-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006209 | 400951234 | Molding | HFTD Tier 2 | Distribution | 2005-12-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006210 | 400952374 | Molding | HFTD Tier 3 | Distribution | 2005-12-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006211 | 400969754 | High Sign | HFTD Tier 2 | Distribution | 2005-12-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006212 | 400970446 | High Sign | HFTD Tier 2 | Distribution | 2005-12-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006213 | 400971317 | High Sign | HFTD Tier 2 | Distribution | 2005-12-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006214 | 400335331 | High Sign | HFTD Tier 3 | Distribution | 2005-12-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006215 | 400381703 | Guy | HFTD Tier 3 | Distribution | 2005-12-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006216 | 400635261 | High Sign | HFTD Tier 3 | Distribution | 2005-12-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006217 | 400954194 | Molding | HFTD Tier 2 | Distribution | 2005-12-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006218 | 400335502 | Molding | HFTD Tier 3 | Distribution | 2005-12-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006219 | 400411857 | Molding | HFTD Tier 3 | Distribution | 2005-12-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006220 | 400414681 | Molding | HFTD Tier 3 | Distribution | 2005-12-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006221 | 400898118 | Guy | HFTD Tier 3 | Distribution | 2005-12-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006222 | 400960678 | Molding | HFTD Tier 3 | Distribution | 2005-12-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006223 | 400657778 | Riser/Conduit | HFTD Tier 2 | Distribution | 2006-01-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006224 | 401006172 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006225 | 400948859 | Molding | HFTD Tier 3 | Distribution | 2006-01-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006226 | 400370983 | High Sign | HFTD Tier 3 | Distribution | 2006-01-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006227 | 400550232 | Molding | HFTD Tier 2 | Distribution | 2006-01-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006228 | 400566629 | Molding | HFTD Tier 3 | Distribution | 2006-01-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006229 | 400701145 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-01-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006230 | 400845531 | Molding | HFTD Tier 2 | Distribution | 2006-01-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006231 | 400960368 | Guy | HFTD Tier 3 | Distribution | 2006-01-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006232 | 400602012 | Molding | HFTD Tier 2 | Distribution | 2006-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006233 | 400604503 | Molding | HFTD Tier 2 | Distribution | 2006-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006234 | 400607168 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006235 | 400765399 | Molding | HFTD Tier 2 | Distribution | 2006-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006236 | 400895597 | Guy | HFTD Tier 2 | Distribution | 2006-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006237 | 400901260 | Insulator | HFTD Tier 2 | Distribution | 2006-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006238 | 400908258 | Molding | HFTD Tier 3 | Distribution | 2006-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006239 | 401491664 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006240 | 401492599 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006241 | 400609881 | High Sign | HFTD Tier 3 | Distribution | 2006-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006242 | 400625525 | Molding | HFTD Tier 2 | Distribution | 2006-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006243 | 400764141 | Guy | HFTD Tier 2 | Distribution | 2006-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006244 | 400965722 | Molding | HFTD Tier 2 | Distribution | 2006-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006245 | 400921283 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006246 | 400927648 | Molding | HFTD Tier 3 | Distribution | 2006-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006247 | 400929766 | Guy | HFTD Tier 2 | Distribution | 2006-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006248 | 400967877 | Riser/Conduit | HFTD Tier 2 | Distribution | 2006-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006249 | 400972550 | Molding | HFTD Tier 2 | Distribution | 2006-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006250 | 400973824 | Molding | HFTD Tier 2 | Distribution | 2006-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006251 | 400973834 | Molding | HFTD Tier 2 | Distribution | 2006-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006252 | 400559076 | Molding | HFTD Tier 2 | Distribution | 2006-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006253 | 400800965 | Molding | HFTD Tier 2 | Distribution | 2006-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006254 | 400809991 | Molding | HFTD Tier 3 | Distribution | 2006-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006255 | 400991989 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006256 | 400583050 | Molding | HFTD Tier 2 | Distribution | 2006-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006257 | 400678077 | Molding | HFTD Tier 2 | Distribution | 2006-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006258 | 400697363 | High Sign | HFTD Tier 3 | Distribution | 2006-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006259 | 400825513 | Molding | HFTD Tier 3 | Distribution | 2006-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006260 | 400948624 | High Sign | HFTD Tier 2 | Distribution | 2006-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006261 | 400948763 | High Sign | HFTD Tier 3 | Distribution | 2006-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006262 | 400954594 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006263 | 400751548 | Guy | HFTD Tier 2 | Distribution | 2006-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006264 | 400757139 | Molding | HFTD Tier 2 | Distribution | 2006-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006265 | 400868530 | Molding | HFTD Tier 2 | Distribution | 2006-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006266 | 400635081 | Molding | HFTD Tier 2 | Distribution | 2006-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006267 | 400651598 | High Sign | HFTD Tier 2 | Distribution | 2006-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006268 | 400858759 | Molding | HFTD Tier 2 | Distribution | 2006-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006269 | 400961238 | High Sign | HFTD Tier 2 | Distribution | 2006-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006270 | 400964916 | High Sign | HFTD Tier 3 | Distribution | 2006-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006271 | 400991875 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006272 | 400648455 | High Sign | HFTD Tier 3 | Distribution | 2006-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006273 | 400757849 | Molding | HFTD Tier 2 | Distribution | 2006-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006274 | 400758229 | Molding | HFTD Tier 2 | Distribution | 2006-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006275 | 400759799 | High Sign | HFTD Tier 2 | Distribution | 2006-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006276 | 400894225 | Molding | HFTD Tier 3 | Distribution | 2006-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006277 | 400919504 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006278 | 400974710 | Insulator | HFTD Tier 2 | Distribution | 2006-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006279 | 400995903 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006280 | 401004450 | High Sign | HFTD Tier 2 | Distribution | 2006-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006281 | 400669514 | High Sign | HFTD Tier 2 | Distribution | 2006-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006282 | 400675062 | Molding | HFTD Tier 3 | Distribution | 2006-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006283 | 400792646 | Molding | HFTD Tier 2 | Distribution | 2006-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006284 | 400797662 | High Sign | HFTD Tier 2 | Distribution | 2006-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006285 | 400801675 | Molding | HFTD Tier 2 | Distribution | 2006-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006286 | 400803836 | High Sign | HFTD Tier 2 | Distribution | 2006-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006287 | 400814650 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006288 | 400977042 | Molding | HFTD Tier 3 | Distribution | 2006-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006289 | 400977261 | Molding | HFTD Tier 2 | Distribution | 2006-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006290 | 400978705 | Molding | HFTD Tier 3 | Distribution | 2006-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006291 | 400712931 | High Sign | HFTD Tier 2 | Distribution | 2006-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006292 | 400716948 | High Sign | HFTD Tier 2 | Distribution | 2006-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006293 | 400757192 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006294 | 400796132 | Molding | HFTD Tier 3 | Distribution | 2006-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006295 | 400836148 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006296 | 400934801 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006297 | 400939674 | Molding | HFTD Tier 2 | Distribution | 2006-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006298 | 400940117 | Molding | HFTD Tier 2 | Distribution | 2006-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006299 | 400950281 | High Sign | HFTD Tier 2 | Distribution | 2006-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006300 | 400975073 | Molding | HFTD Tier 3 | Distribution | 2006-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006301 | 400982906 | High Sign | HFTD Tier 3 | Distribution | 2006-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006302 | 400598689 | High Sign | HFTD Tier 2 | Distribution | 2006-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006303 | 400911401 | High Sign | HFTD Tier 2 | Distribution | 2006-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006304 | 400964209 | Molding | HFTD Tier 3 | Distribution | 2006-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006305 | 400975077 | High Sign | HFTD Tier 3 | Distribution | 2006-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006306 | 400978547 | Molding | HFTD Tier 2 | Distribution | 2006-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006307 | 400856853 | Molding | HFTD Tier 2 | Distribution | 2006-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006308 | 400957389 | Molding | HFTD Tier 2 | Distribution | 2006-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006309 | 400959135 | Molding | HFTD Tier 2 | Distribution | 2006-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006310 | 400959817 | High Sign | HFTD Tier 2 | Distribution | 2006-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006311 | 400979354 | High Sign | HFTD Tier 2 | Distribution | 2006-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006312 | 400368606 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006313 | 400394056 | Molding | HFTD Tier 2 | Distribution | 2006-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006314 | 400797663 | Molding | HFTD Tier 2 | Distribution | 2006-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006315 | 400799097 | Guy | HFTD Tier 2 | Distribution | 2006-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006316 | 400914149 | High Sign | HFTD Tier 2 | Distribution | 2006-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006317 | 400982992 | High Sign | HFTD Tier 2 | Distribution | 2006-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006318 | 400559472 | Molding | HFTD Tier 2 | Distribution | 2006-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006319 | 400817604 | High Sign | HFTD Tier 3 | Distribution | 2006-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006320 | 400910484 | High Sign | HFTD Tier 2 | Distribution | 2006-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006321 | 400976538 | Guy | HFTD Tier 2 | Distribution | 2006-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006322 | 400981819 | Molding | HFTD Tier 2 | Distribution | 2006-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006323 | 400983109 | High Sign | HFTD Tier 2 | Distribution | 2006-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006324 | 400919656 | Molding | HFTD Tier 2 | Distribution | 2006-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006325 | 400922649 | Molding | HFTD Tier 2 | Distribution | 2006-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006326 | 401462984 | Molding | HFTD Tier 3 | Distribution | 2006-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006327 | 400945371 | High Sign | HFTD Tier 3 | Distribution | 2006-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006328 | 400586542 | High Sign | HFTD Tier 2 | Distribution | 2006-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006329 | 400588946 | High Sign | HFTD Tier 2 | Distribution | 2006-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006330 | 400819468 | Molding | HFTD Tier 3 | Distribution | 2006-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006331 | 400869773 | Riser/Conduit | HFTD Tier 2 | Distribution | 2006-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006332 | 400872181 | High Sign | HFTD Tier 2 | Distribution | 2006-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006333 | 400940733 | High Sign | HFTD Tier 2 | Distribution | 2006-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006334 | 400943544 | Molding | HFTD Tier 2 | Distribution | 2006-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006335 | 400983861 | Molding | HFTD Tier 2 | Distribution | 2006-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006336 | 400984038 | High Sign | HFTD Tier 2 | Distribution | 2006-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006337 | 400380454 | High Sign | HFTD Tier 2 | Distribution | 2006-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006338 | 400585265 | Molding | HFTD Tier 2 | Distribution | 2006-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006339 | 400589435 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006340 | 400636257 | High Sign | HFTD Tier 2 | Distribution | 2006-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006341 | 400636361 | High Sign | HFTD Tier 2 | Distribution | 2006-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006342 | 400833026 | High Sign | HFTD Tier 2 | Distribution | 2006-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006343 | 400960398 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006344 | 400371467 | Molding | HFTD Tier 2 | Distribution | 2006-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006345 | 400402809 | Molding | HFTD Tier 2 | Distribution | 2006-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006346 | 400919655 | Molding | HFTD Tier 2 | Distribution | 2006-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006347 | 400662967 | High Sign | HFTD Tier 2 | Distribution | 2006-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006348 | 400967601 | Molding | HFTD Tier 2 | Distribution | 2006-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006349 | 400968651 | Molding | HFTD Tier 2 | Distribution | 2006-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006350 | 400382270 | Guy | HFTD Tier 2 | Distribution | 2006-02-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006351 | 400575981 | High Sign | HFTD Tier 3 | Distribution | 2006-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006352 | 400706588 | Molding | HFTD Tier 3 | Distribution | 2006-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006353 | 400913622 | High Sign | HFTD Tier 3 | Distribution | 2006-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006354 | 400964664 | Molding | HFTD Tier 3 | Distribution | 2006-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006355 | 400964759 | Molding | HFTD Tier 3 | Distribution | 2006-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006356 | 400966079 | Molding | HFTD Tier 3 | Distribution | 2006-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006357 | 400966084 | Guy | HFTD Tier 3 | Distribution | 2006-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006358 | 401496880 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006359 | 400736477 | High Sign | HFTD Tier 3 | Distribution | 2006-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006360 | 400771342 | Molding | HFTD Tier 3 | Distribution | 2006-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006361 | 400715619 | High Sign | HFTD Tier 3 | Distribution | 2006-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006362 | 400935376 | Molding | HFTD Tier 3 | Distribution | 2006-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006363 | 400962919 | Molding | HFTD Tier 3 | Distribution | 2006-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006364 | 400966165 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006365 | 400966758 | High Sign | HFTD Tier 2 | Distribution | 2006-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006366 | 400557165 | Molding | HFTD Tier 3 | Distribution | 2006-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006367 | 400760620 | Molding | HFTD Tier 3 | Distribution | 2006-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006368 | 400945661 | Molding | HFTD Tier 3 | Distribution | 2006-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006369 | 400948157 | Molding | HFTD Tier 2 | Distribution | 2006-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006370 | 400623761 | Molding | HFTD Tier 3 | Distribution | 2006-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006371 | 400753730 | Cable/Conductor | HFTD Tier 3 | Distribution | 2006-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006372 | 400759904 | Molding | HFTD Tier 3 | Distribution | 2006-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006373 | 400949581 | Molding | HFTD Tier 3 | Distribution | 2006-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006374 | 413833707 | High Sign | HFTD Tier 3 | Distribution | 2006-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006375 | 400589380 | Molding | HFTD Tier 2 | Distribution | 2006-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006376 | 400589386 | Molding | HFTD Tier 2 | Distribution | 2006-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006377 | 400912816 | Molding | HFTD Tier 3 | Distribution | 2006-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006378 | 400962601 | Molding | HFTD Tier 2 | Distribution | 2006-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006379 | 401494930 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006380 | 400809890 | Molding | HFTD Tier 2 | Distribution | 2006-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006381 | 400826953 | Molding | HFTD Tier 3 | Distribution | 2006-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006382 | 400967945 | High Sign | HFTD Tier 2 | Distribution | 2006-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006383 | 400969110 | Molding | HFTD Tier 3 | Distribution | 2006-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006384 | 400746602 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006385 | 400836091 | High Sign | HFTD Tier 2 | Distribution | 2006-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006386 | 400723586 | Molding | HFTD Tier 2 | Distribution | 2006-02-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006387 | 400972173 | Molding | HFTD Tier 2 | Distribution | 2006-02-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006388 | 400746765 | High Sign | HFTD Tier 2 | Distribution | 2006-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006389 | 400881934 | High Sign | HFTD Tier 3 | Distribution | 2006-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006390 | 403046776 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006391 | 400911809 | High Sign | HFTD Tier 2 | Distribution | 2006-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006392 | 400978751 | High Sign | HFTD Tier 2 | Distribution | 2006-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006393 | 400951474 | Molding | HFTD Tier 2 | Distribution | 2006-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006394 | 400978163 | Molding | HFTD Tier 3 | Distribution | 2006-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006395 | 400834254 | Molding | HFTD Tier 2 | Distribution | 2006-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006396 | 400943276 | High Sign | HFTD Tier 3 | Distribution | 2006-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006397 | 400979256 | High Sign | HFTD Tier 2 | Distribution | 2006-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006398 | 400979732 | High Sign | HFTD Tier 2 | Distribution | 2006-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006399 | 400980578 | High Sign | HFTD Tier 2 | Distribution | 2006-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006400 | 400015767 | High Sign | HFTD Tier 2 | Distribution | 2006-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006401 | 400857419 | High Sign | HFTD Tier 3 | Distribution | 2006-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006402 | 400950377 | Molding | HFTD Tier 3 | Distribution | 2006-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006403 | 400950640 | Molding | HFTD Tier 2 | Distribution | 2006-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006404 | 400952186 | Molding | HFTD Tier 3 | Distribution | 2006-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006405 | 400956318 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006406 | 400450795 | High Sign | HFTD Tier 3 | Distribution | 2006-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006407 | 400452693 | Molding | HFTD Tier 2 | Distribution | 2006-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006408 | 400955535 | High Sign | HFTD Tier 3 | Distribution | 2006-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006409 | 400015790 | Molding | HFTD Tier 2 | Distribution | 2006-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006410 | 400034003 | High Sign | HFTD Tier 2 | Distribution | 2006-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006411 | 400402503 | Molding | HFTD Tier 3 | Distribution | 2006-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006412 | 400939171 | Molding | HFTD Tier 2 | Distribution | 2006-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006413 | 400557710 | Molding | HFTD Tier 3 | Distribution | 2006-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006414 | 400597790 | Cable/Conductor | HFTD Tier 3 | Distribution | 2006-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006415 | 400935135 | Molding | HFTD Tier 2 | Distribution | 2006-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006416 | 400584291 | High Sign | HFTD Tier 2 | Distribution | 2006-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006417 | 400619574 | High Sign | HFTD Tier 3 | Distribution | 2006-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006418 | 400646664 | High Sign | HFTD Tier 3 | Distribution | 2006-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006419 | 400691423 | High Sign | HFTD Tier 2 | Distribution | 2006-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006420 | 400668574 | Molding | HFTD Tier 2 | Distribution | 2006-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006421 | 400672648 | High Sign | HFTD Tier 2 | Distribution | 2006-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006422 | 400678022 | Molding | HFTD Tier 3 | Distribution | 2006-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006423 | 400690945 | High Sign | HFTD Tier 3 | Distribution | 2006-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006424 | 400976426 | Molding | HFTD Tier 3 | Distribution | 2006-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006425 | 400976793 | High Sign | HFTD Tier 3 | Distribution | 2006-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006426 | 400979801 | High Sign | HFTD Tier 2 | Distribution | 2006-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006427 | 400980930 | Molding | HFTD Tier 2 | Distribution | 2006-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006428 | 400460336 | High Sign | HFTD Tier 3 | Distribution | 2006-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006429 | 400580615 | Molding | HFTD Tier 3 | Distribution | 2006-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006430 | 400628551 | Molding | HFTD Tier 2 | Distribution | 2006-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006431 | 400702892 | High Sign | HFTD Tier 3 | Distribution | 2006-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006432 | 400718618 | High Sign | HFTD Tier 2 | Distribution | 2006-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006433 | 400725901 | High Sign | HFTD Tier 3 | Distribution | 2006-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006434 | 400731505 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006435 | 400736675 | Molding | HFTD Tier 2 | Distribution | 2006-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006436 | 400982033 | Guy | HFTD Tier 2 | Distribution | 2006-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006437 | 400982741 | High Sign | HFTD Tier 2 | Distribution | 2006-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006438 | 400711965 | High Sign | HFTD Tier 3 | Distribution | 2006-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006439 | 400982821 | Insulator | HFTD Tier 2 | Distribution | 2006-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006440 | 400756553 | High Sign | HFTD Tier 2 | Distribution | 2006-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006441 | 400773170 | Molding | HFTD Tier 2 | Distribution | 2006-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006442 | 400804805 | High Sign | HFTD Tier 2 | Distribution | 2006-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006443 | 400011731 | High Sign | HFTD Tier 3 | Distribution | 2006-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006444 | 400024023 | Molding | HFTD Tier 3 | Distribution | 2006-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006445 | 400745240 | Molding | HFTD Tier 2 | Distribution | 2006-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006446 | 400761318 | High Sign | HFTD Tier 3 | Distribution | 2006-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006447 | 400012884 | Molding | HFTD Tier 3 | Distribution | 2006-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006448 | 400426463 | Molding | HFTD Tier 3 | Distribution | 2006-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006449 | 400784973 | Molding | HFTD Tier 2 | Distribution | 2006-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006450 | 400818549 | Molding | HFTD Tier 2 | Distribution | 2006-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006451 | 400676693 | Molding | HFTD Tier 2 | Distribution | 2006-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006452 | 400699921 | High Sign | HFTD Tier 3 | Distribution | 2006-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006453 | 400762108 | High Sign | HFTD Tier 3 | Distribution | 2006-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006454 | 400809615 | Molding | HFTD Tier 2 | Distribution | 2006-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006455 | 400812041 | Molding | HFTD Tier 2 | Distribution | 2006-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006456 | 400820607 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006457 | 400862889 | High Sign | HFTD Tier 2 | Distribution | 2006-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006458 | 400918734 | High Sign | HFTD Tier 2 | Distribution | 2006-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006459 | 400961013 | High Sign | HFTD Tier 3 | Distribution | 2006-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006460 | 401502153 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006461 | 400030784 | Molding | HFTD Tier 3 | Distribution | 2006-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006462 | 400694326 | High Sign | HFTD Tier 3 | Distribution | 2006-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006463 | 400697620 | High Sign | HFTD Tier 3 | Distribution | 2006-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006464 | 400822198 | High Sign | HFTD Tier 3 | Distribution | 2006-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006465 | 400834472 | High Sign | HFTD Tier 3 | Distribution | 2006-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006466 | 400837120 | High Sign | HFTD Tier 3 | Distribution | 2006-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006467 | 400880981 | Molding | HFTD Tier 3 | Distribution | 2006-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006468 | 400881700 | High Sign | HFTD Tier 3 | Distribution | 2006-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006469 | 400887813 | High Sign | HFTD Tier 3 | Distribution | 2006-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006470 | 401499317 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006471 | 400722835 | High Sign | HFTD Tier 3 | Distribution | 2006-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006472 | 400724566 | Molding | HFTD Tier 2 | Distribution | 2006-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006473 | 400839992 | Molding | HFTD Tier 3 | Distribution | 2006-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006474 | 400854419 | Riser/Conduit | HFTD Tier 2 | Distribution | 2006-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006475 | 400875439 | Molding | HFTD Tier 3 | Distribution | 2006-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006476 | 400884037 | High Sign | HFTD Tier 3 | Distribution | 2006-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006477 | 400939170 | High Sign | HFTD Tier 3 | Distribution | 2006-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006478 | 400939176 | Molding | HFTD Tier 2 | Distribution | 2006-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006479 | 400943186 | Guy | HFTD Tier 2 | Distribution | 2006-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006480 | 400944250 | High Sign | HFTD Tier 3 | Distribution | 2006-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006481 | 400952842 | High Sign | HFTD Tier 3 | Distribution | 2006-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006482 | 400959329 | High Sign | HFTD Tier 3 | Distribution | 2006-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006483 | 400967138 | Molding | HFTD Tier 2 | Distribution | 2006-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006484 | 400433966 | High Sign | HFTD Tier 3 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006485 | 400753397 | Molding | HFTD Tier 2 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006486 | 400756314 | Molding | HFTD Tier 2 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006487 | 400756319 | Molding | HFTD Tier 2 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006488 | 400757460 | High Sign | HFTD Tier 3 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006489 | 400761112 | Molding | HFTD Tier 2 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006490 | 400868028 | High Sign | HFTD Tier 3 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006491 | 400870417 | Molding | HFTD Tier 3 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006492 | 400872573 | Molding | HFTD Tier 2 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006493 | 400874260 | High Sign | HFTD Tier 2 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006494 | 400875467 | Molding | HFTD Tier 2 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006495 | 400876504 | High Sign | HFTD Tier 3 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006496 | 400923538 | High Sign | HFTD Tier 3 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006497 | 400933141 | High Sign | HFTD Tier 3 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006498 | 400940836 | High Sign | HFTD Tier 3 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006499 | 400956228 | High Sign | HFTD Tier 3 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006500 | 400957815 | Molding | HFTD Tier 2 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006501 | 400957819 | Molding | HFTD Tier 2 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006502 | 400958850 | Molding | HFTD Tier 2 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006503 | 400959344 | Guy | HFTD Tier 2 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006504 | 400959350 | High Sign | HFTD Tier 2 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006505 | 400960061 | High Sign | HFTD Tier 3 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006506 | 400987148 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006507 | 400779406 | Molding | HFTD Tier 3 | Distribution | 2006-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006508 | 400790962 | High Sign | HFTD Tier 2 | Distribution | 2006-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006509 | 400969802 | Molding | HFTD Tier 2 | Distribution | 2006-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006510 | 400801141 | High Sign | HFTD Tier 3 | Distribution | 2006-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006511 | 400807388 | Insulator | HFTD Tier 2 | Distribution | 2006-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006512 | 400814735 | Molding | HFTD Tier 2 | Distribution | 2006-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006513 | 400919923 | High Sign | HFTD Tier 3 | Distribution | 2006-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006514 | 400920481 | High Sign | HFTD Tier 3 | Distribution | 2006-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006515 | 400920606 | Molding | HFTD Tier 2 | Distribution | 2006-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006516 | 400925914 | Molding | HFTD Tier 3 | Distribution | 2006-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006517 | 400958389 | Molding | HFTD Tier 3 | Distribution | 2006-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006518 | 400959281 | High Sign | HFTD Tier 3 | Distribution | 2006-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006519 | 400961484 | Insulator | HFTD Tier 2 | Distribution | 2006-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006520 | 400961488 | High Sign | HFTD Tier 2 | Distribution | 2006-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006521 | 400961616 | Molding | HFTD Tier 2 | Distribution | 2006-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006522 | 400962317 | High Sign | HFTD Tier 2 | Distribution | 2006-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006523 | 400962505 | Guy | HFTD Tier 2 | Distribution | 2006-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006524 | 400973004 | High Sign | HFTD Tier 3 | Distribution | 2006-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006525 | 400973850 | Molding | HFTD Tier 2 | Distribution | 2006-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006526 | 400976545 | High Sign | HFTD Tier 2 | Distribution | 2006-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006527 | 400845435 | High Sign | HFTD Tier 3 | Distribution | 2006-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006528 | 400910430 | High Sign | HFTD Tier 3 | Distribution | 2006-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006529 | 400971416 | Molding | HFTD Tier 2 | Distribution | 2006-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006530 | 400971682 | Molding | HFTD Tier 2 | Distribution | 2006-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006531 | 400977628 | High Sign | HFTD Tier 3 | Distribution | 2006-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006532 | 400980463 | High Sign | HFTD Tier 3 | Distribution | 2006-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006533 | 400015522 | Molding | HFTD Tier 3 | Distribution | 2006-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006534 | 400559094 | High Sign | HFTD Tier 2 | Distribution | 2006-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006535 | 400573263 | Molding | HFTD Tier 2 | Distribution | 2006-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006536 | 400589346 | Guy | HFTD Tier 2 | Distribution | 2006-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006537 | 400664696 | Molding | HFTD Tier 2 | Distribution | 2006-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006538 | 400870611 | Molding | HFTD Tier 2 | Distribution | 2006-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006539 | 400975950 | High Sign | HFTD Tier 2 | Distribution | 2006-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006540 | 400979018 | Molding | HFTD Tier 2 | Distribution | 2006-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006541 | 401503789 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006542 | 400583401 | High Sign | HFTD Tier 3 | Distribution | 2006-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006543 | 400593470 | High Sign | HFTD Tier 3 | Distribution | 2006-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006544 | 400909116 | High Sign | HFTD Tier 3 | Distribution | 2006-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006545 | 400018114 | High Sign | HFTD Tier 2 | Distribution | 2006-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006546 | 400446576 | Molding | HFTD Tier 3 | Distribution | 2006-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006547 | 400621865 | Molding | HFTD Tier 2 | Distribution | 2006-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006548 | 400639630 | Molding | HFTD Tier 2 | Distribution | 2006-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006549 | 400642750 | High Sign | HFTD Tier 3 | Distribution | 2006-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006550 | 400927824 | Molding | HFTD Tier 2 | Distribution | 2006-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006551 | 400947975 | High Sign | HFTD Tier 2 | Distribution | 2006-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006552 | 400982664 | High Sign | HFTD Tier 2 | Distribution | 2006-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006553 | 400016872 | Molding | HFTD Tier 3 | Distribution | 2006-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006554 | 400595136 | Molding | HFTD Tier 3 | Distribution | 2006-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006555 | 400943638 | High Sign | HFTD Tier 3 | Distribution | 2006-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006556 | 400947327 | High Sign | HFTD Tier 3 | Distribution | 2006-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006557 | 400981764 | High Sign | HFTD Tier 3 | Distribution | 2006-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006558 | 400982381 | High Sign | HFTD Tier 3 | Distribution | 2006-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006559 | 400673590 | High Sign | HFTD Tier 3 | Distribution | 2006-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006560 | 400678383 | High Sign | HFTD Tier 3 | Distribution | 2006-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006561 | 400681936 | High Sign | HFTD Tier 3 | Distribution | 2006-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006562 | 400702890 | Molding | HFTD Tier 3 | Distribution | 2006-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006563 | 400957781 | High Sign | HFTD Tier 3 | Distribution | 2006-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006564 | 400966268 | High Sign | HFTD Tier 3 | Distribution | 2006-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006565 | 400983907 | Molding | HFTD Tier 3 | Distribution | 2006-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006566 | 400563567 | Molding | HFTD Tier 3 | Distribution | 2006-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006567 | 400573236 | High Sign | HFTD Tier 3 | Distribution | 2006-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006568 | 400655294 | High Sign | HFTD Tier 3 | Distribution | 2006-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006569 | 400676815 | High Sign | HFTD Tier 3 | Distribution | 2006-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006570 | 400678366 | Molding | HFTD Tier 3 | Distribution | 2006-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006571 | 400695088 | Molding | HFTD Tier 2 | Distribution | 2006-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006572 | 400696440 | High Sign | HFTD Tier 3 | Distribution | 2006-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006573 | 400697560 | High Sign | HFTD Tier 3 | Distribution | 2006-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006574 | 400700116 | High Sign | HFTD Tier 3 | Distribution | 2006-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006575 | 400964232 | High Sign | HFTD Tier 3 | Distribution | 2006-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006576 | 400966417 | High Sign | HFTD Tier 3 | Distribution | 2006-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006577 | 400702870 | High Sign | HFTD Tier 3 | Distribution | 2006-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006578 | 400707550 | Molding | HFTD Tier 2 | Distribution | 2006-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006579 | 400557485 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006580 | 400680932 | High Sign | HFTD Tier 3 | Distribution | 2006-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006581 | 400687539 | Molding | HFTD Tier 3 | Distribution | 2006-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006582 | 400695504 | High Sign | HFTD Tier 3 | Distribution | 2006-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006583 | 400723201 | High Sign | HFTD Tier 3 | Distribution | 2006-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006584 | 400735928 | Molding | HFTD Tier 3 | Distribution | 2006-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006585 | 400757717 | High Sign | HFTD Tier 3 | Distribution | 2006-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006586 | 400557516 | Molding | HFTD Tier 2 | Distribution | 2006-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006587 | 400572010 | High Sign | HFTD Tier 3 | Distribution | 2006-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006588 | 400697972 | High Sign | HFTD Tier 3 | Distribution | 2006-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006589 | 400762696 | High Sign | HFTD Tier 3 | Distribution | 2006-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006590 | 400614382 | Molding | HFTD Tier 3 | Distribution | 2006-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006591 | 400617109 | High Sign | HFTD Tier 3 | Distribution | 2006-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006592 | 400625336 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006593 | 400745559 | High Sign | HFTD Tier 3 | Distribution | 2006-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006594 | 400748670 | High Sign | HFTD Tier 3 | Distribution | 2006-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006595 | 400776199 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006596 | 400804449 | Molding | HFTD Tier 3 | Distribution | 2006-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006597 | 400610167 | High Sign | HFTD Tier 2 | Distribution | 2006-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006598 | 400618657 | Molding | HFTD Tier 3 | Distribution | 2006-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006599 | 400641526 | Molding | HFTD Tier 2 | Distribution | 2006-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006600 | 400792522 | High Sign | HFTD Tier 3 | Distribution | 2006-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006601 | 400799831 | Molding | HFTD Tier 3 | Distribution | 2006-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006602 | 400827654 | Guy | HFTD Tier 2 | Distribution | 2006-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006603 | 403047039 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006604 | 400687296 | High Sign | HFTD Tier 2 | Distribution | 2006-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006605 | 400681254 | High Sign | HFTD Tier 2 | Distribution | 2006-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006606 | 400752687 | Molding | HFTD Tier 2 | Distribution | 2006-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006607 | 400785616 | High Sign | HFTD Tier 2 | Distribution | 2006-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006608 | 400830537 | Molding | HFTD Tier 2 | Distribution | 2006-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006609 | 400852246 | High Sign | HFTD Tier 2 | Distribution | 2006-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006610 | 400853098 | Molding | HFTD Tier 2 | Distribution | 2006-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006611 | 400638563 | High Sign | HFTD Tier 3 | Distribution | 2006-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006612 | 400789341 | High Sign | HFTD Tier 3 | Distribution | 2006-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006613 | 400828972 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006614 | 400838952 | Cable/Conductor | HFTD Tier 3 | Distribution | 2006-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006615 | 400847344 | Molding | HFTD Tier 2 | Distribution | 2006-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006616 | 400859682 | Molding | HFTD Tier 2 | Distribution | 2006-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006617 | 400861908 | Molding | HFTD Tier 3 | Distribution | 2006-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006618 | 400870710 | High Sign | HFTD Tier 3 | Distribution | 2006-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006619 | 400902121 | Molding | HFTD Tier 2 | Distribution | 2006-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006620 | 400692204 | Molding | HFTD Tier 2 | Distribution | 2006-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006621 | 400697685 | High Sign | HFTD Tier 3 | Distribution | 2006-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006622 | 400716099 | High Sign | HFTD Tier 2 | Distribution | 2006-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006623 | 400742962 | Molding | HFTD Tier 3 | Distribution | 2006-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006624 | 400744075 | High Sign | HFTD Tier 3 | Distribution | 2006-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006625 | 400747013 | High Sign | HFTD Tier 3 | Distribution | 2006-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006626 | 400811817 | Guy | HFTD Tier 2 | Distribution | 2006-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006627 | 400829465 | High Sign | HFTD Tier 2 | Distribution | 2006-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006628 | 400839910 | Guy | HFTD Tier 2 | Distribution | 2006-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006629 | 400869657 | High Sign | HFTD Tier 2 | Distribution | 2006-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006630 | 400882970 | High Sign | HFTD Tier 3 | Distribution | 2006-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006631 | 400909669 | Molding | HFTD Tier 3 | Distribution | 2006-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006632 | 400746541 | High Sign | HFTD Tier 3 | Distribution | 2006-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006633 | 400753176 | Molding | HFTD Tier 3 | Distribution | 2006-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006634 | 400754082 | High Sign | HFTD Tier 2 | Distribution | 2006-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006635 | 400870753 | High Sign | HFTD Tier 2 | Distribution | 2006-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006636 | 400890355 | Ground | HFTD Tier 3 | Distribution | 2006-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006637 | 400903317 | High Sign | HFTD Tier 2 | Distribution | 2006-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006638 | 400555321 | High Sign | HFTD Tier 2 | Distribution | 2006-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006639 | 400757206 | High Sign | HFTD Tier 2 | Distribution | 2006-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006640 | 400757982 | Guy | HFTD Tier 3 | Distribution | 2006-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006641 | 400769986 | High Sign | HFTD Tier 3 | Distribution | 2006-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006642 | 400772814 | Molding | HFTD Tier 3 | Distribution | 2006-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006643 | 400778037 | Molding | HFTD Tier 3 | Distribution | 2006-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006644 | 400896473 | High Sign | HFTD Tier 2 | Distribution | 2006-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006645 | 400903754 | High Sign | HFTD Tier 3 | Distribution | 2006-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006646 | 400905770 | High Sign | HFTD Tier 2 | Distribution | 2006-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006647 | 400919001 | Molding | HFTD Tier 2 | Distribution | 2006-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006648 | 400919246 | Molding | HFTD Tier 2 | Distribution | 2006-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006649 | 400576550 | Molding | HFTD Tier 2 | Distribution | 2006-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006650 | 400913355 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006651 | 400938444 | Molding | HFTD Tier 2 | Distribution | 2006-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006652 | 401002084 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006653 | 400557762 | Molding | HFTD Tier 2 | Distribution | 2006-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006654 | 400596581 | Molding | HFTD Tier 2 | Distribution | 2006-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006655 | 400609914 | Cable/Conductor | HFTD Tier 3 | Distribution | 2006-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006656 | 400930197 | Molding | HFTD Tier 2 | Distribution | 2006-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006657 | 400572981 | Molding | HFTD Tier 3 | Distribution | 2006-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006658 | 400836125 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006659 | 400947791 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006660 | 400638409 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-04-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006661 | 400828408 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-04-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006662 | 401000669 | Cable/Conductor | HFTD Tier 3 | Distribution | 2006-04-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006663 | 400622793 | High Sign | HFTD Tier 3 | Distribution | 2006-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006664 | 400651989 | Molding | HFTD Tier 3 | Distribution | 2006-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006665 | 400607551 | Insulator | HFTD Tier 2 | Distribution | 2006-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006666 | 400639952 | High Sign | HFTD Tier 3 | Distribution | 2006-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006667 | 400643835 | Molding | HFTD Tier 3 | Distribution | 2006-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006668 | 400649065 | Molding | HFTD Tier 2 | Distribution | 2006-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006669 | 400686404 | Molding | HFTD Tier 2 | Distribution | 2006-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006670 | 400850134 | Molding | HFTD Tier 3 | Distribution | 2006-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006671 | 400861741 | High Sign | HFTD Tier 3 | Distribution | 2006-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006672 | 400879015 | Molding | HFTD Tier 3 | Distribution | 2006-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006673 | 400964820 | Molding | HFTD Tier 2 | Distribution | 2006-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006674 | 400965022 | High Sign | HFTD Tier 3 | Distribution | 2006-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006675 | 400621577 | Molding | HFTD Tier 2 | Distribution | 2006-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006676 | 400642153 | Molding | HFTD Tier 2 | Distribution | 2006-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006677 | 400653240 | Molding | HFTD Tier 3 | Distribution | 2006-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006678 | 400658357 | High Sign | HFTD Tier 3 | Distribution | 2006-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006679 | 400661342 | Molding | HFTD Tier 2 | Distribution | 2006-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006680 | 400665778 | Molding | HFTD Tier 2 | Distribution | 2006-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006681 | 400699769 | Molding | HFTD Tier 3 | Distribution | 2006-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006682 | 400700847 | Molding | HFTD Tier 3 | Distribution | 2006-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006683 | 400864912 | Molding | HFTD Tier 2 | Distribution | 2006-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006684 | 400866076 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006685 | 400887304 | Insulator | HFTD Tier 3 | Distribution | 2006-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006686 | 400900041 | Molding | HFTD Tier 3 | Distribution | 2006-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006687 | 400969804 | Molding | HFTD Tier 2 | Distribution | 2006-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006688 | 401001678 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006689 | 400642972 | Molding | HFTD Tier 2 | Distribution | 2006-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006690 | 400703805 | Molding | HFTD Tier 3 | Distribution | 2006-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006691 | 400973712 | Molding | HFTD Tier 2 | Distribution | 2006-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006692 | 400580268 | High Sign | HFTD Tier 3 | Distribution | 2006-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006693 | 400681591 | Guy | HFTD Tier 3 | Distribution | 2006-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006694 | 400913413 | High Sign | HFTD Tier 2 | Distribution | 2006-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006695 | 400921394 | Molding | HFTD Tier 2 | Distribution | 2006-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006696 | 400922848 | High Sign | HFTD Tier 3 | Distribution | 2006-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006697 | 400933915 | High Sign | HFTD Tier 2 | Distribution | 2006-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006698 | 400689610 | Molding | HFTD Tier 3 | Distribution | 2006-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006699 | 400691444 | High Sign | HFTD Tier 2 | Distribution | 2006-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006700 | 400721829 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006701 | 400725267 | Guy | HFTD Tier 2 | Distribution | 2006-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006702 | 400738490 | High Sign | HFTD Tier 2 | Distribution | 2006-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006703 | 400630174 | Guy | HFTD Tier 2 | Distribution | 2006-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006704 | 400703370 | High Sign | HFTD Tier 2 | Distribution | 2006-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006705 | 400742882 | Molding | HFTD Tier 2 | Distribution | 2006-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006706 | 400760399 | Molding | HFTD Tier 3 | Distribution | 2006-05-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006707 | 400765699 | Molding | HFTD Tier 2 | Distribution | 2006-05-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006708 | 400663341 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006709 | 400706071 | High Sign | HFTD Tier 2 | Distribution | 2006-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006710 | 400745907 | High Sign | HFTD Tier 3 | Distribution | 2006-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006711 | 400778711 | Molding | HFTD Tier 2 | Distribution | 2006-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006712 | 400784293 | Molding | HFTD Tier 2 | Distribution | 2006-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006713 | 400674893 | Molding | HFTD Tier 2 | Distribution | 2006-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006714 | 400759435 | Molding | HFTD Tier 2 | Distribution | 2006-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006715 | 400761280 | High Sign | HFTD Tier 2 | Distribution | 2006-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006716 | 400763506 | Molding | HFTD Tier 2 | Distribution | 2006-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006717 | 400803980 | Molding | HFTD Tier 2 | Distribution | 2006-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006718 | 400706258 | Guy | HFTD Tier 3 | Distribution | 2006-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006719 | 400797968 | High Sign | HFTD Tier 2 | Distribution | 2006-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006720 | 400808056 | Molding | HFTD Tier 2 | Distribution | 2006-05-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006721 | 400742199 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006722 | 400814007 | Insulator | HFTD Tier 2 | Distribution | 2006-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006723 | 400815772 | Molding | HFTD Tier 2 | Distribution | 2006-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006724 | 400855755 | Molding | HFTD Tier 2 | Distribution | 2006-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006725 | 400858790 | High Sign | HFTD Tier 3 | Distribution | 2006-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006726 | 400861899 | High Sign | HFTD Tier 3 | Distribution | 2006-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006727 | 400929130 | Riser/Conduit | HFTD Tier 3 | Distribution | 2006-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006728 | 403046436 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006729 | 400052297 | High Sign | HFTD Tier 3 | Distribution | 2006-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006730 | 400734973 | Molding | HFTD Tier 3 | Distribution | 2006-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006731 | 400780577 | High Sign | HFTD Tier 3 | Distribution | 2006-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006732 | 400840936 | Molding | HFTD Tier 2 | Distribution | 2006-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006733 | 400842661 | High Sign | HFTD Tier 3 | Distribution | 2006-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006734 | 400879780 | Molding | HFTD Tier 2 | Distribution | 2006-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006735 | 400892415 | Molding | HFTD Tier 3 | Distribution | 2006-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006736 | 400566412 | Molding | HFTD Tier 2 | Distribution | 2006-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006737 | 400742642 | High Sign | HFTD Tier 3 | Distribution | 2006-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006738 | 400781019 | Molding | HFTD Tier 3 | Distribution | 2006-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006739 | 400808489 | High Sign | HFTD Tier 3 | Distribution | 2006-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006740 | 400550711 | Molding | HFTD Tier 3 | Distribution | 2006-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006741 | 400571953 | Molding | HFTD Tier 3 | Distribution | 2006-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006742 | 400791085 | Molding | HFTD Tier 2 | Distribution | 2006-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006743 | 400883961 | High Sign | HFTD Tier 3 | Distribution | 2006-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006744 | 400567166 | Insulator | HFTD Tier 2 | Distribution | 2006-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006745 | 400576056 | Molding | HFTD Tier 2 | Distribution | 2006-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006746 | 400579992 | Guy | HFTD Tier 2 | Distribution | 2006-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006747 | 400794584 | Molding | HFTD Tier 2 | Distribution | 2006-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006748 | 400798182 | Molding | HFTD Tier 2 | Distribution | 2006-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006749 | 400830152 | Guy | HFTD Tier 2 | Distribution | 2006-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006750 | 400832039 | Guy | HFTD Tier 2 | Distribution | 2006-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006751 | 400834311 | High Sign | HFTD Tier 2 | Distribution | 2006-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006752 | 400928585 | Molding | HFTD Tier 2 | Distribution | 2006-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006753 | 400811828 | Molding | HFTD Tier 3 | Distribution | 2006-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006754 | 400940265 | Molding | HFTD Tier 3 | Distribution | 2006-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006755 | 400604712 | High Sign | HFTD Tier 2 | Distribution | 2006-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006756 | 400815253 | High Sign | HFTD Tier 2 | Distribution | 2006-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006757 | 400823249 | High Sign | HFTD Tier 2 | Distribution | 2006-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006758 | 400858960 | Molding | HFTD Tier 2 | Distribution | 2006-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006759 | 400861910 | Molding | HFTD Tier 2 | Distribution | 2006-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006760 | 400870830 | Molding | HFTD Tier 2 | Distribution | 2006-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006761 | 403047142 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006762 | 400614650 | Molding | HFTD Tier 2 | Distribution | 2006-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006763 | 400875299 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006764 | 400883902 | Molding | HFTD Tier 3 | Distribution | 2006-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006765 | 400937885 | High Sign | HFTD Tier 2 | Distribution | 2006-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006766 | 400938317 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006767 | 400569946 | High Sign | HFTD Tier 2 | Distribution | 2006-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006768 | 400634351 | Molding | HFTD Tier 2 | Distribution | 2006-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006769 | 400842851 | High Sign | HFTD Tier 2 | Distribution | 2006-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006770 | 400846233 | Guy | HFTD Tier 2 | Distribution | 2006-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006771 | 400893459 | Molding | HFTD Tier 2 | Distribution | 2006-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006772 | 400896469 | Molding | HFTD Tier 2 | Distribution | 2006-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006773 | 400989011 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006774 | 400859917 | Molding | HFTD Tier 2 | Distribution | 2006-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006775 | 400866445 | Molding | HFTD Tier 2 | Distribution | 2006-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006776 | 400931994 | High Sign | HFTD Tier 2 | Distribution | 2006-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006777 | 400676607 | Molding | HFTD Tier 2 | Distribution | 2006-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006778 | 400676656 | Guy | HFTD Tier 2 | Distribution | 2006-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006779 | 400677100 | Molding | HFTD Tier 2 | Distribution | 2006-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006780 | 400678432 | High Sign | HFTD Tier 2 | Distribution | 2006-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006781 | 400888998 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006782 | 400559685 | High Sign | HFTD Tier 2 | Distribution | 2006-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006783 | 400630676 | Molding | HFTD Tier 2 | Distribution | 2006-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006784 | 400702653 | Guy | HFTD Tier 2 | Distribution | 2006-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006785 | 400907876 | Guy | HFTD Tier 2 | Distribution | 2006-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006786 | 400913656 | Molding | HFTD Tier 2 | Distribution | 2006-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006787 | 400915556 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006788 | 400934340 | High Sign | HFTD Tier 3 | Distribution | 2006-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006789 | 400581799 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006790 | 400589798 | Insulator | HFTD Tier 2 | Distribution | 2006-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006791 | 400591218 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006792 | 400655625 | Molding | HFTD Tier 2 | Distribution | 2006-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006793 | 400720816 | Molding | HFTD Tier 2 | Distribution | 2006-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006794 | 400727544 | High Sign | HFTD Tier 2 | Distribution | 2006-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006795 | 400931697 | Insulator | HFTD Tier 2 | Distribution | 2006-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006796 | 400933104 | Molding | HFTD Tier 2 | Distribution | 2006-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006797 | 400934203 | Molding | HFTD Tier 2 | Distribution | 2006-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006798 | 400936296 | Molding | HFTD Tier 2 | Distribution | 2006-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006799 | 400555106 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006800 | 400594778 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006801 | 400600475 | High Sign | HFTD Tier 2 | Distribution | 2006-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006802 | 400567082 | High Sign | HFTD Tier 3 | Distribution | 2006-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006803 | 400582451 | Insulator | HFTD Tier 2 | Distribution | 2006-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006804 | 400583109 | High Sign | HFTD Tier 2 | Distribution | 2006-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006805 | 400594714 | Molding | HFTD Tier 2 | Distribution | 2006-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006806 | 400627416 | Molding | HFTD Tier 2 | Distribution | 2006-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006807 | 400631471 | High Sign | HFTD Tier 2 | Distribution | 2006-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006808 | 400681204 | High Sign | HFTD Tier 3 | Distribution | 2006-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006809 | 400685241 | High Sign | HFTD Tier 3 | Distribution | 2006-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006810 | 400702463 | Molding | HFTD Tier 2 | Distribution | 2006-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006811 | 400719461 | High Sign | HFTD Tier 2 | Distribution | 2006-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006812 | 400748170 | High Sign | HFTD Tier 3 | Distribution | 2006-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006813 | 400749582 | High Sign | HFTD Tier 3 | Distribution | 2006-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006814 | 400775505 | High Sign | HFTD Tier 2 | Distribution | 2006-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006815 | 400784125 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006816 | 400627932 | High Sign | HFTD Tier 2 | Distribution | 2006-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006817 | 400660247 | High Sign | HFTD Tier 2 | Distribution | 2006-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006818 | 400672054 | Molding | HFTD Tier 2 | Distribution | 2006-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006819 | 400784303 | High Sign | HFTD Tier 2 | Distribution | 2006-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006820 | 400796758 | Molding | HFTD Tier 2 | Distribution | 2006-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006821 | 401516933 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006822 | 415075950 | High Sign | HFTD Tier 2 | Distribution | 2006-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006823 | 400047555 | Molding | HFTD Tier 2 | Distribution | 2006-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006824 | 400128957 | Guy | HFTD Tier 2 | Distribution | 2006-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006825 | 400663283 | Riser/Conduit | HFTD Tier 3 | Distribution | 2006-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006826 | 400792096 | High Sign | HFTD Tier 3 | Distribution | 2006-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006827 | 400793876 | Molding | HFTD Tier 3 | Distribution | 2006-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006828 | 400814997 | High Sign | HFTD Tier 3 | Distribution | 2006-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006829 | 400136465 | High Sign | HFTD Tier 2 | Distribution | 2006-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006830 | 400688147 | High Sign | HFTD Tier 2 | Distribution | 2006-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006831 | 400690579 | High Sign | HFTD Tier 2 | Distribution | 2006-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006832 | 400694989 | High Sign | HFTD Tier 2 | Distribution | 2006-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006833 | 400705949 | High Sign | HFTD Tier 3 | Distribution | 2006-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006834 | 400726389 | High Sign | HFTD Tier 2 | Distribution | 2006-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006835 | 400776478 | High Sign | HFTD Tier 2 | Distribution | 2006-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006836 | 400785963 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006837 | 400790493 | High Sign | HFTD Tier 2 | Distribution | 2006-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006838 | 400790505 | Molding | HFTD Tier 2 | Distribution | 2006-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006839 | 400836680 | High Sign | HFTD Tier 3 | Distribution | 2006-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006840 | 400840288 | Molding | HFTD Tier 3 | Distribution | 2006-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006841 | 400860736 | Molding | HFTD Tier 2 | Distribution | 2006-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006842 | 400862803 | Molding | HFTD Tier 2 | Distribution | 2006-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006843 | 400887533 | Molding | HFTD Tier 3 | Distribution | 2006-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006844 | 401518057 | Cable/Conductor | HFTD Tier 3 | Distribution | 2006-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006845 | 400088915 | Riser/Conduit | HFTD Tier 2 | Distribution | 2006-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006846 | 400708112 | Molding | HFTD Tier 2 | Distribution | 2006-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006847 | 400740952 | Molding | HFTD Tier 2 | Distribution | 2006-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006848 | 400741575 | High Sign | HFTD Tier 2 | Distribution | 2006-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006849 | 400750940 | High Sign | HFTD Tier 3 | Distribution | 2006-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006850 | 400808409 | High Sign | HFTD Tier 2 | Distribution | 2006-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006851 | 400808607 | Molding | HFTD Tier 2 | Distribution | 2006-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006852 | 400890807 | High Sign | HFTD Tier 3 | Distribution | 2006-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006853 | 400894552 | High Sign | HFTD Tier 3 | Distribution | 2006-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006854 | 400721705 | High Sign | HFTD Tier 3 | Distribution | 2006-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006855 | 400729815 | Riser/Conduit | HFTD Tier 2 | Distribution | 2006-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006856 | 400740031 | High Sign | HFTD Tier 2 | Distribution | 2006-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006857 | 400746094 | Molding | HFTD Tier 2 | Distribution | 2006-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006858 | 400746914 | Molding | HFTD Tier 2 | Distribution | 2006-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006859 | 400766701 | Molding | HFTD Tier 2 | Distribution | 2006-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006860 | 400771102 | High Sign | HFTD Tier 2 | Distribution | 2006-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006861 | 400772007 | High Sign | HFTD Tier 2 | Distribution | 2006-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006862 | 400816425 | High Sign | HFTD Tier 3 | Distribution | 2006-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006863 | 400834844 | Molding | HFTD Tier 2 | Distribution | 2006-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006864 | 400834878 | Molding | HFTD Tier 2 | Distribution | 2006-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006865 | 400837529 | Molding | HFTD Tier 2 | Distribution | 2006-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006866 | 400837574 | Molding | HFTD Tier 2 | Distribution | 2006-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006867 | 400904438 | High Sign | HFTD Tier 2 | Distribution | 2006-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006868 | 400907922 | High Sign | HFTD Tier 2 | Distribution | 2006-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006869 | 400276669 | High Sign | HFTD Tier 3 | Distribution | 2006-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006870 | 400794714 | High Sign | HFTD Tier 2 | Distribution | 2006-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006871 | 400798297 | Molding | HFTD Tier 2 | Distribution | 2006-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006872 | 400860149 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006873 | 400871465 | High Sign | HFTD Tier 3 | Distribution | 2006-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006874 | 400941094 | Insulator | HFTD Tier 2 | Distribution | 2006-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006875 | 400942617 | High Sign | HFTD Tier 2 | Distribution | 2006-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006876 | 400062699 | Molding | HFTD Tier 2 | Distribution | 2006-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006877 | 400064160 | Ground | HFTD Tier 2 | Distribution | 2006-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006878 | 400093118 | Molding | HFTD Tier 2 | Distribution | 2006-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006879 | 400103409 | Molding | HFTD Tier 2 | Distribution | 2006-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006880 | 400105313 | Molding | HFTD Tier 2 | Distribution | 2006-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006881 | 400567631 | Molding | HFTD Tier 2 | Distribution | 2006-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006882 | 400597984 | Molding | HFTD Tier 2 | Distribution | 2006-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006883 | 400775213 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006884 | 400795318 | Molding | HFTD Tier 2 | Distribution | 2006-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006885 | 400814688 | Molding | HFTD Tier 2 | Distribution | 2006-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006886 | 400816581 | Molding | HFTD Tier 2 | Distribution | 2006-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006887 | 400817688 | Molding | HFTD Tier 2 | Distribution | 2006-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006888 | 400885417 | Molding | HFTD Tier 2 | Distribution | 2006-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006889 | 400886355 | Molding | HFTD Tier 2 | Distribution | 2006-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006890 | 400890867 | Guy | HFTD Tier 2 | Distribution | 2006-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006891 | 400891315 | Molding | HFTD Tier 2 | Distribution | 2006-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006892 | 400891334 | Molding | HFTD Tier 2 | Distribution | 2006-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006893 | 400893458 | High Sign | HFTD Tier 2 | Distribution | 2006-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006894 | 400580827 | Molding | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006895 | 400583282 | Termination | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006896 | 400585406 | Molding | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006897 | 400587498 | High Sign | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006898 | 400587546 | High Sign | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006899 | 400619337 | Molding | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006900 | 400620739 | Molding | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006901 | 400624984 | Molding | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006902 | 400647215 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006903 | 400795996 | High Sign | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006904 | 400801330 | High Sign | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006905 | 400810500 | High Sign | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006906 | 400810514 | Molding | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006907 | 400811934 | High Sign | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006908 | 400813480 | Molding | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006909 | 400816820 | High Sign | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006910 | 400828794 | Molding | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006911 | 400831639 | Molding | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006912 | 400833052 | Molding | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006913 | 400833068 | Molding | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006914 | 400836686 | Molding | HFTD Tier 3 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006915 | 400911653 | High Sign | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006916 | 400916402 | High Sign | HFTD Tier 2 | Distribution | 2006-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006917 | 400632711 | High Sign | HFTD Tier 3 | Distribution | 2006-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006918 | 400636862 | High Sign | HFTD Tier 2 | Distribution | 2006-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006919 | 400641283 | Molding | HFTD Tier 2 | Distribution | 2006-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006920 | 400812816 | High Sign | HFTD Tier 3 | Distribution | 2006-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006921 | 400815601 | Molding | HFTD Tier 3 | Distribution | 2006-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006922 | 400825064 | High Sign | HFTD Tier 2 | Distribution | 2006-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006923 | 400830149 | High Sign | HFTD Tier 2 | Distribution | 2006-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006924 | 400840113 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006925 | 400840135 | High Sign | HFTD Tier 3 | Distribution | 2006-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006926 | 400843089 | Molding | HFTD Tier 2 | Distribution | 2006-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006927 | 400846457 | High Sign | HFTD Tier 2 | Distribution | 2006-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006928 | 400872939 | Molding | HFTD Tier 2 | Distribution | 2006-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006929 | 400925282 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006930 | 400935636 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006931 | 401519208 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006932 | 400110718 | Guy | HFTD Tier 2 | Distribution | 2006-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006933 | 400149678 | High Sign | HFTD Tier 2 | Distribution | 2006-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006934 | 400151336 | Molding | HFTD Tier 2 | Distribution | 2006-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006935 | 400847061 | High Sign | HFTD Tier 2 | Distribution | 2006-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006936 | 400987793 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006937 | 401001205 | Cable/Conductor | HFTD Tier 3 | Distribution | 2006-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006938 | 401006604 | High Sign | HFTD Tier 3 | Distribution | 2006-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006939 | 400067853 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006940 | 400112487 | Molding | HFTD Tier 2 | Distribution | 2006-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006941 | 400147042 | High Sign | HFTD Tier 2 | Distribution | 2006-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006942 | 400150002 | High Sign | HFTD Tier 2 | Distribution | 2006-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006943 | 400574867 | High Sign | HFTD Tier 3 | Distribution | 2006-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006944 | 400576556 | High Sign | HFTD Tier 2 | Distribution | 2006-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006945 | 400588288 | High Sign | HFTD Tier 3 | Distribution | 2006-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006946 | 400601046 | Molding | HFTD Tier 3 | Distribution | 2006-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006947 | 400671962 | Insulator | HFTD Tier 2 | Distribution | 2006-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006948 | 400693678 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006949 | 400700946 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006950 | 400866394 | High Sign | HFTD Tier 2 | Distribution | 2006-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006951 | 400879971 | Insulator | HFTD Tier 2 | Distribution | 2006-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006952 | 400880094 | Molding | HFTD Tier 3 | Distribution | 2006-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006953 | 400894551 | Molding | HFTD Tier 2 | Distribution | 2006-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006954 | 400912640 | Molding | HFTD Tier 2 | Distribution | 2006-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006955 | 400068034 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006956 | 400103832 | Molding | HFTD Tier 2 | Distribution | 2006-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006957 | 400601130 | Molding | HFTD Tier 2 | Distribution | 2006-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006958 | 400627699 | Molding | HFTD Tier 3 | Distribution | 2006-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006959 | 400649563 | High Sign | HFTD Tier 2 | Distribution | 2006-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006960 | 400706128 | High Sign | HFTD Tier 3 | Distribution | 2006-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006961 | 400712785 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006962 | 400755851 | High Sign | HFTD Tier 2 | Distribution | 2006-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006963 | 400757342 | High Sign | HFTD Tier 2 | Distribution | 2006-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006964 | 400880842 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006965 | 400891446 | Molding | HFTD Tier 2 | Distribution | 2006-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006966 | 400891471 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006967 | 400722632 | High Sign | HFTD Tier 2 | Distribution | 2006-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006968 | 400724116 | Molding | HFTD Tier 2 | Distribution | 2006-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006969 | 400736659 | Molding | HFTD Tier 2 | Distribution | 2006-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006970 | 400897720 | High Sign | HFTD Tier 2 | Distribution | 2006-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006971 | 400915226 | High Sign | HFTD Tier 2 | Distribution | 2006-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006972 | 400920552 | High Sign | HFTD Tier 2 | Distribution | 2006-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006973 | 400989017 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006974 | 400579710 | High Sign | HFTD Tier 3 | Distribution | 2006-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006975 | 400629839 | High Sign | HFTD Tier 2 | Distribution | 2006-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006976 | 400649656 | Molding | HFTD Tier 3 | Distribution | 2006-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006977 | 400673982 | High Sign | HFTD Tier 3 | Distribution | 2006-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006978 | 400740045 | High Sign | HFTD Tier 2 | Distribution | 2006-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006979 | 400743534 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006980 | 400937394 | High Sign | HFTD Tier 2 | Distribution | 2006-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006981 | 400938373 | Molding | HFTD Tier 2 | Distribution | 2006-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006982 | 400550011 | Guy | HFTD Tier 2 | Distribution | 2006-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006983 | 400558153 | High Sign | HFTD Tier 2 | Distribution | 2006-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006984 | 400560281 | High Sign | HFTD Tier 2 | Distribution | 2006-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006985 | 400561829 | Molding | HFTD Tier 2 | Distribution | 2006-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006986 | 400565357 | High Sign | HFTD Tier 2 | Distribution | 2006-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006987 | 400566382 | Molding | HFTD Tier 2 | Distribution | 2006-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006988 | 400570566 | Molding | HFTD Tier 2 | Distribution | 2006-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006989 | 400653595 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006990 | 400657186 | Insulator | HFTD Tier 2 | Distribution | 2006-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006991 | 400658363 | High Sign | HFTD Tier 2 | Distribution | 2006-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006992 | 400689218 | High Sign | HFTD Tier 2 | Distribution | 2006-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006993 | 400758535 | Molding | HFTD Tier 2 | Distribution | 2006-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006994 | 400761465 | High Sign | HFTD Tier 2 | Distribution | 2006-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006995 | 400773024 | High Sign | HFTD Tier 3 | Distribution | 2006-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006996 | 400936249 | High Sign | HFTD Tier 2 | Distribution | 2006-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006997 | 400938685 | Molding | HFTD Tier 2 | Distribution | 2006-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006998 | 401518528 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120006999 | 400572821 | High Sign | HFTD Tier 2 | Distribution | 2006-06-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007000 | 400597113 | High Sign | HFTD Tier 3 | Distribution | 2006-06-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007001 | 400567781 | High Sign | HFTD Tier 3 | Distribution | 2006-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007002 | 400568296 | Molding | HFTD Tier 2 | Distribution | 2006-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007003 | 400570754 | High Sign | HFTD Tier 2 | Distribution | 2006-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007004 | 400578262 | High Sign | HFTD Tier 2 | Distribution | 2006-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007005 | 400584184 | Molding | HFTD Tier 2 | Distribution | 2006-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007006 | 400589962 | Molding | HFTD Tier 2 | Distribution | 2006-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007007 | 400589979 | Molding | HFTD Tier 2 | Distribution | 2006-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007008 | 400594978 | High Sign | HFTD Tier 2 | Distribution | 2006-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007009 | 400626392 | Molding | HFTD Tier 3 | Distribution | 2006-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007010 | 400633607 | High Sign | HFTD Tier 3 | Distribution | 2006-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007011 | 400778971 | High Sign | HFTD Tier 2 | Distribution | 2006-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007012 | 400782174 | Molding | HFTD Tier 2 | Distribution | 2006-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007013 | 400794751 | Molding | HFTD Tier 2 | Distribution | 2006-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007014 | 401001728 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007015 | 401463248 | Guy | HFTD Tier 2 | Distribution | 2006-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007016 | 401519196 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007017 | 401519255 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007018 | 401522666 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007019 | 400127489 | Molding | HFTD Tier 3 | Distribution | 2006-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007020 | 400597370 | High Sign | HFTD Tier 3 | Distribution | 2006-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007021 | 400609140 | High Sign | HFTD Tier 3 | Distribution | 2006-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007022 | 400613908 | High Sign | HFTD Tier 3 | Distribution | 2006-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007023 | 400617816 | High Sign | HFTD Tier 3 | Distribution | 2006-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007024 | 400617831 | High Sign | HFTD Tier 2 | Distribution | 2006-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007025 | 400701229 | High Sign | HFTD Tier 3 | Distribution | 2006-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007026 | 400797049 | High Sign | HFTD Tier 3 | Distribution | 2006-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007027 | 400798373 | High Sign | HFTD Tier 2 | Distribution | 2006-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007028 | 400799557 | Molding | HFTD Tier 3 | Distribution | 2006-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007029 | 400623045 | High Sign | HFTD Tier 2 | Distribution | 2006-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007030 | 400626590 | High Sign | HFTD Tier 2 | Distribution | 2006-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007031 | 400632327 | Insulator | HFTD Tier 2 | Distribution | 2006-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007032 | 400643550 | High Sign | HFTD Tier 2 | Distribution | 2006-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007033 | 400647758 | Molding | HFTD Tier 3 | Distribution | 2006-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007034 | 400676654 | Cable/Conductor | HFTD Tier 3 | Distribution | 2006-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007035 | 400727987 | Molding | HFTD Tier 2 | Distribution | 2006-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007036 | 400844421 | Molding | HFTD Tier 3 | Distribution | 2006-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007037 | 400643816 | Molding | HFTD Tier 2 | Distribution | 2006-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007038 | 400841886 | High Sign | HFTD Tier 3 | Distribution | 2006-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007039 | 400845225 | Molding | HFTD Tier 3 | Distribution | 2006-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007040 | 413834621 | High Sign | HFTD Tier 3 | Distribution | 2006-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007041 | 400667264 | High Sign | HFTD Tier 2 | Distribution | 2006-06-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007042 | 400689000 | High Sign | HFTD Tier 2 | Distribution | 2006-06-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007043 | 400692557 | High Sign | HFTD Tier 3 | Distribution | 2006-06-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007044 | 400731169 | Molding | HFTD Tier 3 | Distribution | 2006-06-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007045 | 400763294 | High Sign | HFTD Tier 2 | Distribution | 2006-06-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007046 | 400784461 | High Sign | HFTD Tier 3 | Distribution | 2006-06-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007047 | 400871134 | High Sign | HFTD Tier 2 | Distribution | 2006-06-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007048 | 400873179 | High Sign | HFTD Tier 2 | Distribution | 2006-06-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007049 | 400874946 | High Sign | HFTD Tier 2 | Distribution | 2006-06-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007050 | 400876789 | High Sign | HFTD Tier 2 | Distribution | 2006-06-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007051 | 400083009 | Molding | HFTD Tier 2 | Distribution | 2006-07-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007052 | 400677273 | High Sign | HFTD Tier 2 | Distribution | 2006-07-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007053 | 400679011 | High Sign | HFTD Tier 2 | Distribution | 2006-07-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007054 | 400693724 | Molding | HFTD Tier 2 | Distribution | 2006-07-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007055 | 400707970 | Molding | HFTD Tier 3 | Distribution | 2006-07-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007056 | 400775395 | High Sign | HFTD Tier 2 | Distribution | 2006-07-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007057 | 400878313 | Molding | HFTD Tier 2 | Distribution | 2006-07-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007058 | 400920670 | Molding | HFTD Tier 3 | Distribution | 2006-07-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007059 | 400561524 | Molding | HFTD Tier 3 | Distribution | 2006-07-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007060 | 400712747 | High Sign | HFTD Tier 2 | Distribution | 2006-07-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007061 | 400775709 | Molding | HFTD Tier 2 | Distribution | 2006-07-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007062 | 400777406 | High Sign | HFTD Tier 2 | Distribution | 2006-07-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007063 | 400783688 | Molding | HFTD Tier 2 | Distribution | 2006-07-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007064 | 400797769 | Molding | HFTD Tier 3 | Distribution | 2006-07-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007065 | 400894084 | Molding | HFTD Tier 2 | Distribution | 2006-07-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007066 | 400926962 | Molding | HFTD Tier 3 | Distribution | 2006-07-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007067 | 400712170 | Molding | HFTD Tier 2 | Distribution | 2006-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007068 | 400713658 | High Sign | HFTD Tier 3 | Distribution | 2006-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007069 | 400713928 | Molding | HFTD Tier 3 | Distribution | 2006-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007070 | 400727679 | Molding | HFTD Tier 2 | Distribution | 2006-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007071 | 400798769 | Molding | HFTD Tier 2 | Distribution | 2006-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007072 | 401522913 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007073 | 400756864 | High Sign | HFTD Tier 3 | Distribution | 2006-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007074 | 400760908 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-07-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007075 | 400764799 | High Sign | HFTD Tier 2 | Distribution | 2006-07-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007076 | 400764815 | High Sign | HFTD Tier 2 | Distribution | 2006-07-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007077 | 400775123 | Molding | HFTD Tier 3 | Distribution | 2006-07-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007078 | 400823587 | High Sign | HFTD Tier 2 | Distribution | 2006-07-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007079 | 400603724 | Guy | HFTD Tier 2 | Distribution | 2006-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007080 | 400763891 | High Sign | HFTD Tier 2 | Distribution | 2006-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007081 | 400809276 | Molding | HFTD Tier 3 | Distribution | 2006-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007082 | 400810085 | Molding | HFTD Tier 3 | Distribution | 2006-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007083 | 401520937 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007084 | 401520978 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007085 | 400617552 | High Sign | HFTD Tier 2 | Distribution | 2006-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007086 | 400775568 | Molding | HFTD Tier 2 | Distribution | 2006-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007087 | 400778900 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007088 | 400803479 | High Sign | HFTD Tier 3 | Distribution | 2006-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007089 | 400806114 | Molding | HFTD Tier 3 | Distribution | 2006-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007090 | 400810588 | High Sign | HFTD Tier 3 | Distribution | 2006-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007091 | 400813575 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007092 | 400869142 | Molding | HFTD Tier 2 | Distribution | 2006-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007093 | 400807595 | Molding | HFTD Tier 2 | Distribution | 2006-07-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007094 | 400875530 | Molding | HFTD Tier 3 | Distribution | 2006-07-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007095 | 403046181 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007096 | 403047041 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007097 | 400574229 | High Sign | HFTD Tier 3 | Distribution | 2006-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007098 | 400830469 | High Sign | HFTD Tier 2 | Distribution | 2006-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007099 | 400847777 | Molding | HFTD Tier 3 | Distribution | 2006-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007100 | 400866915 | Molding | HFTD Tier 3 | Distribution | 2006-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007101 | 400881743 | High Sign | HFTD Tier 3 | Distribution | 2006-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007102 | 400901965 | Guy | HFTD Tier 3 | Distribution | 2006-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007103 | 400682775 | High Sign | HFTD Tier 2 | Distribution | 2006-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007104 | 400892938 | Molding | HFTD Tier 3 | Distribution | 2006-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007105 | 400917545 | Molding | HFTD Tier 3 | Distribution | 2006-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007106 | 400933972 | High Sign | HFTD Tier 3 | Distribution | 2006-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007107 | 400936049 | Molding | HFTD Tier 2 | Distribution | 2006-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007108 | 400170764 | Molding | HFTD Tier 3 | Distribution | 2006-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007109 | 400547030 | Molding | HFTD Tier 2 | Distribution | 2006-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007110 | 400552902 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007111 | 400779271 | Riser/Conduit | HFTD Tier 3 | Distribution | 2006-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007112 | 400858112 | High Sign | HFTD Tier 3 | Distribution | 2006-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007113 | 400886555 | Molding | HFTD Tier 3 | Distribution | 2006-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007114 | 400564864 | High Sign | HFTD Tier 3 | Distribution | 2006-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007115 | 400720685 | High Sign | HFTD Tier 3 | Distribution | 2006-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007116 | 400878830 | Molding | HFTD Tier 3 | Distribution | 2006-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007117 | 400884633 | Molding | HFTD Tier 3 | Distribution | 2006-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007118 | 400887272 | High Sign | HFTD Tier 3 | Distribution | 2006-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007119 | 400172891 | High Sign | HFTD Tier 3 | Distribution | 2006-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007120 | 400636218 | High Sign | HFTD Tier 3 | Distribution | 2006-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007121 | 400898254 | High Sign | HFTD Tier 3 | Distribution | 2006-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007122 | 400914447 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007123 | 400916285 | High Sign | HFTD Tier 3 | Distribution | 2006-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007124 | 400561463 | Molding | HFTD Tier 2 | Distribution | 2006-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007125 | 400597780 | Molding | HFTD Tier 3 | Distribution | 2006-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007126 | 400770786 | Molding | HFTD Tier 2 | Distribution | 2006-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007127 | 400914246 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007128 | 400915067 | High Sign | HFTD Tier 2 | Distribution | 2006-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007129 | 400921707 | Molding | HFTD Tier 3 | Distribution | 2006-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007130 | 400929931 | Molding | HFTD Tier 3 | Distribution | 2006-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007131 | 400935464 | Guy | HFTD Tier 3 | Distribution | 2006-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007132 | 400941824 | Molding | HFTD Tier 3 | Distribution | 2006-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007133 | 400635543 | High Sign | HFTD Tier 2 | Distribution | 2006-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007134 | 400641394 | High Sign | HFTD Tier 3 | Distribution | 2006-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007135 | 400646040 | Molding | HFTD Tier 3 | Distribution | 2006-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007136 | 400670857 | High Sign | HFTD Tier 3 | Distribution | 2006-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007137 | 400780790 | High Sign | HFTD Tier 3 | Distribution | 2006-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007138 | 400784746 | High Sign | HFTD Tier 3 | Distribution | 2006-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007139 | 400784771 | High Sign | HFTD Tier 3 | Distribution | 2006-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007140 | 400943263 | Molding | HFTD Tier 3 | Distribution | 2006-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007141 | 400645172 | Guy | HFTD Tier 3 | Distribution | 2006-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007142 | 400779947 | High Sign | HFTD Tier 3 | Distribution | 2006-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007143 | 400779971 | High Sign | HFTD Tier 3 | Distribution | 2006-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007144 | 400781755 | High Sign | HFTD Tier 3 | Distribution | 2006-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007145 | 400941240 | High Sign | HFTD Tier 3 | Distribution | 2006-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007146 | 400555823 | Molding | HFTD Tier 3 | Distribution | 2006-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007147 | 400575048 | Molding | HFTD Tier 3 | Distribution | 2006-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007148 | 400575430 | High Sign | HFTD Tier 2 | Distribution | 2006-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007149 | 400579511 | Molding | HFTD Tier 2 | Distribution | 2006-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007150 | 400599167 | High Sign | HFTD Tier 2 | Distribution | 2006-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007151 | 400724035 | Molding | HFTD Tier 3 | Distribution | 2006-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007152 | 400812525 | High Sign | HFTD Tier 2 | Distribution | 2006-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007153 | 400818148 | High Sign | HFTD Tier 3 | Distribution | 2006-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007154 | 400596158 | High Sign | HFTD Tier 2 | Distribution | 2006-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007155 | 400712288 | High Sign | HFTD Tier 2 | Distribution | 2006-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007156 | 400609068 | Molding | HFTD Tier 2 | Distribution | 2006-08-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007157 | 400707077 | Guy | HFTD Tier 2 | Distribution | 2006-08-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007158 | 400621184 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-08-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007159 | 400624307 | High Sign | HFTD Tier 3 | Distribution | 2006-08-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007160 | 400648658 | Molding | HFTD Tier 3 | Distribution | 2006-08-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007161 | 400659397 | Guy | HFTD Tier 3 | Distribution | 2006-08-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007162 | 400854511 | Molding | HFTD Tier 3 | Distribution | 2006-08-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007163 | 400883011 | Molding | HFTD Tier 3 | Distribution | 2006-08-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007164 | 400630409 | High Sign | HFTD Tier 3 | Distribution | 2006-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007165 | 400682136 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007166 | 400710648 | High Sign | HFTD Tier 3 | Distribution | 2006-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007167 | 400733609 | Molding | HFTD Tier 3 | Distribution | 2006-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007168 | 400735020 | Molding | HFTD Tier 3 | Distribution | 2006-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007169 | 400735035 | Riser/Conduit | HFTD Tier 3 | Distribution | 2006-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007170 | 400736810 | Molding | HFTD Tier 3 | Distribution | 2006-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007171 | 400868549 | Molding | HFTD Tier 3 | Distribution | 2006-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007172 | 400661324 | Molding | HFTD Tier 2 | Distribution | 2006-08-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007173 | 400674038 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-08-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007174 | 400700545 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-08-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007175 | 400882443 | Molding | HFTD Tier 3 | Distribution | 2006-08-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007176 | 400185413 | Molding | HFTD Tier 2 | Distribution | 2006-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007177 | 400185553 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007178 | 400782916 | High Sign | HFTD Tier 3 | Distribution | 2006-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007179 | 400922530 | Molding | HFTD Tier 2 | Distribution | 2006-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007180 | 400689767 | Molding | HFTD Tier 3 | Distribution | 2006-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007181 | 400737118 | Molding | HFTD Tier 3 | Distribution | 2006-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007182 | 400728391 | Molding | HFTD Tier 3 | Distribution | 2006-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007183 | 400750533 | Molding | HFTD Tier 3 | Distribution | 2006-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007184 | 400765369 | High Sign | HFTD Tier 3 | Distribution | 2006-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007185 | 400785132 | High Sign | HFTD Tier 3 | Distribution | 2006-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007186 | 400794169 | High Sign | HFTD Tier 2 | Distribution | 2006-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007187 | 400805350 | Molding | HFTD Tier 3 | Distribution | 2006-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007188 | 400808131 | Molding | HFTD Tier 3 | Distribution | 2006-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007189 | 400536798 | High Sign | HFTD Tier 2 | Distribution | 2006-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007190 | 400560148 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007191 | 400751351 | High Sign | HFTD Tier 2 | Distribution | 2006-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007192 | 400797231 | High Sign | HFTD Tier 2 | Distribution | 2006-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007193 | 400805586 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007194 | 400125264 | High Sign | HFTD Tier 3 | Distribution | 2006-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007195 | 400148981 | High Sign | HFTD Tier 3 | Distribution | 2006-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007196 | 400152437 | High Sign | HFTD Tier 3 | Distribution | 2006-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007197 | 400155819 | High Sign | HFTD Tier 3 | Distribution | 2006-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007198 | 400157750 | High Sign | HFTD Tier 3 | Distribution | 2006-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007199 | 400189806 | High Sign | HFTD Tier 3 | Distribution | 2006-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007200 | 400755318 | Molding | HFTD Tier 2 | Distribution | 2006-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007201 | 400766129 | High Sign | HFTD Tier 3 | Distribution | 2006-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007202 | 400769228 | Molding | HFTD Tier 2 | Distribution | 2006-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007203 | 400813238 | Molding | HFTD Tier 3 | Distribution | 2006-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007204 | 400813260 | Molding | HFTD Tier 3 | Distribution | 2006-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007205 | 400604359 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007206 | 400619681 | Cable/Conductor | HFTD Tier 3 | Distribution | 2006-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007207 | 400776026 | Molding | HFTD Tier 3 | Distribution | 2006-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007208 | 400800431 | High Sign | HFTD Tier 3 | Distribution | 2006-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007209 | 400841171 | High Sign | HFTD Tier 3 | Distribution | 2006-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007210 | 400849833 | Molding | HFTD Tier 3 | Distribution | 2006-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007211 | 400613745 | Molding | HFTD Tier 3 | Distribution | 2006-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007212 | 400633128 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007213 | 400647934 | High Sign | HFTD Tier 3 | Distribution | 2006-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007214 | 400771687 | Molding | HFTD Tier 3 | Distribution | 2006-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007215 | 400805120 | Guy | HFTD Tier 3 | Distribution | 2006-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007216 | 400806739 | Molding | HFTD Tier 3 | Distribution | 2006-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007217 | 400808436 | Molding | HFTD Tier 3 | Distribution | 2006-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007218 | 400851427 | Molding | HFTD Tier 3 | Distribution | 2006-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007219 | 400853614 | Molding | HFTD Tier 3 | Distribution | 2006-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007220 | 400860981 | Guy | HFTD Tier 3 | Distribution | 2006-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007221 | 400806504 | Molding | HFTD Tier 3 | Distribution | 2006-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007222 | 400647256 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007223 | 400681014 | Molding | HFTD Tier 3 | Distribution | 2006-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007224 | 400823036 | High Sign | HFTD Tier 2 | Distribution | 2006-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007225 | 400824512 | High Sign | HFTD Tier 3 | Distribution | 2006-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007226 | 401000401 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007227 | 400166303 | Guy | HFTD Tier 2 | Distribution | 2006-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007228 | 400817377 | Guy | HFTD Tier 2 | Distribution | 2006-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007229 | 400836571 | Guy | HFTD Tier 2 | Distribution | 2006-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007230 | 400697166 | Molding | HFTD Tier 2 | Distribution | 2006-08-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007231 | 400698803 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-08-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007232 | 400872900 | High Sign | HFTD Tier 3 | Distribution | 2006-08-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007233 | 400927239 | High Sign | HFTD Tier 3 | Distribution | 2006-08-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007234 | 400934848 | High Sign | HFTD Tier 2 | Distribution | 2006-08-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007235 | 400711316 | High Sign | HFTD Tier 3 | Distribution | 2006-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007236 | 400752119 | Guy | HFTD Tier 2 | Distribution | 2006-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007237 | 400844285 | High Sign | HFTD Tier 3 | Distribution | 2006-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007238 | 400874602 | Guy | HFTD Tier 3 | Distribution | 2006-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007239 | 400874681 | Riser/Conduit | HFTD Tier 2 | Distribution | 2006-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007240 | 400876275 | Molding | HFTD Tier 3 | Distribution | 2006-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007241 | 400878231 | Molding | HFTD Tier 3 | Distribution | 2006-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007242 | 400879898 | Molding | HFTD Tier 3 | Distribution | 2006-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007243 | 400928043 | High Sign | HFTD Tier 2 | Distribution | 2006-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007244 | 400940591 | Molding | HFTD Tier 2 | Distribution | 2006-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007245 | 400554584 | Molding | HFTD Tier 3 | Distribution | 2006-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007246 | 400562492 | Molding | HFTD Tier 3 | Distribution | 2006-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007247 | 400571995 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007248 | 400722641 | High Sign | HFTD Tier 2 | Distribution | 2006-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007249 | 400726254 | Molding | HFTD Tier 3 | Distribution | 2006-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007250 | 400744146 | Molding | HFTD Tier 3 | Distribution | 2006-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007251 | 400866879 | High Sign | HFTD Tier 3 | Distribution | 2006-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007252 | 400915247 | High Sign | HFTD Tier 2 | Distribution | 2006-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007253 | 400916227 | High Sign | HFTD Tier 3 | Distribution | 2006-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007254 | 400933264 | High Sign | HFTD Tier 3 | Distribution | 2006-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007255 | 400934701 | High Sign | HFTD Tier 3 | Distribution | 2006-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007256 | 400938348 | Molding | HFTD Tier 2 | Distribution | 2006-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007257 | 400560063 | High Sign | HFTD Tier 3 | Distribution | 2006-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007258 | 400562611 | High Sign | HFTD Tier 3 | Distribution | 2006-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007259 | 400587087 | Molding | HFTD Tier 2 | Distribution | 2006-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007260 | 400738984 | High Sign | HFTD Tier 3 | Distribution | 2006-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007261 | 400739906 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007262 | 400746470 | High Sign | HFTD Tier 3 | Distribution | 2006-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007263 | 400753645 | Molding | HFTD Tier 2 | Distribution | 2006-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007264 | 400762623 | Guy | HFTD Tier 2 | Distribution | 2006-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007265 | 400905549 | High Sign | HFTD Tier 2 | Distribution | 2006-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007266 | 400912427 | Molding | HFTD Tier 3 | Distribution | 2006-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007267 | 400914352 | Molding | HFTD Tier 3 | Distribution | 2006-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007268 | 400914452 | High Sign | HFTD Tier 3 | Distribution | 2006-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007269 | 400991407 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007270 | 400999209 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007271 | 400771489 | High Sign | HFTD Tier 3 | Distribution | 2006-08-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007272 | 401541528 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-08-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007273 | 400162204 | High Sign | HFTD Tier 2 | Distribution | 2006-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007274 | 400552071 | Guy | HFTD Tier 2 | Distribution | 2006-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007275 | 400567264 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007276 | 400593466 | Molding | HFTD Tier 2 | Distribution | 2006-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007277 | 400600544 | Molding | HFTD Tier 2 | Distribution | 2006-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007278 | 400628024 | Molding | HFTD Tier 3 | Distribution | 2006-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007279 | 400778436 | Molding | HFTD Tier 2 | Distribution | 2006-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007280 | 400939531 | High Sign | HFTD Tier 2 | Distribution | 2006-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007281 | 400939665 | High Sign | HFTD Tier 2 | Distribution | 2006-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007282 | 400941585 | High Sign | HFTD Tier 2 | Distribution | 2006-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007283 | 400591465 | Guy | HFTD Tier 2 | Distribution | 2006-08-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007284 | 400625970 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-08-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007285 | 400805565 | Molding | HFTD Tier 3 | Distribution | 2006-08-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007286 | 400661503 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-08-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007287 | 400664531 | Guy | HFTD Tier 2 | Distribution | 2006-08-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007288 | 400822536 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-08-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007289 | 400663522 | High Sign | HFTD Tier 2 | Distribution | 2006-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007290 | 400824907 | Molding | HFTD Tier 2 | Distribution | 2006-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007291 | 400590512 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-09-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007292 | 400618342 | High Sign | HFTD Tier 2 | Distribution | 2006-09-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007293 | 400665878 | High Sign | HFTD Tier 2 | Distribution | 2006-09-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007294 | 400833451 | High Sign | HFTD Tier 2 | Distribution | 2006-09-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007295 | 400999292 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-09-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007296 | 400608393 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007297 | 400681795 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007298 | 400688129 | High Sign | HFTD Tier 3 | Distribution | 2006-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007299 | 401530738 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007300 | 400608456 | Molding | HFTD Tier 2 | Distribution | 2006-09-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007301 | 400610773 | Molding | HFTD Tier 2 | Distribution | 2006-09-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007302 | 400856276 | High Sign | HFTD Tier 3 | Distribution | 2006-09-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007303 | 400864693 | Molding | HFTD Tier 3 | Distribution | 2006-09-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007304 | 400866728 | High Sign | HFTD Tier 3 | Distribution | 2006-09-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007305 | 400632680 | Molding | HFTD Tier 3 | Distribution | 2006-09-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007306 | 400636340 | High Sign | HFTD Tier 3 | Distribution | 2006-09-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007307 | 400645278 | High Sign | HFTD Tier 3 | Distribution | 2006-09-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007308 | 400654788 | High Sign | HFTD Tier 3 | Distribution | 2006-09-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007309 | 400738303 | High Sign | HFTD Tier 3 | Distribution | 2006-09-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007310 | 400897635 | High Sign | HFTD Tier 3 | Distribution | 2006-09-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007311 | 400901092 | Molding | HFTD Tier 3 | Distribution | 2006-09-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007312 | 400901893 | Molding | HFTD Tier 2 | Distribution | 2006-09-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007313 | 400646264 | Molding | HFTD Tier 3 | Distribution | 2006-09-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007314 | 400649561 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-09-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007315 | 400674592 | Molding | HFTD Tier 2 | Distribution | 2006-09-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007316 | 400674937 | High Sign | HFTD Tier 2 | Distribution | 2006-09-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007317 | 400743826 | Molding | HFTD Tier 3 | Distribution | 2006-09-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007318 | 400662410 | Insulator | HFTD Tier 2 | Distribution | 2006-09-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007319 | 400692264 | High Sign | HFTD Tier 3 | Distribution | 2006-09-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007320 | 400737599 | High Sign | HFTD Tier 2 | Distribution | 2006-09-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007321 | 400756636 | Guy | HFTD Tier 3 | Distribution | 2006-09-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007322 | 400901913 | Molding | HFTD Tier 2 | Distribution | 2006-09-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007323 | 400918885 | Molding | HFTD Tier 2 | Distribution | 2006-09-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007324 | 400929040 | Insulator | HFTD Tier 3 | Distribution | 2006-09-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007325 | 400535635 | High Sign | HFTD Tier 2 | Distribution | 2006-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007326 | 400542605 | High Sign | HFTD Tier 2 | Distribution | 2006-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007327 | 400546120 | High Sign | HFTD Tier 2 | Distribution | 2006-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007328 | 400704824 | High Sign | HFTD Tier 2 | Distribution | 2006-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007329 | 400714565 | Molding | HFTD Tier 2 | Distribution | 2006-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007330 | 400716473 | Guy | HFTD Tier 2 | Distribution | 2006-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007331 | 400721561 | High Sign | HFTD Tier 3 | Distribution | 2006-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007332 | 400761086 | Guy | HFTD Tier 2 | Distribution | 2006-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007333 | 400768543 | Molding | HFTD Tier 3 | Distribution | 2006-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007334 | 400773908 | High Sign | HFTD Tier 2 | Distribution | 2006-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007335 | 400775666 | High Sign | HFTD Tier 2 | Distribution | 2006-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007336 | 400933552 | Guy | HFTD Tier 2 | Distribution | 2006-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007337 | 400549956 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007338 | 400562842 | Molding | HFTD Tier 2 | Distribution | 2006-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007339 | 400564420 | Molding | HFTD Tier 2 | Distribution | 2006-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007340 | 400699960 | Molding | HFTD Tier 2 | Distribution | 2006-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007341 | 400718420 | Molding | HFTD Tier 2 | Distribution | 2006-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007342 | 400731818 | Molding | HFTD Tier 2 | Distribution | 2006-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007343 | 400788725 | High Sign | HFTD Tier 2 | Distribution | 2006-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007344 | 400803101 | Guy | HFTD Tier 2 | Distribution | 2006-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007345 | 400854780 | Molding | HFTD Tier 2 | Distribution | 2006-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007346 | 401528231 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007347 | 401530681 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007348 | 401530899 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007349 | 400565513 | Molding | HFTD Tier 2 | Distribution | 2006-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007350 | 400713927 | Molding | HFTD Tier 3 | Distribution | 2006-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007351 | 400718446 | Guy | HFTD Tier 3 | Distribution | 2006-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007352 | 400175503 | High Sign | HFTD Tier 3 | Distribution | 2006-09-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007353 | 400211623 | Guy | HFTD Tier 3 | Distribution | 2006-09-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007354 | 400564093 | Molding | HFTD Tier 2 | Distribution | 2006-09-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007355 | 400728774 | Molding | HFTD Tier 2 | Distribution | 2006-09-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007356 | 400588917 | Molding | HFTD Tier 2 | Distribution | 2006-09-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007357 | 400742964 | Molding | HFTD Tier 2 | Distribution | 2006-09-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007358 | 400759789 | High Sign | HFTD Tier 2 | Distribution | 2006-09-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007359 | 400761752 | High Sign | HFTD Tier 2 | Distribution | 2006-09-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007360 | 400804051 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-09-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007361 | 400808439 | High Sign | HFTD Tier 2 | Distribution | 2006-09-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007362 | 400823730 | Molding | HFTD Tier 2 | Distribution | 2006-09-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007363 | 400607367 | Guy | HFTD Tier 2 | Distribution | 2006-09-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007364 | 400608854 | Molding | HFTD Tier 2 | Distribution | 2006-09-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007365 | 400620961 | Guy | HFTD Tier 3 | Distribution | 2006-09-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007366 | 400753376 | Guy | HFTD Tier 2 | Distribution | 2006-09-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007367 | 400767574 | Guy | HFTD Tier 2 | Distribution | 2006-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007368 | 400768115 | High Sign | HFTD Tier 2 | Distribution | 2006-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007369 | 400775720 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007370 | 400841150 | Molding | HFTD Tier 2 | Distribution | 2006-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007371 | 400776077 | Molding | HFTD Tier 2 | Distribution | 2006-09-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007372 | 400154413 | High Sign | HFTD Tier 3 | Distribution | 2006-09-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007373 | 400157674 | Molding | HFTD Tier 3 | Distribution | 2006-09-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007374 | 400219194 | Molding | HFTD Tier 3 | Distribution | 2006-09-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007375 | 400783096 | High Sign | HFTD Tier 2 | Distribution | 2006-09-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007376 | 400783856 | Molding | HFTD Tier 3 | Distribution | 2006-09-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007377 | 400655607 | Molding | HFTD Tier 3 | Distribution | 2006-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007378 | 400667626 | Molding | HFTD Tier 3 | Distribution | 2006-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007379 | 400792628 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007380 | 400794777 | Molding | HFTD Tier 2 | Distribution | 2006-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007381 | 400812720 | Molding | HFTD Tier 2 | Distribution | 2006-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007382 | 400822313 | Molding | HFTD Tier 3 | Distribution | 2006-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007383 | 400667215 | Molding | HFTD Tier 2 | Distribution | 2006-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007384 | 400696521 | Molding | HFTD Tier 3 | Distribution | 2006-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007385 | 400698973 | High Sign | HFTD Tier 2 | Distribution | 2006-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007386 | 400808963 | Molding | HFTD Tier 2 | Distribution | 2006-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007387 | 400817935 | Molding | HFTD Tier 2 | Distribution | 2006-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007388 | 400818774 | Molding | HFTD Tier 2 | Distribution | 2006-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007389 | 400829819 | High Sign | HFTD Tier 3 | Distribution | 2006-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007390 | 400843143 | Molding | HFTD Tier 3 | Distribution | 2006-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007391 | 400850367 | High Sign | HFTD Tier 2 | Distribution | 2006-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007392 | 400887143 | Molding | HFTD Tier 2 | Distribution | 2006-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007393 | 400846129 | High Sign | HFTD Tier 2 | Distribution | 2006-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007394 | 400851203 | Molding | HFTD Tier 3 | Distribution | 2006-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007395 | 400914005 | Molding | HFTD Tier 2 | Distribution | 2006-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007396 | 400915023 | High Sign | HFTD Tier 3 | Distribution | 2006-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007397 | 400539202 | Molding | HFTD Tier 2 | Distribution | 2006-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007398 | 400729916 | High Sign | HFTD Tier 2 | Distribution | 2006-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007399 | 400849551 | Molding | HFTD Tier 2 | Distribution | 2006-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007400 | 400867070 | High Sign | HFTD Tier 2 | Distribution | 2006-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007401 | 400878896 | High Sign | HFTD Tier 2 | Distribution | 2006-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007402 | 400883995 | Molding | HFTD Tier 2 | Distribution | 2006-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007403 | 400921471 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007404 | 400934885 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007405 | 400484857 | Guy | HFTD Tier 3 | Distribution | 2006-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007406 | 400726150 | High Sign | HFTD Tier 2 | Distribution | 2006-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007407 | 400848244 | High Sign | HFTD Tier 2 | Distribution | 2006-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007408 | 400855091 | Molding | HFTD Tier 2 | Distribution | 2006-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007409 | 400872527 | Molding | HFTD Tier 2 | Distribution | 2006-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007410 | 400931177 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007411 | 400934865 | Molding | HFTD Tier 2 | Distribution | 2006-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007412 | 400734278 | High Sign | HFTD Tier 3 | Distribution | 2006-10-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007413 | 400862968 | Molding | HFTD Tier 3 | Distribution | 2006-10-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007414 | 400738130 | Cable/Conductor | HFTD Tier 3 | Distribution | 2006-10-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007415 | 400902485 | High Sign | HFTD Tier 3 | Distribution | 2006-10-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007416 | 400988799 | Cable/Conductor | HFTD Tier 3 | Distribution | 2006-10-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007417 | 400571446 | High Sign | HFTD Tier 3 | Distribution | 2006-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007418 | 400773358 | Molding | HFTD Tier 2 | Distribution | 2006-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007419 | 400885768 | Molding | HFTD Tier 2 | Distribution | 2006-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007420 | 400889848 | Guy | HFTD Tier 2 | Distribution | 2006-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007421 | 400890691 | Guy | HFTD Tier 3 | Distribution | 2006-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007422 | 400919238 | High Sign | HFTD Tier 3 | Distribution | 2006-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007423 | 400769381 | Molding | HFTD Tier 2 | Distribution | 2006-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007424 | 400909165 | Molding | HFTD Tier 2 | Distribution | 2006-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007425 | 400918790 | High Sign | HFTD Tier 2 | Distribution | 2006-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007426 | 400936338 | Molding | HFTD Tier 2 | Distribution | 2006-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007427 | 400547490 | High Sign | HFTD Tier 3 | Distribution | 2006-10-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007428 | 400610438 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-10-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007429 | 400930350 | High Sign | HFTD Tier 3 | Distribution | 2006-10-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007430 | 400550892 | High Sign | HFTD Tier 3 | Distribution | 2006-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007431 | 400559321 | Riser/Conduit | HFTD Tier 3 | Distribution | 2006-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007432 | 400573698 | High Sign | HFTD Tier 3 | Distribution | 2006-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007433 | 400573716 | Guy | HFTD Tier 3 | Distribution | 2006-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007434 | 400626136 | Molding | HFTD Tier 3 | Distribution | 2006-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007435 | 400802238 | High Sign | HFTD Tier 3 | Distribution | 2006-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007436 | 400565744 | High Sign | HFTD Tier 2 | Distribution | 2006-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007437 | 400574047 | High Sign | HFTD Tier 2 | Distribution | 2006-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007438 | 400655791 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007439 | 400657865 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007440 | 400832405 | Guy | HFTD Tier 2 | Distribution | 2006-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007441 | 400594658 | Molding | HFTD Tier 3 | Distribution | 2006-10-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007442 | 400623378 | Molding | HFTD Tier 3 | Distribution | 2006-10-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007443 | 400844448 | Molding | HFTD Tier 3 | Distribution | 2006-10-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007444 | 400855443 | Molding | HFTD Tier 3 | Distribution | 2006-10-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007445 | 400165780 | Molding | HFTD Tier 2 | Distribution | 2006-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007446 | 400191116 | Molding | HFTD Tier 2 | Distribution | 2006-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007447 | 400233023 | Molding | HFTD Tier 3 | Distribution | 2006-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007448 | 400667190 | Molding | HFTD Tier 3 | Distribution | 2006-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007449 | 400622533 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-10-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007450 | 400645427 | Molding | HFTD Tier 3 | Distribution | 2006-10-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007451 | 400685246 | Molding | HFTD Tier 3 | Distribution | 2006-10-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007452 | 400688104 | Guy | HFTD Tier 3 | Distribution | 2006-10-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007453 | 400693650 | High Sign | HFTD Tier 2 | Distribution | 2006-10-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007454 | 400693722 | Molding | HFTD Tier 3 | Distribution | 2006-10-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007455 | 400726352 | Molding | HFTD Tier 3 | Distribution | 2006-10-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007456 | 400235462 | Molding | HFTD Tier 3 | Distribution | 2006-10-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007457 | 400641692 | Guy | HFTD Tier 3 | Distribution | 2006-10-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007458 | 400641725 | Molding | HFTD Tier 3 | Distribution | 2006-10-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007459 | 400643830 | Molding | HFTD Tier 3 | Distribution | 2006-10-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007460 | 400643913 | High Sign | HFTD Tier 3 | Distribution | 2006-10-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007461 | 400658963 | Guy | HFTD Tier 3 | Distribution | 2006-10-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007462 | 400659809 | Guy | HFTD Tier 3 | Distribution | 2006-10-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007463 | 400686356 | Guy | HFTD Tier 3 | Distribution | 2006-10-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007464 | 400717817 | High Sign | HFTD Tier 3 | Distribution | 2006-10-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007465 | 400727199 | Guy | HFTD Tier 3 | Distribution | 2006-10-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007466 | 400728767 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-10-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007467 | 400743535 | Guy | HFTD Tier 3 | Distribution | 2006-10-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007468 | 400888789 | Guy | HFTD Tier 3 | Distribution | 2006-10-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007469 | 400890268 | High Sign | HFTD Tier 3 | Distribution | 2006-10-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007470 | 400898955 | Guy | HFTD Tier 3 | Distribution | 2006-10-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007471 | 400665748 | Guy | HFTD Tier 2 | Distribution | 2006-10-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007472 | 400726327 | Molding | HFTD Tier 3 | Distribution | 2006-10-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007473 | 400737927 | High Sign | HFTD Tier 2 | Distribution | 2006-10-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007474 | 400746307 | High Sign | HFTD Tier 2 | Distribution | 2006-10-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007475 | 400671526 | High Sign | HFTD Tier 3 | Distribution | 2006-10-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007476 | 400545044 | Guy | HFTD Tier 3 | Distribution | 2006-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007477 | 400692222 | High Sign | HFTD Tier 3 | Distribution | 2006-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007478 | 400692269 | Molding | HFTD Tier 3 | Distribution | 2006-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007479 | 400728808 | Guy | HFTD Tier 3 | Distribution | 2006-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007480 | 400745679 | Molding | HFTD Tier 3 | Distribution | 2006-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007481 | 400920241 | High Sign | HFTD Tier 3 | Distribution | 2006-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007482 | 401533709 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007483 | 400193261 | Molding | HFTD Tier 3 | Distribution | 2006-10-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007484 | 400196001 | Molding | HFTD Tier 3 | Distribution | 2006-10-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007485 | 400685167 | Molding | HFTD Tier 3 | Distribution | 2006-10-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007486 | 400697231 | Guy | HFTD Tier 3 | Distribution | 2006-10-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007487 | 400702907 | Guy | HFTD Tier 3 | Distribution | 2006-10-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007488 | 400768283 | Guy | HFTD Tier 3 | Distribution | 2006-10-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007489 | 400557568 | High Sign | HFTD Tier 3 | Distribution | 2006-10-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007490 | 400710927 | High Sign | HFTD Tier 3 | Distribution | 2006-10-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007491 | 400760436 | Molding | HFTD Tier 3 | Distribution | 2006-10-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007492 | 400771302 | High Sign | HFTD Tier 3 | Distribution | 2006-10-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007493 | 400776054 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-10-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007494 | 400238326 | Molding | HFTD Tier 3 | Distribution | 2006-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007495 | 400547352 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007496 | 400547376 | High Sign | HFTD Tier 3 | Distribution | 2006-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007497 | 400547401 | High Sign | HFTD Tier 3 | Distribution | 2006-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007498 | 400551220 | Molding | HFTD Tier 3 | Distribution | 2006-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007499 | 400564741 | Molding | HFTD Tier 3 | Distribution | 2006-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007500 | 400566338 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007501 | 400573265 | High Sign | HFTD Tier 3 | Distribution | 2006-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007502 | 400576495 | Molding | HFTD Tier 2 | Distribution | 2006-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007503 | 400745037 | High Sign | HFTD Tier 3 | Distribution | 2006-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007504 | 400746532 | Molding | HFTD Tier 3 | Distribution | 2006-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007505 | 400776391 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007506 | 401536508 | Cable/Conductor | HFTD Tier 3 | Distribution | 2006-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007507 | 403046035 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007508 | 400580710 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007509 | 400724926 | Molding | HFTD Tier 3 | Distribution | 2006-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007510 | 400728761 | Molding | HFTD Tier 2 | Distribution | 2006-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007511 | 400759377 | High Sign | HFTD Tier 2 | Distribution | 2006-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007512 | 400761522 | Riser/Conduit | HFTD Tier 2 | Distribution | 2006-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007513 | 400788678 | High Sign | HFTD Tier 2 | Distribution | 2006-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007514 | 400796850 | Molding | HFTD Tier 3 | Distribution | 2006-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007515 | 400583776 | Molding | HFTD Tier 3 | Distribution | 2006-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007516 | 400589240 | High Sign | HFTD Tier 3 | Distribution | 2006-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007517 | 400735604 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007518 | 400739348 | Guy | HFTD Tier 3 | Distribution | 2006-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007519 | 400801378 | Guy | HFTD Tier 3 | Distribution | 2006-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007520 | 400172868 | Molding | HFTD Tier 2 | Distribution | 2006-10-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007521 | 400196978 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-10-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007522 | 400647070 | Molding | HFTD Tier 2 | Distribution | 2006-10-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007523 | 400766492 | Molding | HFTD Tier 3 | Distribution | 2006-10-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007524 | 400804925 | Guy | HFTD Tier 3 | Distribution | 2006-10-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007525 | 400848931 | Molding | HFTD Tier 2 | Distribution | 2006-10-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007526 | 400604597 | High Sign | HFTD Tier 3 | Distribution | 2006-10-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007527 | 400606282 | Molding | HFTD Tier 3 | Distribution | 2006-10-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007528 | 400759085 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-10-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007529 | 400815706 | Molding | HFTD Tier 3 | Distribution | 2006-10-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007530 | 400621768 | High Sign | HFTD Tier 3 | Distribution | 2006-11-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007531 | 400785421 | High Sign | HFTD Tier 3 | Distribution | 2006-11-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007532 | 400786539 | Molding | HFTD Tier 3 | Distribution | 2006-11-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007533 | 400832477 | Molding | HFTD Tier 3 | Distribution | 2006-11-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007534 | 403046028 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-11-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007535 | 400175250 | Molding | HFTD Tier 3 | Distribution | 2006-11-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007536 | 400775504 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-11-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007537 | 400802039 | Molding | HFTD Tier 3 | Distribution | 2006-11-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007538 | 400793170 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-11-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007539 | 400794431 | High Sign | HFTD Tier 3 | Distribution | 2006-11-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007540 | 400205933 | Guy | HFTD Tier 3 | Distribution | 2006-11-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007541 | 400251847 | Molding | HFTD Tier 3 | Distribution | 2006-11-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007542 | 400830889 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-11-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007543 | 400876049 | Riser/Conduit | HFTD Tier 3 | Distribution | 2006-11-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007544 | 400887759 | Guy | HFTD Tier 3 | Distribution | 2006-11-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007545 | 400205566 | High Sign | HFTD Tier 3 | Distribution | 2006-11-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007546 | 400714969 | High Sign | HFTD Tier 2 | Distribution | 2006-11-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007547 | 400718151 | High Sign | HFTD Tier 2 | Distribution | 2006-11-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007548 | 400811454 | Riser/Conduit | HFTD Tier 3 | Distribution | 2006-11-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007549 | 400814605 | High Sign | HFTD Tier 3 | Distribution | 2006-11-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007550 | 400822850 | Molding | HFTD Tier 3 | Distribution | 2006-11-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007551 | 400837809 | High Sign | HFTD Tier 2 | Distribution | 2006-11-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007552 | 400871410 | High Sign | HFTD Tier 2 | Distribution | 2006-11-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007553 | 400874726 | High Sign | HFTD Tier 2 | Distribution | 2006-11-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007554 | 400902924 | High Sign | HFTD Tier 2 | Distribution | 2006-11-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007555 | 400909950 | High Sign | HFTD Tier 2 | Distribution | 2006-11-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007556 | 400836959 | High Sign | HFTD Tier 3 | Distribution | 2006-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007557 | 400927487 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007558 | 400852810 | Molding | HFTD Tier 2 | Distribution | 2006-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007559 | 400890774 | High Sign | HFTD Tier 3 | Distribution | 2006-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007560 | 400890817 | High Sign | HFTD Tier 2 | Distribution | 2006-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007561 | 400915909 | Molding | HFTD Tier 2 | Distribution | 2006-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007562 | 400252876 | High Sign | HFTD Tier 3 | Distribution | 2006-11-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007563 | 400540191 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-11-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007564 | 400579825 | Molding | HFTD Tier 3 | Distribution | 2006-11-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007565 | 400883302 | High Sign | HFTD Tier 2 | Distribution | 2006-11-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007566 | 400953744 | High Sign | HFTD Tier 3 | Distribution | 2006-11-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007567 | 400558248 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007568 | 400788671 | High Sign | HFTD Tier 2 | Distribution | 2006-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007569 | 400536623 | Molding | HFTD Tier 3 | Distribution | 2006-11-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007570 | 400820795 | High Sign | HFTD Tier 3 | Distribution | 2006-11-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007571 | 400842069 | High Sign | HFTD Tier 2 | Distribution | 2006-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007572 | 400598097 | Guy | HFTD Tier 3 | Distribution | 2006-11-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007573 | 400632229 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-11-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007574 | 400687407 | Molding | HFTD Tier 2 | Distribution | 2006-11-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007575 | 400639413 | Molding | HFTD Tier 2 | Distribution | 2006-11-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007576 | 400642920 | Molding | HFTD Tier 2 | Distribution | 2006-11-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007577 | 400667731 | Guy | HFTD Tier 3 | Distribution | 2006-11-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007578 | 400677133 | High Sign | HFTD Tier 2 | Distribution | 2006-11-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007579 | 400864077 | High Sign | HFTD Tier 2 | Distribution | 2006-11-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007580 | 400663408 | Molding | HFTD Tier 2 | Distribution | 2006-11-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007581 | 400633357 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007582 | 400680464 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007583 | 400702816 | Molding | HFTD Tier 2 | Distribution | 2006-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007584 | 400908222 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007585 | 400912888 | Molding | HFTD Tier 2 | Distribution | 2006-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007586 | 400912944 | Molding | HFTD Tier 2 | Distribution | 2006-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007587 | 400989233 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007588 | 401538886 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-12-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007589 | 401540127 | Cable/Conductor | HFTD Tier 2 | Distribution | 2006-12-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007590 | 400663321 | High Sign | HFTD Tier 2 | Distribution | 2006-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007591 | 400668330 | Molding | HFTD Tier 2 | Distribution | 2006-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007592 | 400710754 | Hardware/Framing | HFTD Tier 2 | Distribution | 2006-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007593 | 400718344 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007594 | 400720466 | Molding | HFTD Tier 2 | Distribution | 2006-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007595 | 400720489 | Molding | HFTD Tier 2 | Distribution | 2006-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007596 | 400722594 | High Sign | HFTD Tier 2 | Distribution | 2006-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007597 | 400728351 | Molding | HFTD Tier 2 | Distribution | 2006-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007598 | 400547347 | High Sign | HFTD Tier 3 | Distribution | 2006-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007599 | 400674843 | Guy | HFTD Tier 2 | Distribution | 2006-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007600 | 400685152 | High Sign | HFTD Tier 3 | Distribution | 2006-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007601 | 400716100 | High Sign | HFTD Tier 3 | Distribution | 2006-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007602 | 400739997 | Molding | HFTD Tier 2 | Distribution | 2006-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007603 | 400551851 | Guy | HFTD Tier 3 | Distribution | 2006-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007604 | 400554962 | Guy | HFTD Tier 3 | Distribution | 2006-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007605 | 400557926 | Guy | HFTD Tier 3 | Distribution | 2006-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007606 | 400560147 | Guy | HFTD Tier 3 | Distribution | 2006-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007607 | 400566071 | Guy | HFTD Tier 3 | Distribution | 2006-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007608 | 400567123 | Molding | HFTD Tier 2 | Distribution | 2006-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007609 | 400680294 | Guy | HFTD Tier 3 | Distribution | 2006-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007610 | 400682036 | Guy | HFTD Tier 3 | Distribution | 2006-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007611 | 400682054 | Guy | HFTD Tier 3 | Distribution | 2006-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007612 | 400686432 | Molding | HFTD Tier 3 | Distribution | 2006-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007613 | 400686497 | Guy | HFTD Tier 3 | Distribution | 2006-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007614 | 400688933 | Guy | HFTD Tier 3 | Distribution | 2006-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007615 | 400725017 | Guy | HFTD Tier 3 | Distribution | 2006-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007616 | 400726139 | Guy | HFTD Tier 3 | Distribution | 2006-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007617 | 400728203 | Guy | HFTD Tier 3 | Distribution | 2006-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007618 | 400728500 | Guy | HFTD Tier 3 | Distribution | 2006-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007619 | 400742582 | Guy | HFTD Tier 3 | Distribution | 2006-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007620 | 400746275 | Guy | HFTD Tier 2 | Distribution | 2006-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007621 | 400751906 | Guy | HFTD Tier 3 | Distribution | 2006-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007622 | 400722656 | Cable/Conductor | HFTD Tier 3 | Distribution | 2006-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007623 | 400740464 | Molding | HFTD Tier 3 | Distribution | 2006-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007624 | 400750240 | High Sign | HFTD Tier 2 | Distribution | 2006-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007625 | 400752113 | Molding | HFTD Tier 2 | Distribution | 2006-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007626 | 400763030 | High Sign | HFTD Tier 2 | Distribution | 2006-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007627 | 400767859 | Guy | HFTD Tier 2 | Distribution | 2006-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007628 | 400242322 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-12-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007629 | 400248060 | High Sign | HFTD Tier 3 | Distribution | 2006-12-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007630 | 400283505 | Molding | HFTD Tier 3 | Distribution | 2006-12-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007631 | 400707097 | Molding | HFTD Tier 2 | Distribution | 2006-12-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007632 | 400728653 | High Sign | HFTD Tier 2 | Distribution | 2006-12-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007633 | 400748719 | Molding | HFTD Tier 3 | Distribution | 2006-12-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007634 | 400749410 | Guy | HFTD Tier 3 | Distribution | 2006-12-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007635 | 400753191 | Molding | HFTD Tier 3 | Distribution | 2006-12-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007636 | 400761423 | Guy | HFTD Tier 3 | Distribution | 2006-12-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007637 | 400774069 | Molding | HFTD Tier 3 | Distribution | 2006-12-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007638 | 400778710 | Molding | HFTD Tier 2 | Distribution | 2006-12-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007639 | 400871239 | High Sign | HFTD Tier 2 | Distribution | 2006-12-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007640 | 400985081 | Cable/Conductor | HFTD Tier 3 | Distribution | 2006-12-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007641 | 400228968 | Molding | HFTD Tier 2 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007642 | 400595409 | Guy | HFTD Tier 3 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007643 | 400595476 | Guy | HFTD Tier 3 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007644 | 400597596 | High Sign | HFTD Tier 3 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007645 | 400597878 | High Sign | HFTD Tier 2 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007646 | 400600553 | Guy | HFTD Tier 3 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007647 | 400648796 | Molding | HFTD Tier 2 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007648 | 400719351 | Molding | HFTD Tier 2 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007649 | 400726530 | Guy | HFTD Tier 3 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007650 | 400728107 | Guy | HFTD Tier 3 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007651 | 400731809 | Guy | HFTD Tier 3 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007652 | 400757697 | High Sign | HFTD Tier 2 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007653 | 400758489 | Guy | HFTD Tier 3 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007654 | 400759448 | Molding | HFTD Tier 2 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007655 | 400769850 | Molding | HFTD Tier 2 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007656 | 400771470 | Molding | HFTD Tier 2 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007657 | 400774735 | Hardware/Framing | HFTD Tier 3 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007658 | 400776038 | Guy | HFTD Tier 3 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007659 | 400776544 | Guy | HFTD Tier 3 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007660 | 400776609 | Guy | HFTD Tier 3 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007661 | 400778251 | High Sign | HFTD Tier 3 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007662 | 400779322 | Guy | HFTD Tier 3 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007663 | 400779363 | High Sign | HFTD Tier 2 | Distribution | 2006-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007664 | 400192532 | Molding | HFTD Tier 2 | Distribution | 2006-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007665 | 400224348 | Molding | HFTD Tier 2 | Distribution | 2006-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007666 | 400227061 | Molding | HFTD Tier 2 | Distribution | 2006-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007667 | 400228955 | Molding | HFTD Tier 2 | Distribution | 2006-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007668 | 400264736 | Molding | HFTD Tier 2 | Distribution | 2006-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007669 | 400625033 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007670 | 400727354 | Molding | HFTD Tier 2 | Distribution | 2006-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007671 | 400783352 | Molding | HFTD Tier 2 | Distribution | 2006-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007672 | 400198079 | Molding | HFTD Tier 2 | Distribution | 2006-12-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007673 | 400753740 | Molding | HFTD Tier 3 | Distribution | 2006-12-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007674 | 400757915 | High Sign | HFTD Tier 2 | Distribution | 2006-12-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007675 | 400795082 | Guy | HFTD Tier 2 | Distribution | 2006-12-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007676 | 400803539 | Guy | HFTD Tier 3 | Distribution | 2006-12-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007677 | 400193238 | High Sign | HFTD Tier 3 | Distribution | 2006-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007678 | 400230981 | High Sign | HFTD Tier 3 | Distribution | 2006-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007679 | 400268195 | High Sign | HFTD Tier 3 | Distribution | 2006-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007680 | 400272883 | High Sign | HFTD Tier 3 | Distribution | 2006-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007681 | 400652924 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007682 | 400676662 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2006-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007683 | 400801498 | High Sign | HFTD Tier 3 | Distribution | 2006-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007684 | 400805686 | High Sign | HFTD Tier 2 | Distribution | 2006-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007685 | 400817278 | Molding | HFTD Tier 3 | Distribution | 2006-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007686 | 400852576 | Molding | HFTD Tier 2 | Distribution | 2006-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007687 | 400193311 | Molding | HFTD Tier 2 | Distribution | 2006-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007688 | 400227847 | Molding | HFTD Tier 2 | Distribution | 2006-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007689 | 400269917 | Molding | HFTD Tier 2 | Distribution | 2006-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007690 | 400271213 | Molding | HFTD Tier 2 | Distribution | 2006-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007691 | 400651564 | Guy | HFTD Tier 3 | Distribution | 2006-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007692 | 400653194 | High Sign | HFTD Tier 2 | Distribution | 2006-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007693 | 400770590 | Molding | HFTD Tier 3 | Distribution | 2006-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007694 | 400806542 | Molding | HFTD Tier 2 | Distribution | 2006-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007695 | 400810078 | Molding | HFTD Tier 2 | Distribution | 2006-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007696 | 400811687 | High Sign | HFTD Tier 2 | Distribution | 2006-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007697 | 400812948 | High Sign | HFTD Tier 2 | Distribution | 2006-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007698 | 400816344 | Guy | HFTD Tier 3 | Distribution | 2006-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007699 | 400830999 | Molding | HFTD Tier 2 | Distribution | 2006-12-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007700 | 400270482 | High Sign | HFTD Tier 3 | Distribution | 2006-12-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007701 | 400673071 | Molding | HFTD Tier 2 | Distribution | 2006-12-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007702 | 400677044 | Guy | HFTD Tier 3 | Distribution | 2006-12-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007703 | 400681113 | High Sign | HFTD Tier 2 | Distribution | 2006-12-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007704 | 400795591 | Insulator | HFTD Tier 3 | Distribution | 2006-12-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007705 | 400798651 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-12-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007706 | 400826548 | Molding | HFTD Tier 2 | Distribution | 2006-12-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007707 | 400836255 | Guy | HFTD Tier 3 | Distribution | 2006-12-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007708 | 400839838 | High Sign | HFTD Tier 2 | Distribution | 2006-12-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007709 | 400846519 | Molding | HFTD Tier 2 | Distribution | 2006-12-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007710 | 400687618 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2006-12-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007711 | 400814130 | High Sign | HFTD Tier 3 | Distribution | 2006-12-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007712 | 400488953 | High Sign | HFTD Tier 2 | Distribution | 2007-01-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007713 | 400723017 | Guy | HFTD Tier 3 | Distribution | 2007-01-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007714 | 400813393 | Molding | HFTD Tier 3 | Distribution | 2007-01-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007715 | 400880904 | High Sign | HFTD Tier 2 | Distribution | 2007-01-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007716 | 400629438 | Guy | HFTD Tier 3 | Distribution | 2007-01-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007717 | 400723998 | Guy | HFTD Tier 3 | Distribution | 2007-01-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007718 | 400731044 | Guy | HFTD Tier 3 | Distribution | 2007-01-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007719 | 400817368 | Guy | HFTD Tier 3 | Distribution | 2007-01-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007720 | 400883559 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-01-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007721 | 400965783 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-01-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007722 | 400896790 | Molding | HFTD Tier 3 | Distribution | 2007-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007723 | 400901457 | Guy | HFTD Tier 3 | Distribution | 2007-01-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007724 | 400202035 | Molding | HFTD Tier 3 | Distribution | 2007-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007725 | 400234108 | Molding | HFTD Tier 3 | Distribution | 2007-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007726 | 400576307 | Molding | HFTD Tier 3 | Distribution | 2007-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007727 | 400911054 | Molding | HFTD Tier 3 | Distribution | 2007-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007728 | 400619326 | Cable/Conductor | HFTD Tier 2 | Distribution | 2007-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007729 | 400628438 | Molding | HFTD Tier 2 | Distribution | 2007-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007730 | 400633539 | Molding | HFTD Tier 2 | Distribution | 2007-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007731 | 400872161 | High Sign | HFTD Tier 3 | Distribution | 2007-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007732 | 400877027 | High Sign | HFTD Tier 2 | Distribution | 2007-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007733 | 400899418 | High Sign | HFTD Tier 3 | Distribution | 2007-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007734 | 400915526 | High Sign | HFTD Tier 2 | Distribution | 2007-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007735 | 400535378 | Guy | HFTD Tier 2 | Distribution | 2007-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007736 | 400544984 | Molding | HFTD Tier 2 | Distribution | 2007-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007737 | 400608165 | Molding | HFTD Tier 2 | Distribution | 2007-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007738 | 400633865 | Molding | HFTD Tier 2 | Distribution | 2007-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007739 | 400783527 | High Sign | HFTD Tier 2 | Distribution | 2007-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007740 | 400202438 | Guy | HFTD Tier 3 | Distribution | 2007-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007741 | 400540194 | Molding | HFTD Tier 2 | Distribution | 2007-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007742 | 400552845 | High Sign | HFTD Tier 2 | Distribution | 2007-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007743 | 400552869 | Molding | HFTD Tier 2 | Distribution | 2007-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007744 | 400790606 | High Sign | HFTD Tier 2 | Distribution | 2007-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007745 | 400792235 | High Sign | HFTD Tier 2 | Distribution | 2007-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007746 | 400793468 | High Sign | HFTD Tier 2 | Distribution | 2007-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007747 | 400808146 | Molding | HFTD Tier 3 | Distribution | 2007-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007748 | 400591194 | Molding | HFTD Tier 2 | Distribution | 2007-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007749 | 400593465 | High Sign | HFTD Tier 2 | Distribution | 2007-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007750 | 400935926 | Molding | HFTD Tier 3 | Distribution | 2007-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007751 | 400203141 | High Sign | HFTD Tier 3 | Distribution | 2007-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007752 | 400244548 | Structure/Equip Itself | HFTD Tier 3 | Transmission | 2007-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007753 | 400572307 | High Sign | HFTD Tier 3 | Distribution | 2007-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007754 | 400818562 | Guy | HFTD Tier 3 | Distribution | 2007-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007755 | 400280837 | Molding | HFTD Tier 3 | Distribution | 2007-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007756 | 400561086 | High Sign | HFTD Tier 3 | Distribution | 2007-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007757 | 400589976 | High Sign | HFTD Tier 3 | Distribution | 2007-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007758 | 400813210 | High Sign | HFTD Tier 3 | Distribution | 2007-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007759 | 400841933 | Guy | HFTD Tier 3 | Distribution | 2007-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007760 | 400935965 | High Sign | HFTD Tier 3 | Distribution | 2007-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007761 | 400583595 | High Sign | HFTD Tier 3 | Distribution | 2007-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007762 | 400587752 | High Sign | HFTD Tier 3 | Distribution | 2007-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007763 | 400587771 | High Sign | HFTD Tier 3 | Distribution | 2007-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007764 | 400590232 | High Sign | HFTD Tier 3 | Distribution | 2007-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007765 | 400593353 | High Sign | HFTD Tier 3 | Distribution | 2007-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007766 | 400551638 | High Sign | HFTD Tier 3 | Distribution | 2007-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007767 | 400606858 | High Sign | HFTD Tier 3 | Distribution | 2007-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007768 | 400611377 | High Sign | HFTD Tier 3 | Distribution | 2007-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007769 | 400848311 | Molding | HFTD Tier 3 | Distribution | 2007-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007770 | 400559213 | Molding | HFTD Tier 3 | Distribution | 2007-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007771 | 400619136 | Molding | HFTD Tier 2 | Distribution | 2007-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007772 | 400592752 | High Sign | HFTD Tier 2 | Distribution | 2007-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007773 | 400602551 | High Sign | HFTD Tier 3 | Distribution | 2007-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007774 | 400636743 | Molding | HFTD Tier 2 | Distribution | 2007-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007775 | 400645404 | High Sign | HFTD Tier 3 | Distribution | 2007-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007776 | 400649241 | High Sign | HFTD Tier 2 | Distribution | 2007-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007777 | 400880690 | Cable/Conductor | HFTD Tier 2 | Distribution | 2007-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007778 | 400653854 | High Sign | HFTD Tier 2 | Distribution | 2007-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007779 | 400283444 | High Sign | HFTD Tier 3 | Distribution | 2007-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007780 | 400677752 | High Sign | HFTD Tier 2 | Distribution | 2007-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007781 | 400916585 | Molding | HFTD Tier 2 | Distribution | 2007-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007782 | 400920013 | High Sign | HFTD Tier 2 | Distribution | 2007-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007783 | 400652090 | Molding | HFTD Tier 2 | Distribution | 2007-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007784 | 400687151 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2007-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007785 | 400696748 | High Sign | HFTD Tier 2 | Distribution | 2007-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007786 | 400926335 | Molding | HFTD Tier 2 | Distribution | 2007-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007787 | 400673599 | High Sign | HFTD Tier 2 | Distribution | 2007-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007788 | 400703600 | Molding | HFTD Tier 3 | Distribution | 2007-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007789 | 400713078 | High Sign | HFTD Tier 2 | Distribution | 2007-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007790 | 400558923 | High Sign | HFTD Tier 3 | Distribution | 2007-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007791 | 400721859 | Guy | HFTD Tier 3 | Distribution | 2007-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007792 | 400690357 | High Sign | HFTD Tier 3 | Distribution | 2007-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007793 | 400722552 | High Sign | HFTD Tier 3 | Distribution | 2007-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007794 | 400725535 | High Sign | HFTD Tier 3 | Distribution | 2007-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007795 | 400593754 | High Sign | HFTD Tier 3 | Distribution | 2007-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007796 | 400704755 | Molding | HFTD Tier 3 | Distribution | 2007-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007797 | 400734576 | High Sign | HFTD Tier 3 | Distribution | 2007-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007798 | 400736013 | High Sign | HFTD Tier 3 | Distribution | 2007-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007799 | 400609359 | High Sign | HFTD Tier 2 | Distribution | 2007-02-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007800 | 400719307 | High Sign | HFTD Tier 2 | Distribution | 2007-02-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007801 | 400759737 | High Sign | HFTD Tier 3 | Distribution | 2007-02-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007802 | 400760979 | Guy | HFTD Tier 3 | Distribution | 2007-02-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007803 | 400765191 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-02-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007804 | 400770724 | Molding | HFTD Tier 2 | Distribution | 2007-02-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007805 | 400621539 | Molding | HFTD Tier 2 | Distribution | 2007-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007806 | 400762574 | Guy | HFTD Tier 2 | Distribution | 2007-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007807 | 400767889 | Cable/Conductor | HFTD Tier 2 | Distribution | 2007-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007808 | 400769911 | High Sign | HFTD Tier 2 | Distribution | 2007-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007809 | 400640363 | Molding | HFTD Tier 3 | Distribution | 2007-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007810 | 400759659 | High Sign | HFTD Tier 2 | Distribution | 2007-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007811 | 400801921 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007812 | 400810170 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007813 | 400772956 | High Sign | HFTD Tier 3 | Distribution | 2007-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007814 | 400803632 | Guy | HFTD Tier 3 | Distribution | 2007-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007815 | 400826216 | High Sign | HFTD Tier 2 | Distribution | 2007-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007816 | 400261243 | High Sign | HFTD Tier 2 | Distribution | 2007-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007817 | 400768631 | Molding | HFTD Tier 3 | Distribution | 2007-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007818 | 400809167 | Molding | HFTD Tier 3 | Distribution | 2007-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007819 | 400842703 | Molding | HFTD Tier 2 | Distribution | 2007-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007820 | 400842808 | High Sign | HFTD Tier 3 | Distribution | 2007-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007821 | 400844327 | Molding | HFTD Tier 2 | Distribution | 2007-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007822 | 400919085 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007823 | 400805516 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007824 | 400840035 | High Sign | HFTD Tier 3 | Distribution | 2007-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007825 | 400845301 | Molding | HFTD Tier 2 | Distribution | 2007-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007826 | 400849557 | High Sign | HFTD Tier 3 | Distribution | 2007-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007827 | 400863956 | High Sign | HFTD Tier 2 | Distribution | 2007-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007828 | 400875798 | Guy | HFTD Tier 2 | Distribution | 2007-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007829 | 400808037 | High Sign | HFTD Tier 2 | Distribution | 2007-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007830 | 400851708 | Molding | HFTD Tier 3 | Distribution | 2007-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007831 | 400833200 | Molding | HFTD Tier 2 | Distribution | 2007-02-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007832 | 400855449 | Molding | HFTD Tier 3 | Distribution | 2007-02-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007833 | 400859721 | Guy | HFTD Tier 3 | Distribution | 2007-02-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007834 | 400866753 | Molding | HFTD Tier 2 | Distribution | 2007-02-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007835 | 400899181 | High Sign | HFTD Tier 2 | Distribution | 2007-02-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007836 | 400257039 | Molding | HFTD Tier 3 | Distribution | 2007-02-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007837 | 400918147 | Molding | HFTD Tier 3 | Distribution | 2007-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007838 | 400918175 | Molding | HFTD Tier 3 | Distribution | 2007-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007839 | 400891426 | Guy | HFTD Tier 3 | Distribution | 2007-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007840 | 401006706 | Molding | HFTD Tier 3 | Distribution | 2007-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007841 | 400939323 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-02-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007842 | 400593617 | High Sign | HFTD Tier 3 | Distribution | 2007-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007843 | 400926133 | Molding | HFTD Tier 3 | Distribution | 2007-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007844 | 400942330 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007845 | 400935079 | High Sign | HFTD Tier 3 | Distribution | 2007-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007846 | 400543653 | Molding | HFTD Tier 2 | Distribution | 2007-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007847 | 400590830 | Molding | HFTD Tier 2 | Distribution | 2007-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007848 | 400614832 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007849 | 400647272 | Molding | HFTD Tier 2 | Distribution | 2007-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007850 | 400634530 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007851 | 400664853 | Molding | HFTD Tier 3 | Distribution | 2007-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007852 | 400665046 | Molding | HFTD Tier 3 | Distribution | 2007-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007853 | 400667412 | High Sign | HFTD Tier 3 | Distribution | 2007-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007854 | 400532075 | Molding | HFTD Tier 3 | Distribution | 2007-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007855 | 400665030 | Molding | HFTD Tier 3 | Distribution | 2007-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007856 | 400670274 | Molding | HFTD Tier 3 | Distribution | 2007-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007857 | 400703067 | High Sign | HFTD Tier 3 | Distribution | 2007-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007858 | 400528035 | Riser/Conduit | HFTD Tier 3 | Distribution | 2007-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007859 | 400685781 | High Sign | HFTD Tier 2 | Distribution | 2007-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007860 | 400688449 | Molding | HFTD Tier 3 | Distribution | 2007-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007861 | 401006622 | Molding | HFTD Tier 3 | Distribution | 2007-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007862 | 403047916 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007863 | 400547803 | High Sign | HFTD Tier 2 | Distribution | 2007-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007864 | 400712614 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007865 | 400569051 | Molding | HFTD Tier 3 | Distribution | 2007-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007866 | 400661921 | High Sign | HFTD Tier 3 | Distribution | 2007-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007867 | 400730577 | Termination | HFTD Tier 3 | Distribution | 2007-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007868 | 400737926 | Molding | HFTD Tier 3 | Distribution | 2007-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007869 | 400599597 | Molding | HFTD Tier 3 | Distribution | 2007-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007870 | 400624083 | Molding | HFTD Tier 2 | Distribution | 2007-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007871 | 400700480 | Guy | HFTD Tier 3 | Distribution | 2007-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007872 | 400730413 | Guy | HFTD Tier 3 | Distribution | 2007-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007873 | 400740006 | Guy | HFTD Tier 3 | Distribution | 2007-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007874 | 400742657 | Ground | HFTD Tier 3 | Distribution | 2007-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007875 | 400770674 | High Sign | HFTD Tier 3 | Distribution | 2007-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007876 | 400778430 | High Sign | HFTD Tier 2 | Distribution | 2007-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007877 | 400677489 | Molding | HFTD Tier 2 | Distribution | 2007-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007878 | 400705320 | Molding | HFTD Tier 3 | Distribution | 2007-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007879 | 400758905 | Molding | HFTD Tier 2 | Distribution | 2007-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007880 | 400729577 | Termination | HFTD Tier 3 | Distribution | 2007-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007881 | 400736962 | Molding | HFTD Tier 3 | Distribution | 2007-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007882 | 400675512 | Molding | HFTD Tier 3 | Distribution | 2007-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007883 | 400764672 | Molding | HFTD Tier 3 | Distribution | 2007-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007884 | 400789749 | Molding | HFTD Tier 3 | Distribution | 2007-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007885 | 400249659 | Molding | HFTD Tier 2 | Distribution | 2007-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007886 | 400254280 | Molding | HFTD Tier 2 | Distribution | 2007-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007887 | 400276088 | High Sign | HFTD Tier 2 | Distribution | 2007-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007888 | 400280488 | Guy | HFTD Tier 2 | Distribution | 2007-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007889 | 400753332 | High Sign | HFTD Tier 2 | Distribution | 2007-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007890 | 400814421 | Molding | HFTD Tier 3 | Distribution | 2007-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007891 | 400690200 | High Sign | HFTD Tier 3 | Distribution | 2007-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007892 | 400751527 | High Sign | HFTD Tier 3 | Distribution | 2007-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007893 | 400778709 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007894 | 400779660 | High Sign | HFTD Tier 3 | Distribution | 2007-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007895 | 400780545 | Molding | HFTD Tier 3 | Distribution | 2007-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007896 | 400886631 | Termination | HFTD Tier 3 | Distribution | 2007-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007897 | 400503118 | High Sign | HFTD Tier 3 | Distribution | 2007-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007898 | 400742622 | Molding | HFTD Tier 3 | Distribution | 2007-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007899 | 400854324 | High Sign | HFTD Tier 3 | Distribution | 2007-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007900 | 400856334 | High Sign | HFTD Tier 3 | Distribution | 2007-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007901 | 400722186 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007902 | 400725379 | High Sign | HFTD Tier 3 | Distribution | 2007-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007903 | 400281290 | Molding | HFTD Tier 3 | Distribution | 2007-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007904 | 400282598 | Molding | HFTD Tier 3 | Distribution | 2007-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007905 | 400284553 | Molding | HFTD Tier 3 | Distribution | 2007-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007906 | 400326511 | Molding | HFTD Tier 3 | Distribution | 2007-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007907 | 400817212 | Molding | HFTD Tier 2 | Distribution | 2007-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007908 | 400845762 | High Sign | HFTD Tier 2 | Distribution | 2007-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007909 | 401006687 | Molding | HFTD Tier 3 | Distribution | 2007-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007910 | 403048890 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2007-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007911 | 400929116 | Guy | HFTD Tier 3 | Distribution | 2007-04-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007912 | 400586940 | Molding | HFTD Tier 3 | Distribution | 2007-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007913 | 400594811 | Molding | HFTD Tier 3 | Distribution | 2007-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007914 | 400907500 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007915 | 400780033 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007916 | 400783636 | Molding | HFTD Tier 3 | Distribution | 2007-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007917 | 400886788 | Molding | HFTD Tier 3 | Distribution | 2007-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007918 | 400556724 | High Sign | HFTD Tier 2 | Distribution | 2007-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007919 | 400868399 | Molding | HFTD Tier 3 | Distribution | 2007-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007920 | 400155364 | High Sign | HFTD Tier 3 | Distribution | 2007-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007921 | 400575199 | High Sign | HFTD Tier 3 | Distribution | 2007-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007922 | 400892803 | High Sign | HFTD Tier 3 | Distribution | 2007-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007923 | 400899993 | Molding | HFTD Tier 2 | Distribution | 2007-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007924 | 400901660 | High Sign | HFTD Tier 2 | Distribution | 2007-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007925 | 400912654 | High Sign | HFTD Tier 3 | Distribution | 2007-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007926 | 400608454 | High Sign | HFTD Tier 3 | Distribution | 2007-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007927 | 400546849 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007928 | 400929337 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007929 | 401006671 | Molding | HFTD Tier 3 | Distribution | 2007-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007930 | 400544676 | Molding | HFTD Tier 2 | Distribution | 2007-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007931 | 400580695 | Molding | HFTD Tier 2 | Distribution | 2007-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007932 | 400626250 | High Sign | HFTD Tier 3 | Distribution | 2007-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007933 | 400641464 | Molding | HFTD Tier 2 | Distribution | 2007-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007934 | 400903938 | Molding | HFTD Tier 2 | Distribution | 2007-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007935 | 400904685 | High Sign | HFTD Tier 2 | Distribution | 2007-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007936 | 400292861 | Molding | HFTD Tier 2 | Distribution | 2007-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007937 | 400378847 | Molding | HFTD Tier 2 | Distribution | 2007-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007938 | 400564746 | High Sign | HFTD Tier 2 | Distribution | 2007-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007939 | 400604540 | High Sign | HFTD Tier 3 | Distribution | 2007-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007940 | 400615323 | Molding | HFTD Tier 3 | Distribution | 2007-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007941 | 400670050 | Molding | HFTD Tier 3 | Distribution | 2007-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007942 | 400289128 | Molding | HFTD Tier 3 | Distribution | 2007-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007943 | 400589135 | High Sign | HFTD Tier 2 | Distribution | 2007-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007944 | 400604371 | Molding | HFTD Tier 2 | Distribution | 2007-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007945 | 400611336 | High Sign | HFTD Tier 2 | Distribution | 2007-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007946 | 400611364 | Molding | HFTD Tier 3 | Distribution | 2007-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007947 | 400670006 | High Sign | HFTD Tier 2 | Distribution | 2007-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007948 | 400911378 | High Sign | HFTD Tier 3 | Distribution | 2007-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007949 | 400605035 | High Sign | HFTD Tier 2 | Distribution | 2007-04-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007950 | 400573706 | Guy | HFTD Tier 3 | Distribution | 2007-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007951 | 400574841 | Guy | HFTD Tier 3 | Distribution | 2007-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007952 | 400624011 | Molding | HFTD Tier 3 | Distribution | 2007-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007953 | 400688583 | Molding | HFTD Tier 3 | Distribution | 2007-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007954 | 400837534 | High Sign | HFTD Tier 3 | Distribution | 2007-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007955 | 400339609 | Molding | HFTD Tier 3 | Distribution | 2007-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007956 | 400781702 | Guy | HFTD Tier 3 | Distribution | 2007-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007957 | 400270033 | Molding | HFTD Tier 3 | Distribution | 2007-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007958 | 400273023 | Molding | HFTD Tier 3 | Distribution | 2007-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007959 | 400291918 | Molding | HFTD Tier 3 | Distribution | 2007-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007960 | 400298416 | High Sign | HFTD Tier 3 | Distribution | 2007-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007961 | 400299940 | High Sign | HFTD Tier 3 | Distribution | 2007-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007962 | 400342954 | Molding | HFTD Tier 3 | Distribution | 2007-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007963 | 400344906 | Molding | HFTD Tier 3 | Distribution | 2007-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007964 | 400577196 | High Sign | HFTD Tier 3 | Distribution | 2007-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007965 | 400660762 | Molding | HFTD Tier 3 | Distribution | 2007-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007966 | 400662889 | Molding | HFTD Tier 3 | Distribution | 2007-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007967 | 400666789 | High Sign | HFTD Tier 2 | Distribution | 2007-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007968 | 400625281 | Molding | HFTD Tier 2 | Distribution | 2007-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007969 | 400683102 | High Sign | HFTD Tier 2 | Distribution | 2007-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007970 | 400684725 | Molding | HFTD Tier 3 | Distribution | 2007-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007971 | 400617693 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007972 | 400688711 | High Sign | HFTD Tier 3 | Distribution | 2007-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007973 | 400711311 | High Sign | HFTD Tier 2 | Distribution | 2007-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007974 | 400716883 | High Sign | HFTD Tier 3 | Distribution | 2007-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007975 | 400839887 | Guy | HFTD Tier 3 | Distribution | 2007-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007976 | 400893133 | Molding | HFTD Tier 3 | Distribution | 2007-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007977 | 400842615 | High Sign | HFTD Tier 3 | Distribution | 2007-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007978 | 400372100 | Molding | HFTD Tier 2 | Distribution | 2007-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007979 | 400645855 | High Sign | HFTD Tier 2 | Distribution | 2007-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007980 | 400666339 | Guy | HFTD Tier 2 | Distribution | 2007-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007981 | 400731666 | Molding | HFTD Tier 3 | Distribution | 2007-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007982 | 400845355 | Molding | HFTD Tier 2 | Distribution | 2007-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007983 | 400855035 | Guy | HFTD Tier 2 | Distribution | 2007-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007984 | 400856601 | Guy | HFTD Tier 2 | Distribution | 2007-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007985 | 400890527 | Molding | HFTD Tier 2 | Distribution | 2007-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007986 | 400733435 | High Sign | HFTD Tier 3 | Distribution | 2007-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007987 | 400742639 | Molding | HFTD Tier 3 | Distribution | 2007-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007988 | 400856642 | Molding | HFTD Tier 3 | Distribution | 2007-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007989 | 400299318 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-05-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007990 | 400753870 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-05-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007991 | 400872907 | High Sign | HFTD Tier 2 | Distribution | 2007-05-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007992 | 400922638 | High Sign | HFTD Tier 3 | Distribution | 2007-05-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007993 | 400749317 | Molding | HFTD Tier 2 | Distribution | 2007-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007994 | 400749343 | Molding | HFTD Tier 2 | Distribution | 2007-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007995 | 400917294 | High Sign | HFTD Tier 2 | Distribution | 2007-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007996 | 401466234 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007997 | 400711861 | Molding | HFTD Tier 2 | Distribution | 2007-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007998 | 400720460 | Molding | HFTD Tier 2 | Distribution | 2007-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120007999 | 400888271 | Guy | HFTD Tier 3 | Distribution | 2007-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008000 | 401003439 | Guy | HFTD Tier 3 | Distribution | 2007-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008001 | 400732404 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008002 | 400799010 | High Sign | HFTD Tier 2 | Distribution | 2007-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008003 | 400943954 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2007-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008004 | 400277556 | Molding | HFTD Tier 2 | Distribution | 2007-05-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008005 | 400278600 | Molding | HFTD Tier 2 | Distribution | 2007-05-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008006 | 400305043 | Molding | HFTD Tier 2 | Distribution | 2007-05-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008007 | 400346659 | Molding | HFTD Tier 2 | Distribution | 2007-05-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008008 | 400729716 | High Sign | HFTD Tier 2 | Distribution | 2007-05-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008009 | 400795317 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-05-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008010 | 400823319 | Guy | HFTD Tier 3 | Distribution | 2007-05-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008011 | 400849038 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-05-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008012 | 400874963 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-05-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008013 | 400899793 | High Sign | HFTD Tier 2 | Distribution | 2007-05-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008014 | 400911757 | High Sign | HFTD Tier 2 | Distribution | 2007-05-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008015 | 400946981 | Molding | HFTD Tier 2 | Distribution | 2007-05-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008016 | 400956178 | High Sign | HFTD Tier 3 | Distribution | 2007-05-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008017 | 400307210 | Molding | HFTD Tier 3 | Distribution | 2007-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008018 | 400809491 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008019 | 400811303 | Molding | HFTD Tier 2 | Distribution | 2007-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008020 | 400926429 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008021 | 400926624 | High Sign | HFTD Tier 2 | Distribution | 2007-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008022 | 400931087 | Molding | HFTD Tier 2 | Distribution | 2007-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008023 | 400951609 | High Sign | HFTD Tier 2 | Distribution | 2007-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008024 | 401002502 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008025 | 400825819 | High Sign | HFTD Tier 2 | Distribution | 2007-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008026 | 400874191 | High Sign | HFTD Tier 3 | Distribution | 2007-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008027 | 400874989 | High Sign | HFTD Tier 3 | Distribution | 2007-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008028 | 400875179 | Molding | HFTD Tier 2 | Distribution | 2007-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008029 | 400877456 | Molding | HFTD Tier 3 | Distribution | 2007-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008030 | 400939372 | High Sign | HFTD Tier 3 | Distribution | 2007-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008031 | 400955861 | Molding | HFTD Tier 3 | Distribution | 2007-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008032 | 400959744 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2007-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008033 | 400883542 | High Sign | HFTD Tier 2 | Distribution | 2007-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008034 | 400947442 | High Sign | HFTD Tier 2 | Distribution | 2007-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008035 | 400959116 | Molding | HFTD Tier 2 | Distribution | 2007-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008036 | 400967026 | Molding | HFTD Tier 2 | Distribution | 2007-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008037 | 400875298 | High Sign | HFTD Tier 3 | Distribution | 2007-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008038 | 400909075 | Riser/Conduit | HFTD Tier 2 | Distribution | 2007-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008039 | 400913574 | Guy | HFTD Tier 3 | Distribution | 2007-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008040 | 400951694 | Guy | HFTD Tier 2 | Distribution | 2007-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008041 | 400952947 | Molding | HFTD Tier 2 | Distribution | 2007-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008042 | 400956088 | Molding | HFTD Tier 3 | Distribution | 2007-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008043 | 400968070 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2007-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008044 | 400528104 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008045 | 400869192 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008046 | 400892841 | Guy | HFTD Tier 3 | Distribution | 2007-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008047 | 400916562 | Molding | HFTD Tier 3 | Distribution | 2007-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008048 | 400958818 | Guy | HFTD Tier 3 | Distribution | 2007-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008049 | 400328998 | Molding | HFTD Tier 3 | Distribution | 2007-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008050 | 400334236 | Molding | HFTD Tier 3 | Distribution | 2007-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008051 | 400546870 | Molding | HFTD Tier 2 | Distribution | 2007-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008052 | 400561738 | Guy | HFTD Tier 3 | Distribution | 2007-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008053 | 400808904 | Molding | HFTD Tier 3 | Distribution | 2007-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008054 | 400963410 | Guy | HFTD Tier 3 | Distribution | 2007-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008055 | 400550468 | Molding | HFTD Tier 3 | Distribution | 2007-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008056 | 400556484 | Molding | HFTD Tier 3 | Distribution | 2007-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008057 | 400556497 | Guy | HFTD Tier 3 | Distribution | 2007-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008058 | 400574913 | High Sign | HFTD Tier 3 | Distribution | 2007-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008059 | 400896020 | Riser/Conduit | HFTD Tier 2 | Distribution | 2007-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008060 | 400929293 | Molding | HFTD Tier 3 | Distribution | 2007-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008061 | 400963630 | Molding | HFTD Tier 2 | Distribution | 2007-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008062 | 400963976 | Molding | HFTD Tier 2 | Distribution | 2007-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008063 | 400596601 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008064 | 400943959 | Molding | HFTD Tier 3 | Distribution | 2007-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008065 | 400949631 | High Sign | HFTD Tier 3 | Distribution | 2007-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008066 | 400966816 | High Sign | HFTD Tier 2 | Distribution | 2007-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008067 | 400970137 | Molding | HFTD Tier 3 | Distribution | 2007-05-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008068 | 400539909 | High Sign | HFTD Tier 2 | Distribution | 2007-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008069 | 400569462 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008070 | 400571969 | Molding | HFTD Tier 3 | Distribution | 2007-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008071 | 400576948 | Molding | HFTD Tier 3 | Distribution | 2007-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008072 | 400576967 | Molding | HFTD Tier 3 | Distribution | 2007-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008073 | 400578054 | High Sign | HFTD Tier 3 | Distribution | 2007-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008074 | 400583509 | Guy | HFTD Tier 3 | Distribution | 2007-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008075 | 400661350 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008076 | 401000599 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008077 | 400286981 | High Sign | HFTD Tier 2 | Distribution | 2007-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008078 | 400288619 | High Sign | HFTD Tier 2 | Distribution | 2007-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008079 | 400319159 | Molding | HFTD Tier 2 | Distribution | 2007-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008080 | 400324435 | High Sign | HFTD Tier 2 | Distribution | 2007-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008081 | 400366985 | Molding | HFTD Tier 2 | Distribution | 2007-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008082 | 400547526 | Molding | HFTD Tier 3 | Distribution | 2007-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008083 | 400566999 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008084 | 400572566 | Molding | HFTD Tier 3 | Distribution | 2007-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008085 | 400577893 | High Sign | HFTD Tier 3 | Distribution | 2007-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008086 | 400661268 | Molding | HFTD Tier 3 | Distribution | 2007-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008087 | 400538230 | Guy | HFTD Tier 3 | Distribution | 2007-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008088 | 400570568 | High Sign | HFTD Tier 3 | Distribution | 2007-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008089 | 400571386 | Molding | HFTD Tier 3 | Distribution | 2007-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008090 | 400576487 | Guy | HFTD Tier 3 | Distribution | 2007-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008091 | 400583141 | High Sign | HFTD Tier 2 | Distribution | 2007-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008092 | 400958213 | High Sign | HFTD Tier 2 | Distribution | 2007-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008093 | 400958498 | Molding | HFTD Tier 2 | Distribution | 2007-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008094 | 400567411 | Guy | HFTD Tier 3 | Distribution | 2007-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008095 | 400568529 | High Sign | HFTD Tier 3 | Distribution | 2007-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008096 | 400570189 | Guy | HFTD Tier 3 | Distribution | 2007-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008097 | 400585430 | Guy | HFTD Tier 3 | Distribution | 2007-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008098 | 400586854 | Guy | HFTD Tier 3 | Distribution | 2007-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008099 | 400592272 | High Sign | HFTD Tier 3 | Distribution | 2007-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008100 | 400606428 | Guy | HFTD Tier 3 | Distribution | 2007-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008101 | 400642107 | High Sign | HFTD Tier 3 | Distribution | 2007-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008102 | 400650141 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008103 | 400671921 | Guy | HFTD Tier 3 | Distribution | 2007-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008104 | 400693502 | Guy | HFTD Tier 3 | Distribution | 2007-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008105 | 400693528 | High Sign | HFTD Tier 3 | Distribution | 2007-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008106 | 400694627 | Molding | HFTD Tier 3 | Distribution | 2007-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008107 | 403048027 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008108 | 400590383 | High Sign | HFTD Tier 3 | Distribution | 2007-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008109 | 400601296 | Molding | HFTD Tier 3 | Distribution | 2007-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008110 | 400609687 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008111 | 400621315 | Molding | HFTD Tier 2 | Distribution | 2007-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008112 | 400622204 | Molding | HFTD Tier 2 | Distribution | 2007-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008113 | 400625913 | Molding | HFTD Tier 2 | Distribution | 2007-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008114 | 400287438 | High Sign | HFTD Tier 2 | Distribution | 2007-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008115 | 400582709 | Molding | HFTD Tier 3 | Distribution | 2007-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008116 | 400584862 | Molding | HFTD Tier 2 | Distribution | 2007-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008117 | 400597879 | Molding | HFTD Tier 2 | Distribution | 2007-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008118 | 400605075 | Guy | HFTD Tier 2 | Distribution | 2007-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008119 | 400622682 | High Sign | HFTD Tier 3 | Distribution | 2007-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008120 | 400633591 | Molding | HFTD Tier 2 | Distribution | 2007-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008121 | 400637200 | High Sign | HFTD Tier 2 | Distribution | 2007-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008122 | 400638459 | High Sign | HFTD Tier 2 | Distribution | 2007-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008123 | 400648220 | Guy | HFTD Tier 2 | Distribution | 2007-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008124 | 400721170 | Guy | HFTD Tier 3 | Distribution | 2007-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008125 | 400723269 | Guy | HFTD Tier 2 | Distribution | 2007-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008126 | 400605159 | Molding | HFTD Tier 2 | Distribution | 2007-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008127 | 400607863 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008128 | 400643402 | Guy | HFTD Tier 3 | Distribution | 2007-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008129 | 400653272 | Guy | HFTD Tier 3 | Distribution | 2007-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008130 | 400617599 | Guy | HFTD Tier 3 | Distribution | 2007-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008131 | 400640329 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008132 | 400646779 | Molding | HFTD Tier 3 | Distribution | 2007-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008133 | 400648711 | Guy | HFTD Tier 3 | Distribution | 2007-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008134 | 400655870 | Molding | HFTD Tier 3 | Distribution | 2007-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008135 | 400655930 | High Sign | HFTD Tier 3 | Distribution | 2007-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008136 | 400656157 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008137 | 400691366 | Molding | HFTD Tier 2 | Distribution | 2007-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008138 | 400742636 | Guy | HFTD Tier 3 | Distribution | 2007-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008139 | 400626830 | Molding | HFTD Tier 3 | Distribution | 2007-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008140 | 400645820 | Molding | HFTD Tier 3 | Distribution | 2007-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008141 | 400664571 | Molding | HFTD Tier 3 | Distribution | 2007-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008142 | 400684758 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008143 | 400775929 | High Sign | HFTD Tier 2 | Distribution | 2007-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008144 | 400687449 | High Sign | HFTD Tier 2 | Distribution | 2007-06-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008145 | 400724110 | High Sign | HFTD Tier 2 | Distribution | 2007-06-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008146 | 400792827 | Molding | HFTD Tier 3 | Distribution | 2007-06-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008147 | 400816459 | Molding | HFTD Tier 2 | Distribution | 2007-06-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008148 | 400843798 | Guy | HFTD Tier 3 | Distribution | 2007-06-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008149 | 400715517 | High Sign | HFTD Tier 2 | Distribution | 2007-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008150 | 400819499 | Molding | HFTD Tier 3 | Distribution | 2007-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008151 | 400867695 | High Sign | HFTD Tier 3 | Distribution | 2007-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008152 | 400869675 | High Sign | HFTD Tier 3 | Distribution | 2007-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008153 | 400935143 | High Sign | HFTD Tier 3 | Distribution | 2007-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008154 | 400838026 | Molding | HFTD Tier 2 | Distribution | 2007-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008155 | 400877186 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008156 | 400775425 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008157 | 400885499 | High Sign | HFTD Tier 3 | Distribution | 2007-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008158 | 400744654 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008159 | 400765347 | High Sign | HFTD Tier 3 | Distribution | 2007-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008160 | 400856235 | Molding | HFTD Tier 2 | Distribution | 2007-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008161 | 400869271 | High Sign | HFTD Tier 2 | Distribution | 2007-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008162 | 400897599 | Molding | HFTD Tier 2 | Distribution | 2007-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008163 | 400871838 | Molding | HFTD Tier 2 | Distribution | 2007-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008164 | 400918113 | Guy | HFTD Tier 3 | Distribution | 2007-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008165 | 400798570 | Guy | HFTD Tier 3 | Distribution | 2007-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008166 | 400798586 | Guy | HFTD Tier 3 | Distribution | 2007-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008167 | 400884519 | High Sign | HFTD Tier 3 | Distribution | 2007-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008168 | 400890649 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008169 | 400941467 | High Sign | HFTD Tier 3 | Distribution | 2007-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008170 | 400532077 | High Sign | HFTD Tier 3 | Distribution | 2007-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008171 | 400535569 | High Sign | HFTD Tier 3 | Distribution | 2007-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008172 | 400774931 | Molding | HFTD Tier 3 | Distribution | 2007-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008173 | 400922116 | Molding | HFTD Tier 3 | Distribution | 2007-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008174 | 400941085 | Guy | HFTD Tier 3 | Distribution | 2007-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008175 | 400805851 | High Sign | HFTD Tier 3 | Distribution | 2007-07-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008176 | 400827439 | Guy | HFTD Tier 3 | Distribution | 2007-07-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008177 | 400796504 | Molding | HFTD Tier 3 | Distribution | 2007-07-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008178 | 400833499 | High Sign | HFTD Tier 2 | Distribution | 2007-07-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008179 | 400834165 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-07-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008180 | 400853216 | Molding | HFTD Tier 2 | Distribution | 2007-07-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008181 | 400861733 | High Sign | HFTD Tier 2 | Distribution | 2007-07-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008182 | 400951104 | High Sign | HFTD Tier 2 | Distribution | 2007-07-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008183 | 400568779 | Guy | HFTD Tier 2 | Distribution | 2007-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008184 | 400814814 | Molding | HFTD Tier 3 | Distribution | 2007-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008185 | 400582081 | Molding | HFTD Tier 3 | Distribution | 2007-07-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008186 | 400595891 | Molding | HFTD Tier 3 | Distribution | 2007-07-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008187 | 400853519 | Molding | HFTD Tier 3 | Distribution | 2007-07-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008188 | 400857288 | Molding | HFTD Tier 3 | Distribution | 2007-07-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008189 | 400859309 | Guy | HFTD Tier 3 | Distribution | 2007-07-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008190 | 400954420 | High Sign | HFTD Tier 3 | Distribution | 2007-07-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008191 | 400955021 | Molding | HFTD Tier 3 | Distribution | 2007-07-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008192 | 400642674 | Molding | HFTD Tier 3 | Distribution | 2007-07-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008193 | 400862862 | High Sign | HFTD Tier 3 | Distribution | 2007-07-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008194 | 400956372 | High Sign | HFTD Tier 3 | Distribution | 2007-07-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008195 | 400644774 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008196 | 400880126 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008197 | 400636683 | Molding | HFTD Tier 3 | Distribution | 2007-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008198 | 400639236 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008199 | 400967613 | Molding | HFTD Tier 3 | Distribution | 2007-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008200 | 400534639 | Molding | HFTD Tier 2 | Distribution | 2007-07-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008201 | 400558507 | Guy | HFTD Tier 3 | Distribution | 2007-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008202 | 400666083 | Guy | HFTD Tier 3 | Distribution | 2007-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008203 | 400669573 | Cable/Conductor | HFTD Tier 2 | Distribution | 2007-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008204 | 400670906 | Guy | HFTD Tier 3 | Distribution | 2007-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008205 | 400539067 | Guy | HFTD Tier 3 | Distribution | 2007-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008206 | 400669592 | Molding | HFTD Tier 3 | Distribution | 2007-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008207 | 400920854 | High Sign | HFTD Tier 2 | Distribution | 2007-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008208 | 400543414 | High Sign | HFTD Tier 3 | Distribution | 2007-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008209 | 400589681 | Molding | HFTD Tier 3 | Distribution | 2007-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008210 | 400548435 | Molding | HFTD Tier 2 | Distribution | 2007-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008211 | 400559964 | High Sign | HFTD Tier 3 | Distribution | 2007-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008212 | 400590816 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008213 | 400597292 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008214 | 400600535 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008215 | 400603861 | High Sign | HFTD Tier 2 | Distribution | 2007-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008216 | 400609657 | High Sign | HFTD Tier 3 | Distribution | 2007-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008217 | 400725378 | High Sign | HFTD Tier 2 | Distribution | 2007-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008218 | 400562985 | Molding | HFTD Tier 2 | Distribution | 2007-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008219 | 400604311 | Guy | HFTD Tier 2 | Distribution | 2007-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008220 | 400714130 | Molding | HFTD Tier 2 | Distribution | 2007-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008221 | 400727105 | Molding | HFTD Tier 2 | Distribution | 2007-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008222 | 400319449 | Molding | HFTD Tier 3 | Distribution | 2007-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008223 | 400576805 | High Sign | HFTD Tier 3 | Distribution | 2007-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008224 | 400583483 | High Sign | HFTD Tier 3 | Distribution | 2007-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008225 | 400586071 | High Sign | HFTD Tier 3 | Distribution | 2007-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008226 | 400619861 | Cable/Conductor | HFTD Tier 2 | Distribution | 2007-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008227 | 400628167 | High Sign | HFTD Tier 2 | Distribution | 2007-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008228 | 400628186 | High Sign | HFTD Tier 3 | Distribution | 2007-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008229 | 400634694 | High Sign | HFTD Tier 3 | Distribution | 2007-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008230 | 400634716 | High Sign | HFTD Tier 3 | Distribution | 2007-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008231 | 400637444 | High Sign | HFTD Tier 3 | Distribution | 2007-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008232 | 400638688 | High Sign | HFTD Tier 3 | Distribution | 2007-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008233 | 400742364 | Insulator | HFTD Tier 3 | Distribution | 2007-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008234 | 400858537 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2007-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008235 | 400568831 | Molding | HFTD Tier 3 | Distribution | 2007-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008236 | 400576787 | Guy | HFTD Tier 2 | Distribution | 2007-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008237 | 400588138 | High Sign | HFTD Tier 2 | Distribution | 2007-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008238 | 400633887 | High Sign | HFTD Tier 3 | Distribution | 2007-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008239 | 400635183 | Molding | HFTD Tier 2 | Distribution | 2007-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008240 | 400636333 | Guy | HFTD Tier 2 | Distribution | 2007-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008241 | 400637468 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008242 | 400637856 | High Sign | HFTD Tier 2 | Distribution | 2007-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008243 | 400639749 | High Sign | HFTD Tier 2 | Distribution | 2007-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008244 | 400643345 | High Sign | HFTD Tier 2 | Distribution | 2007-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008245 | 400652078 | High Sign | HFTD Tier 2 | Distribution | 2007-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008246 | 400653554 | High Sign | HFTD Tier 2 | Distribution | 2007-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008247 | 400850777 | High Sign | HFTD Tier 3 | Distribution | 2007-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008248 | 400854257 | High Sign | HFTD Tier 2 | Distribution | 2007-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008249 | 400858002 | High Sign | HFTD Tier 2 | Distribution | 2007-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008250 | 400861259 | Guy | HFTD Tier 2 | Distribution | 2007-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008251 | 400607215 | High Sign | HFTD Tier 2 | Distribution | 2007-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008252 | 400645783 | High Sign | HFTD Tier 2 | Distribution | 2007-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008253 | 400649191 | High Sign | HFTD Tier 3 | Distribution | 2007-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008254 | 400652482 | High Sign | HFTD Tier 2 | Distribution | 2007-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008255 | 400663557 | High Sign | HFTD Tier 2 | Distribution | 2007-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008256 | 400669739 | High Sign | HFTD Tier 2 | Distribution | 2007-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008257 | 400671659 | High Sign | HFTD Tier 2 | Distribution | 2007-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008258 | 400675405 | High Sign | HFTD Tier 2 | Distribution | 2007-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008259 | 400860376 | High Sign | HFTD Tier 2 | Distribution | 2007-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008260 | 400871761 | High Sign | HFTD Tier 2 | Distribution | 2007-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008261 | 400594476 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008262 | 400607194 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008263 | 400608040 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008264 | 400613415 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008265 | 400613445 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008266 | 400664745 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008267 | 400664763 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008268 | 400665690 | Guy | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008269 | 400666163 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008270 | 400668601 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008271 | 400670606 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008272 | 400671731 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008273 | 400673050 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008274 | 400673371 | Molding | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008275 | 400673728 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008276 | 400676473 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008277 | 400677941 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008278 | 400680063 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008279 | 400681308 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008280 | 400713551 | High Sign | HFTD Tier 3 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008281 | 400861083 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008282 | 400871734 | Guy | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008283 | 400871773 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008284 | 400874027 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008285 | 400874051 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008286 | 400875035 | Guy | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008287 | 400875052 | High Sign | HFTD Tier 2 | Distribution | 2007-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008288 | 400670576 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2007-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008289 | 400883496 | High Sign | HFTD Tier 2 | Distribution | 2007-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008290 | 400344100 | Molding | HFTD Tier 2 | Distribution | 2007-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008291 | 400684259 | High Sign | HFTD Tier 3 | Distribution | 2007-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008292 | 400689120 | Molding | HFTD Tier 2 | Distribution | 2007-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008293 | 400689360 | Molding | HFTD Tier 2 | Distribution | 2007-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008294 | 400689540 | High Sign | HFTD Tier 2 | Distribution | 2007-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008295 | 400693371 | High Sign | HFTD Tier 2 | Distribution | 2007-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008296 | 400898300 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2007-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008297 | 400903533 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008298 | 400641445 | High Sign | HFTD Tier 2 | Distribution | 2007-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008299 | 400643615 | High Sign | HFTD Tier 2 | Distribution | 2007-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008300 | 400655458 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008301 | 400711873 | Molding | HFTD Tier 2 | Distribution | 2007-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008302 | 400746191 | Guy | HFTD Tier 2 | Distribution | 2007-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008303 | 400901056 | High Sign | HFTD Tier 3 | Distribution | 2007-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008304 | 400656359 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-08-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008305 | 400708266 | High Sign | HFTD Tier 3 | Distribution | 2007-08-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008306 | 400721959 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-08-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008307 | 400666035 | High Sign | HFTD Tier 2 | Distribution | 2007-08-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008308 | 400736445 | Molding | HFTD Tier 2 | Distribution | 2007-08-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008309 | 400864008 | Guy | HFTD Tier 3 | Distribution | 2007-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008310 | 400539778 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008311 | 400872168 | Guy | HFTD Tier 2 | Distribution | 2007-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008312 | 400545357 | Guy | HFTD Tier 2 | Distribution | 2007-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008313 | 400714335 | Molding | HFTD Tier 2 | Distribution | 2007-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008314 | 400779909 | Guy | HFTD Tier 3 | Distribution | 2007-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008315 | 400782787 | Molding | HFTD Tier 3 | Distribution | 2007-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008316 | 400810451 | High Sign | HFTD Tier 2 | Distribution | 2007-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008317 | 400882928 | Molding | HFTD Tier 3 | Distribution | 2007-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008318 | 400901615 | Molding | HFTD Tier 3 | Distribution | 2007-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008319 | 400957641 | Molding | HFTD Tier 3 | Distribution | 2007-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008320 | 400760602 | Molding | HFTD Tier 3 | Distribution | 2007-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008321 | 400812223 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008322 | 400821258 | Insulator | HFTD Tier 3 | Distribution | 2007-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008323 | 400899649 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2007-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008324 | 400958466 | High Sign | HFTD Tier 3 | Distribution | 2007-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008325 | 400964445 | Guy | HFTD Tier 3 | Distribution | 2007-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008326 | 400756597 | Molding | HFTD Tier 3 | Distribution | 2007-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008327 | 400759346 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008328 | 400543174 | Guy | HFTD Tier 3 | Distribution | 2007-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008329 | 400583431 | Molding | HFTD Tier 3 | Distribution | 2007-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008330 | 400830712 | High Sign | HFTD Tier 3 | Distribution | 2007-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008331 | 400832689 | Guy | HFTD Tier 2 | Distribution | 2007-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008332 | 400939371 | Guy | HFTD Tier 3 | Distribution | 2007-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008333 | 400596122 | Molding | HFTD Tier 3 | Distribution | 2007-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008334 | 400599626 | Molding | HFTD Tier 3 | Distribution | 2007-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008335 | 400796594 | Guy | HFTD Tier 3 | Distribution | 2007-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008336 | 400865503 | Guy | HFTD Tier 3 | Distribution | 2007-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008337 | 400656688 | High Sign | HFTD Tier 3 | Distribution | 2007-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008338 | 400805774 | High Sign | HFTD Tier 3 | Distribution | 2007-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008339 | 400807600 | Molding | HFTD Tier 3 | Distribution | 2007-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008340 | 400810897 | Molding | HFTD Tier 3 | Distribution | 2007-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008341 | 400929343 | Molding | HFTD Tier 3 | Distribution | 2007-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008342 | 400948415 | Molding | HFTD Tier 3 | Distribution | 2007-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008343 | 400951360 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2007-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008344 | 400955457 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008345 | 400363107 | High Sign | HFTD Tier 3 | Distribution | 2007-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008346 | 400894399 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008347 | 400415099 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008348 | 400822988 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008349 | 400824981 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008350 | 400855757 | Molding | HFTD Tier 2 | Distribution | 2007-08-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008351 | 400927173 | Molding | HFTD Tier 3 | Distribution | 2007-08-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008352 | 400962647 | Molding | HFTD Tier 3 | Distribution | 2007-08-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008353 | 400339155 | Molding | HFTD Tier 2 | Distribution | 2007-08-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008354 | 400539189 | High Sign | HFTD Tier 2 | Distribution | 2007-08-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008355 | 400542338 | Molding | HFTD Tier 2 | Distribution | 2007-08-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008356 | 400845857 | Molding | HFTD Tier 3 | Distribution | 2007-08-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008357 | 400857512 | Molding | HFTD Tier 2 | Distribution | 2007-08-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008358 | 400576858 | High Sign | HFTD Tier 2 | Distribution | 2007-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008359 | 400581845 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008360 | 400674443 | Molding | HFTD Tier 3 | Distribution | 2007-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008361 | 400706094 | Molding | HFTD Tier 2 | Distribution | 2007-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008362 | 400706139 | Riser/Conduit | HFTD Tier 2 | Distribution | 2007-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008363 | 400708903 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-08-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008364 | 400872378 | Molding | HFTD Tier 3 | Distribution | 2007-08-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008365 | 400878930 | High Sign | HFTD Tier 2 | Distribution | 2007-08-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008366 | 400560852 | Guy | HFTD Tier 3 | Distribution | 2007-08-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008367 | 400905706 | Guy | HFTD Tier 2 | Distribution | 2007-08-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008368 | 400578213 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-09-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008369 | 400584767 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-09-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008370 | 400587472 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-09-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008371 | 400618476 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-09-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008372 | 400622392 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-09-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008373 | 400641537 | Molding | HFTD Tier 2 | Distribution | 2007-09-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008374 | 400658188 | High Sign | HFTD Tier 2 | Distribution | 2007-09-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008375 | 400715647 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-09-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008376 | 400734578 | Molding | HFTD Tier 2 | Distribution | 2007-09-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008377 | 400899070 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-09-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008378 | 400900790 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-09-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008379 | 401555415 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-09-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008380 | 401555428 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-09-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008381 | 401556616 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-09-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008382 | 401557274 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-09-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008383 | 401557467 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-09-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008384 | 400622492 | High Sign | HFTD Tier 2 | Distribution | 2007-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008385 | 400651064 | Molding | HFTD Tier 2 | Distribution | 2007-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008386 | 400742038 | High Sign | HFTD Tier 2 | Distribution | 2007-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008387 | 400911108 | Molding | HFTD Tier 2 | Distribution | 2007-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008388 | 400911150 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008389 | 400916939 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008390 | 400917000 | Molding | HFTD Tier 3 | Distribution | 2007-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008391 | 400688143 | Guy | HFTD Tier 3 | Distribution | 2007-09-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008392 | 400543594 | Guy | HFTD Tier 3 | Distribution | 2007-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008393 | 400558040 | Guy | HFTD Tier 2 | Distribution | 2007-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008394 | 400558977 | High Sign | HFTD Tier 2 | Distribution | 2007-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008395 | 400729692 | High Sign | HFTD Tier 2 | Distribution | 2007-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008396 | 400784760 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008397 | 400387604 | High Sign | HFTD Tier 2 | Distribution | 2007-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008398 | 400817100 | Molding | HFTD Tier 2 | Distribution | 2007-09-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008399 | 400346591 | High Sign | HFTD Tier 3 | Distribution | 2007-09-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008400 | 400389480 | Molding | HFTD Tier 3 | Distribution | 2007-09-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008401 | 400584929 | High Sign | HFTD Tier 3 | Distribution | 2007-09-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008402 | 400733734 | Guy | HFTD Tier 3 | Distribution | 2007-09-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008403 | 400737346 | Guy | HFTD Tier 3 | Distribution | 2007-09-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008404 | 400758248 | Molding | HFTD Tier 2 | Distribution | 2007-09-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008405 | 400597171 | High Sign | HFTD Tier 3 | Distribution | 2007-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008406 | 400779160 | High Sign | HFTD Tier 2 | Distribution | 2007-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008407 | 400782423 | Molding | HFTD Tier 2 | Distribution | 2007-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008408 | 400868465 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008409 | 400868990 | Molding | HFTD Tier 2 | Distribution | 2007-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008410 | 400872308 | High Sign | HFTD Tier 2 | Distribution | 2007-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008411 | 400881908 | Molding | HFTD Tier 2 | Distribution | 2007-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008412 | 400594716 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-09-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008413 | 400868513 | High Sign | HFTD Tier 3 | Distribution | 2007-09-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008414 | 400885709 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2007-09-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008415 | 400616367 | High Sign | HFTD Tier 2 | Distribution | 2007-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008416 | 400623246 | High Sign | HFTD Tier 2 | Distribution | 2007-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008417 | 400801910 | Molding | HFTD Tier 2 | Distribution | 2007-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008418 | 400906567 | High Sign | HFTD Tier 2 | Distribution | 2007-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008419 | 400535798 | Molding | HFTD Tier 3 | Distribution | 2007-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008420 | 400610644 | High Sign | HFTD Tier 3 | Distribution | 2007-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008421 | 400618789 | Riser/Conduit | HFTD Tier 3 | Distribution | 2007-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008422 | 400631100 | High Sign | HFTD Tier 2 | Distribution | 2007-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008423 | 400631350 | High Sign | HFTD Tier 2 | Distribution | 2007-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008424 | 400809513 | High Sign | HFTD Tier 2 | Distribution | 2007-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008425 | 400809526 | High Sign | HFTD Tier 2 | Distribution | 2007-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008426 | 400814305 | High Sign | HFTD Tier 2 | Distribution | 2007-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008427 | 400814549 | High Sign | HFTD Tier 2 | Distribution | 2007-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008428 | 400896488 | High Sign | HFTD Tier 2 | Distribution | 2007-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008429 | 400897803 | High Sign | HFTD Tier 2 | Distribution | 2007-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008430 | 400908537 | High Sign | HFTD Tier 3 | Distribution | 2007-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008431 | 400925715 | High Sign | HFTD Tier 2 | Distribution | 2007-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008432 | 400927757 | High Sign | HFTD Tier 2 | Distribution | 2007-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008433 | 400930118 | High Sign | HFTD Tier 2 | Distribution | 2007-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008434 | 400931417 | High Sign | HFTD Tier 2 | Distribution | 2007-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008435 | 400533924 | Molding | HFTD Tier 3 | Distribution | 2007-10-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008436 | 400534527 | High Sign | HFTD Tier 3 | Distribution | 2007-10-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008437 | 400634475 | Guy | HFTD Tier 3 | Distribution | 2007-10-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008438 | 400637585 | Guy | HFTD Tier 3 | Distribution | 2007-10-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008439 | 400641312 | Guy | HFTD Tier 3 | Distribution | 2007-10-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008440 | 400642119 | High Sign | HFTD Tier 2 | Distribution | 2007-10-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008441 | 400822123 | Guy | HFTD Tier 3 | Distribution | 2007-10-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008442 | 400822149 | Guy | HFTD Tier 3 | Distribution | 2007-10-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008443 | 400825271 | Guy | HFTD Tier 3 | Distribution | 2007-10-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008444 | 400825287 | High Sign | HFTD Tier 3 | Distribution | 2007-10-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008445 | 400843298 | High Sign | HFTD Tier 2 | Distribution | 2007-10-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008446 | 400906216 | Guy | HFTD Tier 3 | Distribution | 2007-10-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008447 | 400906985 | High Sign | HFTD Tier 3 | Distribution | 2007-10-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008448 | 400910343 | High Sign | HFTD Tier 3 | Distribution | 2007-10-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008449 | 400642700 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008450 | 400645316 | Cable/Conductor | HFTD Tier 2 | Distribution | 2007-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008451 | 400650588 | High Sign | HFTD Tier 2 | Distribution | 2007-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008452 | 400851968 | Molding | HFTD Tier 2 | Distribution | 2007-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008453 | 400909013 | High Sign | HFTD Tier 3 | Distribution | 2007-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008454 | 400931066 | Molding | HFTD Tier 2 | Distribution | 2007-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008455 | 403048134 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2007-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008456 | 400934180 | High Sign | HFTD Tier 2 | Distribution | 2007-10-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008457 | 400649195 | High Sign | HFTD Tier 2 | Distribution | 2007-10-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008458 | 400649219 | High Sign | HFTD Tier 2 | Distribution | 2007-10-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008459 | 400658329 | High Sign | HFTD Tier 2 | Distribution | 2007-10-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008460 | 400847946 | High Sign | HFTD Tier 3 | Distribution | 2007-10-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008461 | 400848119 | Guy | HFTD Tier 2 | Distribution | 2007-10-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008462 | 400852845 | High Sign | HFTD Tier 2 | Distribution | 2007-10-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008463 | 400870287 | High Sign | HFTD Tier 3 | Distribution | 2007-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008464 | 400940753 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008465 | 400682726 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-10-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008466 | 400686941 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-10-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008467 | 400682754 | Molding | HFTD Tier 3 | Distribution | 2007-10-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008468 | 400906870 | Molding | HFTD Tier 2 | Distribution | 2007-10-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008469 | 400393092 | Molding | HFTD Tier 2 | Distribution | 2007-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008470 | 400394781 | High Sign | HFTD Tier 2 | Distribution | 2007-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008471 | 400403194 | Molding | HFTD Tier 2 | Distribution | 2007-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008472 | 400427332 | Molding | HFTD Tier 2 | Distribution | 2007-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008473 | 400433244 | Molding | HFTD Tier 2 | Distribution | 2007-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008474 | 400909959 | High Sign | HFTD Tier 3 | Distribution | 2007-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008475 | 400912709 | Molding | HFTD Tier 2 | Distribution | 2007-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008476 | 400919240 | Molding | HFTD Tier 3 | Distribution | 2007-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008477 | 400929322 | Guy | HFTD Tier 3 | Distribution | 2007-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008478 | 400957646 | Riser/Conduit | HFTD Tier 3 | Distribution | 2007-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008479 | 400361696 | Molding | HFTD Tier 2 | Distribution | 2007-10-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008480 | 400363589 | Molding | HFTD Tier 2 | Distribution | 2007-10-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008481 | 400778794 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008482 | 400535824 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-10-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008483 | 400543756 | High Sign | HFTD Tier 2 | Distribution | 2007-10-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008484 | 400554806 | High Sign | HFTD Tier 2 | Distribution | 2007-10-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008485 | 400659943 | Molding | HFTD Tier 2 | Distribution | 2007-10-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008486 | 400714065 | High Sign | HFTD Tier 3 | Distribution | 2007-10-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008487 | 400535692 | Guy | HFTD Tier 2 | Distribution | 2007-10-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008488 | 400539156 | Guy | HFTD Tier 2 | Distribution | 2007-10-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008489 | 400551734 | High Sign | HFTD Tier 2 | Distribution | 2007-10-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008490 | 400556486 | High Sign | HFTD Tier 2 | Distribution | 2007-10-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008491 | 400656843 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-10-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008492 | 400656891 | High Sign | HFTD Tier 2 | Distribution | 2007-10-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008493 | 400657170 | Molding | HFTD Tier 2 | Distribution | 2007-10-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008494 | 400566562 | High Sign | HFTD Tier 2 | Distribution | 2007-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008495 | 400580760 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008496 | 400682423 | Molding | HFTD Tier 2 | Distribution | 2007-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008497 | 400588047 | Molding | HFTD Tier 2 | Distribution | 2007-10-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008498 | 400409829 | High Sign | HFTD Tier 3 | Distribution | 2007-10-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008499 | 400375815 | Molding | HFTD Tier 2 | Distribution | 2007-10-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008500 | 400399610 | High Sign | HFTD Tier 2 | Distribution | 2007-10-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008501 | 400439270 | Molding | HFTD Tier 2 | Distribution | 2007-10-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008502 | 400616671 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-10-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008503 | 400618407 | Molding | HFTD Tier 2 | Distribution | 2007-10-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008504 | 400620077 | Molding | HFTD Tier 2 | Distribution | 2007-10-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008505 | 400622661 | High Sign | HFTD Tier 2 | Distribution | 2007-10-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008506 | 400626998 | High Sign | HFTD Tier 2 | Distribution | 2007-10-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008507 | 400759209 | High Sign | HFTD Tier 2 | Distribution | 2007-10-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008508 | 400635852 | High Sign | HFTD Tier 2 | Distribution | 2007-11-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008509 | 400649451 | High Sign | HFTD Tier 2 | Distribution | 2007-11-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008510 | 400762896 | Molding | HFTD Tier 2 | Distribution | 2007-11-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008511 | 400772931 | High Sign | HFTD Tier 2 | Distribution | 2007-11-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008512 | 400757983 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2007-11-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008513 | 400762777 | Molding | HFTD Tier 3 | Distribution | 2007-11-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008514 | 401565012 | Cable/Conductor | HFTD Tier 2 | Distribution | 2007-11-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008515 | 400665468 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008516 | 400670626 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2007-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008517 | 400776970 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008518 | 400676516 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008519 | 400676758 | Molding | HFTD Tier 3 | Distribution | 2007-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008520 | 400780690 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008521 | 400686071 | Cable/Conductor | HFTD Tier 3 | Distribution | 2007-11-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008522 | 400703857 | High Sign | HFTD Tier 3 | Distribution | 2007-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008523 | 400686108 | Guy | HFTD Tier 3 | Distribution | 2007-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008524 | 400695163 | High Sign | HFTD Tier 3 | Distribution | 2007-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008525 | 400696297 | High Sign | HFTD Tier 3 | Distribution | 2007-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008526 | 400797052 | High Sign | HFTD Tier 3 | Distribution | 2007-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008527 | 400713422 | High Sign | HFTD Tier 3 | Distribution | 2007-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008528 | 400802014 | High Sign | HFTD Tier 3 | Distribution | 2007-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008529 | 400727819 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008530 | 400740185 | Molding | HFTD Tier 2 | Distribution | 2007-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008531 | 400806693 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008532 | 400812962 | High Sign | HFTD Tier 2 | Distribution | 2007-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008533 | 400726718 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-11-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008534 | 400816690 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2007-11-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008535 | 400740147 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-11-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008536 | 400811679 | Guy | HFTD Tier 3 | Distribution | 2007-11-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008537 | 400815330 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-11-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008538 | 400831487 | Molding | HFTD Tier 2 | Distribution | 2007-11-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008539 | 400845170 | Molding | HFTD Tier 3 | Distribution | 2007-11-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008540 | 400850079 | Molding | HFTD Tier 3 | Distribution | 2007-11-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008541 | 400850095 | Molding | HFTD Tier 3 | Distribution | 2007-11-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008542 | 400830539 | Molding | HFTD Tier 3 | Distribution | 2007-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008543 | 400844599 | High Sign | HFTD Tier 3 | Distribution | 2007-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008544 | 400844630 | Molding | HFTD Tier 2 | Distribution | 2007-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008545 | 400850656 | High Sign | HFTD Tier 3 | Distribution | 2007-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008546 | 400780136 | Molding | HFTD Tier 2 | Distribution | 2007-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008547 | 400785971 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2007-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008548 | 400840849 | High Sign | HFTD Tier 3 | Distribution | 2007-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008549 | 400848266 | Cable/Conductor | HFTD Tier 2 | Distribution | 2007-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008550 | 400859081 | Molding | HFTD Tier 3 | Distribution | 2007-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008551 | 400797995 | High Sign | HFTD Tier 2 | Distribution | 2007-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008552 | 400845732 | High Sign | HFTD Tier 2 | Distribution | 2007-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008553 | 400877577 | Guy | HFTD Tier 3 | Distribution | 2007-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008554 | 400789137 | Molding | HFTD Tier 3 | Distribution | 2007-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008555 | 400816279 | Molding | HFTD Tier 3 | Distribution | 2007-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008556 | 400818080 | Hardware/Framing | HFTD Tier 2 | Distribution | 2007-12-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008557 | 400854338 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2007-12-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008558 | 400891822 | Molding | HFTD Tier 2 | Distribution | 2007-12-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008559 | 400822349 | Hardware/Framing | HFTD Tier 3 | Distribution | 2007-12-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008560 | 400906817 | High Sign | HFTD Tier 3 | Distribution | 2007-12-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008561 | 400828825 | Guy | HFTD Tier 3 | Distribution | 2007-12-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008562 | 400815341 | Molding | HFTD Tier 3 | Distribution | 2007-12-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008563 | 400867984 | Molding | HFTD Tier 3 | Distribution | 2007-12-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008564 | 400919875 | Molding | HFTD Tier 3 | Distribution | 2007-12-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008565 | 400921743 | High Sign | HFTD Tier 3 | Distribution | 2007-12-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008566 | 400997199 | Cable/Conductor | HFTD Tier 2 | Distribution | 2007-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008567 | 400899005 | Cable/Conductor | HFTD Tier 2 | Distribution | 2007-12-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008568 | 400991164 | Cable/Conductor | HFTD Tier 2 | Distribution | 2007-12-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008569 | 400536828 | High Sign | HFTD Tier 3 | Distribution | 2008-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008570 | 400595143 | High Sign | HFTD Tier 3 | Distribution | 2008-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008571 | 400928361 | High Sign | HFTD Tier 3 | Distribution | 2008-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008572 | 400425450 | Guy | HFTD Tier 3 | Distribution | 2008-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008573 | 400538034 | High Sign | HFTD Tier 3 | Distribution | 2008-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008574 | 400540616 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008575 | 400587566 | Molding | HFTD Tier 3 | Distribution | 2008-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008576 | 400009411 | Guy | HFTD Tier 3 | Distribution | 2008-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008577 | 400528229 | High Sign | HFTD Tier 2 | Distribution | 2008-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008578 | 400926834 | Molding | HFTD Tier 2 | Distribution | 2008-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008579 | 400930781 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008580 | 403048781 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2008-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008581 | 400402869 | Molding | HFTD Tier 3 | Distribution | 2008-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008582 | 400599470 | High Sign | HFTD Tier 2 | Distribution | 2008-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008583 | 400009717 | High Sign | HFTD Tier 3 | Distribution | 2008-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008584 | 401569103 | Cable/Conductor | HFTD Tier 3 | Distribution | 2008-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008585 | 401569256 | Cable/Conductor | HFTD Tier 3 | Distribution | 2008-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008586 | 401570431 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008587 | 401571216 | Cable/Conductor | HFTD Tier 3 | Distribution | 2008-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008588 | 400651493 | High Sign | HFTD Tier 3 | Distribution | 2008-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008589 | 400652944 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008590 | 400681033 | Guy | HFTD Tier 3 | Distribution | 2008-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008591 | 400685283 | High Sign | HFTD Tier 3 | Distribution | 2008-02-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008592 | 401570564 | Ground | HFTD Tier 3 | Distribution | 2008-02-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008593 | 401570603 | Insulator | HFTD Tier 3 | Distribution | 2008-02-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008594 | 400358663 | Molding | HFTD Tier 2 | Distribution | 2008-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008595 | 401461014 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2008-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008596 | 401572854 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008597 | 400628589 | Molding | HFTD Tier 3 | Distribution | 2008-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008598 | 400637050 | High Sign | HFTD Tier 3 | Distribution | 2008-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008599 | 400721265 | High Sign | HFTD Tier 2 | Distribution | 2008-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008600 | 401569533 | Insulator | HFTD Tier 3 | Distribution | 2008-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008601 | 400693636 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008602 | 400394259 | High Sign | HFTD Tier 3 | Distribution | 2008-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008603 | 400438827 | Molding | HFTD Tier 2 | Distribution | 2008-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008604 | 400715257 | High Sign | HFTD Tier 3 | Distribution | 2008-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008605 | 400392756 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008606 | 400434220 | High Sign | HFTD Tier 3 | Distribution | 2008-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008607 | 400676708 | Molding | HFTD Tier 2 | Distribution | 2008-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008608 | 400682280 | High Sign | HFTD Tier 3 | Distribution | 2008-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008609 | 400729400 | High Sign | HFTD Tier 2 | Distribution | 2008-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008610 | 400401732 | High Sign | HFTD Tier 3 | Distribution | 2008-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008611 | 400695998 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008612 | 400737318 | Molding | HFTD Tier 2 | Distribution | 2008-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008613 | 400750079 | High Sign | HFTD Tier 2 | Distribution | 2008-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008614 | 400750856 | High Sign | HFTD Tier 2 | Distribution | 2008-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008615 | 400408403 | Molding | HFTD Tier 3 | Distribution | 2008-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008616 | 400426016 | High Sign | HFTD Tier 3 | Distribution | 2008-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008617 | 400722697 | High Sign | HFTD Tier 3 | Distribution | 2008-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008618 | 400428213 | Molding | HFTD Tier 3 | Distribution | 2008-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008619 | 400703862 | High Sign | HFTD Tier 2 | Distribution | 2008-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008620 | 400770563 | Insulator | HFTD Tier 2 | Distribution | 2008-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008621 | 400773734 | High Sign | HFTD Tier 2 | Distribution | 2008-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008622 | 400824003 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008623 | 400450322 | High Sign | HFTD Tier 2 | Distribution | 2008-02-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008624 | 400744263 | High Sign | HFTD Tier 2 | Distribution | 2008-02-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008625 | 400747320 | High Sign | HFTD Tier 2 | Distribution | 2008-02-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008626 | 400748541 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008627 | 400788679 | Molding | HFTD Tier 3 | Distribution | 2008-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008628 | 400482394 | High Sign | HFTD Tier 2 | Distribution | 2008-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008629 | 400494741 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008630 | 400896670 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008631 | 400495634 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008632 | 400797798 | Molding | HFTD Tier 3 | Distribution | 2008-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008633 | 400895771 | High Sign | HFTD Tier 2 | Distribution | 2008-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008634 | 400502714 | High Sign | HFTD Tier 3 | Distribution | 2008-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008635 | 400889900 | High Sign | HFTD Tier 3 | Distribution | 2008-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008636 | 400502903 | KV Cable Tags | HFTD Tier 3 | Distribution | 2008-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008637 | 400518536 | High Sign | HFTD Tier 3 | Distribution | 2008-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008638 | 400537700 | Lid/Frame | HFTD Tier 3 | Distribution | 2008-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008639 | 400582809 | High Sign | HFTD Tier 3 | Distribution | 2008-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008640 | 400823121 | KV Cable Tags | HFTD Tier 3 | Distribution | 2008-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008641 | 400858125 | High Sign | HFTD Tier 3 | Distribution | 2008-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008642 | 400859762 | High Sign | HFTD Tier 3 | Distribution | 2008-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008643 | 400890713 | KV Cable Tags | HFTD Tier 3 | Distribution | 2008-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008644 | 400892679 | KV Cable Tags | HFTD Tier 3 | Distribution | 2008-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008645 | 400892698 | KV Cable Tags | HFTD Tier 3 | Distribution | 2008-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008646 | 400894897 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008647 | 400844787 | Guy | HFTD Tier 3 | Distribution | 2008-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008648 | 400863722 | Molding | HFTD Tier 3 | Distribution | 2008-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008649 | 400571543 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2008-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008650 | 400582965 | High Sign | HFTD Tier 3 | Distribution | 2008-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008651 | 400847322 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2008-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008652 | 400916899 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008653 | 400523713 | High Sign | HFTD Tier 3 | Distribution | 2008-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008654 | 400639969 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008655 | 400895087 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008656 | 400911508 | Molding | HFTD Tier 3 | Distribution | 2008-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008657 | 400013835 | High Sign | HFTD Tier 3 | Distribution | 2008-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008658 | 400324866 | High Sign | HFTD Tier 2 | Distribution | 2008-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008659 | 400335574 | Molding | HFTD Tier 2 | Distribution | 2008-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008660 | 400339421 | Molding | HFTD Tier 2 | Distribution | 2008-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008661 | 400545433 | Molding | HFTD Tier 2 | Distribution | 2008-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008662 | 400581539 | Molding | HFTD Tier 2 | Distribution | 2008-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008663 | 400672299 | Molding | HFTD Tier 2 | Distribution | 2008-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008664 | 400426539 | High Sign | HFTD Tier 3 | Distribution | 2008-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008665 | 400012341 | High Sign | HFTD Tier 2 | Distribution | 2008-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008666 | 400294217 | KV Cable Tags | HFTD Tier 2 | Distribution | 2008-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008667 | 400305208 | Molding | HFTD Tier 3 | Distribution | 2008-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008668 | 400334673 | Ground | HFTD Tier 2 | Distribution | 2008-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008669 | 400715804 | High Sign | HFTD Tier 3 | Distribution | 2008-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008670 | 400010618 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008671 | 401581129 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008672 | 401581173 | Ground | HFTD Tier 3 | Distribution | 2008-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008673 | 400642049 | High Sign | HFTD Tier 2 | Distribution | 2008-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008674 | 400744864 | Molding | HFTD Tier 2 | Distribution | 2008-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008675 | 400322089 | Molding | HFTD Tier 2 | Distribution | 2008-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008676 | 400322114 | High Sign | HFTD Tier 2 | Distribution | 2008-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008677 | 400437487 | Molding | HFTD Tier 3 | Distribution | 2008-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008678 | 400613792 | High Sign | HFTD Tier 2 | Distribution | 2008-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008679 | 400710913 | High Sign | HFTD Tier 2 | Distribution | 2008-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008680 | 400437407 | Molding | HFTD Tier 2 | Distribution | 2008-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008681 | 400647101 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008682 | 401577890 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008683 | 401578875 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008684 | 401579827 | Ground | HFTD Tier 2 | Distribution | 2008-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008685 | 401581164 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008686 | 400358422 | Molding | HFTD Tier 3 | Distribution | 2008-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008687 | 400358572 | High Sign | HFTD Tier 3 | Distribution | 2008-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008688 | 400397949 | High Sign | HFTD Tier 2 | Distribution | 2008-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008689 | 400636406 | High Sign | HFTD Tier 2 | Distribution | 2008-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008690 | 401580915 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008691 | 400393243 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008692 | 400427957 | KV Cable Tags | HFTD Tier 3 | Distribution | 2008-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008693 | 400430418 | KV Cable Tags | HFTD Tier 3 | Distribution | 2008-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008694 | 400014133 | Molding | HFTD Tier 2 | Distribution | 2008-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008695 | 400390033 | Cable/Conductor | HFTD Tier 3 | Distribution | 2008-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008696 | 400441166 | KV Cable Tags | HFTD Tier 2 | Distribution | 2008-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008697 | 400394177 | Molding | HFTD Tier 3 | Distribution | 2008-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008698 | 400442907 | Termination | HFTD Tier 3 | Distribution | 2008-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008699 | 400451807 | Molding | HFTD Tier 2 | Distribution | 2008-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008700 | 400412397 | Molding | HFTD Tier 2 | Distribution | 2008-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008701 | 400702935 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008702 | 400793607 | High Sign | HFTD Tier 3 | Distribution | 2008-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008703 | 400795141 | High Sign | HFTD Tier 2 | Distribution | 2008-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008704 | 400291517 | High Sign | HFTD Tier 3 | Distribution | 2008-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008705 | 400455154 | Molding | HFTD Tier 3 | Distribution | 2008-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008706 | 400807529 | High Sign | HFTD Tier 3 | Distribution | 2008-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008707 | 400014234 | Molding | HFTD Tier 3 | Distribution | 2008-04-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008708 | 400014732 | Molding | HFTD Tier 3 | Distribution | 2008-04-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008709 | 400015358 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2008-04-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008710 | 400296162 | High Sign | HFTD Tier 3 | Distribution | 2008-04-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008711 | 400469593 | Cable/Conductor | HFTD Tier 3 | Distribution | 2008-04-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008712 | 400832131 | Molding | HFTD Tier 3 | Distribution | 2008-04-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008713 | 400306761 | Cable/Conductor | HFTD Tier 3 | Distribution | 2008-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008714 | 400313969 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008715 | 400487195 | Molding | HFTD Tier 3 | Distribution | 2008-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008716 | 400011787 | Bond | HFTD Tier 3 | Distribution | 2008-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008717 | 400329941 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008718 | 400447308 | Molding | HFTD Tier 3 | Distribution | 2008-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008719 | 400498067 | Molding | HFTD Tier 3 | Distribution | 2008-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008720 | 400501990 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008721 | 400862616 | Cable/Conductor | HFTD Tier 3 | Distribution | 2008-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008722 | 400334730 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008723 | 400462139 | Insulator | HFTD Tier 2 | Distribution | 2008-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008724 | 400462384 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008725 | 400502135 | High Sign | HFTD Tier 3 | Distribution | 2008-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008726 | 400505518 | High Sign | HFTD Tier 2 | Distribution | 2008-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008727 | 400348739 | Molding | HFTD Tier 3 | Distribution | 2008-04-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008728 | 400347056 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008729 | 400348811 | High Sign | HFTD Tier 3 | Distribution | 2008-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008730 | 400477100 | High Sign | HFTD Tier 2 | Distribution | 2008-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008731 | 400478794 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008732 | 400481188 | High Sign | HFTD Tier 3 | Distribution | 2008-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008733 | 400510827 | High Sign | HFTD Tier 3 | Distribution | 2008-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008734 | 400516963 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008735 | 400519481 | Molding | HFTD Tier 2 | Distribution | 2008-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008736 | 400886433 | High Sign | HFTD Tier 3 | Distribution | 2008-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008737 | 401582480 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008738 | 400013256 | Molding | HFTD Tier 2 | Distribution | 2008-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008739 | 400016252 | Crossarm | HFTD Tier 2 | Distribution | 2008-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008740 | 400360770 | High Sign | HFTD Tier 3 | Distribution | 2008-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008741 | 400379453 | Molding | HFTD Tier 2 | Distribution | 2008-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008742 | 400381622 | High Sign | HFTD Tier 2 | Distribution | 2008-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008743 | 400496813 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008744 | 400496927 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008745 | 400518572 | High Sign | HFTD Tier 3 | Distribution | 2008-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008746 | 400519515 | KV Cable Tags | HFTD Tier 2 | Distribution | 2008-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008747 | 400521327 | KV Cable Tags | HFTD Tier 2 | Distribution | 2008-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008748 | 400906499 | Crossarm | HFTD Tier 3 | Distribution | 2008-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008749 | 400497027 | Molding | HFTD Tier 2 | Distribution | 2008-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008750 | 400531184 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008751 | 400301166 | KV Cable Tags | HFTD Tier 2 | Distribution | 2008-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008752 | 400303463 | KV Cable Tags | HFTD Tier 3 | Distribution | 2008-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008753 | 400312622 | Guy | HFTD Tier 2 | Distribution | 2008-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008754 | 400549893 | KV Cable Tags | HFTD Tier 3 | Distribution | 2008-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008755 | 401585207 | Cable/Conductor | HFTD Tier 3 | Distribution | 2008-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008756 | 400009881 | Molding | HFTD Tier 2 | Distribution | 2008-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008757 | 400399978 | Molding | HFTD Tier 3 | Distribution | 2008-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008758 | 400011664 | High Sign | HFTD Tier 2 | Distribution | 2008-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008759 | 400011978 | High Sign | HFTD Tier 2 | Distribution | 2008-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008760 | 400017286 | Molding | HFTD Tier 2 | Distribution | 2008-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008761 | 400429072 | High Sign | HFTD Tier 3 | Distribution | 2008-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008762 | 400598900 | High Sign | HFTD Tier 3 | Distribution | 2008-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008763 | 400016859 | Molding | HFTD Tier 2 | Distribution | 2008-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008764 | 400336438 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2008-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008765 | 400365474 | Molding | HFTD Tier 3 | Distribution | 2008-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008766 | 400433326 | Cable/Conductor | HFTD Tier 3 | Distribution | 2008-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008767 | 400012108 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008768 | 400012688 | High Sign | HFTD Tier 3 | Distribution | 2008-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008769 | 400369547 | High Sign | HFTD Tier 3 | Distribution | 2008-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008770 | 400365798 | High Sign | HFTD Tier 3 | Distribution | 2008-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008771 | 400388889 | High Sign | HFTD Tier 3 | Distribution | 2008-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008772 | 400605608 | High Sign | HFTD Tier 3 | Distribution | 2008-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008773 | 400583386 | Molding | HFTD Tier 2 | Distribution | 2008-04-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008774 | 400014646 | Molding | HFTD Tier 2 | Distribution | 2008-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008775 | 400696679 | Vis Strips | HFTD Tier 3 | Distribution | 2008-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008776 | 401587874 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008777 | 400417728 | Molding | HFTD Tier 2 | Distribution | 2008-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008778 | 400501368 | Molding | HFTD Tier 2 | Distribution | 2008-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008779 | 401590999 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2008-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008780 | 400420163 | High Sign | HFTD Tier 3 | Distribution | 2008-04-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008781 | 400498090 | High Sign | HFTD Tier 3 | Distribution | 2008-04-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008782 | 400505817 | High Sign | HFTD Tier 3 | Distribution | 2008-04-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008783 | 400504582 | Molding | HFTD Tier 3 | Distribution | 2008-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008784 | 400014056 | High Sign | HFTD Tier 3 | Distribution | 2008-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008785 | 400440209 | Molding | HFTD Tier 3 | Distribution | 2008-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008786 | 400333494 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008787 | 400364599 | Molding | HFTD Tier 3 | Distribution | 2008-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008788 | 400477930 | Bond | HFTD Tier 3 | Distribution | 2008-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008789 | 400484791 | Molding | HFTD Tier 2 | Distribution | 2008-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008790 | 400692102 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008791 | 400493037 | High Sign | HFTD Tier 3 | Distribution | 2008-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008792 | 400512366 | High Sign | HFTD Tier 2 | Distribution | 2008-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008793 | 400622027 | High Sign | HFTD Tier 2 | Distribution | 2008-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008794 | 400688012 | High Sign | HFTD Tier 3 | Distribution | 2008-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008795 | 400014273 | Molding | HFTD Tier 3 | Distribution | 2008-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008796 | 400307491 | High Sign | HFTD Tier 3 | Distribution | 2008-05-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008797 | 400322467 | High Sign | HFTD Tier 2 | Distribution | 2008-05-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008798 | 400385175 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2008-05-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008799 | 400509915 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2008-05-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008800 | 400579946 | High Sign | HFTD Tier 3 | Distribution | 2008-05-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008801 | 400318630 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008802 | 400443953 | Molding | HFTD Tier 2 | Distribution | 2008-05-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008803 | 400021703 | High Sign | HFTD Tier 2 | Distribution | 2008-05-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008804 | 400025357 | High Sign | HFTD Tier 2 | Distribution | 2008-05-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008805 | 400436851 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-05-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008806 | 400546034 | High Sign | HFTD Tier 3 | Distribution | 2008-05-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008807 | 400391837 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2008-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008808 | 400577307 | High Sign | HFTD Tier 3 | Distribution | 2008-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008809 | 400015087 | High Sign | HFTD Tier 2 | Distribution | 2008-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008810 | 400524001 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2008-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008811 | 400667312 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008812 | 400019014 | Molding | HFTD Tier 2 | Distribution | 2008-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008813 | 401006440 | Molding | HFTD Tier 3 | Distribution | 2008-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008814 | 400517963 | Molding | HFTD Tier 2 | Distribution | 2008-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008815 | 400519482 | Riser/Conduit | HFTD Tier 3 | Distribution | 2008-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008816 | 400465090 | High Sign | HFTD Tier 2 | Distribution | 2008-05-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008817 | 401006678 | Molding | HFTD Tier 3 | Distribution | 2008-05-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008818 | 400188779 | High Sign | HFTD Tier 3 | Distribution | 2008-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008819 | 400476822 | High Sign | HFTD Tier 3 | Distribution | 2008-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008820 | 400190820 | High Sign | HFTD Tier 3 | Distribution | 2008-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008821 | 400214090 | Molding | HFTD Tier 2 | Distribution | 2008-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008822 | 400211545 | High Sign | HFTD Tier 3 | Distribution | 2008-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008823 | 400214002 | High Sign | HFTD Tier 3 | Distribution | 2008-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008824 | 400515207 | Molding | HFTD Tier 3 | Distribution | 2008-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008825 | 400517995 | High Sign | HFTD Tier 3 | Distribution | 2008-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008826 | 400019968 | Molding | HFTD Tier 2 | Distribution | 2008-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008827 | 400032813 | Ground | HFTD Tier 2 | Distribution | 2008-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008828 | 400520604 | High Sign | HFTD Tier 2 | Distribution | 2008-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008829 | 400518388 | Vis Strips | HFTD Tier 2 | Distribution | 2008-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008830 | 400021552 | Molding | HFTD Tier 2 | Distribution | 2008-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008831 | 400700852 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008832 | 400331794 | Molding | HFTD Tier 3 | Distribution | 2008-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008833 | 400591578 | Molding | HFTD Tier 2 | Distribution | 2008-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008834 | 400302513 | Guy | HFTD Tier 3 | Distribution | 2008-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008835 | 400056430 | Molding | HFTD Tier 2 | Distribution | 2008-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008836 | 400333818 | Molding | HFTD Tier 3 | Distribution | 2008-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008837 | 400424414 | Molding | HFTD Tier 3 | Distribution | 2008-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008838 | 400599092 | High Sign | HFTD Tier 3 | Distribution | 2008-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008839 | 400357750 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-06-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008840 | 400444216 | High Sign | HFTD Tier 3 | Distribution | 2008-06-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008841 | 400080677 | High Sign | HFTD Tier 2 | Distribution | 2008-06-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008842 | 400089324 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008843 | 400359915 | High Sign | HFTD Tier 3 | Distribution | 2008-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008844 | 400450607 | High Sign | HFTD Tier 3 | Distribution | 2008-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008845 | 400453680 | High Sign | HFTD Tier 3 | Distribution | 2008-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008846 | 400454651 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008847 | 400098640 | Molding | HFTD Tier 3 | Distribution | 2008-07-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008848 | 400103830 | Molding | HFTD Tier 3 | Distribution | 2008-07-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008849 | 400459065 | High Sign | HFTD Tier 3 | Distribution | 2008-07-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008850 | 400632251 | High Sign | HFTD Tier 2 | Distribution | 2008-07-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008851 | 400643255 | High Sign | HFTD Tier 3 | Distribution | 2008-07-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008852 | 400470635 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-07-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008853 | 400470658 | High Sign | HFTD Tier 3 | Distribution | 2008-07-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008854 | 400653706 | Molding | HFTD Tier 2 | Distribution | 2008-07-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008855 | 400662189 | Molding | HFTD Tier 3 | Distribution | 2008-07-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008856 | 400107256 | Cable/Conductor | HFTD Tier 3 | Distribution | 2008-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008857 | 400021980 | Bond | HFTD Tier 3 | Distribution | 2008-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008858 | 400321837 | High Sign | HFTD Tier 2 | Distribution | 2008-07-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008859 | 400454428 | Guy | HFTD Tier 2 | Distribution | 2008-07-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008860 | 400507428 | Molding | HFTD Tier 2 | Distribution | 2008-07-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008861 | 400517536 | High Sign | HFTD Tier 3 | Distribution | 2008-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008862 | 400711500 | Ground | HFTD Tier 3 | Distribution | 2008-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008863 | 400237964 | Molding | HFTD Tier 3 | Distribution | 2008-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008864 | 400239995 | Molding | HFTD Tier 3 | Distribution | 2008-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008865 | 400329768 | High Sign | HFTD Tier 3 | Distribution | 2008-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008866 | 400517067 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008867 | 400146392 | Cable/Conductor | HFTD Tier 3 | Distribution | 2008-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008868 | 400035497 | Molding | HFTD Tier 2 | Distribution | 2008-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008869 | 400174780 | High Sign | HFTD Tier 2 | Distribution | 2008-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008870 | 400522597 | Molding | HFTD Tier 3 | Distribution | 2008-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008871 | 400535000 | High Sign | HFTD Tier 2 | Distribution | 2008-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008872 | 400187434 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2008-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008873 | 400019789 | Molding | HFTD Tier 3 | Distribution | 2008-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008874 | 400025102 | Molding | HFTD Tier 2 | Distribution | 2008-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008875 | 400178643 | Molding | HFTD Tier 2 | Distribution | 2008-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008876 | 400182724 | Molding | HFTD Tier 2 | Distribution | 2008-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008877 | 400194467 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008878 | 400023413 | Molding | HFTD Tier 3 | Distribution | 2008-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008879 | 400029942 | Molding | HFTD Tier 3 | Distribution | 2008-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008880 | 400034137 | Molding | HFTD Tier 3 | Distribution | 2008-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008881 | 400325386 | High Sign | HFTD Tier 2 | Distribution | 2008-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008882 | 400044552 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008883 | 400618024 | High Sign | HFTD Tier 3 | Distribution | 2008-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008884 | 400098306 | Molding | HFTD Tier 3 | Distribution | 2008-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008885 | 400224053 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008886 | 400618962 | Molding | HFTD Tier 2 | Distribution | 2008-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008887 | 400174129 | Guy | HFTD Tier 3 | Distribution | 2008-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008888 | 400058141 | Molding | HFTD Tier 2 | Distribution | 2008-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008889 | 400113934 | Riser/Conduit | HFTD Tier 3 | Distribution | 2008-07-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008890 | 400208776 | High Sign | HFTD Tier 3 | Distribution | 2008-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008891 | 400252430 | High Sign | HFTD Tier 3 | Distribution | 2008-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008892 | 400270635 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-08-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008893 | 400184656 | High Sign | HFTD Tier 3 | Distribution | 2008-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008894 | 400685570 | High Sign | HFTD Tier 3 | Distribution | 2008-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008895 | 400712946 | High Sign | HFTD Tier 2 | Distribution | 2008-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008896 | 400059502 | Molding | HFTD Tier 3 | Distribution | 2008-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008897 | 400067367 | High Sign | HFTD Tier 2 | Distribution | 2008-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008898 | 400204490 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2008-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008899 | 400248398 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008900 | 400258219 | Molding | HFTD Tier 3 | Distribution | 2008-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008901 | 400361766 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2008-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008902 | 400367379 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008903 | 400275920 | Molding | HFTD Tier 3 | Distribution | 2008-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008904 | 400246927 | High Sign | HFTD Tier 3 | Distribution | 2008-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008905 | 400253530 | Cable/Conductor | HFTD Tier 3 | Distribution | 2008-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008906 | 400296389 | Riser/Conduit | HFTD Tier 3 | Distribution | 2008-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008907 | 400251615 | High Sign | HFTD Tier 3 | Distribution | 2008-08-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008908 | 400307612 | High Sign | HFTD Tier 3 | Distribution | 2008-08-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008909 | 400189900 | Molding | HFTD Tier 3 | Distribution | 2008-08-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008910 | 400268666 | High Sign | HFTD Tier 3 | Distribution | 2008-08-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008911 | 400421286 | High Sign | HFTD Tier 3 | Distribution | 2008-08-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008912 | 400188682 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2008-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008913 | 400206739 | Crossarm | HFTD Tier 3 | Distribution | 2008-09-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008914 | 400325578 | High Sign | HFTD Tier 3 | Distribution | 2008-09-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008915 | 400200235 | High Sign | HFTD Tier 2 | Distribution | 2008-09-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008916 | 400282441 | High Sign | HFTD Tier 2 | Distribution | 2008-09-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008917 | 400286188 | High Sign | HFTD Tier 2 | Distribution | 2008-09-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008918 | 400321046 | Ground | HFTD Tier 2 | Distribution | 2008-09-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008919 | 400358949 | High Sign | HFTD Tier 2 | Distribution | 2008-09-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008920 | 400247133 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008921 | 400417580 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008922 | 400329861 | High Sign | HFTD Tier 3 | Distribution | 2008-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008923 | 400102856 | Molding | HFTD Tier 2 | Distribution | 2008-10-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008924 | 400445946 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2008-10-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008925 | 400139369 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008926 | 400398148 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008927 | 400159387 | High Sign | HFTD Tier 2 | Distribution | 2008-10-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008928 | 400487947 | Molding | HFTD Tier 2 | Distribution | 2008-10-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008929 | 400151962 | Molding | HFTD Tier 2 | Distribution | 2008-10-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008930 | 400034860 | High Sign | HFTD Tier 3 | Distribution | 2008-10-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008931 | 400197491 | High Sign | HFTD Tier 3 | Distribution | 2008-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008932 | 400192477 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-10-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008933 | 400205301 | High Sign | HFTD Tier 3 | Distribution | 2008-10-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008934 | 400127961 | Molding | HFTD Tier 3 | Distribution | 2008-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008935 | 400163114 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-10-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008936 | 400242428 | Molding | HFTD Tier 3 | Distribution | 2008-10-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008937 | 400048054 | High Sign | HFTD Tier 2 | Distribution | 2008-11-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008938 | 400051154 | Molding | HFTD Tier 2 | Distribution | 2008-11-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008939 | 400053576 | High Sign | HFTD Tier 2 | Distribution | 2008-11-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008940 | 400125854 | Molding | HFTD Tier 3 | Distribution | 2008-11-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008941 | 400188489 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-11-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008942 | 400190897 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2008-11-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008943 | 400271948 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-11-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008944 | 400276716 | Molding | HFTD Tier 3 | Distribution | 2008-11-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008945 | 400276731 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-11-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008946 | 401628718 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2008-11-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008947 | 400149823 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-11-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008948 | 400301061 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2008-11-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008949 | 400218364 | Molding | HFTD Tier 3 | Distribution | 2008-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008950 | 400314637 | Molding | HFTD Tier 3 | Distribution | 2008-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008951 | 400316801 | High Sign | HFTD Tier 3 | Distribution | 2008-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008952 | 400320273 | Molding | HFTD Tier 3 | Distribution | 2008-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008953 | 400219801 | Riser/Conduit | HFTD Tier 3 | Distribution | 2008-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008954 | 400106549 | Molding | HFTD Tier 2 | Distribution | 2008-11-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008955 | 400109682 | Molding | HFTD Tier 3 | Distribution | 2008-11-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008956 | 400175575 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2008-11-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008957 | 400238027 | Molding | HFTD Tier 3 | Distribution | 2008-11-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008958 | 400243179 | High Sign | HFTD Tier 2 | Distribution | 2008-11-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008959 | 400338086 | High Sign | HFTD Tier 3 | Distribution | 2008-11-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008960 | 400122715 | Guy | HFTD Tier 3 | Distribution | 2008-11-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008961 | 400178193 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-11-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008962 | 400180390 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2008-11-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008963 | 400205021 | High Sign | HFTD Tier 3 | Distribution | 2008-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008964 | 400264049 | Guy | HFTD Tier 3 | Distribution | 2008-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008965 | 400145961 | Molding | HFTD Tier 3 | Distribution | 2008-11-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008966 | 400269603 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2008-11-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008967 | 400386181 | Cable/Conductor | HFTD Tier 3 | Distribution | 2008-11-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008968 | 400157701 | Molding | HFTD Tier 3 | Distribution | 2008-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008969 | 400160274 | High Sign | HFTD Tier 3 | Distribution | 2008-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008970 | 400203561 | Molding | HFTD Tier 3 | Distribution | 2008-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008971 | 400283495 | High Sign | HFTD Tier 3 | Distribution | 2008-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008972 | 400395631 | High Sign | HFTD Tier 2 | Distribution | 2008-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008973 | 400220772 | Molding | HFTD Tier 3 | Distribution | 2008-11-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008974 | 400222870 | Molding | HFTD Tier 3 | Distribution | 2008-11-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008975 | 400289758 | Molding | HFTD Tier 3 | Distribution | 2008-11-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008976 | 400392890 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-11-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008977 | 400067636 | Molding | HFTD Tier 3 | Distribution | 2008-11-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008978 | 400222064 | Molding | HFTD Tier 3 | Distribution | 2008-11-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008979 | 400231318 | High Sign | HFTD Tier 3 | Distribution | 2008-11-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008980 | 400397358 | Molding | HFTD Tier 3 | Distribution | 2008-11-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008981 | 400173360 | Guy | HFTD Tier 3 | Distribution | 2008-11-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008982 | 400238357 | Molding | HFTD Tier 3 | Distribution | 2008-12-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008983 | 400319515 | Molding | HFTD Tier 2 | Distribution | 2008-12-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008984 | 400415627 | Riser/Conduit | HFTD Tier 3 | Distribution | 2008-12-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008985 | 400246609 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-12-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008986 | 400211247 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2008-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008987 | 400253124 | High Sign | HFTD Tier 3 | Distribution | 2008-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008988 | 400432849 | Molding | HFTD Tier 3 | Distribution | 2008-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008989 | 400440522 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008990 | 401638651 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008991 | 400211411 | Cable/Conductor | HFTD Tier 3 | Distribution | 2008-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008992 | 400335560 | High Sign | HFTD Tier 3 | Distribution | 2008-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008993 | 400447809 | High Sign | HFTD Tier 3 | Distribution | 2008-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008994 | 400225472 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2008-12-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008995 | 400241108 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2008-12-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008996 | 400292100 | Molding | HFTD Tier 3 | Distribution | 2008-12-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008997 | 400367343 | Molding | HFTD Tier 3 | Distribution | 2008-12-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008998 | 400464336 | Molding | HFTD Tier 3 | Distribution | 2008-12-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120008999 | 400055440 | Molding | HFTD Tier 3 | Distribution | 2008-12-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009000 | 400067209 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-12-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009001 | 400287913 | Molding | HFTD Tier 2 | Distribution | 2008-12-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009002 | 400375181 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2008-12-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009003 | 400086811 | High Sign | HFTD Tier 2 | Distribution | 2008-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009004 | 400250838 | Molding | HFTD Tier 3 | Distribution | 2008-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009005 | 400488896 | High Sign | HFTD Tier 3 | Distribution | 2008-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009006 | 401638977 | Cable/Conductor | HFTD Tier 3 | Distribution | 2008-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009007 | 400037782 | Guy | HFTD Tier 3 | Distribution | 2008-12-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009008 | 400252464 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-12-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009009 | 400308743 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2008-12-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009010 | 400036786 | Termination | HFTD Tier 3 | Distribution | 2008-12-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009011 | 400268129 | Molding | HFTD Tier 3 | Distribution | 2008-12-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009012 | 400319517 | Molding | HFTD Tier 3 | Distribution | 2008-12-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009013 | 400331352 | High Sign | HFTD Tier 3 | Distribution | 2008-12-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009014 | 400401535 | High Sign | HFTD Tier 3 | Distribution | 2008-12-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009015 | 401638155 | Cable/Conductor | HFTD Tier 2 | Distribution | 2008-12-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009016 | 400289367 | Molding | HFTD Tier 3 | Distribution | 2008-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009017 | 400358537 | High Sign | HFTD Tier 3 | Distribution | 2008-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009018 | 400309296 | High Sign | HFTD Tier 2 | Distribution | 2008-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009019 | 400373510 | Hardware/Framing | HFTD Tier 2 | Distribution | 2008-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009020 | 400098053 | High Sign | HFTD Tier 2 | Distribution | 2008-12-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009021 | 400096283 | Molding | HFTD Tier 3 | Distribution | 2008-12-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009022 | 400463933 | Cable/Conductor | HFTD Tier 3 | Distribution | 2008-12-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009023 | 400093212 | High Sign | HFTD Tier 2 | Distribution | 2008-12-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009024 | 400111330 | High Sign | HFTD Tier 2 | Distribution | 2008-12-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009025 | 400346057 | Molding | HFTD Tier 3 | Distribution | 2008-12-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009026 | 400482845 | Hardware/Framing | HFTD Tier 3 | Distribution | 2008-12-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009027 | 400416485 | Molding | HFTD Tier 2 | Distribution | 2009-01-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009028 | 400035178 | High Sign | HFTD Tier 3 | Distribution | 2009-01-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009029 | 400120909 | Molding | HFTD Tier 2 | Distribution | 2009-01-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009030 | 400352852 | High Sign | HFTD Tier 3 | Distribution | 2009-01-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009031 | 400353019 | Hardware/Framing | HFTD Tier 2 | Distribution | 2009-01-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009032 | 400492830 | Molding | HFTD Tier 3 | Distribution | 2009-01-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009033 | 400040141 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009034 | 400045292 | High Sign | HFTD Tier 3 | Distribution | 2009-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009035 | 400130082 | Hardware/Framing | HFTD Tier 2 | Distribution | 2009-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009036 | 400427345 | High Sign | HFTD Tier 3 | Distribution | 2009-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009037 | 400429510 | High Sign | HFTD Tier 3 | Distribution | 2009-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009038 | 400432478 | Molding | HFTD Tier 3 | Distribution | 2009-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009039 | 400373465 | Molding | HFTD Tier 2 | Distribution | 2009-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009040 | 400468096 | Riser/Conduit | HFTD Tier 2 | Distribution | 2009-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009041 | 400098859 | Molding | HFTD Tier 2 | Distribution | 2009-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009042 | 400161543 | Molding | HFTD Tier 3 | Distribution | 2009-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009043 | 400472098 | Molding | HFTD Tier 3 | Distribution | 2009-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009044 | 400080773 | High Sign | HFTD Tier 2 | Distribution | 2009-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009045 | 400165720 | High Sign | HFTD Tier 3 | Distribution | 2009-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009046 | 400472121 | Molding | HFTD Tier 2 | Distribution | 2009-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009047 | 400033731 | Hardware/Framing | HFTD Tier 2 | Distribution | 2009-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009048 | 400034367 | Hardware/Framing | HFTD Tier 2 | Distribution | 2009-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009049 | 400038528 | Guy | HFTD Tier 2 | Distribution | 2009-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009050 | 400067941 | Molding | HFTD Tier 2 | Distribution | 2009-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009051 | 400099421 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009052 | 400099475 | Molding | HFTD Tier 3 | Distribution | 2009-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009053 | 400172245 | High Sign | HFTD Tier 3 | Distribution | 2009-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009054 | 400436014 | High Sign | HFTD Tier 3 | Distribution | 2009-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009055 | 400489655 | High Sign | HFTD Tier 3 | Distribution | 2009-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009056 | 400045671 | Riser/Conduit | HFTD Tier 2 | Distribution | 2009-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009057 | 400127572 | Hardware/Framing | HFTD Tier 2 | Distribution | 2009-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009058 | 400183121 | High Sign | HFTD Tier 3 | Distribution | 2009-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009059 | 400200586 | Molding | HFTD Tier 2 | Distribution | 2009-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009060 | 400444324 | Molding | HFTD Tier 3 | Distribution | 2009-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009061 | 400449016 | Molding | HFTD Tier 2 | Distribution | 2009-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009062 | 400104157 | Guy | HFTD Tier 2 | Distribution | 2009-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009063 | 400041106 | High Sign | HFTD Tier 2 | Distribution | 2009-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009064 | 400211081 | Molding | HFTD Tier 2 | Distribution | 2009-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009065 | 400074197 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009066 | 400101750 | High Sign | HFTD Tier 2 | Distribution | 2009-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009067 | 400061915 | High Sign | HFTD Tier 2 | Distribution | 2009-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009068 | 400067368 | High Sign | HFTD Tier 2 | Distribution | 2009-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009069 | 400099817 | Molding | HFTD Tier 2 | Distribution | 2009-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009070 | 400139494 | Hardware/Framing | HFTD Tier 2 | Distribution | 2009-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009071 | 400140843 | Molding | HFTD Tier 2 | Distribution | 2009-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009072 | 400229875 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009073 | 400081101 | High Sign | HFTD Tier 3 | Distribution | 2009-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009074 | 400081418 | High Sign | HFTD Tier 2 | Distribution | 2009-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009075 | 400105314 | High Sign | HFTD Tier 3 | Distribution | 2009-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009076 | 400166027 | High Sign | HFTD Tier 2 | Distribution | 2009-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009077 | 400046635 | Molding | HFTD Tier 3 | Distribution | 2009-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009078 | 400047761 | High Sign | HFTD Tier 2 | Distribution | 2009-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009079 | 400085706 | Guy | HFTD Tier 2 | Distribution | 2009-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009080 | 400086698 | Ground | HFTD Tier 3 | Distribution | 2009-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009081 | 400107491 | High Sign | HFTD Tier 3 | Distribution | 2009-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009082 | 400164715 | High Sign | HFTD Tier 3 | Distribution | 2009-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009083 | 400168206 | High Sign | HFTD Tier 2 | Distribution | 2009-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009084 | 400070876 | Molding | HFTD Tier 2 | Distribution | 2009-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009085 | 400104091 | High Sign | HFTD Tier 2 | Distribution | 2009-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009086 | 400168583 | Pole Tag | HFTD Tier 2 | Distribution | 2009-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009087 | 400262389 | High Sign | HFTD Tier 3 | Distribution | 2009-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009088 | 400131519 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-01-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009089 | 400278851 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-01-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009090 | 400079557 | Guy | HFTD Tier 2 | Distribution | 2009-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009091 | 400109239 | Guy | HFTD Tier 2 | Distribution | 2009-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009092 | 400195948 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2009-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009093 | 400217354 | Riser/Conduit | HFTD Tier 3 | Distribution | 2009-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009094 | 400303917 | High Sign | HFTD Tier 3 | Distribution | 2009-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009095 | 400140217 | Riser/Conduit | HFTD Tier 3 | Distribution | 2009-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009096 | 400212728 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009097 | 400304082 | High Sign | HFTD Tier 3 | Distribution | 2009-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009098 | 400211576 | Molding | HFTD Tier 3 | Distribution | 2009-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009099 | 400296573 | Molding | HFTD Tier 3 | Distribution | 2009-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009100 | 400312231 | Molding | HFTD Tier 3 | Distribution | 2009-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009101 | 400174608 | Molding | HFTD Tier 3 | Distribution | 2009-02-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009102 | 400353029 | Molding | HFTD Tier 3 | Distribution | 2009-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009103 | 400264703 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009104 | 400346919 | Guy | HFTD Tier 2 | Distribution | 2009-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009105 | 400215850 | Guy | HFTD Tier 3 | Distribution | 2009-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009106 | 400352783 | Molding | HFTD Tier 3 | Distribution | 2009-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009107 | 400369921 | Riser/Conduit | HFTD Tier 2 | Distribution | 2009-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009108 | 403048937 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2009-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009109 | 400265516 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-02-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009110 | 400341227 | High Sign | HFTD Tier 3 | Distribution | 2009-02-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009111 | 400387306 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009112 | 400359966 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-02-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009113 | 400409943 | High Sign | HFTD Tier 2 | Distribution | 2009-02-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009114 | 400284350 | Molding | HFTD Tier 2 | Distribution | 2009-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009115 | 400452917 | Molding | HFTD Tier 2 | Distribution | 2009-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009116 | 400433708 | Molding | HFTD Tier 3 | Distribution | 2009-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009117 | 400468242 | High Sign | HFTD Tier 3 | Distribution | 2009-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009118 | 400306084 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009119 | 400310769 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009120 | 400391529 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009121 | 400398991 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009122 | 400392640 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-02-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009123 | 400460574 | Molding | HFTD Tier 3 | Distribution | 2009-02-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009124 | 400483824 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-02-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009125 | 400491241 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-02-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009126 | 400037022 | Molding | HFTD Tier 2 | Distribution | 2009-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009127 | 400054606 | Molding | HFTD Tier 2 | Distribution | 2009-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009128 | 400058289 | Molding | HFTD Tier 3 | Distribution | 2009-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009129 | 400349692 | High Sign | HFTD Tier 3 | Distribution | 2009-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009130 | 400479590 | Guy | HFTD Tier 2 | Distribution | 2009-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009131 | 400456683 | Molding | HFTD Tier 3 | Distribution | 2009-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009132 | 400479016 | Molding | HFTD Tier 2 | Distribution | 2009-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009133 | 400497373 | Molding | HFTD Tier 2 | Distribution | 2009-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009134 | 400505555 | Crossarm | HFTD Tier 2 | Distribution | 2009-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009135 | 400507901 | Hardware/Framing | HFTD Tier 2 | Distribution | 2009-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009136 | 400510494 | Molding | HFTD Tier 3 | Distribution | 2009-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009137 | 400105203 | Molding | HFTD Tier 2 | Distribution | 2009-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009138 | 400095880 | High Sign | HFTD Tier 2 | Distribution | 2009-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009139 | 400314907 | High Sign | HFTD Tier 2 | Distribution | 2009-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009140 | 400329114 | High Sign | HFTD Tier 2 | Distribution | 2009-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009141 | 400467214 | Molding | HFTD Tier 2 | Distribution | 2009-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009142 | 400483470 | High Sign | HFTD Tier 2 | Distribution | 2009-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009143 | 400484531 | Molding | HFTD Tier 2 | Distribution | 2009-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009144 | 400036662 | High Sign | HFTD Tier 3 | Distribution | 2009-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009145 | 400094087 | Insulator | HFTD Tier 2 | Distribution | 2009-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009146 | 400097670 | High Sign | HFTD Tier 3 | Distribution | 2009-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009147 | 400109986 | Molding | HFTD Tier 3 | Distribution | 2009-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009148 | 400110017 | High Sign | HFTD Tier 3 | Distribution | 2009-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009149 | 400492610 | High Sign | HFTD Tier 3 | Distribution | 2009-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009150 | 403883743 | Molding | HFTD Tier 3 | Distribution | 2009-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009151 | 400115088 | High Sign | HFTD Tier 3 | Distribution | 2009-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009152 | 400496625 | Molding | HFTD Tier 3 | Distribution | 2009-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009153 | 400131260 | Molding | HFTD Tier 3 | Distribution | 2009-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009154 | 400082065 | Molding | HFTD Tier 2 | Distribution | 2009-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009155 | 400117232 | Guy | HFTD Tier 3 | Distribution | 2009-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009156 | 400301876 | Hardware/Framing | HFTD Tier 2 | Distribution | 2009-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009157 | 400112176 | Molding | HFTD Tier 2 | Distribution | 2009-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009158 | 400117308 | High Sign | HFTD Tier 3 | Distribution | 2009-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009159 | 400396156 | High Sign | HFTD Tier 3 | Distribution | 2009-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009160 | 400127536 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009161 | 400128231 | High Sign | HFTD Tier 2 | Distribution | 2009-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009162 | 400110457 | High Sign | HFTD Tier 3 | Distribution | 2009-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009163 | 400117870 | High Sign | HFTD Tier 3 | Distribution | 2009-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009164 | 400127608 | High Sign | HFTD Tier 3 | Distribution | 2009-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009165 | 400132707 | High Sign | HFTD Tier 3 | Distribution | 2009-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009166 | 400178533 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009167 | 400374383 | Molding | HFTD Tier 3 | Distribution | 2009-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009168 | 400472720 | Molding | HFTD Tier 3 | Distribution | 2009-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009169 | 400202009 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009170 | 401657953 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2009-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009171 | 400421963 | Guy | HFTD Tier 3 | Distribution | 2009-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009172 | 400262338 | High Sign | HFTD Tier 3 | Distribution | 2009-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009173 | 400390923 | High Sign | HFTD Tier 3 | Distribution | 2009-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009174 | 400392438 | High Sign | HFTD Tier 3 | Distribution | 2009-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009175 | 400468188 | High Sign | HFTD Tier 3 | Distribution | 2009-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009176 | 400470669 | Molding | HFTD Tier 3 | Distribution | 2009-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009177 | 400252378 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-04-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009178 | 400266942 | Molding | HFTD Tier 2 | Distribution | 2009-04-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009179 | 400276552 | Molding | HFTD Tier 2 | Distribution | 2009-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009180 | 400405986 | High Sign | HFTD Tier 3 | Distribution | 2009-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009181 | 400431019 | High Sign | HFTD Tier 2 | Distribution | 2009-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009182 | 400492513 | High Sign | HFTD Tier 3 | Distribution | 2009-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009183 | 400498358 | Molding | HFTD Tier 3 | Distribution | 2009-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009184 | 400512933 | High Sign | HFTD Tier 2 | Distribution | 2009-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009185 | 400122082 | Molding | HFTD Tier 2 | Distribution | 2009-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009186 | 400486392 | Insulator | HFTD Tier 2 | Distribution | 2009-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009187 | 400527519 | High Sign | HFTD Tier 2 | Distribution | 2009-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009188 | 400391260 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009189 | 400100168 | High Sign | HFTD Tier 2 | Distribution | 2009-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009190 | 401665718 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2009-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009191 | 400424363 | Molding | HFTD Tier 3 | Distribution | 2009-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009192 | 400575069 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2009-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009193 | 400032601 | High Sign | HFTD Tier 3 | Distribution | 2009-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009194 | 400136197 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009195 | 400027534 | Molding | HFTD Tier 3 | Distribution | 2009-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009196 | 400575304 | High Sign | HFTD Tier 3 | Distribution | 2009-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009197 | 400030781 | High Sign | HFTD Tier 2 | Distribution | 2009-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009198 | 400036803 | Molding | HFTD Tier 3 | Distribution | 2009-04-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009199 | 400244471 | Molding | HFTD Tier 3 | Distribution | 2009-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009200 | 400253843 | Molding | HFTD Tier 3 | Distribution | 2009-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009201 | 400123385 | High Sign | HFTD Tier 2 | Distribution | 2009-04-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009202 | 400125087 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-04-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009203 | 400127538 | High Sign | HFTD Tier 2 | Distribution | 2009-04-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009204 | 400130313 | High Sign | HFTD Tier 2 | Distribution | 2009-04-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009205 | 400144767 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-04-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009206 | 400146775 | High Sign | HFTD Tier 2 | Distribution | 2009-04-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009207 | 400130018 | Molding | HFTD Tier 3 | Distribution | 2009-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009208 | 400279542 | High Sign | HFTD Tier 2 | Distribution | 2009-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009209 | 400124597 | Guy | HFTD Tier 2 | Distribution | 2009-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009210 | 400127896 | High Sign | HFTD Tier 2 | Distribution | 2009-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009211 | 400135046 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009212 | 400136158 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009213 | 403883718 | Molding | HFTD Tier 3 | Distribution | 2009-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009214 | 400189235 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009215 | 400286730 | Molding | HFTD Tier 2 | Distribution | 2009-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009216 | 400373064 | High Sign | HFTD Tier 2 | Distribution | 2009-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009217 | 401676039 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-05-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009218 | 400346331 | Molding | HFTD Tier 2 | Distribution | 2009-05-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009219 | 400351158 | High Sign | HFTD Tier 2 | Distribution | 2009-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009220 | 400281370 | Molding | HFTD Tier 3 | Distribution | 2009-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009221 | 400286036 | Molding | HFTD Tier 3 | Distribution | 2009-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009222 | 400373588 | High Sign | HFTD Tier 3 | Distribution | 2009-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009223 | 400376349 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009224 | 400138194 | High Sign | HFTD Tier 2 | Distribution | 2009-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009225 | 400410476 | Molding | HFTD Tier 2 | Distribution | 2009-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009226 | 400056319 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009227 | 400348018 | Hardware/Framing | HFTD Tier 2 | Distribution | 2009-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009228 | 400355052 | High Sign | HFTD Tier 2 | Distribution | 2009-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009229 | 400371393 | High Sign | HFTD Tier 3 | Distribution | 2009-05-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009230 | 400463926 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2009-05-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009231 | 400393881 | Molding | HFTD Tier 2 | Distribution | 2009-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009232 | 400398186 | Molding | HFTD Tier 2 | Distribution | 2009-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009233 | 400466033 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2009-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009234 | 403046480 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2009-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009235 | 400096713 | High Sign | HFTD Tier 3 | Distribution | 2009-05-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009236 | 400481648 | High Sign | HFTD Tier 3 | Distribution | 2009-05-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009237 | 400486968 | High Sign | HFTD Tier 3 | Distribution | 2009-05-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009238 | 400495230 | Guy | HFTD Tier 3 | Distribution | 2009-05-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009239 | 400425335 | High Sign | HFTD Tier 3 | Distribution | 2009-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009240 | 401681932 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2009-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009241 | 400432982 | High Sign | HFTD Tier 3 | Distribution | 2009-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009242 | 400045326 | High Sign | HFTD Tier 3 | Distribution | 2009-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009243 | 400443143 | Molding | HFTD Tier 3 | Distribution | 2009-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009244 | 400069143 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009245 | 400164273 | Molding | HFTD Tier 3 | Distribution | 2009-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009246 | 400465534 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009247 | 400037819 | Molding | HFTD Tier 3 | Distribution | 2009-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009248 | 400061215 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009249 | 400124377 | High Sign | HFTD Tier 3 | Distribution | 2009-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009250 | 400494390 | High Sign | HFTD Tier 2 | Distribution | 2009-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009251 | 401006673 | High Sign | HFTD Tier 3 | Distribution | 2009-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009252 | 400055533 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2009-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009253 | 400161342 | Hardware/Framing | HFTD Tier 2 | Distribution | 2009-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009254 | 400223735 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009255 | 400224721 | High Sign | HFTD Tier 3 | Distribution | 2009-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009256 | 401690344 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2009-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009257 | 400096165 | Molding | HFTD Tier 2 | Distribution | 2009-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009258 | 401686290 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2009-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009259 | 400104602 | Molding | HFTD Tier 2 | Distribution | 2009-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009260 | 400117696 | High Sign | HFTD Tier 2 | Distribution | 2009-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009261 | 400198212 | High Sign | HFTD Tier 2 | Distribution | 2009-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009262 | 400267378 | High Sign | HFTD Tier 3 | Distribution | 2009-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009263 | 400283270 | High Sign | HFTD Tier 2 | Distribution | 2009-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009264 | 400191307 | Hardware/Framing | HFTD Tier 2 | Distribution | 2009-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009265 | 400284011 | Molding | HFTD Tier 2 | Distribution | 2009-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009266 | 400132995 | Molding | HFTD Tier 2 | Distribution | 2009-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009267 | 400207920 | Molding | HFTD Tier 2 | Distribution | 2009-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009268 | 400208809 | Molding | HFTD Tier 3 | Distribution | 2009-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009269 | 400303230 | Molding | HFTD Tier 3 | Distribution | 2009-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009270 | 400329251 | High Sign | HFTD Tier 3 | Distribution | 2009-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009271 | 400144193 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-06-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009272 | 400148789 | High Sign | HFTD Tier 2 | Distribution | 2009-06-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009273 | 400150256 | Molding | HFTD Tier 3 | Distribution | 2009-06-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009274 | 400161909 | Molding | HFTD Tier 2 | Distribution | 2009-06-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009275 | 400217959 | High Sign | HFTD Tier 2 | Distribution | 2009-06-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009276 | 400229138 | Molding | HFTD Tier 2 | Distribution | 2009-06-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009277 | 400167073 | High Sign | HFTD Tier 2 | Distribution | 2009-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009278 | 400316441 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009279 | 400162538 | Molding | HFTD Tier 3 | Distribution | 2009-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009280 | 400167299 | High Sign | HFTD Tier 2 | Distribution | 2009-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009281 | 400174735 | High Sign | HFTD Tier 2 | Distribution | 2009-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009282 | 400174795 | Guy | HFTD Tier 2 | Distribution | 2009-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009283 | 400342454 | Guy | HFTD Tier 2 | Distribution | 2009-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009284 | 400332157 | High Sign | HFTD Tier 3 | Distribution | 2009-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009285 | 400183350 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-06-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009286 | 400193852 | High Sign | HFTD Tier 2 | Distribution | 2009-06-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009287 | 400260849 | Molding | HFTD Tier 3 | Distribution | 2009-06-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009288 | 400224122 | High Sign | HFTD Tier 2 | Distribution | 2009-06-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009289 | 400309289 | Molding | HFTD Tier 2 | Distribution | 2009-06-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009290 | 400352857 | Riser/Conduit | HFTD Tier 2 | Distribution | 2009-06-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009291 | 400254346 | High Sign | HFTD Tier 2 | Distribution | 2009-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009292 | 400433099 | Riser/Conduit | HFTD Tier 2 | Distribution | 2009-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009293 | 400433922 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009294 | 400257813 | Molding | HFTD Tier 3 | Distribution | 2009-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009295 | 400270430 | Molding | HFTD Tier 2 | Distribution | 2009-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009296 | 400464307 | Molding | HFTD Tier 2 | Distribution | 2009-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009297 | 400382591 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009298 | 400485235 | Guy | HFTD Tier 2 | Distribution | 2009-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009299 | 400306594 | High Sign | HFTD Tier 3 | Distribution | 2009-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009300 | 400387035 | Molding | HFTD Tier 3 | Distribution | 2009-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009301 | 400489617 | Molding | HFTD Tier 2 | Distribution | 2009-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009302 | 400304212 | Molding | HFTD Tier 3 | Distribution | 2009-07-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009303 | 400420349 | High Sign | HFTD Tier 3 | Distribution | 2009-07-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009304 | 400332187 | High Sign | HFTD Tier 3 | Distribution | 2009-07-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009305 | 400444728 | High Sign | HFTD Tier 2 | Distribution | 2009-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009306 | 400164609 | Molding | HFTD Tier 2 | Distribution | 2009-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009307 | 400389225 | High Sign | HFTD Tier 3 | Distribution | 2009-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009308 | 400476077 | Molding | HFTD Tier 2 | Distribution | 2009-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009309 | 400366101 | Molding | HFTD Tier 2 | Distribution | 2009-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009310 | 400389198 | High Sign | HFTD Tier 2 | Distribution | 2009-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009311 | 400141610 | Molding | HFTD Tier 3 | Distribution | 2009-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009312 | 400153527 | Riser/Conduit | HFTD Tier 3 | Distribution | 2009-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009313 | 400028730 | Hardware/Framing | HFTD Tier 2 | Distribution | 2009-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009314 | 401703350 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2009-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009315 | 400033294 | Molding | HFTD Tier 3 | Distribution | 2009-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009316 | 401704282 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009317 | 400023061 | Insulator | HFTD Tier 3 | Distribution | 2009-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009318 | 400241873 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009319 | 400249950 | Molding | HFTD Tier 3 | Distribution | 2009-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009320 | 400095040 | Molding | HFTD Tier 3 | Distribution | 2009-08-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009321 | 400183318 | Molding | HFTD Tier 2 | Distribution | 2009-08-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009322 | 400183281 | Molding | HFTD Tier 3 | Distribution | 2009-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009323 | 400090622 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009324 | 400099760 | High Sign | HFTD Tier 3 | Distribution | 2009-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009325 | 400200353 | Molding | HFTD Tier 3 | Distribution | 2009-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009326 | 400202278 | High Sign | HFTD Tier 3 | Distribution | 2009-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009327 | 400298333 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009328 | 400142553 | High Sign | HFTD Tier 2 | Distribution | 2009-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009329 | 400222249 | Hardware/Framing | HFTD Tier 2 | Distribution | 2009-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009330 | 400306924 | Molding | HFTD Tier 3 | Distribution | 2009-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009331 | 400120395 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2009-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009332 | 401712889 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2009-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009333 | 400161407 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009334 | 400178734 | Molding | HFTD Tier 3 | Distribution | 2009-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009335 | 400233117 | Molding | HFTD Tier 3 | Distribution | 2009-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009336 | 400243239 | Molding | HFTD Tier 3 | Distribution | 2009-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009337 | 400151236 | Molding | HFTD Tier 3 | Distribution | 2009-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009338 | 400165744 | High Sign | HFTD Tier 3 | Distribution | 2009-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009339 | 400170719 | Molding | HFTD Tier 3 | Distribution | 2009-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009340 | 400197042 | High Sign | HFTD Tier 2 | Distribution | 2009-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009341 | 400198171 | Molding | HFTD Tier 2 | Distribution | 2009-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009342 | 400362677 | High Sign | HFTD Tier 2 | Distribution | 2009-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009343 | 401712500 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009344 | 400158440 | Hardware/Framing | HFTD Tier 2 | Distribution | 2009-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009345 | 400171849 | High Sign | HFTD Tier 3 | Distribution | 2009-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009346 | 400198209 | High Sign | HFTD Tier 3 | Distribution | 2009-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009347 | 400198246 | High Sign | HFTD Tier 3 | Distribution | 2009-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009348 | 400199519 | High Sign | HFTD Tier 3 | Distribution | 2009-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009349 | 400271997 | High Sign | HFTD Tier 3 | Distribution | 2009-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009350 | 400274162 | Molding | HFTD Tier 3 | Distribution | 2009-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009351 | 400359458 | Molding | HFTD Tier 2 | Distribution | 2009-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009352 | 400385757 | Molding | HFTD Tier 3 | Distribution | 2009-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009353 | 401459511 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2009-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009354 | 400048894 | Hardware/Framing | HFTD Tier 2 | Distribution | 2009-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009355 | 400170510 | Molding | HFTD Tier 2 | Distribution | 2009-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009356 | 400173033 | Molding | HFTD Tier 2 | Distribution | 2009-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009357 | 400180157 | High Sign | HFTD Tier 2 | Distribution | 2009-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009358 | 400208449 | High Sign | HFTD Tier 2 | Distribution | 2009-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009359 | 401714732 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009360 | 400232084 | High Sign | HFTD Tier 2 | Distribution | 2009-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009361 | 400285667 | High Sign | HFTD Tier 3 | Distribution | 2009-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009362 | 400351747 | Molding | HFTD Tier 2 | Distribution | 2009-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009363 | 400245200 | Molding | HFTD Tier 2 | Distribution | 2009-08-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009364 | 400297163 | Molding | HFTD Tier 3 | Distribution | 2009-08-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009365 | 401720812 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-08-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009366 | 400262029 | High Sign | HFTD Tier 3 | Distribution | 2009-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009367 | 400262054 | High Sign | HFTD Tier 3 | Distribution | 2009-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009368 | 400263694 | High Sign | HFTD Tier 3 | Distribution | 2009-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009369 | 400264874 | High Sign | HFTD Tier 3 | Distribution | 2009-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009370 | 400291719 | High Sign | HFTD Tier 2 | Distribution | 2009-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009371 | 400316646 | High Sign | HFTD Tier 3 | Distribution | 2009-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009372 | 400320878 | Molding | HFTD Tier 3 | Distribution | 2009-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009373 | 400320907 | High Sign | HFTD Tier 3 | Distribution | 2009-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009374 | 400325356 | Molding | HFTD Tier 2 | Distribution | 2009-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009375 | 400376480 | High Sign | HFTD Tier 3 | Distribution | 2009-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009376 | 400379180 | High Sign | HFTD Tier 3 | Distribution | 2009-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009377 | 400473225 | Molding | HFTD Tier 3 | Distribution | 2009-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009378 | 400286920 | Hardware/Framing | HFTD Tier 2 | Distribution | 2009-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009379 | 400290409 | High Sign | HFTD Tier 3 | Distribution | 2009-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009380 | 400292095 | Molding | HFTD Tier 3 | Distribution | 2009-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009381 | 400336737 | High Sign | HFTD Tier 2 | Distribution | 2009-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009382 | 400336954 | Molding | HFTD Tier 3 | Distribution | 2009-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009383 | 400339570 | High Sign | HFTD Tier 3 | Distribution | 2009-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009384 | 400394700 | High Sign | HFTD Tier 2 | Distribution | 2009-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009385 | 400400564 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009386 | 400485233 | High Sign | HFTD Tier 2 | Distribution | 2009-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009387 | 400485853 | High Sign | HFTD Tier 3 | Distribution | 2009-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009388 | 400047360 | High Sign | HFTD Tier 2 | Distribution | 2009-08-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009389 | 400322444 | High Sign | HFTD Tier 2 | Distribution | 2009-08-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009390 | 400376308 | High Sign | HFTD Tier 2 | Distribution | 2009-08-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009391 | 400423654 | High Sign | HFTD Tier 3 | Distribution | 2009-08-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009392 | 400443200 | High Sign | HFTD Tier 2 | Distribution | 2009-08-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009393 | 400042326 | High Sign | HFTD Tier 2 | Distribution | 2009-08-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009394 | 400044854 | Hardware/Framing | HFTD Tier 2 | Distribution | 2009-08-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009395 | 400326146 | High Sign | HFTD Tier 2 | Distribution | 2009-08-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009396 | 400374416 | High Sign | HFTD Tier 2 | Distribution | 2009-08-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009397 | 403883957 | High Sign | HFTD Tier 3 | Distribution | 2009-08-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009398 | 400067062 | High Sign | HFTD Tier 2 | Distribution | 2009-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009399 | 400068534 | High Sign | HFTD Tier 3 | Distribution | 2009-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009400 | 400070787 | High Sign | HFTD Tier 2 | Distribution | 2009-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009401 | 400074893 | Molding | HFTD Tier 2 | Distribution | 2009-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009402 | 400182627 | Molding | HFTD Tier 2 | Distribution | 2009-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009403 | 400198339 | Molding | HFTD Tier 3 | Distribution | 2009-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009404 | 400375367 | Guy | HFTD Tier 2 | Distribution | 2009-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009405 | 400376168 | High Sign | HFTD Tier 2 | Distribution | 2009-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009406 | 400387607 | High Sign | HFTD Tier 3 | Distribution | 2009-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009407 | 400401760 | High Sign | HFTD Tier 2 | Distribution | 2009-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009408 | 400406054 | High Sign | HFTD Tier 2 | Distribution | 2009-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009409 | 400430552 | Molding | HFTD Tier 2 | Distribution | 2009-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009410 | 400480041 | High Sign | HFTD Tier 3 | Distribution | 2009-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009411 | 400399465 | Molding | HFTD Tier 2 | Distribution | 2009-09-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009412 | 400404650 | High Sign | HFTD Tier 2 | Distribution | 2009-09-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009413 | 400425580 | High Sign | HFTD Tier 2 | Distribution | 2009-09-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009414 | 400430202 | High Sign | HFTD Tier 2 | Distribution | 2009-09-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009415 | 400430484 | Anchor | HFTD Tier 3 | Distribution | 2009-09-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009416 | 400430525 | High Sign | HFTD Tier 2 | Distribution | 2009-09-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009417 | 400478867 | High Sign | HFTD Tier 2 | Distribution | 2009-09-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009418 | 400480738 | High Sign | HFTD Tier 2 | Distribution | 2009-09-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009419 | 400482583 | High Sign | HFTD Tier 2 | Distribution | 2009-09-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009420 | 400493737 | High Sign | HFTD Tier 2 | Distribution | 2009-09-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009421 | 401457708 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-09-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009422 | 400106939 | High Sign | HFTD Tier 3 | Distribution | 2009-09-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009423 | 400433932 | Molding | HFTD Tier 3 | Distribution | 2009-09-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009424 | 400436429 | Molding | HFTD Tier 3 | Distribution | 2009-09-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009425 | 400440702 | Molding | HFTD Tier 3 | Distribution | 2009-09-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009426 | 400104568 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2009-09-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009427 | 400185598 | High Sign | HFTD Tier 2 | Distribution | 2009-09-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009428 | 400201551 | High Sign | HFTD Tier 2 | Distribution | 2009-09-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009429 | 400459107 | High Sign | HFTD Tier 2 | Distribution | 2009-09-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009430 | 400459132 | High Sign | HFTD Tier 3 | Distribution | 2009-09-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009431 | 400479699 | High Sign | HFTD Tier 3 | Distribution | 2009-09-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009432 | 400021724 | Molding | HFTD Tier 2 | Distribution | 2009-09-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009433 | 400086201 | Molding | HFTD Tier 3 | Distribution | 2009-09-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009434 | 401006386 | High Sign | HFTD Tier 3 | Distribution | 2009-09-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009435 | 401006387 | High Sign | HFTD Tier 3 | Distribution | 2009-09-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009436 | 400025499 | High Sign | HFTD Tier 3 | Distribution | 2009-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009437 | 400084788 | Riser/Conduit | HFTD Tier 3 | Distribution | 2009-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009438 | 400110483 | Molding | HFTD Tier 2 | Distribution | 2009-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009439 | 400079339 | High Sign | HFTD Tier 3 | Distribution | 2009-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009440 | 400085699 | Molding | HFTD Tier 2 | Distribution | 2009-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009441 | 400132960 | Anchor | HFTD Tier 3 | Distribution | 2009-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009442 | 400053658 | High Sign | HFTD Tier 2 | Distribution | 2009-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009443 | 400088458 | High Sign | HFTD Tier 2 | Distribution | 2009-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009444 | 400095893 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009445 | 400220475 | Molding | HFTD Tier 2 | Distribution | 2009-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009446 | 400225322 | Molding | HFTD Tier 2 | Distribution | 2009-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009447 | 400183193 | High Sign | HFTD Tier 2 | Distribution | 2009-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009448 | 400185163 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2009-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009449 | 400139471 | High Sign | HFTD Tier 2 | Distribution | 2009-09-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009450 | 400145233 | Molding | HFTD Tier 3 | Distribution | 2009-09-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009451 | 400148790 | Molding | HFTD Tier 2 | Distribution | 2009-09-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009452 | 400201139 | Molding | HFTD Tier 2 | Distribution | 2009-09-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009453 | 401462634 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2009-09-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009454 | 400155592 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009455 | 400217418 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009456 | 400240063 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009457 | 400388964 | Molding | HFTD Tier 2 | Distribution | 2009-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009458 | 400192826 | Molding | HFTD Tier 3 | Distribution | 2009-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009459 | 400197544 | Molding | HFTD Tier 3 | Distribution | 2009-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009460 | 400209431 | Molding | HFTD Tier 3 | Distribution | 2009-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009461 | 400249002 | High Sign | HFTD Tier 3 | Distribution | 2009-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009462 | 400348338 | High Sign | HFTD Tier 3 | Distribution | 2009-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009463 | 400426246 | High Sign | HFTD Tier 3 | Distribution | 2009-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009464 | 400451714 | Guy | HFTD Tier 3 | Distribution | 2009-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009465 | 401466379 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2009-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009466 | 400283771 | Molding | HFTD Tier 3 | Distribution | 2009-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009467 | 400299249 | High Sign | HFTD Tier 3 | Distribution | 2009-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009468 | 400218330 | Crossarm | HFTD Tier 2 | Distribution | 2009-10-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009469 | 400371370 | Molding | HFTD Tier 2 | Distribution | 2009-10-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009470 | 400422826 | High Sign | HFTD Tier 2 | Distribution | 2009-10-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009471 | 400430499 | High Sign | HFTD Tier 2 | Distribution | 2009-10-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009472 | 400075025 | Molding | HFTD Tier 2 | Distribution | 2009-10-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009473 | 400081780 | Molding | HFTD Tier 2 | Distribution | 2009-10-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009474 | 400022221 | Guy | HFTD Tier 2 | Distribution | 2009-10-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009475 | 400024137 | High Sign | HFTD Tier 2 | Distribution | 2009-10-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009476 | 400444132 | High Sign | HFTD Tier 2 | Distribution | 2009-10-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009477 | 400446479 | Molding | HFTD Tier 2 | Distribution | 2009-10-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009478 | 400455027 | Molding | HFTD Tier 2 | Distribution | 2009-10-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009479 | 400457023 | High Sign | HFTD Tier 2 | Distribution | 2009-10-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009480 | 400197352 | Ground | HFTD Tier 2 | Distribution | 2009-10-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009481 | 400121960 | Molding | HFTD Tier 3 | Distribution | 2009-10-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009482 | 400461735 | High Sign | HFTD Tier 2 | Distribution | 2009-10-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009483 | 401474884 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2009-10-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009484 | 400211657 | High Sign | HFTD Tier 3 | Distribution | 2009-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009485 | 400468812 | Molding | HFTD Tier 3 | Distribution | 2009-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009486 | 400015232 | High Sign | HFTD Tier 3 | Distribution | 2009-10-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009487 | 400030696 | High Sign | HFTD Tier 3 | Distribution | 2009-10-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009488 | 400048943 | High Sign | HFTD Tier 3 | Distribution | 2009-10-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009489 | 400052550 | High Sign | HFTD Tier 3 | Distribution | 2009-10-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009490 | 400052579 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-10-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009491 | 400146800 | High Sign | HFTD Tier 3 | Distribution | 2009-10-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009492 | 400165063 | High Sign | HFTD Tier 3 | Distribution | 2009-10-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009493 | 400475206 | High Sign | HFTD Tier 3 | Distribution | 2009-10-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009494 | 403883808 | High Sign | HFTD Tier 3 | Distribution | 2009-10-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009495 | 403883838 | High Sign | HFTD Tier 3 | Distribution | 2009-10-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009496 | 400013695 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009497 | 400016318 | High Sign | HFTD Tier 3 | Distribution | 2009-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009498 | 400019053 | High Sign | HFTD Tier 2 | Distribution | 2009-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009499 | 400059184 | High Sign | HFTD Tier 3 | Distribution | 2009-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009500 | 400059412 | High Sign | HFTD Tier 3 | Distribution | 2009-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009501 | 400070454 | High Sign | HFTD Tier 3 | Distribution | 2009-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009502 | 400073009 | Guy | HFTD Tier 3 | Distribution | 2009-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009503 | 400200769 | High Sign | HFTD Tier 3 | Distribution | 2009-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009504 | 400487285 | High Sign | HFTD Tier 3 | Distribution | 2009-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009505 | 400071927 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-10-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009506 | 400046071 | Insulator | HFTD Tier 2 | Distribution | 2009-10-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009507 | 400028202 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009508 | 400047589 | Molding | HFTD Tier 3 | Distribution | 2009-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009509 | 400049717 | High Sign | HFTD Tier 3 | Distribution | 2009-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009510 | 400049777 | Guy | HFTD Tier 3 | Distribution | 2009-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009511 | 400077964 | Molding | HFTD Tier 3 | Distribution | 2009-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009512 | 400082632 | Guy | HFTD Tier 3 | Distribution | 2009-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009513 | 400084203 | Guy | HFTD Tier 3 | Distribution | 2009-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009514 | 400084232 | Molding | HFTD Tier 3 | Distribution | 2009-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009515 | 400221563 | High Sign | HFTD Tier 3 | Distribution | 2009-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009516 | 400224063 | Molding | HFTD Tier 3 | Distribution | 2009-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009517 | 400230142 | Molding | HFTD Tier 3 | Distribution | 2009-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009518 | 400063873 | Molding | HFTD Tier 3 | Distribution | 2009-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009519 | 400133618 | High Sign | HFTD Tier 3 | Distribution | 2009-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009520 | 400144875 | Molding | HFTD Tier 3 | Distribution | 2009-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009521 | 400095012 | High Sign | HFTD Tier 2 | Distribution | 2009-10-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009522 | 400150803 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-10-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009523 | 400266911 | Molding | HFTD Tier 3 | Distribution | 2009-10-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009524 | 400269464 | High Sign | HFTD Tier 2 | Distribution | 2009-10-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009525 | 400272573 | High Sign | HFTD Tier 3 | Distribution | 2009-10-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009526 | 400160366 | Molding | HFTD Tier 3 | Distribution | 2009-10-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009527 | 400140211 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2009-10-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009528 | 400140846 | High Sign | HFTD Tier 3 | Distribution | 2009-10-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009529 | 400141377 | High Sign | HFTD Tier 3 | Distribution | 2009-10-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009530 | 400203138 | Molding | HFTD Tier 3 | Distribution | 2009-10-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009531 | 400211515 | High Sign | HFTD Tier 3 | Distribution | 2009-10-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009532 | 400228938 | Molding | HFTD Tier 3 | Distribution | 2009-10-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009533 | 400230986 | Molding | HFTD Tier 3 | Distribution | 2009-10-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009534 | 400282737 | Guy | HFTD Tier 3 | Distribution | 2009-10-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009535 | 400291137 | Molding | HFTD Tier 3 | Distribution | 2009-10-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009536 | 400140967 | Molding | HFTD Tier 3 | Distribution | 2009-11-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009537 | 400143697 | High Sign | HFTD Tier 3 | Distribution | 2009-11-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009538 | 400166960 | High Sign | HFTD Tier 3 | Distribution | 2009-11-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009539 | 400203113 | Molding | HFTD Tier 2 | Distribution | 2009-11-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009540 | 400281746 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-11-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009541 | 400179691 | Guy | HFTD Tier 3 | Distribution | 2009-11-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009542 | 400283010 | Molding | HFTD Tier 3 | Distribution | 2009-11-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009543 | 400388070 | Molding | HFTD Tier 2 | Distribution | 2009-11-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009544 | 400362962 | Molding | HFTD Tier 3 | Distribution | 2009-11-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009545 | 400191601 | High Sign | HFTD Tier 3 | Distribution | 2009-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009546 | 400197449 | Molding | HFTD Tier 2 | Distribution | 2009-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009547 | 400197957 | High Sign | HFTD Tier 3 | Distribution | 2009-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009548 | 400381958 | Molding | HFTD Tier 2 | Distribution | 2009-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009549 | 400383763 | Molding | HFTD Tier 2 | Distribution | 2009-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009550 | 400384469 | High Sign | HFTD Tier 3 | Distribution | 2009-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009551 | 400387935 | Molding | HFTD Tier 2 | Distribution | 2009-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009552 | 400193780 | Molding | HFTD Tier 3 | Distribution | 2009-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009553 | 400214517 | Ground | HFTD Tier 2 | Distribution | 2009-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009554 | 400217205 | Ground | HFTD Tier 2 | Distribution | 2009-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009555 | 400239442 | Molding | HFTD Tier 3 | Distribution | 2009-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009556 | 400261965 | High Sign | HFTD Tier 2 | Distribution | 2009-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009557 | 400200870 | Molding | HFTD Tier 2 | Distribution | 2009-11-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009558 | 400244535 | Guy | HFTD Tier 2 | Distribution | 2009-11-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009559 | 400273393 | Molding | HFTD Tier 3 | Distribution | 2009-11-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009560 | 400415002 | Insulator | HFTD Tier 2 | Distribution | 2009-11-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009561 | 400234460 | Molding | HFTD Tier 2 | Distribution | 2009-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009562 | 400236823 | High Sign | HFTD Tier 3 | Distribution | 2009-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009563 | 400259802 | Molding | HFTD Tier 2 | Distribution | 2009-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009564 | 400262617 | Molding | HFTD Tier 3 | Distribution | 2009-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009565 | 400262817 | Molding | HFTD Tier 3 | Distribution | 2009-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009566 | 400283916 | High Sign | HFTD Tier 3 | Distribution | 2009-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009567 | 400425930 | High Sign | HFTD Tier 2 | Distribution | 2009-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009568 | 400433315 | Molding | HFTD Tier 3 | Distribution | 2009-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009569 | 400236130 | Guy | HFTD Tier 3 | Distribution | 2009-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009570 | 400289289 | Guy | HFTD Tier 3 | Distribution | 2009-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009571 | 400298480 | High Sign | HFTD Tier 2 | Distribution | 2009-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009572 | 400301195 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009573 | 400433666 | Molding | HFTD Tier 3 | Distribution | 2009-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009574 | 400291333 | Molding | HFTD Tier 2 | Distribution | 2009-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009575 | 400291424 | High Sign | HFTD Tier 2 | Distribution | 2009-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009576 | 400447305 | High Sign | HFTD Tier 3 | Distribution | 2009-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009577 | 400459308 | Molding | HFTD Tier 3 | Distribution | 2009-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009578 | 400328889 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009579 | 400317680 | Guy | HFTD Tier 3 | Distribution | 2009-11-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009580 | 400330343 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-11-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009581 | 400345160 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-11-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009582 | 400427928 | High Sign | HFTD Tier 2 | Distribution | 2009-11-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009583 | 401006518 | Molding | HFTD Tier 3 | Distribution | 2009-11-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009584 | 401006519 | High Sign | HFTD Tier 3 | Distribution | 2009-11-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009585 | 401500937 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2009-11-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009586 | 400089750 | High Sign | HFTD Tier 3 | Distribution | 2009-11-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009587 | 400467443 | Molding | HFTD Tier 2 | Distribution | 2009-11-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009588 | 400012626 | Molding | HFTD Tier 3 | Distribution | 2009-11-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009589 | 400098559 | Molding | HFTD Tier 2 | Distribution | 2009-11-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009590 | 400375233 | High Sign | HFTD Tier 3 | Distribution | 2009-11-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009591 | 400428673 | High Sign | HFTD Tier 2 | Distribution | 2009-11-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009592 | 400436502 | High Sign | HFTD Tier 2 | Distribution | 2009-11-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009593 | 400463522 | High Sign | HFTD Tier 2 | Distribution | 2009-11-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009594 | 400465752 | Molding | HFTD Tier 2 | Distribution | 2009-11-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009595 | 400467988 | High Sign | HFTD Tier 2 | Distribution | 2009-11-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009596 | 400469622 | High Sign | HFTD Tier 2 | Distribution | 2009-11-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009597 | 400439427 | Guy | HFTD Tier 3 | Distribution | 2009-11-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009598 | 400463573 | Guy | HFTD Tier 3 | Distribution | 2009-11-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009599 | 400468616 | Guy | HFTD Tier 3 | Distribution | 2009-11-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009600 | 400393414 | Molding | HFTD Tier 2 | Distribution | 2009-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009601 | 400124788 | Insulator | HFTD Tier 3 | Distribution | 2009-12-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009602 | 400013056 | Guy | HFTD Tier 3 | Distribution | 2009-12-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009603 | 400014939 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-12-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009604 | 401506491 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2009-12-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009605 | 400051112 | Hardware/Framing | HFTD Tier 2 | Distribution | 2009-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009606 | 400078675 | Molding | HFTD Tier 3 | Distribution | 2009-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009607 | 400173113 | Ground | HFTD Tier 2 | Distribution | 2009-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009608 | 400469596 | High Sign | HFTD Tier 3 | Distribution | 2009-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009609 | 400012841 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009610 | 400054304 | High Sign | HFTD Tier 2 | Distribution | 2009-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009611 | 400216980 | Molding | HFTD Tier 2 | Distribution | 2009-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009612 | 400225207 | Molding | HFTD Tier 3 | Distribution | 2009-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009613 | 400228202 | Molding | HFTD Tier 3 | Distribution | 2009-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009614 | 400234091 | Molding | HFTD Tier 3 | Distribution | 2009-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009615 | 400237838 | Molding | HFTD Tier 3 | Distribution | 2009-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009616 | 400230341 | Guy | HFTD Tier 3 | Distribution | 2009-12-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009617 | 400030245 | Guy | HFTD Tier 3 | Distribution | 2009-12-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009618 | 400097303 | Riser/Conduit | HFTD Tier 3 | Distribution | 2009-12-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009619 | 400106072 | Hardware/Framing | HFTD Tier 3 | Distribution | 2009-12-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009620 | 400111486 | Guy | HFTD Tier 2 | Distribution | 2009-12-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009621 | 400121335 | Molding | HFTD Tier 2 | Distribution | 2009-12-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009622 | 400223457 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-12-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009623 | 400138410 | Molding | HFTD Tier 2 | Distribution | 2009-12-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009624 | 400140984 | Molding | HFTD Tier 2 | Distribution | 2009-12-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009625 | 400270110 | Hardware/Framing | HFTD Tier 2 | Distribution | 2009-12-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009626 | 400163776 | Molding | HFTD Tier 3 | Distribution | 2009-12-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009627 | 400171562 | Molding | HFTD Tier 2 | Distribution | 2009-12-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009628 | 400177681 | High Sign | HFTD Tier 3 | Distribution | 2009-12-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009629 | 401006605 | High Sign | HFTD Tier 3 | Distribution | 2009-12-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009630 | 400172156 | Molding | HFTD Tier 3 | Distribution | 2009-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009631 | 400175010 | High Sign | HFTD Tier 3 | Distribution | 2009-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009632 | 400175156 | Guy | HFTD Tier 2 | Distribution | 2009-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009633 | 400176232 | Molding | HFTD Tier 3 | Distribution | 2009-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009634 | 400179349 | High Sign | HFTD Tier 3 | Distribution | 2009-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009635 | 400312041 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009636 | 400115229 | Molding | HFTD Tier 2 | Distribution | 2009-12-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009637 | 400118078 | Cable/Conductor | HFTD Tier 2 | Distribution | 2009-12-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009638 | 400119473 | Molding | HFTD Tier 2 | Distribution | 2009-12-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009639 | 400185442 | High Sign | HFTD Tier 2 | Distribution | 2009-12-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009640 | 400197568 | Molding | HFTD Tier 2 | Distribution | 2009-12-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009641 | 400334905 | Insulator | HFTD Tier 2 | Distribution | 2009-12-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009642 | 400339633 | Molding | HFTD Tier 2 | Distribution | 2009-12-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009643 | 400363612 | Guy | HFTD Tier 3 | Distribution | 2009-12-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009644 | 401520819 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2009-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009645 | 401532245 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2009-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009646 | 400187077 | Molding | HFTD Tier 3 | Distribution | 2009-12-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009647 | 400235124 | High Sign | HFTD Tier 3 | Distribution | 2009-12-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009648 | 400251294 | High Sign | HFTD Tier 3 | Distribution | 2009-12-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009649 | 400253502 | Molding | HFTD Tier 3 | Distribution | 2009-12-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009650 | 400385230 | Cable/Conductor | HFTD Tier 3 | Distribution | 2009-12-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009651 | 400430980 | Riser/Conduit | HFTD Tier 3 | Distribution | 2009-12-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009652 | 400015389 | Molding | HFTD Tier 2 | Distribution | 2010-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009653 | 400268279 | Molding | HFTD Tier 2 | Distribution | 2010-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009654 | 400272913 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009655 | 400032020 | High Sign | HFTD Tier 2 | Distribution | 2010-01-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009656 | 400264357 | Molding | HFTD Tier 2 | Distribution | 2010-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009657 | 400123983 | High Sign | HFTD Tier 2 | Distribution | 2010-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009658 | 400189710 | Molding | HFTD Tier 2 | Distribution | 2010-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009659 | 400245595 | Molding | HFTD Tier 2 | Distribution | 2010-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009660 | 400246608 | High Sign | HFTD Tier 2 | Distribution | 2010-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009661 | 400254828 | Molding | HFTD Tier 2 | Distribution | 2010-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009662 | 400256003 | Molding | HFTD Tier 2 | Distribution | 2010-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009663 | 400268891 | Molding | HFTD Tier 2 | Distribution | 2010-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009664 | 400272898 | Molding | HFTD Tier 2 | Distribution | 2010-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009665 | 401551099 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009666 | 400113069 | High Sign | HFTD Tier 3 | Distribution | 2010-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009667 | 400242544 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009668 | 400089687 | High Sign | HFTD Tier 3 | Distribution | 2010-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009669 | 400157205 | Molding | HFTD Tier 3 | Distribution | 2010-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009670 | 400216148 | Ground | HFTD Tier 2 | Distribution | 2010-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009671 | 400205832 | High Sign | HFTD Tier 3 | Distribution | 2010-01-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009672 | 400247398 | Molding | HFTD Tier 3 | Distribution | 2010-01-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009673 | 400256156 | Molding | HFTD Tier 2 | Distribution | 2010-01-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009674 | 400257906 | High Sign | HFTD Tier 3 | Distribution | 2010-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009675 | 400132511 | Molding | HFTD Tier 3 | Distribution | 2010-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009676 | 400132770 | Molding | HFTD Tier 3 | Distribution | 2010-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009677 | 400139845 | Molding | HFTD Tier 3 | Distribution | 2010-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009678 | 400256462 | Molding | HFTD Tier 3 | Distribution | 2010-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009679 | 400258557 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009680 | 400265331 | Molding | HFTD Tier 3 | Distribution | 2010-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009681 | 400266563 | Molding | HFTD Tier 3 | Distribution | 2010-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009682 | 400375797 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009683 | 400379427 | Guy | HFTD Tier 3 | Distribution | 2010-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009684 | 400385911 | Molding | HFTD Tier 3 | Distribution | 2010-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009685 | 400388434 | High Sign | HFTD Tier 3 | Distribution | 2010-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009686 | 401552723 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009687 | 400149941 | Molding | HFTD Tier 3 | Distribution | 2010-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009688 | 400155333 | Molding | HFTD Tier 2 | Distribution | 2010-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009689 | 400291770 | High Sign | HFTD Tier 2 | Distribution | 2010-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009690 | 401732683 | Molding | HFTD Tier 2 | Distribution | 2010-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009691 | 401737514 | Molding | HFTD Tier 2 | Distribution | 2010-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009692 | 400264578 | Molding | HFTD Tier 3 | Distribution | 2010-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009693 | 400447145 | High Sign | HFTD Tier 3 | Distribution | 2010-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009694 | 413834634 | High Sign | HFTD Tier 3 | Distribution | 2010-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009695 | 401579604 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009696 | 400438219 | High Sign | HFTD Tier 3 | Distribution | 2010-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009697 | 400439334 | Molding | HFTD Tier 3 | Distribution | 2010-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009698 | 400455184 | High Sign | HFTD Tier 2 | Distribution | 2010-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009699 | 400271313 | Molding | HFTD Tier 3 | Distribution | 2010-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009700 | 400297538 | High Sign | HFTD Tier 3 | Distribution | 2010-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009701 | 400471691 | Molding | HFTD Tier 3 | Distribution | 2010-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009702 | 400195262 | High Sign | HFTD Tier 3 | Distribution | 2010-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009703 | 400395340 | High Sign | HFTD Tier 3 | Distribution | 2010-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009704 | 400154568 | High Sign | HFTD Tier 3 | Distribution | 2010-02-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009705 | 400205409 | Molding | HFTD Tier 3 | Distribution | 2010-02-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009706 | 400008504 | Molding | HFTD Tier 3 | Distribution | 2010-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009707 | 400008583 | High Sign | HFTD Tier 3 | Distribution | 2010-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009708 | 400072611 | Molding | HFTD Tier 3 | Distribution | 2010-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009709 | 400206148 | Molding | HFTD Tier 2 | Distribution | 2010-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009710 | 400382837 | High Sign | HFTD Tier 3 | Distribution | 2010-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009711 | 400090221 | High Sign | HFTD Tier 3 | Distribution | 2010-02-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009712 | 400100358 | Riser/Conduit | HFTD Tier 3 | Distribution | 2010-02-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009713 | 400440916 | High Sign | HFTD Tier 3 | Distribution | 2010-02-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009714 | 400011873 | Molding | HFTD Tier 3 | Distribution | 2010-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009715 | 400046497 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009716 | 400052133 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009717 | 400269975 | Guy | HFTD Tier 3 | Distribution | 2010-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009718 | 400272162 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009719 | 400278965 | Molding | HFTD Tier 3 | Distribution | 2010-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009720 | 400462137 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009721 | 400076161 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009722 | 400278282 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009723 | 400278296 | High Sign | HFTD Tier 3 | Distribution | 2010-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009724 | 400173349 | High Sign | HFTD Tier 2 | Distribution | 2010-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009725 | 400027530 | High Sign | HFTD Tier 3 | Distribution | 2010-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009726 | 400032573 | Molding | HFTD Tier 2 | Distribution | 2010-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009727 | 400032649 | High Sign | HFTD Tier 3 | Distribution | 2010-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009728 | 400084218 | Guy | HFTD Tier 3 | Distribution | 2010-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009729 | 400176817 | High Sign | HFTD Tier 3 | Distribution | 2010-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009730 | 400313141 | Molding | HFTD Tier 3 | Distribution | 2010-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009731 | 400105799 | Molding | HFTD Tier 3 | Distribution | 2010-02-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009732 | 400201703 | High Sign | HFTD Tier 3 | Distribution | 2010-02-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009733 | 400216415 | Guy | HFTD Tier 3 | Distribution | 2010-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009734 | 400098741 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009735 | 400104526 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009736 | 400125827 | Molding | HFTD Tier 3 | Distribution | 2010-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009737 | 400256777 | Molding | HFTD Tier 3 | Distribution | 2010-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009738 | 400008910 | Molding | HFTD Tier 3 | Distribution | 2010-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009739 | 400178040 | Ground | HFTD Tier 3 | Distribution | 2010-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009740 | 400251062 | High Sign | HFTD Tier 2 | Distribution | 2010-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009741 | 400431187 | Molding | HFTD Tier 2 | Distribution | 2010-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009742 | 400190397 | Molding | HFTD Tier 3 | Distribution | 2010-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009743 | 400282033 | Molding | HFTD Tier 3 | Distribution | 2010-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009744 | 403154542 | High Sign | HFTD Tier 3 | Distribution | 2010-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009745 | 403154548 | Molding | HFTD Tier 3 | Distribution | 2010-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009746 | 400055639 | Molding | HFTD Tier 2 | Distribution | 2010-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009747 | 400191339 | High Sign | HFTD Tier 2 | Distribution | 2010-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009748 | 400006683 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009749 | 400007388 | Molding | HFTD Tier 3 | Distribution | 2010-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009750 | 400082328 | Molding | HFTD Tier 3 | Distribution | 2010-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009751 | 400195217 | High Sign | HFTD Tier 2 | Distribution | 2010-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009752 | 400089857 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009753 | 400092784 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009754 | 400109389 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009755 | 400200539 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009756 | 400206049 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009757 | 400348983 | Riser/Conduit | HFTD Tier 3 | Distribution | 2010-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009758 | 400352305 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009759 | 400009059 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009760 | 400285507 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009761 | 400369173 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009762 | 400374274 | High Sign | HFTD Tier 2 | Distribution | 2010-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009763 | 400374942 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009764 | 400019302 | High Sign | HFTD Tier 3 | Distribution | 2010-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009765 | 400118963 | High Sign | HFTD Tier 3 | Distribution | 2010-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009766 | 400204664 | Guy | HFTD Tier 3 | Distribution | 2010-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009767 | 400208758 | Riser/Conduit | HFTD Tier 3 | Distribution | 2010-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009768 | 400212005 | Molding | HFTD Tier 3 | Distribution | 2010-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009769 | 400212030 | High Sign | HFTD Tier 3 | Distribution | 2010-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009770 | 400397334 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009771 | 400409337 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009772 | 400143625 | High Sign | HFTD Tier 2 | Distribution | 2010-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009773 | 400147086 | Molding | HFTD Tier 2 | Distribution | 2010-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009774 | 400208958 | Riser/Conduit | HFTD Tier 3 | Distribution | 2010-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009775 | 400209470 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009776 | 400215118 | Riser/Conduit | HFTD Tier 3 | Distribution | 2010-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009777 | 400216114 | High Sign | HFTD Tier 2 | Distribution | 2010-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009778 | 400216984 | High Sign | HFTD Tier 2 | Distribution | 2010-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009779 | 400289294 | Molding | HFTD Tier 3 | Distribution | 2010-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009780 | 400415909 | Molding | HFTD Tier 2 | Distribution | 2010-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009781 | 400072147 | Molding | HFTD Tier 2 | Distribution | 2010-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009782 | 400210858 | Guy | HFTD Tier 3 | Distribution | 2010-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009783 | 400216140 | High Sign | HFTD Tier 2 | Distribution | 2010-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009784 | 400305185 | Molding | HFTD Tier 2 | Distribution | 2010-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009785 | 400447545 | Riser/Conduit | HFTD Tier 3 | Distribution | 2010-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009786 | 400452180 | High Sign | HFTD Tier 2 | Distribution | 2010-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009787 | 400464327 | High Sign | HFTD Tier 2 | Distribution | 2010-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009788 | 400106509 | High Sign | HFTD Tier 3 | Distribution | 2010-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009789 | 400159280 | High Sign | HFTD Tier 3 | Distribution | 2010-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009790 | 400008551 | Molding | HFTD Tier 2 | Distribution | 2010-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009791 | 400123021 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009792 | 400131575 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009793 | 400131662 | Molding | HFTD Tier 3 | Distribution | 2010-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009794 | 400174816 | Molding | HFTD Tier 3 | Distribution | 2010-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009795 | 400228685 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009796 | 400231794 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009797 | 400236671 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009798 | 400024126 | High Sign | HFTD Tier 2 | Distribution | 2010-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009799 | 400237221 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009800 | 400151268 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009801 | 400186582 | Molding | HFTD Tier 3 | Distribution | 2010-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009802 | 400069680 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009803 | 400243849 | Molding | HFTD Tier 3 | Distribution | 2010-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009804 | 400086381 | High Sign | HFTD Tier 2 | Distribution | 2010-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009805 | 400195482 | Molding | HFTD Tier 3 | Distribution | 2010-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009806 | 400244313 | High Sign | HFTD Tier 3 | Distribution | 2010-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009807 | 403154589 | High Sign | HFTD Tier 2 | Distribution | 2010-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009808 | 400090759 | Riser/Conduit | HFTD Tier 3 | Distribution | 2010-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009809 | 400167107 | High Sign | HFTD Tier 3 | Distribution | 2010-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009810 | 400234625 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009811 | 400239631 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009812 | 400244906 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009813 | 400244930 | Molding | HFTD Tier 3 | Distribution | 2010-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009814 | 400301639 | High Sign | HFTD Tier 2 | Distribution | 2010-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009815 | 400302400 | Ground | HFTD Tier 2 | Distribution | 2010-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009816 | 400303534 | Ground | HFTD Tier 2 | Distribution | 2010-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009817 | 401732859 | Guy | HFTD Tier 2 | Distribution | 2010-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009818 | 400167650 | Guy | HFTD Tier 3 | Distribution | 2010-04-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009819 | 400202158 | Molding | HFTD Tier 3 | Distribution | 2010-04-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009820 | 400206384 | Molding | HFTD Tier 3 | Distribution | 2010-04-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009821 | 401009422 | Molding | HFTD Tier 2 | Distribution | 2010-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009822 | 401009435 | Riser/Conduit | HFTD Tier 2 | Distribution | 2010-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009823 | 401010714 | High Sign | HFTD Tier 2 | Distribution | 2010-04-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009824 | 401012062 | Molding | HFTD Tier 3 | Distribution | 2010-04-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009825 | 401011836 | Guy | HFTD Tier 3 | Distribution | 2010-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009826 | 401011845 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009827 | 401011859 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009828 | 401011863 | Molding | HFTD Tier 3 | Distribution | 2010-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009829 | 401013331 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009830 | 401013340 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009831 | 403109490 | High Sign | HFTD Tier 2 | Distribution | 2010-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009832 | 401014166 | Termination | HFTD Tier 2 | Distribution | 2010-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009833 | 401014172 | Molding | HFTD Tier 2 | Distribution | 2010-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009834 | 401015483 | High Sign | HFTD Tier 3 | Distribution | 2010-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009835 | 401016218 | High Sign | HFTD Tier 3 | Distribution | 2010-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009836 | 401016410 | Molding | HFTD Tier 2 | Distribution | 2010-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009837 | 401016247 | High Sign | HFTD Tier 3 | Distribution | 2010-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009838 | 401016324 | Vis Strips | HFTD Tier 2 | Distribution | 2010-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009839 | 401016365 | Molding | HFTD Tier 2 | Distribution | 2010-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009840 | 401016394 | Molding | HFTD Tier 2 | Distribution | 2010-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009841 | 401016575 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009842 | 401017040 | Molding | HFTD Tier 2 | Distribution | 2010-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009843 | 401017805 | High Sign | HFTD Tier 3 | Distribution | 2010-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009844 | 401018863 | High Sign | HFTD Tier 3 | Distribution | 2010-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009845 | 401019015 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009846 | 401019017 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009847 | 401007659 | High Sign | HFTD Tier 2 | Distribution | 2010-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009848 | 401007705 | Molding | HFTD Tier 2 | Distribution | 2010-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009849 | 401009345 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009850 | 401011328 | Vis Strips | HFTD Tier 2 | Distribution | 2010-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009851 | 401009061 | High Sign | HFTD Tier 2 | Distribution | 2010-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009852 | 401009301 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009853 | 401009567 | High Sign | HFTD Tier 2 | Distribution | 2010-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009854 | 401009608 | Molding | HFTD Tier 2 | Distribution | 2010-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009855 | 401009611 | Molding | HFTD Tier 2 | Distribution | 2010-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009856 | 401009614 | Guy | HFTD Tier 2 | Distribution | 2010-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009857 | 401009650 | Molding | HFTD Tier 2 | Distribution | 2010-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009858 | 401010638 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-04-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009859 | 401010644 | High Sign | HFTD Tier 2 | Distribution | 2010-04-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009860 | 401010670 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-04-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009861 | 401010710 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-04-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009862 | 401010713 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-04-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009863 | 401010721 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-04-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009864 | 401011099 | Vis Strips | HFTD Tier 2 | Distribution | 2010-04-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009865 | 401012173 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009866 | 401013175 | Molding | HFTD Tier 2 | Distribution | 2010-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009867 | 401013479 | High Sign | HFTD Tier 2 | Distribution | 2010-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009868 | 401013525 | High Sign | HFTD Tier 2 | Distribution | 2010-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009869 | 401013527 | Molding | HFTD Tier 2 | Distribution | 2010-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009870 | 401013654 | High Sign | HFTD Tier 3 | Distribution | 2010-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009871 | 401014607 | Guy | HFTD Tier 2 | Distribution | 2010-04-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009872 | 401014629 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-04-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009873 | 401015407 | High Sign | HFTD Tier 2 | Distribution | 2010-04-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009874 | 401015814 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-04-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009875 | 401015790 | High Sign | HFTD Tier 2 | Distribution | 2010-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009876 | 401015804 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009877 | 401015823 | Guy | HFTD Tier 2 | Distribution | 2010-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009878 | 401015834 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009879 | 401015853 | High Sign | HFTD Tier 2 | Distribution | 2010-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009880 | 401015928 | High Sign | HFTD Tier 3 | Distribution | 2010-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009881 | 401015931 | High Sign | HFTD Tier 3 | Distribution | 2010-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009882 | 401016678 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009883 | 401016834 | Molding | HFTD Tier 2 | Distribution | 2010-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009884 | 401017963 | Guy | HFTD Tier 3 | Distribution | 2010-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009885 | 401017965 | High Sign | HFTD Tier 3 | Distribution | 2010-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009886 | 401017967 | High Sign | HFTD Tier 3 | Distribution | 2010-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009887 | 401018629 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009888 | 401018549 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009889 | 401018592 | Molding | HFTD Tier 2 | Distribution | 2010-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009890 | 401008005 | High Sign | HFTD Tier 3 | Distribution | 2010-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009891 | 401008502 | High Sign | HFTD Tier 3 | Distribution | 2010-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009892 | 401009510 | Molding | HFTD Tier 3 | Distribution | 2010-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009893 | 401009726 | Streetlight | HFTD Tier 2 | Distribution | 2010-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009894 | 401010880 | Molding | HFTD Tier 3 | Distribution | 2010-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009895 | 401010945 | Riser/Conduit | HFTD Tier 3 | Distribution | 2010-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009896 | 401011796 | High Sign | HFTD Tier 3 | Distribution | 2010-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009897 | 401011808 | High Sign | HFTD Tier 3 | Distribution | 2010-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009898 | 401011873 | Molding | HFTD Tier 3 | Distribution | 2010-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009899 | 401012432 | High Sign | HFTD Tier 3 | Distribution | 2010-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009900 | 401012597 | High Sign | HFTD Tier 3 | Distribution | 2010-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009901 | 401012807 | High Sign | HFTD Tier 3 | Distribution | 2010-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009902 | 401012811 | Molding | HFTD Tier 3 | Distribution | 2010-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009903 | 401012912 | High Sign | HFTD Tier 3 | Distribution | 2010-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009904 | 401013524 | High Sign | HFTD Tier 2 | Distribution | 2010-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009905 | 401013540 | High Sign | HFTD Tier 2 | Distribution | 2010-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009906 | 401610973 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009907 | 401014101 | Molding | HFTD Tier 3 | Distribution | 2010-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009908 | 401014201 | Molding | HFTD Tier 3 | Distribution | 2010-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009909 | 401085160 | Molding | HFTD Tier 3 | Distribution | 2010-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009910 | 401085164 | Molding | HFTD Tier 3 | Distribution | 2010-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009911 | 401085165 | High Sign | HFTD Tier 3 | Distribution | 2010-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009912 | 401085170 | Molding | HFTD Tier 3 | Distribution | 2010-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009913 | 401085178 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009914 | 401084918 | Molding | HFTD Tier 3 | Distribution | 2010-05-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009915 | 401084937 | High Sign | HFTD Tier 3 | Distribution | 2010-05-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009916 | 401085263 | High Sign | HFTD Tier 2 | Distribution | 2010-05-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009917 | 401085272 | High Sign | HFTD Tier 2 | Distribution | 2010-05-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009918 | 401085273 | High Sign | HFTD Tier 2 | Distribution | 2010-05-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009919 | 401085276 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2010-05-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009920 | 401085283 | High Sign | HFTD Tier 2 | Distribution | 2010-05-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009921 | 401085767 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-05-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009922 | 401085825 | Molding | HFTD Tier 2 | Distribution | 2010-05-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009923 | 401625096 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-05-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009924 | 402398621 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009925 | 402403176 | Molding | HFTD Tier 3 | Distribution | 2010-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009926 | 402400264 | Molding | HFTD Tier 3 | Distribution | 2010-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009927 | 402400341 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009928 | 402401647 | Molding | HFTD Tier 2 | Distribution | 2010-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009929 | 402401655 | High Sign | HFTD Tier 2 | Distribution | 2010-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009930 | 402401668 | Molding | HFTD Tier 2 | Distribution | 2010-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009931 | 402401681 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009932 | 402402149 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009933 | 402402184 | High Sign | HFTD Tier 3 | Distribution | 2010-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009934 | 402402188 | Molding | HFTD Tier 3 | Distribution | 2010-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009935 | 402402189 | Riser/Conduit | HFTD Tier 3 | Distribution | 2010-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009936 | 402403318 | Molding | HFTD Tier 3 | Distribution | 2010-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009937 | 402403327 | Molding | HFTD Tier 3 | Distribution | 2010-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009938 | 402402254 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009939 | 402405682 | Bond | HFTD Tier 3 | Distribution | 2010-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009940 | 402406821 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009941 | 402406860 | Insulator | HFTD Tier 2 | Distribution | 2010-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009942 | 402407919 | High Sign | HFTD Tier 2 | Distribution | 2010-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009943 | 402409339 | High Sign | HFTD Tier 2 | Distribution | 2010-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009944 | 402410798 | High Sign | HFTD Tier 2 | Distribution | 2010-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009945 | 402411911 | Molding | HFTD Tier 3 | Distribution | 2010-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009946 | 402412515 | High Sign | HFTD Tier 2 | Distribution | 2010-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009947 | 402416600 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009948 | 402416602 | High Sign | HFTD Tier 2 | Distribution | 2010-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009949 | 402417383 | High Sign | HFTD Tier 3 | Distribution | 2010-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009950 | 402417521 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009951 | 402418319 | High Sign | HFTD Tier 2 | Distribution | 2010-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009952 | 402418358 | High Sign | HFTD Tier 2 | Distribution | 2010-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009953 | 402418359 | High Sign | HFTD Tier 2 | Distribution | 2010-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009954 | 402418362 | High Sign | HFTD Tier 2 | Distribution | 2010-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009955 | 402418363 | Molding | HFTD Tier 2 | Distribution | 2010-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009956 | 402418369 | High Sign | HFTD Tier 2 | Distribution | 2010-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009957 | 402418370 | High Sign | HFTD Tier 2 | Distribution | 2010-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009958 | 402418376 | High Sign | HFTD Tier 2 | Distribution | 2010-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009959 | 402418379 | High Sign | HFTD Tier 2 | Distribution | 2010-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009960 | 402423162 | Molding | HFTD Tier 3 | Distribution | 2010-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009961 | 402424463 | Riser/Conduit | HFTD Tier 3 | Distribution | 2010-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009962 | 402421264 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009963 | 402423215 | Molding | HFTD Tier 3 | Distribution | 2010-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009964 | 402423216 | High Sign | HFTD Tier 3 | Distribution | 2010-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009965 | 402423436 | Molding | HFTD Tier 3 | Distribution | 2010-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009966 | 402423437 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009967 | 402423438 | Molding | HFTD Tier 3 | Distribution | 2010-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009968 | 402423455 | High Sign | HFTD Tier 3 | Distribution | 2010-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009969 | 402423456 | High Sign | HFTD Tier 3 | Distribution | 2010-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009970 | 402423465 | Riser/Conduit | HFTD Tier 3 | Distribution | 2010-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009971 | 402423467 | High Sign | HFTD Tier 3 | Distribution | 2010-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009972 | 402423481 | High Sign | HFTD Tier 3 | Distribution | 2010-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009973 | 402423482 | High Sign | HFTD Tier 3 | Distribution | 2010-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009974 | 402423553 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009975 | 402424105 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009976 | 402424121 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009977 | 402424759 | High Sign | HFTD Tier 3 | Distribution | 2010-06-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009978 | 402425030 | High Sign | HFTD Tier 3 | Distribution | 2010-06-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009979 | 402429442 | Molding | HFTD Tier 3 | Distribution | 2010-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009980 | 402429451 | High Sign | HFTD Tier 3 | Distribution | 2010-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009981 | 402429857 | Bond | HFTD Tier 3 | Distribution | 2010-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009982 | 402429858 | Bond | HFTD Tier 3 | Distribution | 2010-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009983 | 402429868 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009984 | 402436574 | Molding | HFTD Tier 3 | Distribution | 2010-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009985 | 402434312 | High Sign | HFTD Tier 2 | Distribution | 2010-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009986 | 402434313 | Molding | HFTD Tier 2 | Distribution | 2010-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009987 | 402434330 | Guy | HFTD Tier 2 | Distribution | 2010-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009988 | 402436621 | Molding | HFTD Tier 3 | Distribution | 2010-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009989 | 402435618 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-06-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009990 | 402435624 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-06-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009991 | 402435628 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-06-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009992 | 402435632 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-06-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009993 | 402439047 | High Sign | HFTD Tier 3 | Distribution | 2010-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009994 | 402440077 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009995 | 402442811 | Molding | HFTD Tier 3 | Distribution | 2010-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009996 | 402442809 | High Sign | HFTD Tier 3 | Distribution | 2010-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009997 | 402443154 | High Sign | HFTD Tier 3 | Distribution | 2010-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009998 | 402444186 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-06-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120009999 | 402445054 | Riser/Conduit | HFTD Tier 3 | Distribution | 2010-06-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010000 | 402445057 | Guy | HFTD Tier 3 | Distribution | 2010-06-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010001 | 402445059 | Riser/Conduit | HFTD Tier 3 | Distribution | 2010-06-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010002 | 402447126 | Molding | HFTD Tier 3 | Distribution | 2010-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010003 | 402447500 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010004 | 402451210 | High Sign | HFTD Tier 3 | Distribution | 2010-07-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010005 | 403294275 | High Sign | HFTD Tier 3 | Distribution | 2010-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010006 | 402454450 | Molding | HFTD Tier 2 | Distribution | 2010-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010007 | 402918191 | Molding | HFTD Tier 3 | Distribution | 2010-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010008 | 403009035 | High Sign | HFTD Tier 3 | Distribution | 2010-07-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010009 | 403009036 | High Sign | HFTD Tier 3 | Distribution | 2010-07-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010010 | 403009037 | Bond | HFTD Tier 3 | Distribution | 2010-07-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010011 | 403009046 | Bond | HFTD Tier 3 | Distribution | 2010-07-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010012 | 403009048 | Bond | HFTD Tier 3 | Distribution | 2010-07-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010013 | 403009062 | Bond | HFTD Tier 3 | Distribution | 2010-07-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010014 | 403009064 | Bond | HFTD Tier 3 | Distribution | 2010-07-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010015 | 403013329 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2010-07-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010016 | 403016743 | High Sign | HFTD Tier 3 | Distribution | 2010-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010017 | 403016756 | High Sign | HFTD Tier 3 | Distribution | 2010-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010018 | 403017455 | Molding | HFTD Tier 3 | Distribution | 2010-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010019 | 403016170 | Guy | HFTD Tier 2 | Distribution | 2010-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010020 | 403030616 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010021 | 403031628 | High Sign | HFTD Tier 2 | Distribution | 2010-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010022 | 403031630 | High Sign | HFTD Tier 2 | Distribution | 2010-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010023 | 403035057 | Molding | HFTD Tier 3 | Distribution | 2010-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010024 | 403035062 | Bond | HFTD Tier 3 | Distribution | 2010-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010025 | 403035456 | High Sign | HFTD Tier 2 | Distribution | 2010-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010026 | 403035457 | High Sign | HFTD Tier 2 | Distribution | 2010-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010027 | 403035703 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010028 | 403035722 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010029 | 403035724 | High Sign | HFTD Tier 2 | Distribution | 2010-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010030 | 403037744 | High Sign | HFTD Tier 2 | Distribution | 2010-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010031 | 403037745 | High Sign | HFTD Tier 2 | Distribution | 2010-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010032 | 403037746 | High Sign | HFTD Tier 2 | Distribution | 2010-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010033 | 403037747 | High Sign | HFTD Tier 2 | Distribution | 2010-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010034 | 403037756 | High Sign | HFTD Tier 2 | Distribution | 2010-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010035 | 403037758 | High Sign | HFTD Tier 2 | Distribution | 2010-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010036 | 403037766 | High Sign | HFTD Tier 2 | Distribution | 2010-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010037 | 403037770 | High Sign | HFTD Tier 2 | Distribution | 2010-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010038 | 403037771 | High Sign | HFTD Tier 2 | Distribution | 2010-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010039 | 403040222 | Molding | HFTD Tier 3 | Distribution | 2010-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010040 | 403040998 | Molding | HFTD Tier 3 | Distribution | 2010-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010041 | 403042604 | Bond | HFTD Tier 3 | Distribution | 2010-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010042 | 403042610 | High Sign | HFTD Tier 3 | Distribution | 2010-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010043 | 403042613 | High Sign | HFTD Tier 3 | Distribution | 2010-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010044 | 403042831 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010045 | 403042841 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010046 | 403042890 | High Sign | HFTD Tier 2 | Distribution | 2010-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010047 | 403042893 | High Sign | HFTD Tier 2 | Distribution | 2010-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010048 | 403042900 | High Sign | HFTD Tier 2 | Distribution | 2010-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010049 | 403294302 | High Sign | HFTD Tier 2 | Distribution | 2010-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010050 | 403043892 | Guy | HFTD Tier 2 | Distribution | 2010-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010051 | 403043895 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010052 | 403044198 | High Sign | HFTD Tier 3 | Distribution | 2010-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010053 | 403044232 | High Sign | HFTD Tier 3 | Distribution | 2010-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010054 | 403044402 | Molding | HFTD Tier 2 | Distribution | 2010-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010055 | 403044482 | Bond | HFTD Tier 3 | Distribution | 2010-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010056 | 403044617 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010057 | 403044630 | Molding | HFTD Tier 2 | Distribution | 2010-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010058 | 403044631 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010059 | 403044637 | High Sign | HFTD Tier 3 | Distribution | 2010-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010060 | 403050746 | High Sign | HFTD Tier 2 | Distribution | 2010-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010061 | 403050747 | High Sign | HFTD Tier 2 | Distribution | 2010-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010062 | 403050753 | High Sign | HFTD Tier 2 | Distribution | 2010-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010063 | 403050754 | High Sign | HFTD Tier 2 | Distribution | 2010-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010064 | 403050755 | High Sign | HFTD Tier 2 | Distribution | 2010-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010065 | 403050763 | High Sign | HFTD Tier 2 | Distribution | 2010-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010066 | 403050766 | High Sign | HFTD Tier 2 | Distribution | 2010-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010067 | 403050768 | High Sign | HFTD Tier 2 | Distribution | 2010-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010068 | 403050769 | High Sign | HFTD Tier 2 | Distribution | 2010-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010069 | 403045445 | High Sign | HFTD Tier 3 | Distribution | 2010-07-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010070 | 403045449 | Molding | HFTD Tier 3 | Distribution | 2010-07-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010071 | 403045481 | Riser/Conduit | HFTD Tier 3 | Distribution | 2010-07-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010072 | 403045501 | Molding | HFTD Tier 3 | Distribution | 2010-07-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010073 | 403045543 | Molding | HFTD Tier 2 | Distribution | 2010-07-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010074 | 403050749 | High Sign | HFTD Tier 2 | Distribution | 2010-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010075 | 403050759 | High Sign | HFTD Tier 2 | Distribution | 2010-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010076 | 403051685 | Molding | HFTD Tier 3 | Distribution | 2010-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010077 | 403051751 | High Sign | HFTD Tier 3 | Distribution | 2010-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010078 | 403051753 | High Sign | HFTD Tier 3 | Distribution | 2010-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010079 | 403051980 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-08-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010080 | 403051983 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-08-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010081 | 403052673 | High Sign | HFTD Tier 2 | Distribution | 2010-08-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010082 | 403053859 | High Sign | HFTD Tier 2 | Distribution | 2010-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010083 | 403053870 | High Sign | HFTD Tier 2 | Distribution | 2010-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010084 | 403054037 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2010-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010085 | 403055796 | High Sign | HFTD Tier 2 | Distribution | 2010-08-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010086 | 403055798 | High Sign | HFTD Tier 2 | Distribution | 2010-08-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010087 | 403055805 | High Sign | HFTD Tier 2 | Distribution | 2010-08-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010088 | 403055814 | High Sign | HFTD Tier 2 | Distribution | 2010-08-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010089 | 403055815 | High Sign | HFTD Tier 2 | Distribution | 2010-08-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010090 | 403056857 | High Sign | HFTD Tier 3 | Distribution | 2010-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010091 | 403056872 | Molding | HFTD Tier 3 | Distribution | 2010-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010092 | 403057077 | High Sign | HFTD Tier 3 | Distribution | 2010-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010093 | 403057088 | High Sign | HFTD Tier 2 | Distribution | 2010-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010094 | 403057090 | Guy | HFTD Tier 3 | Distribution | 2010-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010095 | 403057091 | High Sign | HFTD Tier 3 | Distribution | 2010-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010096 | 403057102 | High Sign | HFTD Tier 2 | Distribution | 2010-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010097 | 403058856 | Molding | HFTD Tier 3 | Distribution | 2010-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010098 | 403058861 | Guy | HFTD Tier 3 | Distribution | 2010-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010099 | 403058067 | Molding | HFTD Tier 3 | Distribution | 2010-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010100 | 403109545 | High Sign | HFTD Tier 3 | Distribution | 2010-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010101 | 403058896 | Molding | HFTD Tier 3 | Distribution | 2010-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010102 | 403059023 | High Sign | HFTD Tier 3 | Distribution | 2010-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010103 | 403059180 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010104 | 403059196 | Riser/Conduit | HFTD Tier 3 | Distribution | 2010-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010105 | 403060024 | Guy | HFTD Tier 2 | Distribution | 2010-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010106 | 403060027 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2010-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010107 | 403062014 | High Sign | HFTD Tier 2 | Distribution | 2010-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010108 | 403062020 | High Sign | HFTD Tier 2 | Distribution | 2010-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010109 | 403062021 | High Sign | HFTD Tier 2 | Distribution | 2010-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010110 | 403062025 | High Sign | HFTD Tier 2 | Distribution | 2010-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010111 | 403062026 | High Sign | HFTD Tier 2 | Distribution | 2010-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010112 | 403062033 | High Sign | HFTD Tier 2 | Distribution | 2010-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010113 | 403062034 | High Sign | HFTD Tier 2 | Distribution | 2010-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010114 | 403062059 | Molding | HFTD Tier 3 | Distribution | 2010-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010115 | 403062113 | Guy | HFTD Tier 3 | Distribution | 2010-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010116 | 403062129 | High Sign | HFTD Tier 3 | Distribution | 2010-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010117 | 403062141 | High Sign | HFTD Tier 3 | Distribution | 2010-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010118 | 403063122 | Molding | HFTD Tier 3 | Distribution | 2010-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010119 | 403064497 | High Sign | HFTD Tier 3 | Distribution | 2010-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010120 | 403065686 | High Sign | HFTD Tier 3 | Distribution | 2010-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010121 | 403066384 | High Sign | HFTD Tier 3 | Distribution | 2010-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010122 | 403066386 | High Sign | HFTD Tier 3 | Distribution | 2010-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010123 | 403066387 | High Sign | HFTD Tier 3 | Distribution | 2010-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010124 | 403066388 | High Sign | HFTD Tier 3 | Distribution | 2010-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010125 | 403066395 | High Sign | HFTD Tier 3 | Distribution | 2010-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010126 | 403066555 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010127 | 403066667 | High Sign | HFTD Tier 3 | Distribution | 2010-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010128 | 403067239 | Bond | HFTD Tier 3 | Distribution | 2010-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010129 | 403067769 | Molding | HFTD Tier 3 | Distribution | 2010-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010130 | 403067775 | Molding | HFTD Tier 3 | Distribution | 2010-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010131 | 403067947 | Guy | HFTD Tier 3 | Distribution | 2010-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010132 | 403068701 | High Sign | HFTD Tier 3 | Distribution | 2010-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010133 | 403080951 | Molding | HFTD Tier 2 | Distribution | 2010-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010134 | 403072972 | Guy | HFTD Tier 3 | Distribution | 2010-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010135 | 403072984 | Guy | HFTD Tier 3 | Distribution | 2010-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010136 | 403073941 | Guy | HFTD Tier 3 | Distribution | 2010-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010137 | 403074762 | Molding | HFTD Tier 2 | Distribution | 2010-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010138 | 403077407 | High Sign | HFTD Tier 3 | Distribution | 2010-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010139 | 403077411 | High Sign | HFTD Tier 3 | Distribution | 2010-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010140 | 403076135 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2010-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010141 | 403076287 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010142 | 403076724 | High Sign | HFTD Tier 3 | Distribution | 2010-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010143 | 403076753 | High Sign | HFTD Tier 3 | Distribution | 2010-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010144 | 403077090 | High Sign | HFTD Tier 3 | Distribution | 2010-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010145 | 403077091 | Bond | HFTD Tier 3 | Distribution | 2010-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010146 | 403077192 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010147 | 403077283 | High Sign | HFTD Tier 3 | Distribution | 2010-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010148 | 403077291 | Molding | HFTD Tier 3 | Distribution | 2010-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010149 | 403078367 | Molding | HFTD Tier 3 | Distribution | 2010-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010150 | 403078679 | Guy | HFTD Tier 3 | Distribution | 2010-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010151 | 403078720 | High Sign | HFTD Tier 3 | Distribution | 2010-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010152 | 403078725 | Molding | HFTD Tier 3 | Distribution | 2010-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010153 | 403078856 | Molding | HFTD Tier 3 | Distribution | 2010-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010154 | 403081043 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010155 | 403081099 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010156 | 403081106 | Molding | HFTD Tier 3 | Distribution | 2010-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010157 | 403086946 | Molding | HFTD Tier 3 | Distribution | 2010-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010158 | 403079761 | Molding | HFTD Tier 2 | Distribution | 2010-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010159 | 403079762 | High Sign | HFTD Tier 2 | Distribution | 2010-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010160 | 403079776 | High Sign | HFTD Tier 2 | Distribution | 2010-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010161 | 403079890 | High Sign | HFTD Tier 3 | Distribution | 2010-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010162 | 403081473 | Molding | HFTD Tier 2 | Distribution | 2010-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010163 | 403082370 | High Sign | HFTD Tier 2 | Distribution | 2010-08-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010164 | 403082511 | High Sign | HFTD Tier 2 | Distribution | 2010-08-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010165 | 403094856 | Molding | HFTD Tier 2 | Distribution | 2010-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010166 | 403094869 | Molding | HFTD Tier 3 | Distribution | 2010-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010167 | 403094888 | Molding | HFTD Tier 2 | Distribution | 2010-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010168 | 403094960 | Molding | HFTD Tier 2 | Distribution | 2010-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010169 | 403095001 | Molding | HFTD Tier 2 | Distribution | 2010-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010170 | 403095108 | Molding | HFTD Tier 2 | Distribution | 2010-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010171 | 403087080 | Riser/Conduit | HFTD Tier 2 | Distribution | 2010-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010172 | 403087177 | Guy | HFTD Tier 2 | Distribution | 2010-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010173 | 403087182 | Ground | HFTD Tier 2 | Distribution | 2010-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010174 | 403087188 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010175 | 403087194 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2010-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010176 | 403088869 | Bond | HFTD Tier 2 | Distribution | 2010-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010177 | 403088872 | Bond | HFTD Tier 2 | Distribution | 2010-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010178 | 403088880 | Bond | HFTD Tier 2 | Distribution | 2010-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010179 | 403088881 | Molding | HFTD Tier 2 | Distribution | 2010-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010180 | 403093980 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010181 | 403093981 | High Sign | HFTD Tier 3 | Distribution | 2010-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010182 | 403093983 | Molding | HFTD Tier 3 | Distribution | 2010-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010183 | 403093985 | High Sign | HFTD Tier 3 | Distribution | 2010-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010184 | 403089434 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010185 | 403090473 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2010-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010186 | 403090978 | Molding | HFTD Tier 2 | Distribution | 2010-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010187 | 403092417 | Bond | HFTD Tier 2 | Distribution | 2010-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010188 | 403092418 | Bond | HFTD Tier 2 | Distribution | 2010-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010189 | 403094031 | Molding | HFTD Tier 3 | Distribution | 2010-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010190 | 403091918 | High Sign | HFTD Tier 3 | Distribution | 2010-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010191 | 403091919 | Guy | HFTD Tier 3 | Distribution | 2010-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010192 | 403092097 | Molding | HFTD Tier 2 | Distribution | 2010-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010193 | 403092452 | High Sign | HFTD Tier 3 | Distribution | 2010-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010194 | 403092462 | High Sign | HFTD Tier 3 | Distribution | 2010-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010195 | 403093119 | High Sign | HFTD Tier 2 | Distribution | 2010-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010196 | 403094053 | Molding | HFTD Tier 3 | Distribution | 2010-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010197 | 403094058 | High Sign | HFTD Tier 3 | Distribution | 2010-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010198 | 403094133 | Molding | HFTD Tier 3 | Distribution | 2010-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010199 | 403093650 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-08-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010200 | 403094063 | Molding | HFTD Tier 3 | Distribution | 2010-08-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010201 | 403094630 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-08-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010202 | 403095830 | Guy | HFTD Tier 3 | Distribution | 2010-08-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010203 | 403096182 | High Sign | HFTD Tier 3 | Distribution | 2010-08-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010204 | 403096369 | Molding | HFTD Tier 2 | Distribution | 2010-08-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010205 | 403096413 | Guy | HFTD Tier 2 | Distribution | 2010-08-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010206 | 403096423 | Ground | HFTD Tier 2 | Distribution | 2010-08-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010207 | 403096446 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-08-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010208 | 403099554 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2010-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010209 | 403106870 | High Sign | HFTD Tier 3 | Distribution | 2010-08-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010210 | 403102782 | Molding | HFTD Tier 3 | Distribution | 2010-08-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010211 | 403102816 | High Sign | HFTD Tier 3 | Distribution | 2010-08-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010212 | 403103098 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-08-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010213 | 403103244 | Guy | HFTD Tier 3 | Distribution | 2010-08-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010214 | 403106907 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-08-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010215 | 403106997 | Molding | HFTD Tier 3 | Distribution | 2010-08-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010216 | 403106923 | Molding | HFTD Tier 2 | Distribution | 2010-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010217 | 403106777 | High Sign | HFTD Tier 2 | Distribution | 2010-09-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010218 | 403106938 | Molding | HFTD Tier 3 | Distribution | 2010-09-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010219 | 403106939 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-09-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010220 | 403106955 | Molding | HFTD Tier 3 | Distribution | 2010-09-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010221 | 403107025 | Molding | HFTD Tier 3 | Distribution | 2010-09-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010222 | 403107066 | Molding | HFTD Tier 3 | Distribution | 2010-09-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010223 | 403107298 | High Sign | HFTD Tier 3 | Distribution | 2010-09-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010224 | 403107308 | Crossarm | HFTD Tier 3 | Distribution | 2010-09-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010225 | 403107319 | High Sign | HFTD Tier 3 | Distribution | 2010-09-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010226 | 403107330 | Molding | HFTD Tier 3 | Distribution | 2010-09-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010227 | 403107878 | Molding | HFTD Tier 3 | Distribution | 2010-09-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010228 | 403110067 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-09-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010229 | 403110074 | Molding | HFTD Tier 2 | Distribution | 2010-09-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010230 | 403110082 | High Sign | HFTD Tier 2 | Distribution | 2010-09-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010231 | 403110141 | Molding | HFTD Tier 2 | Distribution | 2010-09-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010232 | 403110430 | Molding | HFTD Tier 3 | Distribution | 2010-09-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010233 | 403116187 | Guy | HFTD Tier 3 | Distribution | 2010-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010234 | 403116213 | Molding | HFTD Tier 3 | Distribution | 2010-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010235 | 403116260 | High Sign | HFTD Tier 3 | Distribution | 2010-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010236 | 403116474 | Molding | HFTD Tier 3 | Distribution | 2010-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010237 | 403113849 | Vis Strips | HFTD Tier 3 | Distribution | 2010-09-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010238 | 403113850 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-09-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010239 | 403114623 | Guy | HFTD Tier 3 | Distribution | 2010-09-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010240 | 403119958 | Molding | HFTD Tier 2 | Distribution | 2010-09-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010241 | 403116160 | Molding | HFTD Tier 3 | Distribution | 2010-09-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010242 | 403116165 | High Sign | HFTD Tier 3 | Distribution | 2010-09-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010243 | 403117182 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-09-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010244 | 403117185 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2010-09-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010245 | 403117226 | High Sign | HFTD Tier 3 | Distribution | 2010-09-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010246 | 403117245 | High Sign | HFTD Tier 3 | Distribution | 2010-09-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010247 | 403119895 | High Sign | HFTD Tier 2 | Distribution | 2010-09-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010248 | 403119602 | Molding | HFTD Tier 3 | Distribution | 2010-09-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010249 | 403119606 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-09-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010250 | 403122534 | Molding | HFTD Tier 2 | Distribution | 2010-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010251 | 403122537 | Molding | HFTD Tier 2 | Distribution | 2010-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010252 | 403126066 | Guy | HFTD Tier 2 | Distribution | 2010-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010253 | 403131718 | High Sign | HFTD Tier 2 | Distribution | 2010-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010254 | 403126093 | High Sign | HFTD Tier 2 | Distribution | 2010-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010255 | 403126213 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010256 | 403131698 | Molding | HFTD Tier 2 | Distribution | 2010-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010257 | 403131712 | High Sign | HFTD Tier 2 | Distribution | 2010-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010258 | 403132101 | High Sign | HFTD Tier 2 | Distribution | 2010-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010259 | 403128573 | High Sign | HFTD Tier 2 | Distribution | 2010-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010260 | 403128574 | High Sign | HFTD Tier 2 | Distribution | 2010-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010261 | 403128605 | High Sign | HFTD Tier 2 | Distribution | 2010-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010262 | 403128609 | High Sign | HFTD Tier 2 | Distribution | 2010-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010263 | 403128612 | High Sign | HFTD Tier 2 | Distribution | 2010-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010264 | 403128615 | High Sign | HFTD Tier 2 | Distribution | 2010-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010265 | 403128620 | High Sign | HFTD Tier 2 | Distribution | 2010-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010266 | 403128623 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010267 | 403128631 | Molding | HFTD Tier 2 | Distribution | 2010-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010268 | 403128667 | Crossarm | HFTD Tier 2 | Distribution | 2010-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010269 | 403131334 | High Sign | HFTD Tier 2 | Distribution | 2010-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010270 | 403131372 | Molding | HFTD Tier 2 | Distribution | 2010-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010271 | 403131419 | Molding | HFTD Tier 2 | Distribution | 2010-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010272 | 403131732 | Molding | HFTD Tier 2 | Distribution | 2010-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010273 | 403131737 | High Sign | HFTD Tier 2 | Distribution | 2010-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010274 | 403131784 | High Sign | HFTD Tier 2 | Distribution | 2010-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010275 | 403132127 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2010-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010276 | 403131421 | Molding | HFTD Tier 3 | Distribution | 2010-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010277 | 403131482 | High Sign | HFTD Tier 2 | Distribution | 2010-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010278 | 403131513 | Molding | HFTD Tier 2 | Distribution | 2010-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010279 | 403131547 | High Sign | HFTD Tier 2 | Distribution | 2010-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010280 | 403131548 | High Sign | HFTD Tier 2 | Distribution | 2010-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010281 | 403131557 | High Sign | HFTD Tier 2 | Distribution | 2010-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010282 | 403131585 | High Sign | HFTD Tier 2 | Distribution | 2010-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010283 | 403131593 | Molding | HFTD Tier 2 | Distribution | 2010-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010284 | 403131781 | Riser/Conduit | HFTD Tier 2 | Distribution | 2010-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010285 | 403131811 | High Sign | HFTD Tier 2 | Distribution | 2010-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010286 | 403131813 | High Sign | HFTD Tier 2 | Distribution | 2010-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010287 | 403131814 | High Sign | HFTD Tier 2 | Distribution | 2010-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010288 | 403132108 | High Sign | HFTD Tier 2 | Distribution | 2010-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010289 | 403132489 | Guy | HFTD Tier 3 | Distribution | 2010-09-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010290 | 403132515 | Guy | HFTD Tier 3 | Distribution | 2010-09-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010291 | 403132995 | High Sign | HFTD Tier 2 | Distribution | 2010-09-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010292 | 403133641 | Molding | HFTD Tier 3 | Distribution | 2010-09-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010293 | 403133663 | High Sign | HFTD Tier 3 | Distribution | 2010-09-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010294 | 403134501 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-09-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010295 | 403134505 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-09-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010296 | 403134511 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-09-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010297 | 403134512 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-09-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010298 | 403134537 | High Sign | HFTD Tier 2 | Distribution | 2010-09-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010299 | 403134544 | High Sign | HFTD Tier 2 | Distribution | 2010-09-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010300 | 403134569 | Bond | HFTD Tier 2 | Distribution | 2010-09-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010301 | 403134578 | High Sign | HFTD Tier 2 | Distribution | 2010-09-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010302 | 403134610 | High Sign | HFTD Tier 2 | Distribution | 2010-09-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010303 | 403134646 | High Sign | HFTD Tier 2 | Distribution | 2010-09-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010304 | 403134647 | Molding | HFTD Tier 2 | Distribution | 2010-09-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010305 | 403136317 | Molding | HFTD Tier 3 | Distribution | 2010-09-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010306 | 403136679 | High Sign | HFTD Tier 3 | Distribution | 2010-09-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010307 | 403136681 | Molding | HFTD Tier 3 | Distribution | 2010-09-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010308 | 403137675 | High Sign | HFTD Tier 3 | Distribution | 2010-09-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010309 | 403138656 | Molding | HFTD Tier 3 | Distribution | 2010-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010310 | 403138657 | High Sign | HFTD Tier 3 | Distribution | 2010-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010311 | 403138880 | Molding | HFTD Tier 3 | Distribution | 2010-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010312 | 403138900 | Molding | HFTD Tier 3 | Distribution | 2010-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010313 | 403139997 | Riser/Conduit | HFTD Tier 2 | Distribution | 2010-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010314 | 403141234 | Molding | HFTD Tier 3 | Distribution | 2010-09-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010315 | 403141455 | Molding | HFTD Tier 3 | Distribution | 2010-09-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010316 | 403151551 | High Sign | HFTD Tier 3 | Distribution | 2010-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010317 | 403151562 | Molding | HFTD Tier 2 | Distribution | 2010-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010318 | 403151571 | High Sign | HFTD Tier 2 | Distribution | 2010-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010319 | 403151600 | Molding | HFTD Tier 2 | Distribution | 2010-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010320 | 403153199 | Molding | HFTD Tier 3 | Distribution | 2010-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010321 | 403153206 | High Sign | HFTD Tier 3 | Distribution | 2010-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010322 | 403154000 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010323 | 403155395 | Molding | HFTD Tier 3 | Distribution | 2010-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010324 | 403155405 | High Sign | HFTD Tier 3 | Distribution | 2010-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010325 | 403155537 | Molding | HFTD Tier 2 | Distribution | 2010-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010326 | 403156089 | Molding | HFTD Tier 3 | Distribution | 2010-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010327 | 403156125 | High Sign | HFTD Tier 3 | Distribution | 2010-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010328 | 403156128 | High Sign | HFTD Tier 3 | Distribution | 2010-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010329 | 403156135 | High Sign | HFTD Tier 3 | Distribution | 2010-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010330 | 403157289 | Molding | HFTD Tier 3 | Distribution | 2010-10-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010331 | 403157487 | Molding | HFTD Tier 3 | Distribution | 2010-10-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010332 | 403163059 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-10-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010333 | 403163075 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-10-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010334 | 403163799 | Molding | HFTD Tier 3 | Distribution | 2010-10-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010335 | 403163835 | Guy | HFTD Tier 3 | Distribution | 2010-10-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010336 | 403168456 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010337 | 403168490 | Molding | HFTD Tier 2 | Distribution | 2010-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010338 | 403168511 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010339 | 403170438 | High Sign | HFTD Tier 2 | Distribution | 2010-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010340 | 403170441 | Molding | HFTD Tier 2 | Distribution | 2010-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010341 | 403171808 | Molding | HFTD Tier 2 | Distribution | 2010-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010342 | 403171809 | Molding | HFTD Tier 2 | Distribution | 2010-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010343 | 403171829 | High Sign | HFTD Tier 2 | Distribution | 2010-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010344 | 403171833 | High Sign | HFTD Tier 2 | Distribution | 2010-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010345 | 403172301 | Molding | HFTD Tier 2 | Distribution | 2010-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010346 | 403172302 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010347 | 403172424 | Molding | HFTD Tier 3 | Distribution | 2010-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010348 | 403172426 | Molding | HFTD Tier 3 | Distribution | 2010-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010349 | 403172430 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010350 | 403172432 | High Sign | HFTD Tier 3 | Distribution | 2010-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010351 | 403172437 | High Sign | HFTD Tier 3 | Distribution | 2010-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010352 | 403172438 | Molding | HFTD Tier 3 | Distribution | 2010-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010353 | 403173704 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010354 | 403174004 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010355 | 403174663 | High Sign | HFTD Tier 2 | Distribution | 2010-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010356 | 403174681 | High Sign | HFTD Tier 2 | Distribution | 2010-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010357 | 403174536 | Molding | HFTD Tier 2 | Distribution | 2010-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010358 | 403174538 | High Sign | HFTD Tier 2 | Distribution | 2010-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010359 | 403174553 | Molding | HFTD Tier 2 | Distribution | 2010-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010360 | 403174556 | High Sign | HFTD Tier 2 | Distribution | 2010-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010361 | 403174558 | Molding | HFTD Tier 2 | Distribution | 2010-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010362 | 403174571 | High Sign | HFTD Tier 2 | Distribution | 2010-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010363 | 403175061 | High Sign | HFTD Tier 3 | Distribution | 2010-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010364 | 403180304 | Guy | HFTD Tier 3 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010365 | 403181757 | Molding | HFTD Tier 3 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010366 | 403181774 | Molding | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010367 | 403181775 | High Sign | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010368 | 403181776 | High Sign | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010369 | 403181777 | Molding | HFTD Tier 3 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010370 | 403181778 | Molding | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010371 | 403181782 | Ground | HFTD Tier 3 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010372 | 403181785 | Molding | HFTD Tier 3 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010373 | 403181792 | Molding | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010374 | 403181793 | Molding | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010375 | 403181796 | Molding | HFTD Tier 3 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010376 | 403181797 | Molding | HFTD Tier 3 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010377 | 403181804 | Molding | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010378 | 403181811 | Molding | HFTD Tier 3 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010379 | 403181812 | Molding | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010380 | 403183292 | High Sign | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010381 | 403183293 | High Sign | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010382 | 403183294 | High Sign | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010383 | 403183296 | High Sign | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010384 | 403183298 | High Sign | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010385 | 403183299 | High Sign | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010386 | 403183303 | High Sign | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010387 | 403183304 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010388 | 403183306 | High Sign | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010389 | 403183307 | High Sign | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010390 | 403183308 | High Sign | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010391 | 403183309 | High Sign | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010392 | 403183320 | High Sign | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010393 | 403183321 | High Sign | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010394 | 403183322 | Molding | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010395 | 403183323 | High Sign | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010396 | 403183326 | Molding | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010397 | 403194868 | Molding | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010398 | 403194882 | High Sign | HFTD Tier 2 | Distribution | 2010-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010399 | 403182155 | Molding | HFTD Tier 3 | Distribution | 2010-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010400 | 403182162 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010401 | 403182164 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010402 | 403182165 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010403 | 403182187 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010404 | 403182189 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010405 | 403182196 | Molding | HFTD Tier 3 | Distribution | 2010-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010406 | 403182224 | Guy | HFTD Tier 3 | Distribution | 2010-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010407 | 403182257 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010408 | 403183337 | Molding | HFTD Tier 2 | Distribution | 2010-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010409 | 403183339 | High Sign | HFTD Tier 2 | Distribution | 2010-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010410 | 403183345 | Guy | HFTD Tier 2 | Distribution | 2010-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010411 | 403183358 | High Sign | HFTD Tier 2 | Distribution | 2010-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010412 | 403183367 | High Sign | HFTD Tier 2 | Distribution | 2010-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010413 | 403183894 | High Sign | HFTD Tier 3 | Distribution | 2010-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010414 | 403183933 | Molding | HFTD Tier 3 | Distribution | 2010-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010415 | 403183949 | High Sign | HFTD Tier 3 | Distribution | 2010-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010416 | 403183957 | Molding | HFTD Tier 3 | Distribution | 2010-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010417 | 403183959 | Molding | HFTD Tier 3 | Distribution | 2010-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010418 | 403183962 | Molding | HFTD Tier 3 | Distribution | 2010-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010419 | 403194830 | Molding | HFTD Tier 2 | Distribution | 2010-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010420 | 403184459 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010421 | 403184473 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010422 | 403184599 | Molding | HFTD Tier 3 | Distribution | 2010-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010423 | 403184617 | High Sign | HFTD Tier 3 | Distribution | 2010-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010424 | 403184619 | Molding | HFTD Tier 3 | Distribution | 2010-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010425 | 403184685 | Molding | HFTD Tier 3 | Distribution | 2010-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010426 | 403184686 | Molding | HFTD Tier 3 | Distribution | 2010-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010427 | 403184689 | Guy | HFTD Tier 3 | Distribution | 2010-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010428 | 403186006 | High Sign | HFTD Tier 2 | Distribution | 2010-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010429 | 403186014 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2010-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010430 | 403195027 | Molding | HFTD Tier 2 | Distribution | 2010-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010431 | 403186587 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-10-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010432 | 403187612 | Molding | HFTD Tier 2 | Distribution | 2010-10-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010433 | 403195215 | High Sign | HFTD Tier 2 | Distribution | 2010-10-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010434 | 403195352 | Molding | HFTD Tier 2 | Distribution | 2010-10-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010435 | 403195928 | Molding | HFTD Tier 2 | Distribution | 2010-10-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010436 | 403202250 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010437 | 403202285 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2010-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010438 | 403203835 | High Sign | HFTD Tier 2 | Distribution | 2010-10-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010439 | 403204096 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-10-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010440 | 403204355 | Riser/Conduit | HFTD Tier 2 | Distribution | 2010-10-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010441 | 403205251 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-10-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010442 | 403211553 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-10-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010443 | 403211859 | Guy | HFTD Tier 2 | Distribution | 2010-10-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010444 | 403213033 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-10-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010445 | 403216742 | Molding | HFTD Tier 2 | Distribution | 2010-10-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010446 | 403216747 | High Sign | HFTD Tier 2 | Distribution | 2010-10-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010447 | 403216758 | High Sign | HFTD Tier 2 | Distribution | 2010-10-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010448 | 403216759 | High Sign | HFTD Tier 2 | Distribution | 2010-10-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010449 | 403215293 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010450 | 403215297 | Molding | HFTD Tier 2 | Distribution | 2010-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010451 | 403215306 | Molding | HFTD Tier 2 | Distribution | 2010-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010452 | 403215338 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010453 | 403216678 | Guy | HFTD Tier 2 | Distribution | 2010-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010454 | 403216783 | High Sign | HFTD Tier 2 | Distribution | 2010-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010455 | 403216795 | Molding | HFTD Tier 2 | Distribution | 2010-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010456 | 403218125 | Guy | HFTD Tier 3 | Distribution | 2010-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010457 | 403218144 | High Sign | HFTD Tier 3 | Distribution | 2010-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010458 | 403218817 | High Sign | HFTD Tier 2 | Distribution | 2010-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010459 | 403218842 | High Sign | HFTD Tier 2 | Distribution | 2010-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010460 | 403218846 | High Sign | HFTD Tier 2 | Distribution | 2010-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010461 | 403218870 | Riser/Conduit | HFTD Tier 2 | Distribution | 2010-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010462 | 403220039 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010463 | 403220081 | Guy | HFTD Tier 2 | Distribution | 2010-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010464 | 403222040 | High Sign | HFTD Tier 2 | Distribution | 2010-10-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010465 | 403222305 | Guy | HFTD Tier 3 | Distribution | 2010-10-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010466 | 403225708 | Molding | HFTD Tier 2 | Distribution | 2010-11-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010467 | 403225709 | High Sign | HFTD Tier 2 | Distribution | 2010-11-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010468 | 403227772 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-11-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010469 | 403227784 | High Sign | HFTD Tier 3 | Distribution | 2010-11-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010470 | 403229432 | Molding | HFTD Tier 2 | Distribution | 2010-11-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010471 | 403229955 | Riser/Conduit | HFTD Tier 2 | Distribution | 2010-11-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010472 | 403229960 | Molding | HFTD Tier 2 | Distribution | 2010-11-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010473 | 403230199 | Molding | HFTD Tier 3 | Distribution | 2010-11-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010474 | 403230394 | High Sign | HFTD Tier 2 | Distribution | 2010-11-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010475 | 403230887 | Molding | HFTD Tier 3 | Distribution | 2010-11-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010476 | 403231698 | Ground | HFTD Tier 3 | Distribution | 2010-11-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010477 | 403231742 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-11-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010478 | 403231963 | Molding | HFTD Tier 3 | Distribution | 2010-11-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010479 | 403231966 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-11-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010480 | 403231968 | Molding | HFTD Tier 3 | Distribution | 2010-11-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010481 | 403233794 | Molding | HFTD Tier 2 | Distribution | 2010-11-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010482 | 403238556 | Molding | HFTD Tier 3 | Distribution | 2010-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010483 | 403238600 | Molding | HFTD Tier 3 | Distribution | 2010-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010484 | 403238692 | Molding | HFTD Tier 2 | Distribution | 2010-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010485 | 403240439 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2010-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010486 | 403240450 | High Sign | HFTD Tier 3 | Distribution | 2010-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010487 | 403240598 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010488 | 403240709 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010489 | 403240717 | Molding | HFTD Tier 3 | Distribution | 2010-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010490 | 403242373 | Molding | HFTD Tier 3 | Distribution | 2010-11-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010491 | 403243289 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2010-11-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010492 | 403244327 | Guy | HFTD Tier 3 | Distribution | 2010-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010493 | 403248242 | Molding | HFTD Tier 2 | Distribution | 2010-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010494 | 403248448 | Molding | HFTD Tier 3 | Distribution | 2010-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010495 | 403248632 | Crossarm | HFTD Tier 3 | Distribution | 2010-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010496 | 403250854 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2010-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010497 | 403251914 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-11-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010498 | 403253517 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-11-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010499 | 403253610 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-11-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010500 | 403255716 | Molding | HFTD Tier 3 | Distribution | 2010-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010501 | 403272810 | Molding | HFTD Tier 3 | Distribution | 2010-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010502 | 403273193 | High Sign | HFTD Tier 3 | Distribution | 2010-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010503 | 403284564 | High Sign | HFTD Tier 2 | Distribution | 2010-11-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010504 | 403284565 | High Sign | HFTD Tier 2 | Distribution | 2010-11-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010505 | 403284570 | High Sign | HFTD Tier 2 | Distribution | 2010-11-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010506 | 403284572 | High Sign | HFTD Tier 2 | Distribution | 2010-11-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010507 | 403284573 | High Sign | HFTD Tier 2 | Distribution | 2010-11-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010508 | 403284576 | High Sign | HFTD Tier 2 | Distribution | 2010-11-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010509 | 403284578 | High Sign | HFTD Tier 2 | Distribution | 2010-11-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010510 | 403284633 | High Sign | HFTD Tier 2 | Distribution | 2010-11-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010511 | 403285512 | Molding | HFTD Tier 3 | Distribution | 2010-11-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010512 | 403285531 | Ground | HFTD Tier 3 | Distribution | 2010-11-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010513 | 403285542 | Molding | HFTD Tier 3 | Distribution | 2010-11-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010514 | 403285912 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-11-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010515 | 403285913 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-11-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010516 | 403285914 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-11-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010517 | 403288629 | High Sign | HFTD Tier 2 | Distribution | 2010-11-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010518 | 403288634 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-11-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010519 | 403291418 | Guy | HFTD Tier 3 | Distribution | 2010-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010520 | 403291434 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010521 | 403291445 | Molding | HFTD Tier 2 | Distribution | 2010-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010522 | 403291446 | High Sign | HFTD Tier 2 | Distribution | 2010-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010523 | 403291459 | High Sign | HFTD Tier 3 | Distribution | 2010-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010524 | 403291469 | High Sign | HFTD Tier 2 | Distribution | 2010-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010525 | 403293913 | Riser/Conduit | HFTD Tier 3 | Distribution | 2010-12-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010526 | 403294327 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-12-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010527 | 403294328 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-12-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010528 | 403294331 | High Sign | HFTD Tier 2 | Distribution | 2010-12-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010529 | 403294333 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-12-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010530 | 403294335 | High Sign | HFTD Tier 2 | Distribution | 2010-12-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010531 | 403294342 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-12-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010532 | 403294347 | High Sign | HFTD Tier 2 | Distribution | 2010-12-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010533 | 403294354 | High Sign | HFTD Tier 2 | Distribution | 2010-12-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010534 | 403294358 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-12-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010535 | 403294426 | Guy | HFTD Tier 2 | Distribution | 2010-12-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010536 | 403294438 | High Sign | HFTD Tier 2 | Distribution | 2010-12-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010537 | 403299826 | Molding | HFTD Tier 2 | Distribution | 2010-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010538 | 403299839 | High Sign | HFTD Tier 2 | Distribution | 2010-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010539 | 403299864 | High Sign | HFTD Tier 2 | Distribution | 2010-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010540 | 403310442 | Molding | HFTD Tier 2 | Distribution | 2010-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010541 | 403300997 | High Sign | HFTD Tier 2 | Distribution | 2010-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010542 | 403301211 | High Sign | HFTD Tier 3 | Distribution | 2010-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010543 | 403301213 | Cable/Conductor | HFTD Tier 3 | Distribution | 2010-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010544 | 403310640 | Molding | HFTD Tier 2 | Distribution | 2010-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010545 | 403310939 | High Sign | HFTD Tier 2 | Distribution | 2010-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010546 | 403310945 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010547 | 403310957 | High Sign | HFTD Tier 2 | Distribution | 2010-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010548 | 403311105 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010549 | 403313632 | High Sign | HFTD Tier 2 | Distribution | 2010-12-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010550 | 403314116 | High Sign | HFTD Tier 3 | Distribution | 2010-12-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010551 | 403314150 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2010-12-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010552 | 403315333 | High Sign | HFTD Tier 3 | Distribution | 2010-12-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010553 | 403315348 | High Sign | HFTD Tier 3 | Distribution | 2010-12-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010554 | 403315376 | Molding | HFTD Tier 3 | Distribution | 2010-12-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010555 | 403315385 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-12-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010556 | 403315483 | Ground | HFTD Tier 3 | Distribution | 2010-12-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010557 | 403321238 | High Sign | HFTD Tier 2 | Distribution | 2010-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010558 | 403321283 | High Sign | HFTD Tier 2 | Distribution | 2010-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010559 | 403321284 | High Sign | HFTD Tier 2 | Distribution | 2010-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010560 | 403322688 | High Sign | HFTD Tier 3 | Distribution | 2010-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010561 | 403323140 | Molding | HFTD Tier 2 | Distribution | 2010-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010562 | 403323235 | Molding | HFTD Tier 2 | Distribution | 2010-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010563 | 403323243 | Cable/Conductor | HFTD Tier 2 | Distribution | 2010-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010564 | 403323855 | High Sign | HFTD Tier 3 | Distribution | 2010-12-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010565 | 403323862 | High Sign | HFTD Tier 3 | Distribution | 2010-12-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010566 | 403323864 | High Sign | HFTD Tier 3 | Distribution | 2010-12-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010567 | 403324403 | Molding | HFTD Tier 2 | Distribution | 2010-12-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010568 | 403325801 | Guy | HFTD Tier 2 | Distribution | 2010-12-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010569 | 403324791 | Guy | HFTD Tier 3 | Distribution | 2010-12-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010570 | 403324813 | Hardware/Framing | HFTD Tier 2 | Distribution | 2010-12-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010571 | 403324965 | Hardware/Framing | HFTD Tier 3 | Distribution | 2010-12-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010572 | 403325919 | High Sign | HFTD Tier 3 | Distribution | 2010-12-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010573 | 403338911 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2010-12-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010574 | 403339162 | Molding | HFTD Tier 3 | Distribution | 2010-12-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010575 | 403339541 | Molding | HFTD Tier 3 | Distribution | 2010-12-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010576 | 403347014 | High Sign | HFTD Tier 2 | Distribution | 2010-12-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010577 | 403347694 | Molding | HFTD Tier 3 | Distribution | 2010-12-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010578 | 403347728 | High Sign | HFTD Tier 2 | Distribution | 2010-12-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010579 | 403347738 | High Sign | HFTD Tier 2 | Distribution | 2010-12-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010580 | 403347740 | Molding | HFTD Tier 2 | Distribution | 2010-12-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010581 | 403347932 | Molding | HFTD Tier 3 | Distribution | 2010-12-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010582 | 403348365 | High Sign | HFTD Tier 3 | Distribution | 2010-12-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010583 | 403348381 | High Sign | HFTD Tier 3 | Distribution | 2010-12-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010584 | 403353765 | High Sign | HFTD Tier 2 | Distribution | 2011-01-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010585 | 403353766 | Molding | HFTD Tier 2 | Distribution | 2011-01-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010586 | 403353967 | High Sign | HFTD Tier 2 | Distribution | 2011-01-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010587 | 403354007 | High Sign | HFTD Tier 3 | Distribution | 2011-01-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010588 | 403354008 | High Sign | HFTD Tier 3 | Distribution | 2011-01-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010589 | 403354358 | High Sign | HFTD Tier 3 | Distribution | 2011-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010590 | 403354381 | Molding | HFTD Tier 3 | Distribution | 2011-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010591 | 403354460 | Pole Tag | HFTD Tier 3 | Distribution | 2011-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010592 | 403354567 | High Sign | HFTD Tier 2 | Distribution | 2011-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010593 | 403355355 | High Sign | HFTD Tier 2 | Distribution | 2011-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010594 | 403355356 | Molding | HFTD Tier 2 | Distribution | 2011-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010595 | 403355407 | Molding | HFTD Tier 2 | Distribution | 2011-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010596 | 403355437 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010597 | 403357337 | High Sign | HFTD Tier 3 | Distribution | 2011-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010598 | 403357365 | High Sign | HFTD Tier 3 | Distribution | 2011-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010599 | 403355800 | High Sign | HFTD Tier 2 | Distribution | 2011-01-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010600 | 403355806 | Molding | HFTD Tier 3 | Distribution | 2011-01-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010601 | 403355824 | Insulator | HFTD Tier 3 | Distribution | 2011-01-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010602 | 403355863 | Molding | HFTD Tier 3 | Distribution | 2011-01-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010603 | 403355865 | Molding | HFTD Tier 3 | Distribution | 2011-01-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010604 | 403356248 | Molding | HFTD Tier 3 | Distribution | 2011-01-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010605 | 403356258 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-01-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010606 | 403356259 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-01-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010607 | 403356968 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-01-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010608 | 403356995 | Molding | HFTD Tier 2 | Distribution | 2011-01-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010609 | 403357067 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-01-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010610 | 403357069 | Insulator | HFTD Tier 2 | Distribution | 2011-01-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010611 | 403357428 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-01-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010612 | 403357687 | High Sign | HFTD Tier 2 | Distribution | 2011-01-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010613 | 403357691 | Molding | HFTD Tier 2 | Distribution | 2011-01-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010614 | 403357698 | Molding | HFTD Tier 3 | Distribution | 2011-01-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010615 | 403357699 | High Sign | HFTD Tier 3 | Distribution | 2011-01-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010616 | 403357830 | High Sign | HFTD Tier 3 | Distribution | 2011-01-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010617 | 403357839 | High Sign | HFTD Tier 3 | Distribution | 2011-01-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010618 | 403357849 | High Sign | HFTD Tier 3 | Distribution | 2011-01-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010619 | 403358345 | Molding | HFTD Tier 2 | Distribution | 2011-01-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010620 | 403358346 | Molding | HFTD Tier 2 | Distribution | 2011-01-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010621 | 403358425 | Molding | HFTD Tier 2 | Distribution | 2011-01-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010622 | 403359118 | High Sign | HFTD Tier 3 | Distribution | 2011-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010623 | 403359121 | Molding | HFTD Tier 3 | Distribution | 2011-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010624 | 403359160 | High Sign | HFTD Tier 3 | Distribution | 2011-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010625 | 403359313 | High Sign | HFTD Tier 2 | Distribution | 2011-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010626 | 403359587 | Molding | HFTD Tier 2 | Distribution | 2011-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010627 | 403359593 | High Sign | HFTD Tier 2 | Distribution | 2011-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010628 | 403360903 | High Sign | HFTD Tier 3 | Distribution | 2011-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010629 | 403361253 | High Sign | HFTD Tier 3 | Distribution | 2011-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010630 | 403361370 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010631 | 403361524 | Molding | HFTD Tier 3 | Distribution | 2011-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010632 | 403361546 | Molding | HFTD Tier 3 | Distribution | 2011-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010633 | 403361582 | High Sign | HFTD Tier 3 | Distribution | 2011-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010634 | 403361909 | Molding | HFTD Tier 2 | Distribution | 2011-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010635 | 403362467 | High Sign | HFTD Tier 2 | Distribution | 2011-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010636 | 403362468 | High Sign | HFTD Tier 2 | Distribution | 2011-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010637 | 403362470 | High Sign | HFTD Tier 2 | Distribution | 2011-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010638 | 403362485 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010639 | 403363075 | Molding | HFTD Tier 2 | Distribution | 2011-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010640 | 403363093 | High Sign | HFTD Tier 2 | Distribution | 2011-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010641 | 403363135 | Molding | HFTD Tier 3 | Distribution | 2011-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010642 | 403363973 | High Sign | HFTD Tier 2 | Distribution | 2011-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010643 | 403364433 | Molding | HFTD Tier 2 | Distribution | 2011-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010644 | 403364894 | High Sign | HFTD Tier 2 | Distribution | 2011-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010645 | 403364942 | Molding | HFTD Tier 2 | Distribution | 2011-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010646 | 403365000 | Molding | HFTD Tier 3 | Distribution | 2011-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010647 | 403365142 | Molding | HFTD Tier 2 | Distribution | 2011-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010648 | 403365367 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010649 | 403365782 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010650 | 403366847 | Molding | HFTD Tier 2 | Distribution | 2011-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010651 | 403366922 | High Sign | HFTD Tier 2 | Distribution | 2011-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010652 | 403366931 | Molding | HFTD Tier 2 | Distribution | 2011-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010653 | 403366944 | Molding | HFTD Tier 2 | Distribution | 2011-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010654 | 403367510 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010655 | 403367857 | High Sign | HFTD Tier 2 | Distribution | 2011-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010656 | 403368250 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010657 | 403368616 | Guy | HFTD Tier 2 | Distribution | 2011-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010658 | 403368617 | Molding | HFTD Tier 2 | Distribution | 2011-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010659 | 403368618 | High Sign | HFTD Tier 2 | Distribution | 2011-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010660 | 403368619 | Molding | HFTD Tier 2 | Distribution | 2011-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010661 | 403368692 | High Sign | HFTD Tier 3 | Distribution | 2011-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010662 | 403368779 | Molding | HFTD Tier 3 | Distribution | 2011-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010663 | 403368785 | Molding | HFTD Tier 3 | Distribution | 2011-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010664 | 403368860 | High Sign | HFTD Tier 2 | Distribution | 2011-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010665 | 403368879 | High Sign | HFTD Tier 2 | Distribution | 2011-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010666 | 403368885 | High Sign | HFTD Tier 2 | Distribution | 2011-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010667 | 403368912 | Molding | HFTD Tier 2 | Distribution | 2011-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010668 | 403369328 | High Sign | HFTD Tier 2 | Distribution | 2011-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010669 | 403369471 | Molding | HFTD Tier 2 | Distribution | 2011-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010670 | 403369664 | Molding | HFTD Tier 2 | Distribution | 2011-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010671 | 403369677 | High Sign | HFTD Tier 2 | Distribution | 2011-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010672 | 403370838 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010673 | 403370971 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010674 | 403371037 | High Sign | HFTD Tier 2 | Distribution | 2011-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010675 | 403371050 | High Sign | HFTD Tier 2 | Distribution | 2011-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010676 | 403371062 | High Sign | HFTD Tier 2 | Distribution | 2011-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010677 | 403371068 | Guy | HFTD Tier 2 | Distribution | 2011-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010678 | 403371790 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010679 | 403371893 | Guy | HFTD Tier 2 | Distribution | 2011-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010680 | 403371910 | Guy | HFTD Tier 2 | Distribution | 2011-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010681 | 403372129 | Molding | HFTD Tier 2 | Distribution | 2011-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010682 | 403372642 | Molding | HFTD Tier 3 | Distribution | 2011-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010683 | 403373359 | High Sign | HFTD Tier 3 | Distribution | 2011-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010684 | 403373402 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010685 | 403373659 | High Sign | HFTD Tier 2 | Distribution | 2011-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010686 | 403373898 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010687 | 403373903 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010688 | 403373905 | High Sign | HFTD Tier 2 | Distribution | 2011-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010689 | 403373918 | High Sign | HFTD Tier 2 | Distribution | 2011-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010690 | 403374611 | High Sign | HFTD Tier 2 | Distribution | 2011-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010691 | 403374971 | Molding | HFTD Tier 3 | Distribution | 2011-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010692 | 403374976 | Molding | HFTD Tier 3 | Distribution | 2011-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010693 | 403374977 | Molding | HFTD Tier 3 | Distribution | 2011-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010694 | 403374992 | High Sign | HFTD Tier 3 | Distribution | 2011-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010695 | 403375258 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010696 | 403375265 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010697 | 403375293 | High Sign | HFTD Tier 2 | Distribution | 2011-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010698 | 403375295 | Molding | HFTD Tier 2 | Distribution | 2011-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010699 | 403375543 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010700 | 403375553 | High Sign | HFTD Tier 3 | Distribution | 2011-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010701 | 403375576 | Bond | HFTD Tier 3 | Distribution | 2011-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010702 | 403376158 | Guy | HFTD Tier 2 | Distribution | 2011-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010703 | 403376788 | High Sign | HFTD Tier 2 | Distribution | 2011-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010704 | 403376800 | High Sign | HFTD Tier 2 | Distribution | 2011-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010705 | 403376838 | High Sign | HFTD Tier 3 | Distribution | 2011-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010706 | 403376854 | High Sign | HFTD Tier 3 | Distribution | 2011-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010707 | 403377819 | Bond | HFTD Tier 3 | Distribution | 2011-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010708 | 403377827 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010709 | 403377828 | Riser/Conduit | HFTD Tier 3 | Distribution | 2011-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010710 | 403377840 | Bond | HFTD Tier 3 | Distribution | 2011-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010711 | 403377846 | Molding | HFTD Tier 3 | Distribution | 2011-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010712 | 403378675 | Molding | HFTD Tier 2 | Distribution | 2011-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010713 | 403378795 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010714 | 403381034 | High Sign | HFTD Tier 2 | Distribution | 2011-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010715 | 403381131 | Molding | HFTD Tier 2 | Distribution | 2011-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010716 | 403381153 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010717 | 403381378 | High Sign | HFTD Tier 2 | Distribution | 2011-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010718 | 403381495 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010719 | 403381504 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010720 | 403381505 | High Sign | HFTD Tier 3 | Distribution | 2011-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010721 | 403382517 | Molding | HFTD Tier 2 | Distribution | 2011-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010722 | 403382548 | High Sign | HFTD Tier 2 | Distribution | 2011-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010723 | 403383163 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010724 | 403383328 | High Sign | HFTD Tier 2 | Distribution | 2011-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010725 | 403383420 | Molding | HFTD Tier 3 | Distribution | 2011-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010726 | 403383495 | High Sign | HFTD Tier 3 | Distribution | 2011-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010727 | 403383607 | High Sign | HFTD Tier 2 | Distribution | 2011-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010728 | 403384518 | Riser/Conduit | HFTD Tier 3 | Distribution | 2011-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010729 | 403384667 | High Sign | HFTD Tier 3 | Distribution | 2011-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010730 | 403385187 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010731 | 403385236 | High Sign | HFTD Tier 2 | Distribution | 2011-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010732 | 403385238 | High Sign | HFTD Tier 2 | Distribution | 2011-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010733 | 403385241 | High Sign | HFTD Tier 2 | Distribution | 2011-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010734 | 403385962 | High Sign | HFTD Tier 2 | Distribution | 2011-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010735 | 403386009 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010736 | 403386010 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010737 | 403386850 | Guy | HFTD Tier 2 | Distribution | 2011-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010738 | 403387072 | Molding | HFTD Tier 2 | Distribution | 2011-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010739 | 403387076 | Molding | HFTD Tier 2 | Distribution | 2011-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010740 | 403387083 | Guy | HFTD Tier 2 | Distribution | 2011-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010741 | 403387409 | Molding | HFTD Tier 3 | Distribution | 2011-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010742 | 403387419 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010743 | 403387493 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010744 | 403387976 | High Sign | HFTD Tier 3 | Distribution | 2011-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010745 | 403387977 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010746 | 403388108 | Molding | HFTD Tier 3 | Distribution | 2011-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010747 | 403388256 | Molding | HFTD Tier 2 | Distribution | 2011-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010748 | 403388260 | Molding | HFTD Tier 2 | Distribution | 2011-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010749 | 403389226 | High Sign | HFTD Tier 3 | Distribution | 2011-01-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010750 | 403389692 | High Sign | HFTD Tier 2 | Distribution | 2011-01-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010751 | 403391006 | Guy | HFTD Tier 2 | Distribution | 2011-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010752 | 403391017 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010753 | 403391031 | Insulator | HFTD Tier 2 | Distribution | 2011-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010754 | 403391138 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010755 | 403391139 | Guy | HFTD Tier 2 | Distribution | 2011-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010756 | 403391336 | Guy | HFTD Tier 2 | Distribution | 2011-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010757 | 403391358 | High Sign | HFTD Tier 2 | Distribution | 2011-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010758 | 403391377 | High Sign | HFTD Tier 2 | Distribution | 2011-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010759 | 403391793 | Molding | HFTD Tier 2 | Distribution | 2011-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010760 | 403391886 | High Sign | HFTD Tier 3 | Distribution | 2011-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010761 | 403395190 | Molding | HFTD Tier 3 | Distribution | 2011-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010762 | 403395289 | Insulator | HFTD Tier 2 | Distribution | 2011-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010763 | 403395355 | High Sign | HFTD Tier 2 | Distribution | 2011-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010764 | 403395474 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010765 | 403395486 | High Sign | HFTD Tier 2 | Distribution | 2011-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010766 | 403395490 | High Sign | HFTD Tier 2 | Distribution | 2011-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010767 | 403395499 | High Sign | HFTD Tier 2 | Distribution | 2011-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010768 | 403395937 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010769 | 403398832 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010770 | 403398901 | High Sign | HFTD Tier 3 | Distribution | 2011-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010771 | 403397028 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010772 | 403397212 | High Sign | HFTD Tier 2 | Distribution | 2011-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010773 | 403397292 | High Sign | HFTD Tier 2 | Distribution | 2011-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010774 | 403397455 | Guy | HFTD Tier 2 | Distribution | 2011-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010775 | 403397828 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010776 | 403397840 | Molding | HFTD Tier 3 | Distribution | 2011-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010777 | 403399206 | Molding | HFTD Tier 2 | Distribution | 2011-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010778 | 403399207 | Ground | HFTD Tier 2 | Distribution | 2011-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010779 | 403399568 | Molding | HFTD Tier 2 | Distribution | 2011-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010780 | 403400357 | Crossarm | HFTD Tier 2 | Distribution | 2011-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010781 | 403400364 | Guy | HFTD Tier 2 | Distribution | 2011-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010782 | 403400368 | Riser/Conduit | HFTD Tier 2 | Distribution | 2011-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010783 | 403400385 | Vis Strips | HFTD Tier 2 | Distribution | 2011-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010784 | 403400400 | Molding | HFTD Tier 2 | Distribution | 2011-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010785 | 403400757 | High Sign | HFTD Tier 2 | Distribution | 2011-02-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010786 | 403401667 | Guy | HFTD Tier 2 | Distribution | 2011-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010787 | 403401917 | Molding | HFTD Tier 3 | Distribution | 2011-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010788 | 403402403 | High Sign | HFTD Tier 3 | Distribution | 2011-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010789 | 403402544 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010790 | 403406245 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010791 | 403409061 | High Sign | HFTD Tier 3 | Distribution | 2011-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010792 | 403403711 | Molding | HFTD Tier 2 | Distribution | 2011-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010793 | 403404297 | Bond | HFTD Tier 3 | Distribution | 2011-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010794 | 403404302 | Molding | HFTD Tier 3 | Distribution | 2011-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010795 | 403404707 | Molding | HFTD Tier 3 | Distribution | 2011-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010796 | 403404718 | High Sign | HFTD Tier 3 | Distribution | 2011-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010797 | 403405277 | High Sign | HFTD Tier 2 | Distribution | 2011-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010798 | 403405279 | Ground | HFTD Tier 2 | Distribution | 2011-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010799 | 403405708 | Molding | HFTD Tier 2 | Distribution | 2011-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010800 | 403406004 | Molding | HFTD Tier 2 | Distribution | 2011-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010801 | 403409127 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010802 | 403408953 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010803 | 403409213 | Molding | HFTD Tier 3 | Distribution | 2011-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010804 | 403412948 | Molding | HFTD Tier 3 | Distribution | 2011-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010805 | 403413022 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010806 | 403410507 | High Sign | HFTD Tier 2 | Distribution | 2011-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010807 | 403410538 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010808 | 403410543 | Molding | HFTD Tier 2 | Distribution | 2011-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010809 | 403412301 | Molding | HFTD Tier 3 | Distribution | 2011-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010810 | 403412389 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010811 | 403413785 | High Sign | HFTD Tier 2 | Distribution | 2011-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010812 | 403413925 | Molding | HFTD Tier 2 | Distribution | 2011-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010813 | 403413962 | Riser/Conduit | HFTD Tier 2 | Distribution | 2011-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010814 | 403415273 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010815 | 403421935 | Molding | HFTD Tier 3 | Distribution | 2011-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010816 | 403416246 | Molding | HFTD Tier 2 | Distribution | 2011-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010817 | 403416254 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010818 | 403416351 | Molding | HFTD Tier 2 | Distribution | 2011-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010819 | 403416352 | High Sign | HFTD Tier 2 | Distribution | 2011-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010820 | 403416353 | Molding | HFTD Tier 2 | Distribution | 2011-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010821 | 403416362 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010822 | 403416431 | High Sign | HFTD Tier 2 | Distribution | 2011-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010823 | 403416643 | High Sign | HFTD Tier 2 | Distribution | 2011-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010824 | 403418966 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-02-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010825 | 403419819 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010826 | 403419855 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010827 | 403420152 | Molding | HFTD Tier 2 | Distribution | 2011-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010828 | 403422272 | Insulator | HFTD Tier 2 | Distribution | 2011-02-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010829 | 403423016 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-02-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010830 | 403423089 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-02-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010831 | 403423105 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-02-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010832 | 403424368 | High Sign | HFTD Tier 2 | Distribution | 2011-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010833 | 403424379 | High Sign | HFTD Tier 2 | Distribution | 2011-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010834 | 403424389 | Molding | HFTD Tier 2 | Distribution | 2011-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010835 | 403424854 | Molding | HFTD Tier 2 | Distribution | 2011-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010836 | 403424865 | Molding | HFTD Tier 2 | Distribution | 2011-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010837 | 403424937 | High Sign | HFTD Tier 2 | Distribution | 2011-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010838 | 403427249 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010839 | 403428934 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010840 | 403428938 | High Sign | HFTD Tier 2 | Distribution | 2011-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010841 | 403429381 | High Sign | HFTD Tier 2 | Distribution | 2011-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010842 | 403429386 | High Sign | HFTD Tier 2 | Distribution | 2011-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010843 | 403429388 | High Sign | HFTD Tier 2 | Distribution | 2011-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010844 | 403429389 | High Sign | HFTD Tier 2 | Distribution | 2011-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010845 | 403431211 | High Sign | HFTD Tier 2 | Distribution | 2011-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010846 | 403431213 | High Sign | HFTD Tier 2 | Distribution | 2011-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010847 | 403431912 | High Sign | HFTD Tier 2 | Distribution | 2011-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010848 | 403434046 | Molding | HFTD Tier 2 | Distribution | 2011-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010849 | 403434896 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010850 | 403434897 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010851 | 403434898 | High Sign | HFTD Tier 2 | Distribution | 2011-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010852 | 403434906 | High Sign | HFTD Tier 2 | Distribution | 2011-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010853 | 403434986 | High Sign | HFTD Tier 2 | Distribution | 2011-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010854 | 403434990 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010855 | 403435172 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010856 | 403437172 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010857 | 403437299 | High Sign | HFTD Tier 2 | Distribution | 2011-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010858 | 403437317 | Molding | HFTD Tier 2 | Distribution | 2011-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010859 | 403437346 | High Sign | HFTD Tier 2 | Distribution | 2011-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010860 | 403437503 | High Sign | HFTD Tier 3 | Distribution | 2011-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010861 | 403437504 | Molding | HFTD Tier 3 | Distribution | 2011-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010862 | 403437510 | High Sign | HFTD Tier 3 | Distribution | 2011-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010863 | 403437516 | Molding | HFTD Tier 3 | Distribution | 2011-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010864 | 403437522 | High Sign | HFTD Tier 3 | Distribution | 2011-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010865 | 403439379 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010866 | 403439393 | Guy | HFTD Tier 2 | Distribution | 2011-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010867 | 403439462 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010868 | 403439868 | Molding | HFTD Tier 2 | Distribution | 2011-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010869 | 403439869 | Molding | HFTD Tier 3 | Distribution | 2011-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010870 | 403440108 | Molding | HFTD Tier 3 | Distribution | 2011-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010871 | 403440109 | High Sign | HFTD Tier 3 | Distribution | 2011-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010872 | 403440400 | Molding | HFTD Tier 2 | Distribution | 2011-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010873 | 403440552 | Ground | HFTD Tier 3 | Distribution | 2011-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010874 | 403440580 | Guy | HFTD Tier 3 | Distribution | 2011-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010875 | 403441598 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010876 | 403442511 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010877 | 403444179 | Insulator | HFTD Tier 2 | Distribution | 2011-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010878 | 403444188 | Insulator | HFTD Tier 2 | Distribution | 2011-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010879 | 403444473 | High Sign | HFTD Tier 2 | Distribution | 2011-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010880 | 403444475 | Molding | HFTD Tier 2 | Distribution | 2011-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010881 | 403444581 | High Sign | HFTD Tier 3 | Distribution | 2011-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010882 | 403444591 | High Sign | HFTD Tier 3 | Distribution | 2011-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010883 | 403444598 | High Sign | HFTD Tier 3 | Distribution | 2011-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010884 | 403444603 | High Sign | HFTD Tier 3 | Distribution | 2011-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010885 | 403444605 | Molding | HFTD Tier 3 | Distribution | 2011-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010886 | 403445477 | High Sign | HFTD Tier 2 | Distribution | 2011-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010887 | 403445485 | Molding | HFTD Tier 2 | Distribution | 2011-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010888 | 403446345 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010889 | 403446346 | Molding | HFTD Tier 2 | Distribution | 2011-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010890 | 403446749 | High Sign | HFTD Tier 3 | Distribution | 2011-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010891 | 403446757 | High Sign | HFTD Tier 3 | Distribution | 2011-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010892 | 403446762 | High Sign | HFTD Tier 3 | Distribution | 2011-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010893 | 403446771 | High Sign | HFTD Tier 3 | Distribution | 2011-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010894 | 403446773 | High Sign | HFTD Tier 3 | Distribution | 2011-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010895 | 403446838 | Molding | HFTD Tier 2 | Distribution | 2011-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010896 | 403447628 | High Sign | HFTD Tier 3 | Distribution | 2011-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010897 | 403447649 | High Sign | HFTD Tier 3 | Distribution | 2011-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010898 | 403447650 | Molding | HFTD Tier 3 | Distribution | 2011-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010899 | 403447745 | Molding | HFTD Tier 3 | Distribution | 2011-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010900 | 403448234 | Molding | HFTD Tier 3 | Distribution | 2011-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010901 | 403448248 | Molding | HFTD Tier 3 | Distribution | 2011-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010902 | 403448264 | Molding | HFTD Tier 3 | Distribution | 2011-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010903 | 403448912 | High Sign | HFTD Tier 3 | Distribution | 2011-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010904 | 403448941 | High Sign | HFTD Tier 3 | Distribution | 2011-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010905 | 403448946 | High Sign | HFTD Tier 3 | Distribution | 2011-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010906 | 403448947 | High Sign | HFTD Tier 3 | Distribution | 2011-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010907 | 403449437 | Molding | HFTD Tier 2 | Distribution | 2011-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010908 | 403449457 | Guy | HFTD Tier 2 | Distribution | 2011-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010909 | 403449534 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010910 | 403450032 | High Sign | HFTD Tier 3 | Distribution | 2011-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010911 | 403450034 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010912 | 403450253 | Molding | HFTD Tier 3 | Distribution | 2011-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010913 | 403450260 | High Sign | HFTD Tier 3 | Distribution | 2011-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010914 | 403450278 | Molding | HFTD Tier 3 | Distribution | 2011-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010915 | 403451700 | Molding | HFTD Tier 3 | Distribution | 2011-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010916 | 403452006 | High Sign | HFTD Tier 3 | Distribution | 2011-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010917 | 403452335 | Guy | HFTD Tier 3 | Distribution | 2011-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010918 | 403453411 | Molding | HFTD Tier 2 | Distribution | 2011-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010919 | 403456531 | Insulator | HFTD Tier 2 | Distribution | 2011-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010920 | 403457231 | Molding | HFTD Tier 3 | Distribution | 2011-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010921 | 403458373 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010922 | 403459660 | High Sign | HFTD Tier 3 | Distribution | 2011-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010923 | 403460402 | Molding | HFTD Tier 2 | Distribution | 2011-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010924 | 403750527 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010925 | 403460961 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010926 | 403462063 | Cutout/Fuse | HFTD Tier 2 | Distribution | 2011-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010927 | 403462086 | High Sign | HFTD Tier 2 | Distribution | 2011-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010928 | 403463263 | Molding | HFTD Tier 2 | Distribution | 2011-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010929 | 403463667 | High Sign | HFTD Tier 3 | Distribution | 2011-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010930 | 403463687 | High Sign | HFTD Tier 3 | Distribution | 2011-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010931 | 403463688 | Molding | HFTD Tier 3 | Distribution | 2011-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010932 | 403463703 | High Sign | HFTD Tier 3 | Distribution | 2011-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010933 | 403463713 | High Sign | HFTD Tier 3 | Distribution | 2011-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010934 | 403463714 | High Sign | HFTD Tier 3 | Distribution | 2011-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010935 | 403463725 | High Sign | HFTD Tier 3 | Distribution | 2011-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010936 | 403463776 | Insulator | HFTD Tier 3 | Distribution | 2011-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010937 | 403463782 | High Sign | HFTD Tier 3 | Distribution | 2011-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010938 | 403465286 | High Sign | HFTD Tier 3 | Distribution | 2011-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010939 | 403465488 | Vis Strips | HFTD Tier 2 | Distribution | 2011-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010940 | 403465960 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010941 | 403468559 | High Sign | HFTD Tier 3 | Distribution | 2011-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010942 | 403468578 | High Sign | HFTD Tier 3 | Distribution | 2011-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010943 | 403469656 | High Sign | HFTD Tier 2 | Distribution | 2011-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010944 | 403469672 | Molding | HFTD Tier 2 | Distribution | 2011-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010945 | 403469685 | High Sign | HFTD Tier 2 | Distribution | 2011-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010946 | 403469694 | High Sign | HFTD Tier 2 | Distribution | 2011-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010947 | 403469697 | High Sign | HFTD Tier 2 | Distribution | 2011-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010948 | 403473376 | High Sign | HFTD Tier 3 | Distribution | 2011-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010949 | 403473472 | High Sign | HFTD Tier 2 | Distribution | 2011-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010950 | 403473473 | Molding | HFTD Tier 2 | Distribution | 2011-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010951 | 403479931 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010952 | 403480227 | Molding | HFTD Tier 3 | Distribution | 2011-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010953 | 403480233 | High Sign | HFTD Tier 3 | Distribution | 2011-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010954 | 403480586 | Molding | HFTD Tier 2 | Distribution | 2011-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010955 | 403481124 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010956 | 403481125 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010957 | 403481143 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010958 | 403481242 | Insulator | HFTD Tier 2 | Distribution | 2011-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010959 | 403481247 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010960 | 403481254 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010961 | 403481255 | High Sign | HFTD Tier 2 | Distribution | 2011-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010962 | 403481256 | Crossarm | HFTD Tier 2 | Distribution | 2011-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010963 | 403481258 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010964 | 403481273 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010965 | 403481481 | Molding | HFTD Tier 3 | Distribution | 2011-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010966 | 403481778 | Molding | HFTD Tier 2 | Distribution | 2011-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010967 | 403481963 | Molding | HFTD Tier 3 | Distribution | 2011-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010968 | 403481966 | High Sign | HFTD Tier 3 | Distribution | 2011-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010969 | 403481973 | Molding | HFTD Tier 3 | Distribution | 2011-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010970 | 403481982 | High Sign | HFTD Tier 3 | Distribution | 2011-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010971 | 403482010 | Molding | HFTD Tier 2 | Distribution | 2011-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010972 | 403482021 | Molding | HFTD Tier 2 | Distribution | 2011-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010973 | 403482049 | High Sign | HFTD Tier 2 | Distribution | 2011-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010974 | 403482056 | Crossarm | HFTD Tier 2 | Distribution | 2011-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010975 | 403482057 | Molding | HFTD Tier 2 | Distribution | 2011-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010976 | 403482077 | High Sign | HFTD Tier 2 | Distribution | 2011-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010977 | 403482690 | High Sign | HFTD Tier 3 | Distribution | 2011-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010978 | 403482700 | High Sign | HFTD Tier 3 | Distribution | 2011-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010979 | 403482703 | Riser/Conduit | HFTD Tier 3 | Distribution | 2011-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010980 | 403483123 | Insulator | HFTD Tier 2 | Distribution | 2011-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010981 | 403484464 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010982 | 403484912 | High Sign | HFTD Tier 3 | Distribution | 2011-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010983 | 403485989 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010984 | 403486157 | Molding | HFTD Tier 2 | Distribution | 2011-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010985 | 403486169 | High Sign | HFTD Tier 2 | Distribution | 2011-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010986 | 403486170 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010987 | 403486185 | Molding | HFTD Tier 2 | Distribution | 2011-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010988 | 403486432 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010989 | 403486734 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010990 | 403487204 | Guy | HFTD Tier 3 | Distribution | 2011-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010991 | 403487208 | High Sign | HFTD Tier 3 | Distribution | 2011-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010992 | 403487967 | High Sign | HFTD Tier 2 | Distribution | 2011-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010993 | 403487974 | High Sign | HFTD Tier 2 | Distribution | 2011-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010994 | 403487982 | Molding | HFTD Tier 2 | Distribution | 2011-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010995 | 403488117 | High Sign | HFTD Tier 2 | Distribution | 2011-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010996 | 403488422 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010997 | 403488451 | High Sign | HFTD Tier 3 | Distribution | 2011-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010998 | 403490095 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120010999 | 403490096 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011000 | 403490097 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011001 | 403490098 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011002 | 403490099 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011003 | 403490101 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011004 | 403490102 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011005 | 403491044 | Molding | HFTD Tier 2 | Distribution | 2011-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011006 | 403491056 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011007 | 403491103 | Molding | HFTD Tier 2 | Distribution | 2011-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011008 | 403491114 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011009 | 403493077 | Molding | HFTD Tier 2 | Distribution | 2011-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011010 | 403493101 | Molding | HFTD Tier 2 | Distribution | 2011-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011011 | 403493112 | Cutout/Fuse | HFTD Tier 2 | Distribution | 2011-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011012 | 403493125 | High Sign | HFTD Tier 2 | Distribution | 2011-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011013 | 403493204 | High Sign | HFTD Tier 2 | Distribution | 2011-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011014 | 403493494 | Molding | HFTD Tier 3 | Distribution | 2011-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011015 | 403493497 | Molding | HFTD Tier 3 | Distribution | 2011-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011016 | 403495434 | High Sign | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011017 | 403495464 | High Sign | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011018 | 403495474 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011019 | 403495475 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011020 | 403495483 | High Sign | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011021 | 403495500 | Molding | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011022 | 403495726 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011023 | 403495727 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011024 | 403495728 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011025 | 403495740 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011026 | 403495741 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011027 | 403495743 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011028 | 403495745 | High Sign | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011029 | 403495746 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011030 | 403495748 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011031 | 403495751 | High Sign | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011032 | 403495752 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011033 | 403495761 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011034 | 403495778 | High Sign | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011035 | 403495802 | High Sign | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011036 | 403495805 | Molding | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011037 | 403495852 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011038 | 403496285 | Molding | HFTD Tier 3 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011039 | 403496328 | Crossarm | HFTD Tier 2 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011040 | 403496636 | High Sign | HFTD Tier 3 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011041 | 403499403 | High Sign | HFTD Tier 3 | Distribution | 2011-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011042 | 403498099 | Molding | HFTD Tier 2 | Distribution | 2011-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011043 | 403498107 | High Sign | HFTD Tier 2 | Distribution | 2011-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011044 | 403498110 | Molding | HFTD Tier 2 | Distribution | 2011-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011045 | 403498111 | High Sign | HFTD Tier 2 | Distribution | 2011-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011046 | 403498114 | High Sign | HFTD Tier 2 | Distribution | 2011-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011047 | 403498117 | High Sign | HFTD Tier 2 | Distribution | 2011-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011048 | 403498155 | High Sign | HFTD Tier 2 | Distribution | 2011-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011049 | 403498170 | High Sign | HFTD Tier 2 | Distribution | 2011-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011050 | 403498572 | Molding | HFTD Tier 2 | Distribution | 2011-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011051 | 403498582 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011052 | 403500766 | Riser/Conduit | HFTD Tier 3 | Distribution | 2011-04-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011053 | 403500963 | High Sign | HFTD Tier 2 | Distribution | 2011-04-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011054 | 403500988 | High Sign | HFTD Tier 2 | Distribution | 2011-04-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011055 | 403501714 | Molding | HFTD Tier 2 | Distribution | 2011-04-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011056 | 403595810 | High Sign | HFTD Tier 3 | Distribution | 2011-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011057 | 403596884 | Riser/Conduit | HFTD Tier 2 | Distribution | 2011-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011058 | 403597227 | Molding | HFTD Tier 2 | Distribution | 2011-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011059 | 403597729 | High Sign | HFTD Tier 3 | Distribution | 2011-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011060 | 403597740 | High Sign | HFTD Tier 3 | Distribution | 2011-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011061 | 403597742 | High Sign | HFTD Tier 3 | Distribution | 2011-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011062 | 403597744 | High Sign | HFTD Tier 3 | Distribution | 2011-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011063 | 403597745 | High Sign | HFTD Tier 3 | Distribution | 2011-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011064 | 403597833 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011065 | 403597834 | High Sign | HFTD Tier 2 | Distribution | 2011-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011066 | 403598503 | Molding | HFTD Tier 3 | Distribution | 2011-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011067 | 403599070 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011068 | 403599080 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011069 | 403602859 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011070 | 403600537 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011071 | 403600540 | High Sign | HFTD Tier 2 | Distribution | 2011-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011072 | 403600550 | High Sign | HFTD Tier 2 | Distribution | 2011-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011073 | 403602015 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011074 | 403602871 | High Sign | HFTD Tier 2 | Distribution | 2011-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011075 | 403602919 | High Sign | HFTD Tier 3 | Distribution | 2011-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011076 | 403603176 | High Sign | HFTD Tier 2 | Distribution | 2011-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011077 | 403603177 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011078 | 403606051 | Molding | HFTD Tier 2 | Distribution | 2011-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011079 | 403606155 | Molding | HFTD Tier 3 | Distribution | 2011-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011080 | 403606224 | Pole Tag | HFTD Tier 2 | Distribution | 2011-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011081 | 403606232 | Molding | HFTD Tier 2 | Distribution | 2011-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011082 | 403606578 | High Sign | HFTD Tier 3 | Distribution | 2011-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011083 | 403636805 | High Sign | HFTD Tier 2 | Distribution | 2011-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011084 | 403637237 | High Sign | HFTD Tier 3 | Distribution | 2011-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011085 | 403638454 | Molding | HFTD Tier 2 | Distribution | 2011-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011086 | 403638558 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011087 | 403638567 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011088 | 403638570 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011089 | 403638572 | High Sign | HFTD Tier 2 | Distribution | 2011-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011090 | 403638573 | Molding | HFTD Tier 2 | Distribution | 2011-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011091 | 403638587 | High Sign | HFTD Tier 2 | Distribution | 2011-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011092 | 403638594 | Molding | HFTD Tier 2 | Distribution | 2011-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011093 | 403638716 | High Sign | HFTD Tier 2 | Distribution | 2011-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011094 | 403638726 | High Sign | HFTD Tier 2 | Distribution | 2011-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011095 | 403638741 | High Sign | HFTD Tier 2 | Distribution | 2011-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011096 | 403638743 | Molding | HFTD Tier 2 | Distribution | 2011-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011097 | 403638745 | Molding | HFTD Tier 2 | Distribution | 2011-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011098 | 403638746 | High Sign | HFTD Tier 2 | Distribution | 2011-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011099 | 403638758 | High Sign | HFTD Tier 2 | Distribution | 2011-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011100 | 403640644 | High Sign | HFTD Tier 3 | Distribution | 2011-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011101 | 403640744 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011102 | 403640746 | High Sign | HFTD Tier 2 | Distribution | 2011-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011103 | 403640795 | High Sign | HFTD Tier 2 | Distribution | 2011-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011104 | 403640810 | High Sign | HFTD Tier 2 | Distribution | 2011-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011105 | 403640821 | High Sign | HFTD Tier 2 | Distribution | 2011-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011106 | 403641419 | Molding | HFTD Tier 3 | Distribution | 2011-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011107 | 403641444 | High Sign | HFTD Tier 3 | Distribution | 2011-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011108 | 403641729 | Riser/Conduit | HFTD Tier 2 | Distribution | 2011-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011109 | 403641760 | Molding | HFTD Tier 2 | Distribution | 2011-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011110 | 403641977 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011111 | 403642734 | Insulator | HFTD Tier 3 | Distribution | 2011-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011112 | 403642753 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011113 | 403643558 | Ground | HFTD Tier 2 | Distribution | 2011-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011114 | 403642740 | High Sign | HFTD Tier 3 | Distribution | 2011-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011115 | 403643159 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011116 | 403643169 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011117 | 403644758 | High Sign | HFTD Tier 3 | Distribution | 2011-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011118 | 403645789 | High Sign | HFTD Tier 3 | Distribution | 2011-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011119 | 403645821 | Molding | HFTD Tier 3 | Distribution | 2011-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011120 | 403645830 | Guy | HFTD Tier 3 | Distribution | 2011-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011121 | 403646448 | High Sign | HFTD Tier 3 | Distribution | 2011-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011122 | 403646459 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011123 | 403646992 | High Sign | HFTD Tier 3 | Distribution | 2011-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011124 | 403647000 | High Sign | HFTD Tier 3 | Distribution | 2011-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011125 | 403647244 | Guy | HFTD Tier 2 | Distribution | 2011-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011126 | 403647292 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011127 | 403647315 | Molding | HFTD Tier 2 | Distribution | 2011-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011128 | 403647330 | Molding | HFTD Tier 3 | Distribution | 2011-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011129 | 403648108 | Guy | HFTD Tier 2 | Distribution | 2011-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011130 | 403648362 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011131 | 403649375 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011132 | 403650018 | Molding | HFTD Tier 2 | Distribution | 2011-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011133 | 403650553 | High Sign | HFTD Tier 2 | Distribution | 2011-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011134 | 403650658 | Molding | HFTD Tier 3 | Distribution | 2011-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011135 | 403650665 | High Sign | HFTD Tier 3 | Distribution | 2011-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011136 | 403650680 | Molding | HFTD Tier 3 | Distribution | 2011-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011137 | 403653238 | High Sign | HFTD Tier 3 | Distribution | 2011-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011138 | 403653248 | Molding | HFTD Tier 3 | Distribution | 2011-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011139 | 403654059 | High Sign | HFTD Tier 3 | Distribution | 2011-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011140 | 403657206 | Molding | HFTD Tier 3 | Distribution | 2011-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011141 | 403657216 | Molding | HFTD Tier 3 | Distribution | 2011-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011142 | 403657218 | High Sign | HFTD Tier 3 | Distribution | 2011-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011143 | 403657219 | Molding | HFTD Tier 3 | Distribution | 2011-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011144 | 403661470 | Molding | HFTD Tier 2 | Distribution | 2011-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011145 | 403654766 | Molding | HFTD Tier 3 | Distribution | 2011-04-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011146 | 403654767 | Molding | HFTD Tier 3 | Distribution | 2011-04-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011147 | 403655529 | High Sign | HFTD Tier 3 | Distribution | 2011-04-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011148 | 403655532 | High Sign | HFTD Tier 3 | Distribution | 2011-04-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011149 | 403661400 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-04-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011150 | 403657751 | Molding | HFTD Tier 3 | Distribution | 2011-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011151 | 403658264 | High Sign | HFTD Tier 3 | Distribution | 2011-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011152 | 403661434 | Molding | HFTD Tier 2 | Distribution | 2011-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011153 | 403661444 | High Sign | HFTD Tier 2 | Distribution | 2011-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011154 | 403662516 | High Sign | HFTD Tier 2 | Distribution | 2011-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011155 | 403663060 | Riser/Conduit | HFTD Tier 2 | Distribution | 2011-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011156 | 403663679 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011157 | 403667387 | High Sign | HFTD Tier 2 | Distribution | 2011-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011158 | 403664808 | Insulator | HFTD Tier 2 | Distribution | 2011-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011159 | 403664820 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011160 | 403665847 | High Sign | HFTD Tier 3 | Distribution | 2011-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011161 | 403667442 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011162 | 403667480 | Molding | HFTD Tier 3 | Distribution | 2011-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011163 | 403667487 | High Sign | HFTD Tier 3 | Distribution | 2011-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011164 | 403667493 | Molding | HFTD Tier 3 | Distribution | 2011-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011165 | 403667494 | Molding | HFTD Tier 3 | Distribution | 2011-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011166 | 403667516 | Molding | HFTD Tier 2 | Distribution | 2011-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011167 | 403667520 | Molding | HFTD Tier 2 | Distribution | 2011-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011168 | 403667525 | Molding | HFTD Tier 2 | Distribution | 2011-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011169 | 403667526 | Molding | HFTD Tier 2 | Distribution | 2011-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011170 | 403668007 | High Sign | HFTD Tier 2 | Distribution | 2011-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011171 | 403668008 | Molding | HFTD Tier 2 | Distribution | 2011-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011172 | 403668061 | Guy | HFTD Tier 2 | Distribution | 2011-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011173 | 403668174 | Guy | HFTD Tier 2 | Distribution | 2011-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011174 | 403668180 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011175 | 403669069 | Riser/Conduit | HFTD Tier 2 | Distribution | 2011-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011176 | 403669184 | High Sign | HFTD Tier 2 | Distribution | 2011-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011177 | 403669753 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011178 | 403669783 | High Sign | HFTD Tier 2 | Distribution | 2011-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011179 | 403669790 | Molding | HFTD Tier 2 | Distribution | 2011-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011180 | 403672159 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011181 | 403672191 | High Sign | HFTD Tier 3 | Distribution | 2011-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011182 | 403672193 | High Sign | HFTD Tier 3 | Distribution | 2011-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011183 | 403672216 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011184 | 403672572 | High Sign | HFTD Tier 2 | Distribution | 2011-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011185 | 403672578 | Molding | HFTD Tier 2 | Distribution | 2011-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011186 | 403672586 | Molding | HFTD Tier 2 | Distribution | 2011-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011187 | 403673409 | Molding | HFTD Tier 2 | Distribution | 2011-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011188 | 403673567 | Molding | HFTD Tier 3 | Distribution | 2011-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011189 | 403676065 | High Sign | HFTD Tier 2 | Distribution | 2011-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011190 | 403676071 | High Sign | HFTD Tier 2 | Distribution | 2011-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011191 | 403676368 | High Sign | HFTD Tier 2 | Distribution | 2011-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011192 | 403676382 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011193 | 403676527 | High Sign | HFTD Tier 3 | Distribution | 2011-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011194 | 403676664 | Molding | HFTD Tier 2 | Distribution | 2011-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011195 | 403676861 | High Sign | HFTD Tier 2 | Distribution | 2011-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011196 | 403676983 | High Sign | HFTD Tier 3 | Distribution | 2011-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011197 | 403681035 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011198 | 403678519 | Insulator | HFTD Tier 2 | Distribution | 2011-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011199 | 403678553 | Molding | HFTD Tier 2 | Distribution | 2011-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011200 | 403678554 | High Sign | HFTD Tier 2 | Distribution | 2011-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011201 | 403679851 | Molding | HFTD Tier 3 | Distribution | 2011-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011202 | 403681054 | High Sign | HFTD Tier 2 | Distribution | 2011-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011203 | 403681282 | High Sign | HFTD Tier 2 | Distribution | 2011-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011204 | 403681291 | High Sign | HFTD Tier 2 | Distribution | 2011-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011205 | 403681578 | High Sign | HFTD Tier 2 | Distribution | 2011-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011206 | 403681897 | High Sign | HFTD Tier 2 | Distribution | 2011-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011207 | 403684635 | High Sign | HFTD Tier 2 | Distribution | 2011-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011208 | 403684641 | High Sign | HFTD Tier 2 | Distribution | 2011-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011209 | 403684642 | High Sign | HFTD Tier 2 | Distribution | 2011-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011210 | 403684213 | Guy | HFTD Tier 2 | Distribution | 2011-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011211 | 403684697 | High Sign | HFTD Tier 2 | Distribution | 2011-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011212 | 403686414 | Riser/Conduit | HFTD Tier 2 | Distribution | 2011-05-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011213 | 403686437 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-05-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011214 | 403686441 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-05-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011215 | 403686447 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-05-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011216 | 403686448 | Riser/Conduit | HFTD Tier 2 | Distribution | 2011-05-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011217 | 403690978 | High Sign | HFTD Tier 2 | Distribution | 2011-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011218 | 403690987 | High Sign | HFTD Tier 2 | Distribution | 2011-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011219 | 403690991 | Molding | HFTD Tier 2 | Distribution | 2011-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011220 | 403690993 | High Sign | HFTD Tier 2 | Distribution | 2011-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011221 | 403690994 | High Sign | HFTD Tier 2 | Distribution | 2011-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011222 | 403691314 | Guy | HFTD Tier 2 | Distribution | 2011-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011223 | 403691321 | High Sign | HFTD Tier 2 | Distribution | 2011-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011224 | 403691331 | High Sign | HFTD Tier 2 | Distribution | 2011-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011225 | 403693204 | High Sign | HFTD Tier 3 | Distribution | 2011-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011226 | 403693399 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011227 | 403693413 | Guy | HFTD Tier 2 | Distribution | 2011-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011228 | 403693425 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011229 | 403695939 | Riser/Conduit | HFTD Tier 2 | Distribution | 2011-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011230 | 403695973 | Molding | HFTD Tier 2 | Distribution | 2011-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011231 | 403695974 | High Sign | HFTD Tier 2 | Distribution | 2011-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011232 | 403693803 | High Sign | HFTD Tier 2 | Distribution | 2011-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011233 | 403693804 | High Sign | HFTD Tier 2 | Distribution | 2011-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011234 | 403695288 | High Sign | HFTD Tier 3 | Distribution | 2011-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011235 | 403696227 | High Sign | HFTD Tier 2 | Distribution | 2011-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011236 | 403696233 | Molding | HFTD Tier 2 | Distribution | 2011-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011237 | 403698618 | Molding | HFTD Tier 2 | Distribution | 2011-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011238 | 403698619 | High Sign | HFTD Tier 2 | Distribution | 2011-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011239 | 403698636 | Guy | HFTD Tier 2 | Distribution | 2011-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011240 | 403701638 | High Sign | HFTD Tier 2 | Distribution | 2011-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011241 | 403701716 | High Sign | HFTD Tier 2 | Distribution | 2011-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011242 | 403701725 | High Sign | HFTD Tier 2 | Distribution | 2011-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011243 | 403703458 | High Sign | HFTD Tier 2 | Distribution | 2011-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011244 | 403703466 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011245 | 403703470 | High Sign | HFTD Tier 2 | Distribution | 2011-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011246 | 403703476 | Vis Strips | HFTD Tier 2 | Distribution | 2011-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011247 | 403703659 | High Sign | HFTD Tier 3 | Distribution | 2011-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011248 | 403703802 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011249 | 403705811 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011250 | 403705812 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011251 | 403705813 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011252 | 403705820 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011253 | 403706264 | Molding | HFTD Tier 2 | Distribution | 2011-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011254 | 403706271 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011255 | 403706294 | Molding | HFTD Tier 2 | Distribution | 2011-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011256 | 403706341 | Molding | HFTD Tier 2 | Distribution | 2011-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011257 | 403706351 | High Sign | HFTD Tier 2 | Distribution | 2011-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011258 | 403706360 | Molding | HFTD Tier 2 | Distribution | 2011-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011259 | 403706914 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011260 | 403707646 | High Sign | HFTD Tier 2 | Distribution | 2011-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011261 | 403707712 | High Sign | HFTD Tier 2 | Distribution | 2011-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011262 | 403708192 | Molding | HFTD Tier 3 | Distribution | 2011-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011263 | 403708240 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011264 | 403708271 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011265 | 403708869 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011266 | 403710171 | Molding | HFTD Tier 3 | Distribution | 2011-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011267 | 403711615 | High Sign | HFTD Tier 2 | Distribution | 2011-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011268 | 403711616 | High Sign | HFTD Tier 2 | Distribution | 2011-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011269 | 403711617 | High Sign | HFTD Tier 2 | Distribution | 2011-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011270 | 403712234 | High Sign | HFTD Tier 3 | Distribution | 2011-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011271 | 403712767 | Molding | HFTD Tier 3 | Distribution | 2011-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011272 | 403712772 | High Sign | HFTD Tier 3 | Distribution | 2011-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011273 | 403712811 | High Sign | HFTD Tier 3 | Distribution | 2011-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011274 | 403713918 | Molding | HFTD Tier 3 | Distribution | 2011-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011275 | 403714380 | High Sign | HFTD Tier 2 | Distribution | 2011-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011276 | 403714384 | High Sign | HFTD Tier 2 | Distribution | 2011-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011277 | 403715991 | High Sign | HFTD Tier 2 | Distribution | 2011-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011278 | 403715995 | High Sign | HFTD Tier 2 | Distribution | 2011-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011279 | 403717048 | Molding | HFTD Tier 3 | Distribution | 2011-05-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011280 | 403717058 | Riser/Conduit | HFTD Tier 3 | Distribution | 2011-05-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011281 | 403720436 | High Sign | HFTD Tier 2 | Distribution | 2011-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011282 | 403720437 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011283 | 403720850 | High Sign | HFTD Tier 2 | Distribution | 2011-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011284 | 403720853 | High Sign | HFTD Tier 2 | Distribution | 2011-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011285 | 403721753 | Guy | HFTD Tier 3 | Distribution | 2011-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011286 | 403724951 | High Sign | HFTD Tier 3 | Distribution | 2011-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011287 | 403727281 | High Sign | HFTD Tier 3 | Distribution | 2011-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011288 | 403727529 | Molding | HFTD Tier 3 | Distribution | 2011-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011289 | 403727699 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011290 | 403735030 | Molding | HFTD Tier 2 | Distribution | 2011-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011291 | 403736206 | Molding | HFTD Tier 3 | Distribution | 2011-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011292 | 403738988 | Guy | HFTD Tier 3 | Distribution | 2011-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011293 | 403739022 | Guy | HFTD Tier 3 | Distribution | 2011-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011294 | 403743204 | High Sign | HFTD Tier 2 | Distribution | 2011-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011295 | 403743233 | High Sign | HFTD Tier 2 | Distribution | 2011-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011296 | 403739912 | High Sign | HFTD Tier 3 | Distribution | 2011-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011297 | 403740268 | Molding | HFTD Tier 2 | Distribution | 2011-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011298 | 403740363 | Molding | HFTD Tier 2 | Distribution | 2011-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011299 | 403741792 | High Sign | HFTD Tier 2 | Distribution | 2011-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011300 | 403741833 | Molding | HFTD Tier 3 | Distribution | 2011-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011301 | 403741890 | Molding | HFTD Tier 3 | Distribution | 2011-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011302 | 403746559 | High Sign | HFTD Tier 3 | Distribution | 2011-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011303 | 403742576 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011304 | 403742583 | High Sign | HFTD Tier 3 | Distribution | 2011-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011305 | 403742736 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011306 | 403742942 | High Sign | HFTD Tier 2 | Distribution | 2011-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011307 | 403743963 | Molding | HFTD Tier 3 | Distribution | 2011-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011308 | 403743981 | High Sign | HFTD Tier 3 | Distribution | 2011-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011309 | 403745978 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011310 | 403746649 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011311 | 403746713 | Guy | HFTD Tier 3 | Distribution | 2011-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011312 | 403746776 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011313 | 403758760 | Guy | HFTD Tier 2 | Distribution | 2011-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011314 | 403753134 | High Sign | HFTD Tier 3 | Distribution | 2011-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011315 | 403753135 | Molding | HFTD Tier 3 | Distribution | 2011-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011316 | 403753143 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011317 | 403753152 | High Sign | HFTD Tier 3 | Distribution | 2011-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011318 | 403753609 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011319 | 403753823 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011320 | 403754228 | Molding | HFTD Tier 2 | Distribution | 2011-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011321 | 403754476 | High Sign | HFTD Tier 2 | Distribution | 2011-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011322 | 403754558 | High Sign | HFTD Tier 2 | Distribution | 2011-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011323 | 403754560 | Molding | HFTD Tier 2 | Distribution | 2011-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011324 | 403754633 | Molding | HFTD Tier 2 | Distribution | 2011-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011325 | 403754952 | High Sign | HFTD Tier 2 | Distribution | 2011-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011326 | 403756250 | High Sign | HFTD Tier 2 | Distribution | 2011-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011327 | 403756726 | Molding | HFTD Tier 2 | Distribution | 2011-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011328 | 403756746 | High Sign | HFTD Tier 2 | Distribution | 2011-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011329 | 403756753 | Molding | HFTD Tier 2 | Distribution | 2011-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011330 | 403767035 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011331 | 403768351 | Molding | HFTD Tier 3 | Distribution | 2011-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011332 | 403768731 | High Sign | HFTD Tier 2 | Distribution | 2011-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011333 | 403768993 | Molding | HFTD Tier 3 | Distribution | 2011-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011334 | 403769343 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011335 | 403769747 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011336 | 403770515 | High Sign | HFTD Tier 2 | Distribution | 2011-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011337 | 403770818 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011338 | 403771385 | Ground | HFTD Tier 3 | Distribution | 2011-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011339 | 403771386 | Molding | HFTD Tier 3 | Distribution | 2011-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011340 | 403771559 | High Sign | HFTD Tier 2 | Distribution | 2011-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011341 | 403772754 | High Sign | HFTD Tier 3 | Distribution | 2011-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011342 | 403772765 | Molding | HFTD Tier 3 | Distribution | 2011-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011343 | 403773650 | Guy | HFTD Tier 2 | Distribution | 2011-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011344 | 403773651 | Molding | HFTD Tier 2 | Distribution | 2011-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011345 | 403773664 | High Sign | HFTD Tier 2 | Distribution | 2011-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011346 | 403774439 | Bond | HFTD Tier 2 | Distribution | 2011-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011347 | 403774967 | High Sign | HFTD Tier 3 | Distribution | 2011-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011348 | 403774981 | Molding | HFTD Tier 3 | Distribution | 2011-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011349 | 403775039 | High Sign | HFTD Tier 3 | Distribution | 2011-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011350 | 403775045 | Molding | HFTD Tier 3 | Distribution | 2011-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011351 | 403775242 | High Sign | HFTD Tier 3 | Distribution | 2011-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011352 | 403775513 | Molding | HFTD Tier 2 | Distribution | 2011-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011353 | 403776369 | Molding | HFTD Tier 2 | Distribution | 2011-06-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011354 | 403776542 | Molding | HFTD Tier 2 | Distribution | 2011-06-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011355 | 403776829 | Molding | HFTD Tier 2 | Distribution | 2011-06-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011356 | 403776837 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-06-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011357 | 403776853 | Molding | HFTD Tier 3 | Distribution | 2011-06-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011358 | 403776973 | Guy | HFTD Tier 2 | Distribution | 2011-06-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011359 | 403781422 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011360 | 403782926 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011361 | 403783174 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011362 | 403784075 | Guy | HFTD Tier 3 | Distribution | 2011-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011363 | 403784230 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011364 | 403784272 | High Sign | HFTD Tier 2 | Distribution | 2011-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011365 | 403786560 | High Sign | HFTD Tier 2 | Distribution | 2011-06-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011366 | 403786562 | Molding | HFTD Tier 2 | Distribution | 2011-06-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011367 | 403786837 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-06-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011368 | 403787068 | High Sign | HFTD Tier 3 | Distribution | 2011-06-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011369 | 403788977 | High Sign | HFTD Tier 2 | Distribution | 2011-07-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011370 | 403789167 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-07-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011371 | 403789875 | Guy | HFTD Tier 3 | Distribution | 2011-07-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011372 | 403789892 | High Sign | HFTD Tier 3 | Distribution | 2011-07-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011373 | 403789893 | Guy | HFTD Tier 3 | Distribution | 2011-07-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011374 | 403790531 | High Sign | HFTD Tier 2 | Distribution | 2011-07-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011375 | 403790533 | High Sign | HFTD Tier 2 | Distribution | 2011-07-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011376 | 403793180 | High Sign | HFTD Tier 3 | Distribution | 2011-07-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011377 | 403795667 | High Sign | HFTD Tier 3 | Distribution | 2011-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011378 | 403794093 | High Sign | HFTD Tier 2 | Distribution | 2011-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011379 | 403802857 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-07-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011380 | 403802861 | Molding | HFTD Tier 3 | Distribution | 2011-07-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011381 | 403804392 | High Sign | HFTD Tier 3 | Distribution | 2011-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011382 | 403804395 | High Sign | HFTD Tier 3 | Distribution | 2011-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011383 | 403804680 | High Sign | HFTD Tier 2 | Distribution | 2011-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011384 | 403805538 | Molding | HFTD Tier 3 | Distribution | 2011-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011385 | 403806216 | Molding | HFTD Tier 3 | Distribution | 2011-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011386 | 403808919 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011387 | 403811643 | Molding | HFTD Tier 3 | Distribution | 2011-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011388 | 403811872 | Molding | HFTD Tier 2 | Distribution | 2011-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011389 | 403811882 | Molding | HFTD Tier 3 | Distribution | 2011-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011390 | 403811886 | Molding | HFTD Tier 3 | Distribution | 2011-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011391 | 403812437 | Molding | HFTD Tier 3 | Distribution | 2011-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011392 | 403812439 | High Sign | HFTD Tier 3 | Distribution | 2011-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011393 | 403813285 | Molding | HFTD Tier 3 | Distribution | 2011-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011394 | 403813288 | High Sign | HFTD Tier 3 | Distribution | 2011-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011395 | 403813358 | High Sign | HFTD Tier 2 | Distribution | 2011-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011396 | 403816036 | High Sign | HFTD Tier 2 | Distribution | 2011-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011397 | 403816053 | High Sign | HFTD Tier 2 | Distribution | 2011-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011398 | 403814315 | High Sign | HFTD Tier 2 | Distribution | 2011-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011399 | 403815621 | High Sign | HFTD Tier 3 | Distribution | 2011-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011400 | 403815670 | High Sign | HFTD Tier 3 | Distribution | 2011-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011401 | 403819109 | Molding | HFTD Tier 2 | Distribution | 2011-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011402 | 403820562 | High Sign | HFTD Tier 2 | Distribution | 2011-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011403 | 403820680 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011404 | 403822347 | High Sign | HFTD Tier 2 | Distribution | 2011-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011405 | 403822350 | Guy | HFTD Tier 2 | Distribution | 2011-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011406 | 403822665 | Guy | HFTD Tier 2 | Distribution | 2011-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011407 | 403822702 | High Sign | HFTD Tier 2 | Distribution | 2011-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011408 | 403823894 | Molding | HFTD Tier 3 | Distribution | 2011-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011409 | 403824223 | Molding | HFTD Tier 3 | Distribution | 2011-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011410 | 403824231 | High Sign | HFTD Tier 3 | Distribution | 2011-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011411 | 403824736 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011412 | 403827762 | Molding | HFTD Tier 3 | Distribution | 2011-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011413 | 403827765 | Molding | HFTD Tier 3 | Distribution | 2011-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011414 | 403827776 | Molding | HFTD Tier 3 | Distribution | 2011-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011415 | 403827813 | Molding | HFTD Tier 3 | Distribution | 2011-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011416 | 403827874 | High Sign | HFTD Tier 3 | Distribution | 2011-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011417 | 403827960 | Guy | HFTD Tier 2 | Distribution | 2011-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011418 | 403829483 | High Sign | HFTD Tier 3 | Distribution | 2011-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011419 | 403833226 | High Sign | HFTD Tier 3 | Distribution | 2011-07-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011420 | 403834986 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-07-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011421 | 403836228 | Molding | HFTD Tier 3 | Distribution | 2011-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011422 | 403844300 | Molding | HFTD Tier 2 | Distribution | 2011-08-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011423 | 403845792 | High Sign | HFTD Tier 2 | Distribution | 2011-08-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011424 | 403845813 | High Sign | HFTD Tier 2 | Distribution | 2011-08-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011425 | 403846846 | High Sign | HFTD Tier 2 | Distribution | 2011-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011426 | 403848459 | Guy | HFTD Tier 3 | Distribution | 2011-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011427 | 403848469 | Molding | HFTD Tier 3 | Distribution | 2011-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011428 | 403848481 | Guy | HFTD Tier 3 | Distribution | 2011-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011429 | 403849222 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-08-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011430 | 403849309 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-08-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011431 | 403849330 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-08-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011432 | 403849357 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-08-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011433 | 403850910 | Guy | HFTD Tier 3 | Distribution | 2011-08-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011434 | 403851350 | High Sign | HFTD Tier 3 | Distribution | 2011-08-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011435 | 403851351 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-08-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011436 | 403851261 | High Sign | HFTD Tier 3 | Distribution | 2011-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011437 | 403851273 | Guy | HFTD Tier 3 | Distribution | 2011-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011438 | 403851538 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011439 | 403852832 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011440 | 403853778 | Riser/Conduit | HFTD Tier 3 | Distribution | 2011-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011441 | 403854683 | High Sign | HFTD Tier 2 | Distribution | 2011-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011442 | 403859510 | Anchor | HFTD Tier 3 | Distribution | 2011-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011443 | 403856062 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011444 | 403856823 | Molding | HFTD Tier 2 | Distribution | 2011-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011445 | 403856835 | Riser/Conduit | HFTD Tier 2 | Distribution | 2011-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011446 | 403857512 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011447 | 403857513 | High Sign | HFTD Tier 2 | Distribution | 2011-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011448 | 403859515 | Molding | HFTD Tier 3 | Distribution | 2011-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011449 | 403859957 | High Sign | HFTD Tier 2 | Distribution | 2011-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011450 | 403858048 | Molding | HFTD Tier 3 | Distribution | 2011-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011451 | 403858053 | Molding | HFTD Tier 3 | Distribution | 2011-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011452 | 403858081 | Guy | HFTD Tier 3 | Distribution | 2011-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011453 | 403859159 | High Sign | HFTD Tier 2 | Distribution | 2011-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011454 | 403859173 | Molding | HFTD Tier 2 | Distribution | 2011-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011455 | 403859174 | High Sign | HFTD Tier 2 | Distribution | 2011-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011456 | 403859205 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011457 | 403859528 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011458 | 403859545 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011459 | 403859551 | Guy | HFTD Tier 3 | Distribution | 2011-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011460 | 403859990 | High Sign | HFTD Tier 2 | Distribution | 2011-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011461 | 403859992 | High Sign | HFTD Tier 2 | Distribution | 2011-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011462 | 403860692 | Insulator | HFTD Tier 2 | Distribution | 2011-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011463 | 403860855 | Molding | HFTD Tier 2 | Distribution | 2011-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011464 | 403860856 | High Sign | HFTD Tier 2 | Distribution | 2011-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011465 | 403861895 | Guy | HFTD Tier 2 | Distribution | 2011-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011466 | 403861896 | Guy | HFTD Tier 2 | Distribution | 2011-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011467 | 403861905 | Guy | HFTD Tier 2 | Distribution | 2011-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011468 | 403861915 | Guy | HFTD Tier 2 | Distribution | 2011-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011469 | 403862281 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011470 | 403864030 | High Sign | HFTD Tier 2 | Distribution | 2011-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011471 | 403867579 | Molding | HFTD Tier 3 | Distribution | 2011-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011472 | 403867930 | High Sign | HFTD Tier 2 | Distribution | 2011-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011473 | 403867988 | High Sign | HFTD Tier 2 | Distribution | 2011-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011474 | 403868703 | Guy | HFTD Tier 2 | Distribution | 2011-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011475 | 403869698 | High Sign | HFTD Tier 2 | Distribution | 2011-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011476 | 403869899 | High Sign | HFTD Tier 2 | Distribution | 2011-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011477 | 403869952 | High Sign | HFTD Tier 2 | Distribution | 2011-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011478 | 403870755 | Molding | HFTD Tier 2 | Distribution | 2011-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011479 | 403870854 | Molding | HFTD Tier 3 | Distribution | 2011-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011480 | 403871872 | High Sign | HFTD Tier 3 | Distribution | 2011-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011481 | 403871880 | High Sign | HFTD Tier 3 | Distribution | 2011-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011482 | 403872558 | High Sign | HFTD Tier 2 | Distribution | 2011-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011483 | 403873340 | High Sign | HFTD Tier 2 | Distribution | 2011-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011484 | 403873470 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011485 | 403873516 | Molding | HFTD Tier 3 | Distribution | 2011-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011486 | 403873530 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011487 | 403875190 | High Sign | HFTD Tier 2 | Distribution | 2011-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011488 | 403875859 | Molding | HFTD Tier 2 | Distribution | 2011-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011489 | 403875880 | Hardware/Framing | HFTD Tier 2 | Distribution | 2011-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011490 | 403876071 | High Sign | HFTD Tier 2 | Distribution | 2011-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011491 | 403876075 | High Sign | HFTD Tier 2 | Distribution | 2011-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011492 | 403877006 | High Sign | HFTD Tier 2 | Distribution | 2011-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011493 | 403879092 | Molding | HFTD Tier 3 | Distribution | 2011-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011494 | 403879095 | Molding | HFTD Tier 3 | Distribution | 2011-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011495 | 403879101 | High Sign | HFTD Tier 3 | Distribution | 2011-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011496 | 403879105 | Riser/Conduit | HFTD Tier 3 | Distribution | 2011-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011497 | 403883096 | Bond | HFTD Tier 2 | Distribution | 2011-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011498 | 403883098 | Molding | HFTD Tier 2 | Distribution | 2011-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011499 | 403883116 | Molding | HFTD Tier 2 | Distribution | 2011-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011500 | 403883582 | Molding | HFTD Tier 3 | Distribution | 2011-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011501 | 403884764 | High Sign | HFTD Tier 3 | Distribution | 2011-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011502 | 403884765 | Molding | HFTD Tier 3 | Distribution | 2011-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011503 | 403885746 | Guy | HFTD Tier 2 | Distribution | 2011-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011504 | 403886365 | Guy | HFTD Tier 2 | Distribution | 2011-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011505 | 403886377 | High Sign | HFTD Tier 2 | Distribution | 2011-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011506 | 403886496 | High Sign | HFTD Tier 2 | Distribution | 2011-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011507 | 403886505 | Molding | HFTD Tier 2 | Distribution | 2011-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011508 | 403886749 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011509 | 403886752 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011510 | 403889411 | Molding | HFTD Tier 2 | Distribution | 2011-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011511 | 403889415 | High Sign | HFTD Tier 2 | Distribution | 2011-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011512 | 403889023 | Riser/Conduit | HFTD Tier 2 | Distribution | 2011-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011513 | 403889198 | High Sign | HFTD Tier 2 | Distribution | 2011-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011514 | 403889417 | Molding | HFTD Tier 2 | Distribution | 2011-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011515 | 403889459 | Molding | HFTD Tier 2 | Distribution | 2011-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011516 | 403889503 | Molding | HFTD Tier 2 | Distribution | 2011-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011517 | 403889505 | High Sign | HFTD Tier 2 | Distribution | 2011-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011518 | 403890967 | High Sign | HFTD Tier 2 | Distribution | 2011-08-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011519 | 403891874 | High Sign | HFTD Tier 3 | Distribution | 2011-08-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011520 | 403893735 | High Sign | HFTD Tier 2 | Distribution | 2011-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011521 | 403895314 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011522 | 403896614 | High Sign | HFTD Tier 3 | Distribution | 2011-08-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011523 | 403900652 | High Sign | HFTD Tier 2 | Distribution | 2011-08-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011524 | 403900984 | Molding | HFTD Tier 3 | Distribution | 2011-08-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011525 | 403901347 | High Sign | HFTD Tier 3 | Distribution | 2011-08-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011526 | 403901362 | Molding | HFTD Tier 3 | Distribution | 2011-08-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011527 | 403904866 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-09-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011528 | 403904869 | Molding | HFTD Tier 2 | Distribution | 2011-09-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011529 | 403904873 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-09-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011530 | 403904881 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-09-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011531 | 403912121 | Molding | HFTD Tier 2 | Distribution | 2011-09-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011532 | 403913688 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-09-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011533 | 403913694 | High Sign | HFTD Tier 2 | Distribution | 2011-09-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011534 | 403917273 | High Sign | HFTD Tier 3 | Distribution | 2011-09-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011535 | 403919287 | Molding | HFTD Tier 3 | Distribution | 2011-09-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011536 | 403920547 | Molding | HFTD Tier 2 | Distribution | 2011-09-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011537 | 403920548 | High Sign | HFTD Tier 2 | Distribution | 2011-09-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011538 | 403924797 | Molding | HFTD Tier 3 | Distribution | 2011-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011539 | 403924802 | High Sign | HFTD Tier 3 | Distribution | 2011-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011540 | 403924810 | Molding | HFTD Tier 3 | Distribution | 2011-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011541 | 403926299 | Guy | HFTD Tier 2 | Distribution | 2011-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011542 | 403926302 | High Sign | HFTD Tier 2 | Distribution | 2011-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011543 | 403926318 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011544 | 403928272 | High Sign | HFTD Tier 3 | Distribution | 2011-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011545 | 403928300 | Molding | HFTD Tier 3 | Distribution | 2011-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011546 | 403928326 | High Sign | HFTD Tier 3 | Distribution | 2011-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011547 | 403928437 | High Sign | HFTD Tier 3 | Distribution | 2011-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011548 | 403930435 | Molding | HFTD Tier 2 | Distribution | 2011-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011549 | 403930438 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011550 | 403930439 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011551 | 403930564 | Guy | HFTD Tier 2 | Distribution | 2011-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011552 | 403934986 | Guy | HFTD Tier 2 | Distribution | 2011-09-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011553 | 403934987 | Guy | HFTD Tier 2 | Distribution | 2011-09-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011554 | 403935089 | Guy | HFTD Tier 2 | Distribution | 2011-09-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011555 | 403935109 | Guy | HFTD Tier 2 | Distribution | 2011-09-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011556 | 403939925 | High Sign | HFTD Tier 2 | Distribution | 2011-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011557 | 403939939 | Molding | HFTD Tier 2 | Distribution | 2011-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011558 | 403939945 | High Sign | HFTD Tier 2 | Distribution | 2011-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011559 | 403939960 | Guy | HFTD Tier 2 | Distribution | 2011-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011560 | 403939965 | Guy | HFTD Tier 2 | Distribution | 2011-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011561 | 403942737 | High Sign | HFTD Tier 2 | Distribution | 2011-09-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011562 | 403953804 | Molding | HFTD Tier 2 | Distribution | 2011-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011563 | 403953805 | Cable/Conductor | HFTD Tier 2 | Distribution | 2011-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011564 | 403959609 | High Sign | HFTD Tier 2 | Distribution | 2011-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011565 | 403962718 | Molding | HFTD Tier 2 | Distribution | 2011-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011566 | 403967247 | High Sign | HFTD Tier 2 | Distribution | 2011-10-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011567 | 403967847 | High Sign | HFTD Tier 2 | Distribution | 2011-10-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011568 | 403969939 | High Sign | HFTD Tier 2 | Distribution | 2011-10-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011569 | 403971885 | Ground | HFTD Tier 2 | Distribution | 2011-10-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011570 | 403971886 | Molding | HFTD Tier 2 | Distribution | 2011-10-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011571 | 403971895 | Molding | HFTD Tier 2 | Distribution | 2011-10-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011572 | 403971896 | Molding | HFTD Tier 2 | Distribution | 2011-10-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011573 | 403971910 | Molding | HFTD Tier 2 | Distribution | 2011-10-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011574 | 403971936 | Molding | HFTD Tier 2 | Distribution | 2011-10-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011575 | 403971945 | High Sign | HFTD Tier 2 | Distribution | 2011-10-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011576 | 403971947 | Molding | HFTD Tier 2 | Distribution | 2011-10-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011577 | 403971958 | Molding | HFTD Tier 2 | Distribution | 2011-10-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011578 | 403971993 | Molding | HFTD Tier 2 | Distribution | 2011-10-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011579 | 403971997 | Molding | HFTD Tier 2 | Distribution | 2011-10-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011580 | 403976299 | Molding | HFTD Tier 2 | Distribution | 2011-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011581 | 403985519 | High Sign | HFTD Tier 2 | Distribution | 2011-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011582 | 403985530 | Ground | HFTD Tier 2 | Distribution | 2011-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011583 | 403985531 | Molding | HFTD Tier 2 | Distribution | 2011-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011584 | 403985533 | Molding | HFTD Tier 2 | Distribution | 2011-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011585 | 403985536 | Molding | HFTD Tier 2 | Distribution | 2011-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011586 | 403985537 | High Sign | HFTD Tier 2 | Distribution | 2011-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011587 | 403985540 | High Sign | HFTD Tier 2 | Distribution | 2011-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011588 | 403985543 | Molding | HFTD Tier 2 | Distribution | 2011-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011589 | 403985545 | Molding | HFTD Tier 2 | Distribution | 2011-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011590 | 403985546 | Molding | HFTD Tier 2 | Distribution | 2011-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011591 | 403985548 | Molding | HFTD Tier 2 | Distribution | 2011-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011592 | 403985550 | Molding | HFTD Tier 2 | Distribution | 2011-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011593 | 403985554 | Molding | HFTD Tier 2 | Distribution | 2011-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011594 | 403985556 | High Sign | HFTD Tier 2 | Distribution | 2011-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011595 | 403985565 | High Sign | HFTD Tier 2 | Distribution | 2011-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011596 | 403990356 | High Sign | HFTD Tier 2 | Distribution | 2011-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011597 | 403990359 | High Sign | HFTD Tier 2 | Distribution | 2011-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011598 | 403990373 | Ground | HFTD Tier 2 | Distribution | 2011-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011599 | 403990591 | Molding | HFTD Tier 2 | Distribution | 2011-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011600 | 403993906 | Molding | HFTD Tier 3 | Distribution | 2011-10-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011601 | 403997902 | High Sign | HFTD Tier 2 | Distribution | 2011-10-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011602 | 404012424 | High Sign | HFTD Tier 3 | Distribution | 2011-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011603 | 404012426 | High Sign | HFTD Tier 3 | Distribution | 2011-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011604 | 404012427 | High Sign | HFTD Tier 3 | Distribution | 2011-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011605 | 404012428 | High Sign | HFTD Tier 3 | Distribution | 2011-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011606 | 404012434 | High Sign | HFTD Tier 3 | Distribution | 2011-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011607 | 404026109 | Molding | HFTD Tier 3 | Distribution | 2011-11-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011608 | 404033467 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-11-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011609 | 404033769 | High Sign | HFTD Tier 3 | Distribution | 2011-11-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011610 | 404035928 | Guy | HFTD Tier 3 | Distribution | 2011-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011611 | 404035942 | High Sign | HFTD Tier 3 | Distribution | 2011-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011612 | 404035966 | High Sign | HFTD Tier 3 | Distribution | 2011-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011613 | 404036037 | High Sign | HFTD Tier 3 | Distribution | 2011-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011614 | 404036041 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011615 | 404037819 | High Sign | HFTD Tier 3 | Distribution | 2011-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011616 | 404037835 | Molding | HFTD Tier 3 | Distribution | 2011-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011617 | 404037840 | High Sign | HFTD Tier 3 | Distribution | 2011-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011618 | 404037842 | High Sign | HFTD Tier 3 | Distribution | 2011-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011619 | 404038357 | High Sign | HFTD Tier 3 | Distribution | 2011-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011620 | 404038358 | Molding | HFTD Tier 3 | Distribution | 2011-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011621 | 404038359 | High Sign | HFTD Tier 3 | Distribution | 2011-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011622 | 404040389 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-11-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011623 | 404040390 | Molding | HFTD Tier 3 | Distribution | 2011-11-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011624 | 413873256 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-11-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011625 | 404042799 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-11-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011626 | 404042814 | Molding | HFTD Tier 3 | Distribution | 2011-11-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011627 | 404042829 | High Sign | HFTD Tier 3 | Distribution | 2011-11-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011628 | 404042832 | High Sign | HFTD Tier 3 | Distribution | 2011-11-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011629 | 404042834 | High Sign | HFTD Tier 3 | Distribution | 2011-11-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011630 | 404042835 | High Sign | HFTD Tier 3 | Distribution | 2011-11-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011631 | 407592921 | Riser/Conduit | HFTD Tier 3 | Distribution | 2011-11-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011632 | 407592932 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-11-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011633 | 404045376 | High Sign | HFTD Tier 2 | Distribution | 2011-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011634 | 404045513 | Molding | HFTD Tier 3 | Distribution | 2011-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011635 | 404045562 | High Sign | HFTD Tier 3 | Distribution | 2011-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011636 | 404047982 | High Sign | HFTD Tier 3 | Distribution | 2011-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011637 | 404047984 | High Sign | HFTD Tier 3 | Distribution | 2011-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011638 | 404047992 | Molding | HFTD Tier 3 | Distribution | 2011-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011639 | 404048198 | High Sign | HFTD Tier 3 | Distribution | 2011-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011640 | 404052112 | Molding | HFTD Tier 2 | Distribution | 2011-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011641 | 404050828 | High Sign | HFTD Tier 3 | Distribution | 2011-11-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011642 | 404050840 | High Sign | HFTD Tier 3 | Distribution | 2011-11-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011643 | 404050848 | Molding | HFTD Tier 3 | Distribution | 2011-11-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011644 | 404050852 | High Sign | HFTD Tier 3 | Distribution | 2011-11-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011645 | 404050854 | High Sign | HFTD Tier 3 | Distribution | 2011-11-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011646 | 404050856 | Molding | HFTD Tier 3 | Distribution | 2011-11-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011647 | 404050862 | High Sign | HFTD Tier 3 | Distribution | 2011-11-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011648 | 404050864 | High Sign | HFTD Tier 3 | Distribution | 2011-11-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011649 | 404050865 | High Sign | HFTD Tier 3 | Distribution | 2011-11-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011650 | 404050870 | High Sign | HFTD Tier 3 | Distribution | 2011-11-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011651 | 404052718 | High Sign | HFTD Tier 3 | Distribution | 2011-11-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011652 | 404052940 | High Sign | HFTD Tier 3 | Distribution | 2011-11-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011653 | 404052946 | High Sign | HFTD Tier 3 | Distribution | 2011-11-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011654 | 404052947 | High Sign | HFTD Tier 3 | Distribution | 2011-11-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011655 | 404052950 | Guy | HFTD Tier 3 | Distribution | 2011-11-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011656 | 404052952 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-11-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011657 | 404052953 | High Sign | HFTD Tier 3 | Distribution | 2011-11-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011658 | 404052957 | High Sign | HFTD Tier 3 | Distribution | 2011-11-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011659 | 404052961 | High Sign | HFTD Tier 3 | Distribution | 2011-11-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011660 | 404052964 | High Sign | HFTD Tier 3 | Distribution | 2011-11-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011661 | 404054308 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011662 | 404054319 | High Sign | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011663 | 404054328 | High Sign | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011664 | 404054332 | High Sign | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011665 | 404054351 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011666 | 404054359 | High Sign | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011667 | 404054364 | High Sign | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011668 | 404054373 | High Sign | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011669 | 404054380 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011670 | 404054382 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011671 | 404054386 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011672 | 404054391 | High Sign | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011673 | 404054401 | High Sign | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011674 | 404054408 | High Sign | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011675 | 404054420 | High Sign | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011676 | 404054422 | High Sign | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011677 | 404054424 | Molding | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011678 | 404054446 | High Sign | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011679 | 404054895 | High Sign | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011680 | 404054896 | High Sign | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011681 | 404054978 | High Sign | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011682 | 404054979 | High Sign | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011683 | 404054989 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011684 | 404054996 | High Sign | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011685 | 404055006 | High Sign | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011686 | 404055013 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011687 | 404055023 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011688 | 404055024 | Molding | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011689 | 404055027 | Molding | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011690 | 404055029 | High Sign | HFTD Tier 3 | Distribution | 2011-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011691 | 404055845 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-11-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011692 | 404055876 | High Sign | HFTD Tier 3 | Distribution | 2011-11-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011693 | 404055877 | Molding | HFTD Tier 3 | Distribution | 2011-11-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011694 | 404055919 | High Sign | HFTD Tier 3 | Distribution | 2011-11-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011695 | 404059431 | Riser/Conduit | HFTD Tier 3 | Distribution | 2011-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011696 | 404059433 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011697 | 404059436 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011698 | 404059446 | Molding | HFTD Tier 3 | Distribution | 2011-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011699 | 404059447 | High Sign | HFTD Tier 3 | Distribution | 2011-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011700 | 404059460 | Molding | HFTD Tier 3 | Distribution | 2011-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011701 | 404059461 | Molding | HFTD Tier 3 | Distribution | 2011-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011702 | 404059462 | High Sign | HFTD Tier 3 | Distribution | 2011-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011703 | 404059463 | High Sign | HFTD Tier 3 | Distribution | 2011-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011704 | 404061599 | Guy | HFTD Tier 3 | Distribution | 2011-11-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011705 | 404061602 | Riser/Conduit | HFTD Tier 3 | Distribution | 2011-11-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011706 | 404061604 | Bond | HFTD Tier 3 | Distribution | 2011-11-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011707 | 404061613 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-11-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011708 | 404061630 | Molding | HFTD Tier 3 | Distribution | 2011-11-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011709 | 404061633 | Molding | HFTD Tier 3 | Distribution | 2011-11-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011710 | 404061636 | High Sign | HFTD Tier 3 | Distribution | 2011-11-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011711 | 404061650 | High Sign | HFTD Tier 3 | Distribution | 2011-11-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011712 | 404062138 | High Sign | HFTD Tier 2 | Distribution | 2011-11-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011713 | 404062161 | High Sign | HFTD Tier 2 | Distribution | 2011-11-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011714 | 404063768 | Molding | HFTD Tier 3 | Distribution | 2011-11-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011715 | 404063769 | High Sign | HFTD Tier 3 | Distribution | 2011-11-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011716 | 404063772 | Bond | HFTD Tier 3 | Distribution | 2011-11-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011717 | 404063801 | High Sign | HFTD Tier 3 | Distribution | 2011-11-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011718 | 404066337 | Molding | HFTD Tier 3 | Distribution | 2011-11-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011719 | 404066385 | Molding | HFTD Tier 3 | Distribution | 2011-11-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011720 | 404067024 | Molding | HFTD Tier 3 | Distribution | 2011-11-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011721 | 404067040 | Hardware/Framing | HFTD Tier 3 | Distribution | 2011-11-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011722 | 404067058 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-11-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011723 | 404069364 | Molding | HFTD Tier 3 | Distribution | 2011-11-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011724 | 404069365 | High Sign | HFTD Tier 3 | Distribution | 2011-11-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011725 | 404069367 | High Sign | HFTD Tier 3 | Distribution | 2011-11-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011726 | 404069368 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-11-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011727 | 404069401 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-11-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011728 | 404071377 | Riser/Conduit | HFTD Tier 3 | Distribution | 2011-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011729 | 404071398 | High Sign | HFTD Tier 3 | Distribution | 2011-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011730 | 404071413 | High Sign | HFTD Tier 3 | Distribution | 2011-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011731 | 404071431 | High Sign | HFTD Tier 3 | Distribution | 2011-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011732 | 404073493 | High Sign | HFTD Tier 3 | Distribution | 2011-12-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011733 | 404073546 | High Sign | HFTD Tier 3 | Distribution | 2011-12-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011734 | 404073550 | Molding | HFTD Tier 3 | Distribution | 2011-12-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011735 | 404074804 | Molding | HFTD Tier 2 | Distribution | 2011-12-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011736 | 404075536 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-12-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011737 | 404087586 | High Sign | HFTD Tier 2 | Distribution | 2011-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011738 | 404088499 | Guy | HFTD Tier 3 | Distribution | 2011-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011739 | 404088506 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011740 | 404088575 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011741 | 404088591 | Guy | HFTD Tier 3 | Distribution | 2011-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011742 | 404090148 | High Sign | HFTD Tier 3 | Distribution | 2011-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011743 | 404090805 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011744 | 404093153 | Molding | HFTD Tier 3 | Distribution | 2011-12-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011745 | 404093603 | Molding | HFTD Tier 2 | Distribution | 2011-12-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011746 | 404094609 | High Sign | HFTD Tier 3 | Distribution | 2011-12-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011747 | 404094611 | High Sign | HFTD Tier 3 | Distribution | 2011-12-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011748 | 415401182 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2011-12-10 | 40980 | 2 | Ignition Risk, no GO95 exception | [7 empty] | SCE | 2026 | 2
1120011749 | 404108724 | High Sign | HFTD Tier 2 | Distribution | 2011-12-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011750 | 404111301 | High Sign | HFTD Tier 3 | Distribution | 2011-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011751 | 404117025 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011752 | 404117026 | Riser/Conduit | HFTD Tier 3 | Distribution | 2011-12-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011753 | 404119822 | Cable/Conductor | HFTD Tier 3 | Distribution | 2011-12-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011754 | 404119835 | Molding | HFTD Tier 3 | Distribution | 2011-12-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011755 | 404121083 | Molding | HFTD Tier 3 | Distribution | 2011-12-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011756 | 404121114 | Guy | HFTD Tier 3 | Distribution | 2011-12-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011757 | 404121124 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2011-12-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011758 | 404154596 | Guy | HFTD Tier 2 | Distribution | 2012-01-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011759 | 404158144 | Guy | HFTD Tier 3 | Distribution | 2012-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011760 | 404161344 | High Sign | HFTD Tier 2 | Distribution | 2012-01-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011761 | 404176999 | Molding | HFTD Tier 2 | Distribution | 2012-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011762 | 404180083 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011763 | 404180087 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011764 | 404181460 | Molding | HFTD Tier 2 | Distribution | 2012-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011765 | 404182398 | Riser/Conduit | HFTD Tier 3 | Distribution | 2012-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011766 | 404182425 | Molding | HFTD Tier 3 | Distribution | 2012-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011767 | 404182444 | Guy | HFTD Tier 3 | Distribution | 2012-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011768 | 404183533 | Molding | HFTD Tier 3 | Distribution | 2012-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011769 | 404183599 | High Sign | HFTD Tier 3 | Distribution | 2012-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011770 | 404183959 | High Sign | HFTD Tier 3 | Distribution | 2012-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011771 | 404184999 | Molding | HFTD Tier 2 | Distribution | 2012-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011772 | 404185729 | High Sign | HFTD Tier 3 | Distribution | 2012-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011773 | 404185862 | Molding | HFTD Tier 3 | Distribution | 2012-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011774 | 404185863 | High Sign | HFTD Tier 3 | Distribution | 2012-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011775 | 404186683 | Guy | HFTD Tier 3 | Distribution | 2012-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011776 | 404187879 | Molding | HFTD Tier 3 | Distribution | 2012-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011777 | 404188803 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011778 | 404190479 | Riser/Conduit | HFTD Tier 2 | Distribution | 2012-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011779 | 404190846 | High Sign | HFTD Tier 3 | Distribution | 2012-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011780 | 404191220 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011781 | 404191916 | Molding | HFTD Tier 2 | Distribution | 2012-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011782 | 404192809 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011783 | 404193920 | Molding | HFTD Tier 3 | Distribution | 2012-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011784 | 404194239 | Molding | HFTD Tier 3 | Distribution | 2012-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011785 | 404194544 | Molding | HFTD Tier 2 | Distribution | 2012-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011786 | 404194567 | High Sign | HFTD Tier 2 | Distribution | 2012-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011787 | 404194571 | Molding | HFTD Tier 2 | Distribution | 2012-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011788 | 404194637 | Molding | HFTD Tier 2 | Distribution | 2012-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011789 | 404195535 | High Sign | HFTD Tier 3 | Distribution | 2012-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011790 | 404195543 | High Sign | HFTD Tier 3 | Distribution | 2012-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011791 | 404195574 | High Sign | HFTD Tier 3 | Distribution | 2012-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011792 | 404195723 | Molding | HFTD Tier 3 | Distribution | 2012-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011793 | 404195724 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011794 | 404195732 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011795 | 404195749 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011796 | 404195897 | Riser/Conduit | HFTD Tier 3 | Distribution | 2012-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011797 | 404196475 | Guy | HFTD Tier 3 | Distribution | 2012-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011798 | 404198651 | High Sign | HFTD Tier 3 | Distribution | 2012-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011799 | 404199984 | High Sign | HFTD Tier 3 | Distribution | 2012-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011800 | 404199986 | High Sign | HFTD Tier 3 | Distribution | 2012-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011801 | 404199998 | High Sign | HFTD Tier 3 | Distribution | 2012-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011802 | 404200001 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011803 | 404200009 | High Sign | HFTD Tier 3 | Distribution | 2012-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011804 | 404200019 | High Sign | HFTD Tier 3 | Distribution | 2012-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011805 | 404200030 | High Sign | HFTD Tier 3 | Distribution | 2012-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011806 | 404200588 | Molding | HFTD Tier 2 | Distribution | 2012-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011807 | 404200617 | Molding | HFTD Tier 3 | Distribution | 2012-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011808 | 404200623 | Molding | HFTD Tier 3 | Distribution | 2012-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011809 | 404201496 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011810 | 404201517 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011811 | 404203565 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011812 | 404203585 | Molding | HFTD Tier 3 | Distribution | 2012-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011813 | 404203592 | High Sign | HFTD Tier 3 | Distribution | 2012-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011814 | 404205415 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011815 | 404205449 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011816 | 404205454 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011817 | 404205461 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011818 | 404206104 | Molding | HFTD Tier 2 | Distribution | 2012-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011819 | 404206713 | Molding | HFTD Tier 2 | Distribution | 2012-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011820 | 404206865 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011821 | 404209675 | Riser/Conduit | HFTD Tier 3 | Distribution | 2012-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011822 | 404209693 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011823 | 404209729 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011824 | 404210643 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011825 | 404210809 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011826 | 404210817 | Molding | HFTD Tier 3 | Distribution | 2012-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011827 | 404210837 | Molding | HFTD Tier 3 | Distribution | 2012-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011828 | 404210841 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011829 | 404210851 | Molding | HFTD Tier 3 | Distribution | 2012-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011830 | 404210882 | Guy | HFTD Tier 2 | Distribution | 2012-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011831 | 404211245 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011832 | 404211557 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011833 | 404213239 | Molding | HFTD Tier 2 | Distribution | 2012-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011834 | 404213434 | High Sign | HFTD Tier 3 | Distribution | 2012-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011835 | 404213435 | High Sign | HFTD Tier 3 | Distribution | 2012-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011836 | 404214435 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011837 | 404214449 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011838 | 404214470 | High Sign | HFTD Tier 3 | Distribution | 2012-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011839 | 404216342 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011840 | 404216652 | High Sign | HFTD Tier 3 | Distribution | 2012-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011841 | 404216738 | High Sign | HFTD Tier 3 | Distribution | 2012-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011842 | 404216742 | Molding | HFTD Tier 3 | Distribution | 2012-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011843 | 404216754 | High Sign | HFTD Tier 3 | Distribution | 2012-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011844 | 404216768 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011845 | 404218264 | Guy | HFTD Tier 3 | Distribution | 2012-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011846 | 404218809 | High Sign | HFTD Tier 2 | Distribution | 2012-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011847 | 404218814 | Molding | HFTD Tier 2 | Distribution | 2012-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011848 | 404218822 | Molding | HFTD Tier 2 | Distribution | 2012-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011849 | 404220188 | High Sign | HFTD Tier 3 | Distribution | 2012-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011850 | 404223119 | High Sign | HFTD Tier 2 | Distribution | 2012-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011851 | 404223123 | High Sign | HFTD Tier 2 | Distribution | 2012-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011852 | 404223137 | High Sign | HFTD Tier 2 | Distribution | 2012-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011853 | 404223378 | Molding | HFTD Tier 2 | Distribution | 2012-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011854 | 404224366 | Guy | HFTD Tier 3 | Distribution | 2012-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011855 | 404224388 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011856 | 404224669 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011857 | 404225897 | High Sign | HFTD Tier 2 | Distribution | 2012-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011858 | 404225931 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011859 | 404226209 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011860 | 404226593 | High Sign | HFTD Tier 3 | Distribution | 2012-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011861 | 404228805 | Riser/Conduit | HFTD Tier 2 | Distribution | 2012-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011862 | 404230160 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011863 | 404230176 | Bond | HFTD Tier 3 | Distribution | 2012-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011864 | 404230179 | Riser/Conduit | HFTD Tier 3 | Distribution | 2012-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011865 | 404230183 | Bond | HFTD Tier 3 | Distribution | 2012-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011866 | 404233643 | Guy | HFTD Tier 3 | Distribution | 2012-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011867 | 404234161 | Molding | HFTD Tier 3 | Distribution | 2012-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011868 | 404234198 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011869 | 404234207 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011870 | 404234234 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011871 | 404235379 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011872 | 404235382 | Molding | HFTD Tier 2 | Distribution | 2012-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011873 | 404235911 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011874 | 404236742 | High Sign | HFTD Tier 3 | Distribution | 2012-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011875 | 404236763 | High Sign | HFTD Tier 3 | Distribution | 2012-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011876 | 404236767 | Molding | HFTD Tier 3 | Distribution | 2012-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011877 | 404236828 | High Sign | HFTD Tier 3 | Distribution | 2012-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011878 | 404236836 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011879 | 404236854 | Guy | HFTD Tier 2 | Distribution | 2012-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011880 | 404236906 | Guy | HFTD Tier 2 | Distribution | 2012-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011881 | 404238889 | Molding | HFTD Tier 2 | Distribution | 2012-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011882 | 404238930 | High Sign | HFTD Tier 2 | Distribution | 2012-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011883 | 404238774 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011884 | 404238965 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011885 | 404238966 | High Sign | HFTD Tier 2 | Distribution | 2012-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011886 | 404238967 | Molding | HFTD Tier 2 | Distribution | 2012-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011887 | 404238975 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011888 | 404238976 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011889 | 404239006 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011890 | 404240000 | High Sign | HFTD Tier 2 | Distribution | 2012-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011891 | 404243066 | High Sign | HFTD Tier 3 | Distribution | 2012-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011892 | 404243081 | High Sign | HFTD Tier 3 | Distribution | 2012-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011893 | 404243086 | Molding | HFTD Tier 3 | Distribution | 2012-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011894 | 404246875 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011895 | 404244527 | High Sign | HFTD Tier 3 | Distribution | 2012-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011896 | 404246079 | Molding | HFTD Tier 2 | Distribution | 2012-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011897 | 404247526 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011898 | 404247958 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011899 | 404248258 | Molding | HFTD Tier 2 | Distribution | 2012-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011900 | 404248656 | Molding | HFTD Tier 3 | Distribution | 2012-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011901 | 404248672 | Molding | HFTD Tier 3 | Distribution | 2012-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011902 | 404248675 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011903 | 404249764 | Molding | HFTD Tier 2 | Distribution | 2012-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011904 | 404250177 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011905 | 404252389 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011906 | 404258257 | Molding | HFTD Tier 2 | Distribution | 2012-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011907 | 404255338 | Cutout/Fuse | HFTD Tier 3 | Distribution | 2012-02-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011908 | 404255911 | Molding | HFTD Tier 2 | Distribution | 2012-02-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011909 | 404257211 | High Sign | HFTD Tier 3 | Distribution | 2012-02-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011910 | 404258277 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-02-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011911 | 404258280 | Molding | HFTD Tier 2 | Distribution | 2012-02-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011912 | 404258288 | Molding | HFTD Tier 2 | Distribution | 2012-02-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011913 | 404259305 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011914 | 404261374 | Ground | HFTD Tier 3 | Distribution | 2012-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011915 | 404261948 | Molding | HFTD Tier 2 | Distribution | 2012-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011916 | 404264633 | High Sign | HFTD Tier 3 | Distribution | 2012-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011917 | 404264829 | High Sign | HFTD Tier 2 | Distribution | 2012-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011918 | 404264833 | Molding | HFTD Tier 2 | Distribution | 2012-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011919 | 404264838 | Molding | HFTD Tier 2 | Distribution | 2012-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011920 | 404266410 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011921 | 404268423 | Guy | HFTD Tier 2 | Distribution | 2012-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011922 | 404269546 | Molding | HFTD Tier 3 | Distribution | 2012-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011923 | 404269567 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011924 | 404270661 | High Sign | HFTD Tier 3 | Distribution | 2012-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011925 | 404270843 | Molding | HFTD Tier 2 | Distribution | 2012-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011926 | 404270844 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011927 | 404273954 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011928 | 404273959 | Guy | HFTD Tier 2 | Distribution | 2012-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011929 | 404273967 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011930 | 404273968 | Molding | HFTD Tier 2 | Distribution | 2012-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011931 | 404273972 | Guy | HFTD Tier 2 | Distribution | 2012-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011932 | 404274002 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011933 | 404274288 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-02-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011934 | 404277646 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-02-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011935 | 404278453 | Molding | HFTD Tier 2 | Distribution | 2012-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011936 | 404278489 | Vis Strips | HFTD Tier 2 | Distribution | 2012-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011937 | 404278561 | High Sign | HFTD Tier 2 | Distribution | 2012-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011938 | 404278864 | High Sign | HFTD Tier 2 | Distribution | 2012-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011939 | 404280884 | High Sign | HFTD Tier 3 | Distribution | 2012-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011940 | 404280895 | Molding | HFTD Tier 3 | Distribution | 2012-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011941 | 404280914 | Molding | HFTD Tier 3 | Distribution | 2012-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011942 | 404282842 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-02-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011943 | 404284052 | Molding | HFTD Tier 3 | Distribution | 2012-02-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011944 | 404284053 | Molding | HFTD Tier 3 | Distribution | 2012-02-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011945 | 404284109 | Guy | HFTD Tier 3 | Distribution | 2012-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011946 | 404284119 | Insulator | HFTD Tier 3 | Distribution | 2012-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011947 | 404284120 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011948 | 404287247 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011949 | 404287292 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011950 | 404287299 | High Sign | HFTD Tier 2 | Distribution | 2012-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011951 | 404287957 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011952 | 404291137 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011953 | 404291333 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011954 | 404291341 | Molding | HFTD Tier 2 | Distribution | 2012-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011955 | 404291344 | High Sign | HFTD Tier 2 | Distribution | 2012-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011956 | 404291433 | High Sign | HFTD Tier 3 | Distribution | 2012-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011957 | 404291456 | Molding | HFTD Tier 3 | Distribution | 2012-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011958 | 404291459 | High Sign | HFTD Tier 3 | Distribution | 2012-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011959 | 404291487 | High Sign | HFTD Tier 3 | Distribution | 2012-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011960 | 404291734 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011961 | 404291752 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011962 | 404291756 | High Sign | HFTD Tier 2 | Distribution | 2012-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011963 | 404292789 | Bond | HFTD Tier 3 | Distribution | 2012-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011964 | 404292841 | High Sign | HFTD Tier 3 | Distribution | 2012-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011965 | 404293982 | High Sign | HFTD Tier 3 | Distribution | 2012-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011966 | 404293983 | Molding | HFTD Tier 3 | Distribution | 2012-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011967 | 404293984 | High Sign | HFTD Tier 3 | Distribution | 2012-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011968 | 404294059 | Guy | HFTD Tier 3 | Distribution | 2012-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011969 | 404294065 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011970 | 404294070 | Guy | HFTD Tier 3 | Distribution | 2012-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011971 | 404296956 | Molding | HFTD Tier 2 | Distribution | 2012-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011972 | 404296971 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011973 | 404301926 | High Sign | HFTD Tier 2 | Distribution | 2012-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011974 | 404301931 | Guy | HFTD Tier 2 | Distribution | 2012-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011975 | 404302061 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011976 | 404304099 | Riser/Conduit | HFTD Tier 2 | Distribution | 2012-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011977 | 404304125 | Molding | HFTD Tier 2 | Distribution | 2012-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011978 | 404307501 | High Sign | HFTD Tier 2 | Distribution | 2012-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011979 | 404307530 | Guy | HFTD Tier 2 | Distribution | 2012-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011980 | 404309243 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011981 | 404309685 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011982 | 404309700 | Molding | HFTD Tier 2 | Distribution | 2012-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011983 | 404310476 | Ground | HFTD Tier 2 | Distribution | 2012-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011984 | 404310723 | High Sign | HFTD Tier 2 | Distribution | 2012-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011985 | 404313603 | High Sign | HFTD Tier 3 | Distribution | 2012-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011986 | 404314229 | High Sign | HFTD Tier 2 | Distribution | 2012-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011987 | 404315179 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011988 | 404317374 | Molding | HFTD Tier 2 | Distribution | 2012-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011989 | 404317419 | Molding | HFTD Tier 2 | Distribution | 2012-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011990 | 404317435 | High Sign | HFTD Tier 2 | Distribution | 2012-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011991 | 404317851 | Molding | HFTD Tier 2 | Distribution | 2012-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011992 | 404317852 | High Sign | HFTD Tier 2 | Distribution | 2012-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011993 | 404317860 | Molding | HFTD Tier 2 | Distribution | 2012-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011994 | 404317882 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011995 | 404317949 | High Sign | HFTD Tier 2 | Distribution | 2012-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011996 | 404320758 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011997 | 404320858 | High Sign | HFTD Tier 2 | Distribution | 2012-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011998 | 404320876 | Molding | HFTD Tier 2 | Distribution | 2012-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120011999 | 404321047 | High Sign | HFTD Tier 2 | Distribution | 2012-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012000 | 404321065 | Molding | HFTD Tier 2 | Distribution | 2012-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012001 | 404322980 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012002 | 404324776 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012003 | 404324787 | Vis Strips | HFTD Tier 2 | Distribution | 2012-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012004 | 404324806 | Vis Strips | HFTD Tier 2 | Distribution | 2012-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012005 | 404326078 | Insulator | HFTD Tier 3 | Distribution | 2012-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012006 | 404327559 | High Sign | HFTD Tier 2 | Distribution | 2012-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012007 | 404327581 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012008 | 404327596 | Pole Tag | HFTD Tier 2 | Distribution | 2012-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012009 | 404327600 | Molding | HFTD Tier 2 | Distribution | 2012-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012010 | 404327622 | High Sign | HFTD Tier 2 | Distribution | 2012-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012011 | 404330647 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012012 | 404331900 | High Sign | HFTD Tier 3 | Distribution | 2012-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012013 | 404332130 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012014 | 404335617 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012015 | 404339045 | Molding | HFTD Tier 2 | Distribution | 2012-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012016 | 404339047 | High Sign | HFTD Tier 2 | Distribution | 2012-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012017 | 404339072 | High Sign | HFTD Tier 2 | Distribution | 2012-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012018 | 404339074 | Molding | HFTD Tier 2 | Distribution | 2012-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012019 | 404339093 | Molding | HFTD Tier 2 | Distribution | 2012-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012020 | 404339100 | High Sign | HFTD Tier 2 | Distribution | 2012-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012021 | 404339115 | Molding | HFTD Tier 2 | Distribution | 2012-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012022 | 404339118 | High Sign | HFTD Tier 2 | Distribution | 2012-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012023 | 404339119 | Molding | HFTD Tier 2 | Distribution | 2012-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012024 | 404339388 | Molding | HFTD Tier 2 | Distribution | 2012-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012025 | 404340078 | High Sign | HFTD Tier 2 | Distribution | 2012-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012026 | 404340085 | High Sign | HFTD Tier 2 | Distribution | 2012-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012027 | 404340088 | Molding | HFTD Tier 2 | Distribution | 2012-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012028 | 404340094 | High Sign | HFTD Tier 2 | Distribution | 2012-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012029 | 404340110 | High Sign | HFTD Tier 2 | Distribution | 2012-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012030 | 404340826 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012031 | 404343848 | Molding | HFTD Tier 2 | Distribution | 2012-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012032 | 404347615 | Molding | HFTD Tier 3 | Distribution | 2012-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012033 | 404343648 | High Sign | HFTD Tier 2 | Distribution | 2012-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012034 | 404343830 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012035 | 404345403 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012036 | 404345419 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012037 | 404347083 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012038 | 404347129 | High Sign | HFTD Tier 3 | Distribution | 2012-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012039 | 404347134 | Molding | HFTD Tier 3 | Distribution | 2012-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012040 | 404347163 | High Sign | HFTD Tier 3 | Distribution | 2012-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012041 | 404347197 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012042 | 404347243 | Guy | HFTD Tier 2 | Distribution | 2012-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012043 | 404347272 | High Sign | HFTD Tier 2 | Distribution | 2012-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012044 | 404347430 | Molding | HFTD Tier 2 | Distribution | 2012-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012045 | 404347487 | Guy | HFTD Tier 2 | Distribution | 2012-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012046 | 404348699 | High Sign | HFTD Tier 2 | Distribution | 2012-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012047 | 404348702 | High Sign | HFTD Tier 2 | Distribution | 2012-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012048 | 404350491 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012049 | 404350531 | High Sign | HFTD Tier 3 | Distribution | 2012-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012050 | 404350563 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012051 | 404350731 | Molding | HFTD Tier 2 | Distribution | 2012-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012052 | 404350738 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012053 | 404350742 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012054 | 404353260 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012055 | 404353288 | Molding | HFTD Tier 2 | Distribution | 2012-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012056 | 404352902 | High Sign | HFTD Tier 2 | Distribution | 2012-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012057 | 404353361 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012058 | 404353370 | High Sign | HFTD Tier 2 | Distribution | 2012-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012059 | 404353393 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012060 | 404353705 | High Sign | HFTD Tier 3 | Distribution | 2012-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012061 | 404354835 | Guy | HFTD Tier 2 | Distribution | 2012-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012062 | 404354838 | Molding | HFTD Tier 2 | Distribution | 2012-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012063 | 404354839 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012064 | 404356246 | Molding | HFTD Tier 2 | Distribution | 2012-04-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012065 | 404357801 | High Sign | HFTD Tier 2 | Distribution | 2012-04-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012066 | 404357969 | Guy | HFTD Tier 3 | Distribution | 2012-04-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012067 | 404357993 | Guy | HFTD Tier 3 | Distribution | 2012-04-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012068 | 404357999 | High Sign | HFTD Tier 3 | Distribution | 2012-04-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012069 | 404358001 | Guy | HFTD Tier 3 | Distribution | 2012-04-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012070 | 404358019 | High Sign | HFTD Tier 3 | Distribution | 2012-04-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012071 | 404359321 | Molding | HFTD Tier 2 | Distribution | 2012-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012072 | 404359471 | Molding | HFTD Tier 2 | Distribution | 2012-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012073 | 404361256 | Molding | HFTD Tier 3 | Distribution | 2012-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012074 | 404361362 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012075 | 404361705 | High Sign | HFTD Tier 2 | Distribution | 2012-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012076 | 404361713 | High Sign | HFTD Tier 2 | Distribution | 2012-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012077 | 413873259 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012078 | 404362694 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012079 | 404362744 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012080 | 404362906 | High Sign | HFTD Tier 2 | Distribution | 2012-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012081 | 404364409 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012082 | 404364589 | Molding | HFTD Tier 2 | Distribution | 2012-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012083 | 404364602 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012084 | 404364672 | Guy | HFTD Tier 2 | Distribution | 2012-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012085 | 404364785 | Molding | HFTD Tier 3 | Distribution | 2012-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012086 | 404365792 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012087 | 404367210 | High Sign | HFTD Tier 2 | Distribution | 2012-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012088 | 404367272 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012089 | 404367335 | Molding | HFTD Tier 3 | Distribution | 2012-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012090 | 404367349 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012091 | 404369402 | High Sign | HFTD Tier 3 | Distribution | 2012-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012092 | 404369470 | Guy | HFTD Tier 3 | Distribution | 2012-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012093 | 404369493 | Molding | HFTD Tier 3 | Distribution | 2012-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012094 | 404369696 | Guy | HFTD Tier 3 | Distribution | 2012-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012095 | 404369746 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012096 | 404369751 | High Sign | HFTD Tier 3 | Distribution | 2012-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012097 | 404372502 | High Sign | HFTD Tier 3 | Distribution | 2012-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012098 | 404373619 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012099 | 404373630 | High Sign | HFTD Tier 3 | Distribution | 2012-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012100 | 404373700 | Guy | HFTD Tier 3 | Distribution | 2012-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012101 | 404375218 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012102 | 404375226 | High Sign | HFTD Tier 3 | Distribution | 2012-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012103 | 404376428 | Molding | HFTD Tier 3 | Distribution | 2012-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012104 | 404376447 | High Sign | HFTD Tier 3 | Distribution | 2012-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012105 | 404382551 | High Sign | HFTD Tier 3 | Distribution | 2012-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012106 | 404383034 | Guy | HFTD Tier 2 | Distribution | 2012-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012107 | 404383274 | Molding | HFTD Tier 3 | Distribution | 2012-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012108 | 404383365 | High Sign | HFTD Tier 2 | Distribution | 2012-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012109 | 404384163 | High Sign | HFTD Tier 2 | Distribution | 2012-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012110 | 404385708 | Molding | HFTD Tier 2 | Distribution | 2012-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012111 | 404385723 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012112 | 404386563 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012113 | 404386963 | High Sign | HFTD Tier 2 | Distribution | 2012-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012114 | 404387268 | High Sign | HFTD Tier 2 | Distribution | 2012-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012115 | 404388121 | High Sign | HFTD Tier 2 | Distribution | 2012-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012116 | 404388126 | Molding | HFTD Tier 3 | Distribution | 2012-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012117 | 404388246 | High Sign | HFTD Tier 3 | Distribution | 2012-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012118 | 404390418 | Molding | HFTD Tier 3 | Distribution | 2012-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012119 | 404391314 | High Sign | HFTD Tier 2 | Distribution | 2012-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012120 | 404391325 | High Sign | HFTD Tier 2 | Distribution | 2012-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012121 | 404391342 | High Sign | HFTD Tier 2 | Distribution | 2012-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012122 | 404391450 | High Sign | HFTD Tier 2 | Distribution | 2012-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012123 | 404394415 | High Sign | HFTD Tier 3 | Distribution | 2012-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012124 | 404394200 | Guy | HFTD Tier 3 | Distribution | 2012-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012125 | 404395287 | Guy | HFTD Tier 2 | Distribution | 2012-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012126 | 404395302 | Guy | HFTD Tier 2 | Distribution | 2012-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012127 | 404395612 | High Sign | HFTD Tier 3 | Distribution | 2012-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012128 | 404396512 | Molding | HFTD Tier 2 | Distribution | 2012-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012129 | 404396737 | Molding | HFTD Tier 2 | Distribution | 2012-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012130 | 404396779 | Riser/Conduit | HFTD Tier 3 | Distribution | 2012-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012131 | 404397289 | High Sign | HFTD Tier 3 | Distribution | 2012-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012132 | 404397301 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012133 | 404397310 | High Sign | HFTD Tier 3 | Distribution | 2012-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012134 | 404398005 | Guy | HFTD Tier 2 | Distribution | 2012-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012135 | 404398011 | Guy | HFTD Tier 2 | Distribution | 2012-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012136 | 404398016 | High Sign | HFTD Tier 2 | Distribution | 2012-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012137 | 404398134 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012138 | 404399006 | Molding | HFTD Tier 3 | Distribution | 2012-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012139 | 404400464 | Molding | HFTD Tier 2 | Distribution | 2012-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012140 | 404400768 | Guy | HFTD Tier 3 | Distribution | 2012-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012141 | 404406682 | Insulator | HFTD Tier 3 | Distribution | 2012-04-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012142 | 404406683 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-04-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012143 | 404407956 | Guy | HFTD Tier 3 | Distribution | 2012-04-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012144 | 404407959 | Guy | HFTD Tier 3 | Distribution | 2012-04-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012145 | 404408209 | High Sign | HFTD Tier 2 | Distribution | 2012-04-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012146 | 404409519 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012147 | 404409531 | High Sign | HFTD Tier 3 | Distribution | 2012-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012148 | 404409536 | High Sign | HFTD Tier 3 | Distribution | 2012-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012149 | 404410391 | Molding | HFTD Tier 3 | Distribution | 2012-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012150 | 404412558 | High Sign | HFTD Tier 2 | Distribution | 2012-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012151 | 404412571 | Molding | HFTD Tier 2 | Distribution | 2012-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012152 | 404412589 | Molding | HFTD Tier 3 | Distribution | 2012-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012153 | 404413489 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012154 | 404413495 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012155 | 404413150 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012156 | 404413164 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012157 | 404413590 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012158 | 404415927 | Molding | HFTD Tier 3 | Distribution | 2012-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012159 | 404415936 | Riser/Conduit | HFTD Tier 3 | Distribution | 2012-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012160 | 404417055 | High Sign | HFTD Tier 3 | Distribution | 2012-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012161 | 404417060 | High Sign | HFTD Tier 3 | Distribution | 2012-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012162 | 404418374 | Molding | HFTD Tier 3 | Distribution | 2012-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012163 | 404418378 | Molding | HFTD Tier 3 | Distribution | 2012-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012164 | 404418406 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012165 | 404418423 | Guy | HFTD Tier 3 | Distribution | 2012-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012166 | 404418572 | High Sign | HFTD Tier 3 | Distribution | 2012-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012167 | 404418618 | Bond | HFTD Tier 2 | Distribution | 2012-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012168 | 404424351 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012169 | 404419688 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012170 | 404419704 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012171 | 404420321 | Molding | HFTD Tier 2 | Distribution | 2012-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012172 | 404421731 | Molding | HFTD Tier 2 | Distribution | 2012-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012173 | 404421759 | High Sign | HFTD Tier 2 | Distribution | 2012-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012174 | 404421760 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012175 | 404421866 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012176 | 404421867 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012177 | 404421871 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012178 | 404421873 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012179 | 404421877 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012180 | 404421878 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012181 | 404421879 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012182 | 404421881 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012183 | 404421884 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012184 | 404422538 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012185 | 404424719 | High Sign | HFTD Tier 2 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012186 | 404426937 | Guy | HFTD Tier 3 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012187 | 404426938 | High Sign | HFTD Tier 3 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012188 | 404426957 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012189 | 404426972 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012190 | 404426978 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012191 | 404426982 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012192 | 404427018 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012193 | 404427019 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012194 | 404427020 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012195 | 404427022 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012196 | 404427024 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012197 | 404427025 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012198 | 404427026 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012199 | 404427027 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012200 | 404427028 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012201 | 404427030 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012202 | 404427031 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012203 | 404427032 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012204 | 404427061 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012205 | 404427086 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012206 | 404430288 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012207 | 404430020 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012208 | 404430219 | Guy | HFTD Tier 2 | Distribution | 2012-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012209 | 404430236 | High Sign | HFTD Tier 2 | Distribution | 2012-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012210 | 404430242 | Guy | HFTD Tier 2 | Distribution | 2012-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012211 | 404430243 | High Sign | HFTD Tier 2 | Distribution | 2012-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012212 | 404430245 | Guy | HFTD Tier 2 | Distribution | 2012-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012213 | 404430248 | High Sign | HFTD Tier 2 | Distribution | 2012-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012214 | 404431396 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012215 | 404431486 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012216 | 404431516 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012217 | 404432977 | Molding | HFTD Tier 3 | Distribution | 2012-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012218 | 404432991 | High Sign | HFTD Tier 3 | Distribution | 2012-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012219 | 404432994 | High Sign | HFTD Tier 3 | Distribution | 2012-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012220 | 404433066 | High Sign | HFTD Tier 2 | Distribution | 2012-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012221 | 404434406 | Molding | HFTD Tier 2 | Distribution | 2012-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012222 | 404434415 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012223 | 404434432 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012224 | 404434506 | High Sign | HFTD Tier 3 | Distribution | 2012-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012225 | 404434535 | High Sign | HFTD Tier 3 | Distribution | 2012-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012226 | 404435567 | High Sign | HFTD Tier 3 | Distribution | 2012-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012227 | 404435569 | High Sign | HFTD Tier 3 | Distribution | 2012-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012228 | 404435706 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012229 | 404442273 | Insulator | HFTD Tier 2 | Distribution | 2012-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012230 | 404446133 | High Sign | HFTD Tier 2 | Distribution | 2012-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012231 | 404446424 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012232 | 404446432 | High Sign | HFTD Tier 3 | Distribution | 2012-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012233 | 404458085 | Guy | HFTD Tier 2 | Distribution | 2012-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012234 | 413873260 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012235 | 404447267 | Molding | HFTD Tier 3 | Distribution | 2012-05-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012236 | 404449029 | Molding | HFTD Tier 2 | Distribution | 2012-05-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012237 | 404449054 | Molding | HFTD Tier 2 | Distribution | 2012-05-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012238 | 404449065 | Guy | HFTD Tier 2 | Distribution | 2012-05-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012239 | 404449131 | Molding | HFTD Tier 3 | Distribution | 2012-05-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012240 | 404450255 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012241 | 404450259 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012242 | 404451698 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012243 | 404451850 | High Sign | HFTD Tier 3 | Distribution | 2012-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012244 | 404452112 | Molding | HFTD Tier 2 | Distribution | 2012-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012245 | 404452972 | High Sign | HFTD Tier 2 | Distribution | 2012-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012246 | 404452977 | High Sign | HFTD Tier 2 | Distribution | 2012-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012247 | 404456219 | Molding | HFTD Tier 3 | Distribution | 2012-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012248 | 404452995 | High Sign | HFTD Tier 2 | Distribution | 2012-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012249 | 404452998 | High Sign | HFTD Tier 2 | Distribution | 2012-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012250 | 404453001 | High Sign | HFTD Tier 2 | Distribution | 2012-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012251 | 404453317 | High Sign | HFTD Tier 3 | Distribution | 2012-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012252 | 404453435 | Insulator | HFTD Tier 2 | Distribution | 2012-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012253 | 404454860 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012254 | 404455141 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012255 | 404455287 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012256 | 404455333 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012257 | 404455366 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012258 | 404456042 | Molding | HFTD Tier 3 | Distribution | 2012-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012259 | 404456317 | High Sign | HFTD Tier 3 | Distribution | 2012-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012260 | 404456455 | Molding | HFTD Tier 3 | Distribution | 2012-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012261 | 404457477 | High Sign | HFTD Tier 3 | Distribution | 2012-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012262 | 404457494 | Insulator | HFTD Tier 3 | Distribution | 2012-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012263 | 404457765 | Molding | HFTD Tier 3 | Distribution | 2012-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012264 | 404458047 | Vis Strips | HFTD Tier 2 | Distribution | 2012-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012265 | 404458677 | High Sign | HFTD Tier 3 | Distribution | 2012-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012266 | 404458685 | High Sign | HFTD Tier 3 | Distribution | 2012-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012267 | 404461475 | Riser/Conduit | HFTD Tier 3 | Distribution | 2012-05-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012268 | 404461484 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-05-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012269 | 404461617 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-05-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012270 | 404461668 | Molding | HFTD Tier 3 | Distribution | 2012-05-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012271 | 404461750 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-05-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012272 | 404464959 | High Sign | HFTD Tier 2 | Distribution | 2012-05-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012273 | 404462681 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012274 | 404464339 | Molding | HFTD Tier 2 | Distribution | 2012-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012275 | 404474861 | Molding | HFTD Tier 2 | Distribution | 2012-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012276 | 404474936 | Molding | HFTD Tier 2 | Distribution | 2012-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012277 | 404465286 | High Sign | HFTD Tier 3 | Distribution | 2012-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012278 | 404465443 | Guy | HFTD Tier 2 | Distribution | 2012-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012279 | 404466842 | Molding | HFTD Tier 3 | Distribution | 2012-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012280 | 404466865 | Molding | HFTD Tier 3 | Distribution | 2012-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012281 | 404467340 | Guy | HFTD Tier 2 | Distribution | 2012-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012282 | 404468552 | Molding | HFTD Tier 3 | Distribution | 2012-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012283 | 404468569 | Molding | HFTD Tier 3 | Distribution | 2012-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012284 | 404468577 | Molding | HFTD Tier 3 | Distribution | 2012-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012285 | 404468591 | Riser/Conduit | HFTD Tier 3 | Distribution | 2012-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012286 | 404471211 | High Sign | HFTD Tier 2 | Distribution | 2012-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012287 | 404471237 | Crossarm | HFTD Tier 2 | Distribution | 2012-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012288 | 404471253 | Molding | HFTD Tier 2 | Distribution | 2012-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012289 | 404468598 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012290 | 404468603 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012291 | 404470060 | High Sign | HFTD Tier 2 | Distribution | 2012-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012292 | 404470065 | Molding | HFTD Tier 3 | Distribution | 2012-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012293 | 404470244 | High Sign | HFTD Tier 3 | Distribution | 2012-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012294 | 404471248 | High Sign | HFTD Tier 2 | Distribution | 2012-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012295 | 404471283 | High Sign | HFTD Tier 2 | Distribution | 2012-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012296 | 404471288 | Molding | HFTD Tier 2 | Distribution | 2012-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012297 | 404471354 | High Sign | HFTD Tier 2 | Distribution | 2012-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012298 | 404471385 | High Sign | HFTD Tier 2 | Distribution | 2012-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012299 | 404471388 | High Sign | HFTD Tier 2 | Distribution | 2012-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012300 | 404471389 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012301 | 404471391 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012302 | 404471394 | High Sign | HFTD Tier 2 | Distribution | 2012-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012303 | 404471400 | High Sign | HFTD Tier 2 | Distribution | 2012-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012304 | 404472770 | High Sign | HFTD Tier 3 | Distribution | 2012-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012305 | 404472771 | High Sign | HFTD Tier 2 | Distribution | 2012-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012306 | 404472781 | High Sign | HFTD Tier 3 | Distribution | 2012-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012307 | 404472858 | Molding | HFTD Tier 3 | Distribution | 2012-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012308 | 404472986 | Molding | HFTD Tier 3 | Distribution | 2012-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012309 | 404473737 | High Sign | HFTD Tier 3 | Distribution | 2012-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012310 | 404473758 | High Sign | HFTD Tier 3 | Distribution | 2012-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012311 | 404473761 | High Sign | HFTD Tier 3 | Distribution | 2012-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012312 | 404474778 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012313 | 404476459 | High Sign | HFTD Tier 2 | Distribution | 2012-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012314 | 404476802 | Molding | HFTD Tier 2 | Distribution | 2012-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012315 | 404476838 | Guy | HFTD Tier 2 | Distribution | 2012-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012316 | 404476840 | High Sign | HFTD Tier 2 | Distribution | 2012-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012317 | 404479654 | High Sign | HFTD Tier 2 | Distribution | 2012-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012318 | 404479665 | Molding | HFTD Tier 2 | Distribution | 2012-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012319 | 404477655 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012320 | 404477665 | High Sign | HFTD Tier 3 | Distribution | 2012-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012321 | 404477682 | High Sign | HFTD Tier 3 | Distribution | 2012-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012322 | 404477683 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012323 | 404477712 | High Sign | HFTD Tier 3 | Distribution | 2012-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012324 | 404477728 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012325 | 404479027 | High Sign | HFTD Tier 3 | Distribution | 2012-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012326 | 404479031 | High Sign | HFTD Tier 3 | Distribution | 2012-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012327 | 404479315 | Guy | HFTD Tier 3 | Distribution | 2012-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012328 | 404479493 | High Sign | HFTD Tier 2 | Distribution | 2012-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012329 | 404479667 | Molding | HFTD Tier 2 | Distribution | 2012-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012330 | 404479677 | High Sign | HFTD Tier 2 | Distribution | 2012-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012331 | 404479681 | Molding | HFTD Tier 2 | Distribution | 2012-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012332 | 404480211 | High Sign | HFTD Tier 3 | Distribution | 2012-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012333 | 404480225 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012334 | 404480236 | Molding | HFTD Tier 3 | Distribution | 2012-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012335 | 404480275 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012336 | 404485181 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012337 | 404485272 | High Sign | HFTD Tier 3 | Distribution | 2012-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012338 | 404485156 | High Sign | HFTD Tier 3 | Distribution | 2012-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012339 | 404485164 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012340 | 404487107 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012341 | 404487141 | High Sign | HFTD Tier 2 | Distribution | 2012-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012342 | 404489870 | Molding | HFTD Tier 3 | Distribution | 2012-05-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012343 | 404490008 | High Sign | HFTD Tier 2 | Distribution | 2012-05-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012344 | 404490588 | High Sign | HFTD Tier 3 | Distribution | 2012-05-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012345 | 404490589 | High Sign | HFTD Tier 3 | Distribution | 2012-05-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012346 | 404490603 | High Sign | HFTD Tier 3 | Distribution | 2012-05-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012347 | 404490605 | High Sign | HFTD Tier 3 | Distribution | 2012-05-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012348 | 404490606 | High Sign | HFTD Tier 3 | Distribution | 2012-05-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012349 | 404492893 | Molding | HFTD Tier 3 | Distribution | 2012-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012350 | 404493369 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012351 | 404493407 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012352 | 404493411 | High Sign | HFTD Tier 3 | Distribution | 2012-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012353 | 404493501 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012354 | 404495449 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012355 | 404495454 | High Sign | HFTD Tier 2 | Distribution | 2012-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012356 | 404499537 | High Sign | HFTD Tier 2 | Distribution | 2012-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012357 | 404499555 | Molding | HFTD Tier 2 | Distribution | 2012-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012358 | 404499556 | High Sign | HFTD Tier 2 | Distribution | 2012-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012359 | 404499561 | High Sign | HFTD Tier 2 | Distribution | 2012-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012360 | 404499576 | Molding | HFTD Tier 2 | Distribution | 2012-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012361 | 404499590 | Molding | HFTD Tier 2 | Distribution | 2012-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012362 | 404496375 | High Sign | HFTD Tier 3 | Distribution | 2012-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012363 | 404496398 | High Sign | HFTD Tier 3 | Distribution | 2012-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012364 | 404496424 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012365 | 404497640 | Molding | HFTD Tier 3 | Distribution | 2012-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012366 | 404499027 | Molding | HFTD Tier 3 | Distribution | 2012-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012367 | 404500592 | Guy | HFTD Tier 2 | Distribution | 2012-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012368 | 404502221 | High Sign | HFTD Tier 3 | Distribution | 2012-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012369 | 404502320 | Molding | HFTD Tier 3 | Distribution | 2012-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012370 | 404502683 | High Sign | HFTD Tier 2 | Distribution | 2012-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012371 | 404502715 | High Sign | HFTD Tier 2 | Distribution | 2012-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012372 | 404512069 | High Sign | HFTD Tier 2 | Distribution | 2012-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012373 | 404512101 | Guy | HFTD Tier 2 | Distribution | 2012-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012374 | 404512128 | Crossarm | HFTD Tier 2 | Distribution | 2012-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012375 | 404512137 | High Sign | HFTD Tier 2 | Distribution | 2012-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012376 | 404512139 | Molding | HFTD Tier 2 | Distribution | 2012-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012377 | 404512162 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012378 | 404512167 | Molding | HFTD Tier 2 | Distribution | 2012-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012379 | 404505437 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012380 | 404505549 | High Sign | HFTD Tier 3 | Distribution | 2012-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012381 | 404512775 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012382 | 404507904 | High Sign | HFTD Tier 2 | Distribution | 2012-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012383 | 404508352 | Molding | HFTD Tier 3 | Distribution | 2012-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012384 | 404509265 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012385 | 404511710 | High Sign | HFTD Tier 3 | Distribution | 2012-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012386 | 404511807 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012387 | 404512888 | High Sign | HFTD Tier 2 | Distribution | 2012-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012388 | 404512928 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012389 | 404512961 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012390 | 404514242 | Molding | HFTD Tier 2 | Distribution | 2012-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012391 | 404514243 | Guy | HFTD Tier 2 | Distribution | 2012-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012392 | 404518020 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012393 | 404515318 | High Sign | HFTD Tier 2 | Distribution | 2012-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012394 | 404518083 | Guy | HFTD Tier 2 | Distribution | 2012-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012395 | 404518168 | Guy | HFTD Tier 2 | Distribution | 2012-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012396 | 404516349 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012397 | 404516356 | Molding | HFTD Tier 3 | Distribution | 2012-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012398 | 404516360 | High Sign | HFTD Tier 3 | Distribution | 2012-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012399 | 404516377 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012400 | 404516410 | Molding | HFTD Tier 3 | Distribution | 2012-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012401 | 404518290 | Guy | HFTD Tier 2 | Distribution | 2012-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012402 | 404518317 | Molding | HFTD Tier 2 | Distribution | 2012-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012403 | 404518462 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012404 | 404518888 | High Sign | HFTD Tier 3 | Distribution | 2012-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012405 | 404518901 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012406 | 404522132 | High Sign | HFTD Tier 3 | Distribution | 2012-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012407 | 404522151 | Molding | HFTD Tier 3 | Distribution | 2012-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012408 | 404522538 | High Sign | HFTD Tier 3 | Distribution | 2012-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012409 | 404522557 | High Sign | HFTD Tier 3 | Distribution | 2012-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012410 | 404522559 | High Sign | HFTD Tier 3 | Distribution | 2012-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012411 | 404522571 | High Sign | HFTD Tier 3 | Distribution | 2012-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012412 | 404522572 | High Sign | HFTD Tier 3 | Distribution | 2012-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012413 | 404522573 | High Sign | HFTD Tier 3 | Distribution | 2012-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012414 | 404522574 | High Sign | HFTD Tier 3 | Distribution | 2012-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012415 | 404522581 | High Sign | HFTD Tier 3 | Distribution | 2012-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012416 | 404519668 | High Sign | HFTD Tier 3 | Distribution | 2012-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012417 | 404519685 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012418 | 404519691 | Termination | HFTD Tier 3 | Distribution | 2012-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012419 | 404521478 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012420 | 404521588 | Molding | HFTD Tier 3 | Distribution | 2012-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012421 | 404521660 | Riser/Conduit | HFTD Tier 2 | Distribution | 2012-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012422 | 404522149 | Molding | HFTD Tier 3 | Distribution | 2012-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012423 | 404522180 | High Sign | HFTD Tier 3 | Distribution | 2012-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012424 | 404523443 | Streetlight | HFTD Tier 2 | Distribution | 2012-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012425 | 404524371 | Molding | HFTD Tier 3 | Distribution | 2012-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012426 | 404524382 | High Sign | HFTD Tier 3 | Distribution | 2012-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012427 | 404524395 | Molding | HFTD Tier 3 | Distribution | 2012-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012428 | 404524429 | Riser/Conduit | HFTD Tier 3 | Distribution | 2012-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012429 | 404524487 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012430 | 404524690 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012431 | 404529804 | Guy | HFTD Tier 3 | Distribution | 2012-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012432 | 404529823 | High Sign | HFTD Tier 3 | Distribution | 2012-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012433 | 404529835 | High Sign | HFTD Tier 3 | Distribution | 2012-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012434 | 404526384 | High Sign | HFTD Tier 3 | Distribution | 2012-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012435 | 404527166 | High Sign | HFTD Tier 2 | Distribution | 2012-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012436 | 404528038 | High Sign | HFTD Tier 3 | Distribution | 2012-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012437 | 404528088 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012438 | 404529828 | Molding | HFTD Tier 3 | Distribution | 2012-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012439 | 404529841 | High Sign | HFTD Tier 3 | Distribution | 2012-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012440 | 404529844 | Molding | HFTD Tier 3 | Distribution | 2012-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012441 | 404529861 | Molding | HFTD Tier 3 | Distribution | 2012-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012442 | 404528104 | High Sign | HFTD Tier 3 | Distribution | 2012-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012443 | 404528120 | Riser/Conduit | HFTD Tier 3 | Distribution | 2012-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012444 | 404529358 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012445 | 404529370 | Vis Strips | HFTD Tier 3 | Distribution | 2012-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012446 | 404532657 | High Sign | HFTD Tier 2 | Distribution | 2012-06-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012447 | 404532679 | Guy | HFTD Tier 2 | Distribution | 2012-06-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012448 | 404532682 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-06-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012449 | 404532685 | High Sign | HFTD Tier 2 | Distribution | 2012-06-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012450 | 404532690 | High Sign | HFTD Tier 2 | Distribution | 2012-06-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012451 | 404533710 | High Sign | HFTD Tier 3 | Distribution | 2012-06-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012452 | 413838346 | High Sign | HFTD Tier 3 | Distribution | 2012-06-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012453 | 404535378 | High Sign | HFTD Tier 2 | Distribution | 2012-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012454 | 404540708 | Guy | HFTD Tier 2 | Distribution | 2012-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012455 | 404540717 | High Sign | HFTD Tier 2 | Distribution | 2012-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012456 | 404540719 | High Sign | HFTD Tier 2 | Distribution | 2012-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012457 | 404540721 | High Sign | HFTD Tier 2 | Distribution | 2012-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012458 | 404540730 | High Sign | HFTD Tier 2 | Distribution | 2012-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012459 | 404543138 | Molding | HFTD Tier 3 | Distribution | 2012-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012460 | 404543139 | High Sign | HFTD Tier 3 | Distribution | 2012-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012461 | 404537671 | High Sign | HFTD Tier 2 | Distribution | 2012-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012462 | 404539146 | High Sign | HFTD Tier 3 | Distribution | 2012-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012463 | 404540415 | Guy | HFTD Tier 2 | Distribution | 2012-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012464 | 404540510 | Molding | HFTD Tier 3 | Distribution | 2012-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012465 | 404540511 | High Sign | HFTD Tier 3 | Distribution | 2012-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012466 | 404540765 | High Sign | HFTD Tier 2 | Distribution | 2012-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012467 | 404540773 | High Sign | HFTD Tier 2 | Distribution | 2012-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012468 | 404542628 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012469 | 404542947 | High Sign | HFTD Tier 2 | Distribution | 2012-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012470 | 404543412 | High Sign | HFTD Tier 3 | Distribution | 2012-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012471 | 404543413 | High Sign | HFTD Tier 3 | Distribution | 2012-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012472 | 404543414 | High Sign | HFTD Tier 3 | Distribution | 2012-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012473 | 404543415 | High Sign | HFTD Tier 3 | Distribution | 2012-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012474 | 404545655 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012475 | 404545665 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012476 | 404545683 | Guy | HFTD Tier 3 | Distribution | 2012-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012477 | 404543937 | Molding | HFTD Tier 3 | Distribution | 2012-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012478 | 404543968 | High Sign | HFTD Tier 3 | Distribution | 2012-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012479 | 404543973 | Molding | HFTD Tier 3 | Distribution | 2012-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012480 | 404543974 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012481 | 404543981 | Molding | HFTD Tier 3 | Distribution | 2012-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012482 | 404543983 | High Sign | HFTD Tier 3 | Distribution | 2012-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012483 | 404543996 | High Sign | HFTD Tier 3 | Distribution | 2012-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012484 | 404543998 | High Sign | HFTD Tier 3 | Distribution | 2012-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012485 | 404544509 | Guy | HFTD Tier 3 | Distribution | 2012-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012486 | 404548325 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-06-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012487 | 404547216 | Molding | HFTD Tier 3 | Distribution | 2012-06-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012488 | 404547221 | High Sign | HFTD Tier 3 | Distribution | 2012-06-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012489 | 404547230 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-06-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012490 | 404547556 | High Sign | HFTD Tier 3 | Distribution | 2012-06-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012491 | 404547880 | Molding | HFTD Tier 2 | Distribution | 2012-06-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012492 | 404547881 | High Sign | HFTD Tier 2 | Distribution | 2012-06-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012493 | 404551014 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-06-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012494 | 404551026 | Molding | HFTD Tier 3 | Distribution | 2012-06-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012495 | 404549884 | Guy | HFTD Tier 3 | Distribution | 2012-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012496 | 404550106 | Molding | HFTD Tier 3 | Distribution | 2012-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012497 | 404550157 | Vis Strips | HFTD Tier 3 | Distribution | 2012-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012498 | 404550163 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012499 | 404550262 | High Sign | HFTD Tier 3 | Distribution | 2012-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012500 | 404550274 | High Sign | HFTD Tier 3 | Distribution | 2012-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012501 | 404550280 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012502 | 404550289 | Molding | HFTD Tier 3 | Distribution | 2012-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012503 | 404550353 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012504 | 404550355 | High Sign | HFTD Tier 3 | Distribution | 2012-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012505 | 404550361 | High Sign | HFTD Tier 3 | Distribution | 2012-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012506 | 404550370 | High Sign | HFTD Tier 3 | Distribution | 2012-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012507 | 404551081 | Guy | HFTD Tier 3 | Distribution | 2012-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012508 | 404552476 | Molding | HFTD Tier 3 | Distribution | 2012-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012509 | 404552483 | Guy | HFTD Tier 3 | Distribution | 2012-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012510 | 404552501 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012511 | 404555430 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012512 | 404555681 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012513 | 404556063 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012514 | 404556143 | Guy | HFTD Tier 2 | Distribution | 2012-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012515 | 404557837 | Pole Tag | HFTD Tier 3 | Distribution | 2012-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012516 | 404557866 | Molding | HFTD Tier 3 | Distribution | 2012-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012517 | 404558572 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012518 | 404558766 | Guy | HFTD Tier 3 | Distribution | 2012-06-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012519 | 404558793 | Molding | HFTD Tier 3 | Distribution | 2012-06-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012520 | 404558872 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-06-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012521 | 404558880 | Molding | HFTD Tier 3 | Distribution | 2012-06-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012522 | 404558887 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-06-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012523 | 404558956 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-06-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012524 | 404558962 | Molding | HFTD Tier 3 | Distribution | 2012-06-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012525 | 404558980 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-06-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012526 | 404558989 | Vis Strips | HFTD Tier 3 | Distribution | 2012-06-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012527 | 404559012 | Vis Strips | HFTD Tier 3 | Distribution | 2012-06-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012528 | 404561772 | High Sign | HFTD Tier 3 | Distribution | 2012-07-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012529 | 404561773 | High Sign | HFTD Tier 3 | Distribution | 2012-07-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012530 | 404561783 | High Sign | HFTD Tier 3 | Distribution | 2012-07-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012531 | 404561791 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-07-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012532 | 404561800 | Guy | HFTD Tier 3 | Distribution | 2012-07-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012533 | 404561808 | High Sign | HFTD Tier 3 | Distribution | 2012-07-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012534 | 404562179 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-07-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012535 | 404565479 | Molding | HFTD Tier 2 | Distribution | 2012-07-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012536 | 404568736 | Molding | HFTD Tier 2 | Distribution | 2012-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012537 | 404568764 | Riser/Conduit | HFTD Tier 2 | Distribution | 2012-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012538 | 404568820 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012539 | 404568854 | High Sign | HFTD Tier 2 | Distribution | 2012-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012540 | 404572970 | High Sign | HFTD Tier 3 | Distribution | 2012-07-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012541 | 404573443 | Molding | HFTD Tier 3 | Distribution | 2012-07-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012542 | 404573580 | Molding | HFTD Tier 3 | Distribution | 2012-07-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012543 | 404573582 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-07-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012544 | 404573587 | Molding | HFTD Tier 3 | Distribution | 2012-07-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012545 | 404573610 | High Sign | HFTD Tier 3 | Distribution | 2012-07-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012546 | 404573623 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-07-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012547 | 404575275 | Molding | HFTD Tier 3 | Distribution | 2012-07-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012548 | 404577950 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012549 | 404578764 | High Sign | HFTD Tier 2 | Distribution | 2012-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012550 | 404580358 | High Sign | HFTD Tier 3 | Distribution | 2012-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012551 | 404581567 | High Sign | HFTD Tier 3 | Distribution | 2012-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012552 | 404583825 | High Sign | HFTD Tier 3 | Distribution | 2012-07-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012553 | 404583828 | High Sign | HFTD Tier 2 | Distribution | 2012-07-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012554 | 404583833 | High Sign | HFTD Tier 3 | Distribution | 2012-07-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012555 | 404585276 | Vis Strips | HFTD Tier 2 | Distribution | 2012-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012556 | 404585287 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012557 | 404586796 | High Sign | HFTD Tier 2 | Distribution | 2012-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012558 | 404587760 | High Sign | HFTD Tier 2 | Distribution | 2012-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012559 | 404589989 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012560 | 404590049 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012561 | 404592387 | High Sign | HFTD Tier 2 | Distribution | 2012-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012562 | 404592388 | High Sign | HFTD Tier 2 | Distribution | 2012-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012563 | 404592397 | High Sign | HFTD Tier 2 | Distribution | 2012-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012564 | 404592403 | Molding | HFTD Tier 2 | Distribution | 2012-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012565 | 404592404 | Molding | HFTD Tier 2 | Distribution | 2012-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012566 | 404597202 | High Sign | HFTD Tier 2 | Distribution | 2012-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012567 | 404597214 | High Sign | HFTD Tier 2 | Distribution | 2012-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012568 | 404597215 | High Sign | HFTD Tier 2 | Distribution | 2012-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012569 | 404598483 | Molding | HFTD Tier 2 | Distribution | 2012-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012570 | 404598493 | Guy | HFTD Tier 2 | Distribution | 2012-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012571 | 404594898 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012572 | 404594901 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012573 | 404594927 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012574 | 404594928 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012575 | 404594929 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012576 | 404594936 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012577 | 404594937 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012578 | 404594943 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012579 | 404594945 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012580 | 404594946 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012581 | 404594948 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012582 | 404594949 | Molding | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012583 | 404594950 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012584 | 404594951 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012585 | 404594960 | Guy | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012586 | 404594961 | Molding | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012587 | 404594964 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012588 | 404594968 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012589 | 404594990 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012590 | 404597205 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012591 | 404597206 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012592 | 404597209 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012593 | 404597217 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012594 | 404597220 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012595 | 404597221 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012596 | 404597222 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012597 | 404597223 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012598 | 404597224 | Guy | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012599 | 404597227 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012600 | 404597228 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012601 | 404597229 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012602 | 404597232 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012603 | 404597233 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012604 | 404597234 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012605 | 404597235 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012606 | 404597236 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012607 | 404597237 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012608 | 404597238 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012609 | 404597240 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012610 | 404597241 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012611 | 404597243 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012612 | 404597246 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012613 | 404597249 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012614 | 404597253 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012615 | 404597255 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012616 | 404597257 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012617 | 404597260 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012618 | 404597261 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012619 | 404597262 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012620 | 404597271 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012621 | 404598523 | Guy | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012622 | 404598527 | High Sign | HFTD Tier 2 | Distribution | 2012-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012623 | 404595348 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012624 | 404595349 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012625 | 404597294 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012626 | 404597295 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012627 | 404597296 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012628 | 404597299 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012629 | 404597300 | Guy | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012630 | 404597301 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012631 | 404597305 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012632 | 404597306 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012633 | 404597310 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012634 | 404597312 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012635 | 404597313 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012636 | 404597314 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012637 | 404597315 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012638 | 404597316 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012639 | 404597317 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012640 | 404597318 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012641 | 404597319 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012642 | 404597320 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012643 | 404597321 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012644 | 404597322 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012645 | 404597323 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012646 | 404597324 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012647 | 404597325 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012648 | 404597326 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012649 | 404597328 | Molding | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012650 | 404597329 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012651 | 404597330 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012652 | 404597331 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012653 | 404597332 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012654 | 404597334 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012655 | 404597337 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012656 | 404597343 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012657 | 404597347 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012658 | 404597352 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012659 | 404597354 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012660 | 404597357 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012661 | 404597360 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012662 | 404597943 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012663 | 404597963 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012664 | 404597980 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012665 | 404598003 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012666 | 404598063 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012667 | 404598558 | High Sign | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012668 | 404600773 | Guy | HFTD Tier 2 | Distribution | 2012-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012669 | 404598569 | High Sign | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012670 | 404598573 | High Sign | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012671 | 404598593 | High Sign | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012672 | 404599767 | High Sign | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012673 | 404599854 | High Sign | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012674 | 404600809 | Molding | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012675 | 404600817 | High Sign | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012676 | 404600820 | High Sign | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012677 | 404600821 | Guy | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012678 | 404602198 | High Sign | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012679 | 404602209 | Molding | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012680 | 404602210 | High Sign | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012681 | 404602212 | High Sign | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012682 | 404602213 | High Sign | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012683 | 404602214 | High Sign | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012684 | 404602220 | High Sign | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012685 | 404602223 | High Sign | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012686 | 404602224 | High Sign | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012687 | 404602226 | High Sign | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012688 | 404602241 | Guy | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012689 | 404602251 | High Sign | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012690 | 404602255 | Guy | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012691 | 404602256 | High Sign | HFTD Tier 2 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012692 | 404603741 | Molding | HFTD Tier 3 | Distribution | 2012-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012693 | 404602134 | High Sign | HFTD Tier 2 | Distribution | 2012-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012694 | 404602155 | High Sign | HFTD Tier 2 | Distribution | 2012-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012695 | 404602156 | High Sign | HFTD Tier 2 | Distribution | 2012-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012696 | 404602157 | High Sign | HFTD Tier 2 | Distribution | 2012-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012697 | 404602158 | High Sign | HFTD Tier 2 | Distribution | 2012-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012698 | 404602162 | Guy | HFTD Tier 2 | Distribution | 2012-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012699 | 404602163 | High Sign | HFTD Tier 2 | Distribution | 2012-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012700 | 404602165 | High Sign | HFTD Tier 2 | Distribution | 2012-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012701 | 404602166 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012702 | 404602167 | High Sign | HFTD Tier 2 | Distribution | 2012-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012703 | 404602168 | High Sign | HFTD Tier 2 | Distribution | 2012-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012704 | 404602171 | High Sign | HFTD Tier 2 | Distribution | 2012-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012705 | 404602180 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012706 | 404602441 | Riser/Conduit | HFTD Tier 2 | Distribution | 2012-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012707 | 404602463 | High Sign | HFTD Tier 2 | Distribution | 2012-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012708 | 404606469 | Insulator | HFTD Tier 3 | Distribution | 2012-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012709 | 404603668 | High Sign | HFTD Tier 3 | Distribution | 2012-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012710 | 404603677 | High Sign | HFTD Tier 3 | Distribution | 2012-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012711 | 404606497 | High Sign | HFTD Tier 3 | Distribution | 2012-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012712 | 404606517 | High Sign | HFTD Tier 3 | Distribution | 2012-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012713 | 404606049 | Guy | HFTD Tier 2 | Distribution | 2012-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012714 | 404606063 | High Sign | HFTD Tier 2 | Distribution | 2012-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012715 | 404606631 | High Sign | HFTD Tier 2 | Distribution | 2012-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012716 | 404606674 | High Sign | HFTD Tier 2 | Distribution | 2012-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012717 | 404606675 | Molding | HFTD Tier 2 | Distribution | 2012-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012718 | 404608548 | Guy | HFTD Tier 2 | Distribution | 2012-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012719 | 404608999 | High Sign | HFTD Tier 2 | Distribution | 2012-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012720 | 404610429 | Guy | HFTD Tier 2 | Distribution | 2012-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012721 | 404611765 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012722 | 404618937 | High Sign | HFTD Tier 2 | Distribution | 2012-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012723 | 404618955 | High Sign | HFTD Tier 2 | Distribution | 2012-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012724 | 404618991 | High Sign | HFTD Tier 2 | Distribution | 2012-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012725 | 404619001 | High Sign | HFTD Tier 2 | Distribution | 2012-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012726 | 404610964 | High Sign | HFTD Tier 2 | Distribution | 2012-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012727 | 404611010 | Molding | HFTD Tier 2 | Distribution | 2012-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012728 | 404611819 | High Sign | HFTD Tier 3 | Distribution | 2012-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012729 | 404618993 | High Sign | HFTD Tier 2 | Distribution | 2012-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012730 | 404618994 | High Sign | HFTD Tier 2 | Distribution | 2012-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012731 | 404619003 | High Sign | HFTD Tier 2 | Distribution | 2012-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012732 | 404619004 | High Sign | HFTD Tier 2 | Distribution | 2012-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012733 | 404619007 | High Sign | HFTD Tier 2 | Distribution | 2012-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012734 | 404619008 | High Sign | HFTD Tier 2 | Distribution | 2012-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012735 | 404619012 | High Sign | HFTD Tier 2 | Distribution | 2012-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012736 | 404619214 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-07-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012737 | 404620621 | Guy | HFTD Tier 3 | Distribution | 2012-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012738 | 404624024 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012739 | 404624029 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012740 | 404621838 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012741 | 404621852 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012742 | 404624072 | High Sign | HFTD Tier 3 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012743 | 404624501 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012744 | 404624502 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012745 | 404624503 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012746 | 404624504 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012747 | 404624505 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012748 | 404624506 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012749 | 404624507 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012750 | 404624508 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012751 | 404624509 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012752 | 404624511 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012753 | 404624512 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012754 | 404624515 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012755 | 404624517 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012756 | 404624518 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012757 | 404624521 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012758 | 404624522 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012759 | 404624523 | Molding | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012760 | 404624524 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012761 | 404624525 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012762 | 404624526 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012763 | 404624534 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012764 | 404624540 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012765 | 404624542 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012766 | 404624544 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012767 | 404624546 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012768 | 404624550 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012769 | 404624551 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012770 | 404624552 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012771 | 404624553 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012772 | 404624554 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012773 | 404624555 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012774 | 404624556 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012775 | 404624557 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012776 | 404624585 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012777 | 404624586 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012778 | 404624587 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012779 | 404624588 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012780 | 404624595 | High Sign | HFTD Tier 2 | Distribution | 2012-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012781 | 404626524 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-08-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012782 | 404629018 | High Sign | HFTD Tier 2 | Distribution | 2012-08-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012783 | 404629999 | High Sign | HFTD Tier 2 | Distribution | 2012-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012784 | 404630004 | High Sign | HFTD Tier 2 | Distribution | 2012-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012785 | 404631398 | Guy | HFTD Tier 2 | Distribution | 2012-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012786 | 404631399 | Guy | HFTD Tier 2 | Distribution | 2012-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012787 | 404631409 | High Sign | HFTD Tier 2 | Distribution | 2012-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012788 | 404631450 | Guy | HFTD Tier 2 | Distribution | 2012-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012789 | 404631451 | High Sign | HFTD Tier 2 | Distribution | 2012-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012790 | 404631455 | High Sign | HFTD Tier 2 | Distribution | 2012-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012791 | 404631457 | High Sign | HFTD Tier 2 | Distribution | 2012-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012792 | 404631458 | High Sign | HFTD Tier 2 | Distribution | 2012-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012793 | 404631461 | Guy | HFTD Tier 2 | Distribution | 2012-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012794 | 404633211 | Guy | HFTD Tier 3 | Distribution | 2012-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012795 | 404631957 | High Sign | HFTD Tier 2 | Distribution | 2012-08-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012796 | 404632050 | High Sign | HFTD Tier 2 | Distribution | 2012-08-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012797 | 404632142 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-08-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012798 | 404632143 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-08-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012799 | 404632431 | Molding | HFTD Tier 2 | Distribution | 2012-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012800 | 404632432 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012801 | 404632433 | High Sign | HFTD Tier 2 | Distribution | 2012-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012802 | 404632450 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012803 | 404632508 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012804 | 404632593 | High Sign | HFTD Tier 2 | Distribution | 2012-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012805 | 404632594 | Molding | HFTD Tier 2 | Distribution | 2012-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012806 | 404632608 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012807 | 404632619 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012808 | 404632638 | High Sign | HFTD Tier 2 | Distribution | 2012-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012809 | 404632651 | Cutout/Fuse | HFTD Tier 2 | Distribution | 2012-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012810 | 404633222 | High Sign | HFTD Tier 3 | Distribution | 2012-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012811 | 404633229 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012812 | 404633242 | Riser/Conduit | HFTD Tier 3 | Distribution | 2012-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012813 | 404633635 | Molding | HFTD Tier 2 | Distribution | 2012-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012814 | 404635747 | Molding | HFTD Tier 3 | Distribution | 2012-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012815 | 404635748 | Guy | HFTD Tier 3 | Distribution | 2012-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012816 | 404635757 | Guy | HFTD Tier 3 | Distribution | 2012-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012817 | 404637350 | Molding | HFTD Tier 3 | Distribution | 2012-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012818 | 404637366 | High Sign | HFTD Tier 3 | Distribution | 2012-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012819 | 404637395 | High Sign | HFTD Tier 3 | Distribution | 2012-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012820 | 404637665 | High Sign | HFTD Tier 2 | Distribution | 2012-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012821 | 404637671 | Guy | HFTD Tier 2 | Distribution | 2012-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012822 | 404637673 | High Sign | HFTD Tier 2 | Distribution | 2012-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012823 | 404637776 | High Sign | HFTD Tier 2 | Distribution | 2012-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012824 | 404639002 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012825 | 404642747 | High Sign | HFTD Tier 3 | Distribution | 2012-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012826 | 404642790 | Guy | HFTD Tier 3 | Distribution | 2012-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012827 | 404641417 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012828 | 404641803 | High Sign | HFTD Tier 3 | Distribution | 2012-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012829 | 404641940 | Molding | HFTD Tier 3 | Distribution | 2012-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012830 | 404645510 | Molding | HFTD Tier 3 | Distribution | 2012-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012831 | 404643454 | Guy | HFTD Tier 3 | Distribution | 2012-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012832 | 404643489 | Molding | HFTD Tier 3 | Distribution | 2012-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012833 | 404650917 | Molding | HFTD Tier 3 | Distribution | 2012-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012834 | 404653402 | High Sign | HFTD Tier 3 | Distribution | 2012-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012835 | 404653436 | Molding | HFTD Tier 3 | Distribution | 2012-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012836 | 404653444 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012837 | 404653501 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012838 | 404659327 | High Sign | HFTD Tier 3 | Distribution | 2012-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012839 | 404663768 | High Sign | HFTD Tier 3 | Distribution | 2012-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012840 | 404655710 | Insulator | HFTD Tier 3 | Distribution | 2012-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012841 | 404655711 | Insulator | HFTD Tier 3 | Distribution | 2012-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012842 | 404656118 | Molding | HFTD Tier 2 | Distribution | 2012-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012843 | 404659375 | High Sign | HFTD Tier 3 | Distribution | 2012-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012844 | 404659377 | High Sign | HFTD Tier 3 | Distribution | 2012-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012845 | 404659382 | High Sign | HFTD Tier 3 | Distribution | 2012-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012846 | 404659385 | Molding | HFTD Tier 3 | Distribution | 2012-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012847 | 404659392 | High Sign | HFTD Tier 3 | Distribution | 2012-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012848 | 404659396 | High Sign | HFTD Tier 3 | Distribution | 2012-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012849 | 404659397 | High Sign | HFTD Tier 3 | Distribution | 2012-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012850 | 404663814 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012851 | 404663816 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012852 | 404659404 | High Sign | HFTD Tier 3 | Distribution | 2012-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012853 | 404659414 | High Sign | HFTD Tier 3 | Distribution | 2012-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012854 | 404661410 | High Sign | HFTD Tier 3 | Distribution | 2012-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012855 | 404665087 | Guy | HFTD Tier 3 | Distribution | 2012-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012856 | 404665608 | Molding | HFTD Tier 3 | Distribution | 2012-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012857 | 404665636 | Molding | HFTD Tier 3 | Distribution | 2012-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012858 | 404669206 | Molding | HFTD Tier 3 | Distribution | 2012-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012859 | 404672178 | High Sign | HFTD Tier 3 | Distribution | 2012-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012860 | 404668460 | Molding | HFTD Tier 2 | Distribution | 2012-08-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012861 | 404668485 | Guy | HFTD Tier 3 | Distribution | 2012-08-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012862 | 404669218 | Molding | HFTD Tier 3 | Distribution | 2012-08-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012863 | 404669242 | High Sign | HFTD Tier 3 | Distribution | 2012-08-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012864 | 404669246 | Molding | HFTD Tier 3 | Distribution | 2012-08-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012865 | 404669248 | High Sign | HFTD Tier 3 | Distribution | 2012-08-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012866 | 404669260 | Molding | HFTD Tier 3 | Distribution | 2012-08-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012867 | 404669272 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012868 | 404669284 | Molding | HFTD Tier 3 | Distribution | 2012-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012869 | 404669285 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012870 | 404669286 | High Sign | HFTD Tier 3 | Distribution | 2012-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012871 | 404672269 | Molding | HFTD Tier 3 | Distribution | 2012-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012872 | 404672287 | Molding | HFTD Tier 3 | Distribution | 2012-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012873 | 404673994 | High Sign | HFTD Tier 3 | Distribution | 2012-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012874 | 404674027 | Molding | HFTD Tier 3 | Distribution | 2012-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012875 | 404674078 | Molding | HFTD Tier 3 | Distribution | 2012-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012876 | 404674096 | High Sign | HFTD Tier 3 | Distribution | 2012-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012877 | 404672540 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012878 | 404672541 | Molding | HFTD Tier 2 | Distribution | 2012-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012879 | 404672543 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012880 | 404674139 | Molding | HFTD Tier 3 | Distribution | 2012-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012881 | 404674152 | Molding | HFTD Tier 3 | Distribution | 2012-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012882 | 404674160 | High Sign | HFTD Tier 3 | Distribution | 2012-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012883 | 404674681 | Molding | HFTD Tier 3 | Distribution | 2012-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012884 | 404674684 | Molding | HFTD Tier 3 | Distribution | 2012-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012885 | 404674695 | High Sign | HFTD Tier 3 | Distribution | 2012-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012886 | 404676547 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012887 | 404677530 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012888 | 404675768 | Molding | HFTD Tier 3 | Distribution | 2012-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012889 | 404681523 | High Sign | HFTD Tier 3 | Distribution | 2012-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012890 | 404677262 | Molding | HFTD Tier 3 | Distribution | 2012-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012891 | 404677274 | Molding | HFTD Tier 3 | Distribution | 2012-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012892 | 404677287 | High Sign | HFTD Tier 2 | Distribution | 2012-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012893 | 404677330 | High Sign | HFTD Tier 2 | Distribution | 2012-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012894 | 404677334 | High Sign | HFTD Tier 2 | Distribution | 2012-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012895 | 404677515 | Molding | HFTD Tier 3 | Distribution | 2012-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012896 | 404677584 | Molding | HFTD Tier 3 | Distribution | 2012-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012897 | 404677907 | Guy | HFTD Tier 2 | Distribution | 2012-08-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012898 | 404678161 | High Sign | HFTD Tier 2 | Distribution | 2012-08-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012899 | 404678798 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-08-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012900 | 404678800 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-08-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012901 | 404680579 | High Sign | HFTD Tier 3 | Distribution | 2012-08-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012902 | 404683974 | Molding | HFTD Tier 3 | Distribution | 2012-08-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012903 | 404683979 | Guy | HFTD Tier 3 | Distribution | 2012-08-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012904 | 404684043 | Molding | HFTD Tier 3 | Distribution | 2012-08-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012905 | 404684045 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-08-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012906 | 404681566 | High Sign | HFTD Tier 3 | Distribution | 2012-08-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012907 | 404682772 | High Sign | HFTD Tier 3 | Distribution | 2012-08-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012908 | 404683825 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-08-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012909 | 404683826 | Molding | HFTD Tier 2 | Distribution | 2012-08-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012910 | 404683928 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-08-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012911 | 404686871 | High Sign | HFTD Tier 2 | Distribution | 2012-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012912 | 404689968 | High Sign | HFTD Tier 3 | Distribution | 2012-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012913 | 404689974 | High Sign | HFTD Tier 3 | Distribution | 2012-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012914 | 404689984 | Molding | HFTD Tier 3 | Distribution | 2012-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012915 | 404690165 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012916 | 404689999 | Guy | HFTD Tier 3 | Distribution | 2012-08-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012917 | 404690007 | Guy | HFTD Tier 3 | Distribution | 2012-08-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012918 | 404690167 | High Sign | HFTD Tier 3 | Distribution | 2012-08-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012919 | 404691665 | High Sign | HFTD Tier 3 | Distribution | 2012-08-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012920 | 404691811 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012921 | 404691884 | High Sign | HFTD Tier 3 | Distribution | 2012-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012922 | 404691930 | High Sign | HFTD Tier 2 | Distribution | 2012-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012923 | 404697608 | High Sign | HFTD Tier 3 | Distribution | 2012-09-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012924 | 404697609 | High Sign | HFTD Tier 3 | Distribution | 2012-09-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012925 | 404697659 | High Sign | HFTD Tier 3 | Distribution | 2012-09-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012926 | 404697667 | High Sign | HFTD Tier 3 | Distribution | 2012-09-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012927 | 404697671 | High Sign | HFTD Tier 3 | Distribution | 2012-09-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012928 | 404697680 | Molding | HFTD Tier 3 | Distribution | 2012-09-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012929 | 404697691 | Molding | HFTD Tier 3 | Distribution | 2012-09-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012930 | 404698045 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-09-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012931 | 404697713 | High Sign | HFTD Tier 3 | Distribution | 2012-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012932 | 404697721 | High Sign | HFTD Tier 3 | Distribution | 2012-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012933 | 404700421 | High Sign | HFTD Tier 3 | Distribution | 2012-09-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012934 | 404700426 | High Sign | HFTD Tier 3 | Distribution | 2012-09-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012935 | 404700427 | High Sign | HFTD Tier 3 | Distribution | 2012-09-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012936 | 404700434 | High Sign | HFTD Tier 3 | Distribution | 2012-09-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012937 | 404709384 | High Sign | HFTD Tier 3 | Distribution | 2012-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012938 | 404709393 | High Sign | HFTD Tier 3 | Distribution | 2012-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012939 | 404709397 | Molding | HFTD Tier 3 | Distribution | 2012-09-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012940 | 404709414 | High Sign | HFTD Tier 3 | Distribution | 2012-09-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012941 | 404709420 | High Sign | HFTD Tier 3 | Distribution | 2012-09-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012942 | 404719189 | High Sign | HFTD Tier 2 | Distribution | 2012-09-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012943 | 404719209 | Molding | HFTD Tier 2 | Distribution | 2012-09-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012944 | 404712090 | High Sign | HFTD Tier 3 | Distribution | 2012-09-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012945 | 404721519 | High Sign | HFTD Tier 3 | Distribution | 2012-09-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012946 | 404730353 | Molding | HFTD Tier 3 | Distribution | 2012-09-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012947 | 404730100 | Bond | HFTD Tier 3 | Distribution | 2012-09-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012948 | 404738311 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012949 | 404738485 | High Sign | HFTD Tier 3 | Distribution | 2012-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012950 | 404738513 | Guy | HFTD Tier 3 | Distribution | 2012-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012951 | 404743180 | Molding | HFTD Tier 3 | Distribution | 2012-09-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012952 | 404743182 | High Sign | HFTD Tier 3 | Distribution | 2012-09-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012953 | 404743193 | High Sign | HFTD Tier 3 | Distribution | 2012-09-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012954 | 404743194 | High Sign | HFTD Tier 3 | Distribution | 2012-09-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012955 | 404742641 | Molding | HFTD Tier 2 | Distribution | 2012-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012956 | 404742642 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2012-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012957 | 404742645 | Pole Tag | HFTD Tier 2 | Distribution | 2012-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012958 | 404742647 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012959 | 404743085 | High Sign | HFTD Tier 3 | Distribution | 2012-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012960 | 404743090 | High Sign | HFTD Tier 3 | Distribution | 2012-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012961 | 404743205 | High Sign | HFTD Tier 3 | Distribution | 2012-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012962 | 404749429 | Crossarm | HFTD Tier 3 | Distribution | 2012-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012963 | 404751343 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-10-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012964 | 404751344 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-10-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012965 | 404751626 | Molding | HFTD Tier 3 | Distribution | 2012-10-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012966 | 404752186 | High Sign | HFTD Tier 2 | Distribution | 2012-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012967 | 404752203 | High Sign | HFTD Tier 2 | Distribution | 2012-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012968 | 404752211 | High Sign | HFTD Tier 2 | Distribution | 2012-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012969 | 404752213 | High Sign | HFTD Tier 2 | Distribution | 2012-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012970 | 404752214 | High Sign | HFTD Tier 2 | Distribution | 2012-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012971 | 404752215 | High Sign | HFTD Tier 2 | Distribution | 2012-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012972 | 404752216 | High Sign | HFTD Tier 2 | Distribution | 2012-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012973 | 404752226 | High Sign | HFTD Tier 2 | Distribution | 2012-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012974 | 404752242 | High Sign | HFTD Tier 2 | Distribution | 2012-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012975 | 404752255 | High Sign | HFTD Tier 2 | Distribution | 2012-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012976 | 404752263 | High Sign | HFTD Tier 2 | Distribution | 2012-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012977 | 404754588 | Molding | HFTD Tier 2 | Distribution | 2012-10-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012978 | 404755562 | Guy | HFTD Tier 2 | Distribution | 2012-10-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012979 | 404755709 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-10-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012980 | 404757447 | High Sign | HFTD Tier 3 | Distribution | 2012-10-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012981 | 404761547 | High Sign | HFTD Tier 3 | Distribution | 2012-10-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012982 | 404763960 | Molding | HFTD Tier 3 | Distribution | 2012-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012983 | 404763967 | Molding | HFTD Tier 3 | Distribution | 2012-10-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012984 | 404765905 | High Sign | HFTD Tier 2 | Distribution | 2012-10-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012985 | 404765717 | High Sign | HFTD Tier 3 | Distribution | 2012-10-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012986 | 404772753 | High Sign | HFTD Tier 3 | Distribution | 2012-10-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012987 | 404774925 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-10-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012988 | 404779331 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012989 | 404779341 | Molding | HFTD Tier 3 | Distribution | 2012-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012990 | 404779373 | High Sign | HFTD Tier 3 | Distribution | 2012-10-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012991 | 404779375 | Molding | HFTD Tier 3 | Distribution | 2012-10-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012992 | 404779395 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-10-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012993 | 404783315 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-10-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012994 | 404789376 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012995 | 404789625 | High Sign | HFTD Tier 3 | Distribution | 2012-10-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012996 | 404789626 | High Sign | HFTD Tier 3 | Distribution | 2012-10-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012997 | 404791816 | High Sign | HFTD Tier 3 | Distribution | 2012-10-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012998 | 404791841 | High Sign | HFTD Tier 3 | Distribution | 2012-10-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120012999 | 404791842 | High Sign | HFTD Tier 3 | Distribution | 2012-10-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013000 | 404792557 | Riser/Conduit | HFTD Tier 2 | Distribution | 2012-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013001 | 404792903 | High Sign | HFTD Tier 2 | Distribution | 2012-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013002 | 404793778 | High Sign | HFTD Tier 3 | Distribution | 2012-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013003 | 404793785 | High Sign | HFTD Tier 3 | Distribution | 2012-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013004 | 404798947 | Molding | HFTD Tier 3 | Distribution | 2012-10-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013005 | 404798949 | Molding | HFTD Tier 3 | Distribution | 2012-10-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013006 | 404808059 | Molding | HFTD Tier 3 | Distribution | 2012-11-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013007 | 404808069 | High Sign | HFTD Tier 3 | Distribution | 2012-11-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013008 | 404808079 | High Sign | HFTD Tier 3 | Distribution | 2012-11-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013009 | 404808095 | Molding | HFTD Tier 3 | Distribution | 2012-11-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013010 | 404808100 | High Sign | HFTD Tier 3 | Distribution | 2012-11-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013011 | 404808103 | High Sign | HFTD Tier 3 | Distribution | 2012-11-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013012 | 413873255 | Cable/Conductor | HFTD Tier 3 | Distribution | 2012-11-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013013 | 404823412 | Molding | HFTD Tier 3 | Distribution | 2012-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013014 | 404823524 | High Sign | HFTD Tier 3 | Distribution | 2012-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013015 | 404823530 | High Sign | HFTD Tier 3 | Distribution | 2012-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013016 | 404823532 | High Sign | HFTD Tier 3 | Distribution | 2012-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013017 | 404823548 | Molding | HFTD Tier 3 | Distribution | 2012-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013018 | 404823552 | Molding | HFTD Tier 3 | Distribution | 2012-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013019 | 404823441 | High Sign | HFTD Tier 3 | Distribution | 2012-11-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013020 | 404823462 | Molding | HFTD Tier 3 | Distribution | 2012-11-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013021 | 404823618 | High Sign | HFTD Tier 3 | Distribution | 2012-11-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013022 | 404823622 | High Sign | HFTD Tier 3 | Distribution | 2012-11-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013023 | 404823623 | High Sign | HFTD Tier 3 | Distribution | 2012-11-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013024 | 413834616 | Molding | HFTD Tier 3 | Distribution | 2012-11-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013025 | 413834617 | High Sign | HFTD Tier 3 | Distribution | 2012-11-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013026 | 404824831 | Riser/Conduit | HFTD Tier 3 | Distribution | 2012-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013027 | 404824841 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013028 | 404824842 | Molding | HFTD Tier 3 | Distribution | 2012-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013029 | 404825844 | Molding | HFTD Tier 3 | Distribution | 2012-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013030 | 404825848 | Molding | HFTD Tier 3 | Distribution | 2012-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013031 | 404825851 | Molding | HFTD Tier 3 | Distribution | 2012-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013032 | 404825858 | Molding | HFTD Tier 3 | Distribution | 2012-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013033 | 404825865 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013034 | 404825881 | Molding | HFTD Tier 3 | Distribution | 2012-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013035 | 404825905 | Molding | HFTD Tier 3 | Distribution | 2012-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013036 | 404827888 | High Sign | HFTD Tier 3 | Distribution | 2012-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013037 | 404827895 | High Sign | HFTD Tier 3 | Distribution | 2012-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013038 | 404827904 | High Sign | HFTD Tier 3 | Distribution | 2012-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013039 | 404827906 | High Sign | HFTD Tier 3 | Distribution | 2012-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013040 | 404827907 | High Sign | HFTD Tier 3 | Distribution | 2012-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013041 | 404827908 | High Sign | HFTD Tier 3 | Distribution | 2012-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013042 | 404827909 | High Sign | HFTD Tier 3 | Distribution | 2012-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013043 | 404827911 | High Sign | HFTD Tier 3 | Distribution | 2012-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013044 | 404829327 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013045 | 404828107 | High Sign | HFTD Tier 3 | Distribution | 2012-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013046 | 404828133 | Molding | HFTD Tier 3 | Distribution | 2012-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013047 | 404829070 | High Sign | HFTD Tier 3 | Distribution | 2012-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013048 | 404829073 | Molding | HFTD Tier 3 | Distribution | 2012-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013049 | 404829075 | High Sign | HFTD Tier 3 | Distribution | 2012-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013050 | 404829087 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013051 | 404830153 | High Sign | HFTD Tier 3 | Distribution | 2012-11-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013052 | 404841953 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-11-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013053 | 404841954 | Molding | HFTD Tier 2 | Distribution | 2012-11-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013054 | 404841963 | Molding | HFTD Tier 2 | Distribution | 2012-11-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013055 | 404841970 | Molding | HFTD Tier 2 | Distribution | 2012-11-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013056 | 404841985 | Guy | HFTD Tier 2 | Distribution | 2012-11-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013057 | 404842003 | Cable/Conductor | HFTD Tier 2 | Distribution | 2012-11-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013058 | 404838318 | Molding | HFTD Tier 3 | Distribution | 2012-11-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013059 | 404838357 | High Sign | HFTD Tier 3 | Distribution | 2012-11-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013060 | 404838364 | Hardware/Framing | HFTD Tier 3 | Distribution | 2012-11-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013061 | 404838377 | Riser/Conduit | HFTD Tier 3 | Distribution | 2012-11-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013062 | 404838819 | High Sign | HFTD Tier 2 | Distribution | 2012-11-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013063 | 404838828 | High Sign | HFTD Tier 2 | Distribution | 2012-11-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013064 | 404838836 | High Sign | HFTD Tier 2 | Distribution | 2012-11-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013065 | 404838838 | High Sign | HFTD Tier 2 | Distribution | 2012-11-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013066 | 404838856 | High Sign | HFTD Tier 2 | Distribution | 2012-11-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013067 | 404847485 | Molding | HFTD Tier 2 | Distribution | 2012-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013068 | 404849399 | Molding | HFTD Tier 3 | Distribution | 2012-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013069 | 404849403 | Molding | HFTD Tier 3 | Distribution | 2012-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013070 | 404849411 | Molding | HFTD Tier 3 | Distribution | 2012-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013071 | 404851030 | Molding | HFTD Tier 3 | Distribution | 2012-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013072 | 404859289 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2012-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013073 | 404859323 | Molding | HFTD Tier 3 | Distribution | 2012-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013074 | 404859352 | High Sign | HFTD Tier 3 | Distribution | 2012-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013075 | 404859358 | High Sign | HFTD Tier 3 | Distribution | 2012-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013076 | 404859360 | High Sign | HFTD Tier 3 | Distribution | 2012-12-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013077 | 404867428 | Hardware/Framing | HFTD Tier 2 | Distribution | 2012-12-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013078 | 404893868 | High Sign | HFTD Tier 2 | Distribution | 2013-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013079 | 404894218 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013080 | 404897256 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013081 | 404897354 | High Sign | HFTD Tier 3 | Distribution | 2013-01-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013082 | 404898223 | Riser/Conduit | HFTD Tier 2 | Distribution | 2013-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013083 | 404899085 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013084 | 404899088 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013085 | 404899102 | Molding | HFTD Tier 2 | Distribution | 2013-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013086 | 404899488 | Molding | HFTD Tier 3 | Distribution | 2013-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013087 | 404899915 | Molding | HFTD Tier 2 | Distribution | 2013-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013088 | 404899957 | Molding | HFTD Tier 2 | Distribution | 2013-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013089 | 404899992 | High Sign | HFTD Tier 3 | Distribution | 2013-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013090 | 404899999 | High Sign | HFTD Tier 3 | Distribution | 2013-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013091 | 404900014 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013092 | 404907681 | High Sign | HFTD Tier 2 | Distribution | 2013-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013093 | 404900217 | High Sign | HFTD Tier 2 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013094 | 404900385 | Guy | HFTD Tier 2 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013095 | 404900386 | Guy | HFTD Tier 2 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013096 | 404900394 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013097 | 404900396 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013098 | 404900399 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013099 | 404900401 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013100 | 404900446 | High Sign | HFTD Tier 2 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013101 | 404900460 | Termination | HFTD Tier 2 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013102 | 404900462 | High Sign | HFTD Tier 2 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013103 | 404901572 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013104 | 404901573 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013105 | 404902108 | Molding | HFTD Tier 3 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013106 | 404902116 | Molding | HFTD Tier 3 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013107 | 404902157 | Insulator | HFTD Tier 3 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013108 | 404902172 | Molding | HFTD Tier 3 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013109 | 404902214 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013110 | 404905144 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013111 | 404905154 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013112 | 404905205 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013113 | 404907708 | Molding | HFTD Tier 2 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013114 | 404931886 | High Sign | HFTD Tier 3 | Distribution | 2013-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013115 | 404903172 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013116 | 404903249 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013117 | 404903319 | High Sign | HFTD Tier 2 | Distribution | 2013-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013118 | 404903321 | Molding | HFTD Tier 2 | Distribution | 2013-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013119 | 404903328 | High Sign | HFTD Tier 2 | Distribution | 2013-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013120 | 404903329 | High Sign | HFTD Tier 2 | Distribution | 2013-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013121 | 404903586 | Guy | HFTD Tier 3 | Distribution | 2013-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013122 | 404905254 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013123 | 404905259 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013124 | 404905277 | Molding | HFTD Tier 3 | Distribution | 2013-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013125 | 404905281 | Molding | HFTD Tier 3 | Distribution | 2013-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013126 | 404905283 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013127 | 404905306 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013128 | 404907711 | High Sign | HFTD Tier 2 | Distribution | 2013-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013129 | 404907712 | High Sign | HFTD Tier 2 | Distribution | 2013-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013130 | 404907717 | High Sign | HFTD Tier 2 | Distribution | 2013-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013131 | 404932001 | High Sign | HFTD Tier 3 | Distribution | 2013-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013132 | 404932019 | High Sign | HFTD Tier 3 | Distribution | 2013-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013133 | 404932030 | High Sign | HFTD Tier 3 | Distribution | 2013-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013134 | 404905923 | Termination | HFTD Tier 2 | Distribution | 2013-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013135 | 404906020 | Molding | HFTD Tier 2 | Distribution | 2013-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013136 | 404906021 | High Sign | HFTD Tier 2 | Distribution | 2013-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013137 | 404906034 | Molding | HFTD Tier 2 | Distribution | 2013-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013138 | 404906208 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013139 | 404907765 | High Sign | HFTD Tier 2 | Distribution | 2013-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013140 | 404915225 | Molding | HFTD Tier 3 | Distribution | 2013-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013141 | 404915899 | Molding | HFTD Tier 3 | Distribution | 2013-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013142 | 404915912 | Molding | HFTD Tier 3 | Distribution | 2013-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013143 | 404915942 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013144 | 404915949 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013145 | 404915950 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013146 | 404932033 | High Sign | HFTD Tier 3 | Distribution | 2013-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013147 | 404932040 | Molding | HFTD Tier 3 | Distribution | 2013-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013148 | 404932049 | Molding | HFTD Tier 3 | Distribution | 2013-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013149 | 404932062 | Molding | HFTD Tier 3 | Distribution | 2013-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013150 | 404932063 | High Sign | HFTD Tier 3 | Distribution | 2013-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013151 | 404932071 | Molding | HFTD Tier 3 | Distribution | 2013-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013152 | 404908435 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013153 | 404908436 | High Sign | HFTD Tier 3 | Distribution | 2013-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013154 | 404908443 | Guy | HFTD Tier 3 | Distribution | 2013-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013155 | 404932482 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013156 | 404932486 | Molding | HFTD Tier 2 | Distribution | 2013-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013157 | 404932487 | High Sign | HFTD Tier 2 | Distribution | 2013-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013158 | 404932521 | Guy | HFTD Tier 3 | Distribution | 2013-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013159 | 404932531 | High Sign | HFTD Tier 3 | Distribution | 2013-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013160 | 404932532 | Molding | HFTD Tier 2 | Distribution | 2013-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013161 | 404934208 | Molding | HFTD Tier 3 | Distribution | 2013-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013162 | 404934295 | Molding | HFTD Tier 3 | Distribution | 2013-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013163 | 404934309 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013164 | 404934318 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013165 | 404934320 | Molding | HFTD Tier 3 | Distribution | 2013-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013166 | 404934321 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013167 | 404934327 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013168 | 404934819 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013169 | 404934950 | High Sign | HFTD Tier 2 | Distribution | 2013-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013170 | 404934951 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013171 | 404934953 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013172 | 404939388 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013173 | 404939400 | Molding | HFTD Tier 3 | Distribution | 2013-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013174 | 404939403 | Molding | HFTD Tier 3 | Distribution | 2013-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013175 | 404939407 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013176 | 404939422 | Molding | HFTD Tier 3 | Distribution | 2013-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013177 | 404939453 | Molding | HFTD Tier 3 | Distribution | 2013-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013178 | 404937160 | Molding | HFTD Tier 3 | Distribution | 2013-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013179 | 404937454 | High Sign | HFTD Tier 2 | Distribution | 2013-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013180 | 404937464 | Termination | HFTD Tier 2 | Distribution | 2013-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013181 | 404937477 | High Sign | HFTD Tier 2 | Distribution | 2013-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013182 | 404937812 | High Sign | HFTD Tier 3 | Distribution | 2013-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013183 | 404938519 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013184 | 404939264 | Molding | HFTD Tier 3 | Distribution | 2013-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013185 | 404939265 | High Sign | HFTD Tier 3 | Distribution | 2013-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013186 | 404939274 | High Sign | HFTD Tier 3 | Distribution | 2013-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013187 | 404939469 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013188 | 404939484 | High Sign | HFTD Tier 3 | Distribution | 2013-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013189 | 404939495 | Molding | HFTD Tier 3 | Distribution | 2013-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013190 | 404939506 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013191 | 404939516 | Molding | HFTD Tier 3 | Distribution | 2013-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013192 | 404939523 | High Sign | HFTD Tier 3 | Distribution | 2013-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013193 | 404939529 | Molding | HFTD Tier 3 | Distribution | 2013-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013194 | 404939530 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013195 | 404939553 | High Sign | HFTD Tier 3 | Distribution | 2013-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013196 | 404977812 | Molding | HFTD Tier 3 | Distribution | 2013-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013197 | 404940264 | High Sign | HFTD Tier 2 | Distribution | 2013-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013198 | 404940272 | Molding | HFTD Tier 2 | Distribution | 2013-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013199 | 404940368 | High Sign | HFTD Tier 2 | Distribution | 2013-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013200 | 404940378 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013201 | 404940380 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013202 | 404940383 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013203 | 404940384 | Molding | HFTD Tier 2 | Distribution | 2013-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013204 | 404940386 | High Sign | HFTD Tier 2 | Distribution | 2013-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013205 | 404940393 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013206 | 404954372 | High Sign | HFTD Tier 3 | Distribution | 2013-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013207 | 404954373 | Molding | HFTD Tier 3 | Distribution | 2013-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013208 | 404954374 | High Sign | HFTD Tier 3 | Distribution | 2013-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013209 | 404954380 | High Sign | HFTD Tier 3 | Distribution | 2013-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013210 | 404954385 | Molding | HFTD Tier 3 | Distribution | 2013-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013211 | 404954386 | High Sign | HFTD Tier 3 | Distribution | 2013-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013212 | 404954420 | Molding | HFTD Tier 3 | Distribution | 2013-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013213 | 404954422 | Molding | HFTD Tier 3 | Distribution | 2013-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013214 | 404952782 | Vis Strips | HFTD Tier 2 | Distribution | 2013-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013215 | 404952881 | High Sign | HFTD Tier 3 | Distribution | 2013-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013216 | 404952935 | High Sign | HFTD Tier 2 | Distribution | 2013-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013217 | 404953739 | Guy | HFTD Tier 2 | Distribution | 2013-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013218 | 404953740 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013219 | 404953741 | High Sign | HFTD Tier 2 | Distribution | 2013-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013220 | 404953742 | Molding | HFTD Tier 2 | Distribution | 2013-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013221 | 404953754 | Molding | HFTD Tier 2 | Distribution | 2013-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013222 | 404963157 | High Sign | HFTD Tier 3 | Distribution | 2013-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013223 | 404963170 | Guy | HFTD Tier 3 | Distribution | 2013-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013224 | 404963220 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013225 | 404978365 | High Sign | HFTD Tier 2 | Distribution | 2013-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013226 | 404978366 | High Sign | HFTD Tier 2 | Distribution | 2013-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013227 | 404978392 | Molding | HFTD Tier 2 | Distribution | 2013-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013228 | 404978393 | Guy | HFTD Tier 2 | Distribution | 2013-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013229 | 404978665 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013230 | 404967315 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2013-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013231 | 404967905 | High Sign | HFTD Tier 2 | Distribution | 2013-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013232 | 404967926 | High Sign | HFTD Tier 2 | Distribution | 2013-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013233 | 404967978 | Molding | HFTD Tier 2 | Distribution | 2013-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013234 | 404967980 | Molding | HFTD Tier 2 | Distribution | 2013-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013235 | 404967991 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013236 | 404970732 | High Sign | HFTD Tier 3 | Distribution | 2013-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013237 | 404970805 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013238 | 404978690 | Molding | HFTD Tier 3 | Distribution | 2013-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013239 | 404976233 | Molding | HFTD Tier 2 | Distribution | 2013-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013240 | 404976252 | High Sign | HFTD Tier 3 | Distribution | 2013-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013241 | 404976254 | Molding | HFTD Tier 3 | Distribution | 2013-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013242 | 404976262 | Guy | HFTD Tier 3 | Distribution | 2013-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013243 | 404976271 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013244 | 404976293 | Molding | HFTD Tier 2 | Distribution | 2013-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013245 | 404976370 | Guy | HFTD Tier 3 | Distribution | 2013-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013246 | 404978183 | Molding | HFTD Tier 3 | Distribution | 2013-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013247 | 404978287 | Molding | HFTD Tier 3 | Distribution | 2013-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013248 | 404978761 | Molding | HFTD Tier 2 | Distribution | 2013-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013249 | 404984397 | Guy | HFTD Tier 3 | Distribution | 2013-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013250 | 404987805 | Molding | HFTD Tier 2 | Distribution | 2013-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013251 | 404987809 | Molding | HFTD Tier 3 | Distribution | 2013-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013252 | 404987811 | Molding | HFTD Tier 2 | Distribution | 2013-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013253 | 404987812 | High Sign | HFTD Tier 2 | Distribution | 2013-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013254 | 404987818 | Guy | HFTD Tier 3 | Distribution | 2013-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013255 | 404987821 | Guy | HFTD Tier 3 | Distribution | 2013-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013256 | 404987833 | Molding | HFTD Tier 3 | Distribution | 2013-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013257 | 404987834 | High Sign | HFTD Tier 3 | Distribution | 2013-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013258 | 404987836 | High Sign | HFTD Tier 3 | Distribution | 2013-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013259 | 404988062 | Molding | HFTD Tier 2 | Distribution | 2013-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013260 | 404989688 | High Sign | HFTD Tier 2 | Distribution | 2013-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013261 | 404990192 | High Sign | HFTD Tier 3 | Distribution | 2013-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013262 | 404990565 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013263 | 404991723 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013264 | 404991724 | High Sign | HFTD Tier 3 | Distribution | 2013-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013265 | 404991733 | Insulator | HFTD Tier 3 | Distribution | 2013-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013266 | 404991735 | Guy | HFTD Tier 3 | Distribution | 2013-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013267 | 404991736 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013268 | 404992756 | Guy | HFTD Tier 3 | Distribution | 2013-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013269 | 404993784 | High Sign | HFTD Tier 3 | Distribution | 2013-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013270 | 404994414 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013271 | 404994428 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013272 | 404996844 | High Sign | HFTD Tier 3 | Distribution | 2013-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013273 | 404996875 | High Sign | HFTD Tier 3 | Distribution | 2013-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013274 | 404996911 | Guy | HFTD Tier 2 | Distribution | 2013-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013275 | 404996920 | Guy | HFTD Tier 2 | Distribution | 2013-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013276 | 405003492 | Molding | HFTD Tier 3 | Distribution | 2013-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013277 | 405003501 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013278 | 405003856 | Molding | HFTD Tier 3 | Distribution | 2013-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013279 | 405005373 | Molding | HFTD Tier 3 | Distribution | 2013-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013280 | 405005414 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013281 | 405005455 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013282 | 405006513 | Vis Strips | HFTD Tier 2 | Distribution | 2013-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013283 | 405006556 | Vis Strips | HFTD Tier 2 | Distribution | 2013-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013284 | 405007760 | High Sign | HFTD Tier 3 | Distribution | 2013-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013285 | 405007791 | High Sign | HFTD Tier 2 | Distribution | 2013-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013286 | 405008090 | Guy | HFTD Tier 3 | Distribution | 2013-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013287 | 405011087 | High Sign | HFTD Tier 3 | Distribution | 2013-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013288 | 405011658 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013289 | 405011674 | High Sign | HFTD Tier 3 | Distribution | 2013-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013290 | 405011735 | Molding | HFTD Tier 3 | Distribution | 2013-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013291 | 405020385 | Guy | HFTD Tier 2 | Distribution | 2013-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013292 | 405012128 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013293 | 405012132 | Molding | HFTD Tier 3 | Distribution | 2013-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013294 | 405012162 | Molding | HFTD Tier 3 | Distribution | 2013-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013295 | 405013509 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013296 | 405013998 | Molding | HFTD Tier 3 | Distribution | 2013-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013297 | 405016457 | High Sign | HFTD Tier 3 | Distribution | 2013-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013298 | 405016463 | High Sign | HFTD Tier 3 | Distribution | 2013-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013299 | 405017213 | Guy | HFTD Tier 3 | Distribution | 2013-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013300 | 405017215 | Guy | HFTD Tier 3 | Distribution | 2013-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013301 | 405017217 | Molding | HFTD Tier 3 | Distribution | 2013-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013302 | 405017225 | Molding | HFTD Tier 3 | Distribution | 2013-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013303 | 405019621 | High Sign | HFTD Tier 2 | Distribution | 2013-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013304 | 405017579 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013305 | 405017633 | Ground | HFTD Tier 3 | Distribution | 2013-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013306 | 405017652 | Guy | HFTD Tier 3 | Distribution | 2013-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013307 | 405018933 | Molding | HFTD Tier 3 | Distribution | 2013-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013308 | 405020037 | Guy | HFTD Tier 2 | Distribution | 2013-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013309 | 405020047 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013310 | 405020071 | High Sign | HFTD Tier 2 | Distribution | 2013-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013311 | 405020484 | Vis Strips | HFTD Tier 2 | Distribution | 2013-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013312 | 405021132 | Molding | HFTD Tier 3 | Distribution | 2013-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013313 | 405022297 | Molding | HFTD Tier 3 | Distribution | 2013-02-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013314 | 405022300 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-02-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013315 | 405022308 | Molding | HFTD Tier 3 | Distribution | 2013-02-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013316 | 405022315 | Molding | HFTD Tier 3 | Distribution | 2013-02-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013317 | 405022320 | High Sign | HFTD Tier 3 | Distribution | 2013-02-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013318 | 405022323 | Molding | HFTD Tier 3 | Distribution | 2013-02-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013319 | 405023071 | High Sign | HFTD Tier 2 | Distribution | 2013-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013320 | 405023202 | High Sign | HFTD Tier 2 | Distribution | 2013-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013321 | 405023205 | High Sign | HFTD Tier 2 | Distribution | 2013-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013322 | 405023209 | Molding | HFTD Tier 2 | Distribution | 2013-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013323 | 405023221 | High Sign | HFTD Tier 2 | Distribution | 2013-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013324 | 405023222 | High Sign | HFTD Tier 2 | Distribution | 2013-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013325 | 405023250 | High Sign | HFTD Tier 2 | Distribution | 2013-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013326 | 405023279 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013327 | 405025016 | High Sign | HFTD Tier 3 | Distribution | 2013-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013328 | 405025812 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013329 | 405025821 | High Sign | HFTD Tier 3 | Distribution | 2013-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013330 | 405025830 | Molding | HFTD Tier 3 | Distribution | 2013-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013331 | 405025832 | High Sign | HFTD Tier 3 | Distribution | 2013-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013332 | 405026333 | Molding | HFTD Tier 2 | Distribution | 2013-02-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013333 | 405027028 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-02-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013334 | 405027032 | Guy | HFTD Tier 2 | Distribution | 2013-02-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013335 | 405028775 | Vis Strips | HFTD Tier 2 | Distribution | 2013-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013336 | 405028973 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013337 | 405029055 | High Sign | HFTD Tier 2 | Distribution | 2013-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013338 | 405029190 | Molding | HFTD Tier 2 | Distribution | 2013-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013339 | 405029202 | High Sign | HFTD Tier 2 | Distribution | 2013-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013340 | 405030030 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013341 | 405031245 | High Sign | HFTD Tier 3 | Distribution | 2013-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013342 | 405031307 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013343 | 405031377 | Molding | HFTD Tier 3 | Distribution | 2013-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013344 | 405031380 | Molding | HFTD Tier 3 | Distribution | 2013-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013345 | 405033932 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013346 | 405033936 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013347 | 405033955 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013348 | 405033960 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013349 | 405034262 | Vis Strips | HFTD Tier 2 | Distribution | 2013-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013350 | 405034321 | Vis Strips | HFTD Tier 2 | Distribution | 2013-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013351 | 405034342 | Vis Strips | HFTD Tier 2 | Distribution | 2013-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013352 | 405035543 | High Sign | HFTD Tier 2 | Distribution | 2013-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013353 | 405035639 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013354 | 405035653 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013355 | 405035664 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013356 | 405036126 | Molding | HFTD Tier 3 | Distribution | 2013-02-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013357 | 405036744 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-02-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013358 | 405038028 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-02-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013359 | 405038058 | ID Markings | HFTD Tier 2 | Distribution | 2013-02-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013360 | 405038573 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-02-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013361 | 405038579 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-02-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013362 | 405038663 | High Sign | HFTD Tier 2 | Distribution | 2013-02-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013363 | 405038680 | High Sign | HFTD Tier 2 | Distribution | 2013-02-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013364 | 405039113 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-02-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013365 | 405039125 | High Sign | HFTD Tier 2 | Distribution | 2013-02-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013366 | 405039145 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-02-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013367 | 405039147 | High Sign | HFTD Tier 2 | Distribution | 2013-02-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013368 | 405042358 | High Sign | HFTD Tier 3 | Distribution | 2013-02-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013369 | 405040644 | High Sign | HFTD Tier 2 | Distribution | 2013-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013370 | 405040647 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013371 | 405040653 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013372 | 405040658 | High Sign | HFTD Tier 2 | Distribution | 2013-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013373 | 405040659 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013374 | 405040660 | High Sign | HFTD Tier 2 | Distribution | 2013-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013375 | 405040661 | High Sign | HFTD Tier 2 | Distribution | 2013-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013376 | 405040663 | High Sign | HFTD Tier 2 | Distribution | 2013-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013377 | 405040665 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013378 | 405040670 | High Sign | HFTD Tier 2 | Distribution | 2013-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013379 | 405040672 | Molding | HFTD Tier 2 | Distribution | 2013-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013380 | 405041034 | Ground | HFTD Tier 3 | Distribution | 2013-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013381 | 405041048 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013382 | 405041064 | Guy | HFTD Tier 3 | Distribution | 2013-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013383 | 405044553 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013384 | 405045303 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013385 | 405046664 | Molding | HFTD Tier 3 | Distribution | 2013-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013386 | 405046793 | Molding | HFTD Tier 3 | Distribution | 2013-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013387 | 405046851 | High Sign | HFTD Tier 3 | Distribution | 2013-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013388 | 405047982 | Molding | HFTD Tier 3 | Distribution | 2013-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013389 | 405047989 | High Sign | HFTD Tier 3 | Distribution | 2013-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013390 | 405048274 | Molding | HFTD Tier 3 | Distribution | 2013-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013391 | 405048288 | Molding | HFTD Tier 2 | Distribution | 2013-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013392 | 405048339 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013393 | 405048359 | Guy | HFTD Tier 3 | Distribution | 2013-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013394 | 405048718 | High Sign | HFTD Tier 3 | Distribution | 2013-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013395 | 405048743 | High Sign | HFTD Tier 3 | Distribution | 2013-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013396 | 405048744 | Guy | HFTD Tier 3 | Distribution | 2013-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013397 | 405048746 | High Sign | HFTD Tier 3 | Distribution | 2013-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013398 | 405048749 | High Sign | HFTD Tier 3 | Distribution | 2013-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013399 | 405048752 | Molding | HFTD Tier 3 | Distribution | 2013-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013400 | 405048756 | High Sign | HFTD Tier 3 | Distribution | 2013-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013401 | 405048774 | High Sign | HFTD Tier 3 | Distribution | 2013-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013402 | 405050574 | High Sign | HFTD Tier 2 | Distribution | 2013-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013403 | 405051067 | Molding | HFTD Tier 3 | Distribution | 2013-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013404 | 405051081 | Molding | HFTD Tier 2 | Distribution | 2013-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013405 | 405051303 | High Sign | HFTD Tier 2 | Distribution | 2013-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013406 | 405051331 | Guy | HFTD Tier 2 | Distribution | 2013-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013407 | 405051341 | Molding | HFTD Tier 2 | Distribution | 2013-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013408 | 405051503 | High Sign | HFTD Tier 3 | Distribution | 2013-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013409 | 405051516 | High Sign | HFTD Tier 3 | Distribution | 2013-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013410 | 405051541 | Molding | HFTD Tier 3 | Distribution | 2013-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013411 | 405053397 | Molding | HFTD Tier 3 | Distribution | 2013-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013412 | 405053403 | High Sign | HFTD Tier 3 | Distribution | 2013-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013413 | 405053411 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013414 | 405053429 | High Sign | HFTD Tier 3 | Distribution | 2013-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013415 | 405053626 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013416 | 405053637 | Molding | HFTD Tier 3 | Distribution | 2013-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013417 | 405053638 | High Sign | HFTD Tier 3 | Distribution | 2013-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013418 | 405053667 | Molding | HFTD Tier 3 | Distribution | 2013-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013419 | 405053669 | Molding | HFTD Tier 3 | Distribution | 2013-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013420 | 405056063 | High Sign | HFTD Tier 2 | Distribution | 2013-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013421 | 405056066 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013422 | 405056072 | Molding | HFTD Tier 2 | Distribution | 2013-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013423 | 405056093 | Molding | HFTD Tier 2 | Distribution | 2013-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013424 | 405056133 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2013-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013425 | 405056144 | Termination | HFTD Tier 2 | Distribution | 2013-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013426 | 405056237 | High Sign | HFTD Tier 3 | Distribution | 2013-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013427 | 405059661 | High Sign | HFTD Tier 2 | Distribution | 2013-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013428 | 405060208 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013429 | 405061034 | Molding | HFTD Tier 3 | Distribution | 2013-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013430 | 405061698 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013431 | 405062084 | High Sign | HFTD Tier 3 | Distribution | 2013-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013432 | 405062095 | High Sign | HFTD Tier 3 | Distribution | 2013-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013433 | 405062104 | High Sign | HFTD Tier 3 | Distribution | 2013-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013434 | 405062106 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013435 | 405062111 | High Sign | HFTD Tier 3 | Distribution | 2013-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013436 | 405062124 | High Sign | HFTD Tier 3 | Distribution | 2013-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013437 | 405062409 | Molding | HFTD Tier 3 | Distribution | 2013-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013438 | 405062425 | Molding | HFTD Tier 3 | Distribution | 2013-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013439 | 405062433 | Molding | HFTD Tier 3 | Distribution | 2013-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013440 | 405062441 | High Sign | HFTD Tier 3 | Distribution | 2013-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013441 | 405075442 | High Sign | HFTD Tier 2 | Distribution | 2013-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013442 | 405063216 | High Sign | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013443 | 405063250 | High Sign | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013444 | 405063473 | High Sign | HFTD Tier 2 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013445 | 405063869 | High Sign | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013446 | 405063878 | High Sign | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013447 | 405063879 | High Sign | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013448 | 405063881 | Molding | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013449 | 405063882 | High Sign | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013450 | 405063886 | High Sign | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013451 | 405063892 | High Sign | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013452 | 405063893 | High Sign | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013453 | 405063896 | High Sign | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013454 | 405063904 | High Sign | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013455 | 405063909 | High Sign | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013456 | 405063913 | Molding | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013457 | 405063915 | High Sign | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013458 | 405065383 | High Sign | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013459 | 405065716 | Molding | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013460 | 405066000 | High Sign | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013461 | 405066018 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013462 | 405066021 | Molding | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013463 | 405066022 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013464 | 405066031 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013465 | 405066047 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013466 | 405066062 | Molding | HFTD Tier 3 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013467 | 405075444 | Molding | HFTD Tier 2 | Distribution | 2013-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013468 | 405066418 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013469 | 405066434 | High Sign | HFTD Tier 3 | Distribution | 2013-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013470 | 405066437 | High Sign | HFTD Tier 3 | Distribution | 2013-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013471 | 405066467 | High Sign | HFTD Tier 3 | Distribution | 2013-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013472 | 405066468 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013473 | 405066476 | Molding | HFTD Tier 3 | Distribution | 2013-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013474 | 405066573 | Guy | HFTD Tier 2 | Distribution | 2013-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013475 | 405066590 | Molding | HFTD Tier 2 | Distribution | 2013-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013476 | 405068696 | High Sign | HFTD Tier 3 | Distribution | 2013-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013477 | 405068712 | Molding | HFTD Tier 3 | Distribution | 2013-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013478 | 405068732 | High Sign | HFTD Tier 3 | Distribution | 2013-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013479 | 405068743 | High Sign | HFTD Tier 3 | Distribution | 2013-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013480 | 405069220 | Molding | HFTD Tier 3 | Distribution | 2013-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013481 | 405069239 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013482 | 405069240 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013483 | 405069246 | High Sign | HFTD Tier 3 | Distribution | 2013-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013484 | 405069261 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013485 | 405069458 | Molding | HFTD Tier 3 | Distribution | 2013-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013486 | 405069471 | High Sign | HFTD Tier 3 | Distribution | 2013-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013487 | 405069473 | High Sign | HFTD Tier 3 | Distribution | 2013-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013488 | 405070147 | High Sign | HFTD Tier 3 | Distribution | 2013-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013489 | 405070150 | High Sign | HFTD Tier 3 | Distribution | 2013-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013490 | 405070161 | High Sign | HFTD Tier 3 | Distribution | 2013-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013491 | 405070163 | High Sign | HFTD Tier 3 | Distribution | 2013-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013492 | 405070164 | Molding | HFTD Tier 3 | Distribution | 2013-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013493 | 405070167 | High Sign | HFTD Tier 3 | Distribution | 2013-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013494 | 405070169 | High Sign | HFTD Tier 3 | Distribution | 2013-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013495 | 405070676 | Molding | HFTD Tier 3 | Distribution | 2013-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013496 | 405071252 | High Sign | HFTD Tier 3 | Distribution | 2013-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013497 | 405071262 | High Sign | HFTD Tier 3 | Distribution | 2013-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013498 | 405071265 | Molding | HFTD Tier 3 | Distribution | 2013-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013499 | 405071269 | Molding | HFTD Tier 3 | Distribution | 2013-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013500 | 405071279 | High Sign | HFTD Tier 3 | Distribution | 2013-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013501 | 405071301 | High Sign | HFTD Tier 3 | Distribution | 2013-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013502 | 405071304 | High Sign | HFTD Tier 3 | Distribution | 2013-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013503 | 405073101 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013504 | 405075363 | High Sign | HFTD Tier 3 | Distribution | 2013-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013505 | 405075364 | Molding | HFTD Tier 3 | Distribution | 2013-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013506 | 405075366 | Molding | HFTD Tier 3 | Distribution | 2013-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013507 | 405075410 | Molding | HFTD Tier 3 | Distribution | 2013-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013508 | 405075411 | Molding | HFTD Tier 3 | Distribution | 2013-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013509 | 405076649 | High Sign | HFTD Tier 3 | Distribution | 2013-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013510 | 405076659 | High Sign | HFTD Tier 3 | Distribution | 2013-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013511 | 405076686 | Molding | HFTD Tier 3 | Distribution | 2013-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013512 | 405076687 | Molding | HFTD Tier 3 | Distribution | 2013-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013513 | 405078238 | High Sign | HFTD Tier 2 | Distribution | 2013-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013514 | 405078595 | Guy | HFTD Tier 2 | Distribution | 2013-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013515 | 405078884 | Molding | HFTD Tier 3 | Distribution | 2013-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013516 | 405078885 | Molding | HFTD Tier 3 | Distribution | 2013-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013517 | 405078890 | Molding | HFTD Tier 3 | Distribution | 2013-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013518 | 405078893 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013519 | 405078900 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013520 | 413841144 | High Sign | HFTD Tier 3 | Distribution | 2013-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013521 | 405081461 | Molding | HFTD Tier 2 | Distribution | 2013-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013522 | 405081493 | High Sign | HFTD Tier 2 | Distribution | 2013-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013523 | 405081508 | High Sign | HFTD Tier 2 | Distribution | 2013-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013524 | 405081509 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013525 | 405081834 | High Sign | HFTD Tier 3 | Distribution | 2013-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013526 | 405081843 | Molding | HFTD Tier 3 | Distribution | 2013-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013527 | 405081901 | Molding | HFTD Tier 3 | Distribution | 2013-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013528 | 405081910 | High Sign | HFTD Tier 3 | Distribution | 2013-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013529 | 405082087 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013530 | 405082095 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013531 | 405082114 | High Sign | HFTD Tier 3 | Distribution | 2013-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013532 | 405082168 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013533 | 405082182 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013534 | 405083029 | Molding | HFTD Tier 2 | Distribution | 2013-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013535 | 405083734 | High Sign | HFTD Tier 2 | Distribution | 2013-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013536 | 405085411 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013537 | 405087898 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013538 | 405087914 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013539 | 405087916 | Guy | HFTD Tier 3 | Distribution | 2013-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013540 | 405087920 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013541 | 405087921 | Guy | HFTD Tier 3 | Distribution | 2013-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013542 | 405087925 | High Sign | HFTD Tier 3 | Distribution | 2013-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013543 | 405087939 | Guy | HFTD Tier 3 | Distribution | 2013-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013544 | 405088181 | High Sign | HFTD Tier 3 | Distribution | 2013-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013545 | 405088183 | Molding | HFTD Tier 3 | Distribution | 2013-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013546 | 405088192 | High Sign | HFTD Tier 3 | Distribution | 2013-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013547 | 405104305 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013548 | 405089477 | Molding | HFTD Tier 3 | Distribution | 2013-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013549 | 405090629 | Bond | HFTD Tier 2 | Distribution | 2013-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013550 | 405090638 | Guy | HFTD Tier 2 | Distribution | 2013-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013551 | 405090665 | Bond | HFTD Tier 2 | Distribution | 2013-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013552 | 405090878 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013553 | 405091073 | High Sign | HFTD Tier 3 | Distribution | 2013-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013554 | 405091366 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013555 | 405091371 | Guy | HFTD Tier 3 | Distribution | 2013-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013556 | 405091376 | Guy | HFTD Tier 3 | Distribution | 2013-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013557 | 405093120 | Molding | HFTD Tier 3 | Distribution | 2013-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013558 | 405094112 | Molding | HFTD Tier 3 | Distribution | 2013-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013559 | 405094123 | Guy | HFTD Tier 3 | Distribution | 2013-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013560 | 405094172 | Guy | HFTD Tier 3 | Distribution | 2013-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013561 | 405094379 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013562 | 405094402 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013563 | 405094443 | Molding | HFTD Tier 3 | Distribution | 2013-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013564 | 405095017 | Molding | HFTD Tier 3 | Distribution | 2013-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013565 | 405095022 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013566 | 405095023 | Molding | HFTD Tier 3 | Distribution | 2013-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013567 | 405095946 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013568 | 405105017 | Riser/Conduit | HFTD Tier 2 | Distribution | 2013-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013569 | 405105025 | High Sign | HFTD Tier 2 | Distribution | 2013-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013570 | 405105035 | High Sign | HFTD Tier 2 | Distribution | 2013-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013571 | 405105038 | Molding | HFTD Tier 2 | Distribution | 2013-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013572 | 405097390 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013573 | 405098054 | Molding | HFTD Tier 3 | Distribution | 2013-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013574 | 405098056 | Guy | HFTD Tier 3 | Distribution | 2013-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013575 | 405098057 | High Sign | HFTD Tier 3 | Distribution | 2013-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013576 | 405098065 | High Sign | HFTD Tier 3 | Distribution | 2013-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013577 | 405098066 | Guy | HFTD Tier 3 | Distribution | 2013-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013578 | 405098076 | High Sign | HFTD Tier 3 | Distribution | 2013-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013579 | 405098104 | Molding | HFTD Tier 3 | Distribution | 2013-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013580 | 405098136 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013581 | 405098163 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013582 | 405099002 | High Sign | HFTD Tier 3 | Distribution | 2013-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013583 | 405099040 | Molding | HFTD Tier 3 | Distribution | 2013-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013584 | 405099074 | Molding | HFTD Tier 3 | Distribution | 2013-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013585 | 405099080 | High Sign | HFTD Tier 3 | Distribution | 2013-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013586 | 405099081 | Molding | HFTD Tier 3 | Distribution | 2013-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013587 | 405099089 | High Sign | HFTD Tier 3 | Distribution | 2013-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013588 | 405099090 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013589 | 405099092 | Guy | HFTD Tier 3 | Distribution | 2013-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013590 | 405099096 | High Sign | HFTD Tier 3 | Distribution | 2013-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013591 | 405099100 | High Sign | HFTD Tier 3 | Distribution | 2013-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013592 | 405099102 | High Sign | HFTD Tier 3 | Distribution | 2013-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013593 | 405099107 | High Sign | HFTD Tier 3 | Distribution | 2013-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013594 | 405099108 | High Sign | HFTD Tier 3 | Distribution | 2013-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013595 | 405100858 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013596 | 405100871 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013597 | 405100876 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013598 | 405100884 | Molding | HFTD Tier 3 | Distribution | 2013-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013599 | 405100913 | High Sign | HFTD Tier 3 | Distribution | 2013-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013600 | 405107306 | High Sign | HFTD Tier 2 | Distribution | 2013-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013601 | 405107336 | Guy | HFTD Tier 2 | Distribution | 2013-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013602 | 405107342 | High Sign | HFTD Tier 2 | Distribution | 2013-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013603 | 405110008 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013604 | 405103634 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013605 | 405103913 | Molding | HFTD Tier 3 | Distribution | 2013-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013606 | 405105113 | Bond | HFTD Tier 2 | Distribution | 2013-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013607 | 405105975 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013608 | 405105978 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013609 | 405105989 | High Sign | HFTD Tier 3 | Distribution | 2013-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013610 | 405105996 | Molding | HFTD Tier 3 | Distribution | 2013-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013611 | 405106293 | Molding | HFTD Tier 3 | Distribution | 2013-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013612 | 405108930 | Riser/Conduit | HFTD Tier 2 | Distribution | 2013-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013613 | 405108934 | Molding | HFTD Tier 2 | Distribution | 2013-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013614 | 405108942 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013615 | 405108945 | Termination | HFTD Tier 2 | Distribution | 2013-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013616 | 405108957 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2013-04-01 | 41456 | 2 | Ignition Risk, no GO95 exception | [7 empty] | SCE | 2026 | 2
1120013617 | 405110127 | High Sign | HFTD Tier 2 | Distribution | 2013-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013618 | 405110143 | High Sign | HFTD Tier 2 | Distribution | 2013-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013619 | 405110156 | Molding | HFTD Tier 2 | Distribution | 2013-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013620 | 405110163 | Handhole | HFTD Tier 2 | Distribution | 2013-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013621 | 405110180 | Molding | HFTD Tier 2 | Distribution | 2013-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013622 | 405110227 | Molding | HFTD Tier 3 | Distribution | 2013-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013623 | 405110236 | High Sign | HFTD Tier 3 | Distribution | 2013-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013624 | 405121032 | Molding | HFTD Tier 2 | Distribution | 2013-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013625 | 405112283 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2013-04-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013626 | 405113358 | Molding | HFTD Tier 2 | Distribution | 2013-04-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013627 | 405113486 | Molding | HFTD Tier 2 | Distribution | 2013-04-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013628 | 405113503 | Molding | HFTD Tier 2 | Distribution | 2013-04-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013629 | 405117539 | Guy | HFTD Tier 2 | Distribution | 2013-04-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013630 | 405117546 | High Sign | HFTD Tier 2 | Distribution | 2013-04-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013631 | 405128039 | High Sign | HFTD Tier 2 | Distribution | 2013-04-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013632 | 405115235 | Guy | HFTD Tier 2 | Distribution | 2013-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013633 | 405116762 | High Sign | HFTD Tier 3 | Distribution | 2013-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013634 | 405116802 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013635 | 405118620 | High Sign | HFTD Tier 2 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013636 | 405120153 | Vis Strips | HFTD Tier 2 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013637 | 405120155 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013638 | 405120160 | Molding | HFTD Tier 2 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013639 | 405120162 | Molding | HFTD Tier 2 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013640 | 405120245 | Molding | HFTD Tier 2 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013641 | 405120268 | Guy | HFTD Tier 2 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013642 | 405120271 | Molding | HFTD Tier 2 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013643 | 405120449 | Pole Tag | HFTD Tier 3 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013644 | 405120458 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013645 | 405120460 | Molding | HFTD Tier 3 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013646 | 405120470 | Pole Tag | HFTD Tier 3 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013647 | 405120472 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013648 | 405120474 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013649 | 405120475 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013650 | 405120488 | Guy | HFTD Tier 3 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013651 | 405120489 | Molding | HFTD Tier 3 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013652 | 405124058 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013653 | 405124063 | High Sign | HFTD Tier 3 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013654 | 405124070 | High Sign | HFTD Tier 3 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013655 | 405124076 | High Sign | HFTD Tier 3 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013656 | 405124079 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013657 | 405124091 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013658 | 405122246 | Molding | HFTD Tier 2 | Distribution | 2013-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013659 | 405123234 | High Sign | HFTD Tier 2 | Distribution | 2013-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013660 | 405123254 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013661 | 405123271 | Guy | HFTD Tier 2 | Distribution | 2013-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013662 | 405130693 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2013-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013663 | 405145134 | Molding | HFTD Tier 3 | Distribution | 2013-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013664 | 405145147 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013665 | 405145165 | High Sign | HFTD Tier 3 | Distribution | 2013-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013666 | 405145170 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013667 | 405123832 | Molding | HFTD Tier 3 | Distribution | 2013-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013668 | 405123833 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013669 | 405123834 | Guy | HFTD Tier 3 | Distribution | 2013-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013670 | 405125851 | Crossarm | HFTD Tier 2 | Distribution | 2013-04-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013671 | 405126811 | Guy | HFTD Tier 2 | Distribution | 2013-04-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013672 | 405126813 | Molding | HFTD Tier 2 | Distribution | 2013-04-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013673 | 405126815 | Guy | HFTD Tier 2 | Distribution | 2013-04-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013674 | 405126921 | High Sign | HFTD Tier 2 | Distribution | 2013-04-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013675 | 405127585 | High Sign | HFTD Tier 3 | Distribution | 2013-04-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013676 | 405127675 | Molding | HFTD Tier 3 | Distribution | 2013-04-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013677 | 405129488 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013678 | 405130338 | Riser/Conduit | HFTD Tier 2 | Distribution | 2013-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013679 | 405130374 | Molding | HFTD Tier 2 | Distribution | 2013-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013680 | 405130484 | Molding | HFTD Tier 3 | Distribution | 2013-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013681 | 405130498 | High Sign | HFTD Tier 3 | Distribution | 2013-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013682 | 405130500 | High Sign | HFTD Tier 3 | Distribution | 2013-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013683 | 405130502 | High Sign | HFTD Tier 3 | Distribution | 2013-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013684 | 405130817 | Insulator | HFTD Tier 3 | Distribution | 2013-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013685 | 405131143 | Molding | HFTD Tier 3 | Distribution | 2013-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013686 | 405131144 | High Sign | HFTD Tier 3 | Distribution | 2013-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013687 | 405131148 | Molding | HFTD Tier 3 | Distribution | 2013-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013688 | 405131159 | High Sign | HFTD Tier 3 | Distribution | 2013-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013689 | 405131162 | Molding | HFTD Tier 3 | Distribution | 2013-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013690 | 405131183 | Ground | HFTD Tier 3 | Distribution | 2013-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013691 | 405133821 | High Sign | HFTD Tier 2 | Distribution | 2013-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013692 | 405134151 | Molding | HFTD Tier 2 | Distribution | 2013-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013693 | 405134305 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013694 | 405134691 | Molding | HFTD Tier 3 | Distribution | 2013-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013695 | 405144691 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013696 | 405144741 | Guy | HFTD Tier 3 | Distribution | 2013-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013697 | 405138086 | Riser/Conduit | HFTD Tier 2 | Distribution | 2013-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013698 | 405138091 | High Sign | HFTD Tier 3 | Distribution | 2013-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013699 | 405138095 | Guy | HFTD Tier 2 | Distribution | 2013-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013700 | 405141005 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013701 | 405141007 | Molding | HFTD Tier 3 | Distribution | 2013-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013702 | 405141014 | High Sign | HFTD Tier 3 | Distribution | 2013-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013703 | 405144738 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013704 | 405144744 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013705 | 405144754 | Molding | HFTD Tier 3 | Distribution | 2013-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013706 | 405144757 | High Sign | HFTD Tier 3 | Distribution | 2013-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013707 | 405144759 | Guy | HFTD Tier 3 | Distribution | 2013-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013708 | 405144760 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013709 | 405144791 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013710 | 405144824 | Guy | HFTD Tier 3 | Distribution | 2013-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013711 | 405139445 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013712 | 405144808 | Guy | HFTD Tier 3 | Distribution | 2013-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013713 | 405144826 | Molding | HFTD Tier 3 | Distribution | 2013-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013714 | 405143025 | Molding | HFTD Tier 3 | Distribution | 2013-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013715 | 405143031 | High Sign | HFTD Tier 3 | Distribution | 2013-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013716 | 405143032 | Molding | HFTD Tier 3 | Distribution | 2013-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013717 | 405143039 | Molding | HFTD Tier 3 | Distribution | 2013-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013718 | 405143064 | High Sign | HFTD Tier 3 | Distribution | 2013-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013719 | 405144259 | High Sign | HFTD Tier 2 | Distribution | 2013-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013720 | 405144269 | High Sign | HFTD Tier 2 | Distribution | 2013-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013721 | 405144278 | High Sign | HFTD Tier 2 | Distribution | 2013-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013722 | 405144280 | High Sign | HFTD Tier 2 | Distribution | 2013-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013723 | 405144281 | High Sign | HFTD Tier 2 | Distribution | 2013-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013724 | 405144284 | High Sign | HFTD Tier 2 | Distribution | 2013-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013725 | 405144921 | Guy | HFTD Tier 3 | Distribution | 2013-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013726 | 405145067 | Molding | HFTD Tier 3 | Distribution | 2013-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013727 | 405145068 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013728 | 405145092 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013729 | 405145646 | High Sign | HFTD Tier 3 | Distribution | 2013-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013730 | 405145662 | Molding | HFTD Tier 3 | Distribution | 2013-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013731 | 405145681 | High Sign | HFTD Tier 3 | Distribution | 2013-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013732 | 405145688 | Molding | HFTD Tier 3 | Distribution | 2013-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013733 | 405145692 | High Sign | HFTD Tier 3 | Distribution | 2013-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013734 | 405157531 | High Sign | HFTD Tier 3 | Distribution | 2013-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013735 | 405147030 | High Sign | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013736 | 405147041 | High Sign | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013737 | 405147058 | High Sign | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013738 | 405148290 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013739 | 405148492 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013740 | 405148500 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013741 | 405148543 | Molding | HFTD Tier 2 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013742 | 405148552 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013743 | 405148979 | Guy | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013744 | 405148990 | High Sign | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013745 | 405149126 | High Sign | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013746 | 405149136 | High Sign | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013747 | 405149144 | High Sign | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013748 | 405149178 | High Sign | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013749 | 405149184 | Molding | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013750 | 405153294 | Molding | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013751 | 405153304 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013752 | 405153313 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013753 | 405153315 | Molding | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013754 | 405153341 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013755 | 405153457 | Ground | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013756 | 405153472 | Guy | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013757 | 405153473 | Guy | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013758 | 405157555 | Guy | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013759 | 405157556 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013760 | 405149542 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013761 | 405149543 | Guy | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013762 | 405149544 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013763 | 405149546 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013764 | 405150240 | High Sign | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013765 | 405150253 | High Sign | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013766 | 405150255 | High Sign | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013767 | 405150742 | High Sign | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013768 | 405152065 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013769 | 405152136 | Molding | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013770 | 405152219 | Guy | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013771 | 405152223 | High Sign | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013772 | 405152246 | High Sign | HFTD Tier 2 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013773 | 405152248 | High Sign | HFTD Tier 2 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013774 | 405152320 | Guy | HFTD Tier 2 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013775 | 405152436 | Guy | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013776 | 405152437 | Guy | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013777 | 405152446 | High Sign | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013778 | 405152450 | High Sign | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013779 | 405153221 | Molding | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013780 | 405153262 | Molding | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013781 | 405153268 | High Sign | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013782 | 405153382 | High Sign | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013783 | 405153442 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013784 | 405153514 | Molding | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013785 | 405153535 | Molding | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013786 | 405153557 | Molding | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013787 | 405153558 | Guy | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013788 | 405153560 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013789 | 405153575 | High Sign | HFTD Tier 3 | Distribution | 2013-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013790 | 405156023 | Guy | HFTD Tier 2 | Distribution | 2013-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013791 | 405156028 | Bond | HFTD Tier 2 | Distribution | 2013-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013792 | 405156119 | High Sign | HFTD Tier 3 | Distribution | 2013-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013793 | 405156150 | High Sign | HFTD Tier 3 | Distribution | 2013-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013794 | 405156213 | Molding | HFTD Tier 3 | Distribution | 2013-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013795 | 405156217 | High Sign | HFTD Tier 3 | Distribution | 2013-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013796 | 405156240 | Molding | HFTD Tier 3 | Distribution | 2013-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013797 | 405156425 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013798 | 405156446 | Molding | HFTD Tier 2 | Distribution | 2013-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013799 | 405156467 | High Sign | HFTD Tier 2 | Distribution | 2013-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013800 | 405156546 | High Sign | HFTD Tier 3 | Distribution | 2013-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013801 | 405156550 | Guy | HFTD Tier 3 | Distribution | 2013-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013802 | 405156552 | Molding | HFTD Tier 3 | Distribution | 2013-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013803 | 405157641 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013804 | 405157876 | High Sign | HFTD Tier 3 | Distribution | 2013-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013805 | 405157881 | Guy | HFTD Tier 3 | Distribution | 2013-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013806 | 405157884 | Molding | HFTD Tier 3 | Distribution | 2013-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013807 | 405160238 | Molding | HFTD Tier 3 | Distribution | 2013-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013808 | 405157399 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013809 | 405159328 | Molding | HFTD Tier 3 | Distribution | 2013-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013810 | 405162603 | Molding | HFTD Tier 2 | Distribution | 2013-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013811 | 405164253 | Molding | HFTD Tier 3 | Distribution | 2013-04-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013812 | 405165354 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-04-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013813 | 405169760 | High Sign | HFTD Tier 3 | Distribution | 2013-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013814 | 405170140 | Molding | HFTD Tier 3 | Distribution | 2013-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013815 | 405171877 | Molding | HFTD Tier 2 | Distribution | 2013-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013816 | 405171888 | Molding | HFTD Tier 2 | Distribution | 2013-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013817 | 405171895 | Guy | HFTD Tier 2 | Distribution | 2013-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013818 | 405172336 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013819 | 405172693 | Molding | HFTD Tier 3 | Distribution | 2013-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013820 | 405173056 | High Sign | HFTD Tier 3 | Distribution | 2013-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013821 | 405173075 | High Sign | HFTD Tier 3 | Distribution | 2013-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013822 | 405173124 | Molding | HFTD Tier 3 | Distribution | 2013-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013823 | 405173136 | Molding | HFTD Tier 3 | Distribution | 2013-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013824 | 405173139 | Molding | HFTD Tier 3 | Distribution | 2013-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013825 | 405173153 | Molding | HFTD Tier 3 | Distribution | 2013-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013826 | 405174012 | Molding | HFTD Tier 2 | Distribution | 2013-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013827 | 405175003 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013828 | 405175157 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013829 | 405175181 | High Sign | HFTD Tier 3 | Distribution | 2013-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013830 | 405175422 | High Sign | HFTD Tier 3 | Distribution | 2013-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013831 | 405180421 | Molding | HFTD Tier 2 | Distribution | 2013-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013832 | 405180527 | High Sign | HFTD Tier 3 | Distribution | 2013-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013833 | 405180546 | Guy | HFTD Tier 3 | Distribution | 2013-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013834 | 405180782 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2013-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013835 | 405180794 | Molding | HFTD Tier 2 | Distribution | 2013-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013836 | 405180803 | Molding | HFTD Tier 2 | Distribution | 2013-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013837 | 405181763 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013838 | 405182422 | Guy | HFTD Tier 3 | Distribution | 2013-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013839 | 405183373 | Molding | HFTD Tier 2 | Distribution | 2013-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013840 | 405183376 | Molding | HFTD Tier 2 | Distribution | 2013-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013841 | 405183381 | High Sign | HFTD Tier 2 | Distribution | 2013-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013842 | 405183407 | Molding | HFTD Tier 2 | Distribution | 2013-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013843 | 405183629 | Guy | HFTD Tier 2 | Distribution | 2013-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013844 | 405183648 | Guy | HFTD Tier 3 | Distribution | 2013-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013845 | 405191657 | Molding | HFTD Tier 3 | Distribution | 2013-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013846 | 405185160 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013847 | 405185171 | Guy | HFTD Tier 3 | Distribution | 2013-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013848 | 405185181 | Molding | HFTD Tier 3 | Distribution | 2013-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013849 | 405186819 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013850 | 405186891 | High Sign | HFTD Tier 2 | Distribution | 2013-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013851 | 405188767 | High Sign | HFTD Tier 3 | Distribution | 2013-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013852 | 405188769 | Molding | HFTD Tier 3 | Distribution | 2013-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013853 | 405188805 | Guy | HFTD Tier 3 | Distribution | 2013-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013854 | 405188809 | High Sign | HFTD Tier 3 | Distribution | 2013-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013855 | 405188813 | High Sign | HFTD Tier 3 | Distribution | 2013-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013856 | 405194006 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013857 | 405194010 | High Sign | HFTD Tier 3 | Distribution | 2013-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013858 | 405201802 | High Sign | HFTD Tier 2 | Distribution | 2013-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013859 | 405199397 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013860 | 405201596 | High Sign | HFTD Tier 3 | Distribution | 2013-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013861 | 405201598 | High Sign | HFTD Tier 3 | Distribution | 2013-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013862 | 405201620 | High Sign | HFTD Tier 3 | Distribution | 2013-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013863 | 405201660 | Molding | HFTD Tier 3 | Distribution | 2013-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013864 | 405201661 | Molding | HFTD Tier 3 | Distribution | 2013-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013865 | 405201662 | High Sign | HFTD Tier 3 | Distribution | 2013-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013866 | 405201809 | Molding | HFTD Tier 2 | Distribution | 2013-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013867 | 405201837 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013868 | 405202657 | High Sign | HFTD Tier 2 | Distribution | 2013-05-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013869 | 405205105 | Molding | HFTD Tier 3 | Distribution | 2013-05-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013870 | 405205111 | Guy | HFTD Tier 2 | Distribution | 2013-05-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013871 | 405211938 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-05-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013872 | 405228963 | High Sign | HFTD Tier 3 | Distribution | 2013-05-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013873 | 405215937 | Riser/Conduit | HFTD Tier 2 | Distribution | 2013-05-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013874 | 405218109 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-05-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013875 | 405219357 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013876 | 405219364 | High Sign | HFTD Tier 3 | Distribution | 2013-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013877 | 405219365 | High Sign | HFTD Tier 3 | Distribution | 2013-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013878 | 405219377 | High Sign | HFTD Tier 3 | Distribution | 2013-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013879 | 405219555 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013880 | 405219933 | High Sign | HFTD Tier 2 | Distribution | 2013-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013881 | 405221464 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013882 | 405221604 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013883 | 405221623 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013884 | 405221627 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013885 | 405221636 | Molding | HFTD Tier 3 | Distribution | 2013-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013886 | 405221666 | High Sign | HFTD Tier 3 | Distribution | 2013-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013887 | 405221667 | Molding | HFTD Tier 3 | Distribution | 2013-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013888 | 405221668 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013889 | 405221669 | High Sign | HFTD Tier 3 | Distribution | 2013-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013890 | 405221671 | High Sign | HFTD Tier 3 | Distribution | 2013-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013891 | 405221683 | High Sign | HFTD Tier 3 | Distribution | 2013-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013892 | 405223294 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013893 | 405223298 | Guy | HFTD Tier 3 | Distribution | 2013-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013894 | 405223301 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013895 | 405225406 | Molding | HFTD Tier 3 | Distribution | 2013-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013896 | 405225411 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013897 | 405225419 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013898 | 405225422 | Molding | HFTD Tier 3 | Distribution | 2013-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013899 | 405225425 | High Sign | HFTD Tier 3 | Distribution | 2013-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013900 | 405225427 | Molding | HFTD Tier 3 | Distribution | 2013-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013901 | 405225432 | High Sign | HFTD Tier 3 | Distribution | 2013-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013902 | 405230605 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013903 | 405230636 | Ground | HFTD Tier 2 | Distribution | 2013-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013904 | 405232109 | Molding | HFTD Tier 3 | Distribution | 2013-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013905 | 405232115 | High Sign | HFTD Tier 3 | Distribution | 2013-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013906 | 405232118 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013907 | 405233511 | Guy | HFTD Tier 2 | Distribution | 2013-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013908 | 405233518 | High Sign | HFTD Tier 2 | Distribution | 2013-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013909 | 405233633 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013910 | 405235212 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013911 | 405235216 | Molding | HFTD Tier 2 | Distribution | 2013-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013912 | 405235217 | High Sign | HFTD Tier 2 | Distribution | 2013-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013913 | 405235219 | Molding | HFTD Tier 2 | Distribution | 2013-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013914 | 405235549 | Molding | HFTD Tier 3 | Distribution | 2013-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013915 | 405235557 | Molding | HFTD Tier 3 | Distribution | 2013-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013916 | 405235610 | Molding | HFTD Tier 3 | Distribution | 2013-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013917 | 405235623 | Molding | HFTD Tier 3 | Distribution | 2013-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013918 | 405236640 | High Sign | HFTD Tier 2 | Distribution | 2013-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013919 | 405236718 | High Sign | HFTD Tier 2 | Distribution | 2013-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013920 | 405236738 | Molding | HFTD Tier 2 | Distribution | 2013-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013921 | 405236739 | Molding | HFTD Tier 2 | Distribution | 2013-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013922 | 405236755 | Guy | HFTD Tier 2 | Distribution | 2013-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013923 | 405236787 | Guy | HFTD Tier 2 | Distribution | 2013-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013924 | 405238298 | High Sign | HFTD Tier 2 | Distribution | 2013-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013925 | 405238303 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013926 | 405238456 | High Sign | HFTD Tier 3 | Distribution | 2013-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013927 | 405238487 | Molding | HFTD Tier 3 | Distribution | 2013-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013928 | 405238499 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013929 | 405238502 | Molding | HFTD Tier 3 | Distribution | 2013-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013930 | 405238503 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013931 | 405238512 | Molding | HFTD Tier 3 | Distribution | 2013-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013932 | 405238528 | Molding | HFTD Tier 3 | Distribution | 2013-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013933 | 405241363 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013934 | 405239504 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013935 | 405240107 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013936 | 405241407 | Molding | HFTD Tier 2 | Distribution | 2013-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013937 | 405241462 | Guy | HFTD Tier 2 | Distribution | 2013-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013938 | 405241464 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2013-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013939 | 405241861 | Molding | HFTD Tier 3 | Distribution | 2013-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013940 | 405241868 | High Sign | HFTD Tier 3 | Distribution | 2013-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013941 | 405241872 | High Sign | HFTD Tier 3 | Distribution | 2013-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013942 | 405241881 | Molding | HFTD Tier 3 | Distribution | 2013-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013943 | 405241886 | Molding | HFTD Tier 3 | Distribution | 2013-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013944 | 405241891 | High Sign | HFTD Tier 3 | Distribution | 2013-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013945 | 405241892 | Molding | HFTD Tier 3 | Distribution | 2013-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013946 | 405241895 | High Sign | HFTD Tier 3 | Distribution | 2013-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013947 | 405241896 | High Sign | HFTD Tier 3 | Distribution | 2013-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013948 | 405241904 | Guy | HFTD Tier 3 | Distribution | 2013-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013949 | 405241909 | Connector | HFTD Tier 3 | Distribution | 2013-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013950 | 405241913 | Guy | HFTD Tier 3 | Distribution | 2013-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013951 | 405241915 | Insulator | HFTD Tier 3 | Distribution | 2013-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013952 | 405257533 | Guy | HFTD Tier 3 | Distribution | 2013-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013953 | 405242978 | High Sign | HFTD Tier 3 | Distribution | 2013-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013954 | 405242992 | High Sign | HFTD Tier 3 | Distribution | 2013-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013955 | 405243048 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013956 | 405243847 | Guy | HFTD Tier 2 | Distribution | 2013-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013957 | 405257609 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013958 | 405257642 | Molding | HFTD Tier 3 | Distribution | 2013-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013959 | 405245521 | High Sign | HFTD Tier 2 | Distribution | 2013-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013960 | 405245527 | High Sign | HFTD Tier 2 | Distribution | 2013-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013961 | 405245530 | High Sign | HFTD Tier 2 | Distribution | 2013-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013962 | 405245534 | High Sign | HFTD Tier 2 | Distribution | 2013-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013963 | 405245547 | High Sign | HFTD Tier 2 | Distribution | 2013-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013964 | 405245551 | High Sign | HFTD Tier 2 | Distribution | 2013-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013965 | 405245853 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013966 | 405245867 | Molding | HFTD Tier 2 | Distribution | 2013-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013967 | 405245879 | Riser/Conduit | HFTD Tier 2 | Distribution | 2013-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013968 | 405245880 | Molding | HFTD Tier 2 | Distribution | 2013-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013969 | 405248291 | High Sign | HFTD Tier 2 | Distribution | 2013-05-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013970 | 405248307 | High Sign | HFTD Tier 2 | Distribution | 2013-05-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013971 | 405248448 | High Sign | HFTD Tier 2 | Distribution | 2013-05-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013972 | 405248753 | High Sign | HFTD Tier 2 | Distribution | 2013-05-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013973 | 405249038 | High Sign | HFTD Tier 3 | Distribution | 2013-05-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013974 | 405250192 | High Sign | HFTD Tier 3 | Distribution | 2013-05-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013975 | 405250195 | Molding | HFTD Tier 3 | Distribution | 2013-05-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013976 | 405250200 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-05-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013977 | 405251409 | High Sign | HFTD Tier 2 | Distribution | 2013-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013978 | 405251425 | High Sign | HFTD Tier 2 | Distribution | 2013-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013979 | 405251853 | High Sign | HFTD Tier 2 | Distribution | 2013-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013980 | 405251864 | Molding | HFTD Tier 2 | Distribution | 2013-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013981 | 405251873 | Molding | HFTD Tier 2 | Distribution | 2013-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013982 | 405253378 | Molding | HFTD Tier 3 | Distribution | 2013-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013983 | 405253389 | High Sign | HFTD Tier 3 | Distribution | 2013-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013984 | 405253391 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013985 | 405253394 | Molding | HFTD Tier 3 | Distribution | 2013-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013986 | 405253406 | Molding | HFTD Tier 3 | Distribution | 2013-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013987 | 405253408 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013988 | 405253410 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013989 | 405253514 | Guy | HFTD Tier 3 | Distribution | 2013-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013990 | 405255138 | Molding | HFTD Tier 2 | Distribution | 2013-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013991 | 405257048 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013992 | 405257096 | Molding | HFTD Tier 2 | Distribution | 2013-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013993 | 405264616 | Insulator | HFTD Tier 2 | Distribution | 2013-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013994 | 405264622 | Molding | HFTD Tier 2 | Distribution | 2013-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013995 | 405261863 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013996 | 405261870 | High Sign | HFTD Tier 3 | Distribution | 2013-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013997 | 405261886 | Riser/Conduit | HFTD Tier 2 | Distribution | 2013-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013998 | 405261918 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120013999 | 405261921 | Molding | HFTD Tier 2 | Distribution | 2013-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014000 | 405261922 | Riser/Conduit | HFTD Tier 2 | Distribution | 2013-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014001 | 405261933 | Riser/Conduit | HFTD Tier 2 | Distribution | 2013-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014002 | 405261934 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014003 | 405261939 | Riser/Conduit | HFTD Tier 2 | Distribution | 2013-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014004 | 405261950 | Molding | HFTD Tier 2 | Distribution | 2013-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014005 | 405261951 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014006 | 405264200 | Molding | HFTD Tier 2 | Distribution | 2013-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014007 | 405264296 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014008 | 405264301 | Molding | HFTD Tier 3 | Distribution | 2013-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014009 | 405264309 | High Sign | HFTD Tier 3 | Distribution | 2013-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014010 | 405264325 | Molding | HFTD Tier 3 | Distribution | 2013-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014011 | 405264655 | High Sign | HFTD Tier 2 | Distribution | 2013-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014012 | 405264679 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014013 | 405264692 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014014 | 405265679 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014015 | 405266038 | Guy | HFTD Tier 2 | Distribution | 2013-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014016 | 405266496 | High Sign | HFTD Tier 2 | Distribution | 2013-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014017 | 405268256 | Molding | HFTD Tier 3 | Distribution | 2013-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014018 | 405268261 | High Sign | HFTD Tier 3 | Distribution | 2013-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014019 | 405269153 | High Sign | HFTD Tier 2 | Distribution | 2013-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014020 | 405271467 | High Sign | HFTD Tier 3 | Distribution | 2013-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014021 | 405271835 | High Sign | HFTD Tier 3 | Distribution | 2013-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014022 | 405271875 | Molding | HFTD Tier 3 | Distribution | 2013-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014023 | 405275037 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014024 | 405275038 | Molding | HFTD Tier 3 | Distribution | 2013-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014025 | 405275045 | Molding | HFTD Tier 3 | Distribution | 2013-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014026 | 405275053 | Molding | HFTD Tier 3 | Distribution | 2013-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014027 | 405276008 | Molding | HFTD Tier 2 | Distribution | 2013-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014028 | 405276030 | High Sign | HFTD Tier 2 | Distribution | 2013-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014029 | 405276041 | Molding | HFTD Tier 2 | Distribution | 2013-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014030 | 405276054 | High Sign | HFTD Tier 2 | Distribution | 2013-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014031 | 405276043 | High Sign | HFTD Tier 2 | Distribution | 2013-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014032 | 405276052 | Molding | HFTD Tier 2 | Distribution | 2013-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014033 | 405279128 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014034 | 405279129 | Molding | HFTD Tier 3 | Distribution | 2013-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014035 | 405279139 | Molding | HFTD Tier 3 | Distribution | 2013-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014036 | 405279151 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014037 | 405279152 | High Sign | HFTD Tier 3 | Distribution | 2013-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014038 | 405279154 | High Sign | HFTD Tier 3 | Distribution | 2013-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014039 | 405279161 | High Sign | HFTD Tier 3 | Distribution | 2013-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014040 | 405279168 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014041 | 405281198 | High Sign | HFTD Tier 3 | Distribution | 2013-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014042 | 405285986 | High Sign | HFTD Tier 3 | Distribution | 2013-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014043 | 405285990 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014044 | 405285998 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014045 | 405286005 | High Sign | HFTD Tier 3 | Distribution | 2013-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014046 | 405286020 | High Sign | HFTD Tier 3 | Distribution | 2013-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014047 | 405286042 | High Sign | HFTD Tier 3 | Distribution | 2013-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014048 | 405286046 | Molding | HFTD Tier 3 | Distribution | 2013-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014049 | 405283383 | Molding | HFTD Tier 3 | Distribution | 2013-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014050 | 405283384 | High Sign | HFTD Tier 3 | Distribution | 2013-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014051 | 405283402 | Guy | HFTD Tier 3 | Distribution | 2013-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014052 | 405283404 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014053 | 405284256 | Molding | HFTD Tier 3 | Distribution | 2013-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014054 | 405285776 | Molding | HFTD Tier 3 | Distribution | 2013-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014055 | 405285800 | Molding | HFTD Tier 3 | Distribution | 2013-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014056 | 405285803 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014057 | 405286027 | Molding | HFTD Tier 3 | Distribution | 2013-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014058 | 405286029 | High Sign | HFTD Tier 3 | Distribution | 2013-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014059 | 405286037 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014060 | 405286038 | High Sign | HFTD Tier 3 | Distribution | 2013-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014061 | 405286051 | Molding | HFTD Tier 3 | Distribution | 2013-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014062 | 405286062 | Molding | HFTD Tier 3 | Distribution | 2013-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014063 | 405286071 | High Sign | HFTD Tier 3 | Distribution | 2013-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014064 | 405286086 | High Sign | HFTD Tier 3 | Distribution | 2013-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014065 | 405286847 | Molding | HFTD Tier 2 | Distribution | 2013-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014066 | 405288025 | High Sign | HFTD Tier 3 | Distribution | 2013-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014067 | 405288031 | High Sign | HFTD Tier 3 | Distribution | 2013-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014068 | 405291952 | High Sign | HFTD Tier 3 | Distribution | 2013-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014069 | 405292071 | High Sign | HFTD Tier 2 | Distribution | 2013-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014070 | 405292980 | Molding | HFTD Tier 2 | Distribution | 2013-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014071 | 405295006 | Molding | HFTD Tier 3 | Distribution | 2013-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014072 | 405295022 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014073 | 405295028 | High Sign | HFTD Tier 3 | Distribution | 2013-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014074 | 405295039 | High Sign | HFTD Tier 3 | Distribution | 2013-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014075 | 405295048 | Molding | HFTD Tier 3 | Distribution | 2013-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014076 | 405295057 | Molding | HFTD Tier 3 | Distribution | 2013-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014077 | 405295059 | Molding | HFTD Tier 3 | Distribution | 2013-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014078 | 405296241 | High Sign | HFTD Tier 2 | Distribution | 2013-06-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014079 | 405296776 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-06-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014080 | 405298530 | High Sign | HFTD Tier 3 | Distribution | 2013-06-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014081 | 405298549 | High Sign | HFTD Tier 3 | Distribution | 2013-06-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014082 | 405298553 | Molding | HFTD Tier 3 | Distribution | 2013-06-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014083 | 405300326 | Guy | HFTD Tier 2 | Distribution | 2013-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014084 | 405301309 | High Sign | HFTD Tier 2 | Distribution | 2013-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014085 | 405301961 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014086 | 405301962 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014087 | 405301983 | High Sign | HFTD Tier 3 | Distribution | 2013-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014088 | 405301984 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014089 | 405301987 | High Sign | HFTD Tier 3 | Distribution | 2013-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014090 | 405301992 | Molding | HFTD Tier 3 | Distribution | 2013-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014091 | 405301995 | High Sign | HFTD Tier 3 | Distribution | 2013-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014092 | 405301997 | Molding | HFTD Tier 3 | Distribution | 2013-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014093 | 405301998 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014094 | 405302000 | Molding | HFTD Tier 3 | Distribution | 2013-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014095 | 405302001 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014096 | 405304977 | High Sign | HFTD Tier 3 | Distribution | 2013-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014097 | 405304978 | Molding | HFTD Tier 3 | Distribution | 2013-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014098 | 405307899 | Molding | HFTD Tier 2 | Distribution | 2013-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014099 | 405307913 | High Sign | HFTD Tier 2 | Distribution | 2013-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014100 | 405308353 | High Sign | HFTD Tier 3 | Distribution | 2013-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014101 | 405308357 | Guy | HFTD Tier 3 | Distribution | 2013-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014102 | 405308358 | High Sign | HFTD Tier 3 | Distribution | 2013-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014103 | 405308362 | High Sign | HFTD Tier 3 | Distribution | 2013-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014104 | 405308364 | Guy | HFTD Tier 3 | Distribution | 2013-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014105 | 405308370 | Guy | HFTD Tier 3 | Distribution | 2013-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014106 | 405308375 | High Sign | HFTD Tier 3 | Distribution | 2013-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014107 | 405308394 | High Sign | HFTD Tier 3 | Distribution | 2013-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014108 | 405308516 | Guy | HFTD Tier 3 | Distribution | 2013-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014109 | 405308531 | Molding | HFTD Tier 3 | Distribution | 2013-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014110 | 405309616 | Molding | HFTD Tier 3 | Distribution | 2013-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014111 | 405309622 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014112 | 405309929 | Molding | HFTD Tier 3 | Distribution | 2013-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014113 | 405309948 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014114 | 405309958 | Molding | HFTD Tier 3 | Distribution | 2013-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014115 | 405311849 | Guy | HFTD Tier 3 | Distribution | 2013-06-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014116 | 405311850 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-06-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014117 | 405311910 | Guy | HFTD Tier 3 | Distribution | 2013-06-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014118 | 405312467 | Molding | HFTD Tier 2 | Distribution | 2013-06-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014119 | 405314820 | Molding | HFTD Tier 3 | Distribution | 2013-06-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014120 | 405314826 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-06-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014121 | 405315523 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-06-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014122 | 405315586 | Guy | HFTD Tier 3 | Distribution | 2013-06-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014123 | 405315596 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-06-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014124 | 405317933 | Molding | HFTD Tier 2 | Distribution | 2013-06-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014125 | 405318789 | Molding | HFTD Tier 3 | Distribution | 2013-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014126 | 405318791 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014127 | 405318793 | High Sign | HFTD Tier 3 | Distribution | 2013-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014128 | 405318797 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014129 | 405318799 | Molding | HFTD Tier 3 | Distribution | 2013-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014130 | 405318805 | High Sign | HFTD Tier 3 | Distribution | 2013-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014131 | 405319028 | Guy | HFTD Tier 3 | Distribution | 2013-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014132 | 405319031 | Guy | HFTD Tier 3 | Distribution | 2013-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014133 | 405319298 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014134 | 405320145 | High Sign | HFTD Tier 3 | Distribution | 2013-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014135 | 405320148 | Guy | HFTD Tier 3 | Distribution | 2013-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014136 | 405320164 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014137 | 405320165 | Molding | HFTD Tier 3 | Distribution | 2013-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014138 | 405320171 | Molding | HFTD Tier 3 | Distribution | 2013-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014139 | 405325398 | Molding | HFTD Tier 3 | Distribution | 2013-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014140 | 405322261 | Molding | HFTD Tier 2 | Distribution | 2013-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014141 | 405322288 | High Sign | HFTD Tier 2 | Distribution | 2013-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014142 | 405322505 | High Sign | HFTD Tier 3 | Distribution | 2013-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014143 | 405322513 | High Sign | HFTD Tier 3 | Distribution | 2013-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014144 | 405322549 | Guy | HFTD Tier 2 | Distribution | 2013-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014145 | 405323850 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014146 | 405323876 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014147 | 405324205 | Molding | HFTD Tier 3 | Distribution | 2013-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014148 | 405324250 | High Sign | HFTD Tier 3 | Distribution | 2013-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014149 | 405325194 | Guy | HFTD Tier 2 | Distribution | 2013-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014150 | 405325196 | Guy | HFTD Tier 2 | Distribution | 2013-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014151 | 405325200 | Guy | HFTD Tier 2 | Distribution | 2013-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014152 | 405325205 | Guy | HFTD Tier 2 | Distribution | 2013-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014153 | 405327363 | Molding | HFTD Tier 3 | Distribution | 2013-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014154 | 405327368 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014155 | 405327369 | Molding | HFTD Tier 3 | Distribution | 2013-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014156 | 405327372 | Molding | HFTD Tier 3 | Distribution | 2013-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014157 | 405327380 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014158 | 405327382 | Molding | HFTD Tier 3 | Distribution | 2013-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014159 | 405327390 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014160 | 405327395 | Molding | HFTD Tier 3 | Distribution | 2013-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014161 | 405329922 | Molding | HFTD Tier 2 | Distribution | 2013-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014162 | 405329923 | High Sign | HFTD Tier 2 | Distribution | 2013-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014163 | 405330232 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014164 | 405334476 | Molding | HFTD Tier 2 | Distribution | 2013-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014165 | 405337475 | Guy | HFTD Tier 3 | Distribution | 2013-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014166 | 405337490 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014167 | 405332881 | Molding | HFTD Tier 3 | Distribution | 2013-07-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014168 | 405334533 | Molding | HFTD Tier 2 | Distribution | 2013-07-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014169 | 405334559 | Molding | HFTD Tier 2 | Distribution | 2013-07-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014170 | 405334564 | Molding | HFTD Tier 2 | Distribution | 2013-07-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014171 | 405335212 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-07-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014172 | 405335227 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-07-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014173 | 405335229 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-07-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014174 | 405337398 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-07-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014175 | 405337529 | Guy | HFTD Tier 3 | Distribution | 2013-07-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014176 | 405345619 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014177 | 405351793 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014178 | 405343626 | Ground | HFTD Tier 2 | Distribution | 2013-07-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014179 | 405345716 | Molding | HFTD Tier 3 | Distribution | 2013-07-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014180 | 405351830 | Guy | HFTD Tier 3 | Distribution | 2013-07-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014181 | 405346988 | High Sign | HFTD Tier 3 | Distribution | 2013-07-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014182 | 405346998 | Molding | HFTD Tier 3 | Distribution | 2013-07-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014183 | 405347196 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-07-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014184 | 405347205 | Guy | HFTD Tier 3 | Distribution | 2013-07-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014185 | 405347210 | Guy | HFTD Tier 3 | Distribution | 2013-07-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014186 | 405348543 | Molding | HFTD Tier 3 | Distribution | 2013-07-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014187 | 405348581 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-07-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014188 | 405348600 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-07-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014189 | 405348610 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-07-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014190 | 405350700 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-07-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014191 | 405355758 | Molding | HFTD Tier 3 | Distribution | 2013-07-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014192 | 405355759 | High Sign | HFTD Tier 3 | Distribution | 2013-07-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014193 | 405355760 | Molding | HFTD Tier 3 | Distribution | 2013-07-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014194 | 405348635 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014195 | 405351916 | Molding | HFTD Tier 3 | Distribution | 2013-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014196 | 405351948 | Molding | HFTD Tier 3 | Distribution | 2013-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014197 | 405355459 | High Sign | HFTD Tier 3 | Distribution | 2013-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014198 | 405355767 | Molding | HFTD Tier 3 | Distribution | 2013-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014199 | 405355770 | High Sign | HFTD Tier 3 | Distribution | 2013-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014200 | 405355837 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014201 | 405352885 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014202 | 405355825 | Molding | HFTD Tier 3 | Distribution | 2013-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014203 | 405359349 | High Sign | HFTD Tier 3 | Distribution | 2013-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014204 | 405359357 | High Sign | HFTD Tier 3 | Distribution | 2013-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014205 | 405357081 | Molding | HFTD Tier 2 | Distribution | 2013-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014206 | 405357083 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014207 | 405357093 | Insulator | HFTD Tier 2 | Distribution | 2013-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014208 | 405358190 | High Sign | HFTD Tier 3 | Distribution | 2013-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014209 | 405358632 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014210 | 405358960 | High Sign | HFTD Tier 2 | Distribution | 2013-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014211 | 405358968 | High Sign | HFTD Tier 2 | Distribution | 2013-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014212 | 405359055 | High Sign | HFTD Tier 3 | Distribution | 2013-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014213 | 405359057 | Molding | HFTD Tier 3 | Distribution | 2013-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014214 | 405359399 | Molding | HFTD Tier 3 | Distribution | 2013-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014215 | 405359400 | Ground | HFTD Tier 3 | Distribution | 2013-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014216 | 405359446 | Molding | HFTD Tier 3 | Distribution | 2013-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014217 | 405359471 | Molding | HFTD Tier 3 | Distribution | 2013-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014218 | 405370113 | High Sign | HFTD Tier 3 | Distribution | 2013-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014219 | 405360374 | Molding | HFTD Tier 2 | Distribution | 2013-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014220 | 405362240 | Guy | HFTD Tier 3 | Distribution | 2013-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014221 | 405362389 | Guy | HFTD Tier 3 | Distribution | 2013-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014222 | 405365403 | High Sign | HFTD Tier 3 | Distribution | 2013-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014223 | 405365404 | Molding | HFTD Tier 3 | Distribution | 2013-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014224 | 405364036 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014225 | 405365090 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014226 | 405365094 | Molding | HFTD Tier 3 | Distribution | 2013-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014227 | 405366008 | Pole Tag | HFTD Tier 2 | Distribution | 2013-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014228 | 405366055 | High Sign | HFTD Tier 3 | Distribution | 2013-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014229 | 405366057 | High Sign | HFTD Tier 3 | Distribution | 2013-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014230 | 405367147 | Molding | HFTD Tier 2 | Distribution | 2013-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014231 | 405367152 | High Sign | HFTD Tier 2 | Distribution | 2013-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014232 | 405367153 | High Sign | HFTD Tier 2 | Distribution | 2013-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014233 | 405367160 | High Sign | HFTD Tier 2 | Distribution | 2013-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014234 | 405367161 | Molding | HFTD Tier 2 | Distribution | 2013-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014235 | 405367162 | High Sign | HFTD Tier 2 | Distribution | 2013-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014236 | 405367747 | Molding | HFTD Tier 3 | Distribution | 2013-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014237 | 405368896 | Guy | HFTD Tier 2 | Distribution | 2013-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014238 | 405375643 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014239 | 405379708 | Molding | HFTD Tier 2 | Distribution | 2013-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014240 | 405379717 | Molding | HFTD Tier 2 | Distribution | 2013-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014241 | 405388374 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2013-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014242 | 405388987 | Guy | HFTD Tier 3 | Distribution | 2013-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014243 | 405391574 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2013-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014244 | 405381227 | High Sign | HFTD Tier 2 | Distribution | 2013-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014245 | 405383319 | High Sign | HFTD Tier 2 | Distribution | 2013-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014246 | 405383330 | Molding | HFTD Tier 2 | Distribution | 2013-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014247 | 405388739 | High Sign | HFTD Tier 3 | Distribution | 2013-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014248 | 405388740 | Molding | HFTD Tier 3 | Distribution | 2013-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014249 | 405388756 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014250 | 405388778 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014251 | 405389023 | Molding | HFTD Tier 3 | Distribution | 2013-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014252 | 405385397 | Molding | HFTD Tier 3 | Distribution | 2013-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014253 | 405385402 | High Sign | HFTD Tier 3 | Distribution | 2013-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014254 | 405385828 | Guy | HFTD Tier 3 | Distribution | 2013-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014255 | 405386498 | Vis Strips | HFTD Tier 2 | Distribution | 2013-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014256 | 405386587 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014257 | 405388516 | Molding | HFTD Tier 2 | Distribution | 2013-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014258 | 405388826 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-07-25 | 41845 | 2 | Ignition Risk, no GO95 exception | [7 empty] | SCE | 2026 | 2
1120014259 | 405391664 | Guy | HFTD Tier 2 | Distribution | 2013-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014260 | 405388544 | Molding | HFTD Tier 2 | Distribution | 2013-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014261 | 405388565 | Guy | HFTD Tier 2 | Distribution | 2013-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014262 | 405388576 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014263 | 405389815 | Molding | HFTD Tier 3 | Distribution | 2013-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014264 | 405391017 | Molding | HFTD Tier 3 | Distribution | 2013-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014265 | 405391042 | Molding | HFTD Tier 3 | Distribution | 2013-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014266 | 405391667 | High Sign | HFTD Tier 2 | Distribution | 2013-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014267 | 405391690 | Molding | HFTD Tier 2 | Distribution | 2013-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014268 | 405391717 | High Sign | HFTD Tier 2 | Distribution | 2013-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014269 | 405394558 | Molding | HFTD Tier 2 | Distribution | 2013-07-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014270 | 405394766 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-07-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014271 | 405394785 | Molding | HFTD Tier 3 | Distribution | 2013-07-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014272 | 405400237 | High Sign | HFTD Tier 3 | Distribution | 2013-07-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014273 | 405397861 | Molding | HFTD Tier 3 | Distribution | 2013-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014274 | 405402023 | Molding | HFTD Tier 3 | Distribution | 2013-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014275 | 405401453 | High Sign | HFTD Tier 2 | Distribution | 2013-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014276 | 405401644 | Molding | HFTD Tier 3 | Distribution | 2013-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014277 | 405401875 | Molding | HFTD Tier 3 | Distribution | 2013-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014278 | 405401911 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014279 | 405402078 | High Sign | HFTD Tier 3 | Distribution | 2013-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014280 | 405402190 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014281 | 405404694 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2013-08-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014282 | 405404698 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2013-08-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014283 | 405406830 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-08-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014284 | 405408939 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-08-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014285 | 405405842 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-08-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014286 | 405406081 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-08-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014287 | 405407091 | High Sign | HFTD Tier 3 | Distribution | 2013-08-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014288 | 405407092 | High Sign | HFTD Tier 3 | Distribution | 2013-08-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014289 | 405409025 | ID Markings | HFTD Tier 3 | Distribution | 2013-08-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014290 | 405409067 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-08-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014291 | 405420319 | Guy | HFTD Tier 2 | Distribution | 2013-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014292 | 405420344 | Molding | HFTD Tier 2 | Distribution | 2013-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014293 | 405420346 | High Sign | HFTD Tier 2 | Distribution | 2013-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014294 | 405415826 | High Sign | HFTD Tier 3 | Distribution | 2013-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014295 | 405415829 | Guy | HFTD Tier 3 | Distribution | 2013-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014296 | 405415882 | Molding | HFTD Tier 3 | Distribution | 2013-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014297 | 405416292 | Molding | HFTD Tier 2 | Distribution | 2013-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014298 | 405416316 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014299 | 405420372 | Molding | HFTD Tier 2 | Distribution | 2013-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014300 | 405420381 | Molding | HFTD Tier 2 | Distribution | 2013-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014301 | 405420384 | Molding | HFTD Tier 2 | Distribution | 2013-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014302 | 405432792 | Molding | HFTD Tier 2 | Distribution | 2013-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014303 | 405432809 | Molding | HFTD Tier 2 | Distribution | 2013-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014304 | 405432824 | Molding | HFTD Tier 2 | Distribution | 2013-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014305 | 405432830 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014306 | 405420428 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014307 | 405420624 | Molding | HFTD Tier 2 | Distribution | 2013-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014308 | 405420626 | Guy | HFTD Tier 2 | Distribution | 2013-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014309 | 405420655 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2013-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014310 | 405420745 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014311 | 405432862 | High Sign | HFTD Tier 2 | Distribution | 2013-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014312 | 405432880 | Guy | HFTD Tier 2 | Distribution | 2013-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014313 | 405432895 | Molding | HFTD Tier 2 | Distribution | 2013-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014314 | 405432896 | Molding | HFTD Tier 2 | Distribution | 2013-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014315 | 405424729 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2013-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014316 | 405425043 | Molding | HFTD Tier 2 | Distribution | 2013-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014317 | 405425044 | High Sign | HFTD Tier 3 | Distribution | 2013-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014318 | 405425050 | Molding | HFTD Tier 2 | Distribution | 2013-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014319 | 405425052 | High Sign | HFTD Tier 2 | Distribution | 2013-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014320 | 405425055 | High Sign | HFTD Tier 3 | Distribution | 2013-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014321 | 405425059 | Molding | HFTD Tier 3 | Distribution | 2013-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014322 | 405425064 | Guy | HFTD Tier 2 | Distribution | 2013-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014323 | 405425065 | High Sign | HFTD Tier 3 | Distribution | 2013-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014324 | 405432014 | Molding | HFTD Tier 2 | Distribution | 2013-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014325 | 405432015 | Molding | HFTD Tier 2 | Distribution | 2013-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014326 | 405432016 | High Sign | HFTD Tier 2 | Distribution | 2013-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014327 | 405432034 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014328 | 405432036 | Molding | HFTD Tier 2 | Distribution | 2013-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014329 | 405432974 | Molding | HFTD Tier 2 | Distribution | 2013-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014330 | 405432976 | High Sign | HFTD Tier 2 | Distribution | 2013-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014331 | 405427173 | High Sign | HFTD Tier 2 | Distribution | 2013-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014332 | 405428357 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014333 | 405432064 | Molding | HFTD Tier 2 | Distribution | 2013-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014334 | 405432085 | Molding | HFTD Tier 2 | Distribution | 2013-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014335 | 405432947 | Guy | HFTD Tier 2 | Distribution | 2013-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014336 | 405430295 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014337 | 405431356 | Molding | HFTD Tier 3 | Distribution | 2013-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014338 | 405431366 | Molding | HFTD Tier 3 | Distribution | 2013-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014339 | 405431373 | Molding | HFTD Tier 3 | Distribution | 2013-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014340 | 405431562 | High Sign | HFTD Tier 3 | Distribution | 2013-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014341 | 405437562 | Molding | HFTD Tier 3 | Distribution | 2013-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014342 | 405437565 | Molding | HFTD Tier 3 | Distribution | 2013-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014343 | 405437574 | High Sign | HFTD Tier 3 | Distribution | 2013-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014344 | 405437585 | High Sign | HFTD Tier 3 | Distribution | 2013-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014345 | 405437586 | High Sign | HFTD Tier 3 | Distribution | 2013-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014346 | 405437664 | Molding | HFTD Tier 3 | Distribution | 2013-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014347 | 405438008 | High Sign | HFTD Tier 3 | Distribution | 2013-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014348 | 405438020 | Molding | HFTD Tier 3 | Distribution | 2013-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014349 | 405438026 | Molding | HFTD Tier 3 | Distribution | 2013-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014350 | 405438030 | High Sign | HFTD Tier 3 | Distribution | 2013-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014351 | 405441647 | High Sign | HFTD Tier 3 | Distribution | 2013-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014352 | 405441671 | Molding | HFTD Tier 3 | Distribution | 2013-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014353 | 405442968 | High Sign | HFTD Tier 3 | Distribution | 2013-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014354 | 405443213 | High Sign | HFTD Tier 3 | Distribution | 2013-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014355 | 405443218 | High Sign | HFTD Tier 3 | Distribution | 2013-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014356 | 405443230 | High Sign | HFTD Tier 3 | Distribution | 2013-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014357 | 405443233 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014358 | 405443238 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014359 | 405448347 | Molding | HFTD Tier 3 | Distribution | 2013-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014360 | 405448348 | Molding | HFTD Tier 3 | Distribution | 2013-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014361 | 405448351 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014362 | 405448449 | Guy | HFTD Tier 3 | Distribution | 2013-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014363 | 405448698 | Molding | HFTD Tier 3 | Distribution | 2013-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014364 | 405448712 | High Sign | HFTD Tier 3 | Distribution | 2013-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014365 | 405448724 | High Sign | HFTD Tier 3 | Distribution | 2013-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014366 | 405451576 | High Sign | HFTD Tier 2 | Distribution | 2013-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014367 | 405451586 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014368 | 405458383 | High Sign | HFTD Tier 3 | Distribution | 2013-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014369 | 405458399 | High Sign | HFTD Tier 3 | Distribution | 2013-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014370 | 405458400 | High Sign | HFTD Tier 3 | Distribution | 2013-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014371 | 405458415 | High Sign | HFTD Tier 3 | Distribution | 2013-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014372 | 405466438 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014373 | 405485027 | High Sign | HFTD Tier 3 | Distribution | 2013-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014374 | 405491506 | High Sign | HFTD Tier 3 | Distribution | 2013-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014375 | 405491512 | High Sign | HFTD Tier 3 | Distribution | 2013-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014376 | 405491513 | High Sign | HFTD Tier 3 | Distribution | 2013-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014377 | 405491718 | Molding | HFTD Tier 3 | Distribution | 2013-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014378 | 405491747 | Molding | HFTD Tier 3 | Distribution | 2013-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014379 | 405491770 | High Sign | HFTD Tier 3 | Distribution | 2013-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014380 | 405491825 | High Sign | HFTD Tier 3 | Distribution | 2013-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014381 | 405494641 | High Sign | HFTD Tier 3 | Distribution | 2013-08-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014382 | 405494806 | High Sign | HFTD Tier 3 | Distribution | 2013-08-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014383 | 405496592 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014384 | 405497586 | Molding | HFTD Tier 3 | Distribution | 2013-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014385 | 405497781 | Molding | HFTD Tier 3 | Distribution | 2013-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014386 | 405499960 | High Sign | HFTD Tier 3 | Distribution | 2013-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014387 | 405500279 | Bond | HFTD Tier 2 | Distribution | 2013-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014388 | 405500283 | Molding | HFTD Tier 2 | Distribution | 2013-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014389 | 405500368 | High Sign | HFTD Tier 3 | Distribution | 2013-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014390 | 405508812 | Molding | HFTD Tier 3 | Distribution | 2013-08-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014391 | 405508825 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-08-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014392 | 405509392 | Retaining Wall | HFTD Tier 2 | Transmission | 2013-08-29 | 42611 | 2 | [8 empty] | SCE | 2026 | 2
1120014393 | 405524604 | Molding | HFTD Tier 3 | Distribution | 2013-09-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014394 | 405537349 | Molding | HFTD Tier 2 | Distribution | 2013-09-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014395 | 405537360 | Guy | HFTD Tier 2 | Distribution | 2013-09-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014396 | 405537387 | Molding | HFTD Tier 2 | Distribution | 2013-09-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014397 | 405533073 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-09-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014398 | 405537453 | Molding | HFTD Tier 2 | Distribution | 2013-09-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014399 | 405537457 | High Sign | HFTD Tier 2 | Distribution | 2013-09-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014400 | 405537466 | Molding | HFTD Tier 2 | Distribution | 2013-09-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014401 | 405537473 | Molding | HFTD Tier 2 | Distribution | 2013-09-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014402 | 405537491 | High Sign | HFTD Tier 2 | Distribution | 2013-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014403 | 405537494 | Molding | HFTD Tier 2 | Distribution | 2013-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014404 | 405540205 | Molding | HFTD Tier 2 | Distribution | 2013-09-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014405 | 405550518 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-09-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014406 | 405551348 | High Sign | HFTD Tier 3 | Distribution | 2013-09-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014407 | 405551371 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014408 | 405557384 | High Sign | HFTD Tier 3 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014409 | 405557393 | High Sign | HFTD Tier 3 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014410 | 405557394 | High Sign | HFTD Tier 3 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014411 | 405557396 | High Sign | HFTD Tier 3 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014412 | 405557404 | High Sign | HFTD Tier 3 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014413 | 405557406 | High Sign | HFTD Tier 3 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014414 | 405557411 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014415 | 405557434 | High Sign | HFTD Tier 3 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014416 | 405557441 | High Sign | HFTD Tier 3 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014417 | 405557443 | High Sign | HFTD Tier 3 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014418 | 405557445 | High Sign | HFTD Tier 3 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014419 | 405557448 | High Sign | HFTD Tier 3 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014420 | 405557452 | Molding | HFTD Tier 3 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014421 | 405557463 | High Sign | HFTD Tier 3 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014422 | 405557464 | High Sign | HFTD Tier 3 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014423 | 405557472 | High Sign | HFTD Tier 3 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014424 | 405557739 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014425 | 405557762 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014426 | 405557770 | Molding | HFTD Tier 2 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014427 | 405557774 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014428 | 405557777 | High Sign | HFTD Tier 2 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014429 | 405557792 | High Sign | HFTD Tier 2 | Distribution | 2013-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014430 | 405564017 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-09-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014431 | 405564100 | Termination | HFTD Tier 2 | Distribution | 2013-09-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014432 | 405564133 | Molding | HFTD Tier 2 | Distribution | 2013-09-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014433 | 405564183 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-09-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014434 | 405565026 | Molding | HFTD Tier 3 | Distribution | 2013-09-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014435 | 405565034 | High Sign | HFTD Tier 3 | Distribution | 2013-09-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014436 | 405565036 | Molding | HFTD Tier 3 | Distribution | 2013-09-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014437 | 405565038 | High Sign | HFTD Tier 3 | Distribution | 2013-09-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014438 | 405566703 | High Sign | HFTD Tier 2 | Distribution | 2013-09-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014439 | 405567112 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-09-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014440 | 405568643 | Cable/Conductor | HFTD Tier 2 | Distribution | 2013-09-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014441 | 405573569 | Guy | HFTD Tier 2 | Distribution | 2013-09-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014442 | 405576645 | Molding | HFTD Tier 2 | Distribution | 2013-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014443 | 405576660 | Hardware/Framing | HFTD Tier 2 | Distribution | 2013-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014444 | 405576664 | Molding | HFTD Tier 2 | Distribution | 2013-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014445 | 405576669 | High Sign | HFTD Tier 2 | Distribution | 2013-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014446 | 405578688 | High Sign | HFTD Tier 3 | Distribution | 2013-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014447 | 405578690 | High Sign | HFTD Tier 3 | Distribution | 2013-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014448 | 405578960 | High Sign | HFTD Tier 2 | Distribution | 2013-09-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014449 | 405582739 | High Sign | HFTD Tier 3 | Distribution | 2013-09-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014450 | 405582755 | High Sign | HFTD Tier 3 | Distribution | 2013-09-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014451 | 405582756 | High Sign | HFTD Tier 3 | Distribution | 2013-09-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014452 | 405582769 | Bond | HFTD Tier 3 | Distribution | 2013-09-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014453 | 405582776 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-09-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014454 | 405582780 | High Sign | HFTD Tier 3 | Distribution | 2013-09-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014455 | 405582791 | High Sign | HFTD Tier 3 | Distribution | 2013-09-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014456 | 405584504 | High Sign | HFTD Tier 2 | Distribution | 2013-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014457 | 405588262 | High Sign | HFTD Tier 3 | Distribution | 2013-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014458 | 405588263 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014459 | 405590278 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014460 | 405595538 | High Sign | HFTD Tier 3 | Distribution | 2013-10-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014461 | 405595550 | High Sign | HFTD Tier 3 | Distribution | 2013-10-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014462 | 405599008 | Molding | HFTD Tier 3 | Distribution | 2013-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014463 | 405607287 | High Sign | HFTD Tier 3 | Distribution | 2013-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014464 | 405607298 | Molding | HFTD Tier 3 | Distribution | 2013-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014465 | 405611875 | High Sign | HFTD Tier 3 | Distribution | 2013-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014466 | 405617224 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-10-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014467 | 405618107 | High Sign | HFTD Tier 3 | Distribution | 2013-10-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014468 | 405618108 | High Sign | HFTD Tier 3 | Distribution | 2013-10-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014469 | 405618111 | High Sign | HFTD Tier 3 | Distribution | 2013-10-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014470 | 405618113 | High Sign | HFTD Tier 3 | Distribution | 2013-10-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014471 | 405618131 | High Sign | HFTD Tier 3 | Distribution | 2013-10-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014472 | 405618146 | High Sign | HFTD Tier 3 | Distribution | 2013-10-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014473 | 405618148 | High Sign | HFTD Tier 3 | Distribution | 2013-10-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014474 | 405618161 | High Sign | HFTD Tier 3 | Distribution | 2013-10-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014475 | 405620331 | High Sign | HFTD Tier 3 | Distribution | 2013-10-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014476 | 405620332 | High Sign | HFTD Tier 3 | Distribution | 2013-10-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014477 | 405623929 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-10-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014478 | 405623965 | High Sign | HFTD Tier 3 | Distribution | 2013-10-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014479 | 405625778 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-10-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014480 | 405630486 | Molding | HFTD Tier 3 | Distribution | 2013-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014481 | 405630492 | Molding | HFTD Tier 3 | Distribution | 2013-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014482 | 405630497 | Molding | HFTD Tier 3 | Distribution | 2013-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014483 | 405630499 | Bond | HFTD Tier 3 | Distribution | 2013-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014484 | 405630500 | Molding | HFTD Tier 3 | Distribution | 2013-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014485 | 405630842 | Molding | HFTD Tier 3 | Distribution | 2013-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014486 | 405630850 | Molding | HFTD Tier 3 | Distribution | 2013-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014487 | 405633161 | Molding | HFTD Tier 3 | Distribution | 2013-10-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014488 | 405639569 | High Sign | HFTD Tier 3 | Distribution | 2013-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014489 | 405639581 | Molding | HFTD Tier 3 | Distribution | 2013-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014490 | 405651199 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-10-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014491 | 405651207 | Molding | HFTD Tier 3 | Distribution | 2013-10-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014492 | 405655708 | High Sign | HFTD Tier 3 | Distribution | 2013-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014493 | 405655714 | High Sign | HFTD Tier 3 | Distribution | 2013-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014494 | 405655735 | High Sign | HFTD Tier 3 | Distribution | 2013-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014495 | 405655744 | High Sign | HFTD Tier 3 | Distribution | 2013-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014496 | 405655752 | High Sign | HFTD Tier 3 | Distribution | 2013-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014497 | 405658289 | High Sign | HFTD Tier 3 | Distribution | 2013-10-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014498 | 405658306 | High Sign | HFTD Tier 3 | Distribution | 2013-10-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014499 | 405658309 | Molding | HFTD Tier 3 | Distribution | 2013-10-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014500 | 405658311 | High Sign | HFTD Tier 3 | Distribution | 2013-10-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014501 | 405658318 | High Sign | HFTD Tier 3 | Distribution | 2013-10-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014502 | 405661195 | Molding | HFTD Tier 3 | Distribution | 2013-10-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014503 | 405661204 | Molding | HFTD Tier 3 | Distribution | 2013-10-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014504 | 405661220 | Molding | HFTD Tier 3 | Distribution | 2013-10-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014505 | 405661222 | Molding | HFTD Tier 3 | Distribution | 2013-10-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014506 | 405661225 | Molding | HFTD Tier 3 | Distribution | 2013-10-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014507 | 405661227 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-10-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014508 | 405661232 | Molding | HFTD Tier 3 | Distribution | 2013-10-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014509 | 405661235 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-10-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014510 | 405661237 | High Sign | HFTD Tier 3 | Distribution | 2013-10-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014511 | 405661241 | Molding | HFTD Tier 3 | Distribution | 2013-10-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014512 | 405661244 | Molding | HFTD Tier 3 | Distribution | 2013-10-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014513 | 405666191 | High Sign | HFTD Tier 3 | Distribution | 2013-11-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014514 | 405666192 | Molding | HFTD Tier 3 | Distribution | 2013-11-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014515 | 405666193 | High Sign | HFTD Tier 3 | Distribution | 2013-11-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014516 | 405666195 | Molding | HFTD Tier 3 | Distribution | 2013-11-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014517 | 405666201 | Molding | HFTD Tier 3 | Distribution | 2013-11-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014518 | 405666244 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-11-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014519 | 405670035 | High Sign | HFTD Tier 3 | Distribution | 2013-11-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014520 | 405670043 | Molding | HFTD Tier 3 | Distribution | 2013-11-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014521 | 405670047 | High Sign | HFTD Tier 3 | Distribution | 2013-11-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014522 | 405670071 | Molding | HFTD Tier 3 | Distribution | 2013-11-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014523 | 405670078 | High Sign | HFTD Tier 3 | Distribution | 2013-11-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014524 | 405674677 | High Sign | HFTD Tier 3 | Distribution | 2013-11-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014525 | 405674678 | High Sign | HFTD Tier 3 | Distribution | 2013-11-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014526 | 405674681 | High Sign | HFTD Tier 3 | Distribution | 2013-11-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014527 | 405674686 | High Sign | HFTD Tier 3 | Distribution | 2013-11-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014528 | 405674693 | High Sign | HFTD Tier 3 | Distribution | 2013-11-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014529 | 405674694 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-11-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014530 | 405674696 | Molding | HFTD Tier 3 | Distribution | 2013-11-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014531 | 405674704 | High Sign | HFTD Tier 3 | Distribution | 2013-11-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014532 | 405674716 | High Sign | HFTD Tier 3 | Distribution | 2013-11-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014533 | 405674718 | High Sign | HFTD Tier 3 | Distribution | 2013-11-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014534 | 405679093 | High Sign | HFTD Tier 3 | Distribution | 2013-11-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014535 | 405679098 | Molding | HFTD Tier 3 | Distribution | 2013-11-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014536 | 405679107 | High Sign | HFTD Tier 3 | Distribution | 2013-11-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014537 | 405679110 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-11-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014538 | 405679114 | Molding | HFTD Tier 3 | Distribution | 2013-11-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014539 | 405679119 | High Sign | HFTD Tier 3 | Distribution | 2013-11-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014540 | 405679127 | High Sign | HFTD Tier 3 | Distribution | 2013-11-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014541 | 405684435 | High Sign | HFTD Tier 3 | Distribution | 2013-11-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014542 | 405684437 | High Sign | HFTD Tier 3 | Distribution | 2013-11-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014543 | 405684448 | High Sign | HFTD Tier 3 | Distribution | 2013-11-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014544 | 405684450 | High Sign | HFTD Tier 3 | Distribution | 2013-11-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014545 | 405684451 | High Sign | HFTD Tier 3 | Distribution | 2013-11-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014546 | 405684461 | High Sign | HFTD Tier 3 | Distribution | 2013-11-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014547 | 405691039 | Guy | HFTD Tier 3 | Distribution | 2013-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014548 | 405691050 | Molding | HFTD Tier 3 | Distribution | 2013-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014549 | 405691059 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014550 | 405690908 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014551 | 405690912 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014552 | 405690921 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014553 | 405690931 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014554 | 405691451 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014555 | 405693467 | High Sign | HFTD Tier 3 | Distribution | 2013-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014556 | 405693472 | High Sign | HFTD Tier 3 | Distribution | 2013-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014557 | 405693491 | High Sign | HFTD Tier 3 | Distribution | 2013-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014558 | 405693494 | Molding | HFTD Tier 3 | Distribution | 2013-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014559 | 405693495 | Molding | HFTD Tier 3 | Distribution | 2013-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014560 | 405693512 | High Sign | HFTD Tier 3 | Distribution | 2013-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014561 | 405700703 | High Sign | HFTD Tier 3 | Distribution | 2013-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014562 | 405700713 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014563 | 405700738 | Molding | HFTD Tier 3 | Distribution | 2013-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014564 | 405706592 | Molding | HFTD Tier 3 | Distribution | 2013-11-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014565 | 405706597 | Riser/Conduit | HFTD Tier 3 | Distribution | 2013-11-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014566 | 405706599 | Molding | HFTD Tier 3 | Distribution | 2013-11-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014567 | 405706602 | Molding | HFTD Tier 3 | Distribution | 2013-11-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014568 | 405711638 | Molding | HFTD Tier 3 | Distribution | 2013-11-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014569 | 405711647 | Molding | HFTD Tier 3 | Distribution | 2013-11-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014570 | 415054938 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2013-12-03 | 41971 | 2 | Ignition Risk, no GO95 exception | [7 empty] | SCE | 2026 | 2
1120014571 | 405736786 | Riser/Conduit | HFTD Tier 2 | Distribution | 2013-12-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014572 | 405753375 | Guy | HFTD Tier 3 | Distribution | 2013-12-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014573 | 405754296 | Hardware/Framing | HFTD Tier 3 | Distribution | 2013-12-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014574 | 405759284 | Cable/Conductor | HFTD Tier 3 | Distribution | 2013-12-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014575 | 405777343 | High Sign | HFTD Tier 3 | Distribution | 2014-01-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014576 | 405779059 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-01-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014577 | 405782259 | Molding | HFTD Tier 3 | Distribution | 2014-01-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014578 | 405782265 | Molding | HFTD Tier 3 | Distribution | 2014-01-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014579 | 405782272 | High Sign | HFTD Tier 3 | Distribution | 2014-01-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014580 | 405787898 | High Sign | HFTD Tier 3 | Distribution | 2014-01-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014581 | 405780624 | High Sign | HFTD Tier 3 | Distribution | 2014-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014582 | 405780627 | High Sign | HFTD Tier 3 | Distribution | 2014-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014583 | 405780819 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014584 | 405780839 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014585 | 405780855 | High Sign | HFTD Tier 3 | Distribution | 2014-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014586 | 405780866 | High Sign | HFTD Tier 3 | Distribution | 2014-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014587 | 405780985 | Molding | HFTD Tier 2 | Distribution | 2014-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014588 | 405780986 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014589 | 405781690 | Molding | HFTD Tier 3 | Distribution | 2014-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014590 | 405781710 | Molding | HFTD Tier 3 | Distribution | 2014-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014591 | 405781711 | Riser/Conduit | HFTD Tier 3 | Distribution | 2014-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014592 | 405781775 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014593 | 405781778 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014594 | 405782143 | High Sign | HFTD Tier 3 | Distribution | 2014-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014595 | 405782276 | High Sign | HFTD Tier 3 | Distribution | 2014-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014596 | 405787899 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014597 | 405784006 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014598 | 405784686 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014599 | 405784703 | High Sign | HFTD Tier 3 | Distribution | 2014-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014600 | 405784705 | High Sign | HFTD Tier 3 | Distribution | 2014-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014601 | 405785033 | High Sign | HFTD Tier 2 | Distribution | 2014-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014602 | 405785090 | Molding | HFTD Tier 3 | Distribution | 2014-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014603 | 405785204 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014604 | 405787962 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014605 | 405785990 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014606 | 405786003 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014607 | 405786004 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014608 | 405786411 | Guy | HFTD Tier 3 | Distribution | 2014-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014609 | 405786443 | Guy | HFTD Tier 3 | Distribution | 2014-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014610 | 405786574 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014611 | 405786579 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014612 | 405786591 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014613 | 405787466 | High Sign | HFTD Tier 3 | Distribution | 2014-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014614 | 405787659 | High Sign | HFTD Tier 3 | Distribution | 2014-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014615 | 405788987 | Molding | HFTD Tier 2 | Distribution | 2014-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014616 | 405789033 | High Sign | HFTD Tier 2 | Distribution | 2014-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014617 | 405789042 | Molding | HFTD Tier 2 | Distribution | 2014-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014618 | 405789714 | High Sign | HFTD Tier 2 | Distribution | 2014-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014619 | 405789716 | High Sign | HFTD Tier 2 | Distribution | 2014-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014620 | 405789737 | High Sign | HFTD Tier 2 | Distribution | 2014-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014621 | 405789746 | Molding | HFTD Tier 2 | Distribution | 2014-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014622 | 405791534 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014623 | 405791736 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014624 | 405792350 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014625 | 405792570 | High Sign | HFTD Tier 3 | Distribution | 2014-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014626 | 405792572 | High Sign | HFTD Tier 3 | Distribution | 2014-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014627 | 405792904 | Molding | HFTD Tier 3 | Distribution | 2014-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014628 | 405792915 | Riser/Conduit | HFTD Tier 3 | Distribution | 2014-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014629 | 405792921 | Molding | HFTD Tier 3 | Distribution | 2014-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014630 | 405792928 | Molding | HFTD Tier 3 | Distribution | 2014-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014631 | 405792937 | High Sign | HFTD Tier 3 | Distribution | 2014-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014632 | 405792943 | High Sign | HFTD Tier 3 | Distribution | 2014-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014633 | 405794034 | Riser/Conduit | HFTD Tier 2 | Distribution | 2014-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014634 | 405794368 | Guy | HFTD Tier 2 | Distribution | 2014-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014635 | 405795919 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014636 | 405802353 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014637 | 405797179 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014638 | 405797520 | Guy | HFTD Tier 2 | Distribution | 2014-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014639 | 405797534 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014640 | 405797560 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014641 | 405798157 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014642 | 405798861 | Guy | HFTD Tier 3 | Distribution | 2014-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014643 | 405799142 | Molding | HFTD Tier 3 | Distribution | 2014-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014644 | 405799159 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014645 | 405802422 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014646 | 405800226 | Guy | HFTD Tier 2 | Distribution | 2014-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014647 | 405800278 | Molding | HFTD Tier 2 | Distribution | 2014-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014648 | 405801113 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014649 | 405801605 | Molding | HFTD Tier 3 | Distribution | 2014-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014650 | 405804633 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014651 | 405804635 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014652 | 405804642 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014653 | 405802620 | Guy | HFTD Tier 2 | Distribution | 2014-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014654 | 405802623 | Molding | HFTD Tier 2 | Distribution | 2014-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014655 | 405803346 | Vis Strips | HFTD Tier 2 | Distribution | 2014-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014656 | 405803777 | Guy | HFTD Tier 3 | Distribution | 2014-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014657 | 405803787 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014658 | 405805635 | High Sign | HFTD Tier 3 | Distribution | 2014-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014659 | 405805843 | Ground | HFTD Tier 2 | Distribution | 2014-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014660 | 405807511 | High Sign | HFTD Tier 2 | Distribution | 2014-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014661 | 405807537 | Molding | HFTD Tier 2 | Distribution | 2014-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014662 | 405807551 | High Sign | HFTD Tier 2 | Distribution | 2014-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014663 | 405807839 | Molding | HFTD Tier 3 | Distribution | 2014-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014664 | 405808514 | Molding | HFTD Tier 2 | Distribution | 2014-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014665 | 405808527 | High Sign | HFTD Tier 2 | Distribution | 2014-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014666 | 405808528 | Molding | HFTD Tier 2 | Distribution | 2014-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014667 | 405808532 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014668 | 405809094 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014669 | 405810602 | Molding | HFTD Tier 2 | Distribution | 2014-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014670 | 405810609 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014671 | 405810620 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014672 | 405810623 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014673 | 405810625 | Riser/Conduit | HFTD Tier 3 | Distribution | 2014-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014674 | 405810702 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014675 | 405810704 | Guy | HFTD Tier 3 | Distribution | 2014-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014676 | 405810714 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014677 | 405810724 | Molding | HFTD Tier 3 | Distribution | 2014-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014678 | 405815029 | Molding | HFTD Tier 3 | Distribution | 2014-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014679 | 405815033 | High Sign | HFTD Tier 3 | Distribution | 2014-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014680 | 405815035 | High Sign | HFTD Tier 3 | Distribution | 2014-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014681 | 405815036 | Molding | HFTD Tier 3 | Distribution | 2014-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014682 | 405815052 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014683 | 405815076 | High Sign | HFTD Tier 3 | Distribution | 2014-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014684 | 405818866 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014685 | 405812563 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014686 | 405812719 | High Sign | HFTD Tier 2 | Distribution | 2014-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014687 | 405813068 | Molding | HFTD Tier 3 | Distribution | 2014-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014688 | 405813074 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014689 | 405814668 | Molding | HFTD Tier 2 | Distribution | 2014-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014690 | 405814748 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014691 | 405815080 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014692 | 405815434 | High Sign | HFTD Tier 2 | Distribution | 2014-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014693 | 405815443 | High Sign | HFTD Tier 2 | Distribution | 2014-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014694 | 405818889 | Molding | HFTD Tier 3 | Distribution | 2014-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014695 | 405815447 | High Sign | HFTD Tier 2 | Distribution | 2014-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014696 | 405815463 | Molding | HFTD Tier 2 | Distribution | 2014-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014697 | 405816199 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014698 | 405816265 | High Sign | HFTD Tier 3 | Distribution | 2014-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014699 | 405816330 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014700 | 405817900 | Molding | HFTD Tier 3 | Distribution | 2014-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014701 | 405821656 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014702 | 405821701 | Molding | HFTD Tier 3 | Distribution | 2014-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014703 | 405821719 | Molding | HFTD Tier 3 | Distribution | 2014-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014704 | 405819800 | High Sign | HFTD Tier 3 | Distribution | 2014-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014705 | 405819812 | Molding | HFTD Tier 3 | Distribution | 2014-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014706 | 405819814 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014707 | 405819845 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014708 | 405819850 | Riser/Conduit | HFTD Tier 3 | Distribution | 2014-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014709 | 405819851 | Guy | HFTD Tier 3 | Distribution | 2014-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014710 | 405819994 | High Sign | HFTD Tier 2 | Distribution | 2014-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014711 | 405820018 | High Sign | HFTD Tier 2 | Distribution | 2014-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014712 | 405820032 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014713 | 405820033 | High Sign | HFTD Tier 2 | Distribution | 2014-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014714 | 405820042 | High Sign | HFTD Tier 2 | Distribution | 2014-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014715 | 405820044 | High Sign | HFTD Tier 2 | Distribution | 2014-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014716 | 405823138 | Molding | HFTD Tier 3 | Distribution | 2014-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014717 | 405823144 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014718 | 405823148 | High Sign | HFTD Tier 3 | Distribution | 2014-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014719 | 405823153 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014720 | 405823372 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014721 | 405825165 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014722 | 405826228 | Riser/Conduit | HFTD Tier 3 | Distribution | 2014-01-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014723 | 405826235 | Guy | HFTD Tier 2 | Distribution | 2014-01-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014724 | 405826248 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-01-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014725 | 405826256 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-01-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014726 | 405832871 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-01-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014727 | 405830491 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014728 | 405832310 | High Sign | HFTD Tier 3 | Distribution | 2014-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014729 | 405832503 | High Sign | HFTD Tier 3 | Distribution | 2014-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014730 | 405832508 | Molding | HFTD Tier 3 | Distribution | 2014-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014731 | 405832512 | Molding | HFTD Tier 3 | Distribution | 2014-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014732 | 405832516 | High Sign | HFTD Tier 3 | Distribution | 2014-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014733 | 405832527 | Ground | HFTD Tier 3 | Distribution | 2014-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014734 | 405832918 | High Sign | HFTD Tier 3 | Distribution | 2014-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014735 | 405832922 | Riser/Conduit | HFTD Tier 3 | Distribution | 2014-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014736 | 405832962 | High Sign | HFTD Tier 3 | Distribution | 2014-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014737 | 405839453 | Guy | HFTD Tier 3 | Distribution | 2014-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014738 | 405834386 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014739 | 405834403 | Guy | HFTD Tier 3 | Distribution | 2014-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014740 | 405835745 | Molding | HFTD Tier 3 | Distribution | 2014-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014741 | 405837351 | Molding | HFTD Tier 2 | Distribution | 2014-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014742 | 405837375 | Molding | HFTD Tier 2 | Distribution | 2014-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014743 | 405839544 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014744 | 405840547 | High Sign | HFTD Tier 2 | Distribution | 2014-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014745 | 405840560 | High Sign | HFTD Tier 2 | Distribution | 2014-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014746 | 405840624 | High Sign | HFTD Tier 3 | Distribution | 2014-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014747 | 405843759 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014748 | 405843791 | Molding | HFTD Tier 3 | Distribution | 2014-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014749 | 405844072 | Guy | HFTD Tier 2 | Distribution | 2014-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014750 | 405844075 | High Sign | HFTD Tier 3 | Distribution | 2014-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014751 | 405844080 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014752 | 405844093 | High Sign | HFTD Tier 2 | Distribution | 2014-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014753 | 405844369 | High Sign | HFTD Tier 2 | Distribution | 2014-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014754 | 405844384 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014755 | 405844386 | Molding | HFTD Tier 2 | Distribution | 2014-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014756 | 405846209 | Molding | HFTD Tier 3 | Distribution | 2014-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014757 | 405846260 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014758 | 405854666 | High Sign | HFTD Tier 3 | Distribution | 2014-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014759 | 405854710 | High Sign | HFTD Tier 3 | Distribution | 2014-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014760 | 405854724 | High Sign | HFTD Tier 3 | Distribution | 2014-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014761 | 405848517 | High Sign | HFTD Tier 2 | Distribution | 2014-02-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014762 | 405854713 | Guy | HFTD Tier 3 | Distribution | 2014-02-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014763 | 405854734 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-02-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014764 | 405854736 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-02-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014765 | 405854740 | Guy | HFTD Tier 3 | Distribution | 2014-02-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014766 | 405855231 | Molding | HFTD Tier 2 | Distribution | 2014-02-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014767 | 405852069 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014768 | 405855238 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014769 | 405855246 | Molding | HFTD Tier 2 | Distribution | 2014-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014770 | 405858784 | High Sign | HFTD Tier 2 | Distribution | 2014-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014771 | 405858792 | High Sign | HFTD Tier 2 | Distribution | 2014-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014772 | 405860868 | Guy | HFTD Tier 3 | Distribution | 2014-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014773 | 405860887 | High Sign | HFTD Tier 3 | Distribution | 2014-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014774 | 405862886 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014775 | 405862892 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014776 | 405864562 | Molding | HFTD Tier 3 | Distribution | 2014-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014777 | 405872663 | High Sign | HFTD Tier 3 | Distribution | 2014-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014778 | 405868702 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014779 | 405868718 | High Sign | HFTD Tier 3 | Distribution | 2014-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014780 | 405872688 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014781 | 405870170 | High Sign | HFTD Tier 2 | Distribution | 2014-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014782 | 405870173 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014783 | 405872714 | High Sign | HFTD Tier 3 | Distribution | 2014-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014784 | 405872742 | High Sign | HFTD Tier 3 | Distribution | 2014-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014785 | 405875157 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014786 | 405874022 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014787 | 405874277 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014788 | 405874286 | Molding | HFTD Tier 2 | Distribution | 2014-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014789 | 405874287 | Molding | HFTD Tier 2 | Distribution | 2014-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014790 | 405874694 | Molding | HFTD Tier 2 | Distribution | 2014-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014791 | 405874752 | Guy | HFTD Tier 3 | Distribution | 2014-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014792 | 405874762 | Guy | HFTD Tier 3 | Distribution | 2014-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014793 | 405874764 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014794 | 405874827 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014795 | 405874835 | Molding | HFTD Tier 2 | Distribution | 2014-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014796 | 405874840 | Guy | HFTD Tier 2 | Distribution | 2014-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014797 | 405874895 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014798 | 405874905 | Guy | HFTD Tier 2 | Distribution | 2014-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014799 | 405876484 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-02-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014800 | 405876554 | High Sign | HFTD Tier 3 | Distribution | 2014-02-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014801 | 405876780 | Molding | HFTD Tier 3 | Distribution | 2014-02-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014802 | 405876789 | High Sign | HFTD Tier 3 | Distribution | 2014-02-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014803 | 405879245 | Guy | HFTD Tier 3 | Distribution | 2014-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014804 | 405880277 | Guy | HFTD Tier 3 | Distribution | 2014-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014805 | 413834619 | Molding | HFTD Tier 3 | Distribution | 2014-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014806 | 413834620 | High Sign | HFTD Tier 3 | Distribution | 2014-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014807 | 405884967 | High Sign | HFTD Tier 3 | Distribution | 2014-02-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014808 | 405885107 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-02-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014809 | 405885110 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-02-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014810 | 405886470 | High Sign | HFTD Tier 3 | Distribution | 2014-02-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014811 | 405886491 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-02-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014812 | 405893972 | High Sign | HFTD Tier 3 | Distribution | 2014-02-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014813 | 405893989 | Molding | HFTD Tier 3 | Distribution | 2014-02-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014814 | 405893991 | High Sign | HFTD Tier 3 | Distribution | 2014-02-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014815 | 405886779 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014816 | 405886783 | Molding | HFTD Tier 2 | Distribution | 2014-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014817 | 405887023 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014818 | 405887048 | High Sign | HFTD Tier 3 | Distribution | 2014-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014819 | 405888344 | Molding | HFTD Tier 2 | Distribution | 2014-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014820 | 405889802 | High Sign | HFTD Tier 3 | Distribution | 2014-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014821 | 405889811 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014822 | 405891452 | Riser/Conduit | HFTD Tier 2 | Distribution | 2014-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014823 | 405893161 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014824 | 405893163 | High Sign | HFTD Tier 3 | Distribution | 2014-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014825 | 405893165 | High Sign | HFTD Tier 3 | Distribution | 2014-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014826 | 405893938 | Guy | HFTD Tier 3 | Distribution | 2014-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014827 | 405893939 | Guy | HFTD Tier 3 | Distribution | 2014-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014828 | 405893947 | Molding | HFTD Tier 3 | Distribution | 2014-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014829 | 405894074 | Molding | HFTD Tier 3 | Distribution | 2014-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014830 | 405894177 | Molding | HFTD Tier 3 | Distribution | 2014-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014831 | 405904647 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014832 | 405901408 | Guy | HFTD Tier 3 | Distribution | 2014-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014833 | 405904659 | High Sign | HFTD Tier 3 | Distribution | 2014-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014834 | 405904661 | Riser/Conduit | HFTD Tier 3 | Distribution | 2014-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014835 | 405901244 | Molding | HFTD Tier 2 | Distribution | 2014-02-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014836 | 405901246 | Molding | HFTD Tier 2 | Distribution | 2014-02-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014837 | 405901405 | Molding | HFTD Tier 2 | Distribution | 2014-02-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014838 | 405901411 | High Sign | HFTD Tier 2 | Distribution | 2014-02-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014839 | 405904695 | Guy | HFTD Tier 3 | Distribution | 2014-02-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014840 | 405904744 | High Sign | HFTD Tier 3 | Distribution | 2014-02-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014841 | 405906801 | Guy | HFTD Tier 3 | Distribution | 2014-02-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014842 | 405906806 | High Sign | HFTD Tier 3 | Distribution | 2014-02-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014843 | 405908095 | Molding | HFTD Tier 2 | Distribution | 2014-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014844 | 405908141 | Molding | HFTD Tier 2 | Distribution | 2014-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014845 | 405909185 | Guy | HFTD Tier 2 | Distribution | 2014-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014846 | 405909193 | Guy | HFTD Tier 2 | Distribution | 2014-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014847 | 405910961 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014848 | 405917016 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014849 | 405917019 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014850 | 405917036 | Molding | HFTD Tier 3 | Distribution | 2014-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014851 | 405917039 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014852 | 405917040 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014853 | 405917073 | Riser/Conduit | HFTD Tier 3 | Distribution | 2014-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014854 | 405917081 | Guy | HFTD Tier 3 | Distribution | 2014-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014855 | 405917117 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014856 | 405917123 | Molding | HFTD Tier 3 | Distribution | 2014-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014857 | 405922011 | Riser/Conduit | HFTD Tier 2 | Distribution | 2014-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014858 | 405922063 | High Sign | HFTD Tier 2 | Distribution | 2014-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014859 | 405922532 | Molding | HFTD Tier 2 | Distribution | 2014-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014860 | 405922555 | High Sign | HFTD Tier 2 | Distribution | 2014-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014861 | 405924930 | Molding | HFTD Tier 2 | Distribution | 2014-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014862 | 405924941 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014863 | 405928367 | Guy | HFTD Tier 3 | Distribution | 2014-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014864 | 405928393 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014865 | 405928400 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014866 | 405928402 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014867 | 405928410 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014868 | 405928413 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014869 | 405928420 | Molding | HFTD Tier 3 | Distribution | 2014-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014870 | 405928424 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014871 | 405928433 | High Sign | HFTD Tier 3 | Distribution | 2014-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014872 | 405928795 | High Sign | HFTD Tier 2 | Distribution | 2014-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014873 | 405932435 | High Sign | HFTD Tier 3 | Distribution | 2014-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014874 | 405932677 | Molding | HFTD Tier 2 | Distribution | 2014-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014875 | 405932690 | High Sign | HFTD Tier 2 | Distribution | 2014-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014876 | 405932704 | High Sign | HFTD Tier 2 | Distribution | 2014-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014877 | 405932882 | High Sign | HFTD Tier 2 | Distribution | 2014-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014878 | 405936252 | High Sign | HFTD Tier 3 | Distribution | 2014-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014879 | 405936253 | Guy | HFTD Tier 3 | Distribution | 2014-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014880 | 405936256 | Molding | HFTD Tier 3 | Distribution | 2014-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014881 | 405936264 | Guy | HFTD Tier 3 | Distribution | 2014-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014882 | 405936268 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014883 | 405936274 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014884 | 405936298 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014885 | 405936306 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014886 | 405936331 | Termination | HFTD Tier 3 | Distribution | 2014-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014887 | 405949012 | Guy | HFTD Tier 2 | Distribution | 2014-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014888 | 405934116 | High Sign | HFTD Tier 2 | Distribution | 2014-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014889 | 405936346 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014890 | 405936360 | Molding | HFTD Tier 3 | Distribution | 2014-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014891 | 405936366 | Guy | HFTD Tier 3 | Distribution | 2014-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014892 | 405936370 | Molding | HFTD Tier 3 | Distribution | 2014-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014893 | 405936372 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014894 | 405936374 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014895 | 405936379 | High Sign | HFTD Tier 3 | Distribution | 2014-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014896 | 405936800 | High Sign | HFTD Tier 2 | Distribution | 2014-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014897 | 405938265 | Molding | HFTD Tier 2 | Distribution | 2014-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014898 | 405938316 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014899 | 405939565 | High Sign | HFTD Tier 3 | Distribution | 2014-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014900 | 405939567 | High Sign | HFTD Tier 3 | Distribution | 2014-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014901 | 405939999 | Molding | HFTD Tier 2 | Distribution | 2014-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014902 | 405940289 | Molding | HFTD Tier 3 | Distribution | 2014-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014903 | 405940308 | High Sign | HFTD Tier 3 | Distribution | 2014-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014904 | 405940329 | Molding | HFTD Tier 3 | Distribution | 2014-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014905 | 405941716 | Molding | HFTD Tier 3 | Distribution | 2014-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014906 | 405944360 | Molding | HFTD Tier 3 | Distribution | 2014-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014907 | 405944363 | Riser/Conduit | HFTD Tier 3 | Distribution | 2014-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014908 | 405944364 | Molding | HFTD Tier 3 | Distribution | 2014-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014909 | 405949153 | Guy | HFTD Tier 2 | Distribution | 2014-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014910 | 413873252 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014911 | 405944475 | Right of Way | HFTD Tier 2 | Transmission | 2014-03-16 | 42079 | 2 | Ignition Risk, no GO95 exception | [7 empty] | SCE | 2026 | 2
1120014912 | 405946037 | Guy | HFTD Tier 3 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014913 | 405946041 | Molding | HFTD Tier 3 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014914 | 405946045 | Molding | HFTD Tier 3 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014915 | 405946046 | High Sign | HFTD Tier 3 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014916 | 405946053 | Molding | HFTD Tier 3 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014917 | 405946062 | High Sign | HFTD Tier 3 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014918 | 405946072 | Molding | HFTD Tier 3 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014919 | 405946545 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014920 | 405946565 | High Sign | HFTD Tier 2 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014921 | 405946568 | High Sign | HFTD Tier 2 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014922 | 405946572 | High Sign | HFTD Tier 2 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014923 | 405946577 | High Sign | HFTD Tier 2 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014924 | 405948623 | High Sign | HFTD Tier 2 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014925 | 405949203 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014926 | 405952202 | Molding | HFTD Tier 3 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014927 | 405952205 | Molding | HFTD Tier 3 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014928 | 405952206 | Molding | HFTD Tier 3 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014929 | 405952213 | High Sign | HFTD Tier 3 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014930 | 405952221 | High Sign | HFTD Tier 3 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014931 | 405952224 | Molding | HFTD Tier 3 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014932 | 405952233 | High Sign | HFTD Tier 3 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014933 | 405952236 | High Sign | HFTD Tier 3 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014934 | 405952241 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014935 | 405952243 | High Sign | HFTD Tier 3 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014936 | 405952252 | Molding | HFTD Tier 3 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014937 | 405952256 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014938 | 405952263 | ID Markings | HFTD Tier 3 | Distribution | 2014-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014939 | 405950418 | High Sign | HFTD Tier 2 | Distribution | 2014-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014940 | 405952302 | High Sign | HFTD Tier 3 | Distribution | 2014-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014941 | 405952326 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014942 | 405959990 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014943 | 405960007 | Molding | HFTD Tier 3 | Distribution | 2014-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014944 | 405960037 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014945 | 405960484 | Molding | HFTD Tier 2 | Distribution | 2014-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014946 | 405960487 | Molding | HFTD Tier 2 | Distribution | 2014-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014947 | 405961466 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014948 | 405961471 | High Sign | HFTD Tier 2 | Distribution | 2014-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014949 | 405960114 | Molding | HFTD Tier 3 | Distribution | 2014-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014950 | 405960117 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014951 | 405962236 | Molding | HFTD Tier 3 | Distribution | 2014-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014952 | 405964328 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014953 | 405964340 | Molding | HFTD Tier 2 | Distribution | 2014-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014954 | 405965737 | Molding | HFTD Tier 3 | Distribution | 2014-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014955 | 405967133 | Molding | HFTD Tier 3 | Distribution | 2014-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014956 | 405967190 | High Sign | HFTD Tier 3 | Distribution | 2014-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014957 | 405973110 | Molding | HFTD Tier 2 | Distribution | 2014-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014958 | 405977109 | Molding | HFTD Tier 3 | Distribution | 2014-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014959 | 405978627 | Molding | HFTD Tier 3 | Distribution | 2014-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014960 | 405978860 | High Sign | HFTD Tier 2 | Distribution | 2014-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014961 | 405979067 | High Sign | HFTD Tier 3 | Distribution | 2014-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014962 | 405982131 | High Sign | HFTD Tier 3 | Distribution | 2014-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014963 | 405982134 | High Sign | HFTD Tier 3 | Distribution | 2014-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014964 | 405982166 | High Sign | HFTD Tier 3 | Distribution | 2014-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014965 | 405983437 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2014-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014966 | 405983451 | High Sign | HFTD Tier 2 | Distribution | 2014-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014967 | 405985342 | Guy | HFTD Tier 3 | Distribution | 2014-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014968 | 405985948 | Molding | HFTD Tier 3 | Distribution | 2014-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014969 | 405985987 | Molding | HFTD Tier 3 | Distribution | 2014-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014970 | 405986957 | High Sign | HFTD Tier 3 | Distribution | 2014-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014971 | 405986210 | High Sign | HFTD Tier 2 | Distribution | 2014-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014972 | 405986824 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014973 | 405986844 | Molding | HFTD Tier 2 | Distribution | 2014-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014974 | 405987225 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014975 | 405989020 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014976 | 405989030 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014977 | 405989204 | High Sign | HFTD Tier 2 | Distribution | 2014-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014978 | 405989245 | Molding | HFTD Tier 2 | Distribution | 2014-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014979 | 405996502 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014980 | 405996557 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014981 | 405996571 | Molding | HFTD Tier 3 | Distribution | 2014-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014982 | 405996620 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-04-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014983 | 405996640 | High Sign | HFTD Tier 3 | Distribution | 2014-04-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014984 | 405996656 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-04-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014985 | 405996673 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-04-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014986 | 405999237 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014987 | 405999624 | Molding | HFTD Tier 2 | Distribution | 2014-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014988 | 405999630 | Molding | HFTD Tier 2 | Distribution | 2014-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014989 | 405999631 | Molding | HFTD Tier 2 | Distribution | 2014-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014990 | 405999697 | High Sign | HFTD Tier 2 | Distribution | 2014-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014991 | 405999706 | Molding | HFTD Tier 2 | Distribution | 2014-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014992 | 405999716 | High Sign | HFTD Tier 2 | Distribution | 2014-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014993 | 406004198 | High Sign | HFTD Tier 3 | Distribution | 2014-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014994 | 406002788 | High Sign | HFTD Tier 2 | Distribution | 2014-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014995 | 406005795 | High Sign | HFTD Tier 2 | Distribution | 2014-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014996 | 406007458 | Molding | HFTD Tier 3 | Distribution | 2014-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014997 | 406007459 | Ground | HFTD Tier 3 | Distribution | 2014-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014998 | 406007467 | Molding | HFTD Tier 3 | Distribution | 2014-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120014999 | 406007998 | High Sign | HFTD Tier 3 | Distribution | 2014-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015000 | 406007999 | Molding | HFTD Tier 3 | Distribution | 2014-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015001 | 406008002 | Molding | HFTD Tier 3 | Distribution | 2014-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015002 | 406008005 | High Sign | HFTD Tier 3 | Distribution | 2014-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015003 | 406011474 | Molding | HFTD Tier 3 | Distribution | 2014-04-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015004 | 406012802 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015005 | 406013043 | High Sign | HFTD Tier 2 | Distribution | 2014-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015006 | 406013051 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015007 | 406013065 | High Sign | HFTD Tier 2 | Distribution | 2014-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015008 | 406013069 | Molding | HFTD Tier 2 | Distribution | 2014-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015009 | 406013072 | Molding | HFTD Tier 2 | Distribution | 2014-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015010 | 406013075 | High Sign | HFTD Tier 2 | Distribution | 2014-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015011 | 406013082 | High Sign | HFTD Tier 2 | Distribution | 2014-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015012 | 406014887 | Molding | HFTD Tier 3 | Distribution | 2014-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015013 | 406015623 | High Sign | HFTD Tier 3 | Distribution | 2014-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015014 | 406018425 | Molding | HFTD Tier 3 | Distribution | 2014-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015015 | 406018805 | High Sign | HFTD Tier 2 | Distribution | 2014-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015016 | 406018816 | Molding | HFTD Tier 2 | Distribution | 2014-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015017 | 406020115 | Molding | HFTD Tier 3 | Distribution | 2014-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015018 | 406021335 | Molding | HFTD Tier 3 | Distribution | 2014-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015019 | 406021336 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015020 | 406021346 | Molding | HFTD Tier 3 | Distribution | 2014-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015021 | 406023836 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015022 | 406023842 | Bond | HFTD Tier 2 | Distribution | 2014-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015023 | 406023845 | Guy | HFTD Tier 2 | Distribution | 2014-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015024 | 406024205 | High Sign | HFTD Tier 2 | Distribution | 2014-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015025 | 406025456 | Guy | HFTD Tier 3 | Distribution | 2014-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015026 | 406025480 | High Sign | HFTD Tier 3 | Distribution | 2014-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015027 | 406025696 | Guy | HFTD Tier 3 | Distribution | 2014-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015028 | 406025709 | High Sign | HFTD Tier 3 | Distribution | 2014-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015029 | 406029824 | Molding | HFTD Tier 2 | Distribution | 2014-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015030 | 406027537 | High Sign | HFTD Tier 2 | Distribution | 2014-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015031 | 406027594 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015032 | 406027597 | Molding | HFTD Tier 2 | Distribution | 2014-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015033 | 406027606 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015034 | 406028409 | High Sign | HFTD Tier 3 | Distribution | 2014-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015035 | 406029439 | Molding | HFTD Tier 3 | Distribution | 2014-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015036 | 406031639 | Molding | HFTD Tier 2 | Distribution | 2014-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015037 | 406031650 | Riser/Conduit | HFTD Tier 2 | Distribution | 2014-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015038 | 406031656 | High Sign | HFTD Tier 2 | Distribution | 2014-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015039 | 406031711 | High Sign | HFTD Tier 2 | Distribution | 2014-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015040 | 406035976 | Riser/Conduit | HFTD Tier 3 | Distribution | 2014-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015041 | 406036000 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015042 | 406037575 | Molding | HFTD Tier 2 | Distribution | 2014-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015043 | 406044397 | High Sign | HFTD Tier 3 | Distribution | 2014-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015044 | 406044399 | High Sign | HFTD Tier 3 | Distribution | 2014-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015045 | 406047559 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015046 | 406047663 | Molding | HFTD Tier 2 | Distribution | 2014-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015047 | 406047665 | High Sign | HFTD Tier 2 | Distribution | 2014-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015048 | 406047666 | High Sign | HFTD Tier 2 | Distribution | 2014-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015049 | 406051719 | High Sign | HFTD Tier 3 | Distribution | 2014-04-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015050 | 406051744 | High Sign | HFTD Tier 3 | Distribution | 2014-04-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015051 | 406058169 | Guy | HFTD Tier 2 | Distribution | 2014-04-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015052 | 406058180 | Molding | HFTD Tier 2 | Distribution | 2014-04-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015053 | 406058183 | Guy | HFTD Tier 2 | Distribution | 2014-04-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015054 | 406057654 | High Sign | HFTD Tier 3 | Distribution | 2014-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015055 | 406055759 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2014-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015056 | 406055887 | Riser/Conduit | HFTD Tier 3 | Distribution | 2014-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015057 | 406055912 | Guy | HFTD Tier 3 | Distribution | 2014-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015058 | 406056670 | Molding | HFTD Tier 3 | Distribution | 2014-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015059 | 406057735 | Molding | HFTD Tier 3 | Distribution | 2014-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015060 | 406057737 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015061 | 406057748 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015062 | 406057760 | Molding | HFTD Tier 3 | Distribution | 2014-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015063 | 406057765 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015064 | 406058456 | Guy | HFTD Tier 3 | Distribution | 2014-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015065 | 406058457 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015066 | 406057418 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015067 | 406057432 | High Sign | HFTD Tier 2 | Distribution | 2014-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015068 | 406060334 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-04-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015069 | 406060336 | Molding | HFTD Tier 2 | Distribution | 2014-04-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015070 | 406060355 | High Sign | HFTD Tier 2 | Distribution | 2014-04-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015071 | 406060359 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-04-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015072 | 406063415 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-04-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015073 | 406063417 | Molding | HFTD Tier 3 | Distribution | 2014-04-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015074 | 406063449 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-04-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015075 | 406063492 | Molding | HFTD Tier 3 | Distribution | 2014-04-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015076 | 406068113 | Molding | HFTD Tier 3 | Distribution | 2014-04-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015077 | 406061940 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2014-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015078 | 406062170 | Guy | HFTD Tier 2 | Distribution | 2014-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015079 | 406063038 | Molding | HFTD Tier 2 | Distribution | 2014-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015080 | 406063528 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015081 | 406063536 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015082 | 406063563 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015083 | 406063580 | Molding | HFTD Tier 3 | Distribution | 2014-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015084 | 406063601 | Guy | HFTD Tier 3 | Distribution | 2014-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015085 | 406063790 | High Sign | HFTD Tier 3 | Distribution | 2014-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015086 | 406064451 | Molding | HFTD Tier 2 | Distribution | 2014-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015087 | 406065532 | Molding | HFTD Tier 3 | Distribution | 2014-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015088 | 406066558 | High Sign | HFTD Tier 3 | Distribution | 2014-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015089 | 406066567 | Guy | HFTD Tier 3 | Distribution | 2014-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015090 | 406066568 | Molding | HFTD Tier 3 | Distribution | 2014-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015091 | 406070370 | Guy | HFTD Tier 3 | Distribution | 2014-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015092 | 406070655 | Molding | HFTD Tier 2 | Distribution | 2014-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015093 | 406073722 | Molding | HFTD Tier 3 | Distribution | 2014-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015094 | 406073736 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015095 | 406071280 | High Sign | HFTD Tier 3 | Distribution | 2014-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015096 | 406072508 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015097 | 406072517 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015098 | 406072524 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015099 | 406072798 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015100 | 406072820 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015101 | 406076697 | ID Markings | HFTD Tier 3 | Distribution | 2014-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015102 | 406076702 | High Sign | HFTD Tier 3 | Distribution | 2014-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015103 | 406076759 | Riser/Conduit | HFTD Tier 2 | Distribution | 2014-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015104 | 406079159 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015105 | 406081194 | Molding | HFTD Tier 2 | Distribution | 2014-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015106 | 406081471 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015107 | 406081700 | Guy | HFTD Tier 3 | Distribution | 2014-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015108 | 406081718 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015109 | 406098560 | Guy | HFTD Tier 3 | Distribution | 2014-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015110 | 406098565 | High Sign | HFTD Tier 3 | Distribution | 2014-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015111 | 406085835 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015112 | 406085837 | Molding | HFTD Tier 2 | Distribution | 2014-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015113 | 406085852 | High Sign | HFTD Tier 2 | Distribution | 2014-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015114 | 406085855 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2014-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015115 | 406085955 | Guy | HFTD Tier 3 | Distribution | 2014-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015116 | 406085966 | Guy | HFTD Tier 3 | Distribution | 2014-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015117 | 406085971 | Guy | HFTD Tier 3 | Distribution | 2014-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015118 | 406085972 | Molding | HFTD Tier 3 | Distribution | 2014-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015119 | 406086033 | Molding | HFTD Tier 3 | Distribution | 2014-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015120 | 406091109 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015121 | 406091122 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015122 | 406091130 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015123 | 406091134 | Termination | HFTD Tier 3 | Distribution | 2014-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015124 | 406091201 | Riser/Conduit | HFTD Tier 3 | Distribution | 2014-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015125 | 406091207 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015126 | 406091215 | Guy | HFTD Tier 3 | Distribution | 2014-05-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015127 | 406094795 | Molding | HFTD Tier 3 | Distribution | 2014-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015128 | 406095972 | Insulator | HFTD Tier 2 | Distribution | 2014-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015129 | 406098170 | Guy | HFTD Tier 3 | Distribution | 2014-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015130 | 406103844 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015131 | 406103872 | High Sign | HFTD Tier 3 | Distribution | 2014-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015132 | 406104919 | High Sign | HFTD Tier 2 | Distribution | 2014-05-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015133 | 406105271 | High Sign | HFTD Tier 3 | Distribution | 2014-05-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015134 | 406105549 | Molding | HFTD Tier 2 | Distribution | 2014-05-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015135 | 406107927 | High Sign | HFTD Tier 3 | Distribution | 2014-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015136 | 406118480 | Molding | HFTD Tier 3 | Distribution | 2014-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015137 | 406118496 | Guy | HFTD Tier 3 | Distribution | 2014-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015138 | 406122924 | High Sign | HFTD Tier 3 | Distribution | 2014-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015139 | 406122984 | High Sign | HFTD Tier 3 | Distribution | 2014-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015140 | 413834589 | Molding | HFTD Tier 3 | Distribution | 2014-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015141 | 406126757 | Vis Strips | HFTD Tier 2 | Distribution | 2014-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015142 | 406127948 | Molding | HFTD Tier 3 | Distribution | 2014-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015143 | 406128606 | Guy | HFTD Tier 3 | Distribution | 2014-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015144 | 406128667 | Molding | HFTD Tier 3 | Distribution | 2014-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015145 | 406128673 | High Sign | HFTD Tier 3 | Distribution | 2014-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015146 | 406128680 | High Sign | HFTD Tier 3 | Distribution | 2014-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015147 | 406133415 | Ground | HFTD Tier 3 | Distribution | 2014-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015148 | 406133421 | High Sign | HFTD Tier 3 | Distribution | 2014-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015149 | 406141614 | High Sign | HFTD Tier 3 | Distribution | 2014-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015150 | 406136469 | Molding | HFTD Tier 3 | Distribution | 2014-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015151 | 406140537 | Molding | HFTD Tier 2 | Distribution | 2014-05-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015152 | 406141048 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-05-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015153 | 406141052 | High Sign | HFTD Tier 3 | Distribution | 2014-05-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015154 | 406141701 | High Sign | HFTD Tier 3 | Distribution | 2014-05-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015155 | 406141750 | High Sign | HFTD Tier 3 | Distribution | 2014-05-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015156 | 406141752 | High Sign | HFTD Tier 3 | Distribution | 2014-05-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015157 | 406141839 | Molding | HFTD Tier 3 | Distribution | 2014-05-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015158 | 406142472 | High Sign | HFTD Tier 2 | Distribution | 2014-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015159 | 406145183 | Molding | HFTD Tier 3 | Distribution | 2014-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015160 | 406145630 | High Sign | HFTD Tier 2 | Distribution | 2014-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015161 | 406147686 | High Sign | HFTD Tier 3 | Distribution | 2014-05-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015162 | 406154681 | High Sign | HFTD Tier 3 | Distribution | 2014-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015163 | 406156909 | Guy | HFTD Tier 3 | Distribution | 2014-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015164 | 406156920 | Guy | HFTD Tier 3 | Distribution | 2014-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015165 | 406157424 | Guy | HFTD Tier 3 | Distribution | 2014-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015166 | 406157426 | Guy | HFTD Tier 3 | Distribution | 2014-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015167 | 406157430 | Guy | HFTD Tier 3 | Distribution | 2014-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015168 | 406160869 | High Sign | HFTD Tier 3 | Distribution | 2014-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015169 | 406160874 | Molding | HFTD Tier 3 | Distribution | 2014-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015170 | 406160876 | High Sign | HFTD Tier 3 | Distribution | 2014-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015171 | 406163448 | Molding | HFTD Tier 3 | Distribution | 2014-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015172 | 406163485 | High Sign | HFTD Tier 2 | Distribution | 2014-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015173 | 406168358 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015174 | 406165807 | Molding | HFTD Tier 3 | Distribution | 2014-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015175 | 406165808 | High Sign | HFTD Tier 3 | Distribution | 2014-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015176 | 406165809 | Molding | HFTD Tier 3 | Distribution | 2014-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015177 | 406167548 | High Sign | HFTD Tier 2 | Distribution | 2014-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015178 | 406167551 | Molding | HFTD Tier 2 | Distribution | 2014-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015179 | 406167553 | Molding | HFTD Tier 2 | Distribution | 2014-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015180 | 406167559 | High Sign | HFTD Tier 2 | Distribution | 2014-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015181 | 406168479 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015182 | 406168487 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015183 | 406170293 | Guy | HFTD Tier 2 | Distribution | 2014-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015184 | 406170807 | Molding | HFTD Tier 2 | Distribution | 2014-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015185 | 406174019 | Guy | HFTD Tier 2 | Distribution | 2014-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015186 | 406174031 | Guy | HFTD Tier 2 | Distribution | 2014-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015187 | 406174290 | ID Markings | HFTD Tier 3 | Distribution | 2014-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015188 | 406175247 | Bond | HFTD Tier 2 | Distribution | 2014-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015189 | 406177537 | High Sign | HFTD Tier 2 | Distribution | 2014-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015190 | 406177585 | Molding | HFTD Tier 2 | Distribution | 2014-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015191 | 406178802 | Molding | HFTD Tier 2 | Distribution | 2014-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015192 | 406180199 | High Sign | HFTD Tier 3 | Distribution | 2014-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015193 | 406180423 | Guy | HFTD Tier 3 | Distribution | 2014-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015194 | 406180798 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015195 | 406180802 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015196 | 406180805 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015197 | 406182664 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2014-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015198 | 406183403 | Guy | HFTD Tier 3 | Distribution | 2014-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015199 | 406183421 | Guy | HFTD Tier 3 | Distribution | 2014-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015200 | 406186119 | Guy | HFTD Tier 3 | Distribution | 2014-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015201 | 406186374 | Molding | HFTD Tier 2 | Distribution | 2014-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015202 | 406186375 | Molding | HFTD Tier 2 | Distribution | 2014-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015203 | 406186377 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015204 | 406186774 | High Sign | HFTD Tier 2 | Distribution | 2014-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015205 | 406189374 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2014-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015206 | 406189380 | Molding | HFTD Tier 2 | Distribution | 2014-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015207 | 406192072 | High Sign | HFTD Tier 3 | Distribution | 2014-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015208 | 406203854 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-06-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015209 | 406200606 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015210 | 406204674 | Molding | HFTD Tier 2 | Distribution | 2014-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015211 | 406204690 | High Sign | HFTD Tier 2 | Distribution | 2014-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015212 | 406207449 | High Sign | HFTD Tier 2 | Distribution | 2014-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015213 | 406207671 | Guy | HFTD Tier 2 | Distribution | 2014-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015214 | 406208226 | High Sign | HFTD Tier 2 | Distribution | 2014-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015215 | 406208240 | High Sign | HFTD Tier 2 | Distribution | 2014-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015216 | 406208242 | High Sign | HFTD Tier 2 | Distribution | 2014-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015217 | 406208243 | High Sign | HFTD Tier 2 | Distribution | 2014-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015218 | 406208244 | High Sign | HFTD Tier 2 | Distribution | 2014-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015219 | 400135312 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-06-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015220 | 406208424 | Molding | HFTD Tier 2 | Distribution | 2014-06-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015221 | 406208430 | High Sign | HFTD Tier 2 | Distribution | 2014-06-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015222 | 406208494 | Molding | HFTD Tier 3 | Distribution | 2014-06-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015223 | 406209142 | High Sign | HFTD Tier 2 | Distribution | 2014-06-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015224 | 406209513 | Molding | HFTD Tier 3 | Distribution | 2014-06-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015225 | 406211007 | High Sign | HFTD Tier 2 | Distribution | 2014-06-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015226 | 406211008 | High Sign | HFTD Tier 2 | Distribution | 2014-06-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015227 | 406211014 | High Sign | HFTD Tier 2 | Distribution | 2014-06-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015228 | 406217926 | Guy | HFTD Tier 3 | Distribution | 2014-06-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015229 | 406218164 | Molding | HFTD Tier 3 | Distribution | 2014-06-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015230 | 406216922 | High Sign | HFTD Tier 2 | Distribution | 2014-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015231 | 406217833 | Molding | HFTD Tier 3 | Distribution | 2014-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015232 | 406217949 | Molding | HFTD Tier 3 | Distribution | 2014-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015233 | 406217950 | Molding | HFTD Tier 3 | Distribution | 2014-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015234 | 406218219 | Guy | HFTD Tier 3 | Distribution | 2014-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015235 | 406218235 | Guy | HFTD Tier 3 | Distribution | 2014-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015236 | 406218243 | High Sign | HFTD Tier 3 | Distribution | 2014-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015237 | 406218251 | Molding | HFTD Tier 3 | Distribution | 2014-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015238 | 406218799 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015239 | 406220075 | Molding | HFTD Tier 3 | Distribution | 2014-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015240 | 406222297 | Guy | HFTD Tier 3 | Distribution | 2014-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015241 | 406222328 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015242 | 406222340 | Guy | HFTD Tier 3 | Distribution | 2014-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015243 | 406225571 | Guy | HFTD Tier 3 | Distribution | 2014-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015244 | 406225964 | Molding | HFTD Tier 3 | Distribution | 2014-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015245 | 406225998 | Guy | HFTD Tier 3 | Distribution | 2014-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015246 | 406226161 | Molding | HFTD Tier 3 | Distribution | 2014-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015247 | 406226338 | High Sign | HFTD Tier 2 | Distribution | 2014-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015248 | 406226339 | High Sign | HFTD Tier 2 | Distribution | 2014-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015249 | 406226415 | High Sign | HFTD Tier 2 | Distribution | 2014-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015250 | 406226452 | High Sign | HFTD Tier 2 | Distribution | 2014-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015251 | 406228874 | High Sign | HFTD Tier 2 | Distribution | 2014-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015252 | 406228882 | High Sign | HFTD Tier 2 | Distribution | 2014-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015253 | 406228927 | High Sign | HFTD Tier 2 | Distribution | 2014-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015254 | 406228929 | High Sign | HFTD Tier 2 | Distribution | 2014-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015255 | 406229201 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-07-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015256 | 406229675 | Guy | HFTD Tier 3 | Distribution | 2014-07-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015257 | 406229676 | Guy | HFTD Tier 3 | Distribution | 2014-07-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015258 | 406229777 | Guy | HFTD Tier 3 | Distribution | 2014-07-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015259 | 406281371 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-07-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015260 | 406234889 | Guy | HFTD Tier 3 | Distribution | 2014-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015261 | 406235984 | Molding | HFTD Tier 3 | Distribution | 2014-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015262 | 406237629 | Molding | HFTD Tier 3 | Distribution | 2014-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015263 | 406237825 | Molding | HFTD Tier 3 | Distribution | 2014-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015264 | 406237840 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015265 | 406237850 | Molding | HFTD Tier 3 | Distribution | 2014-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015266 | 406238900 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015267 | 406239360 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015268 | 406239370 | High Sign | HFTD Tier 3 | Distribution | 2014-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015269 | 406240851 | Guy | HFTD Tier 3 | Distribution | 2014-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015270 | 406241456 | Molding | HFTD Tier 3 | Distribution | 2014-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015271 | 406241465 | Guy | HFTD Tier 3 | Distribution | 2014-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015272 | 406241514 | Molding | HFTD Tier 3 | Distribution | 2014-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015273 | 406241515 | Guy | HFTD Tier 3 | Distribution | 2014-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015274 | 406245167 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-07-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015275 | 406246934 | High Sign | HFTD Tier 2 | Distribution | 2014-07-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015276 | 406250652 | High Sign | HFTD Tier 3 | Distribution | 2014-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015277 | 406250789 | High Sign | HFTD Tier 3 | Distribution | 2014-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015278 | 406250798 | High Sign | HFTD Tier 3 | Distribution | 2014-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015279 | 406250971 | Guy | HFTD Tier 3 | Distribution | 2014-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015280 | 406251050 | Molding | HFTD Tier 3 | Distribution | 2014-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015281 | 406254149 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015282 | 406254513 | High Sign | HFTD Tier 2 | Distribution | 2014-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015283 | 406254755 | Guy | HFTD Tier 3 | Distribution | 2014-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015284 | 406257616 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015285 | 406257617 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015286 | 406257538 | Guy | HFTD Tier 3 | Distribution | 2014-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015287 | 406257770 | Guy | HFTD Tier 3 | Distribution | 2014-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015288 | 406258117 | Riser/Conduit | HFTD Tier 2 | Distribution | 2014-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015289 | 406258568 | High Sign | HFTD Tier 2 | Distribution | 2014-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015290 | 406262082 | Molding | HFTD Tier 2 | Distribution | 2014-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015291 | 406262197 | High Sign | HFTD Tier 2 | Distribution | 2014-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015292 | 406262318 | Guy | HFTD Tier 3 | Distribution | 2014-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015293 | 406262319 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015294 | 406262340 | Molding | HFTD Tier 3 | Distribution | 2014-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015295 | 406262617 | Guy | HFTD Tier 2 | Distribution | 2014-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015296 | 406262618 | Guy | HFTD Tier 2 | Distribution | 2014-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015297 | 406265027 | Molding | HFTD Tier 3 | Distribution | 2014-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015298 | 406265121 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015299 | 406265464 | Guy | HFTD Tier 2 | Distribution | 2014-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015300 | 406265822 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015301 | 406266334 | Molding | HFTD Tier 2 | Distribution | 2014-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015302 | 406267119 | High Sign | HFTD Tier 3 | Distribution | 2014-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015303 | 406269108 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015304 | 406269115 | Molding | HFTD Tier 3 | Distribution | 2014-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015305 | 406269145 | Molding | HFTD Tier 3 | Distribution | 2014-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015306 | 406269153 | Molding | HFTD Tier 3 | Distribution | 2014-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015307 | 406274139 | Guy | HFTD Tier 3 | Distribution | 2014-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015308 | 406274157 | High Sign | HFTD Tier 3 | Distribution | 2014-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015309 | 406274172 | Guy | HFTD Tier 3 | Distribution | 2014-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015310 | 413838147 | High Sign | HFTD Tier 3 | Distribution | 2014-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015311 | 413838148 | Molding | HFTD Tier 3 | Distribution | 2014-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015312 | 406269948 | Guy | HFTD Tier 2 | Distribution | 2014-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015313 | 406270062 | Molding | HFTD Tier 3 | Distribution | 2014-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015314 | 406270386 | Riser/Conduit | HFTD Tier 3 | Distribution | 2014-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015315 | 406270811 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015316 | 406271094 | High Sign | HFTD Tier 2 | Distribution | 2014-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015317 | 406271095 | Molding | HFTD Tier 2 | Distribution | 2014-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015318 | 406271256 | Molding | HFTD Tier 3 | Distribution | 2014-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015319 | 406271845 | Guy | HFTD Tier 2 | Distribution | 2014-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015320 | 406273842 | High Sign | HFTD Tier 3 | Distribution | 2014-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015321 | 406272418 | Molding | HFTD Tier 2 | Distribution | 2014-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015322 | 406273754 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015323 | 406273850 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015324 | 406274126 | Guy | HFTD Tier 2 | Distribution | 2014-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015325 | 406274144 | Guy | HFTD Tier 2 | Distribution | 2014-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015326 | 406274220 | Guy | HFTD Tier 2 | Distribution | 2014-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015327 | 406274461 | Guy | HFTD Tier 2 | Distribution | 2014-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015328 | 406274536 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015329 | 406274547 | Guy | HFTD Tier 2 | Distribution | 2014-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015330 | 406274664 | High Sign | HFTD Tier 2 | Distribution | 2014-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015331 | 406274666 | Guy | HFTD Tier 2 | Distribution | 2014-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015332 | 406274674 | Guy | HFTD Tier 2 | Distribution | 2014-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015333 | 406289369 | Molding | HFTD Tier 3 | Distribution | 2014-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015334 | 406278228 | Guy | HFTD Tier 3 | Distribution | 2014-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015335 | 406278468 | Guy | HFTD Tier 3 | Distribution | 2014-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015336 | 406279830 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015337 | 406279854 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015338 | 406280984 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015339 | 406281138 | High Sign | HFTD Tier 3 | Distribution | 2014-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015340 | 406283838 | High Sign | HFTD Tier 3 | Distribution | 2014-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015341 | 406303606 | Guy | HFTD Tier 3 | Distribution | 2014-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015342 | 406281799 | Molding | HFTD Tier 3 | Distribution | 2014-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015343 | 406284421 | High Sign | HFTD Tier 3 | Distribution | 2014-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015344 | 406285163 | Guy | HFTD Tier 3 | Distribution | 2014-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015345 | 406285171 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015346 | 406285629 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2014-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015347 | 406286534 | High Sign | HFTD Tier 3 | Distribution | 2014-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015348 | 406286592 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015349 | 406287885 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015350 | 406287914 | High Sign | HFTD Tier 3 | Distribution | 2014-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015351 | 406289100 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015352 | 406289105 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-07-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015353 | 406290959 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015354 | 406290980 | Guy | HFTD Tier 2 | Distribution | 2014-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015355 | 406291004 | Molding | HFTD Tier 2 | Distribution | 2014-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015356 | 406291125 | Molding | HFTD Tier 2 | Distribution | 2014-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015357 | 406291435 | High Sign | HFTD Tier 2 | Distribution | 2014-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015358 | 406291452 | Molding | HFTD Tier 3 | Distribution | 2014-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015359 | 406292093 | Guy | HFTD Tier 3 | Distribution | 2014-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015360 | 406293621 | Molding | HFTD Tier 2 | Distribution | 2014-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015361 | 406294058 | High Sign | HFTD Tier 3 | Distribution | 2014-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015362 | 406294075 | Molding | HFTD Tier 3 | Distribution | 2014-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015363 | 406294104 | High Sign | HFTD Tier 3 | Distribution | 2014-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015364 | 406294105 | Guy | HFTD Tier 3 | Distribution | 2014-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015365 | 406294112 | Guy | HFTD Tier 3 | Distribution | 2014-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015366 | 406294121 | Guy | HFTD Tier 3 | Distribution | 2014-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015367 | 406294875 | Guy | HFTD Tier 2 | Distribution | 2014-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015368 | 406296842 | ID Markings | HFTD Tier 3 | Distribution | 2014-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015369 | 406298210 | High Sign | HFTD Tier 2 | Distribution | 2014-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015370 | 406299468 | High Sign | HFTD Tier 3 | Distribution | 2014-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015371 | 406299927 | Guy | HFTD Tier 2 | Distribution | 2014-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015372 | 406300078 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2014-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015373 | 406303700 | Molding | HFTD Tier 3 | Distribution | 2014-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015374 | 406303728 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015375 | 406303752 | High Sign | HFTD Tier 3 | Distribution | 2014-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015376 | 406303754 | Molding | HFTD Tier 3 | Distribution | 2014-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015377 | 406303755 | High Sign | HFTD Tier 3 | Distribution | 2014-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015378 | 406300967 | High Sign | HFTD Tier 3 | Distribution | 2014-07-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015379 | 406303497 | High Sign | HFTD Tier 3 | Distribution | 2014-07-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015380 | 406303498 | High Sign | HFTD Tier 3 | Distribution | 2014-07-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015381 | 406303505 | High Sign | HFTD Tier 3 | Distribution | 2014-07-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015382 | 406303509 | High Sign | HFTD Tier 3 | Distribution | 2014-07-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015383 | 406303510 | High Sign | HFTD Tier 3 | Distribution | 2014-07-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015384 | 406303522 | Molding | HFTD Tier 3 | Distribution | 2014-07-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015385 | 406303781 | Molding | HFTD Tier 3 | Distribution | 2014-07-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015386 | 406303818 | High Sign | HFTD Tier 3 | Distribution | 2014-07-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015387 | 406303841 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-07-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015388 | 406303857 | High Sign | HFTD Tier 3 | Distribution | 2014-07-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015389 | 406303859 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-07-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015390 | 406303860 | High Sign | HFTD Tier 3 | Distribution | 2014-07-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015391 | 406304254 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-07-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015392 | 406304569 | High Sign | HFTD Tier 2 | Distribution | 2014-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015393 | 406304810 | High Sign | HFTD Tier 2 | Distribution | 2014-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015394 | 406304860 | High Sign | HFTD Tier 3 | Distribution | 2014-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015395 | 406305107 | High Sign | HFTD Tier 3 | Distribution | 2014-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015396 | 406305218 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2014-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015397 | 406306161 | High Sign | HFTD Tier 3 | Distribution | 2014-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015398 | 406306167 | Guy | HFTD Tier 3 | Distribution | 2014-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015399 | 406307495 | High Sign | HFTD Tier 3 | Distribution | 2014-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015400 | 406307547 | High Sign | HFTD Tier 3 | Distribution | 2014-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015401 | 406307616 | High Sign | HFTD Tier 2 | Distribution | 2014-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015402 | 406307630 | Riser/Conduit | HFTD Tier 2 | Distribution | 2014-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015403 | 406307833 | High Sign | HFTD Tier 3 | Distribution | 2014-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015404 | 406307850 | Molding | HFTD Tier 3 | Distribution | 2014-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015405 | 406307851 | Molding | HFTD Tier 3 | Distribution | 2014-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015406 | 406313947 | Molding | HFTD Tier 2 | Distribution | 2014-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015407 | 406313960 | Molding | HFTD Tier 2 | Distribution | 2014-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015408 | 406313961 | Molding | HFTD Tier 2 | Distribution | 2014-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015409 | 406309278 | High Sign | HFTD Tier 3 | Distribution | 2014-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015410 | 406309302 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015411 | 406309898 | Bond | HFTD Tier 3 | Distribution | 2014-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015412 | 406310292 | Guy | HFTD Tier 3 | Distribution | 2014-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015413 | 406311720 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2014-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015414 | 406312849 | High Sign | HFTD Tier 3 | Distribution | 2014-08-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015415 | 406316459 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-08-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015416 | 406321912 | Molding | HFTD Tier 3 | Distribution | 2014-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015417 | 406322229 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015418 | 406322266 | High Sign | HFTD Tier 3 | Distribution | 2014-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015419 | 406323542 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015420 | 406325120 | High Sign | HFTD Tier 3 | Distribution | 2014-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015421 | 406325135 | Insulator | HFTD Tier 3 | Distribution | 2014-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015422 | 406326657 | Guy | HFTD Tier 3 | Distribution | 2014-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015423 | 406327694 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015424 | 406327833 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015425 | 406327834 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015426 | 406327835 | High Sign | HFTD Tier 3 | Distribution | 2014-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015427 | 406328282 | High Sign | HFTD Tier 3 | Distribution | 2014-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015428 | 406329415 | Molding | HFTD Tier 3 | Distribution | 2014-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015429 | 406329417 | High Sign | HFTD Tier 3 | Distribution | 2014-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015430 | 406329430 | Molding | HFTD Tier 3 | Distribution | 2014-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015431 | 406330190 | Guy | HFTD Tier 3 | Distribution | 2014-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015432 | 406332207 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015433 | 406332539 | Guy | HFTD Tier 3 | Distribution | 2014-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015434 | 406332658 | High Sign | HFTD Tier 3 | Distribution | 2014-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015435 | 406332665 | High Sign | HFTD Tier 3 | Distribution | 2014-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015436 | 406332671 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015437 | 406332739 | Guy | HFTD Tier 3 | Distribution | 2014-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015438 | 406333388 | High Sign | HFTD Tier 2 | Distribution | 2014-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015439 | 406333391 | Termination | HFTD Tier 3 | Distribution | 2014-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015440 | 406333744 | High Sign | HFTD Tier 3 | Distribution | 2014-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015441 | 400043068 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015442 | 406336979 | Molding | HFTD Tier 2 | Distribution | 2014-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015443 | 406337456 | High Sign | HFTD Tier 3 | Distribution | 2014-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015444 | 406337457 | Molding | HFTD Tier 3 | Distribution | 2014-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015445 | 406337458 | High Sign | HFTD Tier 3 | Distribution | 2014-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015446 | 406337461 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015447 | 406338241 | Molding | HFTD Tier 3 | Distribution | 2014-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015448 | 406338254 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015449 | 406338264 | High Sign | HFTD Tier 3 | Distribution | 2014-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015450 | 406338667 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2014-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015451 | 406339026 | Molding | HFTD Tier 3 | Distribution | 2014-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015452 | 406341164 | High Sign | HFTD Tier 3 | Distribution | 2014-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015453 | 406341751 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015454 | 406341764 | Guy | HFTD Tier 3 | Distribution | 2014-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015455 | 406341765 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015456 | 406341829 | Molding | HFTD Tier 3 | Distribution | 2014-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015457 | 406341834 | High Sign | HFTD Tier 3 | Distribution | 2014-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015458 | 406342589 | High Sign | HFTD Tier 3 | Distribution | 2014-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015459 | 406342597 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015460 | 406343620 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015461 | 406343876 | Guy | HFTD Tier 3 | Distribution | 2014-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015462 | 406343877 | Guy | HFTD Tier 3 | Distribution | 2014-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015463 | 406344006 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015464 | 406344142 | Guy | HFTD Tier 3 | Distribution | 2014-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015465 | 406344143 | High Sign | HFTD Tier 3 | Distribution | 2014-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015466 | 406344145 | High Sign | HFTD Tier 3 | Distribution | 2014-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015467 | 406344147 | Guy | HFTD Tier 3 | Distribution | 2014-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015468 | 406344158 | Guy | HFTD Tier 3 | Distribution | 2014-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015469 | 406344159 | High Sign | HFTD Tier 3 | Distribution | 2014-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015470 | 406344190 | High Sign | HFTD Tier 3 | Distribution | 2014-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015471 | 406345870 | Guy | HFTD Tier 2 | Distribution | 2014-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015472 | 400290072 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015473 | 400341103 | High Sign | HFTD Tier 2 | Distribution | 2014-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015474 | 400488688 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015475 | 400615261 | High Sign | HFTD Tier 2 | Distribution | 2014-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015476 | 406347135 | Molding | HFTD Tier 2 | Distribution | 2014-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015477 | 406347164 | Guy | HFTD Tier 2 | Distribution | 2014-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015478 | 406347457 | High Sign | HFTD Tier 2 | Distribution | 2014-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015479 | 406359934 | Guy | HFTD Tier 3 | Distribution | 2014-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015480 | 406351117 | High Sign | HFTD Tier 3 | Distribution | 2014-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015481 | 406351754 | Guy | HFTD Tier 2 | Distribution | 2014-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015482 | 406351758 | Guy | HFTD Tier 2 | Distribution | 2014-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015483 | 406351796 | Guy | HFTD Tier 2 | Distribution | 2014-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015484 | 406352934 | Guy | HFTD Tier 2 | Distribution | 2014-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015485 | 406353786 | High Sign | HFTD Tier 2 | Distribution | 2014-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015486 | 406353790 | High Sign | HFTD Tier 2 | Distribution | 2014-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015487 | 406353795 | Guy | HFTD Tier 2 | Distribution | 2014-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015488 | 406353796 | High Sign | HFTD Tier 2 | Distribution | 2014-08-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015489 | 406357625 | Guy | HFTD Tier 2 | Distribution | 2014-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015490 | 406357628 | Guy | HFTD Tier 2 | Distribution | 2014-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015491 | 406357641 | Guy | HFTD Tier 2 | Distribution | 2014-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015492 | 406359133 | High Sign | HFTD Tier 3 | Distribution | 2014-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015493 | 406359256 | Guy | HFTD Tier 3 | Distribution | 2014-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015494 | 406359395 | Guy | HFTD Tier 3 | Distribution | 2014-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015495 | 406359415 | Guy | HFTD Tier 3 | Distribution | 2014-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015496 | 406359453 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015497 | 406360038 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015498 | 406363775 | High Sign | HFTD Tier 3 | Distribution | 2014-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015499 | 406365223 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015500 | 406365225 | Guy | HFTD Tier 3 | Distribution | 2014-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015501 | 406366199 | Riser/Conduit | HFTD Tier 3 | Distribution | 2014-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015502 | 406368304 | Molding | HFTD Tier 3 | Distribution | 2014-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015503 | 406368597 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015504 | 406369089 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015505 | 406369872 | Molding | HFTD Tier 2 | Distribution | 2014-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015506 | 406370176 | High Sign | HFTD Tier 3 | Distribution | 2014-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015507 | 406374058 | Guy | HFTD Tier 3 | Distribution | 2014-08-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015508 | 406374814 | Right of Way | HFTD Tier 2 | Transmission | 2014-08-21 | 42237 | 2 | [8 empty] | SCE | 2026 | 2
1120015509 | 406377937 | Guy | HFTD Tier 3 | Distribution | 2014-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015510 | 406377945 | Guy | HFTD Tier 3 | Distribution | 2014-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015511 | 406379358 | High Sign | HFTD Tier 3 | Distribution | 2014-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015512 | 406379710 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015513 | 406384330 | Molding | HFTD Tier 3 | Distribution | 2014-08-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015514 | 406385094 | High Sign | HFTD Tier 3 | Distribution | 2014-08-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015515 | 406385095 | Molding | HFTD Tier 3 | Distribution | 2014-08-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015516 | 406380463 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-08-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015517 | 406387706 | High Sign | HFTD Tier 2 | Distribution | 2014-08-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015518 | 406387707 | High Sign | HFTD Tier 2 | Distribution | 2014-08-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015519 | 406387709 | High Sign | HFTD Tier 2 | Distribution | 2014-08-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015520 | 406387710 | High Sign | HFTD Tier 2 | Distribution | 2014-08-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015521 | 406387850 | High Sign | HFTD Tier 3 | Distribution | 2014-08-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015522 | 406389395 | Molding | HFTD Tier 2 | Distribution | 2014-08-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015523 | 406389454 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2014-08-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015524 | 406391401 | Guy | HFTD Tier 3 | Distribution | 2014-08-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015525 | 406391855 | Molding | HFTD Tier 3 | Distribution | 2014-08-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015526 | 406391897 | High Sign | HFTD Tier 3 | Distribution | 2014-08-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015527 | 406391898 | Molding | HFTD Tier 3 | Distribution | 2014-08-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015528 | 406392241 | Guy | HFTD Tier 2 | Distribution | 2014-08-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015529 | 406392312 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-08-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015530 | 406392337 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-08-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015531 | 406392343 | Molding | HFTD Tier 3 | Distribution | 2014-08-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015532 | 406392647 | High Sign | HFTD Tier 2 | Distribution | 2014-08-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015533 | 406394193 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-08-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015534 | 406394488 | Molding | HFTD Tier 2 | Distribution | 2014-08-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015535 | 406394590 | Molding | HFTD Tier 2 | Distribution | 2014-08-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015536 | 406395324 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-08-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015537 | 406395228 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015538 | 406395280 | High Sign | HFTD Tier 2 | Distribution | 2014-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015539 | 406395322 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015540 | 406395648 | Molding | HFTD Tier 2 | Distribution | 2014-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015541 | 406396975 | Molding | HFTD Tier 3 | Distribution | 2014-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015542 | 406401615 | Molding | HFTD Tier 2 | Distribution | 2014-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015543 | 406398561 | High Sign | HFTD Tier 3 | Distribution | 2014-09-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015544 | 406399939 | Molding | HFTD Tier 3 | Distribution | 2014-09-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015545 | 406399949 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-09-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015546 | 406411629 | High Sign | HFTD Tier 3 | Distribution | 2014-09-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015547 | 406401973 | Molding | HFTD Tier 2 | Distribution | 2014-09-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015548 | 406403247 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-09-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015549 | 406403576 | High Sign | HFTD Tier 2 | Distribution | 2014-09-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015550 | 406403590 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-09-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015551 | 406403640 | Guy | HFTD Tier 3 | Distribution | 2014-09-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015552 | 406404938 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-09-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015553 | 406404949 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-09-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015554 | 413685970 | Guy Guard | HFTD Tier 3 | Distribution | 2014-09-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015555 | 406406300 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-09-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015556 | 406406310 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-09-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015557 | 406407981 | Riser/Conduit | HFTD Tier 2 | Distribution | 2014-09-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015558 | 406408321 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-09-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015559 | 406410128 | High Sign | HFTD Tier 2 | Distribution | 2014-09-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015560 | 406410220 | Guy | HFTD Tier 3 | Distribution | 2014-09-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015561 | 406410385 | High Sign | HFTD Tier 2 | Distribution | 2014-09-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015562 | 406410449 | Guy | HFTD Tier 3 | Distribution | 2014-09-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015563 | 406410464 | Guy | HFTD Tier 3 | Distribution | 2014-09-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015564 | 406410477 | Guy | HFTD Tier 3 | Distribution | 2014-09-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015565 | 400374125 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015566 | 406412534 | Molding | HFTD Tier 2 | Distribution | 2014-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015567 | 406419557 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-09-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015568 | 400224502 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-09-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015569 | 406417427 | High Sign | HFTD Tier 3 | Distribution | 2014-09-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015570 | 406417879 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-09-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015571 | 406418377 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-09-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015572 | 406418393 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-09-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015573 | 406418556 | High Sign | HFTD Tier 2 | Distribution | 2014-09-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015574 | 406421126 | High Sign | HFTD Tier 3 | Distribution | 2014-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015575 | 406421132 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015576 | 406422085 | Molding | HFTD Tier 3 | Distribution | 2014-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015577 | 406422224 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015578 | 406422458 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015579 | 406423749 | Molding | HFTD Tier 2 | Distribution | 2014-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015580 | 406423799 | High Sign | HFTD Tier 2 | Distribution | 2014-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015581 | 406423808 | Molding | HFTD Tier 2 | Distribution | 2014-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015582 | 406424096 | High Sign | HFTD Tier 2 | Distribution | 2014-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015583 | 406424104 | High Sign | HFTD Tier 2 | Distribution | 2014-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015584 | 406426150 | High Sign | HFTD Tier 2 | Distribution | 2014-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015585 | 406426063 | High Sign | HFTD Tier 2 | Distribution | 2014-09-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015586 | 406426071 | High Sign | HFTD Tier 2 | Distribution | 2014-09-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015587 | 406426074 | Insulator | HFTD Tier 2 | Distribution | 2014-09-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015588 | 406427327 | High Sign | HFTD Tier 2 | Distribution | 2014-09-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015589 | 406427329 | High Sign | HFTD Tier 2 | Distribution | 2014-09-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015590 | 406427330 | Molding | HFTD Tier 2 | Distribution | 2014-09-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015591 | 406427335 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-09-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015592 | 406427775 | High Sign | HFTD Tier 3 | Distribution | 2014-09-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015593 | 406429235 | Molding | HFTD Tier 3 | Distribution | 2014-09-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015594 | 406429474 | Molding | HFTD Tier 3 | Distribution | 2014-09-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015595 | 406429544 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-09-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015596 | 406433565 | High Sign | HFTD Tier 3 | Distribution | 2014-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015597 | 406434898 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015598 | 406434910 | High Sign | HFTD Tier 3 | Distribution | 2014-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015599 | 406437258 | Molding | HFTD Tier 3 | Distribution | 2014-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015600 | 406437832 | Guy | HFTD Tier 3 | Distribution | 2014-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015601 | 406437846 | Molding | HFTD Tier 3 | Distribution | 2014-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015602 | 406437852 | Molding | HFTD Tier 3 | Distribution | 2014-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015603 | 406436311 | High Sign | HFTD Tier 3 | Distribution | 2014-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015604 | 406436419 | Guy | HFTD Tier 3 | Distribution | 2014-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015605 | 406437732 | Guy | HFTD Tier 3 | Distribution | 2014-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015606 | 406438832 | High Sign | HFTD Tier 3 | Distribution | 2014-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015607 | 406441860 | High Sign | HFTD Tier 2 | Distribution | 2014-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015608 | 406439752 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-09-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015609 | 406440555 | Molding | HFTD Tier 3 | Distribution | 2014-09-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015610 | 406440619 | High Sign | HFTD Tier 2 | Distribution | 2014-09-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015611 | 406440626 | High Sign | HFTD Tier 2 | Distribution | 2014-09-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015612 | 406441016 | Guy | HFTD Tier 3 | Distribution | 2014-09-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015613 | 406443974 | Molding | HFTD Tier 3 | Distribution | 2014-09-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015614 | 406444255 | High Sign | HFTD Tier 2 | Distribution | 2014-09-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015615 | 406446106 | High Sign | HFTD Tier 3 | Distribution | 2014-09-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015616 | 406446944 | Molding | HFTD Tier 3 | Distribution | 2014-09-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015617 | 406447415 | High Sign | HFTD Tier 3 | Distribution | 2014-09-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015618 | 406453447 | High Sign | HFTD Tier 2 | Distribution | 2014-09-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015619 | 406453463 | High Sign | HFTD Tier 2 | Distribution | 2014-09-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015620 | 406454563 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-09-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015621 | 406454572 | Molding | HFTD Tier 3 | Distribution | 2014-09-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015622 | 406461578 | High Sign | HFTD Tier 3 | Distribution | 2014-09-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015623 | 406461580 | Molding | HFTD Tier 3 | Distribution | 2014-09-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015624 | 406461869 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-09-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015625 | 406471363 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-09-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015626 | 406471507 | High Sign | HFTD Tier 3 | Distribution | 2014-09-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015627 | 406472801 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-09-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015628 | 406475256 | High Sign | HFTD Tier 2 | Distribution | 2014-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015629 | 406475519 | Guy | HFTD Tier 3 | Distribution | 2014-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015630 | 406475659 | High Sign | HFTD Tier 2 | Distribution | 2014-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015631 | 406475842 | High Sign | HFTD Tier 3 | Distribution | 2014-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015632 | 406476335 | High Sign | HFTD Tier 3 | Distribution | 2014-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015633 | 406476832 | Molding | HFTD Tier 2 | Distribution | 2014-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015634 | 413829850 | Guy | HFTD Tier 3 | Distribution | 2014-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015635 | 406479257 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015636 | 406479379 | Guy | HFTD Tier 3 | Distribution | 2014-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015637 | 406482178 | Molding | HFTD Tier 3 | Distribution | 2014-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015638 | 406482190 | High Sign | HFTD Tier 3 | Distribution | 2014-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015639 | 406482191 | High Sign | HFTD Tier 3 | Distribution | 2014-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015640 | 406483847 | Guy | HFTD Tier 3 | Distribution | 2014-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015641 | 406483858 | Guy | HFTD Tier 3 | Distribution | 2014-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015642 | 406484203 | Guy | HFTD Tier 3 | Distribution | 2014-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015643 | 406495078 | High Sign | HFTD Tier 3 | Distribution | 2014-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015644 | 406495080 | Molding | HFTD Tier 3 | Distribution | 2014-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015645 | 406495101 | Molding | HFTD Tier 3 | Distribution | 2014-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015646 | 400529648 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-10-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015647 | 406488514 | Insulator | HFTD Tier 3 | Distribution | 2014-10-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015648 | 406489581 | High Sign | HFTD Tier 3 | Distribution | 2014-10-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015649 | 406495102 | Guy | HFTD Tier 3 | Distribution | 2014-10-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015650 | 406493853 | High Sign | HFTD Tier 3 | Distribution | 2014-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015651 | 406503073 | Guy | HFTD Tier 2 | Distribution | 2014-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015652 | 406503079 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015653 | 406507585 | High Sign | HFTD Tier 2 | Distribution | 2014-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015654 | 406507594 | Molding | HFTD Tier 2 | Distribution | 2014-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015655 | 406512103 | Guy | HFTD Tier 2 | Distribution | 2014-10-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015656 | 406516574 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-10-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015657 | 406517116 | High Sign | HFTD Tier 2 | Distribution | 2014-10-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015658 | 406517117 | High Sign | HFTD Tier 2 | Distribution | 2014-10-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015659 | 406517150 | Molding | HFTD Tier 2 | Distribution | 2014-10-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015660 | 406523390 | High Sign | HFTD Tier 3 | Distribution | 2014-10-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015661 | 406519439 | Guy | HFTD Tier 3 | Distribution | 2014-10-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015662 | 406519543 | Molding | HFTD Tier 3 | Distribution | 2014-10-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015663 | 406520616 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-10-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015664 | 406520618 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-10-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015665 | 406520728 | Guy | HFTD Tier 3 | Distribution | 2014-10-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015666 | 406523144 | Guy | HFTD Tier 3 | Distribution | 2014-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015667 | 406523487 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015668 | 406524166 | Guy | HFTD Tier 3 | Distribution | 2014-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015669 | 406524492 | High Sign | HFTD Tier 2 | Distribution | 2014-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015670 | 406524536 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015671 | 406524543 | Guy | HFTD Tier 2 | Distribution | 2014-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015672 | 406524617 | Molding | HFTD Tier 2 | Distribution | 2014-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015673 | 406525227 | Molding | HFTD Tier 2 | Distribution | 2014-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015674 | 406525382 | Guy | HFTD Tier 2 | Distribution | 2014-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015675 | 406527891 | Guy | HFTD Tier 3 | Distribution | 2014-10-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015676 | 406529325 | Molding | HFTD Tier 2 | Distribution | 2014-10-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015677 | 406529337 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2014-10-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015678 | 406529362 | Guy | HFTD Tier 3 | Distribution | 2014-10-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015679 | 406529409 | High Sign | HFTD Tier 2 | Distribution | 2014-10-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015680 | 406529642 | Riser/Conduit | HFTD Tier 2 | Distribution | 2014-10-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015681 | 406529651 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-10-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015682 | 406532677 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-10-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015683 | 406532811 | Guy | HFTD Tier 3 | Distribution | 2014-10-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015684 | 406533282 | High Sign | HFTD Tier 2 | Distribution | 2014-10-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015685 | 406534831 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-10-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015686 | 413829871 | High Sign | HFTD Tier 3 | Distribution | 2014-10-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015687 | 406535741 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015688 | 406536862 | Guy | HFTD Tier 3 | Distribution | 2014-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015689 | 406539884 | Guy | HFTD Tier 3 | Distribution | 2014-10-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015690 | 406539891 | Molding | HFTD Tier 3 | Distribution | 2014-10-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015691 | 406540868 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-10-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015692 | 406540881 | Molding | HFTD Tier 2 | Distribution | 2014-10-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015693 | 406540882 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-10-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015694 | 406540904 | Molding | HFTD Tier 2 | Distribution | 2014-10-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015695 | 406544003 | Guy | HFTD Tier 3 | Distribution | 2014-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015696 | 406544306 | Molding | HFTD Tier 2 | Distribution | 2014-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015697 | 406544581 | Termination | HFTD Tier 2 | Distribution | 2014-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015698 | 406548640 | Guy | HFTD Tier 2 | Distribution | 2014-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015699 | 406548652 | High Sign | HFTD Tier 2 | Distribution | 2014-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015700 | 406548657 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-10-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015701 | 406554848 | Insulator | HFTD Tier 3 | Distribution | 2014-10-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015702 | 406554884 | Molding | HFTD Tier 3 | Distribution | 2014-10-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015703 | 406554900 | Guy | HFTD Tier 3 | Distribution | 2014-10-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015704 | 406550923 | High Sign | HFTD Tier 2 | Distribution | 2014-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015705 | 406552317 | High Sign | HFTD Tier 2 | Distribution | 2014-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015706 | 406558565 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015707 | 406561785 | High Sign | HFTD Tier 3 | Distribution | 2014-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015708 | 406561794 | High Sign | HFTD Tier 3 | Distribution | 2014-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015709 | 406564830 | High Sign | HFTD Tier 2 | Distribution | 2014-10-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015710 | 406564885 | Molding | HFTD Tier 2 | Distribution | 2014-10-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015711 | 406565435 | Molding | HFTD Tier 2 | Distribution | 2014-10-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015712 | 406579441 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-11-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015713 | 406579444 | Molding | HFTD Tier 2 | Distribution | 2014-11-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015714 | 406587636 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-11-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015715 | 406587719 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-11-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015716 | 406588122 | Guy | HFTD Tier 2 | Distribution | 2014-11-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015717 | 406588456 | Molding | HFTD Tier 2 | Distribution | 2014-11-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015718 | 406591046 | Guy | HFTD Tier 2 | Distribution | 2014-11-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015719 | 406595996 | Guy | HFTD Tier 2 | Distribution | 2014-11-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015720 | 406594876 | High Sign | HFTD Tier 2 | Distribution | 2014-11-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015721 | 406596182 | High Sign | HFTD Tier 2 | Distribution | 2014-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015722 | 406596924 | High Sign | HFTD Tier 2 | Distribution | 2014-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015723 | 406596983 | Guy | HFTD Tier 3 | Distribution | 2014-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015724 | 406596992 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015725 | 406597131 | Cable/Conductor | HFTD Tier 2 | Distribution | 2014-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015726 | 406597338 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015727 | 406597340 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015728 | 406597455 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015729 | 406598763 | Guy | HFTD Tier 3 | Distribution | 2014-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015730 | 406598979 | High Sign | HFTD Tier 2 | Distribution | 2014-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015731 | 406599291 | Riser/Conduit | HFTD Tier 3 | Distribution | 2014-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015732 | 406599532 | High Sign | HFTD Tier 2 | Distribution | 2014-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015733 | 406599798 | Guy | HFTD Tier 2 | Distribution | 2014-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015734 | 406599939 | Molding | HFTD Tier 3 | Distribution | 2014-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015735 | 406599944 | High Sign | HFTD Tier 3 | Distribution | 2014-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015736 | 406599984 | Molding | HFTD Tier 3 | Distribution | 2014-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015737 | 406607922 | High Sign | HFTD Tier 2 | Distribution | 2014-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015738 | 406603699 | Hardware/Framing | HFTD Tier 2 | Distribution | 2014-11-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015739 | 406605756 | High Sign | HFTD Tier 2 | Distribution | 2014-11-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015740 | 406607938 | High Sign | HFTD Tier 2 | Distribution | 2014-11-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015741 | 406608342 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-11-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015742 | 406608848 | Termination | HFTD Tier 3 | Distribution | 2014-11-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015743 | 406611428 | ID Markings | HFTD Tier 3 | Distribution | 2014-11-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015744 | 406612861 | Molding | HFTD Tier 3 | Distribution | 2014-11-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015745 | 406613302 | High Sign | HFTD Tier 3 | Distribution | 2014-11-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015746 | 406615693 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015747 | 406615786 | Molding | HFTD Tier 2 | Distribution | 2014-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015748 | 406615934 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015749 | 406619123 | Molding | HFTD Tier 3 | Distribution | 2014-11-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015750 | 406619140 | High Sign | HFTD Tier 3 | Distribution | 2014-11-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015751 | 406621620 | High Sign | HFTD Tier 2 | Distribution | 2014-11-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015752 | 406628337 | Guy | HFTD Tier 3 | Distribution | 2014-11-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015753 | 406628898 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-11-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015754 | 406631593 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-11-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015755 | 406634279 | High Sign | HFTD Tier 2 | Distribution | 2014-11-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015756 | 406680015 | Structure/Equip Itself | HFTD Tier 2 | Transmission | 2014-11-25 | 43064 | 2 | [8 empty] | SCE | 2026 | 2
1120015757 | 406640272 | High Sign | HFTD Tier 2 | Distribution | 2014-12-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015758 | 406651037 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015759 | 406651568 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015760 | 406651599 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015761 | 406651605 | Guy | HFTD Tier 3 | Distribution | 2014-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015762 | 406652053 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015763 | 406652058 | High Sign | HFTD Tier 3 | Distribution | 2014-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015764 | 406652092 | High Sign | HFTD Tier 3 | Distribution | 2014-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015765 | 406652266 | High Sign | HFTD Tier 3 | Distribution | 2014-12-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015766 | 406654318 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-12-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015767 | 406656205 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-12-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015768 | 406656208 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-12-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015769 | 406656211 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-12-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015770 | 406656369 | Hardware/Framing | HFTD Tier 3 | Distribution | 2014-12-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015771 | 406656397 | Molding | HFTD Tier 3 | Distribution | 2014-12-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015772 | 406656742 | Guy | HFTD Tier 3 | Distribution | 2014-12-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015773 | 406658131 | Cable/Conductor | HFTD Tier 3 | Distribution | 2014-12-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015774 | 406658529 | Molding | HFTD Tier 3 | Distribution | 2014-12-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015775 | 406658532 | High Sign | HFTD Tier 3 | Distribution | 2014-12-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015776 | 406660665 | Molding | HFTD Tier 3 | Distribution | 2014-12-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015777 | 406672178 | Guy | HFTD Tier 3 | Distribution | 2014-12-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015778 | 406674644 | Guy | HFTD Tier 3 | Distribution | 2014-12-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015779 | 406683001 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2014-12-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015780 | 406687934 | Guy | HFTD Tier 2 | Distribution | 2015-01-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015781 | 406688578 | Molding | HFTD Tier 3 | Distribution | 2015-01-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015782 | 406688706 | High Sign | HFTD Tier 3 | Distribution | 2015-01-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015783 | 406688736 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-01-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015784 | 406688866 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-01-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015785 | 406689395 | High Sign | HFTD Tier 2 | Distribution | 2015-01-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015786 | 406689412 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-01-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015787 | 406689413 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-01-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015788 | 406689416 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-01-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015789 | 406690391 | High Sign | HFTD Tier 3 | Distribution | 2015-01-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015790 | 406690394 | Guy | HFTD Tier 3 | Distribution | 2015-01-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015791 | 406691072 | Guy | HFTD Tier 3 | Distribution | 2015-01-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015792 | 406693241 | Insulator | HFTD Tier 2 | Distribution | 2015-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015793 | 406693446 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2015-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015794 | 406693480 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2015-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015795 | 406693622 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015796 | 406693726 | High Sign | HFTD Tier 2 | Distribution | 2015-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015797 | 406694123 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015798 | 406695050 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2015-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015799 | 406695559 | Molding | HFTD Tier 2 | Distribution | 2015-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015800 | 406695900 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2015-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015801 | 406695920 | Guy | HFTD Tier 3 | Distribution | 2015-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015802 | 406696147 | High Sign | HFTD Tier 2 | Distribution | 2015-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015803 | 406696564 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015804 | 406697054 | High Sign | HFTD Tier 2 | Distribution | 2015-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015805 | 406697055 | Molding | HFTD Tier 2 | Distribution | 2015-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015806 | 406697882 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015807 | 406697937 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015808 | 415121939 | Guy | HFTD Tier 2 | Distribution | 2015-01-08 | 42377 | 2 | Ignition Risk, no GO95 exception | [7 empty] | SCE | 2026 | 2
1120015809 | 406699964 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2015-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015810 | 406700482 | Guy | HFTD Tier 2 | Distribution | 2015-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015811 | 406700924 | Guy | HFTD Tier 2 | Distribution | 2015-01-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015812 | 406702874 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015813 | 406703634 | Molding | HFTD Tier 3 | Distribution | 2015-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015814 | 406703857 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015815 | 406704141 | Riser/Conduit | HFTD Tier 3 | Distribution | 2015-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015816 | 406704430 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015817 | 406704431 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015818 | 406704442 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015819 | 406705251 | Molding | HFTD Tier 2 | Distribution | 2015-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015820 | 406705254 | High Sign | HFTD Tier 2 | Distribution | 2015-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015821 | 406705594 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015822 | 400813290 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015823 | 406705681 | High Sign | HFTD Tier 3 | Distribution | 2015-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015824 | 406705905 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015825 | 406706003 | High Sign | HFTD Tier 3 | Distribution | 2015-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015826 | 406706027 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015827 | 406706219 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015828 | 406706247 | High Sign | HFTD Tier 3 | Distribution | 2015-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015829 | 406706352 | High Sign | HFTD Tier 2 | Distribution | 2015-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015830 | 406706568 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015831 | 406706604 | High Sign | HFTD Tier 2 | Distribution | 2015-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015832 | 406706843 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015833 | 406706920 | High Sign | HFTD Tier 3 | Distribution | 2015-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015834 | 406706966 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015835 | 406707249 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015836 | 406707250 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015837 | 406707258 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015838 | 406709421 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015839 | 406712338 | Molding | HFTD Tier 2 | Distribution | 2015-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015840 | 406712342 | Molding | HFTD Tier 2 | Distribution | 2015-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015841 | 406710109 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015842 | 406710124 | High Sign | HFTD Tier 2 | Distribution | 2015-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015843 | 406710139 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015844 | 406710141 | Molding | HFTD Tier 3 | Distribution | 2015-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015845 | 406710274 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015846 | 406710697 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015847 | 406710785 | Insulator | HFTD Tier 2 | Distribution | 2015-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015848 | 406710836 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015849 | 406710901 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015850 | 406711160 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015851 | 406711188 | Guy | HFTD Tier 3 | Distribution | 2015-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015852 | 406713010 | Vis Strips | HFTD Tier 3 | Distribution | 2015-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015853 | 406713127 | Molding | HFTD Tier 2 | Distribution | 2015-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015854 | 406713166 | Molding | HFTD Tier 2 | Distribution | 2015-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015855 | 406713190 | Molding | HFTD Tier 2 | Distribution | 2015-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015856 | 406713292 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-01-15 | 42384 | 2 | Ignition Risk, no GO95 exception | [7 empty] | SCE | 2026 | 2
1120015857 | 406713560 | Riser/Conduit | HFTD Tier 3 | Distribution | 2015-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015858 | 406713575 | Guy | HFTD Tier 2 | Distribution | 2015-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015859 | 406713578 | High Sign | HFTD Tier 2 | Distribution | 2015-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015860 | 406713785 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015861 | 406714029 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015862 | 406714043 | Guy | HFTD Tier 2 | Distribution | 2015-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015863 | 406714364 | Molding | HFTD Tier 2 | Distribution | 2015-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015864 | 406714371 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015865 | 406715410 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015866 | 406715432 | Molding | HFTD Tier 2 | Distribution | 2015-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015867 | 406715554 | Molding | HFTD Tier 2 | Distribution | 2015-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015868 | 406715573 | High Sign | HFTD Tier 2 | Distribution | 2015-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015869 | 406715582 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015870 | 406715664 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015871 | 406715677 | Molding | HFTD Tier 2 | Distribution | 2015-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015872 | 406716174 | High Sign | HFTD Tier 2 | Distribution | 2015-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015873 | 406723294 | High Sign | HFTD Tier 2 | Distribution | 2015-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015874 | 406723300 | Molding | HFTD Tier 2 | Distribution | 2015-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015875 | 406723303 | High Sign | HFTD Tier 2 | Distribution | 2015-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015876 | 406718436 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015877 | 406718539 | Molding | HFTD Tier 2 | Distribution | 2015-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015878 | 406719333 | High Sign | HFTD Tier 2 | Distribution | 2015-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015879 | 406719377 | Guy | HFTD Tier 2 | Distribution | 2015-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015880 | 406719379 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015881 | 406719498 | Molding | HFTD Tier 3 | Distribution | 2015-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015882 | 406719735 | Riser/Conduit | HFTD Tier 2 | Distribution | 2015-01-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015883 | 406723854 | Guy | HFTD Tier 2 | Distribution | 2015-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015884 | 406724083 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015885 | 406724344 | High Sign | HFTD Tier 2 | Distribution | 2015-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015886 | 406724431 | Molding | HFTD Tier 3 | Distribution | 2015-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015887 | 406724866 | Molding | HFTD Tier 3 | Distribution | 2015-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015888 | 406724891 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015889 | 406726801 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015890 | 406731957 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015891 | 406731967 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015892 | 406727324 | High Sign | HFTD Tier 2 | Distribution | 2015-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015893 | 406727531 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015894 | 406728559 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015895 | 406729657 | High Sign | HFTD Tier 2 | Distribution | 2015-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015896 | 406729783 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015897 | 406730486 | Guy | HFTD Tier 3 | Distribution | 2015-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015898 | 406730353 | Molding | HFTD Tier 3 | Distribution | 2015-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015899 | 406730630 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015900 | 406731154 | High Sign | HFTD Tier 2 | Distribution | 2015-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015901 | 406731318 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015902 | 406731541 | Insulator | HFTD Tier 2 | Distribution | 2015-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015903 | 406731552 | Molding | HFTD Tier 2 | Distribution | 2015-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015904 | 406733012 | Molding | HFTD Tier 2 | Distribution | 2015-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015905 | 406733148 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015906 | 406733155 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015907 | 406739261 | High Sign | HFTD Tier 3 | Distribution | 2015-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015908 | 406734306 | Vis Strips | HFTD Tier 3 | Distribution | 2015-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015909 | 406734967 | Guy | HFTD Tier 2 | Distribution | 2015-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015910 | 406735441 | Molding | HFTD Tier 2 | Distribution | 2015-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015911 | 406736076 | High Sign | HFTD Tier 2 | Distribution | 2015-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015912 | 406736079 | Molding | HFTD Tier 2 | Distribution | 2015-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015913 | 406736188 | High Sign | HFTD Tier 3 | Distribution | 2015-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015914 | 406736189 | High Sign | HFTD Tier 3 | Distribution | 2015-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015915 | 406736193 | Guy | HFTD Tier 3 | Distribution | 2015-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015916 | 406736194 | High Sign | HFTD Tier 3 | Distribution | 2015-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015917 | 406736358 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015918 | 406736408 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015919 | 406739307 | Molding | HFTD Tier 2 | Distribution | 2015-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015920 | 406739308 | Riser/Conduit | HFTD Tier 2 | Distribution | 2015-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015921 | 406739340 | High Sign | HFTD Tier 2 | Distribution | 2015-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015922 | 406738714 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015923 | 406741556 | Riser/Conduit | HFTD Tier 3 | Distribution | 2015-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015924 | 406741684 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015925 | 406743514 | High Sign | HFTD Tier 3 | Distribution | 2015-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015926 | 406744297 | High Sign | HFTD Tier 3 | Distribution | 2015-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015927 | 406744581 | Molding | HFTD Tier 2 | Distribution | 2015-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015928 | 406745186 | Guy | HFTD Tier 3 | Distribution | 2015-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015929 | 406745206 | High Sign | HFTD Tier 3 | Distribution | 2015-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015930 | 406745800 | High Sign | HFTD Tier 2 | Distribution | 2015-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015931 | 406745811 | Molding | HFTD Tier 2 | Distribution | 2015-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015932 | 406746103 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015933 | 406747478 | Guy | HFTD Tier 3 | Distribution | 2015-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015934 | 406748254 | Guy | HFTD Tier 2 | Distribution | 2015-01-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015935 | 406748505 | Molding | HFTD Tier 3 | Distribution | 2015-01-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015936 | 406748519 | Molding | HFTD Tier 3 | Distribution | 2015-01-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015937 | 406748558 | Guy | HFTD Tier 2 | Distribution | 2015-01-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015938 | 406750028 | Guy | HFTD Tier 3 | Distribution | 2015-01-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015939 | 406750036 | High Sign | HFTD Tier 3 | Distribution | 2015-01-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015940 | 406750094 | High Sign | HFTD Tier 3 | Distribution | 2015-01-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015941 | 406750103 | High Sign | HFTD Tier 3 | Distribution | 2015-01-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015942 | 406750105 | High Sign | HFTD Tier 3 | Distribution | 2015-01-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015943 | 406750866 | Molding | HFTD Tier 3 | Distribution | 2015-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015944 | 406751561 | High Sign | HFTD Tier 2 | Distribution | 2015-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015945 | 406751778 | High Sign | HFTD Tier 2 | Distribution | 2015-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015946 | 406753697 | Molding | HFTD Tier 3 | Distribution | 2015-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015947 | 406755906 | High Sign | HFTD Tier 3 | Distribution | 2015-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015948 | 406755962 | Molding | HFTD Tier 2 | Distribution | 2015-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015949 | 406756622 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015950 | 406756910 | High Sign | HFTD Tier 2 | Distribution | 2015-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015951 | 406757149 | Molding | HFTD Tier 2 | Distribution | 2015-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015952 | 406758553 | Molding | HFTD Tier 2 | Distribution | 2015-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015953 | 406759567 | Guy | HFTD Tier 3 | Distribution | 2015-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015954 | 406762012 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015955 | 406762946 | High Sign | HFTD Tier 2 | Distribution | 2015-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015956 | 406763098 | Molding | HFTD Tier 2 | Distribution | 2015-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015957 | 406764848 | High Sign | HFTD Tier 3 | Distribution | 2015-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015958 | 406765472 | High Sign | HFTD Tier 2 | Distribution | 2015-02-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015959 | 406766088 | Molding | HFTD Tier 2 | Distribution | 2015-02-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015960 | 406766813 | High Sign | HFTD Tier 3 | Distribution | 2015-02-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015961 | 406766825 | Molding | HFTD Tier 3 | Distribution | 2015-02-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015962 | 406766830 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-02-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015963 | 406767246 | High Sign | HFTD Tier 2 | Distribution | 2015-02-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015964 | 406768929 | Guy | HFTD Tier 2 | Distribution | 2015-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015965 | 406769457 | Molding | HFTD Tier 2 | Distribution | 2015-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015966 | 406769966 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015967 | 406769967 | Guy | HFTD Tier 2 | Distribution | 2015-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015968 | 406772458 | High Sign | HFTD Tier 2 | Distribution | 2015-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015969 | 406775339 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015970 | 406776091 | Molding | HFTD Tier 2 | Distribution | 2015-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015971 | 406776173 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2015-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015972 | 406778727 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2015-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015973 | 406778829 | Molding | HFTD Tier 2 | Distribution | 2015-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015974 | 406779190 | High Sign | HFTD Tier 2 | Distribution | 2015-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015975 | 406779524 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015976 | 406779723 | High Sign | HFTD Tier 3 | Distribution | 2015-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015977 | 406779737 | High Sign | HFTD Tier 3 | Distribution | 2015-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015978 | 406781807 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015979 | 402413528 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015980 | 406782655 | Molding | HFTD Tier 3 | Distribution | 2015-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015981 | 406782664 | High Sign | HFTD Tier 3 | Distribution | 2015-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015982 | 406782930 | Molding | HFTD Tier 2 | Distribution | 2015-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015983 | 406784687 | Molding | HFTD Tier 3 | Distribution | 2015-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015984 | 406784691 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015985 | 400860123 | Riser/Conduit | HFTD Tier 3 | Distribution | 2015-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015986 | 406785311 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015987 | 406789495 | High Sign | HFTD Tier 3 | Distribution | 2015-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015988 | 406789521 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015989 | 406789804 | High Sign | HFTD Tier 3 | Distribution | 2015-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015990 | 406790140 | High Sign | HFTD Tier 3 | Distribution | 2015-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015991 | 406808652 | High Sign | HFTD Tier 3 | Distribution | 2015-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015992 | 406793044 | High Sign | HFTD Tier 2 | Distribution | 2015-02-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015993 | 406795514 | Guy | HFTD Tier 3 | Distribution | 2015-02-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015994 | 406797102 | Molding | HFTD Tier 3 | Distribution | 2015-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015995 | 406797115 | Guy | HFTD Tier 3 | Distribution | 2015-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015996 | 406797260 | Guy | HFTD Tier 3 | Distribution | 2015-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015997 | 406797316 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015998 | 406797418 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120015999 | 406797465 | Guy | HFTD Tier 3 | Distribution | 2015-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016000 | 406800102 | High Sign | HFTD Tier 2 | Distribution | 2015-02-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016001 | 406800904 | High Sign | HFTD Tier 3 | Distribution | 2015-02-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016002 | 406802781 | High Sign | HFTD Tier 3 | Distribution | 2015-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016003 | 406803073 | Molding | HFTD Tier 2 | Distribution | 2015-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016004 | 406803736 | High Sign | HFTD Tier 3 | Distribution | 2015-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016005 | 406808665 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016006 | 406808670 | Molding | HFTD Tier 3 | Distribution | 2015-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016007 | 406806153 | High Sign | HFTD Tier 2 | Distribution | 2015-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016008 | 406806297 | High Sign | HFTD Tier 3 | Distribution | 2015-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016009 | 406806500 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016010 | 406806764 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016011 | 406807028 | High Sign | HFTD Tier 3 | Distribution | 2015-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016012 | 406807311 | High Sign | HFTD Tier 2 | Distribution | 2015-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016013 | 406807330 | Molding | HFTD Tier 2 | Distribution | 2015-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016014 | 406807334 | Molding | HFTD Tier 2 | Distribution | 2015-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016015 | 406807504 | Guy | HFTD Tier 2 | Distribution | 2015-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016016 | 406808702 | High Sign | HFTD Tier 3 | Distribution | 2015-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016017 | 406814343 | Molding | HFTD Tier 3 | Distribution | 2015-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016018 | 406814344 | Guy | HFTD Tier 3 | Distribution | 2015-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016019 | 406809302 | High Sign | HFTD Tier 3 | Distribution | 2015-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016020 | 406809338 | High Sign | HFTD Tier 3 | Distribution | 2015-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016021 | 406809486 | Molding | HFTD Tier 3 | Distribution | 2015-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016022 | 406809511 | High Sign | HFTD Tier 2 | Distribution | 2015-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016023 | 406809545 | High Sign | HFTD Tier 3 | Distribution | 2015-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016024 | 406809872 | High Sign | HFTD Tier 3 | Distribution | 2015-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016025 | 406809873 | High Sign | HFTD Tier 3 | Distribution | 2015-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016026 | 406810142 | High Sign | HFTD Tier 3 | Distribution | 2015-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016027 | 406810151 | High Sign | HFTD Tier 3 | Distribution | 2015-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016028 | 406810388 | Guy | HFTD Tier 3 | Distribution | 2015-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016029 | 406810419 | High Sign | HFTD Tier 3 | Distribution | 2015-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016030 | 406810490 | High Sign | HFTD Tier 3 | Distribution | 2015-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016031 | 406810910 | High Sign | HFTD Tier 3 | Distribution | 2015-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016032 | 406816699 | Molding | HFTD Tier 3 | Distribution | 2015-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016033 | 406819425 | High Sign | HFTD Tier 3 | Distribution | 2015-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016034 | 406819450 | High Sign | HFTD Tier 3 | Distribution | 2015-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016035 | 406813922 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-02-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016036 | 406814386 | High Sign | HFTD Tier 3 | Distribution | 2015-02-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016037 | 406816051 | High Sign | HFTD Tier 3 | Distribution | 2015-02-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016038 | 406816311 | High Sign | HFTD Tier 3 | Distribution | 2015-02-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016039 | 406816788 | High Sign | HFTD Tier 3 | Distribution | 2015-02-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016040 | 406816792 | High Sign | HFTD Tier 3 | Distribution | 2015-02-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016041 | 406816802 | Molding | HFTD Tier 3 | Distribution | 2015-02-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016042 | 406816882 | High Sign | HFTD Tier 3 | Distribution | 2015-02-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016043 | 406816949 | High Sign | HFTD Tier 3 | Distribution | 2015-02-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016044 | 406817037 | High Sign | HFTD Tier 3 | Distribution | 2015-02-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016045 | 406817039 | High Sign | HFTD Tier 3 | Distribution | 2015-02-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016046 | 406820281 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016047 | 406822192 | High Sign | HFTD Tier 2 | Distribution | 2015-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016048 | 406822752 | High Sign | HFTD Tier 3 | Distribution | 2015-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016049 | 406822939 | High Sign | HFTD Tier 3 | Distribution | 2015-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016050 | 406823145 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2015-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016051 | 406826444 | Guy | HFTD Tier 3 | Distribution | 2015-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016052 | 406826455 | Guy | HFTD Tier 3 | Distribution | 2015-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016053 | 406826958 | High Sign | HFTD Tier 3 | Distribution | 2015-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016054 | 406826959 | High Sign | HFTD Tier 3 | Distribution | 2015-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016055 | 406826964 | High Sign | HFTD Tier 3 | Distribution | 2015-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016056 | 406826965 | High Sign | HFTD Tier 3 | Distribution | 2015-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016057 | 406827207 | High Sign | HFTD Tier 3 | Distribution | 2015-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016058 | 406827444 | High Sign | HFTD Tier 3 | Distribution | 2015-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016059 | 406828044 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016060 | 406829307 | High Sign | HFTD Tier 2 | Distribution | 2015-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016061 | 406831217 | Molding | HFTD Tier 3 | Distribution | 2015-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016062 | 406831237 | High Sign | HFTD Tier 3 | Distribution | 2015-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016063 | 406830543 | High Sign | HFTD Tier 3 | Distribution | 2015-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016064 | 406830546 | High Sign | HFTD Tier 3 | Distribution | 2015-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016065 | 406830596 | High Sign | HFTD Tier 3 | Distribution | 2015-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016066 | 406830923 | Molding | HFTD Tier 3 | Distribution | 2015-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016067 | 406831022 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016068 | 406831041 | High Sign | HFTD Tier 3 | Distribution | 2015-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016069 | 406831046 | Molding | HFTD Tier 3 | Distribution | 2015-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016070 | 406831150 | Guy | HFTD Tier 3 | Distribution | 2015-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016071 | 406831357 | High Sign | HFTD Tier 3 | Distribution | 2015-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016072 | 406831409 | High Sign | HFTD Tier 3 | Distribution | 2015-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016073 | 406831411 | High Sign | HFTD Tier 3 | Distribution | 2015-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016074 | 406831413 | High Sign | HFTD Tier 3 | Distribution | 2015-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016075 | 406831487 | High Sign | HFTD Tier 3 | Distribution | 2015-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016076 | 406831494 | High Sign | HFTD Tier 3 | Distribution | 2015-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016077 | 406834074 | High Sign | HFTD Tier 3 | Distribution | 2015-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016078 | 406834099 | Guy | HFTD Tier 3 | Distribution | 2015-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016079 | 406834104 | Guy | HFTD Tier 3 | Distribution | 2015-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016080 | 406834193 | High Sign | HFTD Tier 3 | Distribution | 2015-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016081 | 406834390 | High Sign | HFTD Tier 3 | Distribution | 2015-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016082 | 406834569 | High Sign | HFTD Tier 3 | Distribution | 2015-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016083 | 406837960 | Guy | HFTD Tier 3 | Distribution | 2015-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016084 | 406838021 | High Sign | HFTD Tier 3 | Distribution | 2015-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016085 | 406838270 | Guy | HFTD Tier 3 | Distribution | 2015-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016086 | 406838328 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016087 | 406838580 | Riser/Conduit | HFTD Tier 2 | Distribution | 2015-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016088 | 406840265 | High Sign | HFTD Tier 2 | Distribution | 2015-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016089 | 406840791 | Molding | HFTD Tier 2 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016090 | 406840866 | Molding | HFTD Tier 3 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016091 | 406841025 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016092 | 406841183 | High Sign | HFTD Tier 2 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016093 | 406841297 | High Sign | HFTD Tier 2 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016094 | 406841367 | High Sign | HFTD Tier 3 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016095 | 406841376 | Molding | HFTD Tier 3 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016096 | 406841467 | Molding | HFTD Tier 2 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016097 | 406841477 | Molding | HFTD Tier 2 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016098 | 406841482 | High Sign | HFTD Tier 2 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016099 | 406841503 | High Sign | HFTD Tier 2 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016100 | 406841607 | Termination | HFTD Tier 2 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016101 | 406841664 | High Sign | HFTD Tier 2 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016102 | 406841713 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016103 | 406841718 | Molding | HFTD Tier 2 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016104 | 406841748 | Guy | HFTD Tier 2 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016105 | 406841867 | Guy | HFTD Tier 2 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016106 | 406841982 | Termination | HFTD Tier 2 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016107 | 406842030 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016108 | 406842031 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016109 | 406842074 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016110 | 406842346 | Guy | HFTD Tier 3 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016111 | 406842351 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016112 | 406842900 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016113 | 406844592 | Termination | HFTD Tier 2 | Distribution | 2015-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016114 | 406844744 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016115 | 406845042 | Guy | HFTD Tier 3 | Distribution | 2015-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016116 | 406845235 | High Sign | HFTD Tier 3 | Distribution | 2015-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016117 | 406845236 | Molding | HFTD Tier 3 | Distribution | 2015-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016118 | 406845269 | Molding | HFTD Tier 2 | Distribution | 2015-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016119 | 406845945 | Molding | HFTD Tier 3 | Distribution | 2015-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016120 | 406848302 | Guy | HFTD Tier 3 | Distribution | 2015-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016121 | 406848486 | Guy | HFTD Tier 2 | Distribution | 2015-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016122 | 406850394 | Molding | HFTD Tier 3 | Distribution | 2015-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016123 | 406850412 | Molding | HFTD Tier 3 | Distribution | 2015-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016124 | 406852954 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016125 | 400771544 | Guy | HFTD Tier 3 | Distribution | 2015-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016126 | 406852603 | Insulator | HFTD Tier 3 | Distribution | 2015-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016127 | 406853190 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016128 | 406853233 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016129 | 406853634 | Riser/Conduit | HFTD Tier 3 | Distribution | 2015-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016130 | 406853676 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016131 | 406853960 | High Sign | HFTD Tier 3 | Distribution | 2015-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016132 | 406853982 | Molding | HFTD Tier 3 | Distribution | 2015-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016133 | 406853993 | High Sign | HFTD Tier 3 | Distribution | 2015-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016134 | 406854145 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016135 | 406854739 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016136 | 406856385 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016137 | 406856386 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016138 | 406862849 | Molding | HFTD Tier 3 | Distribution | 2015-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016139 | 406887779 | High Sign | HFTD Tier 2 | Distribution | 2015-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016140 | 406887782 | High Sign | HFTD Tier 2 | Distribution | 2015-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016141 | 406887783 | Molding | HFTD Tier 2 | Distribution | 2015-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016142 | 406856727 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016143 | 406856917 | High Sign | HFTD Tier 3 | Distribution | 2015-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016144 | 406857389 | Molding | HFTD Tier 3 | Distribution | 2015-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016145 | 406858347 | Molding | HFTD Tier 2 | Distribution | 2015-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016146 | 406859600 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016147 | 406887796 | High Sign | HFTD Tier 2 | Distribution | 2015-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016148 | 406860860 | Riser/Conduit | HFTD Tier 3 | Distribution | 2015-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016149 | 406860944 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016150 | 406861252 | Molding | HFTD Tier 3 | Distribution | 2015-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016151 | 406862462 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016152 | 406862468 | Molding | HFTD Tier 3 | Distribution | 2015-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016153 | 406863372 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016154 | 406863374 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016155 | 406863578 | Guy | HFTD Tier 3 | Distribution | 2015-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016156 | 406863613 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016157 | 406863878 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016158 | 406863982 | Guy | HFTD Tier 3 | Distribution | 2015-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016159 | 406869482 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016160 | 406869502 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016161 | 406869503 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016162 | 406869587 | Molding | HFTD Tier 3 | Distribution | 2015-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016163 | 406869638 | Molding | HFTD Tier 3 | Distribution | 2015-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016164 | 406870470 | High Sign | HFTD Tier 3 | Distribution | 2015-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016165 | 406873228 | High Sign | HFTD Tier 2 | Distribution | 2015-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016166 | 406873234 | High Sign | HFTD Tier 2 | Distribution | 2015-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016167 | 406873313 | Molding | HFTD Tier 3 | Distribution | 2015-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016168 | 406873899 | Molding | HFTD Tier 3 | Distribution | 2015-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016169 | 406873950 | High Sign | HFTD Tier 2 | Distribution | 2015-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016170 | 406875480 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016171 | 406876549 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016172 | 406876566 | High Sign | HFTD Tier 3 | Distribution | 2015-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016173 | 406875970 | Molding | HFTD Tier 3 | Distribution | 2015-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016174 | 406875981 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016175 | 406876543 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016176 | 406876545 | High Sign | HFTD Tier 3 | Distribution | 2015-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016177 | 406876553 | Molding | HFTD Tier 3 | Distribution | 2015-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016178 | 406876678 | High Sign | HFTD Tier 3 | Distribution | 2015-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016179 | 406877011 | High Sign | HFTD Tier 3 | Distribution | 2015-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016180 | 406877433 | Molding | HFTD Tier 3 | Distribution | 2015-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016181 | 406878870 | Molding | HFTD Tier 3 | Distribution | 2015-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016182 | 406878871 | High Sign | HFTD Tier 3 | Distribution | 2015-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016183 | 406879452 | High Sign | HFTD Tier 3 | Distribution | 2015-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016184 | 406879455 | High Sign | HFTD Tier 3 | Distribution | 2015-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016185 | 406880712 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-03-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016186 | 406884654 | High Sign | HFTD Tier 3 | Distribution | 2015-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016187 | 406884670 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016188 | 406885158 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016189 | 406885351 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016190 | 406885392 | Riser/Conduit | HFTD Tier 2 | Distribution | 2015-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016191 | 406885614 | Guy | HFTD Tier 3 | Distribution | 2015-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016192 | 406885620 | Guy | HFTD Tier 3 | Distribution | 2015-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016193 | 406886907 | Molding | HFTD Tier 3 | Distribution | 2015-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016194 | 406886917 | Pole Tag | HFTD Tier 3 | Distribution | 2015-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016195 | 406888232 | High Sign | HFTD Tier 3 | Distribution | 2015-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016196 | 406888234 | Molding | HFTD Tier 3 | Distribution | 2015-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016197 | 406888368 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016198 | 406888373 | Molding | HFTD Tier 3 | Distribution | 2015-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016199 | 406888717 | Molding | HFTD Tier 3 | Distribution | 2015-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016200 | 406889472 | Guy | HFTD Tier 2 | Distribution | 2015-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016201 | 406890285 | Guy | HFTD Tier 3 | Distribution | 2015-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016202 | 406890531 | High Sign | HFTD Tier 3 | Distribution | 2015-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016203 | 406905025 | Molding | HFTD Tier 3 | Distribution | 2015-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016204 | 406905171 | Molding | HFTD Tier 3 | Distribution | 2015-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016205 | 406891400 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016206 | 406891826 | Guy | HFTD Tier 3 | Distribution | 2015-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016207 | 406891830 | Guy | HFTD Tier 3 | Distribution | 2015-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016208 | 406891840 | Molding | HFTD Tier 3 | Distribution | 2015-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016209 | 406892163 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016210 | 406892745 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016211 | 406892764 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016212 | 406904901 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016213 | 406905990 | Guy | HFTD Tier 3 | Distribution | 2015-04-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016214 | 406906270 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-04-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016215 | 406912656 | Molding | HFTD Tier 3 | Distribution | 2015-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016216 | 406915531 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016217 | 406915979 | Molding | HFTD Tier 3 | Distribution | 2015-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016218 | 406916008 | High Sign | HFTD Tier 3 | Distribution | 2015-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016219 | 406916037 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016220 | 406916190 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016221 | 406916254 | High Sign | HFTD Tier 3 | Distribution | 2015-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016222 | 406916307 | High Sign | HFTD Tier 3 | Distribution | 2015-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016223 | 406916392 | Molding | HFTD Tier 3 | Distribution | 2015-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016224 | 406916505 | Molding | HFTD Tier 2 | Distribution | 2015-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016225 | 406916506 | High Sign | HFTD Tier 2 | Distribution | 2015-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016226 | 406916508 | Molding | HFTD Tier 3 | Distribution | 2015-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016227 | 406916518 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016228 | 406917298 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016229 | 406917403 | Molding | HFTD Tier 3 | Distribution | 2015-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016230 | 406917501 | Molding | HFTD Tier 3 | Distribution | 2015-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016231 | 406918337 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016232 | 406918338 | Molding | HFTD Tier 3 | Distribution | 2015-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016233 | 406918555 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016234 | 406919039 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016235 | 406919175 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016236 | 406919176 | Molding | HFTD Tier 3 | Distribution | 2015-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016237 | 406919507 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016238 | 406919780 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016239 | 406922762 | Molding | HFTD Tier 3 | Distribution | 2015-04-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016240 | 406923088 | High Sign | HFTD Tier 3 | Distribution | 2015-04-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016241 | 406923098 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-04-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016242 | 406923100 | Guy | HFTD Tier 3 | Distribution | 2015-04-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016243 | 406924189 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016244 | 415244315 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-04-08 | 42467 | 2 | Ignition Risk, no GO95 exception | [7 empty] | SCE | 2026 | 2
1120016245 | 406924959 | Guy | HFTD Tier 3 | Distribution | 2015-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016246 | 406924963 | High Sign | HFTD Tier 3 | Distribution | 2015-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016247 | 406924964 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016248 | 406925279 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016249 | 406925880 | Guy | HFTD Tier 2 | Distribution | 2015-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016250 | 406928083 | Molding | HFTD Tier 3 | Distribution | 2015-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016251 | 406928085 | Molding | HFTD Tier 3 | Distribution | 2015-04-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016252 | 406932180 | High Sign | HFTD Tier 3 | Distribution | 2015-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016253 | 406932191 | Guy | HFTD Tier 3 | Distribution | 2015-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016254 | 406932536 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016255 | 406932537 | Molding | HFTD Tier 3 | Distribution | 2015-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016256 | 406932569 | Molding | HFTD Tier 3 | Distribution | 2015-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016257 | 406934383 | Molding | HFTD Tier 3 | Distribution | 2015-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016258 | 406934393 | Molding | HFTD Tier 3 | Distribution | 2015-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016259 | 406934411 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016260 | 406934420 | Guy | HFTD Tier 3 | Distribution | 2015-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016261 | 406934550 | High Sign | HFTD Tier 3 | Distribution | 2015-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016262 | 406936003 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016263 | 406937892 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016264 | 406938338 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016265 | 406938570 | Molding | HFTD Tier 3 | Distribution | 2015-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016266 | 406938575 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016267 | 406939721 | High Sign | HFTD Tier 3 | Distribution | 2015-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016268 | 406940468 | High Sign | HFTD Tier 3 | Distribution | 2015-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016269 | 406940481 | High Sign | HFTD Tier 3 | Distribution | 2015-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016270 | 406940482 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016271 | 406940483 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016272 | 406940484 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016273 | 406940722 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016274 | 406941017 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016275 | 406941337 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016276 | 406941348 | Guy | HFTD Tier 3 | Distribution | 2015-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016277 | 406941361 | High Sign | HFTD Tier 3 | Distribution | 2015-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016278 | 406941372 | High Sign | HFTD Tier 3 | Distribution | 2015-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016279 | 406943777 | Molding | HFTD Tier 2 | Distribution | 2015-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016280 | 406957029 | Guy | HFTD Tier 3 | Distribution | 2015-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016281 | 406944450 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016282 | 406945306 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016283 | 406947886 | High Sign | HFTD Tier 2 | Distribution | 2015-04-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016284 | 406947574 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016285 | 406950207 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2015-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016286 | 406951000 | High Sign | HFTD Tier 2 | Distribution | 2015-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016287 | 406951001 | Molding | HFTD Tier 2 | Distribution | 2015-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016288 | 406951024 | Vis Strips | HFTD Tier 3 | Distribution | 2015-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016289 | 406951031 | Guy | HFTD Tier 2 | Distribution | 2015-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016290 | 406952178 | High Sign | HFTD Tier 2 | Distribution | 2015-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016291 | 406953006 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016292 | 406953468 | Molding | HFTD Tier 3 | Distribution | 2015-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016293 | 406953469 | Molding | HFTD Tier 3 | Distribution | 2015-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016294 | 406953478 | High Sign | HFTD Tier 3 | Distribution | 2015-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016295 | 406953483 | Molding | HFTD Tier 3 | Distribution | 2015-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016296 | 406953486 | High Sign | HFTD Tier 3 | Distribution | 2015-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016297 | 406953487 | High Sign | HFTD Tier 3 | Distribution | 2015-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016298 | 406953502 | High Sign | HFTD Tier 3 | Distribution | 2015-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016299 | 406953504 | High Sign | HFTD Tier 3 | Distribution | 2015-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016300 | 406953506 | High Sign | HFTD Tier 3 | Distribution | 2015-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016301 | 406953510 | High Sign | HFTD Tier 3 | Distribution | 2015-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016302 | 406953731 | Molding | HFTD Tier 3 | Distribution | 2015-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016303 | 406953902 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016304 | 406953955 | Guy | HFTD Tier 3 | Distribution | 2015-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016305 | 406954971 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016306 | 406955359 | High Sign | HFTD Tier 3 | Distribution | 2015-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016307 | 406955365 | High Sign | HFTD Tier 3 | Distribution | 2015-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016308 | 406955416 | Guy | HFTD Tier 3 | Distribution | 2015-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016309 | 406955442 | Molding | HFTD Tier 2 | Distribution | 2015-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016310 | 406955637 | Molding | HFTD Tier 3 | Distribution | 2015-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016311 | 406955638 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016312 | 406955645 | Molding | HFTD Tier 3 | Distribution | 2015-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016313 | 406956873 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2015-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016314 | 406957665 | Molding | HFTD Tier 3 | Distribution | 2015-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016315 | 406957751 | Molding | HFTD Tier 2 | Distribution | 2015-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016316 | 406957897 | Riser/Conduit | HFTD Tier 2 | Distribution | 2015-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016317 | 406957907 | High Sign | HFTD Tier 2 | Distribution | 2015-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016318 | 406957908 | Molding | HFTD Tier 2 | Distribution | 2015-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016319 | 406958369 | Molding | HFTD Tier 3 | Distribution | 2015-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016320 | 406959049 | High Sign | HFTD Tier 3 | Distribution | 2015-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016321 | 406959306 | Molding | HFTD Tier 3 | Distribution | 2015-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016322 | 406959652 | Guy | HFTD Tier 2 | Distribution | 2015-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016323 | 406961727 | Molding | HFTD Tier 3 | Distribution | 2015-04-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016324 | 406962804 | Guy | HFTD Tier 3 | Distribution | 2015-04-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016325 | 406962971 | Molding | HFTD Tier 2 | Distribution | 2015-04-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016326 | 406965874 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016327 | 406965882 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016328 | 406968228 | Guy | HFTD Tier 3 | Distribution | 2015-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016329 | 406968819 | Molding | HFTD Tier 3 | Distribution | 2015-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016330 | 406968822 | Guy | HFTD Tier 3 | Distribution | 2015-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016331 | 406969231 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016332 | 406969736 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016333 | 406969757 | High Sign | HFTD Tier 3 | Distribution | 2015-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016334 | 406969761 | High Sign | HFTD Tier 3 | Distribution | 2015-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016335 | 406969766 | High Sign | HFTD Tier 3 | Distribution | 2015-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016336 | 406969767 | Molding | HFTD Tier 3 | Distribution | 2015-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016337 | 406969812 | High Sign | HFTD Tier 2 | Distribution | 2015-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016338 | 406969813 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016339 | 406969978 | High Sign | HFTD Tier 2 | Distribution | 2015-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016340 | 406970167 | Guy | HFTD Tier 3 | Distribution | 2015-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016341 | 406971917 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016342 | 406971928 | Molding | HFTD Tier 3 | Distribution | 2015-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016343 | 406971929 | High Sign | HFTD Tier 3 | Distribution | 2015-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016344 | 406972994 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016345 | 406973362 | Molding | HFTD Tier 3 | Distribution | 2015-04-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016346 | 406973622 | Molding | HFTD Tier 3 | Distribution | 2015-04-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016347 | 406974071 | High Sign | HFTD Tier 3 | Distribution | 2015-04-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016348 | 406976220 | Molding | HFTD Tier 3 | Distribution | 2015-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016349 | 406976402 | Guy | HFTD Tier 2 | Distribution | 2015-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016350 | 406976929 | Guy | HFTD Tier 3 | Distribution | 2015-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016351 | 406976942 | High Sign | HFTD Tier 3 | Distribution | 2015-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016352 | 406978876 | Riser/Conduit | HFTD Tier 3 | Distribution | 2015-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016353 | 406979225 | Molding | HFTD Tier 3 | Distribution | 2015-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016354 | 406979226 | Molding | HFTD Tier 3 | Distribution | 2015-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016355 | 406981398 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016356 | 406981403 | Riser/Conduit | HFTD Tier 3 | Distribution | 2015-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016357 | 406981406 | Molding | HFTD Tier 3 | Distribution | 2015-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016358 | 406981414 | High Sign | HFTD Tier 3 | Distribution | 2015-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016359 | 406981416 | Molding | HFTD Tier 3 | Distribution | 2015-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016360 | 406981633 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016361 | 406981671 | Molding | HFTD Tier 3 | Distribution | 2015-04-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016362 | 406983080 | Molding | HFTD Tier 3 | Distribution | 2015-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016363 | 406984587 | High Sign | HFTD Tier 3 | Distribution | 2015-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016364 | 406984600 | Molding | HFTD Tier 3 | Distribution | 2015-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016365 | 406984603 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016366 | 413847958 | Guy | HFTD Tier 3 | Distribution | 2015-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016367 | 400850628 | Molding | HFTD Tier 3 | Distribution | 2015-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016368 | 406985765 | Guy | HFTD Tier 2 | Distribution | 2015-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016369 | 406985854 | Guy | HFTD Tier 2 | Distribution | 2015-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016370 | 406986706 | High Sign | HFTD Tier 2 | Distribution | 2015-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016371 | 406986825 | Guy | HFTD Tier 3 | Distribution | 2015-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016372 | 406986936 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016373 | 406986993 | High Sign | HFTD Tier 2 | Distribution | 2015-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016374 | 406987000 | High Sign | HFTD Tier 2 | Distribution | 2015-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016375 | 406987009 | Molding | HFTD Tier 3 | Distribution | 2015-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016376 | 406987013 | Guy | HFTD Tier 2 | Distribution | 2015-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016377 | 406987419 | High Sign | HFTD Tier 3 | Distribution | 2015-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016378 | 406987495 | Guy | HFTD Tier 3 | Distribution | 2015-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016379 | 406987496 | Molding | HFTD Tier 3 | Distribution | 2015-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016380 | 406987497 | Guy | HFTD Tier 3 | Distribution | 2015-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016381 | 406988265 | High Sign | HFTD Tier 2 | Distribution | 2015-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016382 | 406988945 | Molding | HFTD Tier 3 | Distribution | 2015-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016383 | 406989672 | Guy | HFTD Tier 3 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016384 | 406989712 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016385 | 406989799 | Molding | HFTD Tier 3 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016386 | 406989806 | High Sign | HFTD Tier 3 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016387 | 406989829 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016388 | 406989918 | Pole Tag | HFTD Tier 3 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016389 | 406989994 | Guy | HFTD Tier 3 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016390 | 406990084 | High Sign | HFTD Tier 3 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016391 | 406990107 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016392 | 406990168 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016393 | 406990169 | Guy | HFTD Tier 2 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016394 | 406990180 | High Sign | HFTD Tier 2 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016395 | 406990735 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016396 | 406990888 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016397 | 406991451 | Guy | HFTD Tier 3 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016398 | 406992650 | Molding | HFTD Tier 2 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016399 | 406992800 | Molding | HFTD Tier 2 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016400 | 406992814 | Molding | HFTD Tier 2 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016401 | 406992910 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016402 | 406993201 | High Sign | HFTD Tier 3 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016403 | 406993244 | High Sign | HFTD Tier 2 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016404 | 406996655 | High Sign | HFTD Tier 2 | Distribution | 2015-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016405 | 406993634 | High Sign | HFTD Tier 3 | Distribution | 2015-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016406 | 406993785 | High Sign | HFTD Tier 2 | Distribution | 2015-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016407 | 406994719 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016408 | 406994957 | High Sign | HFTD Tier 3 | Distribution | 2015-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016409 | 406995390 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016410 | 406996362 | High Sign | HFTD Tier 2 | Distribution | 2015-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016411 | 406996883 | High Sign | HFTD Tier 3 | Distribution | 2015-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016412 | 406996890 | High Sign | HFTD Tier 3 | Distribution | 2015-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016413 | 406997020 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016414 | 406997308 | Guy | HFTD Tier 3 | Distribution | 2015-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016415 | 415052926 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-05-06 | 42495 | 2 | Ignition Risk, no GO95 exception | [7 empty] | SCE | 2026 | 2
1120016416 | 406997467 | High Sign | HFTD Tier 2 | Distribution | 2015-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016417 | 406997490 | High Sign | HFTD Tier 3 | Distribution | 2015-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016418 | 406997702 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016419 | 406997704 | Molding | HFTD Tier 3 | Distribution | 2015-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016420 | 406997712 | High Sign | HFTD Tier 3 | Distribution | 2015-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016421 | 406998074 | Guy | HFTD Tier 2 | Distribution | 2015-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016422 | 406998355 | Riser/Conduit | HFTD Tier 2 | Distribution | 2015-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016423 | 406998398 | Molding | HFTD Tier 2 | Distribution | 2015-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016424 | 406998828 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016425 | 406998889 | Riser/Conduit | HFTD Tier 3 | Distribution | 2015-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016426 | 406998891 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016427 | 406998984 | High Sign | HFTD Tier 2 | Distribution | 2015-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016428 | 407000260 | High Sign | HFTD Tier 2 | Distribution | 2015-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016429 | 407000262 | High Sign | HFTD Tier 2 | Distribution | 2015-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016430 | 407000892 | High Sign | HFTD Tier 2 | Distribution | 2015-05-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016431 | 407005118 | Guy | HFTD Tier 2 | Distribution | 2015-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016432 | 407005133 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016433 | 407005466 | High Sign | HFTD Tier 3 | Distribution | 2015-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016434 | 407006227 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016435 | 407008044 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016436 | 407008259 | Guy | HFTD Tier 3 | Distribution | 2015-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016437 | 407008755 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016438 | 407008907 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016439 | 407009695 | Guy | HFTD Tier 2 | Distribution | 2015-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016440 | 407011314 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016441 | 407011394 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016442 | 407011808 | Molding | HFTD Tier 3 | Distribution | 2015-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016443 | 407011817 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016444 | 407012338 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-05-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016445 | 407012397 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-05-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016446 | 407013680 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-05-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016447 | 407013711 | Molding | HFTD Tier 3 | Distribution | 2015-05-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016448 | 407014424 | Molding | HFTD Tier 2 | Distribution | 2015-05-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016449 | 407016524 | High Sign | HFTD Tier 3 | Distribution | 2015-05-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016450 | 407022511 | Molding | HFTD Tier 3 | Distribution | 2015-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016451 | 407022962 | Insulator | HFTD Tier 3 | Distribution | 2015-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016452 | 407023052 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016453 | 407026403 | Guy | HFTD Tier 3 | Distribution | 2015-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016454 | 407026423 | Guy | HFTD Tier 3 | Distribution | 2015-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016455 | 407026589 | High Sign | HFTD Tier 2 | Distribution | 2015-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016456 | 407026802 | Molding | HFTD Tier 2 | Distribution | 2015-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016457 | 407031534 | High Sign | HFTD Tier 2 | Distribution | 2015-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016458 | 403012120 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016459 | 407035570 | Cutout/Fuse | HFTD Tier 3 | Distribution | 2015-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016460 | 407035600 | High Sign | HFTD Tier 3 | Distribution | 2015-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016461 | 407036052 | Molding | HFTD Tier 3 | Distribution | 2015-05-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016462 | 407038406 | High Sign | HFTD Tier 3 | Distribution | 2015-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016463 | 407041042 | Guy | HFTD Tier 3 | Distribution | 2015-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016464 | 407041146 | Guy | HFTD Tier 3 | Distribution | 2015-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016465 | 407041731 | Guy | HFTD Tier 3 | Distribution | 2015-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016466 | 407042356 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016467 | 407043400 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016468 | 407043048 | Molding | HFTD Tier 3 | Distribution | 2015-05-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016469 | 407044259 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-05-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016470 | 407046491 | Guy | HFTD Tier 3 | Distribution | 2015-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016471 | 407047298 | Guy | HFTD Tier 3 | Distribution | 2015-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016472 | 407047426 | High Sign | HFTD Tier 2 | Distribution | 2015-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016473 | 407047613 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-05-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016474 | 407050023 | High Sign | HFTD Tier 2 | Distribution | 2015-05-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016475 | 407051143 | High Sign | HFTD Tier 3 | Distribution | 2015-05-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016476 | 407052386 | Riser/Conduit | HFTD Tier 3 | Distribution | 2015-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016477 | 407052405 | Molding | HFTD Tier 3 | Distribution | 2015-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016478 | 407052999 | Molding | HFTD Tier 3 | Distribution | 2015-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016479 | 407053081 | High Sign | HFTD Tier 3 | Distribution | 2015-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016480 | 407053272 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016481 | 407053340 | Guy | HFTD Tier 3 | Distribution | 2015-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016482 | 407054436 | Guy | HFTD Tier 3 | Distribution | 2015-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016483 | 407054602 | Guy | HFTD Tier 3 | Distribution | 2015-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016484 | 407055480 | Molding | HFTD Tier 3 | Distribution | 2015-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016485 | 407055767 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016486 | 407056890 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016487 | 407057878 | High Sign | HFTD Tier 3 | Distribution | 2015-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016488 | 407058542 | Molding | HFTD Tier 3 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016489 | 407058735 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016490 | 407058796 | High Sign | HFTD Tier 2 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016491 | 407058836 | High Sign | HFTD Tier 2 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016492 | 407058890 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016493 | 407058893 | High Sign | HFTD Tier 2 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016494 | 407059238 | Guy | HFTD Tier 3 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016495 | 407059259 | Molding | HFTD Tier 3 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016496 | 407059484 | Guy | HFTD Tier 3 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016497 | 407059519 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016498 | 407059638 | Molding | HFTD Tier 3 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016499 | 407059656 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016500 | 407059745 | Guy | HFTD Tier 3 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016501 | 407059798 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016502 | 407059887 | High Sign | HFTD Tier 3 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016503 | 407059908 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016504 | 407059945 | Molding | HFTD Tier 3 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016505 | 407060099 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016506 | 407060100 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016507 | 407060216 | Guy | HFTD Tier 3 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016508 | 407060485 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016509 | 407060489 | High Sign | HFTD Tier 2 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016510 | 407060688 | High Sign | HFTD Tier 2 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016511 | 407060920 | Molding | HFTD Tier 2 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016512 | 407061466 | High Sign | HFTD Tier 2 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016513 | 407061663 | High Sign | HFTD Tier 2 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016514 | 407061695 | High Sign | HFTD Tier 2 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016515 | 407061737 | High Sign | HFTD Tier 2 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016516 | 407061738 | High Sign | HFTD Tier 2 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016517 | 407061750 | High Sign | HFTD Tier 2 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016518 | 407061751 | High Sign | HFTD Tier 2 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016519 | 407061752 | High Sign | HFTD Tier 2 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016520 | 407061761 | High Sign | HFTD Tier 2 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016521 | 407061768 | High Sign | HFTD Tier 2 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016522 | 407061770 | High Sign | HFTD Tier 2 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016523 | 407061811 | High Sign | HFTD Tier 2 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016524 | 407062272 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-06-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016525 | 407062374 | High Sign | HFTD Tier 2 | Distribution | 2015-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016526 | 407062502 | Insulator | HFTD Tier 3 | Distribution | 2015-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016527 | 407062518 | High Sign | HFTD Tier 3 | Distribution | 2015-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016528 | 407062529 | High Sign | HFTD Tier 3 | Distribution | 2015-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016529 | 407063309 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016530 | 407063417 | Molding | HFTD Tier 2 | Distribution | 2015-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016531 | 407063424 | High Sign | HFTD Tier 3 | Distribution | 2015-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016532 | 407063823 | Guy | HFTD Tier 3 | Distribution | 2015-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016533 | 407063864 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016534 | 407063989 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016535 | 407064141 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016536 | 407064343 | High Sign | HFTD Tier 3 | Distribution | 2015-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016537 | 407066081 | High Sign | HFTD Tier 3 | Distribution | 2015-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016538 | 407066102 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016539 | 407066193 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016540 | 407066328 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016541 | 407066423 | Molding | HFTD Tier 3 | Distribution | 2015-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016542 | 407069930 | Guy | HFTD Tier 3 | Distribution | 2015-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016543 | 407070035 | Molding | HFTD Tier 2 | Distribution | 2015-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016544 | 407071119 | High Sign | HFTD Tier 2 | Distribution | 2015-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016545 | 407071425 | High Sign | HFTD Tier 2 | Distribution | 2015-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016546 | 407071576 | High Sign | HFTD Tier 2 | Distribution | 2015-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016547 | 407072823 | Guy | HFTD Tier 2 | Distribution | 2015-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016548 | 407072835 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016549 | 407072842 | Guy | HFTD Tier 2 | Distribution | 2015-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016550 | 407072845 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016551 | 407072855 | Guy | HFTD Tier 2 | Distribution | 2015-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016552 | 407072864 | High Sign | HFTD Tier 2 | Distribution | 2015-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016553 | 407074869 | Guy | HFTD Tier 3 | Distribution | 2015-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016554 | 407074874 | Molding | HFTD Tier 3 | Distribution | 2015-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016555 | 407074971 | Guy | HFTD Tier 3 | Distribution | 2015-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016556 | 407074972 | High Sign | HFTD Tier 3 | Distribution | 2015-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016557 | 407076117 | Molding | HFTD Tier 3 | Distribution | 2015-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016558 | 407076653 | Guy | HFTD Tier 3 | Distribution | 2015-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016559 | 407077664 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016560 | 407077865 | Guy | HFTD Tier 3 | Distribution | 2015-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016561 | 407078073 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016562 | 407078151 | High Sign | HFTD Tier 3 | Distribution | 2015-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016563 | 407078553 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016564 | 407079747 | High Sign | HFTD Tier 3 | Distribution | 2015-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016565 | 407079748 | High Sign | HFTD Tier 3 | Distribution | 2015-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016566 | 407079785 | High Sign | HFTD Tier 3 | Distribution | 2015-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016567 | 407079891 | High Sign | HFTD Tier 3 | Distribution | 2015-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016568 | 407080586 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016569 | 407080684 | Molding | HFTD Tier 3 | Distribution | 2015-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016570 | 407081699 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016571 | 407082865 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2015-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016572 | 407083397 | Guy | HFTD Tier 3 | Distribution | 2015-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016573 | 407083442 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016574 | 407083461 | Molding | HFTD Tier 3 | Distribution | 2015-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016575 | 407084698 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016576 | 407084705 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016577 | 407086347 | Riser/Conduit | HFTD Tier 3 | Distribution | 2015-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016578 | 407086485 | Molding | HFTD Tier 3 | Distribution | 2015-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016579 | 407086531 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016580 | 407086656 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016581 | 407087322 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016582 | 407087623 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016583 | 407087715 | High Sign | HFTD Tier 3 | Distribution | 2015-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016584 | 407087760 | High Sign | HFTD Tier 3 | Distribution | 2015-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016585 | 407087774 | High Sign | HFTD Tier 2 | Distribution | 2015-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016586 | 407088740 | Guy | HFTD Tier 3 | Distribution | 2015-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016587 | 407099886 | Guy | HFTD Tier 3 | Distribution | 2015-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016588 | 407099937 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016589 | 407089662 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016590 | 407089687 | Molding | HFTD Tier 3 | Distribution | 2015-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016591 | 407089889 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016592 | 407089968 | Guy | HFTD Tier 3 | Distribution | 2015-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016593 | 407090001 | Guy | HFTD Tier 3 | Distribution | 2015-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016594 | 407090239 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016595 | 407090610 | Molding | HFTD Tier 2 | Distribution | 2015-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016596 | 407090701 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016597 | 407092053 | Ground | HFTD Tier 3 | Distribution | 2015-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016598 | 407099977 | High Sign | HFTD Tier 2 | Distribution | 2015-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016599 | 407092553 | High Sign | HFTD Tier 3 | Distribution | 2015-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016600 | 407092646 | Molding | HFTD Tier 3 | Distribution | 2015-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016601 | 407092673 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016602 | 407092696 | High Sign | HFTD Tier 3 | Distribution | 2015-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016603 | 407092979 | High Sign | HFTD Tier 3 | Distribution | 2015-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016604 | 407093092 | Molding | HFTD Tier 3 | Distribution | 2015-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016605 | 407095303 | Guy | HFTD Tier 3 | Distribution | 2015-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016606 | 407096011 | Molding | HFTD Tier 2 | Distribution | 2015-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016607 | 407100098 | Molding | HFTD Tier 3 | Distribution | 2015-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016608 | 407096515 | Guy | HFTD Tier 3 | Distribution | 2015-06-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016609 | 415052923 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-06-18 | 42538 | 2 | Ignition Risk, no GO95 exception | [7 empty] | SCE | 2026 | 2
1120016610 | 407100452 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016611 | 407100500 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016612 | 407100649 | Molding | HFTD Tier 2 | Distribution | 2015-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016613 | 407100674 | High Sign | HFTD Tier 2 | Distribution | 2015-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016614 | 407101524 | Molding | HFTD Tier 2 | Distribution | 2015-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016615 | 407104634 | Guy | HFTD Tier 2 | Distribution | 2015-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016616 | 407105962 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016617 | 407106077 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016618 | 407106177 | Guy | HFTD Tier 3 | Distribution | 2015-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016619 | 407106732 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016620 | 407106913 | High Sign | HFTD Tier 3 | Distribution | 2015-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016621 | 407106941 | High Sign | HFTD Tier 3 | Distribution | 2015-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016622 | 407106950 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016623 | 407108016 | Molding | HFTD Tier 3 | Distribution | 2015-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016624 | 407109125 | Molding | HFTD Tier 3 | Distribution | 2015-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016625 | 407109284 | Molding | HFTD Tier 3 | Distribution | 2015-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016626 | 407109286 | High Sign | HFTD Tier 2 | Distribution | 2015-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016627 | 407109325 | Molding | HFTD Tier 3 | Distribution | 2015-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016628 | 407109792 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016629 | 407109827 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016630 | 407115691 | High Sign | HFTD Tier 2 | Distribution | 2015-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016631 | 407113471 | Molding | HFTD Tier 3 | Distribution | 2015-06-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016632 | 407113935 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-06-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016633 | 407115090 | High Sign | HFTD Tier 3 | Distribution | 2015-06-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016634 | 407118017 | Molding | HFTD Tier 3 | Distribution | 2015-06-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016635 | 407118332 | Molding | HFTD Tier 3 | Distribution | 2015-06-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016636 | 407116270 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-06-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016637 | 407116863 | Molding | HFTD Tier 2 | Distribution | 2015-06-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016638 | 407116912 | High Sign | HFTD Tier 3 | Distribution | 2015-06-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016639 | 407117342 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-06-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016640 | 407117800 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-06-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016641 | 407117801 | Molding | HFTD Tier 2 | Distribution | 2015-06-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016642 | 407119096 | High Sign | HFTD Tier 3 | Distribution | 2015-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016643 | 407119494 | Molding | HFTD Tier 3 | Distribution | 2015-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016644 | 407119671 | High Sign | HFTD Tier 3 | Distribution | 2015-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016645 | 407122217 | Guy | HFTD Tier 2 | Distribution | 2015-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016646 | 407122529 | Molding | HFTD Tier 2 | Distribution | 2015-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016647 | 407123721 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016648 | 407125082 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016649 | 407125850 | High Sign | HFTD Tier 3 | Distribution | 2015-06-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016650 | 407126413 | High Sign | HFTD Tier 2 | Distribution | 2015-06-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016651 | 407128793 | High Sign | HFTD Tier 2 | Distribution | 2015-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016652 | 407129897 | Molding | HFTD Tier 2 | Distribution | 2015-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016653 | 407133374 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-07-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016654 | 407134128 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-07-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016655 | 407134348 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-07-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016656 | 407134449 | Guy | HFTD Tier 2 | Distribution | 2015-07-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016657 | 407134456 | Guy | HFTD Tier 2 | Distribution | 2015-07-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016658 | 407134476 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-07-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016659 | 407139119 | High Sign | HFTD Tier 3 | Distribution | 2015-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016660 | 407139482 | High Sign | HFTD Tier 3 | Distribution | 2015-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016661 | 407139559 | High Sign | HFTD Tier 3 | Distribution | 2015-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016662 | 407139585 | Guy | HFTD Tier 3 | Distribution | 2015-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016663 | 407139609 | Molding | HFTD Tier 3 | Distribution | 2015-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016664 | 407139620 | Guy | HFTD Tier 3 | Distribution | 2015-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016665 | 407140060 | Guy | HFTD Tier 3 | Distribution | 2015-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016666 | 407140064 | Streetlight | HFTD Tier 3 | Distribution | 2015-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016667 | 407140361 | Molding | HFTD Tier 2 | Distribution | 2015-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016668 | 407144795 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016669 | 407144831 | Molding | HFTD Tier 3 | Distribution | 2015-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016670 | 407141968 | High Sign | HFTD Tier 3 | Distribution | 2015-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016671 | 407142168 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016672 | 407142184 | Guy | HFTD Tier 2 | Distribution | 2015-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016673 | 407142292 | High Sign | HFTD Tier 3 | Distribution | 2015-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016674 | 407142398 | Guy | HFTD Tier 3 | Distribution | 2015-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016675 | 407142414 | High Sign | HFTD Tier 2 | Distribution | 2015-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016676 | 407142421 | Molding | HFTD Tier 2 | Distribution | 2015-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016677 | 407142486 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016678 | 407142489 | Molding | HFTD Tier 2 | Distribution | 2015-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016679 | 407142648 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016680 | 407143348 | High Sign | HFTD Tier 2 | Distribution | 2015-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016681 | 407144786 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016682 | 407144837 | Molding | HFTD Tier 3 | Distribution | 2015-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016683 | 407145028 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016684 | 407146465 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016685 | 407146571 | High Sign | HFTD Tier 3 | Distribution | 2015-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016686 | 407146792 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016687 | 407150651 | Molding | HFTD Tier 3 | Distribution | 2015-07-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016688 | 407155432 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-07-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016689 | 407158549 | Guy | HFTD Tier 2 | Distribution | 2015-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016690 | 407160487 | Molding | HFTD Tier 3 | Distribution | 2015-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016691 | 407160643 | Guy | HFTD Tier 3 | Distribution | 2015-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016692 | 407161029 | Guy | HFTD Tier 3 | Distribution | 2015-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016693 | 407161045 | High Sign | HFTD Tier 2 | Distribution | 2015-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016694 | 407162136 | High Sign | HFTD Tier 2 | Distribution | 2015-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016695 | 407165145 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016696 | 407169398 | Molding | HFTD Tier 3 | Distribution | 2015-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016697 | 407166464 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016698 | 407167335 | High Sign | HFTD Tier 3 | Distribution | 2015-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016699 | 407167353 | Guy | HFTD Tier 3 | Distribution | 2015-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016700 | 407167532 | High Sign | HFTD Tier 3 | Distribution | 2015-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016701 | 407168554 | High Sign | HFTD Tier 3 | Distribution | 2015-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016702 | 407168842 | High Sign | HFTD Tier 2 | Distribution | 2015-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016703 | 407168884 | Molding | HFTD Tier 2 | Distribution | 2015-07-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016704 | 407169907 | Guy | HFTD Tier 3 | Distribution | 2015-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016705 | 407169956 | Guy | HFTD Tier 3 | Distribution | 2015-07-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016706 | 407175248 | High Sign | HFTD Tier 3 | Distribution | 2015-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016707 | 407176969 | High Sign | HFTD Tier 2 | Distribution | 2015-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016708 | 407177081 | High Sign | HFTD Tier 2 | Distribution | 2015-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016709 | 407176253 | Molding | HFTD Tier 3 | Distribution | 2015-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016710 | 407176355 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016711 | 407176580 | High Sign | HFTD Tier 2 | Distribution | 2015-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016712 | 407176697 | Guy | HFTD Tier 2 | Distribution | 2015-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016713 | 407176835 | Guy | HFTD Tier 2 | Distribution | 2015-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016714 | 407176870 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016715 | 407178208 | Guy | HFTD Tier 3 | Distribution | 2015-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016716 | 407178209 | High Sign | HFTD Tier 3 | Distribution | 2015-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016717 | 407178309 | Guy | HFTD Tier 3 | Distribution | 2015-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016718 | 407178332 | Guy | HFTD Tier 3 | Distribution | 2015-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016719 | 407178342 | Guy | HFTD Tier 3 | Distribution | 2015-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016720 | 407178352 | Guy | HFTD Tier 3 | Distribution | 2015-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016721 | 407178360 | Guy | HFTD Tier 3 | Distribution | 2015-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016722 | 407178365 | High Sign | HFTD Tier 3 | Distribution | 2015-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016723 | 407178372 | Guy | HFTD Tier 3 | Distribution | 2015-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016724 | 407178376 | Guy | HFTD Tier 3 | Distribution | 2015-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016725 | 407179727 | High Sign | HFTD Tier 3 | Distribution | 2015-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016726 | 407179896 | Guy | HFTD Tier 3 | Distribution | 2015-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016727 | 407179897 | High Sign | HFTD Tier 3 | Distribution | 2015-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016728 | 407179937 | High Sign | HFTD Tier 2 | Distribution | 2015-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016729 | 407179991 | High Sign | HFTD Tier 3 | Distribution | 2015-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016730 | 407180010 | Molding | HFTD Tier 2 | Distribution | 2015-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016731 | 407180055 | Molding | HFTD Tier 2 | Distribution | 2015-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016732 | 407180287 | Molding | HFTD Tier 2 | Distribution | 2015-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016733 | 407181738 | Molding | HFTD Tier 2 | Distribution | 2015-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016734 | 407182626 | Guy | HFTD Tier 3 | Distribution | 2015-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016735 | 407183768 | Pole step | HFTD Tier 3 | Distribution | 2015-07-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016736 | 407190442 | Guy | HFTD Tier 3 | Distribution | 2015-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016737 | 407196215 | Molding | HFTD Tier 2 | Distribution | 2015-07-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016738 | 407197804 | Guy | HFTD Tier 2 | Distribution | 2015-07-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016739 | 407201002 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016740 | 407201030 | High Sign | HFTD Tier 2 | Distribution | 2015-07-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016741 | 407202861 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016742 | 407203691 | High Sign | HFTD Tier 3 | Distribution | 2015-07-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016743 | 407205490 | Molding | HFTD Tier 3 | Distribution | 2015-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016744 | 407206084 | Molding | HFTD Tier 3 | Distribution | 2015-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016745 | 407206995 | Guy | HFTD Tier 3 | Distribution | 2015-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016746 | 407213285 | Guy | HFTD Tier 3 | Distribution | 2015-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016747 | 407213323 | High Sign | HFTD Tier 3 | Distribution | 2015-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016748 | 407213324 | High Sign | HFTD Tier 3 | Distribution | 2015-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016749 | 407213334 | Guy | HFTD Tier 3 | Distribution | 2015-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016750 | 407213344 | Guy | HFTD Tier 3 | Distribution | 2015-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016751 | 407213350 | Molding | HFTD Tier 3 | Distribution | 2015-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016752 | 407213360 | Guy | HFTD Tier 3 | Distribution | 2015-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016753 | 407214528 | Molding | HFTD Tier 3 | Distribution | 2015-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016754 | 407215472 | High Sign | HFTD Tier 2 | Distribution | 2015-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016755 | 407217251 | High Sign | HFTD Tier 3 | Distribution | 2015-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016756 | 407223646 | Guy | HFTD Tier 2 | Distribution | 2015-08-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016757 | 407223695 | High Sign | HFTD Tier 2 | Distribution | 2015-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016758 | 407223713 | High Sign | HFTD Tier 2 | Distribution | 2015-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016759 | 407223721 | High Sign | HFTD Tier 2 | Distribution | 2015-08-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016760 | 407224952 | Molding | HFTD Tier 2 | Distribution | 2015-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016761 | 407224955 | Riser/Conduit | HFTD Tier 2 | Distribution | 2015-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016762 | 407227918 | High Sign | HFTD Tier 2 | Distribution | 2015-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016763 | 407230539 | High Sign | HFTD Tier 2 | Distribution | 2015-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016764 | 407230628 | High Sign | HFTD Tier 2 | Distribution | 2015-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016765 | 407232824 | Molding | HFTD Tier 3 | Distribution | 2015-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016766 | 407232944 | High Sign | HFTD Tier 2 | Distribution | 2015-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016767 | 407232953 | High Sign | HFTD Tier 2 | Distribution | 2015-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016768 | 407234198 | High Sign | HFTD Tier 2 | Distribution | 2015-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016769 | 407234238 | Molding | HFTD Tier 2 | Distribution | 2015-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016770 | 407234261 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016771 | 407234321 | High Sign | HFTD Tier 2 | Distribution | 2015-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016772 | 407234330 | High Sign | HFTD Tier 2 | Distribution | 2015-08-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016773 | 407242972 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016774 | 407243054 | High Sign | HFTD Tier 2 | Distribution | 2015-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016775 | 407244163 | High Sign | HFTD Tier 2 | Distribution | 2015-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016776 | 407245510 | Bond | HFTD Tier 3 | Distribution | 2015-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016777 | 407248042 | High Sign | HFTD Tier 2 | Distribution | 2015-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016778 | 407250998 | Guy | HFTD Tier 2 | Distribution | 2015-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016779 | 407251984 | Pole step | HFTD Tier 2 | Distribution | 2015-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016780 | 407252059 | Molding | HFTD Tier 2 | Distribution | 2015-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016781 | 407252838 | Vis Strips | HFTD Tier 2 | Distribution | 2015-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016782 | 407253222 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016783 | 407261363 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-08-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016784 | 407259797 | Bond | HFTD Tier 3 | Distribution | 2015-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016785 | 407260158 | Pole step | HFTD Tier 3 | Distribution | 2015-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016786 | 407260203 | Pole step | HFTD Tier 3 | Distribution | 2015-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016787 | 407260216 | Guy | HFTD Tier 3 | Distribution | 2015-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016788 | 407260983 | Pole step | HFTD Tier 3 | Distribution | 2015-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016789 | 407264556 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016790 | 407261937 | Molding | HFTD Tier 3 | Distribution | 2015-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016791 | 407262367 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016792 | 407262898 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016793 | 407267855 | Molding | HFTD Tier 3 | Distribution | 2015-08-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016794 | 407268716 | High Sign | HFTD Tier 2 | Distribution | 2015-08-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016795 | 407268946 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-08-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016796 | 407272424 | Riser/Conduit | HFTD Tier 3 | Distribution | 2015-08-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016797 | 407276691 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-08-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016798 | 407279075 | Guy | HFTD Tier 3 | Distribution | 2015-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016799 | 407279693 | Molding | HFTD Tier 3 | Distribution | 2015-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016800 | 407279851 | ID Markings | HFTD Tier 3 | Distribution | 2015-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016801 | 407280206 | High Sign | HFTD Tier 2 | Distribution | 2015-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016802 | 407280245 | Guy | HFTD Tier 3 | Distribution | 2015-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016803 | 407281546 | Molding | HFTD Tier 3 | Distribution | 2015-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016804 | 407281870 | Molding | HFTD Tier 3 | Distribution | 2015-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016805 | 407282389 | High Sign | HFTD Tier 2 | Distribution | 2015-09-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016806 | 407282394 | Molding | HFTD Tier 2 | Distribution | 2015-09-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016807 | 407282906 | Guy | HFTD Tier 3 | Distribution | 2015-09-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016808 | 407283742 | Guy | HFTD Tier 3 | Distribution | 2015-09-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016809 | 407286796 | Guy | HFTD Tier 3 | Distribution | 2015-09-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016810 | 407286896 | Vis Strips | HFTD Tier 3 | Distribution | 2015-09-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016811 | 407287136 | Molding | HFTD Tier 3 | Distribution | 2015-09-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016812 | 407290565 | Pole Tag | HFTD Tier 3 | Distribution | 2015-09-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016813 | 407293720 | High Sign | HFTD Tier 2 | Distribution | 2015-09-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016814 | 407297739 | Bond | HFTD Tier 3 | Distribution | 2015-09-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016815 | 407299959 | Bond | HFTD Tier 3 | Distribution | 2015-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016816 | 407301209 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016817 | 407301230 | Guy | HFTD Tier 3 | Distribution | 2015-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016818 | 407302307 | Molding | HFTD Tier 3 | Distribution | 2015-09-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016819 | 407304969 | High Sign | HFTD Tier 3 | Distribution | 2015-09-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016820 | 407305027 | High Sign | HFTD Tier 3 | Distribution | 2015-09-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016821 | 407314843 | Molding | HFTD Tier 2 | Distribution | 2015-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016822 | 407317701 | High Sign | HFTD Tier 2 | Distribution | 2015-09-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016823 | 407320005 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-09-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016824 | 407320032 | Guy | HFTD Tier 3 | Distribution | 2015-09-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016825 | 407320458 | Bond | HFTD Tier 3 | Distribution | 2015-09-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016826 | 407320631 | Molding | HFTD Tier 3 | Distribution | 2015-09-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016827 | 407320934 | Bond | HFTD Tier 3 | Distribution | 2015-09-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016828 | 407325150 | Molding | HFTD Tier 3 | Distribution | 2015-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016829 | 407325409 | Pole Tag | HFTD Tier 3 | Distribution | 2015-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016830 | 407325665 | High Sign | HFTD Tier 3 | Distribution | 2015-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016831 | 407326508 | High Sign | HFTD Tier 3 | Distribution | 2015-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016832 | 407332590 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-09-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016833 | 407342495 | High Sign | HFTD Tier 3 | Distribution | 2015-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016834 | 407343936 | High Sign | HFTD Tier 2 | Distribution | 2015-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016835 | 407343940 | Pole Tag | HFTD Tier 3 | Distribution | 2015-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016836 | 407343998 | Molding | HFTD Tier 2 | Distribution | 2015-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016837 | 407344293 | High Sign | HFTD Tier 2 | Distribution | 2015-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016838 | 407346172 | Pole Tag | HFTD Tier 3 | Distribution | 2015-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016839 | 407346906 | Molding | HFTD Tier 2 | Distribution | 2015-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016840 | 407346916 | Guy | HFTD Tier 2 | Distribution | 2015-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016841 | 407348268 | Guy | HFTD Tier 2 | Distribution | 2015-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016842 | 407350472 | Bond | HFTD Tier 3 | Distribution | 2015-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016843 | 407351337 | Guy | HFTD Tier 2 | Distribution | 2015-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016844 | 407351440 | Guy | HFTD Tier 2 | Distribution | 2015-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016845 | 407352452 | High Sign | HFTD Tier 2 | Distribution | 2015-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016846 | 407353708 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-10-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016847 | 407358074 | High Sign | HFTD Tier 2 | Distribution | 2015-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016848 | 407358099 | High Sign | HFTD Tier 2 | Distribution | 2015-10-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016849 | 407363837 | Molding | HFTD Tier 2 | Distribution | 2015-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016850 | 407364416 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016851 | 407367808 | Molding | HFTD Tier 2 | Distribution | 2015-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016852 | 407367817 | Molding | HFTD Tier 2 | Distribution | 2015-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016853 | 407367850 | Molding | HFTD Tier 2 | Distribution | 2015-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016854 | 407368742 | High Sign | HFTD Tier 3 | Distribution | 2015-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016855 | 407385938 | Molding | HFTD Tier 3 | Distribution | 2015-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016856 | 407383240 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016857 | 407383250 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016858 | 407384442 | High Sign | HFTD Tier 2 | Distribution | 2015-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016859 | 407386023 | Molding | HFTD Tier 3 | Distribution | 2015-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016860 | 407386070 | Molding | HFTD Tier 3 | Distribution | 2015-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016861 | 407386078 | High Sign | HFTD Tier 2 | Distribution | 2015-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016862 | 407386138 | High Sign | HFTD Tier 2 | Distribution | 2015-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016863 | 407386146 | High Sign | HFTD Tier 2 | Distribution | 2015-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016864 | 407386154 | High Sign | HFTD Tier 2 | Distribution | 2015-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016865 | 407386190 | High Sign | HFTD Tier 2 | Distribution | 2015-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016866 | 407386409 | Insulator | HFTD Tier 3 | Distribution | 2015-10-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016867 | 407388704 | Molding | HFTD Tier 3 | Distribution | 2015-10-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016868 | 407389395 | Guy | HFTD Tier 2 | Distribution | 2015-10-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016869 | 407389466 | High Sign | HFTD Tier 3 | Distribution | 2015-10-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016870 | 407390103 | Molding | HFTD Tier 2 | Distribution | 2015-10-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016871 | 407390717 | Molding | HFTD Tier 2 | Distribution | 2015-10-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016872 | 407392538 | Molding | HFTD Tier 2 | Distribution | 2015-10-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016873 | 407392563 | Molding | HFTD Tier 2 | Distribution | 2015-10-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016874 | 407394143 | Molding | HFTD Tier 2 | Distribution | 2015-10-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016875 | 407394655 | Guy | HFTD Tier 2 | Distribution | 2015-10-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016876 | 407398395 | Molding | HFTD Tier 3 | Distribution | 2015-10-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016877 | 407398796 | Molding | HFTD Tier 3 | Distribution | 2015-10-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016878 | 407400039 | High Sign | HFTD Tier 3 | Distribution | 2015-10-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016879 | 407403213 | Molding | HFTD Tier 3 | Distribution | 2015-10-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016880 | 407403250 | Molding | HFTD Tier 3 | Distribution | 2015-10-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016881 | 407402993 | High Sign | HFTD Tier 2 | Distribution | 2015-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016882 | 407403959 | Guy | HFTD Tier 3 | Distribution | 2015-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016883 | 407408550 | Guy | HFTD Tier 3 | Distribution | 2015-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016884 | 407408860 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016885 | 407409744 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-10-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016886 | 407411750 | Guy | HFTD Tier 3 | Distribution | 2015-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016887 | 407411757 | High Sign | HFTD Tier 2 | Distribution | 2015-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016888 | 407412004 | Molding | HFTD Tier 3 | Distribution | 2015-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016889 | 407412320 | Guy | HFTD Tier 3 | Distribution | 2015-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016890 | 407414745 | High Sign | HFTD Tier 3 | Distribution | 2015-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016891 | 407415888 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-10-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016892 | 407418815 | Pole step | HFTD Tier 3 | Distribution | 2015-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016893 | 407420033 | Riser/Conduit | HFTD Tier 3 | Distribution | 2015-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016894 | 407420471 | Pole step | HFTD Tier 3 | Distribution | 2015-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016895 | 407420485 | High Sign | HFTD Tier 3 | Distribution | 2015-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016896 | 407420490 | Pole step | HFTD Tier 3 | Distribution | 2015-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016897 | 407421033 | High Sign | HFTD Tier 3 | Distribution | 2015-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016898 | 407421060 | Molding | HFTD Tier 3 | Distribution | 2015-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016899 | 407427759 | Guy | HFTD Tier 2 | Distribution | 2015-10-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016900 | 407428058 | High Sign | HFTD Tier 2 | Distribution | 2015-10-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016901 | 407428071 | High Sign | HFTD Tier 2 | Distribution | 2015-10-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016902 | 407430073 | Pole step | HFTD Tier 3 | Distribution | 2015-11-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016903 | 407433516 | Hardware/Framing | HFTD Tier 3 | Distribution | 2015-11-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016904 | 407433910 | Hardware/Framing | HFTD Tier 2 | Distribution | 2015-11-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016905 | 407436397 | Pole step | HFTD Tier 3 | Distribution | 2015-11-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016906 | 407436520 | High Sign | HFTD Tier 3 | Distribution | 2015-11-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016907 | 407438136 | High Sign | HFTD Tier 3 | Distribution | 2015-11-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016908 | 407438137 | Pole step | HFTD Tier 3 | Distribution | 2015-11-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016909 | 407438179 | Pole step | HFTD Tier 3 | Distribution | 2015-11-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016910 | 407438301 | Guy | HFTD Tier 3 | Distribution | 2015-11-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016911 | 407439321 | Guy | HFTD Tier 3 | Distribution | 2015-11-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016912 | 407439530 | Guy | HFTD Tier 3 | Distribution | 2015-11-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016913 | 407439540 | High Sign | HFTD Tier 3 | Distribution | 2015-11-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016914 | 407445993 | Cable/Conductor | HFTD Tier 2 | Distribution | 2015-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016915 | 407449360 | Guy | HFTD Tier 3 | Distribution | 2015-11-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016916 | 407452324 | Cable/Conductor | HFTD Tier 3 | Distribution | 2015-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016917 | 407454777 | Guy | HFTD Tier 3 | Distribution | 2015-11-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016918 | 407456522 | Guy | HFTD Tier 3 | Distribution | 2015-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016919 | 407457137 | Molding | HFTD Tier 3 | Distribution | 2015-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016920 | 407457374 | Molding | HFTD Tier 3 | Distribution | 2015-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016921 | 407457380 | Guy | HFTD Tier 3 | Distribution | 2015-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016922 | 407457410 | Pole step | HFTD Tier 3 | Distribution | 2015-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016923 | 407457420 | Molding | HFTD Tier 3 | Distribution | 2015-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016924 | 407457421 | High Sign | HFTD Tier 3 | Distribution | 2015-11-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016925 | 407462116 | High Sign | HFTD Tier 2 | Distribution | 2015-11-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016926 | 407468740 | High Sign | HFTD Tier 3 | Distribution | 2015-11-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016927 | 407471283 | High Sign | HFTD Tier 3 | Distribution | 2015-11-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016928 | 407482641 | High Sign | HFTD Tier 3 | Distribution | 2015-12-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016929 | 407482828 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-12-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016930 | 407482953 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2015-12-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016931 | 407483298 | Pole step | HFTD Tier 3 | Distribution | 2015-12-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016932 | 407483338 | Molding | HFTD Tier 3 | Distribution | 2015-12-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016933 | 407487405 | Guy | HFTD Tier 3 | Distribution | 2015-12-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016934 | 407489177 | High Sign | HFTD Tier 3 | Distribution | 2015-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016935 | 407489232 | High Sign | HFTD Tier 3 | Distribution | 2015-12-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016936 | 407494199 | High Sign | HFTD Tier 3 | Distribution | 2015-12-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016937 | 407494316 | High Sign | HFTD Tier 3 | Distribution | 2015-12-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016938 | 407494351 | High Sign | HFTD Tier 3 | Distribution | 2015-12-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016939 | 407494352 | High Sign | HFTD Tier 3 | Distribution | 2015-12-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016940 | 407494361 | Molding | HFTD Tier 3 | Distribution | 2015-12-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016941 | 407494370 | Molding | HFTD Tier 3 | Distribution | 2015-12-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016942 | 407494371 | Molding | HFTD Tier 3 | Distribution | 2015-12-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016943 | 407494380 | Molding | HFTD Tier 3 | Distribution | 2015-12-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016944 | 407494381 | Molding | HFTD Tier 3 | Distribution | 2015-12-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016945 | 407496155 | Molding | HFTD Tier 3 | Distribution | 2015-12-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016946 | 407496220 | High Sign | HFTD Tier 3 | Distribution | 2015-12-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016947 | 407496221 | Molding | HFTD Tier 3 | Distribution | 2015-12-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016948 | 407512117 | Right of Way | HFTD Tier 2 | Transmission | 2015-12-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016949 | 407521190 | Molding | HFTD Tier 2 | Distribution | 2016-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016950 | 407521432 | High Sign | HFTD Tier 2 | Distribution | 2016-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016951 | 407521446 | High Sign | HFTD Tier 2 | Distribution | 2016-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016952 | 407521544 | High Sign | HFTD Tier 2 | Distribution | 2016-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016953 | 407521749 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016954 | 407521872 | High Sign | HFTD Tier 2 | Distribution | 2016-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016955 | 407521876 | Guy | HFTD Tier 3 | Distribution | 2016-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016956 | 407521884 | Guy | HFTD Tier 3 | Distribution | 2016-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016957 | 407521911 | Guy | HFTD Tier 3 | Distribution | 2016-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016958 | 407522001 | Molding | HFTD Tier 2 | Distribution | 2016-01-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016959 | 407522761 | Molding | HFTD Tier 2 | Distribution | 2016-01-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016960 | 407523861 | Molding | HFTD Tier 2 | Distribution | 2016-01-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016961 | 407524028 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-01-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016962 | 407524118 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-01-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016963 | 407525238 | High Sign | HFTD Tier 3 | Distribution | 2016-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016964 | 407525340 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016965 | 407525854 | Riser/Conduit | HFTD Tier 3 | Distribution | 2016-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016966 | 407525905 | Pole step | HFTD Tier 3 | Distribution | 2016-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016967 | 407526053 | High Sign | HFTD Tier 2 | Distribution | 2016-01-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016968 | 407526709 | Guy | HFTD Tier 3 | Distribution | 2016-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016969 | 407527140 | High Sign | HFTD Tier 3 | Distribution | 2016-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016970 | 407527153 | Guy | HFTD Tier 2 | Distribution | 2016-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016971 | 407527202 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016972 | 407527264 | High Sign | HFTD Tier 2 | Distribution | 2016-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016973 | 407527419 | Molding | HFTD Tier 3 | Distribution | 2016-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016974 | 407527435 | High Sign | HFTD Tier 3 | Distribution | 2016-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016975 | 407527454 | Molding | HFTD Tier 3 | Distribution | 2016-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016976 | 407527534 | High Sign | HFTD Tier 3 | Distribution | 2016-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016977 | 407527628 | Molding | HFTD Tier 3 | Distribution | 2016-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016978 | 407527674 | High Sign | HFTD Tier 3 | Distribution | 2016-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016979 | 407527675 | High Sign | HFTD Tier 3 | Distribution | 2016-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016980 | 407527805 | Guy | HFTD Tier 3 | Distribution | 2016-01-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016981 | 407529181 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016982 | 407529191 | High Sign | HFTD Tier 3 | Distribution | 2016-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016983 | 407529396 | Guy | HFTD Tier 3 | Distribution | 2016-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016984 | 407529416 | High Sign | HFTD Tier 3 | Distribution | 2016-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016985 | 407529601 | Bond | HFTD Tier 3 | Distribution | 2016-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016986 | 407529881 | Molding | HFTD Tier 3 | Distribution | 2016-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016987 | 407532072 | Termination | HFTD Tier 2 | Distribution | 2016-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016988 | 407532120 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016989 | 407532143 | High Sign | HFTD Tier 2 | Distribution | 2016-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016990 | 407532151 | Molding | HFTD Tier 2 | Distribution | 2016-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016991 | 407532165 | High Sign | HFTD Tier 3 | Distribution | 2016-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016992 | 407532167 | High Sign | HFTD Tier 2 | Distribution | 2016-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016993 | 407532254 | Molding | HFTD Tier 3 | Distribution | 2016-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016994 | 407532361 | Molding | HFTD Tier 3 | Distribution | 2016-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016995 | 407532465 | High Sign | HFTD Tier 3 | Distribution | 2016-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016996 | 407532529 | High Sign | HFTD Tier 2 | Distribution | 2016-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016997 | 407532670 | Molding | HFTD Tier 2 | Distribution | 2016-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016998 | 407532926 | Guy | HFTD Tier 2 | Distribution | 2016-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120016999 | 407532973 | High Sign | HFTD Tier 2 | Distribution | 2016-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017000 | 407534301 | High Sign | HFTD Tier 2 | Distribution | 2016-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017001 | 407534401 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017002 | 407534870 | Molding | HFTD Tier 3 | Distribution | 2016-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017003 | 407535399 | Guy | HFTD Tier 2 | Distribution | 2016-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017004 | 407535569 | High Sign | HFTD Tier 2 | Distribution | 2016-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017005 | 407535599 | High Sign | HFTD Tier 2 | Distribution | 2016-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017006 | 407535617 | High Sign | HFTD Tier 2 | Distribution | 2016-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017007 | 407535808 | Guy | HFTD Tier 2 | Distribution | 2016-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017008 | 407535827 | High Sign | HFTD Tier 3 | Distribution | 2016-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017009 | 407535962 | High Sign | HFTD Tier 2 | Distribution | 2016-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017010 | 407535994 | High Sign | HFTD Tier 2 | Distribution | 2016-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017011 | 407537876 | Guy | HFTD Tier 2 | Distribution | 2016-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017012 | 407537931 | High Sign | HFTD Tier 2 | Distribution | 2016-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017013 | 407538187 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017014 | 407538191 | Guy | HFTD Tier 3 | Distribution | 2016-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017015 | 407538534 | High Sign | HFTD Tier 3 | Distribution | 2016-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017016 | 407538594 | High Sign | HFTD Tier 2 | Distribution | 2016-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017017 | 407539164 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017018 | 407540066 | High Sign | HFTD Tier 2 | Distribution | 2016-01-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017019 | 407541101 | High Sign | HFTD Tier 3 | Distribution | 2016-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017020 | 407541310 | High Sign | HFTD Tier 3 | Distribution | 2016-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017021 | 407541449 | High Sign | HFTD Tier 3 | Distribution | 2016-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017022 | 407541452 | High Sign | HFTD Tier 3 | Distribution | 2016-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017023 | 407541481 | High Sign | HFTD Tier 3 | Distribution | 2016-01-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017024 | 407543509 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017025 | 407543585 | High Sign | HFTD Tier 3 | Distribution | 2016-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017026 | 407543688 | Riser/Conduit | HFTD Tier 2 | Distribution | 2016-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017027 | 407544057 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017028 | 407544256 | Molding | HFTD Tier 3 | Distribution | 2016-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017029 | 407544292 | Molding | HFTD Tier 3 | Distribution | 2016-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017030 | 407544449 | High Sign | HFTD Tier 2 | Distribution | 2016-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017031 | 407544456 | Guy Guard | HFTD Tier 3 | Distribution | 2016-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017032 | 407544468 | Guy | HFTD Tier 3 | Distribution | 2016-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017033 | 407544512 | High Sign | HFTD Tier 2 | Distribution | 2016-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017034 | 407544530 | High Sign | HFTD Tier 2 | Distribution | 2016-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017035 | 407544556 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017036 | 407544750 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017037 | 407546139 | Molding | HFTD Tier 3 | Distribution | 2016-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017038 | 407546340 | High Sign | HFTD Tier 3 | Distribution | 2016-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017039 | 407546354 | High Sign | HFTD Tier 3 | Distribution | 2016-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017040 | 407546367 | Molding | HFTD Tier 2 | Distribution | 2016-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017041 | 407546468 | High Sign | HFTD Tier 3 | Distribution | 2016-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017042 | 407546520 | High Sign | HFTD Tier 3 | Distribution | 2016-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017043 | 407546521 | Molding | HFTD Tier 3 | Distribution | 2016-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017044 | 407546534 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017045 | 407546622 | High Sign | HFTD Tier 3 | Distribution | 2016-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017046 | 407546732 | Molding | HFTD Tier 3 | Distribution | 2016-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017047 | 407546752 | Molding | HFTD Tier 3 | Distribution | 2016-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017048 | 407546780 | Guy | HFTD Tier 3 | Distribution | 2016-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017049 | 407546838 | Guy | HFTD Tier 3 | Distribution | 2016-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017050 | 407547192 | High Sign | HFTD Tier 3 | Distribution | 2016-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017051 | 407547357 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017052 | 407547500 | High Sign | HFTD Tier 2 | Distribution | 2016-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017053 | 407549123 | High Sign | HFTD Tier 2 | Distribution | 2016-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017054 | 407549129 | High Sign | HFTD Tier 2 | Distribution | 2016-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017055 | 407549270 | High Sign | HFTD Tier 3 | Distribution | 2016-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017056 | 407549348 | High Sign | HFTD Tier 3 | Distribution | 2016-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017057 | 407549737 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017058 | 407549738 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017059 | 407549918 | High Sign | HFTD Tier 2 | Distribution | 2016-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017060 | 407550191 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017061 | 407550323 | High Sign | HFTD Tier 2 | Distribution | 2016-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017062 | 407550324 | Guy | HFTD Tier 3 | Distribution | 2016-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017063 | 407550400 | High Sign | HFTD Tier 2 | Distribution | 2016-01-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017064 | 407552376 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017065 | 407552511 | Molding | HFTD Tier 3 | Distribution | 2016-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017066 | 407552674 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017067 | 407552677 | Molding | HFTD Tier 3 | Distribution | 2016-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017068 | 407552732 | Pole step | HFTD Tier 3 | Distribution | 2016-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017069 | 407552948 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017070 | 407553444 | Molding | HFTD Tier 2 | Distribution | 2016-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017071 | 407553477 | High Sign | HFTD Tier 2 | Distribution | 2016-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017072 | 407553582 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017073 | 407553599 | High Sign | HFTD Tier 2 | Distribution | 2016-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017074 | 407554495 | Guy Guard | HFTD Tier 3 | Distribution | 2016-01-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017075 | 407555648 | Pole step | HFTD Tier 3 | Distribution | 2016-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017076 | 407555564 | High Sign | HFTD Tier 3 | Distribution | 2016-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017077 | 407555860 | High Sign | HFTD Tier 2 | Distribution | 2016-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017078 | 407556029 | High Sign | HFTD Tier 2 | Distribution | 2016-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017079 | 407556035 | Guy | HFTD Tier 2 | Distribution | 2016-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017080 | 407556066 | Molding | HFTD Tier 2 | Distribution | 2016-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017081 | 407556094 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017082 | 407556105 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017083 | 407556131 | High Sign | HFTD Tier 3 | Distribution | 2016-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017084 | 407556141 | Molding | HFTD Tier 3 | Distribution | 2016-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017085 | 407556236 | High Sign | HFTD Tier 2 | Distribution | 2016-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017086 | 407556373 | High Sign | HFTD Tier 2 | Distribution | 2016-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017087 | 407556470 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017088 | 407556562 | Guy | HFTD Tier 3 | Distribution | 2016-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017089 | 407556570 | Molding | HFTD Tier 3 | Distribution | 2016-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017090 | 407556733 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017091 | 407556766 | High Sign | HFTD Tier 3 | Distribution | 2016-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017092 | 407558597 | High Sign | HFTD Tier 3 | Distribution | 2016-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017093 | 407558808 | High Sign | HFTD Tier 3 | Distribution | 2016-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017094 | 407558930 | Guy | HFTD Tier 3 | Distribution | 2016-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017095 | 407558991 | High Sign | HFTD Tier 3 | Distribution | 2016-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017096 | 407559369 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017097 | 407559383 | Pole step | HFTD Tier 2 | Distribution | 2016-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017098 | 407559634 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017099 | 407559831 | Molding | HFTD Tier 3 | Distribution | 2016-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017100 | 407559891 | High Sign | HFTD Tier 3 | Distribution | 2016-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017101 | 407559976 | High Sign | HFTD Tier 3 | Distribution | 2016-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017102 | 407560114 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017103 | 407560175 | High Sign | HFTD Tier 3 | Distribution | 2016-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017104 | 407560238 | High Sign | HFTD Tier 3 | Distribution | 2016-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017105 | 407560284 | High Sign | HFTD Tier 2 | Distribution | 2016-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017106 | 407560420 | Molding | HFTD Tier 2 | Distribution | 2016-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017107 | 407560744 | Guy | HFTD Tier 3 | Distribution | 2016-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017108 | 415052848 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-01-26 | 42760 | 2 | Ignition Risk, no GO95 exception | [7 empty] | SCE | 2026 | 2
1120017109 | 407561825 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017110 | 407561857 | High Sign | HFTD Tier 2 | Distribution | 2016-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017111 | 407561931 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017112 | 407562011 | High Sign | HFTD Tier 2 | Distribution | 2016-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017113 | 407562081 | Guy | HFTD Tier 3 | Distribution | 2016-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017114 | 407562099 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017115 | 407562274 | High Sign | HFTD Tier 3 | Distribution | 2016-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017116 | 407562531 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017117 | 407562672 | High Sign | HFTD Tier 3 | Distribution | 2016-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017118 | 407562949 | High Sign | HFTD Tier 3 | Distribution | 2016-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017119 | 407562988 | High Sign | HFTD Tier 3 | Distribution | 2016-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017120 | 407563059 | Pole step | HFTD Tier 3 | Distribution | 2016-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017121 | 407563086 | Guy | HFTD Tier 3 | Distribution | 2016-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017122 | 407563247 | Guy | HFTD Tier 2 | Distribution | 2016-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017123 | 407563273 | Molding | HFTD Tier 3 | Distribution | 2016-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017124 | 407563313 | Guy | HFTD Tier 2 | Distribution | 2016-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017125 | 407563334 | Guy | HFTD Tier 2 | Distribution | 2016-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017126 | 407563465 | High Sign | HFTD Tier 3 | Distribution | 2016-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017127 | 407564440 | Guy | HFTD Tier 3 | Distribution | 2016-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017128 | 407565075 | High Sign | HFTD Tier 2 | Distribution | 2016-01-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017129 | 407565679 | Molding | HFTD Tier 3 | Distribution | 2016-01-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017130 | 407565816 | Molding | HFTD Tier 3 | Distribution | 2016-01-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017131 | 407565819 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-01-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017132 | 407565843 | High Sign | HFTD Tier 2 | Distribution | 2016-01-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017133 | 407565852 | High Sign | HFTD Tier 2 | Distribution | 2016-01-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017134 | 407567736 | Guy Guard | HFTD Tier 3 | Distribution | 2016-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017135 | 407569871 | Guy | HFTD Tier 2 | Distribution | 2016-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017136 | 407569950 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017137 | 407570051 | Molding | HFTD Tier 2 | Distribution | 2016-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017138 | 407570145 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017139 | 407570162 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017140 | 407571419 | Guy | HFTD Tier 2 | Distribution | 2016-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017141 | 407571424 | Molding | HFTD Tier 2 | Distribution | 2016-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017142 | 407571438 | High Sign | HFTD Tier 3 | Distribution | 2016-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017143 | 407571536 | Molding | HFTD Tier 3 | Distribution | 2016-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017144 | 407571775 | High Sign | HFTD Tier 2 | Distribution | 2016-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017145 | 407571796 | High Sign | HFTD Tier 3 | Distribution | 2016-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017146 | 407572175 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017147 | 407572241 | Molding | HFTD Tier 3 | Distribution | 2016-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017148 | 415054941 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-02-01 | 42769 | 2 | Ignition Risk, no GO95 exception | [7 empty] | SCE | 2026 | 2
1120017149 | 407573529 | Guy | HFTD Tier 3 | Distribution | 2016-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017150 | 407573562 | High Sign | HFTD Tier 3 | Distribution | 2016-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017151 | 407574081 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017152 | 407574115 | High Sign | HFTD Tier 2 | Distribution | 2016-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017153 | 407574461 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017154 | 407575970 | High Sign | HFTD Tier 3 | Distribution | 2016-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017155 | 407576202 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017156 | 407576255 | High Sign | HFTD Tier 3 | Distribution | 2016-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017157 | 407576258 | Guy | HFTD Tier 3 | Distribution | 2016-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017158 | 407576487 | Anchor | HFTD Tier 3 | Distribution | 2016-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017159 | 407576491 | High Sign | HFTD Tier 2 | Distribution | 2016-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017160 | 407576504 | Molding | HFTD Tier 3 | Distribution | 2016-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017161 | 407576509 | Molding | HFTD Tier 3 | Distribution | 2016-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017162 | 407576548 | High Sign | HFTD Tier 3 | Distribution | 2016-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017163 | 407576709 | High Sign | HFTD Tier 2 | Distribution | 2016-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017164 | 407576824 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017165 | 407576958 | Molding | HFTD Tier 3 | Distribution | 2016-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017166 | 407576959 | High Sign | HFTD Tier 3 | Distribution | 2016-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017167 | 407576971 | High Sign | HFTD Tier 2 | Distribution | 2016-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017168 | 407576976 | High Sign | HFTD Tier 2 | Distribution | 2016-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017169 | 407578386 | Guy Guard | HFTD Tier 3 | Distribution | 2016-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017170 | 407579175 | High Sign | HFTD Tier 3 | Distribution | 2016-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017171 | 407579255 | Guy | HFTD Tier 2 | Distribution | 2016-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017172 | 407579758 | High Sign | HFTD Tier 2 | Distribution | 2016-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017173 | 407579988 | High Sign | HFTD Tier 2 | Distribution | 2016-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017174 | 407580064 | Molding | HFTD Tier 2 | Distribution | 2016-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017175 | 407580281 | High Sign | HFTD Tier 2 | Distribution | 2016-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017176 | 407580382 | Molding | HFTD Tier 2 | Distribution | 2016-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017177 | 407580410 | High Sign | HFTD Tier 2 | Distribution | 2016-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017178 | 407580429 | Guy | HFTD Tier 2 | Distribution | 2016-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017179 | 407580434 | High Sign | HFTD Tier 3 | Distribution | 2016-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017180 | 407580683 | High Sign | HFTD Tier 2 | Distribution | 2016-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017181 | 407580765 | Molding | HFTD Tier 3 | Distribution | 2016-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017182 | 407580773 | Guy | HFTD Tier 2 | Distribution | 2016-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017183 | 407580792 | Guy Guard | HFTD Tier 2 | Distribution | 2016-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017184 | 407581093 | High Sign | HFTD Tier 2 | Distribution | 2016-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017185 | 407582154 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017186 | 407582245 | High Sign | HFTD Tier 2 | Distribution | 2016-02-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017187 | 407582725 | Molding | HFTD Tier 3 | Distribution | 2016-02-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017188 | 407582744 | High Sign | HFTD Tier 3 | Distribution | 2016-02-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017189 | 407583240 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-02-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017190 | 407583463 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-02-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017191 | 407583547 | Molding | HFTD Tier 3 | Distribution | 2016-02-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017192 | 407583552 | High Sign | HFTD Tier 3 | Distribution | 2016-02-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017193 | 407584506 | Pole step | HFTD Tier 3 | Distribution | 2016-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017194 | 407584875 | Molding | HFTD Tier 3 | Distribution | 2016-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017195 | 407585017 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017196 | 407585097 | Molding | HFTD Tier 3 | Distribution | 2016-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017197 | 407585362 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017198 | 407585384 | Pole step | HFTD Tier 3 | Distribution | 2016-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017199 | 407586077 | Molding | HFTD Tier 3 | Distribution | 2016-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017200 | 407586613 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017201 | 407586717 | High Sign | HFTD Tier 2 | Distribution | 2016-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017202 | 407586763 | Guy Guard | HFTD Tier 2 | Distribution | 2016-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017203 | 407586804 | High Sign | HFTD Tier 2 | Distribution | 2016-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017204 | 407586891 | High Sign | HFTD Tier 2 | Distribution | 2016-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017205 | 407586949 | High Sign | HFTD Tier 2 | Distribution | 2016-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017206 | 407587054 | Pole step | HFTD Tier 2 | Distribution | 2016-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017207 | 407587056 | High Sign | HFTD Tier 3 | Distribution | 2016-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017208 | 407587067 | High Sign | HFTD Tier 3 | Distribution | 2016-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017209 | 407587085 | High Sign | HFTD Tier 3 | Distribution | 2016-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017210 | 407587133 | High Sign | HFTD Tier 3 | Distribution | 2016-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017211 | 407587152 | Guy | HFTD Tier 2 | Distribution | 2016-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017212 | 407588429 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017213 | 407588433 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017214 | 407588493 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017215 | 407588549 | Guy | HFTD Tier 2 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017216 | 407588606 | Molding | HFTD Tier 3 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017217 | 407588680 | High Sign | HFTD Tier 2 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017218 | 407588713 | Guy Guard | HFTD Tier 3 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017219 | 407588757 | Molding | HFTD Tier 2 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017220 | 407588922 | High Sign | HFTD Tier 2 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017221 | 407588935 | High Sign | HFTD Tier 2 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017222 | 407589098 | Molding | HFTD Tier 2 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017223 | 407589099 | Guy | HFTD Tier 3 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017224 | 407589219 | Insulator | HFTD Tier 2 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017225 | 407589301 | High Sign | HFTD Tier 3 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017226 | 407589327 | High Sign | HFTD Tier 3 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017227 | 407589422 | High Sign | HFTD Tier 3 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017228 | 407589447 | Molding | HFTD Tier 3 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017229 | 407589464 | Guy | HFTD Tier 2 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017230 | 407589485 | High Sign | HFTD Tier 2 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017231 | 407589555 | Molding | HFTD Tier 3 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017232 | 407589572 | Guy | HFTD Tier 3 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017233 | 407589620 | Molding | HFTD Tier 3 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017234 | 407589722 | High Sign | HFTD Tier 2 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017235 | 407590274 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017236 | 407591074 | Crossarm | HFTD Tier 2 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017237 | 407591506 | Anchor | HFTD Tier 3 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017238 | 407591519 | Anchor | HFTD Tier 3 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017239 | 407591569 | Guy | HFTD Tier 3 | Distribution | 2016-02-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017240 | 407592287 | Pole step | HFTD Tier 2 | Distribution | 2016-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017241 | 407592309 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017242 | 407593277 | Molding | HFTD Tier 3 | Distribution | 2016-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017243 | 407593284 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017244 | 407593624 | Guy | HFTD Tier 3 | Distribution | 2016-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017245 | 407594776 | Guy | HFTD Tier 2 | Distribution | 2016-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017246 | 407595931 | Molding | HFTD Tier 3 | Distribution | 2016-02-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017247 | 407596260 | High Sign | HFTD Tier 2 | Distribution | 2016-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017248 | 407596267 | Molding | HFTD Tier 3 | Distribution | 2016-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017249 | 407596337 | Molding | HFTD Tier 3 | Distribution | 2016-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017250 | 407596619 | High Sign | HFTD Tier 2 | Distribution | 2016-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017251 | 407596734 | High Sign | HFTD Tier 2 | Distribution | 2016-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017252 | 407596830 | High Sign | HFTD Tier 2 | Distribution | 2016-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017253 | 407596833 | Molding | HFTD Tier 3 | Distribution | 2016-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017254 | 407596997 | Molding | HFTD Tier 3 | Distribution | 2016-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017255 | 407596999 | High Sign | HFTD Tier 3 | Distribution | 2016-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017256 | 407597064 | High Sign | HFTD Tier 3 | Distribution | 2016-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017257 | 407597169 | High Sign | HFTD Tier 2 | Distribution | 2016-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017258 | 407597433 | High Sign | HFTD Tier 3 | Distribution | 2016-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017259 | 407597607 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017260 | 407598238 | Molding | HFTD Tier 2 | Distribution | 2016-02-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017261 | 407598853 | Molding | HFTD Tier 3 | Distribution | 2016-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017262 | 407599217 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017263 | 407599600 | Molding | HFTD Tier 3 | Distribution | 2016-02-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017264 | 407601308 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017265 | 407601328 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017266 | 407601372 | Guy | HFTD Tier 3 | Distribution | 2016-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017267 | 407601392 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017268 | 407601431 | High Sign | HFTD Tier 2 | Distribution | 2016-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017269 | 407601859 | Molding | HFTD Tier 3 | Distribution | 2016-02-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017270 | 407602703 | High Sign | HFTD Tier 2 | Distribution | 2016-02-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017271 | 407602733 | High Sign | HFTD Tier 2 | Distribution | 2016-02-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017272 | 407602812 | Molding | HFTD Tier 2 | Distribution | 2016-02-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017273 | 407602897 | High Sign | HFTD Tier 2 | Distribution | 2016-02-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017274 | 407602945 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-02-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017275 | 407603015 | Guy | HFTD Tier 2 | Distribution | 2016-02-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017276 | 407603071 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-02-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017277 | 407603261 | Termination | HFTD Tier 2 | Distribution | 2016-02-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017278 | 407603291 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-02-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017279 | 407603437 | Guy Guard | HFTD Tier 3 | Distribution | 2016-02-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017280 | 407603519 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-02-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017281 | 407603589 | Termination | HFTD Tier 2 | Distribution | 2016-02-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017282 | 407604099 | High Sign | HFTD Tier 2 | Distribution | 2016-02-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017283 | 407604283 | High Sign | HFTD Tier 2 | Distribution | 2016-02-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017284 | 407605316 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-02-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017285 | 407605545 | Guy | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017286 | 407605564 | Molding | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017287 | 407605671 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017288 | 407605761 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017289 | 407605860 | Guy | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017290 | 407606344 | Molding | HFTD Tier 3 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017291 | 407606376 | High Sign | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017292 | 407606621 | High Sign | HFTD Tier 3 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017293 | 407606676 | Guy | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017294 | 407606797 | High Sign | HFTD Tier 3 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017295 | 407607099 | High Sign | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017296 | 407607183 | Molding | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017297 | 407607834 | Pole step | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017298 | 407607846 | Riser/Conduit | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017299 | 407608694 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017300 | 407608708 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017301 | 407609026 | Molding | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017302 | 407609032 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017303 | 407609041 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017304 | 407609050 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017305 | 407609051 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017306 | 407609070 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017307 | 407609080 | Molding | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017308 | 407609081 | High Sign | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017309 | 407611829 | Guy | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017310 | 407611912 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-02-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017311 | 407609745 | Cutout/Fuse | HFTD Tier 3 | Distribution | 2016-02-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017312 | 407609802 | Guy | HFTD Tier 3 | Distribution | 2016-02-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017313 | 407610237 | Guy | HFTD Tier 3 | Distribution | 2016-02-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017314 | 407611135 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-02-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017315 | 407611841 | Guy | HFTD Tier 3 | Distribution | 2016-02-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017316 | 407612074 | Guy | HFTD Tier 2 | Distribution | 2016-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017317 | 407612469 | High Sign | HFTD Tier 2 | Distribution | 2016-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017318 | 407612483 | Guy | HFTD Tier 3 | Distribution | 2016-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017319 | 407612520 | Guy | HFTD Tier 3 | Distribution | 2016-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017320 | 407612704 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017321 | 407612881 | Guy | HFTD Tier 3 | Distribution | 2016-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017322 | 407613105 | Pole step | HFTD Tier 3 | Distribution | 2016-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017323 | 407613992 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-02-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017324 | 407614814 | Molding | HFTD Tier 3 | Distribution | 2016-02-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017325 | 407617127 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-02-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017326 | 407617131 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-02-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017327 | 407615870 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017328 | 407615894 | Guy | HFTD Tier 3 | Distribution | 2016-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017329 | 407615972 | Guy | HFTD Tier 3 | Distribution | 2016-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017330 | 407616023 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017331 | 407616082 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017332 | 407616345 | High Sign | HFTD Tier 3 | Distribution | 2016-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017333 | 407617115 | High Sign | HFTD Tier 2 | Distribution | 2016-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017334 | 407617162 | Guy Guard | HFTD Tier 3 | Distribution | 2016-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017335 | 407617215 | Ground | HFTD Tier 2 | Distribution | 2016-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017336 | 407617216 | Molding | HFTD Tier 2 | Distribution | 2016-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017337 | 407617230 | Molding | HFTD Tier 2 | Distribution | 2016-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017338 | 407617328 | Guy | HFTD Tier 3 | Distribution | 2016-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017339 | 407617397 | High Sign | HFTD Tier 3 | Distribution | 2016-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017340 | 407618718 | Guy Guard | HFTD Tier 3 | Distribution | 2016-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017341 | 407618795 | Guy | HFTD Tier 3 | Distribution | 2016-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017342 | 407618828 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017343 | 407618888 | Guy | HFTD Tier 3 | Distribution | 2016-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017344 | 407619359 | High Sign | HFTD Tier 2 | Distribution | 2016-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017345 | 407619386 | Molding | HFTD Tier 3 | Distribution | 2016-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017346 | 407619543 | Molding | HFTD Tier 2 | Distribution | 2016-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017347 | 407620184 | Guy | HFTD Tier 2 | Distribution | 2016-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017348 | 407620199 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017349 | 407620242 | Pole step | HFTD Tier 2 | Distribution | 2016-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017350 | 407620267 | Molding | HFTD Tier 3 | Distribution | 2016-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017351 | 407620320 | High Sign | HFTD Tier 3 | Distribution | 2016-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017352 | 407620321 | High Sign | HFTD Tier 3 | Distribution | 2016-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017353 | 407620324 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017354 | 407620325 | High Sign | HFTD Tier 2 | Distribution | 2016-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017355 | 407620342 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017356 | 407621410 | High Sign | HFTD Tier 3 | Distribution | 2016-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017357 | 407622148 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017358 | 407622224 | Molding | HFTD Tier 3 | Distribution | 2016-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017359 | 407622890 | High Sign | HFTD Tier 2 | Distribution | 2016-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017360 | 407623176 | Guy | HFTD Tier 3 | Distribution | 2016-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017361 | 407624400 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017362 | 407624401 | Guy | HFTD Tier 2 | Distribution | 2016-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017363 | 407625211 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017364 | 407625966 | High Sign | HFTD Tier 3 | Distribution | 2016-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017365 | 407626026 | High Sign | HFTD Tier 3 | Distribution | 2016-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017366 | 407626072 | Molding | HFTD Tier 3 | Distribution | 2016-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017367 | 407626372 | High Sign | HFTD Tier 3 | Distribution | 2016-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017368 | 407626375 | High Sign | HFTD Tier 2 | Distribution | 2016-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017369 | 407626735 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-02-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017370 | 415054928 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-02-25 | 42790 | 2 | Ignition Risk, no GO95 exception | [7 empty] | SCE | 2026 | 2
1120017371 | 407628029 | High Sign | HFTD Tier 3 | Distribution | 2016-02-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017372 | 407628246 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-02-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017373 | 407629333 | High Sign | HFTD Tier 3 | Distribution | 2016-02-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017374 | 407630525 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-02-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017375 | 407630770 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-02-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017376 | 407631374 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-02-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017377 | 407631904 | Molding | HFTD Tier 3 | Distribution | 2016-02-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017378 | 407632045 | High Sign | HFTD Tier 3 | Distribution | 2016-02-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017379 | 407632222 | Guy | HFTD Tier 3 | Distribution | 2016-02-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017380 | 407632334 | High Sign | HFTD Tier 2 | Distribution | 2016-02-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017381 | 407632385 | Molding | HFTD Tier 2 | Distribution | 2016-02-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017382 | 407632508 | Riser/Conduit | HFTD Tier 3 | Distribution | 2016-02-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017383 | 407632592 | Guy | HFTD Tier 3 | Distribution | 2016-02-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017384 | 407632810 | Guy | HFTD Tier 2 | Distribution | 2016-02-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017385 | 407634059 | Guy | HFTD Tier 3 | Distribution | 2016-02-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017386 | 407634151 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-02-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017387 | 407634737 | High Sign | HFTD Tier 3 | Distribution | 2016-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017388 | 407634947 | High Sign | HFTD Tier 3 | Distribution | 2016-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017389 | 407635014 | High Sign | HFTD Tier 2 | Distribution | 2016-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017390 | 407635033 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017391 | 407635059 | High Sign | HFTD Tier 2 | Distribution | 2016-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017392 | 407635209 | Guy | HFTD Tier 3 | Distribution | 2016-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017393 | 407635252 | Guy | HFTD Tier 3 | Distribution | 2016-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017394 | 407635284 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017395 | 407635316 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017396 | 407635352 | Molding | HFTD Tier 2 | Distribution | 2016-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017397 | 407635504 | Guy Guard | HFTD Tier 3 | Distribution | 2016-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017398 | 407635751 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017399 | 407636037 | High Sign | HFTD Tier 2 | Distribution | 2016-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017400 | 407636120 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017401 | 407636134 | Molding | HFTD Tier 3 | Distribution | 2016-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017402 | 407636267 | Guy Guard | HFTD Tier 3 | Distribution | 2016-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017403 | 407638268 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017404 | 407638465 | Guy | HFTD Tier 3 | Distribution | 2016-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017405 | 407638467 | Guy | HFTD Tier 3 | Distribution | 2016-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017406 | 407638468 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017407 | 407638509 | High Sign | HFTD Tier 2 | Distribution | 2016-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017408 | 407638560 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017409 | 407638603 | High Sign | HFTD Tier 2 | Distribution | 2016-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017410 | 407639012 | Molding | HFTD Tier 3 | Distribution | 2016-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017411 | 407639034 | High Sign | HFTD Tier 3 | Distribution | 2016-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017412 | 407639144 | High Sign | HFTD Tier 2 | Distribution | 2016-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017413 | 407639193 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017414 | 407641323 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017415 | 407641942 | High Sign | HFTD Tier 3 | Distribution | 2016-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017416 | 407642324 | Molding | HFTD Tier 3 | Distribution | 2016-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017417 | 407642541 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017418 | 407642818 | Molding | HFTD Tier 3 | Distribution | 2016-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017419 | 407645117 | High Sign | HFTD Tier 3 | Distribution | 2016-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017420 | 407645157 | Pole step | HFTD Tier 2 | Distribution | 2016-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017421 | 407645172 | High Sign | HFTD Tier 3 | Distribution | 2016-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017422 | 407645484 | Pole step | HFTD Tier 2 | Distribution | 2016-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017423 | 407645513 | High Sign | HFTD Tier 2 | Distribution | 2016-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017424 | 407645531 | Pole step | HFTD Tier 2 | Distribution | 2016-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017425 | 407647188 | Guy | HFTD Tier 3 | Distribution | 2016-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017426 | 407647226 | Guy | HFTD Tier 3 | Distribution | 2016-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017427 | 407647248 | High Sign | HFTD Tier 3 | Distribution | 2016-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017428 | 407647311 | Guy | HFTD Tier 3 | Distribution | 2016-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017429 | 407647576 | Guy Guard | HFTD Tier 2 | Distribution | 2016-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017430 | 407647579 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017431 | 407647612 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017432 | 407647616 | Guy | HFTD Tier 2 | Distribution | 2016-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017433 | 407647624 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017434 | 407647630 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017435 | 407647654 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017436 | 407647681 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-03-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017437 | 407648405 | High Sign | HFTD Tier 3 | Distribution | 2016-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017438 | 407648594 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017439 | 407649417 | Molding | HFTD Tier 3 | Distribution | 2016-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017440 | 407650958 | Guy | HFTD Tier 2 | Distribution | 2016-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017441 | 407651105 | Guy | HFTD Tier 3 | Distribution | 2016-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017442 | 407651789 | Guy | HFTD Tier 2 | Distribution | 2016-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017443 | 407651855 | Molding | HFTD Tier 2 | Distribution | 2016-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017444 | 407651856 | Guy | HFTD Tier 2 | Distribution | 2016-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017445 | 407651862 | Guy | HFTD Tier 2 | Distribution | 2016-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017446 | 407651885 | Molding | HFTD Tier 2 | Distribution | 2016-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017447 | 415054929 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-03-08 | 42769 | 2 | Ignition Risk, no GO95 exception | [7 empty] | SCE | 2026 | 2
1120017448 | 407654149 | Pole step | HFTD Tier 2 | Distribution | 2016-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017449 | 407654177 | Guy | HFTD Tier 2 | Distribution | 2016-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017450 | 407654189 | High Sign | HFTD Tier 3 | Distribution | 2016-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017451 | 407654198 | High Sign | HFTD Tier 3 | Distribution | 2016-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017452 | 407654234 | High Sign | HFTD Tier 2 | Distribution | 2016-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017453 | 407654291 | High Sign | HFTD Tier 2 | Distribution | 2016-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017454 | 407654349 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017455 | 407654421 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017456 | 407654681 | High Sign | HFTD Tier 3 | Distribution | 2016-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017457 | 407654738 | High Sign | HFTD Tier 2 | Distribution | 2016-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017458 | 407654797 | Guy | HFTD Tier 3 | Distribution | 2016-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017459 | 407655042 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017460 | 407656798 | High Sign | HFTD Tier 2 | Distribution | 2016-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017461 | 407657413 | Guy | HFTD Tier 3 | Distribution | 2016-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017462 | 407657458 | Molding | HFTD Tier 2 | Distribution | 2016-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017463 | 407657691 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017464 | 407657854 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017465 | 415054930 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-03-10 | 42797 | 2 | Ignition Risk, no GO95 exception | [7 empty] | SCE | 2026 | 2
1120017466 | 407659459 | Guy | HFTD Tier 3 | Distribution | 2016-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017467 | 407659625 | High Sign | HFTD Tier 3 | Distribution | 2016-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017468 | 407659651 | High Sign | HFTD Tier 3 | Distribution | 2016-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017469 | 407660386 | High Sign | HFTD Tier 3 | Distribution | 2016-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017470 | 407662015 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-03-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017471 | 407663786 | High Sign | HFTD Tier 3 | Distribution | 2016-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017472 | 407663958 | Molding | HFTD Tier 3 | Distribution | 2016-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017473 | 407665761 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017474 | 407665976 | Termination | HFTD Tier 2 | Distribution | 2016-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017475 | 407665984 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017476 | 407665987 | Guy Guard | HFTD Tier 3 | Distribution | 2016-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017477 | 407666783 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017478 | 407666792 | Molding | HFTD Tier 3 | Distribution | 2016-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017479 | 407666828 | Guy Guard | HFTD Tier 3 | Distribution | 2016-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017480 | 407666855 | High Sign | HFTD Tier 3 | Distribution | 2016-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017481 | 407667139 | Guy | HFTD Tier 2 | Distribution | 2016-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017482 | 407669370 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017483 | 407669689 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017484 | 407669894 | High Sign | HFTD Tier 3 | Distribution | 2016-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017485 | 407669898 | High Sign | HFTD Tier 3 | Distribution | 2016-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017486 | 407669916 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017487 | 407669928 | High Sign | HFTD Tier 3 | Distribution | 2016-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017488 | 407669947 | High Sign | HFTD Tier 3 | Distribution | 2016-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017489 | 407670036 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017490 | 407670069 | High Sign | HFTD Tier 3 | Distribution | 2016-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017491 | 407670084 | Guy Guard | HFTD Tier 2 | Distribution | 2016-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017492 | 407670092 | Guy | HFTD Tier 2 | Distribution | 2016-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017493 | 407670101 | Guy | HFTD Tier 2 | Distribution | 2016-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017494 | 407670309 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017495 | 407670344 | Riser/Conduit | HFTD Tier 3 | Distribution | 2016-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017496 | 407670353 | Pole step | HFTD Tier 3 | Distribution | 2016-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017497 | 407670719 | High Sign | HFTD Tier 2 | Distribution | 2016-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017498 | 413841143 | High Sign | HFTD Tier 3 | Distribution | 2016-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017499 | 407673433 | High Sign | HFTD Tier 2 | Distribution | 2016-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017500 | 407673625 | Guy | HFTD Tier 2 | Distribution | 2016-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017501 | 407673653 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017502 | 407673761 | Insulator | HFTD Tier 2 | Distribution | 2016-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017503 | 407673921 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017504 | 407675353 | Molding | HFTD Tier 3 | Distribution | 2016-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017505 | 407675694 | High Sign | HFTD Tier 3 | Distribution | 2016-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017506 | 407675732 | High Sign | HFTD Tier 3 | Distribution | 2016-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017507 | 407675740 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017508 | 407676413 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017509 | 407681744 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017510 | 407681790 | Guy Guard | HFTD Tier 3 | Distribution | 2016-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017511 | 407678414 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017512 | 407678440 | Molding | HFTD Tier 2 | Distribution | 2016-03-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017513 | 407679925 | High Sign | HFTD Tier 2 | Distribution | 2016-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017514 | 407679937 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017515 | 407681758 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017516 | 407681779 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017517 | 407682132 | Guy | HFTD Tier 2 | Distribution | 2016-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017518 | 407682327 | Guy | HFTD Tier 2 | Distribution | 2016-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017519 | 407682449 | High Sign | HFTD Tier 3 | Distribution | 2016-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017520 | 407684895 | Guy | HFTD Tier 2 | Distribution | 2016-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017521 | 407684912 | Guy | HFTD Tier 2 | Distribution | 2016-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017522 | 407685119 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017523 | 407685232 | High Sign | HFTD Tier 2 | Distribution | 2016-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017524 | 407685244 | Guy | HFTD Tier 2 | Distribution | 2016-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017525 | 407685807 | Guy Guard | HFTD Tier 3 | Distribution | 2016-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017526 | 407685901 | Molding | HFTD Tier 3 | Distribution | 2016-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017527 | 407685911 | High Sign | HFTD Tier 3 | Distribution | 2016-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017528 | 407687117 | Molding | HFTD Tier 3 | Distribution | 2016-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017529 | 407687131 | High Sign | HFTD Tier 3 | Distribution | 2016-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017530 | 407687775 | Guy | HFTD Tier 2 | Distribution | 2016-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017531 | 407687789 | Guy | HFTD Tier 2 | Distribution | 2016-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017532 | 407687827 | Insulator | HFTD Tier 2 | Distribution | 2016-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017533 | 407687839 | Guy Guard | HFTD Tier 3 | Distribution | 2016-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017534 | 407687857 | Insulator | HFTD Tier 2 | Distribution | 2016-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017535 | 407687880 | Guy Guard | HFTD Tier 3 | Distribution | 2016-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017536 | 407688515 | Molding | HFTD Tier 2 | Distribution | 2016-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017537 | 407688536 | Insulator | HFTD Tier 2 | Distribution | 2016-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017538 | 407688537 | Molding | HFTD Tier 2 | Distribution | 2016-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017539 | 407688571 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017540 | 407688613 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017541 | 407689937 | Vis Strips | HFTD Tier 3 | Distribution | 2016-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017542 | 407689963 | High Sign | HFTD Tier 2 | Distribution | 2016-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017543 | 407692555 | Molding | HFTD Tier 3 | Distribution | 2016-03-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017544 | 407690396 | High Sign | HFTD Tier 2 | Distribution | 2016-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017545 | 407691133 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017546 | 407691171 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-03-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017547 | 407693186 | Guy | HFTD Tier 2 | Distribution | 2016-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017548 | 407693396 | High Sign | HFTD Tier 2 | Distribution | 2016-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017549 | 407693479 | High Sign | HFTD Tier 2 | Distribution | 2016-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017550 | 407694396 | High Sign | HFTD Tier 3 | Distribution | 2016-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017551 | 407694534 | High Sign | HFTD Tier 3 | Distribution | 2016-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017552 | 407694543 | Molding | HFTD Tier 3 | Distribution | 2016-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017553 | 407695616 | High Sign | HFTD Tier 2 | Distribution | 2016-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017554 | 407698065 | Molding | HFTD Tier 2 | Distribution | 2016-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017555 | 407698134 | High Sign | HFTD Tier 2 | Distribution | 2016-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017556 | 407698715 | High Sign | HFTD Tier 2 | Distribution | 2016-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017557 | 407699242 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017558 | 407700786 | High Sign | HFTD Tier 3 | Distribution | 2016-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017559 | 407700825 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017560 | 407700903 | High Sign | HFTD Tier 2 | Distribution | 2016-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017561 | 407702882 | High Sign | HFTD Tier 3 | Distribution | 2016-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017562 | 407701494 | Guy Guard | HFTD Tier 3 | Distribution | 2016-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017563 | 407701671 | Molding | HFTD Tier 2 | Distribution | 2016-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017564 | 407701682 | High Sign | HFTD Tier 2 | Distribution | 2016-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017565 | 407702889 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-03-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017566 | 407704135 | Molding | HFTD Tier 3 | Distribution | 2016-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017567 | 407704158 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-04-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017568 | 407706235 | High Sign | HFTD Tier 3 | Distribution | 2016-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017569 | 407706423 | Molding | HFTD Tier 2 | Distribution | 2016-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017570 | 407706430 | Molding | HFTD Tier 2 | Distribution | 2016-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017571 | 407706845 | High Sign | HFTD Tier 2 | Distribution | 2016-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017572 | 407706876 | Molding | HFTD Tier 2 | Distribution | 2016-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017573 | 407708803 | Anchor | HFTD Tier 3 | Distribution | 2016-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017574 | 407709371 | Molding | HFTD Tier 2 | Distribution | 2016-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017575 | 407709643 | Guy | HFTD Tier 3 | Distribution | 2016-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017576 | 407709673 | Molding | HFTD Tier 3 | Distribution | 2016-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017577 | 407709712 | Insulator | HFTD Tier 2 | Distribution | 2016-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017578 | 407709726 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017579 | 407709735 | Molding | HFTD Tier 3 | Distribution | 2016-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017580 | 407709742 | Termination | HFTD Tier 2 | Distribution | 2016-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017581 | 407709761 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017582 | 407709795 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017583 | 407709959 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017584 | 407710034 | Insulator | HFTD Tier 2 | Distribution | 2016-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017585 | 407710091 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017586 | 407710195 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017587 | 407712016 | Guy | HFTD Tier 2 | Distribution | 2016-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017588 | 407713119 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017589 | 407714410 | High Sign | HFTD Tier 2 | Distribution | 2016-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017590 | 407715265 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017591 | 407715439 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017592 | 407715450 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017593 | 407716187 | High Sign | HFTD Tier 3 | Distribution | 2016-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017594 | 407716226 | High Sign | HFTD Tier 3 | Distribution | 2016-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017595 | 407716402 | High Sign | HFTD Tier 2 | Distribution | 2016-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017596 | 407716408 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017597 | 407717702 | Guy | HFTD Tier 3 | Distribution | 2016-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017598 | 407718642 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-04-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017599 | 407718694 | High Sign | HFTD Tier 2 | Distribution | 2016-04-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017600 | 407719258 | Molding | HFTD Tier 2 | Distribution | 2016-04-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017601 | 407719732 | Guy | HFTD Tier 2 | Distribution | 2016-04-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017602 | 407722220 | Guy | HFTD Tier 3 | Distribution | 2016-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017603 | 407722482 | Riser/Conduit | HFTD Tier 2 | Distribution | 2016-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017604 | 407722514 | Guy Guard | HFTD Tier 3 | Distribution | 2016-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017605 | 407722534 | Molding | HFTD Tier 3 | Distribution | 2016-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017606 | 407722595 | High Sign | HFTD Tier 3 | Distribution | 2016-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017607 | 407722623 | High Sign | HFTD Tier 3 | Distribution | 2016-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017608 | 415052924 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-04-11 | 42836 | 2 | Ignition Risk, no GO95 exception | [7 empty] | SCE | 2026 | 2
1120017609 | 407724142 | Molding | HFTD Tier 3 | Distribution | 2016-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017610 | 407724368 | Pole step | HFTD Tier 2 | Distribution | 2016-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017611 | 407724675 | Guy | HFTD Tier 2 | Distribution | 2016-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017612 | 407724754 | Molding | HFTD Tier 2 | Distribution | 2016-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017613 | 407724953 | Molding | HFTD Tier 3 | Distribution | 2016-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017614 | 407725107 | Guy | HFTD Tier 3 | Distribution | 2016-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017615 | 407725221 | High Sign | HFTD Tier 2 | Distribution | 2016-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017616 | 407725306 | Guy | HFTD Tier 3 | Distribution | 2016-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017617 | 407725309 | Guy | HFTD Tier 3 | Distribution | 2016-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017618 | 407725502 | High Sign | HFTD Tier 3 | Distribution | 2016-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017619 | 407725503 | Molding | HFTD Tier 3 | Distribution | 2016-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017620 | 407725533 | Guy | HFTD Tier 3 | Distribution | 2016-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017621 | 407726717 | Pole step | HFTD Tier 3 | Distribution | 2016-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017622 | 407728192 | Guy Guard | HFTD Tier 3 | Distribution | 2016-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017623 | 407728205 | Guy | HFTD Tier 3 | Distribution | 2016-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017624 | 407728325 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017625 | 407728330 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017626 | 407728377 | Guy | HFTD Tier 2 | Distribution | 2016-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017627 | 407728447 | Guy | HFTD Tier 3 | Distribution | 2016-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017628 | 407728531 | High Sign | HFTD Tier 3 | Distribution | 2016-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017629 | 407728532 | High Sign | HFTD Tier 3 | Distribution | 2016-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017630 | 407728733 | High Sign | HFTD Tier 3 | Distribution | 2016-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017631 | 407728735 | High Sign | HFTD Tier 3 | Distribution | 2016-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017632 | 407728799 | High Sign | HFTD Tier 3 | Distribution | 2016-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017633 | 407730071 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-04-13 | 42838 | 2 | Ignition Risk, no GO95 exception | [7 empty] | SCE | 2026 | 2
1120017634 | 415052928 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-04-13 | 42838 | 2 | Ignition Risk, no GO95 exception | [7 empty] | SCE | 2026 | 2
1120017635 | 407730927 | Guy | HFTD Tier 3 | Distribution | 2016-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017636 | 407730933 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017637 | 407731018 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017638 | 407731529 | Molding | HFTD Tier 2 | Distribution | 2016-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017639 | 407731867 | High Sign | HFTD Tier 3 | Distribution | 2016-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017640 | 407731974 | Molding | HFTD Tier 3 | Distribution | 2016-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017641 | 407731985 | Molding | HFTD Tier 3 | Distribution | 2016-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017642 | 407732023 | Guy Guard | HFTD Tier 3 | Distribution | 2016-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017643 | 407732078 | Anchor | HFTD Tier 3 | Distribution | 2016-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017644 | 407734557 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017645 | 407734591 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017646 | 407734593 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-04-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017647 | 407737256 | Guy | HFTD Tier 2 | Distribution | 2016-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017648 | 407737274 | High Sign | HFTD Tier 2 | Distribution | 2016-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017649 | 407737998 | High Sign | HFTD Tier 3 | Distribution | 2016-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017650 | 407738211 | Guy | HFTD Tier 3 | Distribution | 2016-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017651 | 407738259 | High Sign | HFTD Tier 3 | Distribution | 2016-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017652 | 407738273 | High Sign | HFTD Tier 3 | Distribution | 2016-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017653 | 407739666 | High Sign | HFTD Tier 2 | Distribution | 2016-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017654 | 407740318 | Guy Guard | HFTD Tier 2 | Distribution | 2016-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017655 | 407740370 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017656 | 407740385 | Anchor | HFTD Tier 3 | Distribution | 2016-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017657 | 407740396 | High Sign | HFTD Tier 2 | Distribution | 2016-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017658 | 407740625 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017659 | 407740714 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017660 | 407740907 | High Sign | HFTD Tier 3 | Distribution | 2016-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017661 | 407741149 | High Sign | HFTD Tier 3 | Distribution | 2016-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017662 | 407742175 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017663 | 407742187 | High Sign | HFTD Tier 3 | Distribution | 2016-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017664 | 407743786 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017665 | 407745338 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017666 | 407746060 | Guy Guard | HFTD Tier 3 | Distribution | 2016-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017667 | 407756238 | High Sign | HFTD Tier 3 | Distribution | 2016-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017668 | 407756641 | High Sign | HFTD Tier 3 | Distribution | 2016-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017669 | 407756673 | High Sign | HFTD Tier 3 | Distribution | 2016-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017670 | 407756674 | High Sign | HFTD Tier 3 | Distribution | 2016-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017671 | 407756691 | Riser/Conduit | HFTD Tier 3 | Distribution | 2016-04-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017672 | 407749737 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017673 | 407749818 | High Sign | HFTD Tier 2 | Distribution | 2016-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017674 | 407750267 | Molding | HFTD Tier 3 | Distribution | 2016-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017675 | 407750284 | High Sign | HFTD Tier 3 | Distribution | 2016-04-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017676 | 407750884 | Guy | HFTD Tier 2 | Distribution | 2016-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017677 | 407753208 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017678 | 407753840 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017679 | 407754468 | High Sign | HFTD Tier 3 | Distribution | 2016-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017680 | 407754540 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017681 | 407756200 | Molding | HFTD Tier 3 | Distribution | 2016-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017682 | 407766935 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017683 | 407757013 | Guy Guard | HFTD Tier 2 | Distribution | 2016-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017684 | 407757169 | Guy Guard | HFTD Tier 3 | Distribution | 2016-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017685 | 407757824 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017686 | 407759322 | Molding | HFTD Tier 2 | Distribution | 2016-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017687 | 407759599 | Riser/Conduit | HFTD Tier 2 | Distribution | 2016-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017688 | 407759957 | Guy | HFTD Tier 3 | Distribution | 2016-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017689 | 407759965 | Molding | HFTD Tier 3 | Distribution | 2016-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017690 | 407759984 | Guy Guard | HFTD Tier 3 | Distribution | 2016-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017691 | 407761209 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017692 | 407779658 | Molding | HFTD Tier 2 | Distribution | 2016-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017693 | 407779663 | Termination | HFTD Tier 2 | Distribution | 2016-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017694 | 407779695 | Molding | HFTD Tier 2 | Distribution | 2016-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017695 | 407779701 | High Sign | HFTD Tier 2 | Distribution | 2016-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017696 | 407779702 | High Sign | HFTD Tier 2 | Distribution | 2016-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017697 | 415054952 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-04-28 | 42853 | 2 | Ignition Risk, no GO95 exception | [7 empty] | SCE | 2026 | 2
1120017698 | 407763304 | Guy | HFTD Tier 2 | Distribution | 2016-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017699 | 407763594 | High Sign | HFTD Tier 3 | Distribution | 2016-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017700 | 407763725 | Molding | HFTD Tier 2 | Distribution | 2016-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017701 | 407764218 | Guy Guard | HFTD Tier 2 | Distribution | 2016-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017702 | 407764257 | Insulator | HFTD Tier 2 | Distribution | 2016-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017703 | 407764352 | High Sign | HFTD Tier 2 | Distribution | 2016-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017704 | 407764366 | High Sign | HFTD Tier 2 | Distribution | 2016-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017705 | 407764371 | High Sign | HFTD Tier 2 | Distribution | 2016-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017706 | 407766641 | High Sign | HFTD Tier 2 | Distribution | 2016-04-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017707 | 407767373 | Molding | HFTD Tier 2 | Distribution | 2016-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017708 | 407767399 | High Sign | HFTD Tier 2 | Distribution | 2016-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017709 | 407767438 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017710 | 407768171 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017711 | 407769584 | Guy | HFTD Tier 3 | Distribution | 2016-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017712 | 407769620 | Bond | HFTD Tier 2 | Distribution | 2016-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017713 | 407769726 | High Sign | HFTD Tier 2 | Distribution | 2016-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017714 | 407770694 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017715 | 407771245 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017716 | 407771670 | Guy | HFTD Tier 2 | Distribution | 2016-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017717 | 407771933 | Insulator | HFTD Tier 2 | Distribution | 2016-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017718 | 407772036 | Guy | HFTD Tier 2 | Distribution | 2016-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017719 | 407772440 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017720 | 407779728 | Molding | HFTD Tier 2 | Distribution | 2016-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017721 | 407779806 | High Sign | HFTD Tier 2 | Distribution | 2016-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017722 | 407779816 | High Sign | HFTD Tier 2 | Distribution | 2016-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017723 | 407779837 | High Sign | HFTD Tier 2 | Distribution | 2016-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017724 | 407772846 | Guy Guard | HFTD Tier 3 | Distribution | 2016-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017725 | 407772888 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017726 | 407773492 | Molding | HFTD Tier 2 | Distribution | 2016-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017727 | 407777946 | High Sign | HFTD Tier 2 | Distribution | 2016-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017728 | 407777995 | High Sign | HFTD Tier 2 | Distribution | 2016-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017729 | 407778003 | High Sign | HFTD Tier 2 | Distribution | 2016-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017730 | 407778083 | High Sign | HFTD Tier 2 | Distribution | 2016-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017731 | 407778130 | High Sign | HFTD Tier 2 | Distribution | 2016-05-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017732 | 407779818 | High Sign | HFTD Tier 2 | Distribution | 2016-05-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017733 | 407779839 | High Sign | HFTD Tier 2 | Distribution | 2016-05-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017734 | 407779850 | High Sign | HFTD Tier 2 | Distribution | 2016-05-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017735 | 407779860 | High Sign | HFTD Tier 2 | Distribution | 2016-05-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017736 | 407779852 | High Sign | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017737 | 407779853 | High Sign | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017738 | 407779875 | High Sign | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017739 | 407779907 | High Sign | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017740 | 407779934 | High Sign | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017741 | 407779948 | High Sign | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017742 | 407779950 | High Sign | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017743 | 407779962 | High Sign | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017744 | 407780240 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017745 | 407780281 | High Sign | HFTD Tier 3 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017746 | 407780406 | High Sign | HFTD Tier 3 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017747 | 407780517 | High Sign | HFTD Tier 3 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017748 | 407780580 | Riser/Conduit | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017749 | 407780592 | Ground | HFTD Tier 3 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017750 | 407780757 | High Sign | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017751 | 407780766 | High Sign | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017752 | 407780785 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017753 | 407780786 | High Sign | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017754 | 407780792 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017755 | 407780805 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017756 | 407780823 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017757 | 407780824 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017758 | 407780833 | High Sign | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017759 | 407780873 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017760 | 407780907 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017761 | 407780959 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017762 | 407781005 | Guy | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017763 | 407781083 | Guy | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017764 | 407781090 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017765 | 407781095 | High Sign | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017766 | 407781930 | Guy | HFTD Tier 2 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017767 | 407782415 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017768 | 407782938 | Guy | HFTD Tier 3 | Distribution | 2016-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017769 | 407782981 | Guy | HFTD Tier 3 | Distribution | 2016-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017770 | 407783071 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017771 | 407783122 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017772 | 407783136 | Guy | HFTD Tier 2 | Distribution | 2016-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017773 | 407783731 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017774 | 407784032 | Molding | HFTD Tier 2 | Distribution | 2016-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017775 | 407784253 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017776 | 407784263 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017777 | 407784365 | Molding | HFTD Tier 3 | Distribution | 2016-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017778 | 407784394 | Guy Guard | HFTD Tier 3 | Distribution | 2016-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017779 | 407786081 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-05-10 | 42865 | 2 | Ignition Risk, no GO95 exception | [7 empty] | SCE | 2026 | 2
1120017780 | 407786213 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017781 | 407786226 | High Sign | HFTD Tier 2 | Distribution | 2016-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017782 | 407786271 | Guy | HFTD Tier 2 | Distribution | 2016-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017783 | 407786351 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017784 | 407786568 | Molding | HFTD Tier 3 | Distribution | 2016-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017785 | 407786647 | High Sign | HFTD Tier 3 | Distribution | 2016-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017786 | 407786702 | High Sign | HFTD Tier 3 | Distribution | 2016-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017787 | 407786797 | High Sign | HFTD Tier 3 | Distribution | 2016-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017788 | 407786823 | Molding | HFTD Tier 3 | Distribution | 2016-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017789 | 407787136 | Riser/Conduit | HFTD Tier 3 | Distribution | 2016-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017790 | 407787334 | Molding | HFTD Tier 3 | Distribution | 2016-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017791 | 407787496 | High Sign | HFTD Tier 3 | Distribution | 2016-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017792 | 407787511 | High Sign | HFTD Tier 3 | Distribution | 2016-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017793 | 407787534 | High Sign | HFTD Tier 3 | Distribution | 2016-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017794 | 407787952 | High Sign | HFTD Tier 2 | Distribution | 2016-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017795 | 407788154 | High Sign | HFTD Tier 2 | Distribution | 2016-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017796 | 407789295 | Molding | HFTD Tier 3 | Distribution | 2016-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017797 | 407789450 | Molding | HFTD Tier 3 | Distribution | 2016-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017798 | 407792019 | High Sign | HFTD Tier 2 | Distribution | 2016-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017799 | 407789970 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017800 | 407790160 | High Sign | HFTD Tier 3 | Distribution | 2016-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017801 | 407790289 | Vis Strips | HFTD Tier 2 | Distribution | 2016-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017802 | 407790294 | High Sign | HFTD Tier 2 | Distribution | 2016-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017803 | 407790304 | High Sign | HFTD Tier 2 | Distribution | 2016-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017804 | 407790331 | High Sign | HFTD Tier 3 | Distribution | 2016-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017805 | 407790450 | High Sign | HFTD Tier 2 | Distribution | 2016-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017806 | 407790504 | High Sign | HFTD Tier 3 | Distribution | 2016-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017807 | 407790567 | High Sign | HFTD Tier 2 | Distribution | 2016-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017808 | 407790581 | Vis Strips | HFTD Tier 3 | Distribution | 2016-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017809 | 407790782 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017810 | 407790853 | Molding | HFTD Tier 3 | Distribution | 2016-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017811 | 407792114 | High Sign | HFTD Tier 2 | Distribution | 2016-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017812 | 407792144 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017813 | 407792230 | Molding | HFTD Tier 2 | Distribution | 2016-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017814 | 407792239 | High Sign | HFTD Tier 3 | Distribution | 2016-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017815 | 407796020 | High Sign | HFTD Tier 2 | Distribution | 2016-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017816 | 407797071 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017817 | 407797079 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017818 | 407797311 | High Sign | HFTD Tier 2 | Distribution | 2016-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017819 | 407802084 | Molding | HFTD Tier 2 | Distribution | 2016-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017820 | 407799001 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017821 | 407799606 | High Sign | HFTD Tier 3 | Distribution | 2016-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017822 | 407799614 | High Sign | HFTD Tier 3 | Distribution | 2016-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017823 | 407800203 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017824 | 407800393 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017825 | 407800608 | Guy | HFTD Tier 2 | Distribution | 2016-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017826 | 407800763 | Molding | HFTD Tier 3 | Distribution | 2016-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017827 | 407800833 | High Sign | HFTD Tier 3 | Distribution | 2016-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017828 | 407800840 | Pole step | HFTD Tier 3 | Distribution | 2016-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017829 | 407800964 | High Sign | HFTD Tier 2 | Distribution | 2016-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017830 | 407801059 | Pole step | HFTD Tier 3 | Distribution | 2016-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017831 | 407801114 | Pole step | HFTD Tier 3 | Distribution | 2016-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017832 | 407801156 | High Sign | HFTD Tier 3 | Distribution | 2016-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017833 | 407801301 | High Sign | HFTD Tier 3 | Distribution | 2016-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017834 | 407802120 | High Sign | HFTD Tier 2 | Distribution | 2016-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017835 | 407802121 | Molding | HFTD Tier 2 | Distribution | 2016-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017836 | 407802891 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017837 | 407802899 | High Sign | HFTD Tier 3 | Distribution | 2016-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017838 | 407803149 | Guy | HFTD Tier 2 | Distribution | 2016-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017839 | 407804854 | High Sign | HFTD Tier 3 | Distribution | 2016-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017840 | 407804959 | Molding | HFTD Tier 3 | Distribution | 2016-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017841 | 407805007 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017842 | 407805011 | High Sign | HFTD Tier 3 | Distribution | 2016-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017843 | 407805311 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017844 | 407805695 | Molding | HFTD Tier 3 | Distribution | 2016-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017845 | 407805735 | High Sign | HFTD Tier 3 | Distribution | 2016-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017846 | 407805930 | Guy Guard | HFTD Tier 3 | Distribution | 2016-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017847 | 407808132 | Molding | HFTD Tier 2 | Distribution | 2016-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017848 | 407806296 | High Sign | HFTD Tier 3 | Distribution | 2016-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017849 | 407807239 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017850 | 407808205 | High Sign | HFTD Tier 3 | Distribution | 2016-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017851 | 407808231 | Guy | HFTD Tier 2 | Distribution | 2016-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017852 | 407808295 | Molding | HFTD Tier 3 | Distribution | 2016-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017853 | 407809419 | High Sign | HFTD Tier 3 | Distribution | 2016-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017854 | 407809495 | High Sign | HFTD Tier 3 | Distribution | 2016-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017855 | 407809533 | High Sign | HFTD Tier 3 | Distribution | 2016-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017856 | 407809534 | Guy | HFTD Tier 3 | Distribution | 2016-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017857 | 407809541 | High Sign | HFTD Tier 3 | Distribution | 2016-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017858 | 407809068 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-05-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017859 | 407811383 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017860 | 407811837 | High Sign | HFTD Tier 2 | Distribution | 2016-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017861 | 407812958 | Guy | HFTD Tier 3 | Distribution | 2016-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017862 | 407816326 | Molding | HFTD Tier 2 | Distribution | 2016-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017863 | 407816437 | High Sign | HFTD Tier 2 | Distribution | 2016-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017864 | 407816442 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017865 | 407816460 | High Sign | HFTD Tier 2 | Distribution | 2016-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017866 | 407816536 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017867 | 407816549 | Molding | HFTD Tier 3 | Distribution | 2016-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017868 | 407816586 | Bond | HFTD Tier 3 | Distribution | 2016-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017869 | 407816592 | Riser/Conduit | HFTD Tier 3 | Distribution | 2016-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017870 | 407816594 | Molding | HFTD Tier 3 | Distribution | 2016-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017871 | 407816597 | Molding | HFTD Tier 3 | Distribution | 2016-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017872 | 407816602 | Bond | HFTD Tier 3 | Distribution | 2016-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017873 | 407817117 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017874 | 407817388 | High Sign | HFTD Tier 3 | Distribution | 2016-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017875 | 407817439 | High Sign | HFTD Tier 3 | Distribution | 2016-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017876 | 407817528 | Molding | HFTD Tier 3 | Distribution | 2016-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017877 | 407817537 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017878 | 407817608 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017879 | 407817611 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017880 | 407817853 | Insulator | HFTD Tier 2 | Distribution | 2016-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017881 | 407817949 | Molding | HFTD Tier 3 | Distribution | 2016-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017882 | 407817957 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017883 | 407818104 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017884 | 407818142 | Molding | HFTD Tier 2 | Distribution | 2016-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017885 | 407818317 | High Sign | HFTD Tier 2 | Distribution | 2016-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017886 | 407820189 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017887 | 407820304 | Riser/Conduit | HFTD Tier 2 | Distribution | 2016-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017888 | 407820340 | Molding | HFTD Tier 2 | Distribution | 2016-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017889 | 407820363 | Riser/Conduit | HFTD Tier 2 | Distribution | 2016-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017890 | 407820366 | Pole step | HFTD Tier 2 | Distribution | 2016-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017891 | 407820390 | High Sign | HFTD Tier 2 | Distribution | 2016-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017892 | 407820588 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017893 | 407824195 | Guy | HFTD Tier 3 | Distribution | 2016-05-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017894 | 407825576 | Guy | HFTD Tier 2 | Distribution | 2016-05-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017895 | 407826664 | High Sign | HFTD Tier 3 | Distribution | 2016-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017896 | 407826675 | Guy | HFTD Tier 3 | Distribution | 2016-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017897 | 407827081 | Molding | HFTD Tier 3 | Distribution | 2016-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017898 | 407827194 | High Sign | HFTD Tier 2 | Distribution | 2016-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017899 | 407827382 | High Sign | HFTD Tier 3 | Distribution | 2016-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017900 | 407828681 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017901 | 407829095 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017902 | 407829660 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017903 | 407830556 | Molding | HFTD Tier 2 | Distribution | 2016-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017904 | 407830864 | Guy | HFTD Tier 3 | Distribution | 2016-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017905 | 407831463 | Guy | HFTD Tier 3 | Distribution | 2016-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017906 | 407831470 | Guy | HFTD Tier 3 | Distribution | 2016-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017907 | 407831471 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017908 | 407831491 | Guy | HFTD Tier 2 | Distribution | 2016-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017909 | 407831691 | High Sign | HFTD Tier 3 | Distribution | 2016-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017910 | 407831958 | Structure/Equip Itself | HFTD Tier 2 | Transmission | 2016-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017911 | 407831961 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017912 | 407831987 | Structure/Equip Itself | HFTD Tier 2 | Transmission | 2016-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017913 | 407831995 | Structure/Equip Itself | HFTD Tier 2 | Transmission | 2016-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017914 | 407832010 | Structure/Equip Itself | HFTD Tier 2 | Transmission | 2016-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017915 | 407832011 | Structure/Equip Itself | HFTD Tier 2 | Transmission | 2016-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017916 | 407833593 | High Sign | HFTD Tier 3 | Distribution | 2016-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017917 | 407833650 | Molding | HFTD Tier 3 | Distribution | 2016-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017918 | 407835019 | Molding | HFTD Tier 2 | Distribution | 2016-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017919 | 407835115 | High Sign | HFTD Tier 3 | Distribution | 2016-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017920 | 407838579 | Molding | HFTD Tier 2 | Distribution | 2016-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017921 | 407838637 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017922 | 407838763 | High Sign | HFTD Tier 2 | Distribution | 2016-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017923 | 407838770 | Molding | HFTD Tier 2 | Distribution | 2016-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017924 | 407838805 | Molding | HFTD Tier 2 | Distribution | 2016-06-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017925 | 407839700 | Molding | HFTD Tier 2 | Distribution | 2016-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017926 | 407839782 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017927 | 407839914 | High Sign | HFTD Tier 3 | Distribution | 2016-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017928 | 407839924 | Bond | HFTD Tier 3 | Distribution | 2016-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017929 | 407839932 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017930 | 407839979 | High Sign | HFTD Tier 2 | Distribution | 2016-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017931 | 407841334 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017932 | 407841444 | Riser/Conduit | HFTD Tier 2 | Distribution | 2016-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017933 | 407841452 | Pole step | HFTD Tier 2 | Distribution | 2016-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017934 | 407846419 | Guy | HFTD Tier 2 | Distribution | 2016-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017935 | 407842057 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017936 | 407842073 | Molding | HFTD Tier 2 | Distribution | 2016-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017937 | 407842437 | High Sign | HFTD Tier 2 | Distribution | 2016-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017938 | 407842467 | Guy | HFTD Tier 2 | Distribution | 2016-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017939 | 407842485 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017940 | 407842497 | Molding | HFTD Tier 2 | Distribution | 2016-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017941 | 407842835 | Molding | HFTD Tier 3 | Distribution | 2016-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017942 | 407842888 | Molding | HFTD Tier 3 | Distribution | 2016-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017943 | 407842889 | Molding | HFTD Tier 3 | Distribution | 2016-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017944 | 407842922 | High Sign | HFTD Tier 3 | Distribution | 2016-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017945 | 407842941 | Pole step | HFTD Tier 2 | Distribution | 2016-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017946 | 407842950 | High Sign | HFTD Tier 3 | Distribution | 2016-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017947 | 407845433 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017948 | 407845453 | High Sign | HFTD Tier 2 | Distribution | 2016-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017949 | 407845454 | High Sign | HFTD Tier 2 | Distribution | 2016-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017950 | 407845581 | High Sign | HFTD Tier 3 | Distribution | 2016-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017951 | 407845807 | Ground | HFTD Tier 3 | Distribution | 2016-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017952 | 407845923 | High Sign | HFTD Tier 3 | Distribution | 2016-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017953 | 407845960 | High Sign | HFTD Tier 3 | Distribution | 2016-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017954 | 407846439 | High Sign | HFTD Tier 3 | Distribution | 2016-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017955 | 407846444 | High Sign | HFTD Tier 3 | Distribution | 2016-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017956 | 407846514 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017957 | 407848345 | Guy Guard | HFTD Tier 2 | Distribution | 2016-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017958 | 407848411 | High Sign | HFTD Tier 2 | Distribution | 2016-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017959 | 407849145 | Molding | HFTD Tier 2 | Distribution | 2016-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017960 | 407849152 | Molding | HFTD Tier 2 | Distribution | 2016-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017961 | 407849154 | High Sign | HFTD Tier 2 | Distribution | 2016-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017962 | 407849155 | Termination | HFTD Tier 2 | Distribution | 2016-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017963 | 407849166 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017964 | 407849171 | Molding | HFTD Tier 2 | Distribution | 2016-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017965 | 415054953 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-06-08 | 43259 | 2 | Ignition Risk, no GO95 exception | [7 empty] | SCE | 2026 | 2
1120017966 | 407849406 | Molding | HFTD Tier 2 | Distribution | 2016-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017967 | 407849488 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017968 | 407849667 | ID Markings | HFTD Tier 3 | Distribution | 2016-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017969 | 407849696 | High Sign | HFTD Tier 3 | Distribution | 2016-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017970 | 407849718 | High Sign | HFTD Tier 3 | Distribution | 2016-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017971 | 407850722 | Molding | HFTD Tier 2 | Distribution | 2016-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017972 | 407850823 | High Sign | HFTD Tier 2 | Distribution | 2016-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017973 | 407850967 | Vis Strips | HFTD Tier 2 | Distribution | 2016-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017974 | 407851191 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017975 | 407851304 | Molding | HFTD Tier 3 | Distribution | 2016-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017976 | 407853335 | High Sign | HFTD Tier 2 | Distribution | 2016-06-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017977 | 407852311 | Guy | HFTD Tier 3 | Distribution | 2016-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017978 | 407852317 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017979 | 407853987 | High Sign | HFTD Tier 3 | Distribution | 2016-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017980 | 407853989 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-06-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017981 | 407854845 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017982 | 407855556 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017983 | 407855587 | High Sign | HFTD Tier 2 | Distribution | 2016-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017984 | 407855743 | Molding | HFTD Tier 2 | Distribution | 2016-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017985 | 407855844 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017986 | 407856087 | High Sign | HFTD Tier 2 | Distribution | 2016-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017987 | 407857385 | High Sign | HFTD Tier 2 | Distribution | 2016-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017988 | 407857395 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017989 | 407858203 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017990 | 407859832 | Molding | HFTD Tier 3 | Distribution | 2016-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017991 | 407860002 | High Sign | HFTD Tier 3 | Distribution | 2016-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017992 | 407860201 | Guy Guard | HFTD Tier 3 | Distribution | 2016-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017993 | 407860203 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017994 | 407860290 | Guy | HFTD Tier 3 | Distribution | 2016-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017995 | 407860315 | Guy | HFTD Tier 3 | Distribution | 2016-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017996 | 407860382 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017997 | 407860392 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017998 | 407860416 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120017999 | 407860438 | High Sign | HFTD Tier 2 | Distribution | 2016-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018000 | 407860451 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018001 | 407860796 | Termination | HFTD Tier 2 | Distribution | 2016-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018002 | 407860818 | Molding | HFTD Tier 2 | Distribution | 2016-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018003 | 407860898 | Molding | HFTD Tier 2 | Distribution | 2016-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018004 | 407860926 | High Sign | HFTD Tier 3 | Distribution | 2016-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018005 | 407860939 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018006 | 407860953 | High Sign | HFTD Tier 2 | Distribution | 2016-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018007 | 407860989 | High Sign | HFTD Tier 3 | Distribution | 2016-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018008 | 407861074 | High Sign | HFTD Tier 3 | Distribution | 2016-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018009 | 407861847 | Molding | HFTD Tier 2 | Distribution | 2016-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018010 | 407861879 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018011 | 407861953 | Guy Guard | HFTD Tier 3 | Distribution | 2016-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018012 | 407862297 | Guy | HFTD Tier 2 | Distribution | 2016-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018013 | 407862387 | High Sign | HFTD Tier 3 | Distribution | 2016-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018014 | 407863643 | High Sign | HFTD Tier 2 | Distribution | 2016-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018015 | 407863897 | High Sign | HFTD Tier 2 | Distribution | 2016-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018016 | 407863899 | High Sign | HFTD Tier 2 | Distribution | 2016-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018017 | 407863900 | High Sign | HFTD Tier 2 | Distribution | 2016-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018018 | 407867306 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018019 | 407864811 | High Sign | HFTD Tier 3 | Distribution | 2016-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018020 | 407864820 | High Sign | HFTD Tier 3 | Distribution | 2016-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018021 | 407864850 | High Sign | HFTD Tier 3 | Distribution | 2016-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018022 | 407865043 | High Sign | HFTD Tier 3 | Distribution | 2016-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018023 | 407865339 | Guy | HFTD Tier 2 | Distribution | 2016-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018024 | 407865412 | Guy Guard | HFTD Tier 2 | Distribution | 2016-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018025 | 407865420 | Guy | HFTD Tier 2 | Distribution | 2016-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018026 | 407865513 | High Sign | HFTD Tier 3 | Distribution | 2016-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018027 | 407865563 | High Sign | HFTD Tier 3 | Distribution | 2016-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018028 | 407865612 | Molding | HFTD Tier 3 | Distribution | 2016-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018029 | 407865722 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018030 | 407865746 | High Sign | HFTD Tier 3 | Distribution | 2016-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018031 | 407865765 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018032 | 407866270 | High Sign | HFTD Tier 3 | Distribution | 2016-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018033 | 407866299 | High Sign | HFTD Tier 3 | Distribution | 2016-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018034 | 407866547 | High Sign | HFTD Tier 3 | Distribution | 2016-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018035 | 407866694 | High Sign | HFTD Tier 3 | Distribution | 2016-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018036 | 407866874 | Molding | HFTD Tier 3 | Distribution | 2016-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018037 | 407867288 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018038 | 407867645 | High Sign | HFTD Tier 3 | Distribution | 2016-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018039 | 407867704 | High Sign | HFTD Tier 3 | Distribution | 2016-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018040 | 407868557 | Molding | HFTD Tier 2 | Distribution | 2016-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018041 | 407868576 | High Sign | HFTD Tier 2 | Distribution | 2016-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018042 | 407868663 | High Sign | HFTD Tier 2 | Distribution | 2016-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018043 | 407868732 | High Sign | HFTD Tier 2 | Distribution | 2016-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018044 | 407868790 | High Sign | HFTD Tier 2 | Distribution | 2016-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018045 | 407868791 | High Sign | HFTD Tier 2 | Distribution | 2016-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018046 | 407869415 | Guy Guard | HFTD Tier 3 | Distribution | 2016-06-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018047 | 407870209 | Molding | HFTD Tier 2 | Distribution | 2016-06-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018048 | 407871135 | Guy | HFTD Tier 3 | Distribution | 2016-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018049 | 407871221 | Vis Strips | HFTD Tier 2 | Distribution | 2016-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018050 | 407871500 | Molding | HFTD Tier 3 | Distribution | 2016-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018051 | 407871893 | Guy Guard | HFTD Tier 2 | Distribution | 2016-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018052 | 407872034 | High Sign | HFTD Tier 2 | Distribution | 2016-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018053 | 407872035 | Guy Guard | HFTD Tier 3 | Distribution | 2016-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018054 | 407872268 | Guy | HFTD Tier 2 | Distribution | 2016-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018055 | 407872313 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018056 | 407873370 | High Sign | HFTD Tier 3 | Distribution | 2016-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018057 | 407873535 | Guy | HFTD Tier 3 | Distribution | 2016-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018058 | 407873614 | High Sign | HFTD Tier 3 | Distribution | 2016-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018059 | 407874065 | Molding | HFTD Tier 3 | Distribution | 2016-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018060 | 407874067 | Molding | HFTD Tier 3 | Distribution | 2016-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018061 | 407874165 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018062 | 407874169 | Molding | HFTD Tier 3 | Distribution | 2016-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018063 | 407874481 | Molding | HFTD Tier 3 | Distribution | 2016-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018064 | 407874644 | Guy Guard | HFTD Tier 3 | Distribution | 2016-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018065 | 407874658 | High Sign | HFTD Tier 3 | Distribution | 2016-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018066 | 407874687 | High Sign | HFTD Tier 3 | Distribution | 2016-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018067 | 407874848 | High Sign | HFTD Tier 2 | Distribution | 2016-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018068 | 407874894 | High Sign | HFTD Tier 2 | Distribution | 2016-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018069 | 407874915 | High Sign | HFTD Tier 2 | Distribution | 2016-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018070 | 407874980 | Guy Guard | HFTD Tier 3 | Distribution | 2016-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018071 | 407875078 | Guy | HFTD Tier 3 | Distribution | 2016-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018072 | 407875079 | Guy | HFTD Tier 3 | Distribution | 2016-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018073 | 407875109 | Guy | HFTD Tier 3 | Distribution | 2016-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018074 | 407875213 | Molding | HFTD Tier 3 | Distribution | 2016-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018075 | 407876332 | High Sign | HFTD Tier 3 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018076 | 407876334 | Guy | HFTD Tier 3 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018077 | 407876350 | Molding | HFTD Tier 3 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018078 | 407876371 | High Sign | HFTD Tier 3 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018079 | 407876383 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018080 | 407876470 | Riser/Conduit | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018081 | 407876682 | Guy | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018082 | 407876936 | Riser/Conduit | HFTD Tier 3 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018083 | 407877753 | Guy | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018084 | 407877884 | Guy Guard | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018085 | 407877923 | Guy Guard | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018086 | 407877946 | Guy Guard | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018087 | 407877947 | Guy | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018088 | 407877954 | Guy Guard | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018089 | 407877955 | Guy Guard | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018090 | 407877983 | Guy Guard | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018091 | 407877990 | Guy Guard | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018092 | 407877992 | Guy | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018093 | 407878000 | Guy | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018094 | 407878002 | Guy Guard | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018095 | 407878007 | Guy Guard | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018096 | 407878011 | Guy Guard | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018097 | 407878013 | Guy Guard | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018098 | 407878034 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018099 | 407878246 | Molding | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018100 | 407878368 | High Sign | HFTD Tier 3 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018101 | 407881955 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018102 | 407881957 | Molding | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018103 | 407882004 | Molding | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018104 | 407882012 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018105 | 407882031 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018106 | 407882831 | High Sign | HFTD Tier 2 | Distribution | 2016-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018107 | 407879009 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018108 | 407881030 | Guy | HFTD Tier 2 | Distribution | 2016-06-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018109 | 407884693 | Molding | HFTD Tier 2 | Distribution | 2016-06-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018110 | 407884702 | High Sign | HFTD Tier 2 | Distribution | 2016-06-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018111 | 407885938 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-06-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018112 | 407885991 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-06-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018113 | 407886033 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-06-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018114 | 407886036 | Guy | HFTD Tier 2 | Distribution | 2016-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018115 | 407886051 | Guy | HFTD Tier 2 | Distribution | 2016-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018116 | 407886077 | High Sign | HFTD Tier 2 | Distribution | 2016-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018117 | 407886175 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018118 | 407886515 | High Sign | HFTD Tier 3 | Distribution | 2016-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018119 | 407886640 | Guy | HFTD Tier 2 | Distribution | 2016-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018120 | 407886981 | Guy | HFTD Tier 3 | Distribution | 2016-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018121 | 407887175 | Guy Guard | HFTD Tier 3 | Distribution | 2016-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018122 | 407888262 | Guy Guard | HFTD Tier 3 | Distribution | 2016-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018123 | 407888286 | Riser/Conduit | HFTD Tier 3 | Distribution | 2016-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018124 | 407889299 | Termination | HFTD Tier 2 | Distribution | 2016-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018125 | 407889307 | Termination | HFTD Tier 2 | Distribution | 2016-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018126 | 407889503 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018127 | 407889715 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018128 | 407889744 | Molding | HFTD Tier 2 | Distribution | 2016-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018129 | 407890138 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018130 | 407890257 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018131 | 407890477 | Molding | HFTD Tier 3 | Distribution | 2016-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018132 | 407890507 | High Sign | HFTD Tier 3 | Distribution | 2016-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018133 | 407890534 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018134 | 407890646 | Molding | HFTD Tier 3 | Distribution | 2016-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018135 | 407893984 | Termination | HFTD Tier 2 | Distribution | 2016-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018136 | 407894063 | High Sign | HFTD Tier 2 | Distribution | 2016-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018137 | 407894072 | High Sign | HFTD Tier 2 | Distribution | 2016-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018138 | 407894341 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018139 | 407895292 | Molding | HFTD Tier 2 | Distribution | 2016-06-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018140 | 407895490 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-06-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018141 | 407895609 | Molding | HFTD Tier 2 | Distribution | 2016-06-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018142 | 407895626 | Ground | HFTD Tier 2 | Distribution | 2016-06-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018143 | 407895763 | Guy | HFTD Tier 3 | Distribution | 2016-06-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018144 | 407895866 | Guy | HFTD Tier 3 | Distribution | 2016-06-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018145 | 407895887 | Guy Guard | HFTD Tier 2 | Distribution | 2016-06-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018146 | 407896371 | High Sign | HFTD Tier 2 | Distribution | 2016-06-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018147 | 407898400 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-07-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018148 | 407903293 | Riser/Conduit | HFTD Tier 2 | Distribution | 2016-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018149 | 407903417 | Riser/Conduit | HFTD Tier 2 | Distribution | 2016-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018150 | 407903422 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018151 | 407904305 | Insulator | HFTD Tier 2 | Distribution | 2016-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018152 | 407904383 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018153 | 407904417 | Pole step | HFTD Tier 3 | Distribution | 2016-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018154 | 407904426 | High Sign | HFTD Tier 3 | Distribution | 2016-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018155 | 407904451 | Molding | HFTD Tier 3 | Distribution | 2016-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018156 | 407904498 | High Sign | HFTD Tier 3 | Distribution | 2016-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018157 | 407904686 | High Sign | HFTD Tier 3 | Distribution | 2016-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018158 | 407907317 | Molding | HFTD Tier 2 | Distribution | 2016-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018159 | 407907451 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018160 | 407907759 | High Sign | HFTD Tier 3 | Distribution | 2016-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018161 | 407907788 | Molding | HFTD Tier 3 | Distribution | 2016-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018162 | 407907841 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018163 | 407907865 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018164 | 407907876 | High Sign | HFTD Tier 3 | Distribution | 2016-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018165 | 407907898 | Guy Guard | HFTD Tier 3 | Distribution | 2016-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018166 | 407907921 | High Sign | HFTD Tier 3 | Distribution | 2016-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018167 | 407908122 | Riser/Conduit | HFTD Tier 2 | Distribution | 2016-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018168 | 407908131 | Guy | HFTD Tier 2 | Distribution | 2016-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018169 | 407908146 | Molding | HFTD Tier 2 | Distribution | 2016-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018170 | 407909943 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018171 | 407910230 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018172 | 407910737 | Guy | HFTD Tier 2 | Distribution | 2016-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018173 | 407910825 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018174 | 407911398 | Guy | HFTD Tier 3 | Distribution | 2016-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018175 | 407911471 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-07-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018176 | 407913449 | Insulator | HFTD Tier 2 | Distribution | 2016-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018177 | 407913518 | Molding | HFTD Tier 2 | Distribution | 2016-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018178 | 407913550 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018179 | 407913553 | Molding | HFTD Tier 2 | Distribution | 2016-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018180 | 407913582 | Pole step | HFTD Tier 2 | Distribution | 2016-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018181 | 407913640 | High Sign | HFTD Tier 2 | Distribution | 2016-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018182 | 407913797 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018183 | 407914429 | Pole step | HFTD Tier 3 | Distribution | 2016-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018184 | 407914589 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018185 | 407914591 | High Sign | HFTD Tier 3 | Distribution | 2016-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018186 | 407914600 | High Sign | HFTD Tier 3 | Distribution | 2016-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018187 | 407915616 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018188 | 407915623 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-07-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018189 | 407916609 | High Sign | HFTD Tier 3 | Distribution | 2016-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018190 | 407916630 | Guy | HFTD Tier 3 | Distribution | 2016-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018191 | 407916815 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018192 | 407916912 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018193 | 407917023 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018194 | 407917059 | Riser/Conduit | HFTD Tier 2 | Distribution | 2016-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018195 | 407917234 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018196 | 407917335 | High Sign | HFTD Tier 3 | Distribution | 2016-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018197 | 407917398 | Pole step | HFTD Tier 3 | Distribution | 2016-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018198 | 407917417 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018199 | 407917427 | Insulator | HFTD Tier 3 | Distribution | 2016-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018200 | 407917433 | Pole step | HFTD Tier 3 | Distribution | 2016-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018201 | 407917896 | High Sign | HFTD Tier 2 | Distribution | 2016-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018202 | 407918059 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018203 | 407918160 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018204 | 407918243 | Molding | HFTD Tier 2 | Distribution | 2016-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018205 | 407918434 | High Sign | HFTD Tier 3 | Distribution | 2016-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018206 | 407918555 | Molding | HFTD Tier 2 | Distribution | 2016-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018207 | 407918566 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018208 | 407918887 | Guy | HFTD Tier 3 | Distribution | 2016-07-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018209 | 407920816 | High Sign | HFTD Tier 3 | Distribution | 2016-07-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018210 | 407921945 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-07-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018211 | 407922086 | Molding | HFTD Tier 2 | Distribution | 2016-07-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018212 | 407922137 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-07-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018213 | 407922552 | High Sign | HFTD Tier 3 | Distribution | 2016-07-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018214 | 407922581 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-07-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018215 | 407923458 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-07-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018216 | 407923781 | Guy | HFTD Tier 2 | Distribution | 2016-07-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018217 | 407924066 | Guy | HFTD Tier 2 | Distribution | 2016-07-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018218 | 407924096 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-07-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018219 | 407924122 | Insulator | HFTD Tier 2 | Distribution | 2016-07-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018220 | 407924269 | High Sign | HFTD Tier 3 | Distribution | 2016-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018221 | 407924295 | High Sign | HFTD Tier 3 | Distribution | 2016-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018222 | 407924305 | High Sign | HFTD Tier 3 | Distribution | 2016-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018223 | 407924308 | Insulator | HFTD Tier 2 | Distribution | 2016-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018224 | 407924309 | High Sign | HFTD Tier 2 | Distribution | 2016-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018225 | 407924331 | Molding | HFTD Tier 3 | Distribution | 2016-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018226 | 407924368 | Guy Guard | HFTD Tier 3 | Distribution | 2016-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018227 | 407924587 | Pole step | HFTD Tier 2 | Distribution | 2016-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018228 | 407924637 | Molding | HFTD Tier 3 | Distribution | 2016-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018229 | 407924939 | Termination | HFTD Tier 2 | Distribution | 2016-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018230 | 407925761 | Guy | HFTD Tier 2 | Distribution | 2016-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018231 | 407925821 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018232 | 407925959 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018233 | 407926297 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018234 | 407926302 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018235 | 407926351 | Guy | HFTD Tier 2 | Distribution | 2016-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018236 | 407926829 | High Sign | HFTD Tier 3 | Distribution | 2016-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018237 | 407926854 | Guy | HFTD Tier 3 | Distribution | 2016-07-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018238 | 407928885 | Molding | HFTD Tier 2 | Distribution | 2016-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018239 | 407929212 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-07-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018240 | 407931215 | High Sign | HFTD Tier 3 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018241 | 407931238 | High Sign | HFTD Tier 3 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018242 | 407931242 | High Sign | HFTD Tier 3 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018243 | 407931251 | High Sign | HFTD Tier 3 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018244 | 407931292 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018245 | 407931300 | High Sign | HFTD Tier 3 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018246 | 407931310 | High Sign | HFTD Tier 3 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018247 | 407931322 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018248 | 407931328 | Molding | HFTD Tier 3 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018249 | 407931468 | High Sign | HFTD Tier 3 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018250 | 407931503 | High Sign | HFTD Tier 3 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018251 | 407931639 | High Sign | HFTD Tier 3 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018252 | 407931744 | Molding | HFTD Tier 3 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018253 | 407931780 | High Sign | HFTD Tier 3 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018254 | 407932127 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018255 | 407932189 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018256 | 407932197 | High Sign | HFTD Tier 2 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018257 | 407932222 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018258 | 407932762 | Pole step | HFTD Tier 3 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018259 | 407932797 | Pole step | HFTD Tier 3 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018260 | 407932810 | Molding | HFTD Tier 3 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018261 | 407932820 | Molding | HFTD Tier 3 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018262 | 407933696 | High Sign | HFTD Tier 3 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018263 | 407933771 | High Sign | HFTD Tier 3 | Distribution | 2016-07-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018264 | 407933919 | Guy | HFTD Tier 3 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018265 | 407934272 | High Sign | HFTD Tier 3 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018266 | 407934300 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018267 | 407934418 | Molding | HFTD Tier 2 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018268 | 407934463 | Guy Guard | HFTD Tier 3 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018269 | 407934469 | Molding | HFTD Tier 2 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018270 | 407934487 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018271 | 407934511 | Molding | HFTD Tier 2 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018272 | 407934521 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018273 | 407934844 | Molding | HFTD Tier 3 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018274 | 407935024 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018275 | 407935025 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018276 | 407935036 | High Sign | HFTD Tier 2 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018277 | 407935038 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018278 | 407935101 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018279 | 407935206 | High Sign | HFTD Tier 3 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018280 | 407935238 | Molding | HFTD Tier 3 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018281 | 407935254 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018282 | 407935278 | High Sign | HFTD Tier 2 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018283 | 407935313 | High Sign | HFTD Tier 2 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018284 | 407935459 | High Sign | HFTD Tier 2 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018285 | 407936744 | Riser/Conduit | HFTD Tier 2 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018286 | 407936827 | Guy | HFTD Tier 2 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018287 | 407936835 | Guy Guard | HFTD Tier 2 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018288 | 407936863 | Guy | HFTD Tier 2 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018289 | 407937533 | High Sign | HFTD Tier 2 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018290 | 407937547 | Guy | HFTD Tier 2 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018291 | 407938175 | Molding | HFTD Tier 2 | Distribution | 2016-07-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018292 | 407937669 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018293 | 407937672 | High Sign | HFTD Tier 2 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018294 | 407937676 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018295 | 407937700 | High Sign | HFTD Tier 2 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018296 | 407937801 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018297 | 407937808 | Molding | HFTD Tier 2 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018298 | 407938106 | High Sign | HFTD Tier 2 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018299 | 407938341 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018300 | 407938489 | Molding | HFTD Tier 2 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018301 | 407938755 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018302 | 407938760 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018303 | 407938872 | Guy | HFTD Tier 3 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018304 | 407938917 | Molding | HFTD Tier 3 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018305 | 407938940 | Guy | HFTD Tier 3 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018306 | 407938960 | Pole step | HFTD Tier 3 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018307 | 407939947 | Guy | HFTD Tier 2 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018308 | 407940637 | High Sign | HFTD Tier 2 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018309 | 407941411 | Guy | HFTD Tier 2 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018310 | 407943432 | Molding | HFTD Tier 3 | Distribution | 2016-07-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018311 | 407941267 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018312 | 407941269 | High Sign | HFTD Tier 3 | Distribution | 2016-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018313 | 407941281 | High Sign | HFTD Tier 2 | Distribution | 2016-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018314 | 407941329 | Molding | HFTD Tier 3 | Distribution | 2016-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018315 | 407941471 | High Sign | HFTD Tier 2 | Distribution | 2016-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018316 | 407941483 | High Sign | HFTD Tier 2 | Distribution | 2016-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018317 | 407941514 | High Sign | HFTD Tier 3 | Distribution | 2016-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018318 | 407941536 | High Sign | HFTD Tier 3 | Distribution | 2016-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018319 | 407941693 | High Sign | HFTD Tier 3 | Distribution | 2016-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018320 | 407941933 | Guy Guard | HFTD Tier 3 | Distribution | 2016-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018321 | 407942029 | High Sign | HFTD Tier 3 | Distribution | 2016-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018322 | 407942032 | Molding | HFTD Tier 2 | Distribution | 2016-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018323 | 407942163 | High Sign | HFTD Tier 2 | Distribution | 2016-07-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018324 | 407943966 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018325 | 407944358 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018326 | 407945279 | High Sign | HFTD Tier 2 | Distribution | 2016-07-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018327 | 407947438 | Guy Guard | HFTD Tier 3 | Distribution | 2016-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018328 | 407947480 | Guy | HFTD Tier 3 | Distribution | 2016-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018329 | 407947692 | Guy | HFTD Tier 2 | Distribution | 2016-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018330 | 407948312 | Molding | HFTD Tier 3 | Distribution | 2016-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018331 | 407948341 | High Sign | HFTD Tier 3 | Distribution | 2016-07-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018332 | 407950551 | Guy Guard | HFTD Tier 2 | Distribution | 2016-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018333 | 407950828 | High Sign | HFTD Tier 3 | Distribution | 2016-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018334 | 407950907 | High Sign | HFTD Tier 3 | Distribution | 2016-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018335 | 407950921 | High Sign | HFTD Tier 3 | Distribution | 2016-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018336 | 407950941 | Guy | HFTD Tier 3 | Distribution | 2016-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018337 | 407950950 | High Sign | HFTD Tier 3 | Distribution | 2016-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018338 | 407952516 | High Sign | HFTD Tier 2 | Distribution | 2016-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018339 | 407952523 | High Sign | HFTD Tier 2 | Distribution | 2016-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018340 | 407952533 | High Sign | HFTD Tier 2 | Distribution | 2016-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018341 | 407952542 | Molding | HFTD Tier 2 | Distribution | 2016-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018342 | 407952921 | Molding | HFTD Tier 3 | Distribution | 2016-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018343 | 407952923 | Guy | HFTD Tier 3 | Distribution | 2016-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018344 | 407952985 | Molding | HFTD Tier 2 | Distribution | 2016-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018345 | 407953151 | High Sign | HFTD Tier 3 | Distribution | 2016-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018346 | 407953297 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018347 | 407953428 | Molding | HFTD Tier 3 | Distribution | 2016-07-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018348 | 407954338 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018349 | 407954342 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018350 | 407954361 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018351 | 407954536 | Molding | HFTD Tier 3 | Distribution | 2016-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018352 | 407954678 | High Sign | HFTD Tier 3 | Distribution | 2016-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018353 | 407955196 | Molding | HFTD Tier 3 | Distribution | 2016-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018354 | 407955841 | High Sign | HFTD Tier 3 | Distribution | 2016-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018355 | 407955859 | High Sign | HFTD Tier 3 | Distribution | 2016-07-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018356 | 407958435 | Guy Guard | HFTD Tier 3 | Distribution | 2016-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018357 | 407958706 | Guy Guard | HFTD Tier 3 | Distribution | 2016-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018358 | 407964514 | High Sign | HFTD Tier 2 | Distribution | 2016-07-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018359 | 407963602 | Guy | HFTD Tier 3 | Distribution | 2016-08-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018360 | 407964543 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-08-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018361 | 407964568 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-08-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018362 | 407964599 | High Sign | HFTD Tier 3 | Distribution | 2016-08-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018363 | 407964645 | High Sign | HFTD Tier 3 | Distribution | 2016-08-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018364 | 407964656 | Molding | HFTD Tier 3 | Distribution | 2016-08-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018365 | 407964658 | High Sign | HFTD Tier 3 | Distribution | 2016-08-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018366 | 407964659 | High Sign | HFTD Tier 3 | Distribution | 2016-08-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018367 | 407964665 | High Sign | HFTD Tier 3 | Distribution | 2016-08-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018368 | 407964694 | High Sign | HFTD Tier 3 | Distribution | 2016-08-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018369 | 407967197 | Molding | HFTD Tier 2 | Distribution | 2016-08-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018370 | 407969190 | High Sign | HFTD Tier 2 | Distribution | 2016-08-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018371 | 407970360 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-08-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018372 | 415054954 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-08-02 | 42949 | 2 | Ignition Risk, no GO95 exception | [7 empty] | SCE | 2026 | 2
1120018373 | 407970942 | High Sign | HFTD Tier 3 | Distribution | 2016-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018374 | 407971046 | High Sign | HFTD Tier 3 | Distribution | 2016-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018375 | 407971130 | High Sign | HFTD Tier 3 | Distribution | 2016-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018376 | 407971171 | Guy Guard | HFTD Tier 2 | Distribution | 2016-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018377 | 407971209 | Guy | HFTD Tier 2 | Distribution | 2016-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018378 | 407971220 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018379 | 407971267 | Termination | HFTD Tier 2 | Distribution | 2016-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018380 | 407971319 | Anchor | HFTD Tier 2 | Distribution | 2016-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018381 | 407971426 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018382 | 407971468 | Guy | HFTD Tier 2 | Distribution | 2016-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018383 | 407971514 | High Sign | HFTD Tier 3 | Distribution | 2016-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018384 | 407971525 | Guy | HFTD Tier 2 | Distribution | 2016-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018385 | 407971670 | Guy Guard | HFTD Tier 2 | Distribution | 2016-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018386 | 407971711 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018387 | 407971935 | Guy | HFTD Tier 3 | Distribution | 2016-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018388 | 407971993 | Guy | HFTD Tier 3 | Distribution | 2016-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018389 | 407972853 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018390 | 407972967 | High Sign | HFTD Tier 2 | Distribution | 2016-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018391 | 407974130 | Molding | HFTD Tier 2 | Distribution | 2016-08-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018392 | 407975015 | Pole step | HFTD Tier 2 | Distribution | 2016-08-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018393 | 407975129 | Guy | HFTD Tier 3 | Distribution | 2016-08-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018394 | 407975162 | High Sign | HFTD Tier 3 | Distribution | 2016-08-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018395 | 407975233 | High Sign | HFTD Tier 2 | Distribution | 2016-08-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018396 | 407977230 | High Sign | HFTD Tier 2 | Distribution | 2016-08-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018397 | 407978103 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018398 | 407978193 | Molding | HFTD Tier 2 | Distribution | 2016-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018399 | 407978524 | Molding | HFTD Tier 2 | Distribution | 2016-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018400 | 407978604 | Molding | HFTD Tier 2 | Distribution | 2016-08-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018401 | 407981954 | Molding | HFTD Tier 2 | Distribution | 2016-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018402 | 407982069 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018403 | 407982078 | Riser/Conduit | HFTD Tier 2 | Distribution | 2016-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018404 | 407982079 | Pole step | HFTD Tier 2 | Distribution | 2016-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018405 | 407982104 | Molding | HFTD Tier 2 | Distribution | 2016-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018406 | 407982647 | High Sign | HFTD Tier 2 | Distribution | 2016-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018407 | 407982711 | High Sign | HFTD Tier 3 | Distribution | 2016-08-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018408 | 407985158 | High Sign | HFTD Tier 2 | Distribution | 2016-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018409 | 407985240 | Molding | HFTD Tier 2 | Distribution | 2016-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018410 | 407985285 | High Sign | HFTD Tier 2 | Distribution | 2016-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018411 | 407985319 | High Sign | HFTD Tier 2 | Distribution | 2016-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018412 | 407985448 | Anchor | HFTD Tier 2 | Distribution | 2016-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018413 | 407985478 | High Sign | HFTD Tier 2 | Distribution | 2016-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018414 | 407985484 | Molding | HFTD Tier 2 | Distribution | 2016-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018415 | 407986048 | Molding | HFTD Tier 3 | Distribution | 2016-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018416 | 407986068 | Molding | HFTD Tier 3 | Distribution | 2016-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018417 | 407986117 | High Sign | HFTD Tier 3 | Distribution | 2016-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018418 | 407986128 | Molding | HFTD Tier 3 | Distribution | 2016-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018419 | 407986129 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018420 | 407986170 | Molding | HFTD Tier 3 | Distribution | 2016-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018421 | 407986173 | High Sign | HFTD Tier 2 | Distribution | 2016-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018422 | 407986181 | Molding | HFTD Tier 3 | Distribution | 2016-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018423 | 407986226 | High Sign | HFTD Tier 2 | Distribution | 2016-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018424 | 407986263 | Guy | HFTD Tier 2 | Distribution | 2016-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018425 | 407987045 | Molding | HFTD Tier 2 | Distribution | 2016-08-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018426 | 407988975 | Guy | HFTD Tier 3 | Distribution | 2016-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018427 | 407988978 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018428 | 407989026 | Molding | HFTD Tier 3 | Distribution | 2016-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018429 | 407989052 | High Sign | HFTD Tier 3 | Distribution | 2016-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018430 | 407989169 | High Sign | HFTD Tier 3 | Distribution | 2016-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018431 | 407989250 | Molding | HFTD Tier 3 | Distribution | 2016-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018432 | 407989320 | Guy | HFTD Tier 2 | Distribution | 2016-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018433 | 407989476 | High Sign | HFTD Tier 2 | Distribution | 2016-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018434 | 407989544 | High Sign | HFTD Tier 2 | Distribution | 2016-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018435 | 407989660 | Molding | HFTD Tier 3 | Distribution | 2016-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018436 | 407989725 | High Sign | HFTD Tier 2 | Distribution | 2016-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018437 | 407989827 | Molding | HFTD Tier 3 | Distribution | 2016-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018438 | 407989871 | High Sign | HFTD Tier 2 | Distribution | 2016-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018439 | 407990016 | Guy | HFTD Tier 2 | Distribution | 2016-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018440 | 407990098 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018441 | 407990123 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018442 | 407992927 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018443 | 407992958 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018444 | 407995130 | High Sign | HFTD Tier 3 | Distribution | 2016-08-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018445 | 407992567 | High Sign | HFTD Tier 3 | Distribution | 2016-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018446 | 407992582 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018447 | 407992585 | High Sign | HFTD Tier 3 | Distribution | 2016-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018448 | 407992731 | Guy | HFTD Tier 3 | Distribution | 2016-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018449 | 407992972 | High Sign | HFTD Tier 2 | Distribution | 2016-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018450 | 407993051 | High Sign | HFTD Tier 2 | Distribution | 2016-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018451 | 407993230 | Molding | HFTD Tier 3 | Distribution | 2016-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018452 | 407993241 | Guy | HFTD Tier 3 | Distribution | 2016-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018453 | 407993254 | High Sign | HFTD Tier 3 | Distribution | 2016-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018454 | 407993290 | High Sign | HFTD Tier 3 | Distribution | 2016-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018455 | 407993528 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018456 | 407993759 | High Sign | HFTD Tier 2 | Distribution | 2016-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018457 | 407993792 | Guy | HFTD Tier 3 | Distribution | 2016-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018458 | 407995089 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018459 | 407995097 | High Sign | HFTD Tier 3 | Distribution | 2016-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018460 | 407995145 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-08-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018461 | 407996159 | Molding | HFTD Tier 3 | Distribution | 2016-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018462 | 407996284 | Molding | HFTD Tier 3 | Distribution | 2016-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018463 | 407996288 | Guy | HFTD Tier 3 | Distribution | 2016-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018464 | 407996306 | Guy | HFTD Tier 3 | Distribution | 2016-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018465 | 407996377 | Guy | HFTD Tier 3 | Distribution | 2016-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018466 | 407996471 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-08-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018467 | 407999265 | Guy | HFTD Tier 3 | Distribution | 2016-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018468 | 407999279 | Guy | HFTD Tier 3 | Distribution | 2016-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018469 | 407999304 | Guy | HFTD Tier 3 | Distribution | 2016-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018470 | 407999547 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018471 | 407999673 | Termination | HFTD Tier 2 | Distribution | 2016-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018472 | 407999719 | High Sign | HFTD Tier 2 | Distribution | 2016-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018473 | 408000274 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018474 | 408000311 | Molding | HFTD Tier 3 | Distribution | 2016-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018475 | 408001448 | High Sign | HFTD Tier 2 | Distribution | 2016-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018476 | 408001715 | Molding | HFTD Tier 2 | Distribution | 2016-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018477 | 408001728 | High Sign | HFTD Tier 2 | Distribution | 2016-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018478 | 408001771 | High Sign | HFTD Tier 2 | Distribution | 2016-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018479 | 408002191 | Guy Guard | HFTD Tier 2 | Distribution | 2016-08-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018480 | 408001958 | Molding | HFTD Tier 3 | Distribution | 2016-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018481 | 408001978 | High Sign | HFTD Tier 3 | Distribution | 2016-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018482 | 408002046 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018483 | 408002080 | High Sign | HFTD Tier 3 | Distribution | 2016-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018484 | 408002153 | Termination | HFTD Tier 2 | Distribution | 2016-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018485 | 408002354 | High Sign | HFTD Tier 3 | Distribution | 2016-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018486 | 408002377 | Riser/Conduit | HFTD Tier 3 | Distribution | 2016-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018487 | 408002410 | High Sign | HFTD Tier 2 | Distribution | 2016-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018488 | 408002434 | High Sign | HFTD Tier 3 | Distribution | 2016-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018489 | 408002462 | High Sign | HFTD Tier 3 | Distribution | 2016-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018490 | 408002467 | High Sign | HFTD Tier 3 | Distribution | 2016-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018491 | 408002472 | High Sign | HFTD Tier 3 | Distribution | 2016-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018492 | 408002492 | High Sign | HFTD Tier 3 | Distribution | 2016-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018493 | 408002664 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018494 | 408002887 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018495 | 408004194 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-08-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018496 | 408005055 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018497 | 408005208 | Termination | HFTD Tier 2 | Distribution | 2016-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018498 | 408005232 | Guy | HFTD Tier 3 | Distribution | 2016-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018499 | 408005240 | Molding | HFTD Tier 3 | Distribution | 2016-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018500 | 408005445 | High Sign | HFTD Tier 3 | Distribution | 2016-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018501 | 408005459 | High Sign | HFTD Tier 3 | Distribution | 2016-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018502 | 408005537 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018503 | 408005622 | Molding | HFTD Tier 3 | Distribution | 2016-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018504 | 408005679 | Molding | HFTD Tier 3 | Distribution | 2016-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018505 | 408006239 | Molding | HFTD Tier 3 | Distribution | 2016-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018506 | 408006258 | Guy | HFTD Tier 3 | Distribution | 2016-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018507 | 408006259 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018508 | 408006343 | High Sign | HFTD Tier 3 | Distribution | 2016-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018509 | 408008121 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018510 | 408009035 | Structure/Equip Itself | HFTD Tier 2 | Transmission | 2016-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018511 | 408009036 | Structure/Equip Itself | HFTD Tier 2 | Transmission | 2016-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018512 | 408009037 | Structure/Equip Itself | HFTD Tier 2 | Transmission | 2016-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018513 | 408009038 | Structure/Equip Itself | HFTD Tier 2 | Transmission | 2016-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018514 | 408009056 | Structure/Equip Itself | HFTD Tier 2 | Transmission | 2016-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018515 | 408009057 | Structure/Equip Itself | HFTD Tier 2 | Transmission | 2016-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018516 | 408009059 | Structure/Equip Itself | HFTD Tier 2 | Transmission | 2016-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018517 | 408009122 | Structure/Equip Itself | HFTD Tier 2 | Transmission | 2016-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018518 | 408009130 | Structure/Equip Itself | HFTD Tier 2 | Transmission | 2016-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018519 | 408009140 | Structure/Equip Itself | HFTD Tier 2 | Transmission | 2016-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018520 | 408009251 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-08-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018521 | 408008249 | Termination | HFTD Tier 3 | Distribution | 2016-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018522 | 408008276 | High Sign | HFTD Tier 3 | Distribution | 2016-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018523 | 408008691 | Molding | HFTD Tier 3 | Distribution | 2016-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018524 | 408008699 | Termination | HFTD Tier 3 | Distribution | 2016-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018525 | 408008715 | Guy | HFTD Tier 3 | Distribution | 2016-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018526 | 408008744 | Guy | HFTD Tier 3 | Distribution | 2016-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018527 | 408008926 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018528 | 408009031 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018529 | 408009392 | Molding | HFTD Tier 2 | Distribution | 2016-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018530 | 408009838 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018531 | 408009839 | Molding | HFTD Tier 3 | Distribution | 2016-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018532 | 408009911 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018533 | 408009926 | Molding | HFTD Tier 3 | Distribution | 2016-08-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018534 | 415052927 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-08-18 | 43329 | 2 | Ignition Risk, no GO95 exception | [7 empty] | SCE | 2026 | 2
1120018535 | 408012279 | Structure/Equip Itself | HFTD Tier 2 | Transmission | 2016-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018536 | 408012289 | Structure/Equip Itself | HFTD Tier 2 | Transmission | 2016-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018537 | 408012315 | Structure/Equip Itself | HFTD Tier 2 | Transmission | 2016-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018538 | 408012316 | Structure/Equip Itself | HFTD Tier 2 | Transmission | 2016-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018539 | 408012317 | Structure/Equip Itself | HFTD Tier 2 | Transmission | 2016-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018540 | 408012320 | Structure/Equip Itself | HFTD Tier 2 | Transmission | 2016-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018541 | 408012321 | Structure/Equip Itself | HFTD Tier 2 | Transmission | 2016-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018542 | 408012322 | Structure/Equip Itself | HFTD Tier 2 | Transmission | 2016-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018543 | 408012323 | Structure/Equip Itself | HFTD Tier 2 | Transmission | 2016-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018544 | 408012324 | Structure/Equip Itself | HFTD Tier 2 | Transmission | 2016-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018545 | 408012330 | Structure/Equip Itself | HFTD Tier 2 | Transmission | 2016-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018546 | 408012331 | Structure/Equip Itself | HFTD Tier 2 | Transmission | 2016-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018547 | 408012332 | Structure/Equip Itself | HFTD Tier 2 | Transmission | 2016-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018548 | 408012335 | Structure/Equip Itself | HFTD Tier 2 | Transmission | 2016-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018549 | 408012337 | Structure/Equip Itself | HFTD Tier 2 | Transmission | 2016-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018550 | 408012338 | Structure/Equip Itself | HFTD Tier 2 | Transmission | 2016-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018551 | 408012339 | Structure/Equip Itself | HFTD Tier 2 | Transmission | 2016-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018552 | 408012340 | Structure/Equip Itself | HFTD Tier 2 | Transmission | 2016-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018553 | 408012427 | Molding | HFTD Tier 2 | Distribution | 2016-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018554 | 408012724 | Guy | HFTD Tier 3 | Distribution | 2016-08-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018555 | 408016015 | Molding | HFTD Tier 3 | Distribution | 2016-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018556 | 408016985 | High Sign | HFTD Tier 3 | Distribution | 2016-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018557 | 408018108 | Molding | HFTD Tier 3 | Distribution | 2016-08-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018558 | 415052925 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-08-22 | 43334 | 2 | Ignition Risk, no GO95 exception | [7 empty] | SCE | 2026 | 2
1120018559 | 408019289 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018560 | 408019473 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018561 | 408019483 | Guy Guard | HFTD Tier 3 | Distribution | 2016-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018562 | 408019680 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018563 | 408019693 | Guy | HFTD Tier 3 | Distribution | 2016-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018564 | 408020086 | Guy | HFTD Tier 3 | Distribution | 2016-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018565 | 408020218 | Molding | HFTD Tier 3 | Distribution | 2016-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018566 | 408020411 | High Sign | HFTD Tier 3 | Distribution | 2016-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018567 | 408020647 | Guy | HFTD Tier 2 | Distribution | 2016-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018568 | 408020657 | Guy Guard | HFTD Tier 2 | Distribution | 2016-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018569 | 408020662 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-08-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018570 | 408023201 | Guy | HFTD Tier 3 | Distribution | 2016-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018571 | 408023539 | High Sign | HFTD Tier 3 | Distribution | 2016-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018572 | 408023716 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018573 | 408024056 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018574 | 408024136 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018575 | 408024283 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018576 | 408024989 | Molding | HFTD Tier 3 | Distribution | 2016-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018577 | 408025369 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018578 | 408025402 | High Sign | HFTD Tier 2 | Distribution | 2016-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018579 | 408026376 | Molding | HFTD Tier 3 | Distribution | 2016-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018580 | 408026562 | Molding | HFTD Tier 3 | Distribution | 2016-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018581 | 408026745 | Structure/Equip Itself | HFTD Tier 2 | Transmission | 2016-08-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018582 | 408028892 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018583 | 408029072 | High Sign | HFTD Tier 3 | Distribution | 2016-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018584 | 408029100 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018585 | 408029129 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018586 | 408029216 | Guy Guard | HFTD Tier 2 | Distribution | 2016-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018587 | 408029583 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-08-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018588 | 408033707 | High Sign | HFTD Tier 3 | Distribution | 2016-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018589 | 408033722 | High Sign | HFTD Tier 3 | Distribution | 2016-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018590 | 408034872 | Pole step | HFTD Tier 2 | Distribution | 2016-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018591 | 408034901 | Molding | HFTD Tier 2 | Distribution | 2016-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018592 | 408034957 | Guy Guard | HFTD Tier 3 | Distribution | 2016-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018593 | 408035003 | Guy | HFTD Tier 3 | Distribution | 2016-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018594 | 408035170 | Guy Guard | HFTD Tier 2 | Distribution | 2016-08-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018595 | 415063712 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-08-29 | 42976 | 2 | Ignition Risk, no GO95 exception | [7 empty] | SCE | 2026 | 2
1120018596 | 408036960 | High Sign | HFTD Tier 2 | Distribution | 2016-08-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018597 | 408036979 | Guy Guard | HFTD Tier 2 | Distribution | 2016-08-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018598 | 408037066 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-08-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018599 | 408037495 | Molding | HFTD Tier 2 | Distribution | 2016-08-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018600 | 408037632 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-08-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018601 | 408037874 | Molding | HFTD Tier 3 | Distribution | 2016-08-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018602 | 408038525 | Molding | HFTD Tier 2 | Distribution | 2016-08-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018603 | 408040638 | Molding | HFTD Tier 2 | Distribution | 2016-08-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018604 | 408041787 | Guy | HFTD Tier 3 | Distribution | 2016-08-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018605 | 408041804 | Guy | HFTD Tier 3 | Distribution | 2016-08-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018606 | 408041894 | Guy | HFTD Tier 3 | Distribution | 2016-08-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018607 | 408043107 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-08-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018608 | 408043410 | Anchor | HFTD Tier 3 | Distribution | 2016-08-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018609 | 408043947 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018610 | 408044164 | Guy Guard | HFTD Tier 3 | Distribution | 2016-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018611 | 408044621 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018612 | 408044694 | Molding | HFTD Tier 3 | Distribution | 2016-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018613 | 408044734 | Guy | HFTD Tier 3 | Distribution | 2016-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018614 | 408045308 | Molding | HFTD Tier 3 | Distribution | 2016-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018615 | 408045371 | Pole step | HFTD Tier 3 | Distribution | 2016-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018616 | 408049967 | Anchor | HFTD Tier 3 | Distribution | 2016-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018617 | 408050016 | High Sign | HFTD Tier 3 | Distribution | 2016-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018618 | 408050222 | Anchor | HFTD Tier 3 | Distribution | 2016-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018619 | 408050223 | Anchor | HFTD Tier 3 | Distribution | 2016-09-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018620 | 408048745 | Molding | HFTD Tier 3 | Distribution | 2016-09-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018621 | 408050497 | Guy Guard | HFTD Tier 3 | Distribution | 2016-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018622 | 408051634 | Pole step | HFTD Tier 3 | Distribution | 2016-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018623 | 408053792 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018624 | 408053793 | Guy | HFTD Tier 3 | Distribution | 2016-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018625 | 408057110 | High Sign | HFTD Tier 3 | Distribution | 2016-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018626 | 408057120 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-09-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018627 | 408055107 | High Sign | HFTD Tier 2 | Distribution | 2016-09-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018628 | 408055108 | High Sign | HFTD Tier 2 | Distribution | 2016-09-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018629 | 408055135 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-09-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018630 | 408055243 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-09-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018631 | 408057078 | Anchor | HFTD Tier 3 | Distribution | 2016-09-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018632 | 408057117 | Anchor | HFTD Tier 3 | Distribution | 2016-09-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018633 | 408057330 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-09-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018634 | 408058336 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-09-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018635 | 408058802 | High Sign | HFTD Tier 3 | Distribution | 2016-09-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018636 | 408065637 | Anchor | HFTD Tier 3 | Distribution | 2016-09-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018637 | 408060578 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-09-09 | 44417 | 2 | Ignition Risk, no GO95 exception | [7 empty] | SCE | 2026 | 2
1120018638 | 408062383 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-09-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018639 | 408064412 | Molding | HFTD Tier 3 | Distribution | 2016-09-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018640 | 408064843 | Guy Guard | HFTD Tier 3 | Distribution | 2016-09-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018641 | 408065526 | Molding | HFTD Tier 3 | Distribution | 2016-09-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018642 | 408066064 | Guy Guard | HFTD Tier 3 | Distribution | 2016-09-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018643 | 408067798 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-09-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018644 | 408069063 | Pole step | HFTD Tier 3 | Distribution | 2016-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018645 | 408069576 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018646 | 408069916 | Molding | HFTD Tier 3 | Distribution | 2016-09-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018647 | 408072493 | Molding | HFTD Tier 2 | Distribution | 2016-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018648 | 408072989 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018649 | 408073141 | Molding | HFTD Tier 3 | Distribution | 2016-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018650 | 408073496 | Molding | HFTD Tier 3 | Distribution | 2016-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018651 | 408073719 | Guy Guard | HFTD Tier 3 | Distribution | 2016-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018652 | 408073776 | Molding | HFTD Tier 2 | Distribution | 2016-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018653 | 408073845 | High Sign | HFTD Tier 2 | Distribution | 2016-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018654 | 408074324 | High Sign | HFTD Tier 2 | Distribution | 2016-09-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018655 | 408076888 | High Sign | HFTD Tier 3 | Distribution | 2016-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018656 | 408077521 | High Sign | HFTD Tier 3 | Distribution | 2016-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018657 | 408078143 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018658 | 408078171 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018659 | 408079749 | Guy | HFTD Tier 3 | Distribution | 2016-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018660 | 408080089 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018661 | 408080106 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018662 | 408080142 | Riser/Conduit | HFTD Tier 3 | Distribution | 2016-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018663 | 408080282 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-09-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018664 | 408081523 | High Sign | HFTD Tier 2 | Distribution | 2016-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018665 | 408083056 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018666 | 408083491 | Molding | HFTD Tier 3 | Distribution | 2016-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018667 | 408083510 | Guy Guard | HFTD Tier 3 | Distribution | 2016-09-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018668 | 408085274 | Molding | HFTD Tier 3 | Distribution | 2016-09-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018669 | 408087016 | Molding | HFTD Tier 3 | Distribution | 2016-09-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018670 | 408088178 | Riser/Conduit | HFTD Tier 3 | Distribution | 2016-09-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018671 | 408089122 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-09-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018672 | 408089141 | High Sign | HFTD Tier 2 | Distribution | 2016-09-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018673 | 408089150 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-09-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018674 | 408089192 | Pole step | HFTD Tier 3 | Distribution | 2016-09-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018675 | 408091895 | Guy | HFTD Tier 3 | Distribution | 2016-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018676 | 408092757 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018677 | 408092795 | High Sign | HFTD Tier 3 | Distribution | 2016-09-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018678 | 408099901 | Insulator | HFTD Tier 2 | Distribution | 2016-09-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018679 | 408100920 | Guy | HFTD Tier 2 | Distribution | 2016-09-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018680 | 408102236 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018681 | 408102453 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018682 | 408102772 | Vis Strips | HFTD Tier 3 | Distribution | 2016-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018683 | 408102822 | High Sign | HFTD Tier 3 | Distribution | 2016-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018684 | 408102969 | Guy | HFTD Tier 2 | Distribution | 2016-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018685 | 408103116 | Molding | HFTD Tier 2 | Distribution | 2016-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018686 | 408104606 | Pole step | HFTD Tier 2 | Distribution | 2016-09-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018687 | 408106809 | Riser/Conduit | HFTD Tier 2 | Distribution | 2016-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018688 | 408106884 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018689 | 408107054 | Pole step | HFTD Tier 3 | Distribution | 2016-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018690 | 408107159 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018691 | 408107454 | High Sign | HFTD Tier 3 | Distribution | 2016-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018692 | 408107747 | High Sign | HFTD Tier 2 | Distribution | 2016-09-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018693 | 408109027 | High Sign | HFTD Tier 2 | Distribution | 2016-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018694 | 408109727 | High Sign | HFTD Tier 3 | Distribution | 2016-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018695 | 408110041 | High Sign | HFTD Tier 3 | Distribution | 2016-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018696 | 408110246 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018697 | 408110360 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018698 | 408110370 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-09-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018699 | 408112207 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018700 | 408112259 | Guy Guard | HFTD Tier 3 | Distribution | 2016-09-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018701 | 408115498 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018702 | 408115943 | Molding | HFTD Tier 3 | Distribution | 2016-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018703 | 408116082 | Molding | HFTD Tier 3 | Distribution | 2016-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018704 | 408116262 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-09-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018705 | 408118570 | Guy | HFTD Tier 3 | Distribution | 2016-10-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018706 | 408128712 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-10-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018707 | 408121341 | High Sign | HFTD Tier 3 | Distribution | 2016-10-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018708 | 408132798 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-10-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018709 | 408132802 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-10-04 | 43012 | 2 | Ignition Risk, no GO95 exception | [7 empty] | SCE | 2026 | 2
1120018710 | 408132822 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-10-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018711 | 408136713 | Molding | HFTD Tier 2 | Distribution | 2016-10-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018712 | 408136721 | Molding | HFTD Tier 2 | Distribution | 2016-10-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018713 | 408129565 | Guy Guard | HFTD Tier 3 | Distribution | 2016-10-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018714 | 408138365 | Guy | HFTD Tier 3 | Distribution | 2016-10-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018715 | 408136468 | Molding | HFTD Tier 3 | Distribution | 2016-10-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018716 | 408137077 | High Sign | HFTD Tier 3 | Distribution | 2016-10-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018717 | 408137081 | High Sign | HFTD Tier 3 | Distribution | 2016-10-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018718 | 408137155 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-10-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018719 | 408137198 | Guy | HFTD Tier 3 | Distribution | 2016-10-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018720 | 408138643 | Molding | HFTD Tier 3 | Distribution | 2016-10-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018721 | 408139204 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-10-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018722 | 408140595 | Molding | HFTD Tier 3 | Distribution | 2016-10-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018723 | 408140623 | Molding | HFTD Tier 3 | Distribution | 2016-10-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018724 | 408140670 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-10-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018725 | 408141069 | High Sign | HFTD Tier 2 | Distribution | 2016-10-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018726 | 408141084 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-10-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018727 | 408141106 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-10-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018728 | 408141122 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-10-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018729 | 408141199 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-10-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018730 | 408141252 | High Sign | HFTD Tier 2 | Distribution | 2016-10-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018731 | 408141270 | High Sign | HFTD Tier 2 | Distribution | 2016-10-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018732 | 408141294 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-10-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018733 | 408141320 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-10-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018734 | 408144157 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018735 | 408144238 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018736 | 408144261 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018737 | 408144407 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018738 | 408144501 | Guy | HFTD Tier 3 | Distribution | 2016-10-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018739 | 408149065 | Molding | HFTD Tier 2 | Distribution | 2016-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018740 | 408149181 | Guy | HFTD Tier 2 | Distribution | 2016-10-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018741 | 408157368 | High Sign | HFTD Tier 3 | Distribution | 2016-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018742 | 408157415 | Guy | HFTD Tier 3 | Distribution | 2016-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018743 | 408157428 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-10-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018744 | 408157910 | Molding | HFTD Tier 2 | Distribution | 2016-10-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018745 | 408158131 | High Sign | HFTD Tier 2 | Distribution | 2016-10-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018746 | 408158430 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-10-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018747 | 408158634 | High Sign | HFTD Tier 2 | Distribution | 2016-10-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018748 | 408162539 | Guy | HFTD Tier 3 | Distribution | 2016-10-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018749 | 408162423 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-10-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018750 | 408162578 | Guy | HFTD Tier 3 | Distribution | 2016-10-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018751 | 408165515 | Riser/Conduit | HFTD Tier 3 | Distribution | 2016-10-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018752 | 408165522 | Molding | HFTD Tier 3 | Distribution | 2016-10-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018753 | 408166056 | Molding | HFTD Tier 2 | Distribution | 2016-10-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018754 | 408167350 | Guy | HFTD Tier 3 | Distribution | 2016-10-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018755 | 408167354 | High Sign | HFTD Tier 3 | Distribution | 2016-10-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018756 | 408168228 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018757 | 408170028 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018758 | 408170115 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018759 | 408170148 | Guy | HFTD Tier 3 | Distribution | 2016-10-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018760 | 408171327 | Guy | HFTD Tier 3 | Distribution | 2016-10-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018761 | 408171463 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-10-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018762 | 408174368 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-10-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018763 | 408174490 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-10-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018764 | 408174061 | Molding | HFTD Tier 2 | Distribution | 2016-10-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018765 | 408174090 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-10-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018766 | 408174512 | Pole step | HFTD Tier 3 | Distribution | 2016-10-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018767 | 408174615 | High Sign | HFTD Tier 3 | Distribution | 2016-10-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018768 | 408176335 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-10-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018769 | 408177506 | Molding | HFTD Tier 3 | Distribution | 2016-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018770 | 408177528 | Guy | HFTD Tier 3 | Distribution | 2016-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018771 | 408177590 | Molding | HFTD Tier 3 | Distribution | 2016-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018772 | 408179901 | High Sign | HFTD Tier 2 | Distribution | 2016-10-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018773 | 408183824 | Guy Guard | HFTD Tier 3 | Distribution | 2016-10-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018774 | 408187834 | Molding | HFTD Tier 2 | Distribution | 2016-10-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018775 | 408188011 | Molding | HFTD Tier 2 | Distribution | 2016-10-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018776 | 408188069 | Guy Guard | HFTD Tier 2 | Distribution | 2016-10-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018777 | 408188283 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-10-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018778 | 408188362 | Pole step | HFTD Tier 2 | Distribution | 2016-10-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018779 | 408191956 | Guy Guard | HFTD Tier 3 | Distribution | 2016-11-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018780 | 408192043 | Riser/Conduit | HFTD Tier 3 | Distribution | 2016-11-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018781 | 408192062 | Molding | HFTD Tier 3 | Distribution | 2016-11-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018782 | 408194659 | High Sign | HFTD Tier 2 | Distribution | 2016-11-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018783 | 408194928 | Hardware/Framing | HFTD Tier 3 | Distribution | 2016-11-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018784 | 408196758 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-11-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018785 | 408197303 | High Sign | HFTD Tier 2 | Distribution | 2016-11-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018786 | 408199069 | Termination | HFTD Tier 2 | Distribution | 2016-11-03 | 43042 | 2 | Ignition Risk, no GO95 exception | [7 empty] | SCE | 2026 | 2
1120018787 | 408202444 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-11-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018788 | 408200166 | Molding | HFTD Tier 2 | Distribution | 2016-11-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018789 | 408200214 | High Sign | HFTD Tier 2 | Distribution | 2016-11-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018790 | 408200428 | Pole step | HFTD Tier 2 | Distribution | 2016-11-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018791 | 408200571 | Guy | HFTD Tier 2 | Distribution | 2016-11-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018792 | 408200572 | Guy | HFTD Tier 2 | Distribution | 2016-11-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018793 | 408202175 | High Sign | HFTD Tier 2 | Transmission | 2016-11-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018794 | 408203273 | Guy Guard | HFTD Tier 3 | Distribution | 2016-11-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018795 | 408203593 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-11-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018796 | 408203978 | Molding | HFTD Tier 3 | Distribution | 2016-11-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018797 | 408204062 | Molding | HFTD Tier 3 | Distribution | 2016-11-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018798 | 408205625 | Encroachment | HFTD Tier 2 | Transmission | 2016-11-07 | 43046 | 2 | [8 empty] | SCE | 2026 | 2
1120018799 | 408205759 | Guy Guard | HFTD Tier 3 | Distribution | 2016-11-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018800 | 408206206 | Guy | HFTD Tier 2 | Distribution | 2016-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018801 | 408206211 | Guy Guard | HFTD Tier 2 | Distribution | 2016-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018802 | 408206229 | Guy Guard | HFTD Tier 3 | Distribution | 2016-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018803 | 408210593 | Guy | HFTD Tier 3 | Distribution | 2016-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018804 | 408210606 | Guy | HFTD Tier 3 | Distribution | 2016-11-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018805 | 408209763 | Guy Guard | HFTD Tier 3 | Distribution | 2016-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018806 | 408210753 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2016-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018807 | 408211108 | Riser/Conduit | HFTD Tier 2 | Distribution | 2016-11-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018808 | 408213231 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-11-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018809 | 408214719 | High Sign | HFTD Tier 2 | Distribution | 2016-11-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018810 | 408214947 | Molding | HFTD Tier 2 | Distribution | 2016-11-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018811 | 408214949 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2016-11-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018812 | 408214984 | High Sign | HFTD Tier 2 | Distribution | 2016-11-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018813 | 408215143 | High Sign | HFTD Tier 2 | Distribution | 2016-11-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018814 | 408216625 | Vis Strips | HFTD Tier 3 | Distribution | 2016-11-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018815 | 408219082 | High Sign | HFTD Tier 2 | Distribution | 2016-11-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018816 | 408219113 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-11-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018817 | 408219201 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-11-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018818 | 408220148 | Guy Guard | HFTD Tier 2 | Distribution | 2016-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018819 | 408220578 | Molding | HFTD Tier 3 | Distribution | 2016-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018820 | 408221177 | Vis Strips | HFTD Tier 3 | Distribution | 2016-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018821 | 408221196 | Guy Guard | HFTD Tier 3 | Distribution | 2016-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018822 | 408221202 | Guy Guard | HFTD Tier 3 | Distribution | 2016-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018823 | 408221212 | High Sign | HFTD Tier 3 | Distribution | 2016-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018824 | 408221220 | Guy Guard | HFTD Tier 3 | Distribution | 2016-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018825 | 408221336 | Guy Guard | HFTD Tier 2 | Distribution | 2016-11-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018826 | 408224690 | Anchor | HFTD Tier 3 | Distribution | 2016-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018827 | 408225179 | Guy | HFTD Tier 2 | Distribution | 2016-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018828 | 408225218 | Anchor | HFTD Tier 2 | Distribution | 2016-11-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018829 | 408227888 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-11-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018830 | 408227966 | High Sign | HFTD Tier 2 | Distribution | 2016-11-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018831 | 408228206 | Molding | HFTD Tier 2 | Distribution | 2016-11-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018832 | 408228241 | Vis Strips | HFTD Tier 2 | Distribution | 2016-11-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018833 | 408230569 | High Sign | HFTD Tier 2 | Distribution | 2016-11-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018834 | 408230605 | High Sign | HFTD Tier 2 | Distribution | 2016-11-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018835 | 408231125 | Pole step | HFTD Tier 2 | Distribution | 2016-11-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018836 | 408231407 | High Sign | HFTD Tier 2 | Distribution | 2016-11-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018837 | 408234575 | Pole step | HFTD Tier 3 | Distribution | 2016-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018838 | 408234612 | Riser/Conduit | HFTD Tier 3 | Distribution | 2016-11-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018839 | 408240032 | Guy | HFTD Tier 2 | Distribution | 2016-11-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018840 | 408240033 | Guy | HFTD Tier 2 | Distribution | 2016-11-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018841 | 408240052 | Guy | HFTD Tier 2 | Distribution | 2016-11-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018842 | 408240072 | Guy | HFTD Tier 2 | Distribution | 2016-11-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018843 | 408240196 | Guy | HFTD Tier 3 | Distribution | 2016-11-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018844 | 408240852 | High Sign | HFTD Tier 2 | Distribution | 2016-11-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018845 | 408246866 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-11-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018846 | 408249773 | Guy | HFTD Tier 2 | Distribution | 2016-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018847 | 408249803 | Guy | HFTD Tier 2 | Distribution | 2016-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018848 | 408249815 | High Sign | HFTD Tier 2 | Distribution | 2016-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018849 | 408250036 | Molding | HFTD Tier 3 | Distribution | 2016-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018850 | 408250065 | High Sign | HFTD Tier 3 | Distribution | 2016-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018851 | 408250083 | Guy | HFTD Tier 3 | Distribution | 2016-11-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018852 | 408252378 | Guy | HFTD Tier 2 | Distribution | 2016-12-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018853 | 408253593 | Insulator | HFTD Tier 2 | Distribution | 2016-12-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018854 | 408254315 | Guy | HFTD Tier 2 | Distribution | 2016-12-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018855 | 408254317 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-12-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018856 | 408254402 | Guy | HFTD Tier 2 | Distribution | 2016-12-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018857 | 408254421 | Cable/Conductor | HFTD Tier 2 | Distribution | 2016-12-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018858 | 408254424 | High Sign | HFTD Tier 2 | Distribution | 2016-12-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018859 | 408255521 | Guy | HFTD Tier 3 | Distribution | 2016-12-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018860 | 408255592 | Guy Guard | HFTD Tier 3 | Distribution | 2016-12-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018861 | 408255835 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-12-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018862 | 408255843 | Cable/Conductor | HFTD Tier 3 | Distribution | 2016-12-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018863 | 408256033 | Guy Guard | HFTD Tier 3 | Distribution | 2016-12-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018864 | 408262006 | Guy Guard | HFTD Tier 3 | Distribution | 2016-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018865 | 408263260 | Guy | HFTD Tier 3 | Distribution | 2016-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018866 | 408263355 | Hardware/Framing | HFTD Tier 2 | Distribution | 2016-12-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018867 | 408266379 | Guy Guard | HFTD Tier 3 | Distribution | 2016-12-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018868 | 408266419 | Guy | HFTD Tier 3 | Distribution | 2016-12-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018869 | 408266436 | Guy | HFTD Tier 3 | Distribution | 2016-12-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018870 | 408266520 | Molding | HFTD Tier 3 | Distribution | 2016-12-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018871 | 408266651 | Molding | HFTD Tier 3 | Distribution | 2016-12-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018872 | 408267727 | High Sign | HFTD Tier 2 | Distribution | 2016-12-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018873 | 408269577 | High Sign | HFTD Tier 2 | Distribution | 2016-12-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018874 | 408269744 | Molding | HFTD Tier 3 | Distribution | 2016-12-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018875 | 408271037 | High Sign | HFTD Tier 2 | Distribution | 2016-12-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018876 | 408274377 | Guy | HFTD Tier 3 | Distribution | 2016-12-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018877 | 408274434 | High Sign | HFTD Tier 3 | Distribution | 2016-12-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018878 | 408274472 | Bond | HFTD Tier 3 | Distribution | 2016-12-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018879 | 408275011 | Guy | HFTD Tier 2 | Distribution | 2016-12-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018880 | 408276369 | Guy Guard | HFTD Tier 2 | Distribution | 2016-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018881 | 408276434 | High Sign | HFTD Tier 2 | Distribution | 2016-12-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018882 | 408279603 | High Sign | HFTD Tier 2 | Distribution | 2016-12-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018883 | 408303003 | High Sign | HFTD Tier 2 | Distribution | 2017-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018884 | 408303056 | Molding | HFTD Tier 2 | Distribution | 2017-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018885 | 408303269 | Guy | HFTD Tier 2 | Distribution | 2017-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018886 | 408304484 | High Sign | HFTD Tier 2 | Distribution | 2017-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018887 | 408304772 | Guy | HFTD Tier 3 | Distribution | 2017-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018888 | 408304787 | Pole step | HFTD Tier 3 | Distribution | 2017-01-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018889 | 408305350 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018890 | 408305660 | Molding | HFTD Tier 3 | Distribution | 2017-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018891 | 408305759 | Molding | HFTD Tier 2 | Distribution | 2017-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018892 | 408306499 | High Sign | HFTD Tier 2 | Distribution | 2017-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018893 | 408306718 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-01-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018894 | 408307733 | High Sign | HFTD Tier 3 | Distribution | 2017-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018895 | 408307734 | Molding | HFTD Tier 3 | Distribution | 2017-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018896 | 408309630 | Guy | HFTD Tier 3 | Distribution | 2017-01-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018897 | 408309520 | Guy | HFTD Tier 2 | Distribution | 2017-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018898 | 408310201 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-01-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018899 | 408312216 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018900 | 408312555 | Molding | HFTD Tier 2 | Distribution | 2017-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018901 | 408313591 | Pole step | HFTD Tier 3 | Distribution | 2017-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018902 | 408313602 | Molding | HFTD Tier 3 | Distribution | 2017-01-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018903 | 408314271 | High Sign | HFTD Tier 2 | Distribution | 2017-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018904 | 408315936 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018905 | 408315944 | Riser/Conduit | HFTD Tier 3 | Distribution | 2017-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018906 | 408316114 | High Sign | HFTD Tier 3 | Distribution | 2017-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018907 | 408316205 | Pole step | HFTD Tier 3 | Distribution | 2017-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018908 | 408316460 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018909 | 408316467 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2017-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018910 | 408316480 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2017-01-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018911 | 408317002 | Riser/Conduit | HFTD Tier 3 | Distribution | 2017-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018912 | 408317444 | High Sign | HFTD Tier 3 | Distribution | 2017-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018913 | 408318608 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018914 | 408318627 | High Sign | HFTD Tier 2 | Distribution | 2017-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018915 | 408318647 | Pole step | HFTD Tier 2 | Distribution | 2017-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018916 | 408320335 | High Sign | HFTD Tier 3 | Distribution | 2017-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018917 | 408320337 | High Sign | HFTD Tier 3 | Distribution | 2017-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018918 | 408320354 | High Sign | HFTD Tier 3 | Distribution | 2017-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018919 | 408320400 | High Sign | HFTD Tier 3 | Distribution | 2017-01-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018920 | 408320394 | Streetlight | HFTD Tier 3 | Distribution | 2017-01-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018921 | 408321180 | Right of Way | HFTD Tier 2 | Transmission | 2017-01-23 | 43852 | 2 | Ignition Risk, no GO95 exception | [7 empty] | SCE | 2026 | 2
1120018922 | 408321492 | Guy | HFTD Tier 3 | Distribution | 2017-01-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018923 | 408322612 | Molding | HFTD Tier 3 | Distribution | 2017-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018924 | 408323335 | High Sign | HFTD Tier 3 | Distribution | 2017-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018925 | 408323463 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018926 | 408323526 | Molding | HFTD Tier 3 | Distribution | 2017-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018927 | 408323558 | Riser/Conduit | HFTD Tier 3 | Distribution | 2017-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018928 | 408323840 | Molding | HFTD Tier 3 | Distribution | 2017-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018929 | 408324127 | High Sign | HFTD Tier 3 | Distribution | 2017-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018930 | 408324152 | Molding | HFTD Tier 3 | Distribution | 2017-01-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018931 | 408325287 | High Sign | HFTD Tier 2 | Distribution | 2017-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018932 | 408325326 | High Sign | HFTD Tier 3 | Distribution | 2017-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018933 | 408325364 | High Sign | HFTD Tier 3 | Distribution | 2017-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018934 | 408325446 | Guy | HFTD Tier 3 | Distribution | 2017-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018935 | 408325843 | Molding | HFTD Tier 3 | Distribution | 2017-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018936 | 408326042 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018937 | 408326185 | Guy | HFTD Tier 3 | Distribution | 2017-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018938 | 408326206 | High Sign | HFTD Tier 3 | Distribution | 2017-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018939 | 408326208 | Guy | HFTD Tier 3 | Distribution | 2017-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018940 | 408326230 | High Sign | HFTD Tier 3 | Distribution | 2017-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018941 | 408326232 | High Sign | HFTD Tier 3 | Distribution | 2017-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018942 | 408326234 | Guy | HFTD Tier 3 | Distribution | 2017-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018943 | 408326240 | Hardware/Framing | HFTD Tier 3 | Distribution | 2017-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018944 | 408326578 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2017-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018945 | 408327179 | Molding | HFTD Tier 2 | Distribution | 2017-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018946 | 408327191 | Guy | HFTD Tier 2 | Distribution | 2017-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018947 | 408327212 | High Sign | HFTD Tier 2 | Distribution | 2017-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018948 | 408327222 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018949 | 408327232 | High Sign | HFTD Tier 2 | Distribution | 2017-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018950 | 408327241 | Molding | HFTD Tier 2 | Distribution | 2017-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018951 | 408327312 | Guy | HFTD Tier 2 | Distribution | 2017-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018952 | 408327376 | High Sign | HFTD Tier 3 | Distribution | 2017-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018953 | 408327401 | High Sign | HFTD Tier 3 | Distribution | 2017-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018954 | 408327595 | Molding | HFTD Tier 3 | Distribution | 2017-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018955 | 408327661 | Molding | HFTD Tier 2 | Distribution | 2017-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018956 | 408327691 | High Sign | HFTD Tier 3 | Distribution | 2017-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018957 | 408327704 | Molding | HFTD Tier 3 | Distribution | 2017-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018958 | 408328198 | High Sign | HFTD Tier 3 | Distribution | 2017-01-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018959 | 408328702 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018960 | 408328719 | Molding | HFTD Tier 2 | Distribution | 2017-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018961 | 408329359 | Hardware/Framing | HFTD Tier 3 | Distribution | 2017-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018962 | 408329583 | High Sign | HFTD Tier 2 | Distribution | 2017-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018963 | 408329897 | Molding | HFTD Tier 3 | Distribution | 2017-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018964 | 408330091 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-01-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018965 | 408332153 | High Sign | HFTD Tier 3 | Distribution | 2017-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018966 | 408332328 | Molding | HFTD Tier 3 | Distribution | 2017-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018967 | 408332427 | Guy | HFTD Tier 3 | Distribution | 2017-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018968 | 408332447 | Guy | HFTD Tier 3 | Distribution | 2017-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018969 | 408332760 | Molding | HFTD Tier 2 | Distribution | 2017-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018970 | 408334139 | Pole step | HFTD Tier 3 | Distribution | 2017-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018971 | 408334240 | Pole step | HFTD Tier 3 | Distribution | 2017-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018972 | 408334527 | Molding | HFTD Tier 3 | Distribution | 2017-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018973 | 408334529 | High Sign | HFTD Tier 3 | Distribution | 2017-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018974 | 408334554 | High Sign | HFTD Tier 3 | Distribution | 2017-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018975 | 408334584 | Molding | HFTD Tier 3 | Distribution | 2017-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018976 | 408334585 | High Sign | HFTD Tier 3 | Distribution | 2017-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018977 | 408334620 | High Sign | HFTD Tier 3 | Distribution | 2017-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018978 | 413834615 | High Sign | HFTD Tier 3 | Distribution | 2017-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018979 | 413834618 | Molding | HFTD Tier 3 | Distribution | 2017-01-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018980 | 408334225 | High Sign | HFTD Tier 3 | Distribution | 2017-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018981 | 408334242 | High Sign | HFTD Tier 3 | Distribution | 2017-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018982 | 408334502 | Guy | HFTD Tier 3 | Distribution | 2017-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018983 | 408334577 | Hardware/Framing | HFTD Tier 3 | Distribution | 2017-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018984 | 408334613 | Riser/Conduit | HFTD Tier 3 | Distribution | 2017-01-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018985 | 408334849 | Hardware/Framing | HFTD Tier 2 | Distribution | 2017-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018986 | 408334954 | Riser/Conduit | HFTD Tier 2 | Distribution | 2017-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018987 | 408335179 | High Sign | HFTD Tier 3 | Distribution | 2017-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018988 | 408335262 | Guy | HFTD Tier 3 | Distribution | 2017-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018989 | 408335589 | High Sign | HFTD Tier 3 | Distribution | 2017-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018990 | 408335655 | Molding | HFTD Tier 3 | Distribution | 2017-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018991 | 408335697 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2017-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018992 | 408336348 | High Sign | HFTD Tier 3 | Distribution | 2017-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018993 | 408336436 | Molding | HFTD Tier 3 | Distribution | 2017-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018994 | 408336494 | Molding | HFTD Tier 3 | Distribution | 2017-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018995 | 408336504 | Molding | HFTD Tier 3 | Distribution | 2017-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018996 | 408336522 | Molding | HFTD Tier 3 | Distribution | 2017-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018997 | 408336541 | High Sign | HFTD Tier 3 | Distribution | 2017-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018998 | 408336604 | Molding | HFTD Tier 2 | Distribution | 2017-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120018999 | 408336649 | Guy Guard | HFTD Tier 3 | Distribution | 2017-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019000 | 408336763 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019001 | 408336826 | Guy | HFTD Tier 2 | Distribution | 2017-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019002 | 408336855 | Guy | HFTD Tier 3 | Distribution | 2017-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019003 | 408336930 | High Sign | HFTD Tier 3 | Distribution | 2017-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019004 | 408337191 | High Sign | HFTD Tier 2 | Distribution | 2017-01-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019005 | 408337741 | High Sign | HFTD Tier 3 | Distribution | 2017-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019006 | 408337877 | Molding | HFTD Tier 3 | Distribution | 2017-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019007 | 408338046 | High Sign | HFTD Tier 3 | Distribution | 2017-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019008 | 408338155 | High Sign | HFTD Tier 3 | Distribution | 2017-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019009 | 408338159 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019010 | 408339031 | Guy | HFTD Tier 2 | Distribution | 2017-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019011 | 408339427 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2017-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019012 | 408340137 | High Sign | HFTD Tier 3 | Distribution | 2017-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019013 | 408340164 | Molding | HFTD Tier 3 | Distribution | 2017-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019014 | 408340192 | Riser/Conduit | HFTD Tier 3 | Distribution | 2017-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019015 | 408340220 | Guy Guard | HFTD Tier 3 | Distribution | 2017-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019016 | 408340279 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019017 | 408340288 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019018 | 408340346 | Molding | HFTD Tier 2 | Distribution | 2017-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019019 | 408340359 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019020 | 408340399 | Stlt Wire | HFTD Tier 2 | Distribution | 2017-01-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019021 | 408340376 | Guy | HFTD Tier 2 | Distribution | 2017-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019022 | 408340441 | Guy | HFTD Tier 2 | Distribution | 2017-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019023 | 408340490 | Molding | HFTD Tier 2 | Distribution | 2017-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019024 | 408340912 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019025 | 408340917 | High Sign | HFTD Tier 3 | Distribution | 2017-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019026 | 408341594 | Ground | HFTD Tier 3 | Distribution | 2017-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019027 | 408341964 | Molding | HFTD Tier 3 | Distribution | 2017-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019028 | 408342427 | High Sign | HFTD Tier 2 | Distribution | 2017-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019029 | 408342494 | Pole step | HFTD Tier 2 | Distribution | 2017-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019030 | 408342576 | Guy | HFTD Tier 3 | Distribution | 2017-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019031 | 408342583 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2017-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019032 | 408342607 | Pole step | HFTD Tier 2 | Distribution | 2017-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019033 | 408343038 | Guy | HFTD Tier 2 | Distribution | 2017-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019034 | 408343331 | Guy | HFTD Tier 3 | Distribution | 2017-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019035 | 408343547 | High Sign | HFTD Tier 3 | Distribution | 2017-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019036 | 408343548 | High Sign | HFTD Tier 3 | Distribution | 2017-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019037 | 408343549 | High Sign | HFTD Tier 3 | Distribution | 2017-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019038 | 408343658 | Molding | HFTD Tier 3 | Distribution | 2017-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019039 | 408343705 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019040 | 408343706 | Guy | HFTD Tier 3 | Distribution | 2017-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019041 | 408343746 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2017-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019042 | 408343752 | Pole step | HFTD Tier 3 | Distribution | 2017-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019043 | 408343762 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019044 | 408343763 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2017-02-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019045 | 408343913 | High Sign | HFTD Tier 2 | Distribution | 2017-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019046 | 408343923 | Guy | HFTD Tier 2 | Distribution | 2017-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019047 | 408343930 | Molding | HFTD Tier 2 | Distribution | 2017-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019048 | 408344458 | Riser/Conduit | HFTD Tier 3 | Distribution | 2017-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019049 | 408344459 | Molding | HFTD Tier 3 | Distribution | 2017-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019050 | 408345635 | Pole step | HFTD Tier 3 | Distribution | 2017-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019051 | 408345858 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2017-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019052 | 408345868 | Guy Guard | HFTD Tier 2 | Distribution | 2017-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019053 | 408345943 | Molding | HFTD Tier 2 | Distribution | 2017-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019054 | 408345987 | Guy | HFTD Tier 2 | Distribution | 2017-02-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019055 | 408346681 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2017-02-03 | 43344 | 2 | [8 empty] | SCE | 2026 | 2
1120019056 | 408347239 | High Sign | HFTD Tier 2 | Distribution | 2017-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019057 | 408347468 | Guy | HFTD Tier 3 | Distribution | 2017-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019058 | 408347478 | Bond | HFTD Tier 2 | Distribution | 2017-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019059 | 408347587 | High Sign | HFTD Tier 3 | Distribution | 2017-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019060 | 408347632 | High Sign | HFTD Tier 3 | Distribution | 2017-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019061 | 408347723 | Molding | HFTD Tier 3 | Distribution | 2017-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019062 | 408347743 | Guy | HFTD Tier 3 | Distribution | 2017-02-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019063 | 408349993 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-02-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019064 | 408351875 | Guy | HFTD Tier 2 | Distribution | 2017-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019065 | 408351931 | Guy | HFTD Tier 3 | Distribution | 2017-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019066 | 408356458 | Guy Guard | HFTD Tier 3 | Distribution | 2017-02-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019067 | 408354488 | Guy Guard | HFTD Tier 3 | Distribution | 2017-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019068 | 408354604 | Pole step | HFTD Tier 3 | Distribution | 2017-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019069 | 408354624 | Pole step | HFTD Tier 3 | Distribution | 2017-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019070 | 408354658 | Guy | HFTD Tier 3 | Distribution | 2017-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019071 | 408354924 | Guy | HFTD Tier 2 | Distribution | 2017-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019072 | 408355414 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019073 | 408355583 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2017-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019074 | 408355588 | Hardware/Framing | HFTD Tier 2 | Distribution | 2017-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019075 | 408355628 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019076 | 408356368 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019077 | 408356408 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019078 | 408356512 | Guy Guard | HFTD Tier 3 | Distribution | 2017-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019079 | 408356713 | Guy | HFTD Tier 2 | Distribution | 2017-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019080 | 408357842 | Guy | HFTD Tier 3 | Distribution | 2017-02-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019081 | 408361785 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2017-02-11 | 44572 | 2 | Ignition Risk, no GO95 exception | [7 empty] | SCE | 2026 | 2
1120019082 | 408363037 | Guy | HFTD Tier 3 | Distribution | 2017-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019083 | 408363062 | Guy | HFTD Tier 3 | Distribution | 2017-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019084 | 408363081 | High Sign | HFTD Tier 3 | Distribution | 2017-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019085 | 408363125 | Molding | HFTD Tier 3 | Distribution | 2017-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019086 | 408363772 | Guy | HFTD Tier 3 | Distribution | 2017-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019087 | 408363946 | High Sign | HFTD Tier 2 | Distribution | 2017-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019088 | 408365243 | Bond | HFTD Tier 3 | Distribution | 2017-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019089 | 408365328 | High Sign | HFTD Tier 3 | Distribution | 2017-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019090 | 408365366 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019091 | 408369577 | Guy | HFTD Tier 3 | Distribution | 2017-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019092 | 408369579 | Guy | HFTD Tier 3 | Distribution | 2017-02-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019093 | 408365507 | High Sign | HFTD Tier 2 | Distribution | 2017-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019094 | 408365752 | Bond | HFTD Tier 2 | Distribution | 2017-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019095 | 408365848 | Molding | HFTD Tier 2 | Distribution | 2017-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019096 | 408366564 | Guy | HFTD Tier 3 | Distribution | 2017-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019097 | 408366956 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019098 | 408366964 | High Sign | HFTD Tier 3 | Distribution | 2017-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019099 | 408368559 | High Sign | HFTD Tier 3 | Distribution | 2017-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019100 | 408368630 | Molding | HFTD Tier 3 | Distribution | 2017-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019101 | 408369762 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-02-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019102 | 408369124 | High Sign | HFTD Tier 3 | Distribution | 2017-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019103 | 408369134 | Molding | HFTD Tier 3 | Distribution | 2017-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019104 | 408369834 | Pole Tag | HFTD Tier 2 | Distribution | 2017-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019105 | 408370070 | High Sign | HFTD Tier 3 | Distribution | 2017-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019106 | 408370324 | Hardware/Framing | HFTD Tier 2 | Distribution | 2017-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019107 | 408370993 | High Sign | HFTD Tier 3 | Distribution | 2017-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019108 | 408370996 | High Sign | HFTD Tier 3 | Distribution | 2017-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019109 | 408371011 | High Sign | HFTD Tier 3 | Distribution | 2017-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019110 | 408371012 | Pole step | HFTD Tier 3 | Distribution | 2017-02-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019111 | 408372611 | Guy Guard | HFTD Tier 3 | Distribution | 2017-02-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019112 | 408372624 | Guy | HFTD Tier 3 | Distribution | 2017-02-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019113 | 408372664 | Guy Guard | HFTD Tier 3 | Distribution | 2017-02-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019114 | 408372711 | Molding | HFTD Tier 2 | Distribution | 2017-02-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019115 | 408373297 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-02-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019116 | 408373620 | Right of Way | HFTD Tier 2 | Transmission | 2017-02-16 | 43511 | 2 | Ignition Risk, no GO95 exception | [7 empty] | SCE | 2026 | 2
1120019117 | 408373860 | Molding | HFTD Tier 2 | Distribution | 2017-02-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019118 | 408374658 | Guy | HFTD Tier 2 | Distribution | 2017-02-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019119 | 408378557 | High Sign | HFTD Tier 2 | Distribution | 2017-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019120 | 408379366 | Molding | HFTD Tier 2 | Distribution | 2017-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019121 | 408379666 | High Sign | HFTD Tier 3 | Distribution | 2017-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019122 | 408379755 | Molding | HFTD Tier 2 | Distribution | 2017-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019123 | 408379810 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2017-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019124 | 408379951 | Molding | HFTD Tier 2 | Distribution | 2017-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019125 | 408380266 | High Sign | HFTD Tier 3 | Distribution | 2017-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019126 | 408380339 | Pole step | HFTD Tier 3 | Distribution | 2017-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019127 | 408380395 | Molding | HFTD Tier 3 | Distribution | 2017-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019128 | 408381033 | Molding | HFTD Tier 3 | Distribution | 2017-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019129 | 408381494 | Guy | HFTD Tier 2 | Distribution | 2017-02-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019130 | 408381325 | Hardware/Framing | HFTD Tier 2 | Distribution | 2017-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019131 | 408381617 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2017-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019132 | 408381897 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2017-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019133 | 408381967 | High Sign | HFTD Tier 3 | Distribution | 2017-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019134 | 408382090 | Ground | HFTD Tier 3 | Distribution | 2017-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019135 | 408382406 | Guy | HFTD Tier 3 | Distribution | 2017-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019136 | 408383015 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019137 | 408383270 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-02-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019138 | 408384283 | Molding | HFTD Tier 2 | Distribution | 2017-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019139 | 408384307 | Pole step | HFTD Tier 2 | Distribution | 2017-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019140 | 408384344 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019141 | 408384388 | Guy | HFTD Tier 3 | Distribution | 2017-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019142 | 408385601 | Guy | HFTD Tier 3 | Distribution | 2017-02-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019143 | 408387500 | Guy | HFTD Tier 2 | Distribution | 2017-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019144 | 408387749 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019145 | 408387860 | High Sign | HFTD Tier 2 | Distribution | 2017-02-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019146 | 408390869 | High Sign | HFTD Tier 2 | Distribution | 2017-02-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019147 | 408391382 | Riser/Conduit | HFTD Tier 3 | Distribution | 2017-02-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019148 | 408391388 | Guy | HFTD Tier 3 | Distribution | 2017-02-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019149 | 408391579 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2017-02-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019150 | 408391779 | High Sign | HFTD Tier 3 | Distribution | 2017-02-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019151 | 408392480 | High Sign | HFTD Tier 3 | Distribution | 2017-02-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019152 | 408392695 | High Sign | HFTD Tier 2 | Distribution | 2017-02-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019153 | 408393324 | High Sign | HFTD Tier 3 | Distribution | 2017-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019154 | 408393475 | Pole step | HFTD Tier 3 | Distribution | 2017-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019155 | 408393487 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019156 | 408393919 | Guy Guard | HFTD Tier 3 | Distribution | 2017-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019157 | 408394109 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019158 | 408394181 | Guy Guard | HFTD Tier 3 | Distribution | 2017-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019159 | 408394200 | Guy Guard | HFTD Tier 3 | Distribution | 2017-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019160 | 408394235 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2017-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019161 | 408394262 | Guy | HFTD Tier 3 | Distribution | 2017-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019162 | 408394272 | Molding | HFTD Tier 3 | Distribution | 2017-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019163 | 408394353 | High Sign | HFTD Tier 3 | Distribution | 2017-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019164 | 408394388 | High Sign | HFTD Tier 3 | Distribution | 2017-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019165 | 408394442 | Riser/Conduit | HFTD Tier 3 | Distribution | 2017-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019166 | 408394464 | Pole step | HFTD Tier 3 | Distribution | 2017-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019167 | 408394536 | High Sign | HFTD Tier 3 | Distribution | 2017-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019168 | 408394563 | Molding | HFTD Tier 3 | Distribution | 2017-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019169 | 408394565 | Molding | HFTD Tier 3 | Distribution | 2017-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019170 | 408394574 | Guy Guard | HFTD Tier 3 | Distribution | 2017-02-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019171 | 408396334 | High Sign | HFTD Tier 3 | Distribution | 2017-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019172 | 408396373 | Guy Guard | HFTD Tier 3 | Distribution | 2017-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019173 | 408396420 | Molding | HFTD Tier 2 | Distribution | 2017-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019174 | 408397075 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019175 | 408397155 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019176 | 408397196 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019177 | 408398047 | Guy | HFTD Tier 3 | Distribution | 2017-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019178 | 408398824 | Molding | HFTD Tier 2 | Distribution | 2017-03-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019179 | 408400087 | High Sign | HFTD Tier 3 | Distribution | 2017-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019180 | 408400315 | Guy Guard | HFTD Tier 3 | Distribution | 2017-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019181 | 408400667 | Hardware/Framing | HFTD Tier 3 | Distribution | 2017-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019182 | 408400669 | Molding | HFTD Tier 3 | Distribution | 2017-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019183 | 408400674 | Guy | HFTD Tier 3 | Distribution | 2017-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019184 | 408400681 | Guy Guard | HFTD Tier 3 | Distribution | 2017-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019185 | 408400690 | Guy | HFTD Tier 3 | Distribution | 2017-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019186 | 408400711 | High Sign | HFTD Tier 3 | Distribution | 2017-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019187 | 408400723 | Riser/Conduit | HFTD Tier 3 | Distribution | 2017-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019188 | 408401378 | High Sign | HFTD Tier 3 | Distribution | 2017-03-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019189 | 408402226 | Guy | HFTD Tier 3 | Distribution | 2017-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019190 | 408402280 | Molding | HFTD Tier 2 | Distribution | 2017-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019191 | 408402311 | Pole step | HFTD Tier 3 | Distribution | 2017-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019192 | 408402377 | Guy | HFTD Tier 3 | Distribution | 2017-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019193 | 408402646 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019194 | 408403219 | Molding | HFTD Tier 3 | Distribution | 2017-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019195 | 408403260 | High Sign | HFTD Tier 3 | Distribution | 2017-03-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019196 | 408404414 | High Sign | HFTD Tier 3 | Distribution | 2017-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019197 | 408404470 | Molding | HFTD Tier 3 | Distribution | 2017-03-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019198 | 408405940 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2017-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019199 | 408406603 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019200 | 408406652 | High Sign | HFTD Tier 2 | Distribution | 2017-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019201 | 408406912 | Guy | HFTD Tier 2 | Distribution | 2017-03-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019202 | 408408568 | High Sign | HFTD Tier 3 | Distribution | 2017-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019203 | 408408579 | Pole step | HFTD Tier 3 | Distribution | 2017-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019204 | 408408744 | High Sign | HFTD Tier 3 | Distribution | 2017-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019205 | 408408797 | High Sign | HFTD Tier 2 | Distribution | 2017-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019206 | 408408916 | High Sign | HFTD Tier 3 | Distribution | 2017-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019207 | 408408935 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019208 | 408408962 | High Sign | HFTD Tier 3 | Distribution | 2017-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019209 | 408408991 | Molding | HFTD Tier 3 | Distribution | 2017-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019210 | 408409001 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019211 | 408409003 | High Sign | HFTD Tier 3 | Distribution | 2017-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019212 | 408409155 | High Sign | HFTD Tier 3 | Distribution | 2017-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019213 | 408409393 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019214 | 408409399 | Molding | HFTD Tier 3 | Distribution | 2017-03-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019215 | 408411738 | High Sign | HFTD Tier 3 | Distribution | 2017-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019216 | 408411979 | Molding | HFTD Tier 3 | Distribution | 2017-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019217 | 408412472 | Molding | HFTD Tier 2 | Distribution | 2017-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019218 | 408412698 | Guy Guard | HFTD Tier 2 | Distribution | 2017-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019219 | 408412850 | Vis Strips | HFTD Tier 2 | Distribution | 2017-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019220 | 408413665 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-03-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019221 | 408414784 | Molding | HFTD Tier 3 | Distribution | 2017-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019222 | 408415247 | High Sign | HFTD Tier 2 | Distribution | 2017-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019223 | 408415506 | Riser/Conduit | HFTD Tier 2 | Distribution | 2017-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019224 | 408416262 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019225 | 408416560 | Guy | HFTD Tier 3 | Distribution | 2017-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019226 | 408416583 | Molding | HFTD Tier 3 | Distribution | 2017-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019227 | 408416602 | High Sign | HFTD Tier 3 | Distribution | 2017-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019228 | 408416739 | High Sign | HFTD Tier 2 | Distribution | 2017-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019229 | 408416817 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019230 | 408423637 | Hardware/Framing | HFTD Tier 2 | Distribution | 2017-03-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019231 | 408418402 | Pole step | HFTD Tier 2 | Distribution | 2017-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019232 | 408419199 | Pole step | HFTD Tier 3 | Distribution | 2017-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019233 | 408419351 | High Sign | HFTD Tier 2 | Distribution | 2017-03-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019234 | 408420396 | High Sign | HFTD Tier 3 | Distribution | 2017-03-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019235 | 408420963 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2017-03-13 | 44605 | 2 | Ignition Risk, no GO95 exception | [7 empty] | SCE | 2026 | 2
1120019236 | 408421386 | High Sign | HFTD Tier 3 | Distribution | 2017-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019237 | 408421452 | Molding | HFTD Tier 3 | Distribution | 2017-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019238 | 408421600 | Hardware/Framing | HFTD Tier 2 | Distribution | 2017-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019239 | 408421949 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019240 | 408422219 | High Sign | HFTD Tier 2 | Distribution | 2017-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019241 | 408422233 | Hardware/Framing | HFTD Tier 2 | Distribution | 2017-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019242 | 408422244 | High Sign | HFTD Tier 2 | Distribution | 2017-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019243 | 408422245 | High Sign | HFTD Tier 2 | Distribution | 2017-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019244 | 408422252 | High Sign | HFTD Tier 2 | Distribution | 2017-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019245 | 408422280 | Guy | HFTD Tier 2 | Distribution | 2017-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019246 | 408422301 | High Sign | HFTD Tier 2 | Distribution | 2017-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019247 | 408422320 | High Sign | HFTD Tier 2 | Distribution | 2017-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019248 | 408423210 | High Sign | HFTD Tier 3 | Distribution | 2017-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019249 | 408423290 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2017-03-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019250 | 408423766 | Guy | HFTD Tier 2 | Distribution | 2017-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019251 | 408424207 | High Sign | HFTD Tier 2 | Distribution | 2017-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019252 | 408424613 | High Sign | HFTD Tier 2 | Distribution | 2017-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019253 | 408424633 | Molding | HFTD Tier 2 | Distribution | 2017-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019254 | 408424640 | Molding | HFTD Tier 3 | Distribution | 2017-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019255 | 408424649 | High Sign | HFTD Tier 2 | Distribution | 2017-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019256 | 408424729 | Molding | HFTD Tier 2 | Distribution | 2017-03-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019257 | 415054422 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-03-14 | 43173 | 2 | Ignition Risk, no GO95 exception | [7 empty] | SCE | 2026 | 2
1120019258 | 408426367 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019259 | 408426436 | High Sign | HFTD Tier 3 | Distribution | 2017-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019260 | 408426994 | Guy | HFTD Tier 3 | Distribution | 2017-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019261 | 408427272 | Guy Guard | HFTD Tier 3 | Distribution | 2017-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019262 | 408427291 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019263 | 408427471 | Guy | HFTD Tier 3 | Distribution | 2017-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019264 | 408427571 | Molding | HFTD Tier 3 | Distribution | 2017-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019265 | 408427583 | High Sign | HFTD Tier 3 | Distribution | 2017-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019266 | 408428539 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019267 | 408428565 | Molding | HFTD Tier 2 | Distribution | 2017-03-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019268 | 408429487 | Riser/Conduit | HFTD Tier 3 | Distribution | 2017-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019269 | 408429734 | High Sign | HFTD Tier 3 | Distribution | 2017-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019270 | 408429774 | Molding | HFTD Tier 3 | Distribution | 2017-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019271 | 408429923 | Guy | HFTD Tier 3 | Distribution | 2017-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019272 | 408429934 | High Sign | HFTD Tier 3 | Distribution | 2017-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019273 | 408430287 | Hardware/Framing | HFTD Tier 3 | Distribution | 2017-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019274 | 408430334 | High Sign | HFTD Tier 2 | Distribution | 2017-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019275 | 408430452 | Guy | HFTD Tier 3 | Distribution | 2017-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019276 | 408430534 | High Sign | HFTD Tier 2 | Distribution | 2017-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019277 | 408430550 | Guy | HFTD Tier 3 | Distribution | 2017-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019278 | 408430670 | Molding | HFTD Tier 2 | Distribution | 2017-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019279 | 408430900 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019280 | 408431623 | High Sign | HFTD Tier 2 | Distribution | 2017-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019281 | 408434630 | Pole step | HFTD Tier 2 | Distribution | 2017-03-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019282 | 408432830 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019283 | 408432835 | Guy | HFTD Tier 3 | Distribution | 2017-03-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019284 | 408434050 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2017-03-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019285 | 408434448 | Molding | HFTD Tier 2 | Distribution | 2017-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019286 | 408434735 | High Sign | HFTD Tier 2 | Distribution | 2017-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019287 | 408434868 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2017-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019288 | 408434869 | Guy Guard | HFTD Tier 3 | Distribution | 2017-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019289 | 408434893 | Guy | HFTD Tier 3 | Distribution | 2017-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019290 | 408434904 | High Sign | HFTD Tier 2 | Distribution | 2017-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019291 | 408434921 | High Sign | HFTD Tier 2 | Distribution | 2017-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019292 | 408434965 | High Sign | HFTD Tier 2 | Distribution | 2017-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019293 | 408435120 | High Sign | HFTD Tier 2 | Distribution | 2017-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019294 | 408435132 | Pole step | HFTD Tier 3 | Distribution | 2017-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019295 | 408435142 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2017-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019296 | 408435247 | Insulator | HFTD Tier 3 | Distribution | 2017-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019297 | 408435347 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019298 | 408435392 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2017-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019299 | 408435402 | High Sign | HFTD Tier 2 | Distribution | 2017-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019300 | 408435467 | Hardware/Framing | HFTD Tier 3 | Distribution | 2017-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019301 | 408435632 | Guy | HFTD Tier 3 | Distribution | 2017-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019302 | 408436086 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019303 | 408436092 | Guy | HFTD Tier 2 | Distribution | 2017-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019304 | 408436123 | High Sign | HFTD Tier 2 | Distribution | 2017-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019305 | 408436227 | High Sign | HFTD Tier 3 | Distribution | 2017-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019306 | 408436300 | Pole step | HFTD Tier 2 | Distribution | 2017-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019307 | 408436924 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019308 | 408436958 | Guy Guard | HFTD Tier 3 | Distribution | 2017-03-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019309 | 415054423 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-03-20 | 43179 | 2 | Ignition Risk, no GO95 exception | [7 empty] | SCE | 2026 | 2
1120019310 | 408437473 | High Sign | HFTD Tier 3 | Distribution | 2017-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019311 | 408437871 | Hardware/Framing | HFTD Tier 3 | Distribution | 2017-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019312 | 408437996 | Guy | HFTD Tier 3 | Distribution | 2017-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019313 | 408438359 | Pole step | HFTD Tier 3 | Distribution | 2017-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019314 | 408439471 | Guy | HFTD Tier 2 | Distribution | 2017-03-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019315 | 408440254 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019316 | 408440737 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019317 | 408440776 | Molding | HFTD Tier 3 | Distribution | 2017-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019318 | 408440869 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019319 | 408440991 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019320 | 408441019 | Molding | HFTD Tier 2 | Distribution | 2017-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019321 | 408441138 | Hardware/Framing | HFTD Tier 2 | Distribution | 2017-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019322 | 408441384 | High Sign | HFTD Tier 2 | Distribution | 2017-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019323 | 408441982 | High Sign | HFTD Tier 2 | Distribution | 2017-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019324 | 408442030 | Guy Guard | HFTD Tier 2 | Distribution | 2017-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019325 | 408442179 | High Sign | HFTD Tier 2 | Distribution | 2017-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019326 | 408442287 | High Sign | HFTD Tier 2 | Distribution | 2017-03-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019327 | 408442829 | Riser/Conduit | HFTD Tier 2 | Distribution | 2017-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019328 | 408443210 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2017-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019329 | 408443280 | Guy | HFTD Tier 3 | Distribution | 2017-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019330 | 408443518 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2017-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019331 | 408443533 | High Sign | HFTD Tier 2 | Distribution | 2017-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019332 | 408443585 | Guy | HFTD Tier 2 | Distribution | 2017-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019333 | 408443613 | Guy | HFTD Tier 3 | Distribution | 2017-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019334 | 408443681 | High Sign | HFTD Tier 2 | Distribution | 2017-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019335 | 408443858 | Guy | HFTD Tier 2 | Distribution | 2017-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019336 | 408443906 | Riser/Conduit | HFTD Tier 3 | Distribution | 2017-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019337 | 408443941 | High Sign | HFTD Tier 2 | Distribution | 2017-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019338 | 408443965 | Guy | HFTD Tier 2 | Distribution | 2017-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019339 | 408443990 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-03-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019340 | 408447849 | High Sign | HFTD Tier 2 | Distribution | 2017-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019341 | 408447918 | Guy | HFTD Tier 3 | Distribution | 2017-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019342 | 408448466 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019343 | 408448667 | Anchor | HFTD Tier 3 | Distribution | 2017-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019344 | 408448704 | Guy Guard | HFTD Tier 3 | Distribution | 2017-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019345 | 408448753 | Guy | HFTD Tier 3 | Distribution | 2017-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019346 | 408449165 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2017-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019347 | 408449175 | High Sign | HFTD Tier 2 | Distribution | 2017-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019348 | 408449181 | Guy | HFTD Tier 3 | Distribution | 2017-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019349 | 408449353 | Guy | HFTD Tier 3 | Distribution | 2017-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019350 | 408450242 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-03-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019351 | 408450999 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019352 | 408451160 | Molding | HFTD Tier 3 | Distribution | 2017-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019353 | 408451198 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019354 | 408451306 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2017-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019355 | 408451432 | High Sign | HFTD Tier 3 | Distribution | 2017-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019356 | 408451472 | Riser/Conduit | HFTD Tier 3 | Distribution | 2017-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019357 | 408451502 | High Sign | HFTD Tier 3 | Distribution | 2017-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019358 | 408451510 | Hardware/Framing | HFTD Tier 3 | Distribution | 2017-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019359 | 408451701 | Guy | HFTD Tier 3 | Distribution | 2017-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019360 | 408452641 | Molding | HFTD Tier 2 | Distribution | 2017-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019361 | 408452714 | Molding | HFTD Tier 2 | Distribution | 2017-03-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019362 | 408453099 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019363 | 408453112 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019364 | 408453215 | Guy | HFTD Tier 3 | Distribution | 2017-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019365 | 408453862 | Guy Guard | HFTD Tier 3 | Distribution | 2017-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019366 | 408454396 | High Sign | HFTD Tier 2 | Distribution | 2017-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019367 | 408454429 | High Sign | HFTD Tier 2 | Distribution | 2017-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019368 | 408454621 | High Sign | HFTD Tier 2 | Distribution | 2017-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019369 | 408454704 | High Sign | HFTD Tier 2 | Distribution | 2017-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019370 | 408455090 | Guy Guard | HFTD Tier 3 | Distribution | 2017-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019371 | 408455199 | Molding | HFTD Tier 3 | Distribution | 2017-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019372 | 408455242 | High Sign | HFTD Tier 3 | Distribution | 2017-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019373 | 408455636 | High Sign | HFTD Tier 2 | Distribution | 2017-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019374 | 408455665 | Molding | HFTD Tier 2 | Distribution | 2017-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019375 | 408456472 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019376 | 408456514 | Guy | HFTD Tier 2 | Distribution | 2017-03-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019377 | 408456188 | Guy Guard | HFTD Tier 3 | Distribution | 2017-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019378 | 408456515 | High Sign | HFTD Tier 2 | Distribution | 2017-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019379 | 408456850 | Guy | HFTD Tier 3 | Distribution | 2017-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019380 | 408456860 | Guy Guard | HFTD Tier 3 | Distribution | 2017-03-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019381 | 408460702 | Guy | HFTD Tier 3 | Distribution | 2017-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019382 | 408460771 | Guy Guard | HFTD Tier 3 | Distribution | 2017-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019383 | 408460906 | Hardware/Framing | HFTD Tier 3 | Distribution | 2017-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019384 | 408461062 | High Sign | HFTD Tier 2 | Distribution | 2017-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019385 | 408461073 | Molding | HFTD Tier 2 | Distribution | 2017-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019386 | 408461827 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-04-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019387 | 408464541 | Guy | HFTD Tier 3 | Distribution | 2017-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019388 | 408464563 | High Sign | HFTD Tier 3 | Distribution | 2017-04-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019389 | 408466012 | Molding | HFTD Tier 2 | Distribution | 2017-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019390 | 408466022 | Molding | HFTD Tier 2 | Distribution | 2017-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019391 | 408466174 | Molding | HFTD Tier 3 | Distribution | 2017-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019392 | 408466290 | High Sign | HFTD Tier 2 | Distribution | 2017-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019393 | 408466401 | High Sign | HFTD Tier 2 | Distribution | 2017-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019394 | 408466572 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019395 | 408466799 | Molding | HFTD Tier 2 | Distribution | 2017-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019396 | 408467202 | Molding | HFTD Tier 2 | Distribution | 2017-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019397 | 408467616 | Guy | HFTD Tier 3 | Distribution | 2017-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019398 | 408467831 | High Sign | HFTD Tier 2 | Distribution | 2017-04-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019399 | 408468481 | High Sign | HFTD Tier 3 | Distribution | 2017-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019400 | 408468493 | High Sign | HFTD Tier 3 | Distribution | 2017-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019401 | 408468498 | High Sign | HFTD Tier 3 | Distribution | 2017-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019402 | 408468708 | Molding | HFTD Tier 2 | Distribution | 2017-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019403 | 408468990 | High Sign | HFTD Tier 3 | Distribution | 2017-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019404 | 408469196 | High Sign | HFTD Tier 2 | Distribution | 2017-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019405 | 408469304 | Guy | HFTD Tier 2 | Distribution | 2017-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019406 | 408469718 | High Sign | HFTD Tier 2 | Distribution | 2017-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019407 | 408469732 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-04-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019408 | 408471855 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019409 | 408471856 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019410 | 408471869 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019411 | 408471873 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019412 | 408471888 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019413 | 408471914 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019414 | 408471915 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019415 | 408471918 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019416 | 408471923 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019417 | 408471924 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019418 | 408471928 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019419 | 408471929 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019420 | 408471958 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019421 | 408471959 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019422 | 408471975 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019423 | 408471983 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019424 | 408471984 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019425 | 408471989 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019426 | 408471997 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019427 | 408471998 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019428 | 408472021 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019429 | 408472022 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019430 | 408472023 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019431 | 408472026 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019432 | 408472027 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019433 | 408472037 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019434 | 408472039 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019435 | 408472049 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019436 | 408472055 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019437 | 408472058 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019438 | 408472098 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019439 | 408472105 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019440 | 408472110 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019441 | 408472111 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019442 | 408472114 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019443 | 408472116 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019444 | 408472117 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019445 | 408472121 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019446 | 408472122 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019447 | 408472128 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019448 | 408472129 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019449 | 408472132 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019450 | 408472134 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019451 | 408472135 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019452 | 408472137 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019453 | 408472141 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019454 | 408472145 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019455 | 408472148 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019456 | 408472152 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019457 | 408472154 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019458 | 408472157 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019459 | 408472161 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019460 | 408472162 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019461 | 408472163 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019462 | 408472181 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019463 | 408472183 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019464 | 408472184 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019465 | 408472192 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019466 | 408472196 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019467 | 408472198 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019468 | 408472199 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019469 | 408472215 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019470 | 408472222 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019471 | 408472240 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019472 | 408472241 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019473 | 408472251 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019474 | 408472252 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019475 | 408472270 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019476 | 408472479 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019477 | 408472489 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019478 | 408472497 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019479 | 408472498 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019480 | 408472499 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019481 | 408472519 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019482 | 408472523 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019483 | 408472524 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019484 | 408472527 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019485 | 408472554 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019486 | 408472558 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019487 | 408472562 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019488 | 408472565 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019489 | 408472569 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019490 | 408472573 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019491 | 408472575 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019492 | 408472576 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019493 | 408472581 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019494 | 408472586 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019495 | 408472591 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019496 | 408472592 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019497 | 408472601 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019498 | 408472602 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019499 | 408472603 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019500 | 408472610 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019501 | 408472612 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019502 | 408472630 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019503 | 408472631 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019504 | 408472632 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019505 | 408472634 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019506 | 408472638 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019507 | 408472640 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019508 | 408472641 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019509 | 408472652 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019510 | 408472655 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019511 | 408472664 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019512 | 408472665 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019513 | 408472667 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019514 | 408472671 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019515 | 408472680 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019516 | 408472683 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019517 | 408472691 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019518 | 408472700 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019519 | 408472720 | Guy | HFTD Tier 2 | Distribution | 2017-04-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019520 | 408475373 | Guy | HFTD Tier 2 | Distribution | 2017-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019521 | 408476311 | Molding | HFTD Tier 3 | Distribution | 2017-04-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019522 | 408476656 | Guy Guard | HFTD Tier 3 | Distribution | 2017-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019523 | 408477450 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019524 | 408478285 | High Sign | HFTD Tier 3 | Distribution | 2017-04-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019525 | 408478347 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019526 | 408478508 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019527 | 408478870 | High Sign | HFTD Tier 2 | Distribution | 2017-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019528 | 408479014 | High Sign | HFTD Tier 3 | Distribution | 2017-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019529 | 408480124 | Molding | HFTD Tier 2 | Distribution | 2017-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019530 | 408480341 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019531 | 408480597 | Guy | HFTD Tier 3 | Distribution | 2017-04-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019532 | 408481246 | High Sign | HFTD Tier 2 | Distribution | 2017-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019533 | 408481551 | Guy | HFTD Tier 3 | Distribution | 2017-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019534 | 408481568 | Molding | HFTD Tier 2 | Distribution | 2017-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019535 | 408481614 | Molding | HFTD Tier 2 | Distribution | 2017-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019536 | 408481794 | Molding | HFTD Tier 2 | Distribution | 2017-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019537 | 408481865 | Molding | HFTD Tier 3 | Distribution | 2017-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019538 | 408481951 | High Sign | HFTD Tier 3 | Distribution | 2017-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019539 | 408481960 | High Sign | HFTD Tier 3 | Distribution | 2017-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019540 | 408483070 | Hardware/Framing | HFTD Tier 2 | Distribution | 2017-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019541 | 408483282 | Guy | HFTD Tier 2 | Distribution | 2017-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019542 | 408484226 | Guy Guard | HFTD Tier 3 | Distribution | 2017-04-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019543 | 408483669 | Molding | HFTD Tier 2 | Distribution | 2017-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019544 | 408483856 | Molding | HFTD Tier 2 | Distribution | 2017-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019545 | 408483857 | Molding | HFTD Tier 2 | Distribution | 2017-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019546 | 408483923 | Molding | HFTD Tier 2 | Distribution | 2017-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019547 | 408483984 | High Sign | HFTD Tier 2 | Distribution | 2017-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019548 | 408485094 | Guy | HFTD Tier 2 | Distribution | 2017-04-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019549 | 408486346 | High Sign | HFTD Tier 2 | Distribution | 2017-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019550 | 408486699 | Molding | HFTD Tier 2 | Distribution | 2017-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019551 | 408487237 | Hardware/Framing | HFTD Tier 2 | Distribution | 2017-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019552 | 408487358 | Guy Guard | HFTD Tier 2 | Distribution | 2017-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019553 | 408488229 | High Sign | HFTD Tier 3 | Distribution | 2017-04-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019554 | 408488845 | High Sign | HFTD Tier 2 | Distribution | 2017-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019555 | 408488851 | Molding | HFTD Tier 3 | Distribution | 2017-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019556 | 408488890 | Molding | HFTD Tier 2 | Distribution | 2017-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019557 | 408488896 | High Sign | HFTD Tier 3 | Distribution | 2017-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019558 | 408489084 | High Sign | HFTD Tier 2 | Distribution | 2017-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019559 | 408489628 | High Sign | HFTD Tier 2 | Distribution | 2017-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019560 | 408489691 | Molding | HFTD Tier 2 | Distribution | 2017-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019561 | 408489787 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019562 | 408490387 | Pole step | HFTD Tier 2 | Distribution | 2017-04-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019563 | 408491577 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019564 | 408491759 | Molding | HFTD Tier 3 | Distribution | 2017-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019565 | 408492281 | Guy | HFTD Tier 3 | Distribution | 2017-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019566 | 408492671 | Molding | HFTD Tier 2 | Distribution | 2017-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019567 | 408493066 | High Sign | HFTD Tier 3 | Distribution | 2017-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019568 | 408493437 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019569 | 408493558 | High Sign | HFTD Tier 2 | Distribution | 2017-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019570 | 408493891 | Guy | HFTD Tier 3 | Distribution | 2017-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019571 | 408494084 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-04-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019572 | 408494546 | Guy | HFTD Tier 3 | Distribution | 2017-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019573 | 408495587 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019574 | 408495809 | Guy | HFTD Tier 3 | Distribution | 2017-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019575 | 408495877 | Pole step | HFTD Tier 3 | Distribution | 2017-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019576 | 408495914 | Insulator | HFTD Tier 3 | Distribution | 2017-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019577 | 408495915 | High Sign | HFTD Tier 3 | Distribution | 2017-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019578 | 408495936 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019579 | 408496297 | Guy | HFTD Tier 3 | Distribution | 2017-04-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019580 | 408500164 | Molding | HFTD Tier 3 | Distribution | 2017-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019581 | 408500335 | High Sign | HFTD Tier 2 | Distribution | 2017-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019582 | 408500476 | Pole step | HFTD Tier 3 | Distribution | 2017-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019583 | 408500494 | High Sign | HFTD Tier 2 | Distribution | 2017-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019584 | 408500580 | High Sign | HFTD Tier 3 | Distribution | 2017-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019585 | 408500664 | Molding | HFTD Tier 3 | Distribution | 2017-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019586 | 408500874 | Pole step | HFTD Tier 3 | Distribution | 2017-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019587 | 408501128 | Guy | HFTD Tier 3 | Distribution | 2017-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019588 | 408501319 | High Sign | HFTD Tier 3 | Distribution | 2017-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019589 | 408501434 | High Sign | HFTD Tier 3 | Distribution | 2017-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019590 | 408501442 | High Sign | HFTD Tier 3 | Distribution | 2017-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019591 | 408501450 | Molding | HFTD Tier 3 | Distribution | 2017-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019592 | 408501503 | Guy | HFTD Tier 2 | Distribution | 2017-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019593 | 408501915 | Hardware/Framing | HFTD Tier 3 | Distribution | 2017-04-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019594 | 408502439 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019595 | 408502826 | Guy | HFTD Tier 2 | Distribution | 2017-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019596 | 408503349 | High Sign | HFTD Tier 3 | Distribution | 2017-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019597 | 408503577 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019598 | 408504258 | High Sign | HFTD Tier 2 | Distribution | 2017-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019599 | 408504379 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2017-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019600 | 408504393 | Molding | HFTD Tier 2 | Distribution | 2017-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019601 | 408504403 | Molding | HFTD Tier 2 | Distribution | 2017-04-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019602 | 408505691 | High Sign | HFTD Tier 3 | Distribution | 2017-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019603 | 408505755 | Molding | HFTD Tier 3 | Distribution | 2017-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019604 | 408506033 | Guy | HFTD Tier 3 | Distribution | 2017-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019605 | 408506099 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019606 | 408506127 | Guy Guard | HFTD Tier 3 | Distribution | 2017-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019607 | 408506193 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019608 | 408506313 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019609 | 408506731 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019610 | 408506829 | High Sign | HFTD Tier 3 | Distribution | 2017-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019611 | 408506830 | Guy | HFTD Tier 3 | Distribution | 2017-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019612 | 408507219 | Guy Guard | HFTD Tier 3 | Distribution | 2017-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019613 | 408507245 | Guy Guard | HFTD Tier 3 | Distribution | 2017-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019614 | 408507809 | Guy | HFTD Tier 3 | Distribution | 2017-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019615 | 408508096 | Guy | HFTD Tier 3 | Distribution | 2017-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019616 | 408508186 | Anchor | HFTD Tier 3 | Distribution | 2017-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019617 | 408512586 | Guy | HFTD Tier 2 | Distribution | 2017-04-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019618 | 408508813 | Guy | HFTD Tier 3 | Distribution | 2017-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019619 | 408508856 | Guy | HFTD Tier 3 | Distribution | 2017-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019620 | 408509292 | Molding | HFTD Tier 3 | Distribution | 2017-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019621 | 408509726 | Guy | HFTD Tier 3 | Distribution | 2017-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019622 | 408509838 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019623 | 408509920 | Guy | HFTD Tier 3 | Distribution | 2017-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019624 | 408510513 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019625 | 408510555 | Guy | HFTD Tier 3 | Distribution | 2017-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019626 | 408510878 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019627 | 408511176 | High Sign | HFTD Tier 3 | Distribution | 2017-04-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019628 | 408511520 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2017-04-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019629 | 408512712 | Guy | HFTD Tier 2 | Distribution | 2017-04-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019630 | 408514106 | High Sign | HFTD Tier 3 | Distribution | 2017-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019631 | 408514326 | High Sign | HFTD Tier 3 | Distribution | 2017-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019632 | 408514633 | Molding | HFTD Tier 3 | Distribution | 2017-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019633 | 408514713 | High Sign | HFTD Tier 3 | Distribution | 2017-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019634 | 408514714 | Molding | HFTD Tier 3 | Distribution | 2017-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019635 | 408514956 | Hardware/Framing | HFTD Tier 2 | Distribution | 2017-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019636 | 408515662 | Molding | HFTD Tier 3 | Distribution | 2017-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019637 | 408515672 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019638 | 408515708 | High Sign | HFTD Tier 2 | Distribution | 2017-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019639 | 408515888 | High Sign | HFTD Tier 2 | Distribution | 2017-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019640 | 408515972 | Molding | HFTD Tier 3 | Distribution | 2017-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019641 | 408517543 | Pole step | HFTD Tier 2 | Distribution | 2017-05-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019642 | 415054955 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2017-05-01 | 43586 | 2 | Ignition Risk, no GO95 exception | [7 empty] | SCE | 2026 | 2
1120019643 | 408517995 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019644 | 408518343 | Guy | HFTD Tier 2 | Distribution | 2017-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019645 | 408518598 | High Sign | HFTD Tier 3 | Distribution | 2017-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019646 | 408518628 | Guy Guard | HFTD Tier 2 | Distribution | 2017-05-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019647 | 408520554 | High Sign | HFTD Tier 2 | Distribution | 2017-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019648 | 408520568 | High Sign | HFTD Tier 2 | Distribution | 2017-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019649 | 408520648 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019650 | 408520656 | Guy | HFTD Tier 3 | Distribution | 2017-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019651 | 408520694 | High Sign | HFTD Tier 2 | Distribution | 2017-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019652 | 408520718 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019653 | 408520740 | High Sign | HFTD Tier 2 | Distribution | 2017-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019654 | 408520743 | Guy | HFTD Tier 3 | Distribution | 2017-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019655 | 408520852 | High Sign | HFTD Tier 2 | Distribution | 2017-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019656 | 408521662 | High Sign | HFTD Tier 3 | Distribution | 2017-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019657 | 408521787 | High Sign | HFTD Tier 2 | Distribution | 2017-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019658 | 408521829 | High Sign | HFTD Tier 2 | Distribution | 2017-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019659 | 408521882 | High Sign | HFTD Tier 2 | Distribution | 2017-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019660 | 408522102 | Hardware/Framing | HFTD Tier 3 | Distribution | 2017-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019661 | 408522128 | Molding | HFTD Tier 3 | Distribution | 2017-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019662 | 408522172 | High Sign | HFTD Tier 3 | Distribution | 2017-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019663 | 408522178 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019664 | 408522187 | Termination | HFTD Tier 3 | Distribution | 2017-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019665 | 408522963 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2017-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019666 | 408522991 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2017-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019667 | 408522992 | Molding | HFTD Tier 2 | Distribution | 2017-05-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019668 | 415054421 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-05-03 | 43223 | 2 | Ignition Risk, no GO95 exception | [7 empty] | SCE | 2026 | 2
1120019669 | 408524279 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019670 | 408524826 | Guy | HFTD Tier 2 | Distribution | 2017-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019671 | 408524840 | High Sign | HFTD Tier 2 | Distribution | 2017-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019672 | 408524939 | High Sign | HFTD Tier 3 | Distribution | 2017-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019673 | 408524986 | High Sign | HFTD Tier 2 | Distribution | 2017-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019674 | 408525119 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2017-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019675 | 408526060 | Bond | HFTD Tier 2 | Distribution | 2017-05-04 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019676 | 408528041 | High Sign | HFTD Tier 2 | Distribution | 2017-05-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019677 | 408529283 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-05-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019678 | 408529389 | Molding | HFTD Tier 3 | Distribution | 2017-05-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019679 | 408529493 | Molding | HFTD Tier 3 | Distribution | 2017-05-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019680 | 408530098 | Molding | HFTD Tier 3 | Distribution | 2017-05-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019681 | 408530251 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2017-05-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019682 | 408530331 | High Sign | HFTD Tier 2 | Distribution | 2017-05-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019683 | 408530466 | High Sign | HFTD Tier 3 | Distribution | 2017-05-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019684 | 408530882 | Guy Guard | HFTD Tier 2 | Distribution | 2017-05-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019685 | 408531665 | High Sign | HFTD Tier 2 | Distribution | 2017-05-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019686 | 408533148 | High Sign | HFTD Tier 3 | Distribution | 2017-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019687 | 408533275 | High Sign | HFTD Tier 3 | Distribution | 2017-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019688 | 408533285 | Molding | HFTD Tier 3 | Distribution | 2017-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019689 | 408533320 | Pole step | HFTD Tier 3 | Distribution | 2017-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019690 | 408533347 | Guy Guard | HFTD Tier 3 | Distribution | 2017-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019691 | 408533381 | Riser/Conduit | HFTD Tier 3 | Distribution | 2017-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019692 | 408533816 | High Sign | HFTD Tier 3 | Distribution | 2017-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019693 | 408533949 | Guy | HFTD Tier 3 | Distribution | 2017-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019694 | 408534032 | Molding | HFTD Tier 3 | Distribution | 2017-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019695 | 408534174 | High Sign | HFTD Tier 3 | Distribution | 2017-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019696 | 408535056 | Hardware/Framing | HFTD Tier 3 | Distribution | 2017-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019697 | 408535083 | Guy | HFTD Tier 3 | Distribution | 2017-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019698 | 408535097 | High Sign | HFTD Tier 2 | Distribution | 2017-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019699 | 408535127 | Guy Guard | HFTD Tier 2 | Distribution | 2017-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019700 | 408535149 | Guy Guard | HFTD Tier 2 | Distribution | 2017-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019701 | 408535175 | Guy Guard | HFTD Tier 2 | Distribution | 2017-05-09 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019702 | 408535591 | Guy | HFTD Tier 3 | Distribution | 2017-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019703 | 408535892 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019704 | 408536229 | Molding | HFTD Tier 3 | Distribution | 2017-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019705 | 408536275 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019706 | 408536522 | Guy | HFTD Tier 3 | Distribution | 2017-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019707 | 408536613 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019708 | 408536652 | High Sign | HFTD Tier 3 | Distribution | 2017-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019709 | 408536654 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019710 | 408536803 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019711 | 408536857 | Molding | HFTD Tier 3 | Distribution | 2017-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019712 | 408537022 | High Sign | HFTD Tier 3 | Distribution | 2017-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019713 | 408537364 | Guy | HFTD Tier 3 | Distribution | 2017-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019714 | 408537898 | High Sign | HFTD Tier 2 | Distribution | 2017-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019715 | 408537923 | High Sign | HFTD Tier 2 | Distribution | 2017-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019716 | 408537927 | Hardware/Framing | HFTD Tier 2 | Distribution | 2017-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019717 | 408537931 | High Sign | HFTD Tier 2 | Distribution | 2017-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019718 | 408537933 | Molding | HFTD Tier 2 | Distribution | 2017-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019719 | 408537958 | High Sign | HFTD Tier 2 | Distribution | 2017-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019720 | 408537994 | High Sign | HFTD Tier 2 | Distribution | 2017-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019721 | 408538007 | High Sign | HFTD Tier 2 | Distribution | 2017-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019722 | 408538020 | High Sign | HFTD Tier 2 | Distribution | 2017-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019723 | 408538092 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019724 | 408538403 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2017-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019725 | 408538404 | High Sign | HFTD Tier 3 | Distribution | 2017-05-10 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019726 | 408538672 | Guy | HFTD Tier 3 | Distribution | 2017-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019727 | 408538899 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019728 | 408540303 | Molding | HFTD Tier 2 | Distribution | 2017-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019729 | 408540332 | High Sign | HFTD Tier 2 | Distribution | 2017-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019730 | 408540537 | High Sign | HFTD Tier 3 | Distribution | 2017-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019731 | 408540648 | Molding | HFTD Tier 2 | Distribution | 2017-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019732 | 408540709 | High Sign | HFTD Tier 2 | Distribution | 2017-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019733 | 408540767 | High Sign | HFTD Tier 2 | Distribution | 2017-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019734 | 408540799 | High Sign | HFTD Tier 2 | Distribution | 2017-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019735 | 408540839 | High Sign | HFTD Tier 2 | Distribution | 2017-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019736 | 408540853 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019737 | 408540875 | Molding | HFTD Tier 2 | Distribution | 2017-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019738 | 408540892 | High Sign | HFTD Tier 2 | Distribution | 2017-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019739 | 408540911 | Hardware/Framing | HFTD Tier 2 | Distribution | 2017-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019740 | 408541699 | Molding | HFTD Tier 3 | Distribution | 2017-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019741 | 408541794 | High Sign | HFTD Tier 3 | Distribution | 2017-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019742 | 408541808 | Hardware/Framing | HFTD Tier 3 | Distribution | 2017-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019743 | 408541863 | Guy | HFTD Tier 3 | Distribution | 2017-05-11 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019744 | 408542323 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2017-05-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019745 | 408545243 | High Sign | HFTD Tier 2 | Distribution | 2017-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019746 | 408545367 | Molding | HFTD Tier 2 | Distribution | 2017-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019747 | 408545417 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019748 | 408545450 | High Sign | HFTD Tier 2 | Distribution | 2017-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019749 | 408546136 | Pole step | HFTD Tier 3 | Distribution | 2017-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019750 | 408546187 | Riser/Conduit | HFTD Tier 2 | Distribution | 2017-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019751 | 408546220 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019752 | 408546221 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019753 | 408546315 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2017-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019754 | 408546472 | Molding | HFTD Tier 2 | Distribution | 2017-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019755 | 408546646 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-05-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019756 | 408547445 | Pole step | HFTD Tier 3 | Distribution | 2017-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019757 | 408547956 | Riser/Conduit | HFTD Tier 3 | Distribution | 2017-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019758 | 408548033 | Guy | HFTD Tier 3 | Distribution | 2017-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019759 | 408548045 | Guy | HFTD Tier 3 | Distribution | 2017-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019760 | 408548060 | Guy Guard | HFTD Tier 3 | Distribution | 2017-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019761 | 408549164 | Molding | HFTD Tier 3 | Distribution | 2017-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019762 | 408549270 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019763 | 408549342 | Molding | HFTD Tier 3 | Distribution | 2017-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019764 | 408549428 | High Sign | HFTD Tier 2 | Distribution | 2017-05-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019765 | 408550679 | Guy | HFTD Tier 3 | Distribution | 2017-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019766 | 408550714 | Guy | HFTD Tier 3 | Distribution | 2017-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019767 | 408550771 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019768 | 408551150 | Pole step | HFTD Tier 2 | Distribution | 2017-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019769 | 408551238 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019770 | 408552338 | Guy Guard | HFTD Tier 3 | Distribution | 2017-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019771 | 408552397 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2017-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019772 | 408552426 | Guy | HFTD Tier 3 | Distribution | 2017-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019773 | 408552633 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2017-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019774 | 408555379 | High Sign | HFTD Tier 2 | Distribution | 2017-05-17 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019775 | 408553395 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019776 | 408554170 | Guy | HFTD Tier 3 | Distribution | 2017-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019777 | 408554470 | High Sign | HFTD Tier 3 | Distribution | 2017-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019778 | 408555193 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019779 | 408555194 | High Sign | HFTD Tier 3 | Distribution | 2017-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019780 | 408555297 | High Sign | HFTD Tier 3 | Distribution | 2017-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019781 | 408555370 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019782 | 408555390 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2017-05-18 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019783 | 408556398 | Molding | HFTD Tier 3 | Distribution | 2017-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019784 | 408561220 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-05-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019785 | 408558630 | High Sign | HFTD Tier 3 | Distribution | 2017-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019786 | 408558818 | Guy | HFTD Tier 3 | Distribution | 2017-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019787 | 408558851 | High Sign | HFTD Tier 3 | Distribution | 2017-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019788 | 408558924 | High Sign | HFTD Tier 3 | Distribution | 2017-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019789 | 408559027 | High Sign | HFTD Tier 3 | Distribution | 2017-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019790 | 408559029 | High Sign | HFTD Tier 3 | Distribution | 2017-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019791 | 408559053 | Molding | HFTD Tier 3 | Distribution | 2017-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019792 | 408559130 | Guy | HFTD Tier 3 | Distribution | 2017-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019793 | 408559140 | High Sign | HFTD Tier 3 | Distribution | 2017-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019794 | 408559151 | High Sign | HFTD Tier 3 | Distribution | 2017-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019795 | 408559152 | High Sign | HFTD Tier 3 | Distribution | 2017-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019796 | 408559153 | Guy | HFTD Tier 3 | Distribution | 2017-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019797 | 408559202 | Molding | HFTD Tier 3 | Distribution | 2017-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019798 | 408559233 | High Sign | HFTD Tier 3 | Distribution | 2017-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019799 | 408559235 | Guy | HFTD Tier 3 | Distribution | 2017-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019800 | 408559545 | High Sign | HFTD Tier 3 | Distribution | 2017-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019801 | 408559546 | Ground | HFTD Tier 2 | Distribution | 2017-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019802 | 408559602 | High Sign | HFTD Tier 3 | Distribution | 2017-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019803 | 408559612 | Molding | HFTD Tier 3 | Distribution | 2017-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019804 | 408559656 | High Sign | HFTD Tier 3 | Distribution | 2017-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019805 | 408559695 | Guy Guard | HFTD Tier 3 | Distribution | 2017-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019806 | 408559717 | High Sign | HFTD Tier 3 | Distribution | 2017-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019807 | 408559834 | Guy | HFTD Tier 3 | Distribution | 2017-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019808 | 408559872 | High Sign | HFTD Tier 3 | Distribution | 2017-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019809 | 408560608 | Guy | HFTD Tier 3 | Distribution | 2017-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019810 | 408560648 | High Sign | HFTD Tier 3 | Distribution | 2017-05-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019811 | 408561073 | High Sign | HFTD Tier 3 | Distribution | 2017-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019812 | 408561765 | High Sign | HFTD Tier 3 | Distribution | 2017-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019813 | 408561772 | Guy | HFTD Tier 3 | Distribution | 2017-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019814 | 408561811 | High Sign | HFTD Tier 3 | Distribution | 2017-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019815 | 408562166 | High Sign | HFTD Tier 3 | Distribution | 2017-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019816 | 408562245 | Guy Guard | HFTD Tier 3 | Distribution | 2017-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019817 | 408562291 | High Sign | HFTD Tier 3 | Distribution | 2017-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019818 | 408562389 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019819 | 408562522 | Guy | HFTD Tier 2 | Distribution | 2017-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019820 | 408562591 | Molding | HFTD Tier 3 | Distribution | 2017-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019821 | 408562614 | High Sign | HFTD Tier 3 | Distribution | 2017-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019822 | 408562705 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019823 | 408562737 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019824 | 408562808 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019825 | 408562932 | High Sign | HFTD Tier 3 | Distribution | 2017-05-23 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019826 | 408564426 | Guy Guard | HFTD Tier 3 | Distribution | 2017-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019827 | 408564529 | Guy Guard | HFTD Tier 3 | Distribution | 2017-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019828 | 408564795 | High Sign | HFTD Tier 2 | Distribution | 2017-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019829 | 408564819 | Molding | HFTD Tier 2 | Distribution | 2017-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019830 | 408564928 | Molding | HFTD Tier 2 | Distribution | 2017-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019831 | 408565138 | High Sign | HFTD Tier 3 | Distribution | 2017-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019832 | 408565143 | High Sign | HFTD Tier 3 | Distribution | 2017-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019833 | 408565190 | High Sign | HFTD Tier 3 | Distribution | 2017-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019834 | 408565243 | Guy | HFTD Tier 3 | Distribution | 2017-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019835 | 408565254 | High Sign | HFTD Tier 3 | Distribution | 2017-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019836 | 408565277 | High Sign | HFTD Tier 3 | Distribution | 2017-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019837 | 408565666 | High Sign | HFTD Tier 2 | Distribution | 2017-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019838 | 408565677 | High Sign | HFTD Tier 3 | Distribution | 2017-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019839 | 408565985 | Hardware/Framing | HFTD Tier 3 | Distribution | 2017-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019840 | 408566017 | Guy | HFTD Tier 3 | Distribution | 2017-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019841 | 408566161 | High Sign | HFTD Tier 3 | Distribution | 2017-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019842 | 408567819 | Guy | HFTD Tier 3 | Distribution | 2017-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019843 | 408567911 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-05-24 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019844 | 408570265 | Guy | HFTD Tier 3 | Distribution | 2017-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019845 | 408570438 | Vis Strips | HFTD Tier 2 | Distribution | 2017-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019846 | 408570512 | Pole step | HFTD Tier 2 | Distribution | 2017-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019847 | 408573320 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-05-25 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019848 | 408572989 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2017-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019849 | 408573085 | High Sign | HFTD Tier 3 | Distribution | 2017-05-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019850 | 408573449 | Guy | HFTD Tier 3 | Distribution | 2017-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019851 | 408573533 | High Sign | HFTD Tier 3 | Distribution | 2017-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019852 | 408573627 | Guy | HFTD Tier 3 | Distribution | 2017-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019853 | 408573683 | Molding | HFTD Tier 3 | Distribution | 2017-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019854 | 408573791 | Guy | HFTD Tier 3 | Distribution | 2017-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019855 | 408573884 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019856 | 408574374 | High Sign | HFTD Tier 3 | Distribution | 2017-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019857 | 408574379 | High Sign | HFTD Tier 3 | Distribution | 2017-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019858 | 408574409 | Guy | HFTD Tier 3 | Distribution | 2017-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019859 | 408574465 | Guy | HFTD Tier 3 | Distribution | 2017-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019860 | 408574812 | Guy | HFTD Tier 2 | Distribution | 2017-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019861 | 408574814 | Riser/Conduit | HFTD Tier 2 | Distribution | 2017-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019862 | 408574849 | Guy | HFTD Tier 2 | Distribution | 2017-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019863 | 408575537 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2017-05-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019864 | 408576238 | Guy | HFTD Tier 3 | Distribution | 2017-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019865 | 408576253 | Guy | HFTD Tier 3 | Distribution | 2017-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019866 | 408576276 | Molding | HFTD Tier 3 | Distribution | 2017-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019867 | 408576284 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019868 | 408577519 | High Sign | HFTD Tier 3 | Distribution | 2017-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019869 | 408582784 | Guy | HFTD Tier 2 | Distribution | 2017-05-31 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019870 | 408580449 | High Sign | HFTD Tier 3 | Distribution | 2017-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019871 | 408580594 | Hardware/Framing | HFTD Tier 3 | Distribution | 2017-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019872 | 408580885 | Molding | HFTD Tier 3 | Distribution | 2017-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019873 | 408581102 | High Sign | HFTD Tier 2 | Distribution | 2017-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019874 | 408585157 | High Sign | HFTD Tier 3 | Distribution | 2017-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019875 | 408585181 | High Sign | HFTD Tier 3 | Distribution | 2017-06-01 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019876 | 408583690 | Guy | HFTD Tier 2 | Distribution | 2017-06-02 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019877 | 408586025 | Guy | HFTD Tier 2 | Distribution | 2017-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019878 | 408586054 | High Sign | HFTD Tier 2 | Distribution | 2017-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019879 | 408586091 | Hardware/Framing | HFTD Tier 2 | Distribution | 2017-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019880 | 408586204 | Molding | HFTD Tier 2 | Distribution | 2017-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019881 | 408586223 | Guy | HFTD Tier 2 | Distribution | 2017-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019882 | 408586236 | Molding | HFTD Tier 2 | Distribution | 2017-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019883 | 408586238 | Guy | HFTD Tier 2 | Distribution | 2017-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019884 | 408586391 | High Sign | HFTD Tier 2 | Distribution | 2017-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019885 | 408586435 | High Sign | HFTD Tier 2 | Distribution | 2017-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019886 | 408587036 | Molding | HFTD Tier 2 | Distribution | 2017-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019887 | 408587126 | Hardware/Framing | HFTD Tier 2 | Distribution | 2017-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019888 | 408587359 | Guy Guard | HFTD Tier 3 | Distribution | 2017-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019889 | 408588174 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019890 | 408590056 | Guy | HFTD Tier 2 | Distribution | 2017-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019891 | 408590110 | Guy | HFTD Tier 2 | Distribution | 2017-06-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019892 | 408588781 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019893 | 408589170 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019894 | 408589267 | Molding | HFTD Tier 3 | Distribution | 2017-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019895 | 408589352 | Guy | HFTD Tier 2 | Distribution | 2017-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019896 | 408590544 | High Sign | HFTD Tier 2 | Distribution | 2017-06-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019897 | 408591466 | Guy | HFTD Tier 3 | Distribution | 2017-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019898 | 408592521 | Molding | HFTD Tier 3 | Distribution | 2017-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019899 | 408592735 | Hardware/Framing | HFTD Tier 3 | Distribution | 2017-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019900 | 408592830 | Molding | HFTD Tier 2 | Distribution | 2017-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019901 | 408592842 | Molding | HFTD Tier 2 | Distribution | 2017-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019902 | 408592909 | Molding | HFTD Tier 3 | Distribution | 2017-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019903 | 408592920 | Hardware/Framing | HFTD Tier 2 | Distribution | 2017-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019904 | 408598285 | Riser/Conduit | HFTD Tier 2 | Distribution | 2017-06-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019905 | 408594519 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2017-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019906 | 408594639 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2017-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019907 | 408594849 | Molding | HFTD Tier 2 | Distribution | 2017-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019908 | 408594873 | High Sign | HFTD Tier 3 | Distribution | 2017-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019909 | 408594913 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2017-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019910 | 408595697 | Guy | HFTD Tier 3 | Distribution | 2017-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019911 | 408596083 | Guy | HFTD Tier 3 | Distribution | 2017-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019912 | 408596459 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019913 | 408596732 | High Sign | HFTD Tier 3 | Distribution | 2017-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019914 | 408596799 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2017-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019915 | 408598245 | Guy Guard | HFTD Tier 2 | Distribution | 2017-06-08 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019916 | 408598029 | Right of Way | HFTD Tier 2 | Transmission | 2017-06-09 | 43990 | 2 | [8 empty] | SCE | 2026 | 2
1120019917 | 408598063 | Right of Way | HFTD Tier 2 | Transmission | 2017-06-09 | 43990 | 2 | [8 empty] | SCE | 2026 | 2
1120019918 | 408598086 | Right of Way | HFTD Tier 2 | Transmission | 2017-06-09 | 43990 | 2 | [8 empty] | SCE | 2026 | 2
1120019919 | 408598122 | Right of Way | HFTD Tier 2 | Transmission | 2017-06-09 | 43990 | 2 | [8 empty] | SCE | 2026 | 2
1120019920 | 408600495 | Molding | HFTD Tier 3 | Distribution | 2017-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019921 | 408601356 | Guy Guard | HFTD Tier 3 | Distribution | 2017-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019922 | 408602614 | Guy Guard | HFTD Tier 3 | Distribution | 2017-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019923 | 408605251 | High Sign | HFTD Tier 2 | Distribution | 2017-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019924 | 408605276 | High Sign | HFTD Tier 2 | Distribution | 2017-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019925 | 408616155 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2017-06-12 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019926 | 408603026 | Molding | HFTD Tier 3 | Distribution | 2017-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019927 | 408603043 | Molding | HFTD Tier 3 | Distribution | 2017-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019928 | 408603359 | Guy | HFTD Tier 3 | Distribution | 2017-06-13 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019929 | 408607668 | High Sign | HFTD Tier 2 | Distribution | 2017-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019930 | 408607823 | High Sign | HFTD Tier 2 | Distribution | 2017-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019931 | 408607845 | High Sign | HFTD Tier 2 | Distribution | 2017-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019932 | 408607882 | High Sign | HFTD Tier 2 | Distribution | 2017-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019933 | 408607942 | High Sign | HFTD Tier 3 | Distribution | 2017-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019934 | 408608656 | High Sign | HFTD Tier 2 | Distribution | 2017-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019935 | 408608709 | Guy | HFTD Tier 3 | Distribution | 2017-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019936 | 408608803 | Guy | HFTD Tier 3 | Distribution | 2017-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019937 | 408609064 | Guy | HFTD Tier 3 | Distribution | 2017-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019938 | 408616214 | Pole step | HFTD Tier 2 | Distribution | 2017-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019939 | 408616245 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2017-06-14 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019940 | 408609129 | Pole step | HFTD Tier 2 | Distribution | 2017-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019941 | 408610033 | High Sign | HFTD Tier 2 | Distribution | 2017-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019942 | 408610093 | High Sign | HFTD Tier 2 | Distribution | 2017-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019943 | 408610101 | High Sign | HFTD Tier 2 | Distribution | 2017-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019944 | 408610249 | Guy Guard | HFTD Tier 3 | Distribution | 2017-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019945 | 408610357 | Riser/Conduit | HFTD Tier 3 | Distribution | 2017-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019946 | 408610599 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019947 | 408610842 | Molding | HFTD Tier 3 | Distribution | 2017-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019948 | 408611412 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019949 | 408612234 | Molding | HFTD Tier 2 | Distribution | 2017-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019950 | 408612241 | Guy Guard | HFTD Tier 2 | Distribution | 2017-06-15 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019951 | 408612337 | Guy Guard | HFTD Tier 3 | Distribution | 2017-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019952 | 408613100 | Guy Guard | HFTD Tier 3 | Distribution | 2017-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019953 | 408613376 | Guy Guard | HFTD Tier 3 | Distribution | 2017-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019954 | 408613403 | High Sign | HFTD Tier 3 | Distribution | 2017-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019955 | 408613451 | High Sign | HFTD Tier 3 | Distribution | 2017-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019956 | 408613452 | High Sign | HFTD Tier 3 | Distribution | 2017-06-16 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019957 | 408615807 | Pole step | HFTD Tier 3 | Distribution | 2017-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019958 | 408617789 | High Sign | HFTD Tier 2 | Distribution | 2017-06-19 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019959 | 408617537 | Guy | HFTD Tier 3 | Distribution | 2017-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019960 | 408617628 | Riser/Conduit | HFTD Tier 3 | Distribution | 2017-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019961 | 408617752 | Guy | HFTD Tier 3 | Distribution | 2017-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019962 | 408617762 | High Sign | HFTD Tier 3 | Distribution | 2017-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019963 | 408617783 | High Sign | HFTD Tier 3 | Distribution | 2017-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019964 | 408618267 | Guy Guard | HFTD Tier 3 | Distribution | 2017-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019965 | 408618549 | High Sign | HFTD Tier 2 | Distribution | 2017-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019966 | 408618679 | High Sign | HFTD Tier 2 | Distribution | 2017-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019967 | 408618711 | High Sign | HFTD Tier 2 | Distribution | 2017-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019968 | 408618761 | High Sign | HFTD Tier 2 | Distribution | 2017-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019969 | 408619489 | High Sign | HFTD Tier 2 | Distribution | 2017-06-20 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019970 | 408620394 | High Sign | HFTD Tier 2 | Distribution | 2017-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019971 | 408621428 | Insulator | HFTD Tier 3 | Distribution | 2017-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019972 | 408621477 | Bond | HFTD Tier 3 | Distribution | 2017-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019973 | 408621489 | Guy | HFTD Tier 3 | Distribution | 2017-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019974 | 408621508 | Guy Guard | HFTD Tier 3 | Distribution | 2017-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019975 | 408621537 | Guy Guard | HFTD Tier 3 | Distribution | 2017-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019976 | 408621555 | Guy | HFTD Tier 3 | Distribution | 2017-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019977 | 408621581 | Pole Tag | HFTD Tier 3 | Distribution | 2017-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019978 | 408622366 | Hardware/Framing | HFTD Tier 2 | Distribution | 2017-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019979 | 408622549 | Hardware/Framing | HFTD Tier 3 | Distribution | 2017-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019980 | 408622703 | High Sign | HFTD Tier 2 | Distribution | 2017-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019981 | 408622732 | High Sign | HFTD Tier 2 | Distribution | 2017-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019982 | 408622761 | High Sign | HFTD Tier 2 | Distribution | 2017-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019983 | 408623138 | Molding | HFTD Tier 3 | Distribution | 2017-06-21 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019984 | 408623362 | Hardware/Framing | HFTD Tier 3 | Distribution | 2017-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019985 | 408624331 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019986 | 408624453 | Guy Guard | HFTD Tier 3 | Distribution | 2017-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019987 | 408624883 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019988 | 408625174 | High Sign | HFTD Tier 2 | Distribution | 2017-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019989 | 408626999 | Guy | HFTD Tier 2 | Distribution | 2017-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019990 | 408630915 | High Sign | HFTD Tier 3 | Distribution | 2017-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019991 | 408630935 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-06-22 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019992 | 408628717 | Guy | HFTD Tier 3 | Distribution | 2017-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019993 | 408628794 | High Sign | HFTD Tier 3 | Distribution | 2017-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019994 | 408629007 | High Sign | HFTD Tier 2 | Distribution | 2017-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019995 | 408629014 | High Sign | HFTD Tier 2 | Distribution | 2017-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019996 | 408629038 | High Sign | HFTD Tier 2 | Distribution | 2017-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019997 | 408629100 | High Sign | HFTD Tier 2 | Distribution | 2017-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019998 | 408629843 | Guy | HFTD Tier 3 | Distribution | 2017-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120019999 | 408630100 | Vis Strips | HFTD Tier 3 | Distribution | 2017-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020000 | 408630189 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020001 | 408633048 | Guy | HFTD Tier 2 | Distribution | 2017-06-26 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020002 | 408630876 | Guy | HFTD Tier 2 | Distribution | 2017-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020003 | 408631036 | Guy | HFTD Tier 2 | Distribution | 2017-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020004 | 408631051 | High Sign | HFTD Tier 2 | Distribution | 2017-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020005 | 408631091 | Guy | HFTD Tier 2 | Distribution | 2017-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020006 | 408631718 | Pole step | HFTD Tier 2 | Distribution | 2017-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020007 | 408632419 | Guy | HFTD Tier 3 | Distribution | 2017-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020008 | 408633137 | Guy | HFTD Tier 2 | Distribution | 2017-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020009 | 408633240 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020010 | 408633276 | High Sign | HFTD Tier 2 | Distribution | 2017-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020011 | 408633296 | Hardware/Framing | HFTD Tier 2 | Distribution | 2017-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020012 | 408633342 | High Sign | HFTD Tier 2 | Distribution | 2017-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020013 | 408633358 | High Sign | HFTD Tier 2 | Distribution | 2017-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020014 | 408633360 | High Sign | HFTD Tier 2 | Distribution | 2017-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020015 | 408633370 | High Sign | HFTD Tier 2 | Distribution | 2017-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020016 | 408633597 | Guy | HFTD Tier 2 | Distribution | 2017-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020017 | 408633655 | High Sign | HFTD Tier 2 | Distribution | 2017-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020018 | 408633690 | Guy Guard | HFTD Tier 2 | Distribution | 2017-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020019 | 408634127 | Guy | HFTD Tier 3 | Distribution | 2017-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020020 | 408634211 | Guy | HFTD Tier 3 | Distribution | 2017-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020021 | 408634474 | Molding | HFTD Tier 3 | Distribution | 2017-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020022 | 408634483 | Hardware/Framing | HFTD Tier 3 | Distribution | 2017-06-27 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020023 | 408634504 | High Sign | HFTD Tier 2 | Distribution | 2017-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020024 | 408634527 | High Sign | HFTD Tier 2 | Distribution | 2017-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020025 | 408634595 | High Sign | HFTD Tier 2 | Distribution | 2017-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020026 | 408634596 | High Sign | HFTD Tier 2 | Distribution | 2017-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020027 | 408634899 | Structure/Equip Itself | HFTD Tier 3 | Distribution | 2017-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020028 | 408635135 | Guy Guard | HFTD Tier 2 | Distribution | 2017-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020029 | 408635199 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020030 | 408636206 | High Sign | HFTD Tier 2 | Distribution | 2017-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020031 | 408636261 | Hardware/Framing | HFTD Tier 2 | Distribution | 2017-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020032 | 408636437 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020033 | 408636676 | High Sign | HFTD Tier 2 | Distribution | 2017-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020034 | 408636709 | High Sign | HFTD Tier 2 | Distribution | 2017-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020035 | 408636745 | High Sign | HFTD Tier 2 | Distribution | 2017-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020036 | 408636761 | High Sign | HFTD Tier 2 | Distribution | 2017-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020037 | 408636780 | High Sign | HFTD Tier 2 | Distribution | 2017-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020038 | 408636781 | High Sign | HFTD Tier 2 | Distribution | 2017-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020039 | 408636790 | High Sign | HFTD Tier 2 | Distribution | 2017-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020040 | 408636983 | High Sign | HFTD Tier 2 | Distribution | 2017-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020041 | 408637031 | High Sign | HFTD Tier 2 | Distribution | 2017-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020042 | 408637231 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020043 | 408637509 | High Sign | HFTD Tier 2 | Distribution | 2017-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020044 | 408637568 | High Sign | HFTD Tier 2 | Distribution | 2017-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020045 | 408637587 | High Sign | HFTD Tier 2 | Distribution | 2017-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020046 | 408637592 | High Sign | HFTD Tier 2 | Distribution | 2017-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020047 | 408637676 | Cable/Conductor | HFTD Tier 2 | Distribution | 2017-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020048 | 408637847 | Pole step | HFTD Tier 2 | Distribution | 2017-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020049 | 408637866 | High Sign | HFTD Tier 2 | Distribution | 2017-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020050 | 408637887 | High Sign | HFTD Tier 2 | Distribution | 2017-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020051 | 408637942 | Molding | HFTD Tier 2 | Distribution | 2017-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020052 | 408637950 | Molding | HFTD Tier 2 | Distribution | 2017-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020053 | 408637951 | High Sign | HFTD Tier 2 | Distribution | 2017-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020054 | 408637960 | High Sign | HFTD Tier 2 | Distribution | 2017-06-28 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020055 | 408638035 | High Sign | HFTD Tier 2 | Distribution | 2017-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020056 | 408638085 | High Sign | HFTD Tier 2 | Distribution | 2017-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020057 | 408638104 | High Sign | HFTD Tier 2 | Distribution | 2017-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020058 | 408638123 | High Sign | HFTD Tier 2 | Distribution | 2017-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020059 | 408638173 | Molding | HFTD Tier 3 | Distribution | 2017-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020060 | 408638433 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020061 | 408638586 | High Sign | HFTD Tier 2 | Distribution | 2017-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020062 | 408638628 | High Sign | HFTD Tier 2 | Distribution | 2017-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020063 | 408638635 | High Sign | HFTD Tier 2 | Distribution | 2017-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020064 | 408638918 | Molding | HFTD Tier 2 | Distribution | 2017-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020065 | 408638990 | High Sign | HFTD Tier 2 | Distribution | 2017-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020066 | 408640136 | High Sign | HFTD Tier 2 | Distribution | 2017-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020067 | 408640147 | High Sign | HFTD Tier 2 | Distribution | 2017-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020068 | 408640174 | High Sign | HFTD Tier 2 | Distribution | 2017-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020069 | 408640185 | High Sign | HFTD Tier 2 | Distribution | 2017-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020070 | 408640241 | High Sign | HFTD Tier 2 | Distribution | 2017-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020071 | 408640493 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2017-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020072 | 408640530 | Structure/Equip Itself | HFTD Tier 2 | Distribution | 2017-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020073 | 408640967 | Riser/Conduit | HFTD Tier 2 | Distribution | 2017-06-29 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020074 | 408641497 | Molding | HFTD Tier 3 | Distribution | 2017-06-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020075 | 408642064 | High Sign | HFTD Tier 3 | Distribution | 2017-06-30 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020076 | 408644240 | Molding | HFTD Tier 3 | Distribution | 2017-07-03 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020077 | 408646197 | High Sign | HFTD Tier 3 | Distribution | 2017-07-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020078 | 408646462 | High Sign | HFTD Tier 3 | Distribution | 2017-07-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020079 | 408646490 | High Sign | HFTD Tier 2 | Distribution | 2017-07-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020080 | 408646700 | High Sign | HFTD Tier 3 | Distribution | 2017-07-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020081 | 408647391 | High Sign | HFTD Tier 2 | Distribution | 2017-07-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020082 | 408647410 | High Sign | HFTD Tier 2 | Distribution | 2017-07-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020083 | 408647636 | Guy | HFTD Tier 3 | Distribution | 2017-07-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020084 | 408647753 | High Sign | HFTD Tier 2 | Distribution | 2017-07-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020085 | 408647775 | High Sign | HFTD Tier 2 | Distribution | 2017-07-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020086 | 408647795 | Molding | HFTD Tier 2 | Distribution | 2017-07-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020087 | 408647805 | High Sign | HFTD Tier 2 | Distribution | 2017-07-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020088 | 408647814 | High Sign | HFTD Tier 2 | Distribution | 2017-07-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020089 | 408650525 | High Sign | HFTD Tier 2 | Distribution | 2017-07-05 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020090 | 408648385 | Molding | HFTD Tier 2 | Distribution | 2017-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020091 | 408649698 | High Sign | HFTD Tier 3 | Distribution | 2017-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020092 | 408650357 | High Sign | HFTD Tier 2 | Distribution | 2017-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020093 | 408650407 | High Sign | HFTD Tier 2 | Distribution | 2017-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020094 | 408650444 | High Sign | HFTD Tier 2 | Distribution | 2017-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020095 | 408650459 | High Sign | HFTD Tier 2 | Distribution | 2017-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020096 | 408650469 | High Sign | HFTD Tier 2 | Distribution | 2017-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020097 | 408650509 | High Sign | HFTD Tier 2 | Distribution | 2017-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020098 | 408650542 | High Sign | HFTD Tier 2 | Distribution | 2017-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020099 | 408650551 | High Sign | HFTD Tier 2 | Distribution | 2017-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020100 | 408650580 | High Sign | HFTD Tier 2 | Distribution | 2017-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020101 | 408662668 | Guy | HFTD Tier 2 | Distribution | 2017-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020102 | 408662669 | High Sign | HFTD Tier 2 | Distribution | 2017-07-06 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020103 | 408651577 | High Sign | HFTD Tier 2 | Distribution | 2017-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020104 | 408651648 | High Sign | HFTD Tier 2 | Distribution | 2017-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020105 | 408651752 | High Sign | HFTD Tier 3 | Distribution | 2017-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020106 | 408651818 | High Sign | HFTD Tier 2 | Distribution | 2017-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020107 | 408652004 | Guy Guard | HFTD Tier 2 | Distribution | 2017-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2
1120020108 | 408652276 | Cable/Conductor | HFTD Tier 3 | Distribution | 2017-07-07 |  | 3 | Ignition Risk, no GO95 exception | [6 empty] | Due Date N/A | SCE | 2026 | 2