## Request
Scope
SPD is updating the WMP Implementation Dashboard using the data provided in the 2026-28 WMP, 2026 Q1 QDR, and the Costs data received in "02.a-d_IOU WMP Cost Reporting and Account Tracking Template 2026_09".
Request
Some mitigation targets/unit counts and mitigation IDs appear to have changed or may have been added between the 2026-28 Approved WMP and what was reported to SPD in "02.a-d_IOU WMP Cost Reporting and Account Tracking Template 2026_09".
Fill in columns H through K of the Worksheet tab to reflect any necessary updates.

## Worksheet
|  | 02.a-d_IOU WMP Cost Reporting and Account Tracking Template 2026_09 |  |  | Approved 2026-28 WMP | SPD Request | SCE Response
Mitigation | Year | Target | Total CapEx | Total OpEx | Target |  | CapEx | OpEx | Target | SCE Comment (if any)
IN-11 | 2026 | N/A | N/A | N/A | Close 70% of P2 notifications in HFRA with ignition-risk potential that are past due (as of Dec 31, 2025) in the “Inactive equipment/FLOC" and “Other" categories. | Provide (1) estimated Target in units, not percentage, (2) CapEx and (3) OpEx | N/A | N/A | 1257 | Costs associated with preventative maintenance are addressed as part of the WMP initiative "Equipment Maintenance and Repair". Estimated numerical target is provided using the total relevant past due notifications as of 12/31/2026. SCE provides the WMP target as a percentage because future quantities are unknown at this time.
IN-11 | 2027 | N/A | N/A | N/A | Close 70% of P2 notifications in HFRA with ignition-risk potential that are past due (as of December 31, 2026) in the “Inactive equipment/FLOC" and “Other" categories | Provide (1) estimated Target in units, not percentage, (2) CapEx and (3) OpEx | N/A | N/A | Not available | Costs associated with preventative maintenance are addressed as part of the WMP initiative "Equipment Maintenance and Repair". Numerical target for 2027 cannot be derived without knowing the number of past due notifications as of December 31, 2026.
IN-11 | 2028 | N/A | N/A | N/A | Close 70% of P2 notifications in HFRA with ignition-risk potential that are past due (as of December 31, 2027) in the “Inactive equipment/FLOC" and “Other" categories | Provide (1) estimated Target in units, not percentage, (2) CapEx and (3) OpEx | N/A | N/A | Not available | Costs associated with preventative maintenance are addressed as part of the WMP initiative "Equipment Maintenance and Repair". Numerical target for 2027 cannot be derived without knowing the number of past due notifications as of December 31, 2027.
VM-7 | 2026 | N/A | 0 | 173713.7897 | Inspect 100% of distribution circuit miles in HFRA and prescribe mitigation as needed to achieve clearance | Page 367 of SCE approved 2026-28 Base WMP (R2) indicates that the population size is 9,177 distribution miles. Confirm or provide an accurate target value. | N/A | 232325.5887 | 9171 | Forecast amounts are for HFRA. SCE provides an estimated mileage target that can be used as a proxy, should SPD need to have a roughly equivalent numerical target. SCE provides its official target as a percentage because HFRA mileage can charge marginally for a number of reasons.
VM-7 | 2027 | N/A | 0 | 177258.0874 | Inspect 100% of distribution circuit miles in HFRA and prescribe mitigation as needed to achieve clearance | Page 367 of SCE approved 2026-28 Base WMP (R2) indicates that the population size is 9,177 distribution miles. Confirm or provide an accurate target value. | N/A | 232789.1051 | 9171 | Forecast amounts are for HFRA. SCE provides an estimated mileage target that can be used as a proxy, should SPD need to have a roughly equivalent numerical target. SCE provides its official target as a percentage because HFRA mileage can charge marginally for a number of reasons.
VM-7 | 2028 | N/A | 0 | 180885.6531 | Inspect 100% of distribution circuit miles in HFRA and prescribe mitigation as needed to achieve clearance | Page 367 of SCE approved 2026-28 Base WMP (R2) indicates that the population size is 9,177 distribution miles. Confirm or provide an accurate target value. | N/A | 233182.8511 | 9171 | Forecast amounts are for HFRA. SCE provides an estimated mileage target that can be used as a proxy, should SPD need to have a roughly equivalent numerical target. SCE provides its official target as a percentage because HFRA mileage can charge marginally for a number of reasons.
VM-8 | 2026 | N/A | 0 | 16193.9157 | Inspect 100% of transmsission circuit miles in HFRA and prescribe mitigation as needed to achieve clearance | Page 367 of SCE approved 2026-28 Base WMP (R2) indicates that the population is ~13,000 transmission miles, and page 27 shows that overhead transmission miles includes 8,318 non_HFTD miles. This results in 13,000-8,318=4,682 HFRA transmission miles. Confirm or provide an accurate target value. | N/A | 30096.9447 | 4257 | Forecast amounts are for HFRA. SCE provides an estimated mileage target that can be used as a proxy, should SPD need to have a roughly equivalent numerical target. SCE provides its official target as a percentage because HFRA mileage can charge marginally for a number of reasons.
VM-8 | 2027 | N/A | 0 | 16174.471 | Inspect 100% of transmsission circuit miles in HFRA and prescribe mitigation as needed to achieve clearance | Page 367 of SCE approved 2026-28 Base WMP (R2) indicates that the population is ~13,000 transmission miles, and page 27 shows that overhead transmission miles includes 8,318 non_HFTD miles. This results in 13,000-8,318=4,682 HFRA transmission miles. Confirm or provide an accurate target value. | N/A | 29606.4788 | 4257 | Forecast amounts are for HFRA. SCE provides an estimated mileage target that can be used as a proxy, should SPD need to have a roughly equivalent numerical target. SCE provides its official target as a percentage because HFRA mileage can charge marginally for a number of reasons.
VM-8 | 2028 | N/A | 0 | 16195.482 | Inspect 100% of transmsission circuit miles in HFRA and prescribe mitigation as needed to achieve clearance | Page 367 of SCE approved 2026-28 Base WMP (R2) indicates that the population is ~13,000 transmission miles, and page 27 shows that overhead transmission miles includes 8,318 non_HFTD miles. This results in 13,000-8,318=4,682 HFRA transmission miles. Confirm or provide an accurate target value. | N/A | 29132.053 | 4257 | Forecast amounts are for HFRA. SCE provides an estimated mileage target that can be used as a proxy, should SPD need to have a roughly equivalent numerical target. SCE provides its official target as a percentage because HFRA mileage can charge marginally for a number of reasons.
VM-2.1 | 2026 | N/A | N/A | N/A | 135000 | SCE approved 2026-28 Base WMP (R2) appears to have broken out "02.a-d_IOU WMP Cost Reporting and Account Tracking Template 2026_09"'s VM-2 into VM-2.1 and VM-2.2. Provide OpEx and CapEx. | N/A | N/A | No change | SCE does not separately track costs associated with VM-2.1 and/or VM-2.2. Structure brushing costs are tracked in Table 11 under the WMP initiative of "Pole Clearing"
VM-2.1 | 2027 | N/A | N/A | N/A | 135000 | SCE approved 2026-28 Base WMP (R2) appears to have broken out "02.a-d_IOU WMP Cost Reporting and Account Tracking Template 2026_09"'s VM-2 into VM-2.1 and VM-2.2. Provide OpEx and CapEx. | N/A | N/A | No change | SCE does not separately track costs associated with VM-2.1 and/or VM-2.2. Structure brushing costs are tracked in Table 11 under the WMP initiative of "Pole Clearing"
VM-2.1 | 2028 | N/A | N/A | N/A | 135000 | SCE approved 2026-28 Base WMP (R2) appears to have broken out "02.a-d_IOU WMP Cost Reporting and Account Tracking Template 2026_09"'s VM-2 into VM-2.1 and VM-2.2. Provide OpEx and CapEx. | N/A | N/A | No change | SCE does not separately track costs associated with VM-2.1 and/or VM-2.2. Structure brushing costs are tracked in Table 11 under the WMP initiative of "Pole Clearing"
VM-2.2 | 2026 | N/A | N/A | N/A | 73000 | SCE approved 2026-28 Base WMP (R2) appears to have broken out "02.a-d_IOU WMP Cost Reporting and Account Tracking Template 2026_09"'s VM-2 into VM-2.1 and VM-2.2. Provide OpEx and CapEx. | N/A | N/A | No change | SCE does not separately track costs associated with VM-2.1 and/or VM-2.2. Structure brushing costs are tracked in Table 11 under the WMP initiative of "Pole Clearing"
VM-2.2 | 2027 | N/A | N/A | N/A | 73000 | SCE approved 2026-28 Base WMP (R2) appears to have broken out "02.a-d_IOU WMP Cost Reporting and Account Tracking Template 2026_09"'s VM-2 into VM-2.1 and VM-2.2. Provide OpEx and CapEx. | N/A | N/A | No change | SCE does not separately track costs associated with VM-2.1 and/or VM-2.2. Structure brushing costs are tracked in Table 11 under the WMP initiative of "Pole Clearing"
VM-2.2 | 2028 | N/A | N/A | N/A | 73000 | SCE approved 2026-28 Base WMP (R2) appears to have broken out "02.a-d_IOU WMP Cost Reporting and Account Tracking Template 2026_09"'s VM-2 into VM-2.1 and VM-2.2. Provide OpEx and CapEx. | N/A | N/A | No change | SCE does not separately track costs associated with VM-2.1 and/or VM-2.2. Structure brushing costs are tracked in Table 11 under the WMP initiative of "Pole Clearing"
SH-20 | 2027 | N/A | N/A | N/A | Perform splice shunting based on learnings from 2026, subject to resource/external constraints and other execution risks | Provide (1) estimated Target in units, (2) CapEx and (3) OpEx | N/A | N/A | Not available | Target and budget for 2027 and 2028 have not yet been determined and will be based on learnings from 2026.
SH-20 | 2028 | N/A | N/A | N/A | Perform splice shunting based on learnings from 2026 and 2027, subject to resource constraints and other execution risks | Provide (1) estimated Target in units, (2) CapEx and (3) OpEx | N/A | N/A | Not available | Target and budget for 2027 and 2028 are not yet determined and will be based on learnings from 2026.
SH-14 | 2028 | N/A | N/A | N/A | Remediate the balance of remaining spans in SCE’s HFRA, subject to resource constraints and other execution risks | Provide (1) estimated Target in units, (2) CapEx and (3) OpEx | 4550.9687 | 4617.9668 | Not available | Target for 2028 is not yet determined and will depend on execution in 2026 and 2027.