ATTACHMENT 1

Additional Provisions

{SCE Selection Note: applicable to IFOM Renewable Projects.

Selection terms for FCDS and Energy Only are based on the status of the Interconnection Agreement. Please interpret drafting notes consistent with the following:

- For a Project that is stand-alone RPS and that is not sharing its Interconnection Agreement with another project, and if the Project’s Interconnection Agreement has FCDS, utilize the language designated as FCDS.

- For a Project that is stand-alone RPS and that is not sharing its Interconnection Agreement with another project, and if the Project’s Interconnection Agreement is Energy Only, utilize the language designated as Energy Only.

- For a Project that is RPS and that is co-located with BESS, if the Interconnection Agreement has FCDS, but zero deliverability is being allocated to the RPS Project, utilize the language designated as Energy Only and incorporate appropriate Co-Located and Shared Facilities Language.

- For a Project that is RPS and that is co-located with BESS, if the Interconnection Agreement has FCDS, and any deliverability is allocated to the RPS Project, utilize the language designated as FCDS and incorporate appropriate Co-Located and Shared Facilities Language.

PURCHASE AND SALE OF PRODUCT

  - Product.

The “Product” consists of any and all Energy net of Station Use, Green Attributes, and Capacity Attributes, generated by, associated with, or attributable to the Project throughout the Delivery Period. Seller shall not substitute or purchase any Green Attributes from any generating resource other than the Project for delivery hereunder.

Project.

The “Project” consists of Seller’s electric renewable generating facility and Prevention Equipment, and Protective Apparatus, together with all materials, equipment, systems, structures, features and improvements necessary to produce energy at the renewable generating facility, excluding the Site, land rights and interests in land as more fully described in Attachment 2.

Project Name. [Name].

Location of Project. [Project Address], as further described in Attachment 2.

Delivery Point. The Delivery Point for the Project shall be at the point of interconnection with the CAISO Controlled Grid, [insert name or location] {SCE Note: Placeholder for identifying location on CAISO Controlled Grid}, as specified in Attachment 2.

Interconnection Point. The Interconnection Point is [insert name and location], as specified in Attachment 2.

Interconnection Queue Position. [Number(s) to be inserted], as specified in Attachment 2.

Meters. The locations of the CAISO Approved Project Meter and each Check Meter is set forth in the single-line diagram of the CAISO Controlled Grid interconnection set forth in Attachment 2.

Project ERR Type. [Generation Technology].

Local Capacity Area. [examples: CAISO System, Big Creek-Ventura, LA Basin, etc.].

Station Use. Seller shall be responsible for all costs related to Station Use. The Project is expected to use [number #] MWh per year for Station Use. {SCE Note: insert description of Station Use}

Site Location and Control.

This Agreement is specific to the Site set forth in Section 1.02(b) of this Attachment 1. Seller may change the location of the Site only upon SCE’s prior written consent, which consent is in SCE’s sole discretion.

Seller shall have Site Control from the Effective Date and continuing throughout the Term.

Seller shall provide SCE with prompt Notice of any change in the status of Seller’s Site Control.

Committed Amount.

Seller shall construct and install the Project such that the Project can provide the Contract Capacity, AC Nameplate Capacity, [DC Rating Capacity] {SCE Selection Note: applicable to Solar, otherwise delete}, and the Expected Annual Net Energy Production (collectively referred to as the “Committed Amount”). The Expected Contract Capacity, Expected AC Nameplate Capacity, and [Expected DC Rating Capacity] {SCE Selection Note: applicable to Solar, otherwise delete} are each provided in Attachment 3, and the Expected Annual Net Energy Production is as set forth below.

Failure to Demonstrate the Expected Contract Capacity.

[If Seller has otherwise complied with its obligations under this Agreement, including satisfying the criteria set forth in Section 2.04 of this Attachment 1, and the Renewable Capacity Test indicates that the Demonstrated DC Rating Capacity is less than the Expected DC Rating Capacity, and the Demonstrated Contract Capacity is less than the Expected Contract Capacity and greater than or equal to seventy-five percent (75%) of the Expected Contract Capacity, then:

The Expected Annual Net Energy Production will be recalculated using the Demonstrated DC Rating Capacity; and

Prior to the Initial Delivery Date (and as a condition to its occurrence), Seller shall pay SCE an amount equal to the product of [Dollar amount text] dollars ($[Number]) {SCE Note: amount to be provided by SCE} per kW and the difference (in kWs) between the Expected DC Rating Capacity and the Demonstrated DC Rating Capacity; provided that, with SCE’s consent, Seller may elect to apply its Development Security toward this payment.] {SCE Selection Note: the foregoing bracketed language is applicable to Solar, otherwise delete}

[If Seller has otherwise complied with its obligations under this Agreement, including satisfying the criteria set forth in Section 2.04 of this Attachment 1, and the Renewable Capacity Test indicates that the Demonstrated Contract Capacity is less than one hundred percent (100%) of the Expected Contract Capacity and is greater than or equal to seventy-five percent (75%) of the Expected Contract Capacity, then, prior to the Initial Delivery Date (and as a condition to its occurrence):

      - The Expected Annual Net Energy Production will be recalculated using the Demonstrated Contract Capacity; and

Seller shall pay SCE an amount equal to the product of [Dollar amount text] dollars ($[Number]) {SCE Note: amount to be provided by SCE} per kW and the difference (in kWs) between the Expected Contract Capacity and the Demonstrated Contract Capacity; provided that, with SCE’s consent, Seller may elect to apply its Development Security toward this payment.] {SCE Note: the foregoing bracketed language is applicable to IFOM Renewable Projects that are not Solar, delete for Solar}

Over-Installed Amounts.

If, at any time during the Delivery Period, any of the Demonstrated Contract Capacity, Demonstrated AC Nameplate Capacity, or Demonstrated DC Rating Capacity, installed at the Site exceeds the Expected Contract Capacity, Expected AC Nameplate Capacity, or Expected DC Rating Capacity, respectively (collectively, the “Over-Installed Amounts”), then, notwithstanding anything contained in this Agreement to the contrary: (1) SCE shall have the exclusive right to the applicable Product from such Over-Installed Amounts during the Delivery Period, and (2) the Product Price applicable to such Over-Installed Amounts during the Delivery Period shall be zero dollars.

Expected Annual Net Energy Production.

During the Delivery Period, the Expected Annual Net Energy Production for the Project for each Term Year will be the value calculated in accordance with the following formula:

Expected Annual Net Energy Production in Term Year y (in kWh) = A x B [x Cy] {SCE Note: bracketed language applicable to Solar and Baseload, delete for Wind}

Where:

y = 	Term Year,

[A = 	DC Rating Capacity,] {SCE Selection Note: applicable to Solar, otherwise delete}

[A = 	Contract Capacity,] {SCE Selection Note: applicable to IFOM Renewable Projects that are not Solar}

[B = 	Annual Energy Yield Factor: [Number] kWh AC per kWPDC per year, {SCE Note: this should be the annual AC energy in kWh that is expected to be delivered to SCE per installed peak DC power in kWPDC of Photovoltaic Modules}] {SCE Selection Note: applicable to Solar, otherwise delete}

[B =	[Number] % capacity factor x 8,760 hours per year,] {SCE Selection Note: applicable to IFOM Renewable Projects that are not Solar}

[Cy =	Annual Degradation Factor for the applicable Term Year.] {SCE Selection Note: applicable to Solar, otherwise delete}

[Cy =	Annual Production Factor for the applicable Term Year] {SCE Selection Note: applicable to Baseload projects with predictable production variation over time due to technology type}

Price.

The price for the Product from the Project will be the Product Price, as set forth in Attachment 3.

If the Expected Initial Delivery Date is adjusted pursuant to Section 2.06 or Section 8.03, then the dates in the price table(s) in Attachment 3 shall be adjusted forward to reflect the adjusted Expected Initial Delivery Date. In no event shall the foregoing adjustment result in an increase in payments from Buyer to Seller in excess of what would have originally occurred absent such adjustment.

Intentionally Omitted.

Resource Adequacy.

Seller’s obligation to deliver, and SCE’s obligation to purchase, Capacity Attributes, shall include the following:

[Full Capacity Deliverability Status. Seller shall apply for Full Capacity Deliverability Status in an amount equal to the Expected Contract Capacity. Commencing on the Initial Delivery Date and continuing throughout the Delivery Period, Seller shall ensure that the Project is allocated the maximum amount of Full Capacity Deliverability Status it is eligible to receive by the CAISO.] {SCE Note: applicable to Projects with FCDS, delete and replace with “Intentionally Omitted” for Energy Only Projects}

Effectuating SCE’s use of Capacity Attributes. At least six (6) months before the Initial Delivery Date and throughout the Delivery Period, Seller shall, at its own cost, take all actions and execute all documents or instruments necessary to effectuate the use of any and all Capacity Attributes and Resource Adequacy Benefits for SCE’s sole benefit throughout the Delivery Period, which actions include:

Cooperating with and encouraging the regional entity responsible for resource adequacy administration to certify or qualify the Project for resource adequacy purposes;

[Cooperating with the CPUC, any other applicable Governmental Authority, the CAISO, and SCE to ensure completion of all Regulatory RA Qualification Activities, in accordance with Section 5.03(a)(iii) of this Attachment 1, and otherwise testing the Project in order to certify the Project in accordance with RA Compliance Obligations;] {SCE Note: applicable to Projects with FCDS, delete for Energy Only} [Testing the Project in order to certify the Project for resource adequacy purposes and in accordance with RA Compliance Obligations;] {SCE Note: applicable to Energy Only Projects, delete for Projects with FCDS}

Complying with all current and future RA Compliance Obligations applicable to the Project, including provisions regarding performance obligations and penalties, if applicable;

Pursuing and obtaining any and all Capacity Attributes and Resource Adequacy Benefits to the extent that Applicable Laws, including as may be changed after the Effective Date, allow for any Capacity Attributes or Resource Adequacy Benefits to be obtained other than by the completion of Delivery Network Upgrades (as defined in the CAISO Tariff and as applicable to the Project);

Execute all documents or instruments necessary, and provide all information otherwise needed, (1) for the Product to be shown on [Supply Plans and] {SCE Note: delete bracketed language for Energy Only Projects} RA Compliance Showings and to be used to satisfy RA Compliance Obligations; and (2) as required by the CAISO or CPUC for SCE to comply with Applicable Laws;

Engaging in commercially reasonable efforts to cause the Resource ID and the benefitting load serving entity SC identification number to (A) be included in all applicable [Supply Plans and] {SCE Note: delete bracketed language for Energy Only Projects} RA Compliance Showings, and (B) promptly communicate changes in such information to each other;

Take all actions necessary to allow SCE to perform its duties as an SC for the Project, including providing (A) all information needed for SCE to include the Project on SCE’s [Supply Plans, and] {SCE Note: delete bracketed language for Energy Only Projects} RA Compliance Showings, and (B) any information requested by SCE related to the Project that is required to be provided to the CAISO or CPUC for SCE to comply with Applicable Laws.

[Delivery Obligations.] {SCE Note: this subsection (c) is applicable to Projects with FCDS, delete entire subsection (c) and replace with “Intentionally Omitted” for Energy Only Projects}

Showing Month Notice. For each Showing Month of the Delivery Period, if Seller intends to deliver less than the NQC or EFC of the Project for any reason, then Seller shall submit written notification to SCE no later than fifteen (15) Business Days before the initial RA Compliance Showing deadline for such Showing Month (such timely notice, the “Showing Month Notice”), identifying the amount of NQC and EFC Seller intends to deliver to SCE.

Intentionally Omitted.

Excusable Adjustment to Capacity Attribute Delivery Obligations.

For each Showing Month that is part of the Delivery Period, if Seller provides a timely Showing Month Notice to SCE and complies with the outage requirements set forth in Article 6, Seller’s obligation to deliver, and SCE’s obligation to purchase, the Capacity Attributes of the Project may be reduced by the amount of any Maintenance Outages which exist with respect to any portion of the Project during the applicable Showing Month.

Change in Capacity Attributes. If any change by the CAISO, CPUC or other Governmental Authority occurs that defines new or re-defines existing:

Local Capacity Areas, resulting in a decrease or increase in the amount of Capacity Attributes related to a Local Capacity Area provided hereunder, or resulting in the Project subsequently qualifying for a Local Capacity Area, there will be no change in payments made pursuant to this Agreement; and

Flexible RAR, resulting in an increase in the amount of Capacity Attributes related to Flexible RAR provided hereunder, or resulting in the Project, or a portion of the Project which did not previously qualify to satisfy Flexible RAR, subsequently qualifying to satisfy Flexible RAR, there will be no change in payments made pursuant to this Agreement.

Green Attributes.

### Seller’s obligation to deliver, and SCE’s obligation to purchase, Green Attributes, shall include the following:

[Throughout the Delivery Period, Seller (i) represents and warrants that Seller holds the rights to all Green Attributes from the Project, (ii) shall provide, dedicate and convey title to and possession of all Green Attributes associated with all electricity generation from the Project to SCE as part of the Product being delivered, (iii) represents and warrants that all energy generated by the Project results in the production of Renewable Energy Credits, and (iv) Seller shall convey title to all Green Attributes.] {SCE Note: for full buy-sell}

[Throughout the Delivery Period, Seller (i) represents and warrants that Seller holds the rights to all Green Attributes associated with all Metered Amounts from the Project, (ii) Seller shall provide, dedicate, and convey title to and possession of all Green Attributes associated with all associated with all Metered Amounts from the Project to SCE as part of the Product being delivered, and (iii) Seller represents and warrants that all associated with all Metered Amounts associated with the Project results in the production of Renewable Energy Credits] {SCE Note: for Excess Sales}

Effectuating SCE’s use of Green Attributes. Commencing at least six (6) months before the Initial Delivery Date and throughout the Delivery Period, Seller shall, at its own cost, take all actions and execute all documents or instruments necessary to effectuate the use of any and all Green Attributes for SCE’s sole benefit throughout the Delivery Period, which actions include:

#### Committing the entire Metered Amounts to SCE;

#### Complying with Applicable Laws regarding the certification and transfer of Renewable Energy Credits, including participation in WREGIS or other process recognized under Applicable Laws for the registration, transfer or ownership of Green Attributes associated with the Project. Seller will take all actions to ensure SCE is the Account Holder and Qualified Reporting Entity for the Project throughout the Delivery Period, and shall register the Project as a Registered Generating Unit. Seller shall provide SCE with all supporting documents requested for registration approval, as required by WREGIS; and

#### If Seller has sold Green Attributes (or product that would be considered Green Attributes under this Agreement if it were attributable to the Delivery Period) to any party other than SCE with respect to a period that is prior to the Initial Delivery Date of the Project, Seller shall, or shall cause such party to: (i) take all actions necessary for SCE to be the Account Holder as of the Initial Delivery Date of the Project, and (ii) take all actions necessary for SCE to be the Qualified Reporting Entity prior to the generation of any WREGIS Certificates associated with deliveries of Product on and after the Initial Delivery Date of the Project. SCE agrees to transfer all WREGIS Certificates associated with generation from the Project prior to the Initial Delivery Date of the Project to Seller or Seller’s designee.

[Bioenergy Benefits.

For all electric generation using biomethane as fuel, Seller shall transfer to SCE sufficient renewable and environmental attributes of biomethane production and capture to ensure that there are zero (0) net emissions associated with the production of electricity from the Project using the biomethane.

For all electric generation using biomethane as fuel, neither SCE nor Seller may make a marketing, regulatory, or retail claim that asserts that a procurement contract to which that entity was a party resulted, or will result, in greenhouse gas reductions related to the destruction of methane if the capture and destruction is required by law. If the capture and destruction of the biomethane is not required by law, neither SCE nor Seller may make a marketing, regulatory, or retail claim that asserts that a procurement contract to which that entity was a party resulted, or will result, in greenhouse gas reductions related to the destruction of methane, unless the environmental attributes associated with the capture and destruction of the biomethane pursuant to that contract are transferred to SCE and retired on behalf of the retail customers consuming the electricity associated with the use of that biomethane, or unless Seller’s procurement contract with the source of biomethane prohibits the source of biomethane from separately marketing the environmental attributes associated with the capture and destruction of the biomethane sold pursuant to that contract, and such attributes have been retired.] {SCE Note: Biomethane projects only}

Compliance Expenditure Cap.

If Seller establishes to SCE’s reasonable satisfaction that an RA Change in Law or an RPS Change in Law has occurred, then Seller’s required out-of-pocket expenses in connection with any Compliance Actions or any RPS Compliance Actions incurred between the Effective Date and the last day of the Term shall be limited in the aggregate over the Term to the amount shown below (“Compliance Expenditure Cap”) associated with the Term Year in which such RA Change in Law or RPS Change in Law occurs:

| Term Year | Compliance Expenditure Cap |
| --- | --- |
| 1 |  |
| 2 |  |
| 3 |  |
| 4 |  |
| 5 |  |
| 6 |  |
| 7 |  |
| 8 |  |
| 9 |  |
| 10 |  |
| 11 |  |
| 12 |  |
| 13 |  |
| 14 |  |
| 15 |  |
| 16 |  |
| 17 |  |
| 18 |  |
| 19 |  |
| 20 |  |

If Seller reasonably anticipates the need to incur out-of-pocket expenses in excess of the Compliance Expenditure Cap in order to take any Compliance Action or any RPS Compliance Action, then Seller shall provide Notice to SCE within sixty (60) days after the enactment of such RA Change in Law or such RPS Change in Law, as applicable, of such anticipated costs and expenses, together with an explanation of the RA Change in Law or RPS Change in Law and resulting change to Compliance Actions or RPS Compliance Actions that would cause the increased costs or expenses.

SCE will have sixty (60) days to evaluate such Notice (during which time period Seller is not obligated to take any Compliance Actions or RPS Compliance Actions described in the Notice) and shall, within such time, either:

(1) agree to reimburse Seller for all, or if such Compliance Actions or RPS Compliance Actions may be partially accomplished, then some portion of, the costs and expenses that exceed the Compliance Expenditure Cap (such SCE-agreed upon costs, the “Accepted Compliance Costs” and those costs not accepted, the “Rejected Compliance Costs”), and, if applicable, (2) waive Seller’s obligation to take such Compliance Actions or RPS Compliance Actions for costs that exceed the Compliance Expenditure Cap and that SCE has not agreed to reimburse Seller; or

(1) elect to receive payment from Seller of an amount equal to the Compliance Expenditure Cap within sixty (60) days of Notice of SCE’s election and (2) waive Seller’s obligation to take any Compliance Actions or RPS Compliance Actions (whether or not they exceed the Compliance Expenditure Cap) with respect to the RA Change in Law or RPS Change in Law.

Seller shall not be obligated to take any Compliance Actions or RPS Compliance Actions referenced in Seller’s notice to SCE until SCE has agreed to reimburse Seller for the Accepted Compliance Costs related to such Compliance Actions or RPS Compliance Actions. If SCE agrees to reimburse Seller for the Accepted Compliance Costs, then Seller shall take all Compliance Actions or RPS Compliance Actions covered by the Accepted Compliance Costs and SCE shall reimburse Seller for Seller’s reasonable, actual, and documented costs to accomplish the Compliance Actions or RPS Compliance Actions, not to exceed the Accepted Compliance Costs.

If Seller believes that no reasonably practicable Compliance Actions or RPS Compliance Actions are available with respect to an RA Change in Law or RPS Change in Law, then Seller shall provide Notice to SCE within sixty (60) days after the enactment of such RA Change in Law or RPS Change in Law together with an explanation of the RA Change in Law or RPS Change in Law and why the potential Compliance Actions or the potential RPS Compliance Actions are not reasonably practicable. If SCE agrees that no reasonably practicable Compliance Actions or RPS Compliance Actions are available with respect to such RA Change in Law or RPS Change in Law, then Seller shall pay to SCE an amount equal to the Compliance Expenditure Cap within sixty (60) days after receipt of SCE’s Notice confirming that no reasonably practicable Compliance Actions or RPS Compliance Action are available with respect to such RA Change in Law or RPS Change in Law. Payment of such amount will satisfy Seller’s obligations with respect to such RA Change in Law or RPS Change in Law. If SCE disagrees that no reasonably practicable Compliance Actions or RPS Compliance Actions are available with respect to such RA Change in Law or RPS Change in Law, then:

SCE shall provide Notice to Seller, within thirty (30) days after receipt of Seller’s Notice, indicating the Compliance Actions or RPS Compliance Actions that SCE believes are reasonably practicable;

Seller shall provide Notice to SCE, within thirty (30) days after receipt of SCE’s Notice, of the anticipated costs and expenses in excess of the Compliance Expenditure Cap to take such Compliance Actions or such RPS Compliance Actions; and

SCE shall have sixty (60) days to evaluate such Notice (during which time Seller is not obligated to take any Compliance Actions or RPS Compliance Actions described in the Notice) and the Parties shall proceed in accordance with Section 1.08(b) of this Attachment 1 above.

[To the extent that (A) an RA Change in Law results in any Rejected Compliance Costs, and the failure to complete the Compliance Actions associated with such Rejected Compliance Costs results in the reduction of the Project’s NQC or EFC or (B) no reasonably practicable Compliance Actions are available with respect to such RA Change in Law and such RA Change in Law results in the reduction of the Project’s NQC or EFC and Seller has, as applicable, (I) completed or made reasonable progress toward the completion of the Compliance Actions for which Seller is financially responsible and the Compliance Actions that are associated with any related Accepted Compliance Costs, or (II) paid to SCE an amount equal to the Compliance Expenditure Cap pursuant to this Section 1.08 of this Attachment 1, then commencing upon the implementation of any such RA Change in Law and continuing through the end of the Delivery Term, this Agreement shall be interpreted in accordance with the following guidelines:

the Expected NQC [and the Expected EFC] shall be deemed to refer to the reduced NQC [and reduced EFC] referenced above. {SCE Note: delete bracketed language for IFOM Renewable Projects that are not expected to provide EFC}]

{SCE Note: delete subsection (d) in its entirety for IFOM Renewable Projects that are Energy Only Projects}

TERM AND DELIVERY PERIOD

  - Initial Delivery Date.

The conditions to the Initial Delivery Date for the Project shall also include:

The following conditions have been satisfied for the Project:

The Demonstrated Contract Capacity, as demonstrated in the Renewable Capacity Test, is greater than or equal to seventy-five percent (75%) of the Expected Contract Capacity; and

The Project has been constructed and installed in accordance with Attachment 2 and Attachment 3;

Seller has received:

authority from FERC, pursuant to Section 205 of the Federal Power Act, 16 U.S.C. § 824d, for wholesale sales of energy, capacity and ancillary services at market-based rates, and

all other approvals and authorizations required for Seller to perform its obligations under this Agreement;

Seller has executed a “Participating Generator Agreement” or “Participating Load Agreement,” as applicable, a “Meter Service Agreement For CAISO Metered Entities,” as those terms are defined in the CAISO Tariff, and any other forms or agreements required by the CAISO with respect to the Project, and delivered true and complete copies of all such forms and agreements to SCE;

Seller has provided to SCE the number filed by the T&D Provider with FERC as a representation for all net energy losses or avoided losses, as filed by the T&D Provider at FERC, associated with the transmission of energy through the electric system from the high voltage side of the Project’s substation bus bar to the interface with the CAISO Controlled Grid, also known as the distribution loss factor (the “DLF”), if a DLF is applicable to the Project;

Seller has registered with the NERC as the Project’s Generator Owner and Generator Operator if Seller is required to be a registered entity pursuant to the NERC Reliability Standards;

Seller has entered into and complied in all material respects with all obligations under the Interconnection Agreement and all other agreements, tariffs, and requirements necessary to enable parallel operation of the Project with the T&D Provider’s electric system and the CAISO Controlled Grid;

Seller has obtained certification (the “CAISO Certification”) for the Project such that the Project meets the certification and testing requirements applicable to the Project, as set forth in the CAISO Tariff, including certification and testing for all ancillary services, PMAX, and PMIN, and is otherwise compliant with all CAISO Tariff requirements applicable to the Project;

[Seller has obtained and delivered to SCE a certification that the Project has Full Capacity Deliverability Status, as determined by the CAISO, in an amount equal to the Expected Contract Capacity;] {SCE NTD: applicable to Projects with FCDS, delete and replace with “Intentionally Omitted” for Energy Only Projects}

Intentionally Omitted;

At least thirty (30) days prior to the Expected Initial Delivery Date, Seller has:

taken all actions and executed all documents and instruments, required to authorize SCE to act as Scheduling Coordinator for the Project under this Agreement, and SCE is authorized to act as Scheduling Coordinator for the Project effective as of the first day of the Delivery Period;

provided SCE with all facility and metering information necessary to communicate with SCE as requested by SCE;

[Seller has obtained an NQC for the Project which is equal to the maximum amount for which the Project is eligible under the then-current Resource Adequacy Rulings;] {SCE NTD: applicable to Projects with FCDS, delete and replace with “Intentionally Omitted” for Energy Only Projects}

[Seller has obtained an EFC for the Project which is equal to the maximum amount for which the Project is eligible under the then-current Resource Adequacy Rulings;] {SCE NTD: applicable to Projects with FCDS, delete and replace with “Intentionally Omitted” for Energy Only Projects}

Seller has delivered an Outage Schedule in accordance with Section 6.04 of this Attachment 1;

Seller has completed the installation and testing of the Project for purposes of financing, Permits, the Interconnection Agreement, operating agreements, the EPC agreement and manufacturer’s warranties;

Seller has received an Independent Engineer’s certification that the Project has been completed in all material respects and consistent with Attachment 2 and Attachment 3 (except punch list items that do not materially and adversely affect the ability of the Project to operate as intended);

[Seller has timely submitted its Showing Month Notice for the Showing Month associated with the Expected Initial Delivery Date;] {SCE NTD: applicable to Projects with FCDS, delete and replace with “Intentionally Omitted” for Energy Only Projects}

Seller has taken all steps necessary to allow SCE to be designated as the Account Holder in accordance with Section 1.07(b) of this Attachment 1;

Seller has obtained CEC Pre-Certification;

Seller is Forecasting to SCE in accordance with Article 6 of this Attachment 1; and

Seller has provided SCE with evidence that the CAISO Approved Meter has been programmed to account for all losses required by the CEC for the purpose of claiming Green Attributes from the Project.

The Parties shall cooperate with each other in order for SCE to be able to utilize the Project and receive the Product beginning on the Initial Delivery Date.

Payments

  - Payment Mechanisms.

“Invoicing Party”: SCE

“Paying Party”:

SCE for Product Payments;

Seller for Product Replacement Damage Amounts; and

SCE or Seller, as applicable, for other amounts payable under this Agreement from time to time.

“Invoice Date”: The last Business Day of the month following the Invoice Calculation Period for which the Paying Party’s payment obligations are calculated.

“Payment Date”: The last Business Day of the month following the Invoice Calculation Period for which the Paying Party’s payment obligations are calculated.

“Invoice Calculation Period”: a calendar month.

Other Payment and Invoicing Requirements.

The invoice shall include documentation supporting any SCE penalties, Negative LMP Costs, Term Year Negative CAISO Revenues, Negative CAISO Revenues, CAISO Costs, CAISO Sanctions, or other applicable revenues, charges and offsets which affected the net amount in the invoice.

Allocation of Other Payments and Costs.

Throughout the Delivery Period, except as otherwise provided herein, (1) SCE shall be entitled to receive and retain all revenues associated with the Product, including any capacity revenues and any CAISO Revenues, and (2) SCE shall be responsible for all CAISO Costs and CAISO Sanctions.

To the extent that SCE requires Seller to participate in the PIRP/EIRP program, SCE shall be responsible for PIRP/EIRP forecasting fees.

Product Payments.

SCE shall make a Product Payment to Seller for each month of the Delivery Period for Product delivered by Seller to the Delivery Point, as measured by the CAISO Approved Meter, in accordance with this Agreement, the CAISO Tariff, and Applicable Law. Except for Curtailed Product, SCE has no obligation to purchase Product that is not or cannot be delivered to the Delivery Point as a result of any circumstance.

The Product Payment shall be calculated as set forth below:

[“Product Payment” = (A×B-C-D+H)-E-F+G] {SCE Note: this formula and variables below are applicable to Projects that are using the Federal Investment Tax Credit and are not using the Federal Production Tax Credit, as represented in Section 3.05}

where:

A = the Product Price, in $/kWh (i.e., $/MWh/1000), as specified in Section 1.04 of this Attachment 1,

B = The sum of Metered Amounts in kWh,

C = The sum of any Excess Amounts in kWh,

D = The sum of any amount of energy produced by the Project that Seller delivers in violation of Section 6.01(b) of this Attachment 1, in kWh,

E = The sum of the absolute value of each of any Negative LMP Costs, any Term Year Negative CAISO Revenues, and any Negative CAISO Revenues, in dollars,

F = The sum of the absolute value of each of any CAISO Sanctions and CAISO Costs that are the responsibility of Seller, in dollars,

G = The sum of any amount due attributable to any Term Year Excess Amounts in accordance with Sections 3.03(b)(iv) of this Attachment 1, and

H = The sum of any Curtailed Product in kWh.

[“Product Payment” = A×B-C-D+((A+I )×H)-E-F+G] {SCE Note: this formula and variables below are applicable to Projects using Federal Production Tax Credit, and are not using the Federal Investment Tax Credit, as represented in Section 3.05}

where:

A = the Product Price, in $/kWh (i.e., $/MWh/1000), as specified in Section 1.04 of this Attachment 1,

B = The sum of Metered Amounts in kWh,

C = The sum of any Excess Amounts in kWh,

D = The sum of any amount of energy produced by the Project that Seller delivers in violation of Section 6.01(b) of this Attachment 1, in kWh,

E = The sum of the absolute value of each of any Negative LMP Costs, any Term Year Negative CAISO Revenues, and any Negative CAISO Revenues, in dollars,

F = The sum of the absolute value of each of any CAISO Sanctions and CAISO Costs that are the responsibility of Seller, in dollars,

G = The sum of any amount due attributable to any Term Year Excess Amounts in accordance with Sections 3.03(b)(iv) of this Attachment 1,

H = The sum of any Curtailed Product in kWh, and

I = either:

- for the first ten (10) Term Years of the Delivery Period, the Federal Production Tax Credit Amount multiplied by [insert number in text] ([insert number numerically]), which multiplier grosses up, on an after-tax basis, the Federal Production Tax Credit Amount that Seller would have earned but failed to earn directly and solely as a result of a Project curtailment in accordance with Section 6.01(b)(iii) and any resulting Curtailed Product (in $/kWh); {SCE NTD: multiplier to be a number greater than 1.00, Offeror to provide documentation sufficient to substantiate}

- commencing at the start of the eleventh (11th) Term Year and continuing through the remaining of the Delivery Period, zero dollars ($0.00) per kWh.

If either Party determines that the Federal Production Tax Credit the Project would have received, with respect to any Curtailed Product, is less than the Federal Production Tax Credit Amount used to calculate the applicable Product Payment associated with such Curtailed Product, then, such Party shall Notify the other Party as soon as reasonably practicable, which Notice shall include: (x) the applicable quantity of Curtailed Product impacted, (y) documentation sufficient to substantiate the Federal Production Tax Credit the Project was eligible for, and (z) a calculation of any payment adjustment that results in an amount due to SCE, which amount shall be made as an adjustment to the next monthly invoice or separately invoiced to Seller (in which case, due within twenty (20) days after receipt of such invoice).

Excess Amounts.

If (i) during any Settlement Interval, Seller delivers Metered Amounts, expressed in MWh, in excess of the product of (x) the lesser of the Contract Capacity and the interconnection capacity, expressed in MW, and (y) the length of such Settlement Interval, expressed in hours (such excess amounts, “Settlement Interval Excess Amounts”), or (ii) during any Term Year, Seller delivers Metered Amounts, that are in the aggregate in excess of one hundred percent (100%) of the Expected Annual Net Energy Production for such Term Year (such excess amounts, “Term Year Excess Amounts”, and together with the Settlement Interval Excess Amounts are collectively referred to as “Excess Amounts”), then:

Except as set forth in Sections 3.03(b)(iv) of this Attachment 1, SCE shall be under no obligation to pay for any Excess Amounts,

If there is a Negative LMP during any Settlement Interval associated with Settlement Interval Excess Amounts, Seller shall pay to SCE an amount equal to the absolute value of the Negative LMP times such Settlement Interval Excess Amounts (“Negative LMP Costs”),

Seller shall be responsible for, shall pay for, or shall otherwise reimburse SCE for, all CAISO Sanctions and CAISO Costs attributable to any Term Year Excess Amounts,

For those Term Year Excess Amounts less than one hundred twenty percent (120%) of the Expected Annual Net Energy Production for such Term Year, the following shall apply:

If SCE submits Bids to the CAISO for the Project with a price that is greater than or equal to zero dollars ($0.00), then for each Settlement Interval, Seller shall be entitled to the lesser of (x) the product of the Term Year Excess Amounts multiplied by the Product Price, and (y) the CAISO Revenues attributable to such Term Year Excess Amounts, or

If SCE submits Bids to the CAISO for the Project as a Self-Schedule or with a price that is less than zero dollars ($0.00), then for each Settlement Interval with Term Year Excess Amounts (“Negatively Bid Term Year Excess Amounts”), Seller shall be entitled to the greater of (x) zero dollars ($0.00) and (y) the lesser of (1) the product of the Product Price multiplied by Negatively Bid Term Year Excess Amounts, and (2) CAISO Revenues attributable to such Negatively Bid Term Year Excess Amounts,

For those Term Year Excess Amounts greater than or equal to one hundred twenty percent (120%) of the Expected Annual Net Energy Production for such Term Year, SCE shall retain all CAISO Revenues attributable to such Term Year Excess Amounts; provided if SCE submits Bids to the CAISO for the Project with a price that is greater than or equal to zero dollars ($0.00), and the CAISO Revenue during any Settlement Interval associated with such Term Year Excess Amounts are less than zero dollars ($0.00), then Seller shall be responsible for such negative CAISO Revenues (“Term Year Negative CAISO Revenues”).

Additional Cost Responsibility.

For any Product that (1) Seller delivers as a result of Seller’s failure to adhere to its obligations under the CAISO Tariff (except to the extent attributable to SCE’s failure to perform its obligations as Scheduling Coordinator) or any CAISO directive, as such directive may be communicated to Seller by SCE, or (2) is associated with Seller’s violation of Section 6.01(b) of this Attachment 1, the following shall apply:

SCE will not be obligated to pay Seller for any such Product,

SCE shall retain all positive CAISO Revenues attributable to such Product, and

Seller shall be responsible for and shall pay all CAISO Sanctions, CAISO Costs, and all negative CAISO Revenues attributable to such Product (such negative CAISO Revenues, “Negative CAISO Revenues”).

As of the Effective Date, CAISO Sanctions are available for billing approximately one hundred twenty (120) days following the last day of the calendar month in which the event giving rise to the sanction occurs, or thirty (30) days after the CAISO final settlement data is available to SCE, whichever is sooner.

[If in any hour of any month in the Delivery Period Seller either:

fails to comply with its Forecasting requirements under this Agreement; or

is required to provide a Forecast, provides a Forecast, and the sum of Energy Deviations for each of the Settlement Intervals in that hour exceed the Performance Tolerance Band,

then, Seller shall be required to pay SCE liquidated damages equal to one hundred fifty percent (150%) of the Product Price for each MWh of Energy Deviation, or any portion thereof, in that hour.] {SCE Note: Intermittent only}

[Seller shall be responsible for all CAISO Costs for all Settlement Intervals where Energy Deviations exceed the Performance Tolerance Band.] {SCE Note: Baseload only}

“Energy Deviations” in kWh, means the absolute value of the difference, in kWh, in any Settlement Interval between (A) [Forecast-Derived Energy] {SCE Note: Intermittent only} [Expected Energy of the Project] {SCE Note: Baseload only}; and (B) Metered Amounts plus Lost Output.

The “Performance Tolerance Band,” shall be expressed in kWh, and is calculated as follows:

Performance Tolerance Band = 3% * Contract Capacity * one (1) hour

Seller’s Energy Delivery Obligation.

On the commencement of the first Term Year and for every Term Year thereafter, Seller is subject to the electric energy delivery [and availability] {SCE Note: Wind only} requirements and damages for failure to perform as set forth in this Section 3.03(d).

Seller’s Energy Delivery Obligation.

[“Seller’s Energy Delivery Obligation” for the twenty-four (24) month period immediately preceding the end of each Term Year commencing at the end of the second Term Year (“Deficiency Calculation Period”) is one hundred seventy percent (170%) of the average of the Expected Annual Net Energy Production amount over the two (2) Term Years comprising such Deficiency Calculation Period.] {SCE Note: applicable to Intermittent technologies}

[“Seller’s Energy Delivery Obligation” for the twelve (12) month period immediately preceding the end of each Term Year commencing at the end of the first Term Year (“Deficiency Calculation Period”) is ninety percent (90%) of the Expected Annual Net Energy Production amount applicable to such Term Year.] {SCE Note: applicable to Baseload technologies}

Event of Deficient Energy Deliveries.

[At the end of each Term Year, commencing with the end of the second Term Year, if the sum of Metered Amounts plus any Lost Output (calculated in accordance with Exhibit J) during the applicable Deficiency Calculation Period does not equal or exceed Seller’s Energy Delivery Obligation, then an “Event of Deficient Energy Deliveries” will be deemed to have occurred and the shortfall amount (in kWh) will be the “Energy Shortfall Amount.”

Notwithstanding the foregoing Energy Shortfall Amount calculation, if (1) there is an Event of Deficient Energy Deliveries for a particular Deficiency Calculation Period (“Shortfall Deficiency Calculation Period”), (2) the amount of Metered Amounts plus any Lost Output (calculated in accordance with Exhibit J) in the second Term Year of the applicable Shortfall Deficiency Calculation Period, which is also the first Term Year of the following Deficiency Calculation Period (“Shared Term Year”), is less than eighty five percent (85%) of the Expected Annual Net Energy Production amount for such Term Year, and (3) Seller has paid the Product Replacement Damage Amount for the applicable Shortfall Deficiency Calculation Period, then, solely for purposes of calculating the Energy Shortfall Amount in the following Deficiency Calculation Period, the amount of Metered Amounts plus any Lost Output (calculated in accordance with Exhibit J) in the Shared Term Year, shall be deemed equal to eighty five percent (85%) of the Expected Annual Net Energy Production for the Shared Term Year.] {SCE Note: applicable to Intermittent technologies}

[At the end of each Term Year, if the sum of the Metered Amounts plus any Lost Output (calculated in accordance with Exhibit J) during such Term Year does not equal or exceed Seller’s Energy Delivery Obligation, then an “Event of Deficient Energy Deliveries” will be deemed to have occurred, and the shortfall amount (in kWh) will be the “Energy Shortfall Amount.”] {SCE Note: applicable to Baseload technologies}

Product Replacement Damage Amount.

The Parties acknowledge that the damages sustained by SCE associated with an Event of Deficient Energy Deliveries would be difficult or impossible to determine, or that obtaining an adequate remedy would be unreasonably time consuming or expensive, and therefore agree that Seller shall pay SCE as liquidated damages an amount calculated under this Section 3.03(d), which is intended to compensate SCE for Seller’s failure to perform.

If an Event of Deficient Energy Deliveries occurs, Seller shall pay the Product Replacement Damage Amount calculated as follows:

“Product Replacement Damage Amount” = A × (B + C – D)

where:

A = the Energy Shortfall Amount for the applicable Deficiency Calculation Period (in kWh),

[B = the price obtained by calculating the simple average of the Market Clearing Price for the following hours of the applicable Deficiency Calculation Period: hour ending eleven (HE1100) through hour ending seventeen (HE1700) (expressed in $/kWh),] {SCE Note: applicable to Intermittent technologies other than Wind}

[B = the price obtained by calculating the simple average of the Market Clearing Price for all hours of the applicable Deficiency Calculation Period (expressed in $/kWh),] {SCE Note: applicable to Wind and Baseload only}

C = the price obtained by calculating the simple average price for California PCC-1 renewable energy credits, as published by Platts, or successor thereof (expressed in $/kWh) for the ninety (90) days immediately prior to, and including the last day of, the Deficiency Calculation Period, and

D = Product Price (in $/kWh).

If foregoing calculation results in a negative value, then the Product Replacement Damage Amount shall be deemed to equal zero dollars ($0.00). Notwithstanding anything contained in this Agreement to the contrary, in no event shall SCE owe Seller a Product Replacement Damage Amount.

Within ninety (90) days after the end of the applicable Term Year, SCE shall calculate any Product Replacement Damage Amount, and shall provide Notice to Seller of any Product Replacement Damage Amount owing, including a detailed explanation of, and rationale for, its calculation methodology, annotated work papers and source data.

Seller shall have thirty (30) days after receipt of SCE’s Notice to review SCE’s calculation and either pay the entire Product Replacement Damage Amount claimed by SCE or pay any undisputed portion and provide Notice to SCE of the portion Seller disputes along with a detailed explanation of, and rationale for, Seller’s calculation methodology, annotated work papers and source data.

The Parties shall negotiate in good faith to resolve any disputed portion of the Product Replacement Damage Amount and shall, as part of such good faith negotiations, promptly provide information or data relevant to the dispute as each Party may possess which is requested by the other Party.

Allocation of Resource Adequacy Capacity Product Payments and Charges.

During the Delivery Period, if the Project is subject to the terms of:

the Availability Standards, Non-Availability Charges, and Availability Incentive Payments, as those terms are defined by the CAISO Tariff, and as contemplated under the CAISO Tariff, or

any similar standards, charges or payments that may be implemented for resources providing flexible capacity resource adequacy attributes or other types of Resource Adequacy Benefits,

then, any Availability Incentive Payments and other resulting payments will be for the benefit of Seller and for Seller’s account and any Non-Availability Charges and other resulting charges are the responsibility of Seller and for Seller’s account.

DESIGN AND CONSTRUCTION OF PROJECT

  - Seller’s Obligations.

Seller’s obligations to be performed pursuant to Section 4.01 shall include the obligations to:

Provide accurate and complete operating characteristics of the Project in compliance with the CAISO Tariff:

At least thirty (30) days prior to the start of the Delivery Period, and

Within ten (10) days after such information changes during the Delivery Period.

Provide to SCE, at least thirty (30) days before the Expected Initial Delivery Date, Project information requested by SCE, including, at the minimum, the following and in the form issued for construction documents and drawings:

Site plan drawings for the Project;

Electrical one-line diagrams;

Control and data-acquisition details and configuration documents;

Major electrical equipment specifications;

General arrangement drawings;

Longitude and latitude of the centroid of the Site [and of each renewable component generator] {SCE Note: applicable to Wind and Geothermal, delete for all other technologies};

Artist renderings of the Site, if any;

Aerial photographs of the Site, if any;

Transformer specification;

Energy collection grid diagrams;

Intentionally Omitted;

Description of auxiliary loads;

Power conversion system specification;

Utility transmission/distribution one-line diagram;

Physical location, address or descriptive identification;

Updates to Seller’s contact information in Exhibit E, if applicable;

[Site plan drawing of the geothermal well field;

Process flow diagrams;

Piping and instrumentation diagrams;

Production and injection well flow rates and volumes;

Wellhead pressures;

Geothermal fluid chemistry;

Non-condensable gas composition;] {SCE Note: immediately above bracketed sections applicable to geothermal}

[Current inverter specification;

Photovoltaic module specification;

Solar energy collection grid diagrams;] {SCE Note: immediately above bracketed sections applicable to solar}

[Wind Turbine specification;

Wind energy collection grid diagrams;

Topographical maps showing the location of all Wind Turbines, and specifying the Wind Turbine model and Site-specific identification number;] {SCE Note: immediately above bracketed sections applicable to wind}

[Map showing the location of the Meteorological Equipment, including specifying the longitude and latitude of such;] {SCE Note: include for solar and wind}

No later than sixty (60) days after the Initial Delivery Date, Seller shall submit to SCE a complete set of as-built drawings of the Project, including civil, structural, mechanical and electric drawings and final process instrumentation diagrams, and the information in Section 4.01(b) of this Attachment 1.

Seller must not (A) withdraw the Interconnection Queue Position identified in Section 1.02 of this Attachment 1, (B) assign or transfer that Interconnection Queue Position or Interconnection Application to any entity, or (C) utilize the Interconnection Queue Position or Interconnection Application for the benefit of any power purchase and sale agreement other than this Agreement, in each case, without SCE’s prior written consent.

Within thirty (30) days after the Effective Date, Seller shall provide to SCE a P50 (median) production analysis for each hour in the year accounting for interannual resource variability and the final design (the “P50 Engineering Assessment”) of the Project as of the contract Effective Date. The P50 Engineering Assessment shall be conducted using standard practices in project financing. Seller shall promptly provide to SCE any updates or revisions to its P50 Engineering Assessment within ten (10) Business Days after receipt thereof.

Notwithstanding anything contained in this Agreement to the contrary, throughout the Term, SCE shall retain the right to review any proposed changes to Attachment 2 and accept or reject such changes in its sole discretion.

Provision of Information.

Items to be provided by Seller pursuant to Section 4.04 shall include:

All final and revised copies of material reports, studies and analyses furnished by the CAISO or any T&D Provider, and any correspondence related thereto, concerning the interconnection of the Project to the T&D Provider’s electric system or the transmission of energy on the T&D Provider’s electric system;

All notifications of adjustments in the DLF used by the T&D Provider in the administration of the transmission service agreement for the Project within thirty (30) days of receiving such notification from the T&D Provider, if a DLF is applicable to the Project;

[The names of the Interconnection Point and the Delivery Point within thirty (30) days after Seller’s receipt of such information from the T&D Provider or CAISO, as applicable;] {SCE Note: Applicable if the official names of the Interconnection Point or Delivery Point are not known as of the Effective Date}

All applications and approvals or disapprovals relating to CEC Pre-Certification, CEC Certification, CEC Verification, any Permit and PIRP/EIRP (if SCE requests Seller to apply to be in PIRP/EIRP);

All [reports prepared by an Independent Engineer concerning the energy producing potential of the Site or assessing the solar resource potential at the Site] [Geothermal Reservoir Report] [Final Wind Report] {SCE Note: select appropriate technology or remove}, and any revisions thereto, for the time period beginning on the Effective Date and ending on the last day of the first Term Year; and

[Notice of the Federal Production Tax Credit the Project is eligible to receive (in $/kWh, the “Federal Production Tax Credit Amount”), no later than thirty (30) days prior to the Expected Initial Delivery Date and five (5) Business Days after any change to such amount. Seller’s Notice shall include documentation sufficient to substantiate, to SCE’s reasonable satisfaction, such amount and the Project’s eligibility to receive such amount. The Federal Production Tax Credit Amount provided by Seller shall be effective commencing the first (1st) day of the calendar month after Seller provides such Notice.]. {SCE NTD: subsection (f) is only applicable to Projects utilizing the Federal Production Tax Credit; for other Projects, delete subsection (f) in its entirety and delete “; and” in subsection (e) and include a “.” at the end thereof}

Interconnection; metering; testing

  - Transmission and Interconnection.

Additional interconnection requirements for the Project pursuant to Section 5.01 shall include:

Intentionally Omitted.

Intentionally Omitted

Seller shall obtain and maintain throughout the Delivery Period any and all interconnection and transmission service rights and Permits required to effect delivery of the energy from the Project to the Delivery Point.

Seller shall comply with the CAISO Tariff, including securing and maintaining in full force all required CAISO agreements, certifications and approvals.

Seller shall secure through the CAISO the Resource ID that is to be used solely for the Project.

Metering, Communications, Dispatch and Telemetry.

Throughout the Delivery Period, all communication, metering, telemetry, and associated operation equipment will be centralized into the Project’s SCADA.

Throughout the Delivery Period, Seller shall configure the SCADA so that SCE may access it via an automated system to remotely monitor, dispatch, and control the Project in real-time (“Generation Management System” or “GMS”) from SCE’s Generation Operations Center. Seller shall link the systems via an approved SCE communication network, utilizing existing industry standard network protocol, as approved by SCE. The connection will be bidirectional in nature and used by the Parties to exchange all data points to and from the Generation Operations Center.

Throughout the Delivery Period, Seller shall be responsible for the costs of installing, configuring, maintaining and operating the SCADA and internal site links for the Project. Seller shall, at its own cost, install, maintain and test all CAISO Approved Meters pursuant to the CAISO Tariff.

Throughout the Delivery Period, Seller shall be responsible for designing, furnishing, installing, operating, maintaining and testing a real-time Telemetry System capable of interconnecting to the GMS, the CAISO Approved Meters, and the Project’s control system with the CAISO infrastructure network (data highway) used by all CAISO participants to exchange data to and from resources and CAISO (the “Energy Communication Network”).

The Telemetry System shall be designed in accordance with the CAISO monitoring and communication requirements, must include a remote intelligent gateway, internet connection, interconnecting cabling and all service agreements required for accessing the Energy Communication Network, and must be capable of:

Reporting data from the CAISO Approved Meter;

Providing the status of key control points from the Project’s control system;

Routing resource unit set points to the Project’s control system;

Communicating availability of the Project pursuant to Section 5.02(f) of this Attachment 1 (Real-Time Communication of Availability via Web Client); and

Controlling the Project from multiple locations to dispatch the Project for Energy, Ancillary Services, and Supplemental Energy functions.

The above-mentioned connections and data transfer must be fully functional prior to the Initial Delivery Date.

Throughout the Delivery Period, Seller shall promptly notify SCE of any malfunction, outage or other condition affecting above-mentioned connections and data transfer between the Project and SCE’s GMS that could impair the ability of the Project to respond to Dispatch Instructions or SCE’s ability to monitor the Project by telephoning Real-Time Scheduling at the telephone number(s) listed in Exhibit E, and by entering outage information as required by the CAISO Tariff, both within ten (10) minutes after the commencement of the event. Seller shall promptly prepare and provide to SCE, using the Web Client or email to Real-Time Scheduling as instructed by SCE, all reports related to such event that SCE may reasonably require for purposes of compliance with Applicable Laws.

Real-Time Communication of Availability via Web Client.

Prior to the Initial Delivery Date, Seller shall install a telecommunication system and demonstrate to SCE’s reasonable satisfaction that the system interfaces with the Web Client and the GMS to provide SCE with Seller’s cumulative available capacity of the Project on a real-time basis.

Seller shall maintain the telecommunications path, the hardware, and software to provide quality data to SCE throughout the Delivery Period.

Upon Notice from SCE, Seller shall repair or have corrected as soon as possible, but no later than five (5) days after receipt of such Notice any:

Inoperable telecommunications path;

Inoperable software; or

Faulty instrumentation.

Check Meter.

Seller will permit SCE to furnish and install one (1) or more, depending on final design configuration, SCE revenue-quality meter section or meter, which will include those devices normally supplied by SCE or Seller under the applicable utility electric service requirements (a “Check Meter”) for each CAISO Approved Meter on the high voltage side of the step-up transformer, substation, or any other location at SCE’s sole discretion, associated with the Project in compliance with the applicable utility electric service requirements. Each Check Meter must be interconnected with SCE’s communication network to permit:

Periodic, remote collection of revenue quality meter data; and

Back-up real-time transmission of operating-quality meter data.

SCE may test and recalibrate the Check Meter(s) at least once every Calendar Year. The Check Meter(s) will be locked or sealed, and the lock or seal will be broken, only by a SCE representative. Seller has the right to be present whenever such lock or seal is broken. SCE may replace the battery of the Check Meter(s) at least once every thirty-six (36) months; provided, if a Check Meter battery fails, SCE may promptly replace such battery.

SCE may routinely compare the Check Meter data to the CAISO Approved Meter data after adjusting the Check Meter for any compensation introduced by the CAISO into the CAISO Approved Meter.

If the deviation between the CAISO Approved Meter data and the Check Meter data for any comparison is greater than point three percent (0.3%), SCE shall provide Notice to Seller of such deviation and the Parties will mutually arrange for a meter check or recertification of the Check Meter or CAISO Approved Meter, as applicable.

SCE will bear its own costs for any meter check or recertification of the Check Meter.

Testing procedures and standards for the Check Meters will be the same as for a comparable SCE-owned revenue-grade meter. Seller has the right to have representatives present during all such tests.

SCE Access.

Seller shall take all actions and execute all documents reasonably necessary to grant SCE access to all metering, communications, and telemetry systems specified in this Section 5.02 throughout the Delivery Period, including all CAISO Approved Meters and Check Meters. Seller shall promptly provide SCE access to all meter data and data acquisition services both in real-time, and at later times, as SCE may reasonably request.

CAISO Approved Meters.

Seller shall install, maintain, test and calibrate all CAISO Approved Meters, as necessary, but in no event will the period between testing and calibration dates be greater than twelve (12) months.

Seller shall bear its own costs for any meter check or recertification of the CAISO Approved Meters.

Seller shall replace each CAISO Approved Meter battery at least once every thirty-six (36) months or such shorter period as may be recommended by the CAISO Approved Meter manufacturer.

Notwithstanding the foregoing, if a CAISO Approved Meter battery fails, Seller shall replace such battery within one (1) day after becoming aware of its failure.

Seller shall use certified test and calibration technicians to perform any work associated with the CAISO Approved Meters.

Seller shall inform SCE of test and calibration dates, provide SCE with access to observe and witness such testing and calibration, and provide SCE certified results of tests and calibrations within thirty (30) days after completion.

[Meteorological Station(s) and Reporting Requirements.] {SCE Note: Intermittent Only, replace with “Intentionally Omitted” for all other technologies}

[Seller, at its own expense, shall install and maintain one (1) or more stand-alone meteorological stations at the Project in accordance with Exhibit K to monitor and report weather data to both the CAISO and SCE.

The station(s) must be installed at least sixty (60) days before Commercial Operation.

The station(s) must be equipped with Meteorological Equipment, as may be modified by Seller at SCE’s direction from time to time to reflect the CAISO’s PIRP/EIRP protocol and the requirements of Exhibit K.

The station(s) must be designed to collect and record data in accordance with CAISO’s PIRP/EIRP protocols and the requirements of Exhibit K.

Seller shall submit to SCE for review and approval, Seller’s technical specifications for the meteorological station(s) along with a site plan showing the location of the station(s), the location of all [photovoltaic modules, inverters,] [Wind Turbines, the wind rose for the Site,] [Solar Generating Units,] and other prominent features, as applicable. {SCE Note: Intermittent only}

[Seller shall calibrate all first- and second-class thermopile pyranometers to the same nationally recognized standard and apply temperature correction to the measurement. Seller’s Telemetry System shall transmit the calibrated data to SCE. Such temperature correction shall be based upon a calibration of the actual instrument or to a generic temperature curve that is supported by data from a nationally recognized testing laboratory to be representative of the exact vintage and model of instruments to be used by Seller. Furthermore, Seller shall calibrate all thermopile pyranometers, regardless of type, every Calendar Year and upon SCE’s reasonable request.] {SCE Note: applicable to Solar PV only}

Additional Metering and Telemetry Obligations.

Seller shall install, or cause to be installed, and bear all costs of installing all CAISO Approved Meters, any additional meters, and any related facilities or equipment that may be required for the Project. The final metering scheme for the Project shall be subject to SCE approval, not to be unreasonably withheld.

The Project will have separate telemetry and meteorological equipment to provide data and telemetry for each component in accordance with CAISO Tariff. Such data requirements will include forecasts for the high sustainable limit for Variable Energy Resource or VER components. Throughout the Delivery Period, Seller will submit telemetry and meteorological data for all VER components of the Project, including high sustainable limit, to SCE and CAISO.

Testing.

Demonstration of Contract Capacity[, and RA Capacity Qualification]. {SCE NTD: bracketed language applicable to Projects with FCDS, delete bracketed language for Energy Only Projects}

Intentionally Omitted.

Demonstration of Contract Capacity. At least thirty (30) days prior to the Expected Initial Delivery Date, the following tests shall be conducted to establish the Demonstrated Contract Capacity [and the Demonstrated DC Rating Capacity] {SCE Note: applicable to Solar only} (the “Renewable Capacity Test”).

Seller shall provide at least [thirty (30) days prior Notice to SCE of the date] {SCE Note: applicable to Intermittent only} [ten (10) Business Days prior Notice to SCE of the date and hour (“Demonstration Hour”)] {SCE Note: applicable to Baseload only} during which the Renewable Capacity Test shall occur. Upon SCE’s request, Seller shall make reasonable efforts to reschedule the Renewable Capacity Test.

[During the Renewable Capacity Test, SCE shall complete a site visit (physically or virtually) to verify that the Project was developed in accordance with Attachment 2 and to determine the Demonstrated Contract Capacity [and the Demonstrated DC Rating Capacity.] {SCE Note: applicable to Solar PV only}] {SCE Note: Intermittent Only}

[Unless SCE provides timely Notice to Seller that additional days are required to substantiate data, SCE shall, within thirty (30) days after Seller’s Notice of the Demonstration Hour, retrieve interval data downloaded from each applicable CAISO Approved Meter or each applicable Check Meter for the twelve (12) hour periods before and after the Demonstration Hour; and SCE may, at its sole discretion, complete a site visit within thirty (30) days after the Renewable Capacity Test to verify that the Project was developed in accordance with the Attachment 2 and Attachment 3.] {SCE Note: applicable to Baseload only}

[RA Capacity Assessment.

Regulatory RA Qualification Activities. In sufficient time to achieve the Initial Delivery Date by the Expected Initial Delivery Date, and in no event later than sixty (60) days prior to the Initial Delivery Date, Seller shall undertake and complete any and all Regulatory RA Qualification Activities required by the CPUC, the CAISO, or any other applicable Governmental Authority, and provide all information required by the CPUC, the CAISO, or any other applicable Governmental Authority, in order for the Seller to obtain published results from the CAISO and the CPUC identifying the Project’s Capacity Attributes.

SCE RA Capacity Demonstration.

In sufficient time to achieve the Initial Delivery Date by the Expected Initial Delivery Date, and in no event later than sixty (60) days prior to the Initial Delivery Date, Seller shall schedule and complete an SCE RA Capacity Demonstration, and provide all information required by SCE, in order for SCE to assess the Project’s Capacity Attributes.

If the SCE RA Capacity Demonstration demonstrates that the Project is eligible for Capacity Attributes that are different from the Project’s Capacity Attributes recognized by the CAISO, the CPUC, or any other applicable Governmental Authority, then SCE may seek guidance from, and provide such results and associated information to, the CPUC and the CAISO.

The Parties shall cooperate in good faith to accurately report to the CPUC and the CAISO Project’s Capacity Attributes.] {SCE NTD: applicable to Projects with FCDS, delete and replace with “Intentionally Omitted” for Energy Only Projects}

[Other Periodic Testing After the Initial Delivery Date.] {SCE NTD: this subsection (b) is applicable to Projects with FCDS, delete and replace with “Intentionally Omitted” for Energy Only Projects}

Regulatory RA Qualification Activities.

Throughout the Delivery Period, Seller shall schedule and complete any and all Regulatory RA Qualification Activities and provide all information required by the CPUC, any other applicable Governmental Authority, or the CAISO, in order for the Seller to maintain and obtain updated published results from the CAISO and the CPUC identifying the Project’s Capacity Attributes.

Testing Costs. Seller is responsible for all costs associated with all tests conducted in accordance with this Section 5.03 of this Attachment 1 and all costs associated with providing any information related to such tests.

Testing Records. Seller shall maintain and provide to SCE, within fifteen (15) days after SCE’s request, accurate records with respect to all tests conducted in accordance with this Section 5.03 of this Attachment 1 including the outcomes of such tests.

[Additional Requirements for Regulatory RA Qualification Activities and SCE RA Capacity Demonstration.] {SCE NTD: this subsection (e) is applicable to Projects with FCDS, delete and replace entire section with “Intentionally Omitted” for Energy Only Projects}

Testing Notification and Attendance.

Seller shall provide SCE with at least seven (7) Business Days’ Notice of Seller’s proposed dates for all Regulatory RA Qualification Activities and SCE RA Capacity Demonstration. SCE shall be entitled to have at least one (1) representative from SCE and one (1) independent third-party witness present, physically or virtually, at SCE’s discretion, to witness each such test and such persons shall be allowed unrestricted access to the area from where the plant is being controlled (e.g., plant control room), and unrestricted access to inspect the instrumentation used for test data acquisition prior to commencement of any test.

Testing Results Notification.

Seller shall provide all Regulatory RA Qualification Activities and SCE RA Capacity Demonstration results to SCE throughout the Term within three (3) Business Days after Seller’s receipt.

Within fifteen (15) Business Days after the completion of any Regulatory RA Qualification Activities or SCE RA Capacity Demonstration, Seller shall prepare and submit to SCE a written report of such test. The report shall include: (A) a record of any unusual or abnormal conditions or events that occurred during such test and any actions taken in response thereto, and (B) the measured data.

Updated NQC or EFC.

Seller shall notify SCE within three (3) Business Days after it, or the Project’s SC, receives notice from the CAISO, or Seller or the Project’s SC becomes aware, that the NQC or EFC for the Project has changed, regardless of whether there is an increase or decrease in any such NQC or EFC.

CAISO Certification and CEC Certification.

Seller shall provide all CAISO Certification test results for each initial or subsequent test of the Project, within three (3) Business Days after Seller’s receipt. Nothing in this Agreement shall be amended to reflect the outcome of any CAISO Certification.

Within one hundred eighty (180) days after the Effective Date, Seller shall file an application or other appropriate request for provisional certification of the proposed Project as an ERR by the CEC upon submission by a facility of a complete CEC pre-certification application and required supplemental information (“CEC Pre-Certification”).

Within thirty (30) days after the Initial Delivery Date, Seller shall file an application or other appropriate request with the CEC for certification by the CEC that the Project is an ERR for purposes of the California Renewables Portfolio Standard and that all energy produced by the Project qualifies as generation from an ERR for purposes of the California Renewables Portfolio Standard (“CEC Certification”).

Seller shall take all necessary steps, including making or supporting timely filings with the CEC, to obtain and to maintain throughout the Delivery Period (i) CEC Certification and (ii) verification by the CEC based on ongoing reporting by Seller that Project is an ERR for purposes of the California Renewables Portfolio Standard and that all energy produced by the Project qualifies as generation from an ERR for purposes of the California Renewables Portfolio Standard (“CEC Verification”).

Upon request by SCE, Seller shall provide copies of all correspondence and documentation exchanged between the CEC and Seller.

operation, maintenance and repair obligations

  - Seller’s Operation and Record Keeping Obligations.

{Subject To Change Based on Technology}

Seller’s operation and record keeping obligations pursuant to Section 6.01 shall include:

Throughout the Delivery Period, Seller shall maintain all records applicable to the Project, including the electrical characteristics of the Project and settings or adjustments of the Project control equipment (including the power conversion system) and protective devices, and a daily log of maintenance (both breakdown and preventative) performed, outages, changes in operating status, manufacturer recommended services and replacement, inspections, electrical characteristics of the Project, control settings or adjustments of equipment and protective devices, and any other significant events related to the operation of the Project.

Throughout the Delivery Period, Seller shall maintain a daily operations log for each Project, which shall include the following information:

Availability, including availability of the [Inverter Block Units and associated inverters,] {SCE Note: applicable to Solar PV only} [Project] {SCE Note: applicable to all other technologies},

Circuit breaker trip operations,

Any significant events related to the operation of the Project or changes in operating status,

Real and reactive energy production and consumption,

Protective apparatus operations, and

Any unusual conditions found during inspections.

At SCE’s request, Seller shall make all reasonable efforts to deliver Energy to the Delivery Point at an average rate of delivery at least equal to the maximum interconnection capacity associated with the Project during periods of CAISO-declared system emergency for as long as necessary to respond to the CAISO-declared system emergency;

Throughout the Term, Seller shall maintain documentation of all procedures applicable to the testing and maintenance of the Project’s protective devices as necessary to comply with NERC Reliability Standards applicable to protection systems for large electric generators, if Seller is required to be a registered entity pursuant to the NERC Reliability Standards;

At least thirty (30) days prior to the start of the Delivery Period, and whenever such information changes during the Delivery Period, within ten (10) days after such change, Seller shall provide accurate and complete operating characteristics of the Project in compliance with the CAISO Tariff;

Throughout the Term, Seller shall comply with CAISO operating orders, the CAISO Tariff, and Applicable Laws relating to the Product. SCE shall have no liability for the failure of Seller to comply with such CAISO operating orders, the CAISO Tariff, or Applicable Laws, including any penalties, charges or fines imposed on Seller for such noncompliance;

Throughout the Delivery Period, in the event of any conflict between any Dispatch Instruction and any CAISO operating instructions, CAISO Tariff provisions, and Applicable Laws relating to the Product, Seller shall (i) immediately notify SCE of the conflict and (ii) comply with the CAISO operating instructions, CAISO Tariff provisions, or Applicable Laws, to the extent that they conflict with such Dispatch Instruction, while such conflict persists;

[Throughout the Term, maintain complete records of the Project’s plane of array insolation, other pertinent meteorological conditions and operational status of each Inverter Block Unit.] {SCE Note: applicable to Solar PV only}

[Throughout the Term, log changes in the generator output setting if it is “block-loaded” to a specific kW capacity.] {SCE Note: applicable to Baseload only}

[Throughout the Term, maintain complete records of the Project’s wind speeds and other pertinent meteorological conditions and operational status of each Wind Turbine.] {SCE Note: applicable to Wind only}

[Throughout the Term, maintain complete records of the Project’s direct normal insolation, other pertinent meteorological conditions and operational status of each Solar Generating Unit.] {SCE Note: applicable to Solar Thermal only}

[Throughout the Term, maintain complete records of the Project’s fuel consumption if a biomass or landfill generating facility, or geothermal fluid consumption if a geothermal generating facility.] {SCE Note: applicable to Biomass and Geothermal only}

Curtailment.

Seller shall promptly curtail the production of the Project:

Upon notice from SCE that Seller has been instructed by the CAISO or T&D Provider to curtail energy deliveries; provided, solely the action of the CAISO issuing a Schedule shall not by itself, without other factors, constitute an instruction by the CAISO to curtail energy deliveries pursuant to this Section 6.01(b)(i) of this Attachment 1;

Upon notice that Seller has been given a curtailment instruction or similar instruction in order to respond to an Emergency; or

If SCE issues a Curtailment Order.

Notices of curtailment may be oral, written, or sent via the Telemetry System, and must be made in accordance with accepted industry practices for such notices.

Scheduling Coordinator.

SCE as Scheduling Coordinator.

Throughout the Delivery Period, Seller shall not authorize or designate any other party to act as SC, nor shall Seller perform for its own benefit the duties of SC, and Seller shall not revoke SCE’s authorization to act as SC unless agreed to in writing by SCE. SCE, in its capacity as SC, shall submit bids and schedules to the CAISO in accordance with the CAISO Tariff. Seller shall reasonably cooperate with SCE in performing any actions necessary prior to the start of the Delivery Period to allow the Project to be (x) dispatched (or otherwise scheduled to operate) for the first day of the Delivery Period and (y) reported to or scheduled with the CAISO pursuant to the CAISO Tariff, either through the CAISO’s outage management system or as otherwise required by the CAISO.

No later than two (2) weeks prior to the first day of the Delivery Period, Seller shall take all actions necessary with the CAISO and SCE to ensure that by the day immediately prior to the first (1st) day of the Delivery Period, the Master File and the RMR Contract, if applicable, reflect the values that SCE deems appropriate based on the requirements set forth in this Agreement. If, at any time prior to the termination of this Agreement, any action or inaction of Seller, or a condition of the Project could result in a revision to the Master File or to an RMR Contract (if applicable), then Seller shall promptly give Notice to SCE.

Seller is responsible for and shall pay SCE an “SC Set-Up Fee” equal to twenty thousand dollars ($20,000).

SCE’s Scheduling Coordinator Obligations.

SCE’s obligations, in its capacity as SC, shall be limited to the following:

CAISO Notices. Throughout the Delivery Period, subject to Seller complying with its obligations under this Agreement, SCE, as SC, shall transfer Dispatch Notices from the CAISO to Seller, and transfer outage information provided by Seller to the CAISO.

CAISO Settlements. Throughout the Delivery Period, SCE, as SC, shall be responsible for all settlement functions with the CAISO related to the Project, including, if applicable, as RMR Contract settlement coordinator in accordance with the terms of this Agreement. Seller shall cooperate with SCE in SCE’s performance of any settlement functions, and Seller shall promptly deliver to SCE all Project data and any correspondence or communications with the CAISO related to the Project, including any invoices or settlement data, in the format reasonably requested by SCE.

Terminating SCE’s Designation as SC. At least thirty (30) days prior to the expiration of the Delivery Period, or, in the event of an Early Termination Date being declared, two (2) Business Days prior to the Early Termination Date, the Parties will take all actions necessary to terminate the designation of SCE as SC as of the hour ending 12:00 a.m. on the final date of the Delivery Period (“SC Replacement Date”). Such actions include the following:

Seller shall (A) submit to the CAISO a designation of a new SC to replace SCE effective as of the SC Replacement Date, and (B) cause its newly designated SC to submit a letter to the CAISO accepting the designation; and

SCE shall submit a letter to the CAISO resigning as SC effective as of the SC Replacement Date.

Seller bears sole responsibility for locating, selecting, and reaching agreement on terms with any replacement SC.

Outages.

Scheduled Outages.

Quarterly Outages Schedule. Sixty (60) days prior to the Expected Initial Delivery Date and throughout the Delivery Period, Seller shall, no later than January 1, April 1, July 1 and October 1 of each year submit to SCE, using the Web Client, the proposed schedule of scheduled outages, including any reduction in capacity of any component of the Project (“Outage Schedule”), for the following twenty-four-month period. If the Web Client is not available, Seller shall submit the Outage Schedule in substantially the form set forth in Exhibit H. Seller shall provide the following information for each proposed scheduled outage:

Description of the work to be performed during the scheduled outage;

Start date and time;

End date and time; and

Contract Capacity online, in MW, during the scheduled outage.

SCE’s Outage Schedule Change Request. SCE shall notify Seller in writing of any request for changes to the Outage Schedule, and Seller shall, consistent with Prudent Electrical Practices, accommodate SCE’s requests regarding the timing of any scheduled outage. If SCE’s request to change the timing of any scheduled outage would result in Seller incurring incremental costs in excess of, or a reduction in revenue relative to, what would have been incurred without the scheduled outage timing change requested by SCE, then within five (5) Business Days after receipt of SCE’s request Seller shall provide reasonable documentation to SCE of the cost and/or revenue impact that would be incurred by Seller and SCE may either:

agree to reimburse (subject to audit by SCE) Seller for such cost and/or revenue impact or

withdraw its request for such change in scheduled outage timing.

Outage Schedule Revisions. If a condition occurs which causes Seller to revise its scheduled outages, Seller shall promptly provide Notice to SCE, using the Web Client (with a second Notice to SCE’s Outage Desk if the scheduled outage is more than three months in the future), of such change (including an estimate of the length of such scheduled outage) as required in the CAISO Tariff after the condition causing the change becomes known to Seller.

Outage Confirmation. In addition to providing the Outage Schedule, Seller must provide Notice to SCE at least sixty (60) days prior to the start of any scheduled outage, confirming such outage.

Notices During Outage. Upon commencement of any scheduled outage and continuing throughout the end of such outage, Seller shall notify SCE, using the Web Client, of: (A) any change to the Outage Schedule, (B) the outage’s actual start time, (C) the outage’s actual end time, (D) Ancillary Services actually available, (E) PMAX actually available, (F) PMIN actually available, (G) the Contract Capacity actually available, and (H) any other condition, data point, or information required by the CAISO Tariff.

Additional Outage Requirements.

Seller shall cooperate with SCE to arrange and coordinate all Outage Schedules with the CAISO in compliance with the CAISO Tariff.

Seller shall promptly prepare and provide to SCE upon request, using the Web Client, all reports of actual or forecasted outages that SCE may reasonably require for the purpose of enabling SCE to comply with Section 761.3 of the California Public Utilities Code, the CAISO Tariff, or any Applicable Law mandating the reporting by investor-owned utilities of expected or experienced outages by energy generating facilities under contract to supply energy.

Seller shall promptly prepare and provide to SCE, using SCE-provided software or forms, all reports of scheduled outages during the Delivery Period that SCE may reasonably require for the purpose of enabling SCE to comply with any Applicable Laws.

No Scheduled Outages During Restricted Months. Unless agreed in writing and coordinated in advance by the Parties, no outages shall be scheduled or planned from each June 1 through October 31 during the Delivery Period. If Seller has a previously scheduled outage that becomes coincident with a CAISO-declared system emergency, then Seller shall make all reasonable efforts to reschedule such scheduled outage.

Forced Outages.

Notice. Throughout the Delivery Period, Seller shall: (1) within ten (10) minutes after commencement of any Forced Outage, enter outage information utilizing SCE’s Web Client, as required by the CAISO Tariff; and (2) within twenty (20) minutes after commencement of any Forced Outage, telephone SCE’s Generation Operations Center and Real-Time Scheduling, as set forth in Exhibit E.

CAISO Sanctions and Penalties. If the CAISO imposes a sanction or penalty upon SCE, as Seller’s SC, due to Seller’s failure to timely provide SCE with a report of a Forced Outage or scheduled outage, Seller shall be responsible for such sanction or penalty.

Inspection. SCE shall have the right to inspect the Project and all records relating to any Forced Outage during the Delivery Period on any Business Day and at a reasonable time and Seller shall reasonably cooperate with SCE during any such inspection.

Reports of Forced Outages. Seller shall promptly prepare and provide to SCE, using SCE-provided software or forms, all reports of Forced Outages during the Delivery Period that SCE may reasonably require for the purpose of enabling SCE to comply with any Applicable Laws.

Operational Notices.

Dispatch Instructions.

Throughout the Delivery Period, SCE will have the right to dispatch the Project up to PMAX or down to PMIN, seven (7) days per week and twenty-four (24) hours per day (including holidays), by providing Dispatch Instructions to Seller electronically (in a form provided by SCE, in its sole discretion), and subject to the requirements and limitations set forth in this Agreement. Each Dispatch Instruction will be effective unless and until SCE modifies such Dispatch Instruction by providing Seller with an updated Dispatch Instruction. If an electronic submittal is not possible for reasons beyond SCE’s control, SCE may provide Dispatch Instructions by (in order or preference, unless the Parties agree to a different order) electronic mail, facsimile transmission or telephonically to Seller’s personnel designated in Section 6.04(c) of this Attachment 1 to receive such communications. In addition to any other requirements set forth in this Agreement, all Dispatch Instructions will be made in accordance with market notice timelines as specified in the CAISO Tariff.

Writing Requirements.

In documenting and confirming Dispatch Instructions, conversations between the Parties’ personnel and contractors may be recorded by tape or other electronic means and any such recording will satisfy any “writing” requirements under Applicable Laws. Such recordings shall be made available to both SCE and Seller upon request for settlement purposes.

Communication Protocols.

The communication protocols in this Section 6.04(c) of this Attachment 1 shall be modified, at SCE’s reasonable discretion, as market conditions and rules evolve.

Intra-day Communication.

All communications and notices between the Parties that occur intra-day and intra-hour for the applicable day including those regarding emergencies, Dispatch Instructions, and notices to avoid imbalance penalties, Uninstructed Deviation charges/credits or any other CAISO charges, and shall be provided electronically or telephonically as SCE directs to the applicable Party.

If to Seller, such notices and communications shall be provided to the following contact, in order of priority, (1) [___________], (2) [___________], (3) [___________]. If to SCE, such notices and communications shall be provided to Real-Time Scheduling. Each Party shall confirm all intra-day communication either electronically or via telephone as soon as practicable.

Communication Failure.

In the event of a failure of the primary communication link between Seller and SCE, both Parties will try all available means to communicate, including cell phones or additional communication devices.

System Emergency.

SCE and Seller shall communicate as soon as possible all changes to the schedule requested by the CAISO as a result of a system emergency.

Staffing.

During the Delivery Period, the Parties will have available 24 hours a day, seven days a week, personnel available to communicate regarding the implementation of this Section 6.04(c) of this Attachment 1.

Lost Output Report.

Monthly Report; SCE Review.

Commencing on the Initial Delivery Date and continuing throughout the Delivery Period, Seller shall calculate Lost Output and prepare and provide to SCE a Lost Output Report by the tenth (10th) Business Day of each month that is within the Delivery Period, in accordance with Exhibit J. SCE will have sixty (60) days after receipt of Seller’s monthly Lost Output Report or Supplemental Lost Output Report to review such report. Upon SCE’s request, Seller shall promptly provide to SCE any additional data and supporting documentation necessary for SCE to audit and verify any matters in the Lost Output Report.

Disputes of Lost Output.

If SCE disputes Seller’s Lost Output calculation, SCE shall provide Notice to Seller within thirty (30) days after receipt of Seller’s Lost Output Report and include SCE’s calculations and other data supporting its position.

The Parties shall negotiate in good faith to resolve any Disputes regarding the Lost Output calculation.

Seller will have no right to claim any Lost Output for any month or any Lost Output Event that was not identified in the original Lost Output Report for that month; provided, Seller may supplement the amount of Lost Output claimed (“Supplemental Lost Output”) for a month with a supplemental Lost Output Report (“Supplemental Lost Output Report”) if Seller can demonstrate that Seller neither knew nor could have known through the exercise of reasonable diligence about the Supplemental Lost Output during such month and Seller provides the Supplemental Lost Output Report within ten (10) Business Days after learning the facts which provide the basis for the Supplemental Lost Output claim; provided further, in no event will SCE be obligated to accept a Supplemental Lost Output Report after thirty (30) days following the end of the applicable Term Year.

Forecasting.

Seller shall provide SCE a forecast of the Project’s available capacity (in MW) and energy (in MWh) (“Forecast”), via the Web Client (a) no later than thirty (30) days prior to the Expected Initial Delivery Date and continuing [until the Project has a CAISO VER Forecast, or for any portion of the Delivery Period that the Project’s CAISO VER Forecast is unavailable] {SCE Note: bracketed language applicable to intermittent} [throughout the Delivery Period] {SCE Note: bracketed language applicable to Baseload}, and (b) if the CAISO VER Forecast is materially inaccurate or incomplete, then upon SCE’s request. Seller shall provide its Forecast to SCE for each Settlement Interval and at the frequency determined by SCE, such that the Forecast is sufficient to allow SCE to Schedule the Project and comply with any CAISO Tariff requirements, including to allow for automated forecast and outage submissions. Any Forecast submitted must not include any anticipated or expected electric energy losses after the CAISO Approved Meter or Check Meter.

- Representations, warranties, and covenants

  - Additional Seller Representations and Warranties.

Seller and, if applicable, its successors, represents and warrants that throughout the Delivery Term of this Agreement:

Seller warrants that all necessary steps to allow the Renewable Energy Credits transferred to Buyer to be tracked in the Western Renewable Energy Generation Information System will be taken prior to the first delivery under the contract. {SCE Note: green highlighted text constitutes an RPS non-modifiable term (D.11-01-025)}

Seller has no knowledge of any plans by SCE or another T&D Provider to seek to construct a transmission or distribution line through or on the Site.

The energy generated with the Green Attributes delivered under this Agreement was not and will not be separately sold, marketed, reported, or otherwise represented as renewable energy, renewable electricity, clean energy, zero-emission energy, or in any similar manner.

The Project has an interconnection capacity and associated interconnection rights that is at least equal to the Contract Capacity.

  - Seller Covenants.

Seller’s covenants pursuant to Section 9.04 include:

[The Project shall have Full Capacity Deliverability Status in an amount equal to the Contract Capacity.] {SCE NTD: this subsection (a) is applicable to Projects with FCDS, delete and replace entire section with “Intentionally Omitted” for Energy Only Projects}

Intentionally Omitted.

Intentionally Omitted.

Throughout the Delivery Period, Seller will not use, grant, pledge, assign or otherwise commit any portion of the generating capacity of the Project to meet the Resource Adequacy Requirements of, or to confer Resource Adequacy Benefits on, any entity other than SCE.

Seller shall take all actions necessary for the Project to qualify and be certified by the CEC as an ERR and to qualify under the requirements of the California Renewables Portfolio Standard.

Seller, and, if applicable, its successors, represents and warrants that throughout the Delivery Term of this Agreement that:

The Project qualifies and is certified by the CEC as an Eligible Renewable Energy Resource (“ERR”) as such term is defined in Public Utilities Code Section 399.12 or Section 399.16; and

The Project’s output delivered to Buyer qualifies under the requirements of the California Renewables Portfolio Standard.

To the extent a change in law occurs after execution of this Agreement that causes this representation and warranty to be materially false or misleading, it shall not be an Event of Default if Seller has used commercially reasonable efforts to comply with such change in law. {SCE Note: subsection (f) in green highlighted text constitutes an RPS non-modifiable term (D.08-04-009)}

Seller and, if applicable, its successors, represents and warrants that throughout the Delivery Term of this Agreement the Renewable Energy Credits transferred to Buyer conform to the definition and attributes required for compliance with the California Renewables Portfolio Standard, as set forth in California Public Utilities Commission Decision 08-08-028, and as may be modified by subsequent decision of the California Public Utilities Commission or by subsequent legislation. To the extent a change in law occurs after execution of this Agreement that causes this representation and warranty to be materially false or misleading, it shall not be an Event of Default if Seller has used commercially reasonable efforts to comply with such change in law. {SCE Note: subsection (g) in green highlighted text constitutes an RPS non-modifiable term (D.11-01-025)}

EVENTS OF DEFAULT

  - Additional Seller Events of Default.

In addition to those Events of Default listed in Section 10.01(b), with respect to Seller, the occurrence of any of the following shall be considered an Event of Default:

Seller removes equipment from the Site that the Demonstrated Contract Capacity has been based, and substantially the same equipment is not returned, within five (5) Business Days after Notice from SCE; provided, Seller may remove equipment from the Site if such removal is necessary for Seller to replace, refurbish, repair or maintain such equipment and such replacement, refurbishment, repair, or maintenance is necessary for Seller to comply with this Agreement; provided further, the foregoing replacement, refurbishment, repair or maintenance of equipment excludes repowers or other modifications to the Project that may result in any payment made by SCE hereunder in excess of the amount that would have been payable as of the Initial Delivery Date;

Seller makes any material misrepresentation or omission in any Outage Schedule or Forced Outage notice;

Seller does not have Site Control in accordance with Section 1.02(j) of this Attachment 1;

Seller transfers or assigns the Interconnection Queue Position or the Interconnection Agreement;

[Seller allows:] {SCE NTD: this subsection (e) is applicable to Projects with FCDS, delete and replace entire section with “Intentionally Omitted” for Energy Only Projects}

the NQC of the Project to fall below seventy-five percent (75%) of the Expected NQC during four (4) months, whether or not consecutive, in any rolling twelve (12) month period, [or

the EFC of the Project to fall below seventy-five percent (75%) of the Expected EFC during four (4) months, whether or not consecutive, in any rolling twelve (12) month period;] {SCE Note: delete bracketed language for IFOM Renewable Projects that are not expected to provide EFC and reformat as needed}

[Seller fails to obtain and maintain Full Capacity Deliverability Status of the Project;] {SCE NTD: this subsection (f) is applicable to Projects with FCDS, delete and replace entire section with “Intentionally Omitted” for Energy Only Projects}

Seller fails to deliver to SCE all of the Capacity Attributes associated with the Project;

Intentionally Omitted;

Intentionally Omitted;

Seller fails to take any actions necessary to dedicate, convey or effectuate the use of any and all Green Attributes for SCE’s sole benefit as specified in Sections 1.01 and 1.07 of this Attachment 1;

The occurrence of an Event of Deficient Energy Deliveries during two (2) Deficiency Calculation Periods, whether consecutive or non-consecutive;

[Seller installs renewable generating capacity in excess of the Demonstrated Contract Capacity and such excess generating capacity is not removed within five (5) Business Days after Notice from SCE;] {SCE Note: Intermittent Only}

[The Metered Amounts in any one hour interval, in kWh, exceed one hundred fifteen percent (115%) of the Contract Capacity of the Project, in kW, to this Agreement, (an “Event of Excess Deliveries”), and within ten (10) Business Days after Notice from SCE, Seller fails to demonstrate to SCE’s satisfaction that Seller has identified the reason that the Event of Excess Deliveries occurred and that Seller has employed or is employing best efforts to ensure that no additional Events of Excess Deliveries will occur throughout the Delivery Period;] {SCE Note: Baseload only}

[Seller installs Direct Current generating capacity in excess of the DC Rating Capacity and such excess Direct Current generating capacity is not removed within five (5) Business Days after Notice from SCE;] {SCE Note: Solar PV only}

The Project consists of an ERR type(s) different than that specified in Section 1.02 of this Attachment 1;

Except where there has been a change in Applicable Laws that would affect Seller’s status as an ERR, and Seller has made commercially reasonable efforts in accordance with Section 9.04(f) of this Attachment 1 to comply with the change in law, the Project fails to qualify as an ERR;

Except where there has been a change in Applicable Law that would affect the eligibility of energy to qualify as renewable energy for the purposes of the California Renewables Portfolio Standard and Seller has made commercially reasonable efforts in accordance with Section 9.04(g) of this Attachment 1 to comply with the change in law, any energy from the Project and sold or to be sold to SCE hereunder fails to qualify as eligible renewable energy for purposes of the California Renewables Portfolio Standard;

[Seller fails to provide to SCE a copy of the certification identified in Public Utilities Code Sections 2821(d)(1) and (e)(1) as evidence of Seller’s compliance with Public Utilities Code Section 2821(c) within thirty (30) days of Seller’s receipt of such documentation from the State Water Resources Control Board or in no event later than sixty (60) days after the Initial Delivery Date.] {SCE Note: Applicable to Hydro only, otherwise delete}

- INDEMNIFICATION; GOVERNMENTAL CHARGES

  - Seller’s Indemnification Obligations.

Seller’s indemnification obligations pursuant to Section 13.02 shall also extend to:

Seller’s failure to provide any portion of the Project’s Capacity Attributes for any portion of the Delivery Period;

[Seller’s failure to timely or accurately submit, or otherwise satisfy its Showing Month Notice for any portion of the Delivery Period;] {SCE NTD: this subsection (b) is applicable to Projects with FCDS, delete and replace entire subsection (b) with “Intentionally Omitted” for Energy Only Projects}

Seller’s [failure to fulfill its obligations regarding Resource Adequacy Benefits as set forth herein, including Seller’s failure to timely provide a Showing Month Notice to SCE and Seller’s] {SCE NTD: bracketed language applicable to Projects with FCDS, delete bracketed language for Energy Only Projects} failure to provide notice of or any malfunction, outage or other condition affecting the Project as required under Article 6, in accordance with this Agreement;

[Seller’s failure to provide SCE with the full amount of Resource Adequacy Benefits associated with the Project (in accordance with then current resource adequacy counting rules);] {SCE NTD: this subsection (d) is applicable to Projects with FCDS, delete and replace entire subsection (d) with “Intentionally Omitted” for Energy Only Projects}

[SCE’s replacement or substitution of any portion of Capacity Attributes associated with the Project that was shown by SCE in its RA Compliance Showings, if SCE is required to replace or substitute such portion in accordance with the CAISO Tariff;] {SCE NTD: this subsection (e) is applicable to Projects with FCDS, delete and replace entire subsection (e) with “Intentionally Omitted” for Energy Only Projects}

Any NERC Standards Non-Compliance Penalties or an attempt by any Governmental Authority, person or entity to assess such NERC Standards Non-Compliance Penalties against SCE, except to the extent solely due to SCE’s negligence in performing its role as Seller’s Scheduling Coordinator throughout the Delivery Period as set forth in Section 6.02 of this Attachment 1;

SCE’s transfer to Seller or Seller’s designee of WREGIS Certificates generated by the Project prior to the Initial Delivery Date pursuant to Section 1.07(b) of this Attachment 1; and

The disqualification by WREGIS or any Governmental Authority of any Renewable Energy Credits transferred to SCE, or the failure to transfer any Renewable Energy Credits to SCE within four (4) months after the generation of the associated Metered Amounts.

ATTACHMENT 2

Project Description

{SCE Note: Applicable to In Front of the Meter Renewables. Do not modify table headers or table formatting}

PART I.	General Project Description

| General Information Table (ID-ATT2-GI) |  |
| --- | --- |
| Element | Entry |
| Delivery Point |  |
| Interconnection Point |  |
| Interconnection Queue Position |  |
| Generation Technology |  |
| Local Capacity Area | [e.g., CAISO System, Big Creek-Ventura, LA Basin] |
| Air Pollution Control District | [e.g., SCAQMD] |
| Interconnection Voltage (kV) |  |

PART IB. Project DESCRIPTION {SCE Note: applicable to solar, delete wind table}

| Table (ID-ATT2-PC) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Component | Manufacturer | Model No. | Rating | Rating Unit | Quantity | Total Rating (Rating x Quantity) |
| Photovoltaic Modules |  |  |  | Rating, in W DC, of a single module |  |  |
| Inverter |  |  |  | Power rating in kW at a specific ambient temperature to be defined (e.g., 800kVA @ 50°C) |  |  |
| Medium Voltage Transformer |  |  |  | Apparent power rating in kVA at a specific ambient temperature to be defined and high/low voltage ratings |  |  |
| Primary Step-Up Transformer |  |  |  | Apparent power rating in kVA at a specific ambient to be defined temperature and high/low voltage ratings |  |  |

{SCE Note: specify fixed tilt, single or dual axis tracking and mono or poly crystalline silicon or thin film, single or bifacial}

PART 1B. Project DESCRIPTION {SCE Note: applicable to wind, delete solar table}

| Table (ID-ATT2-PC) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Component | Manufacturer | Model No. | Rating | Rating Unit | Quantity | Total Rating (Rating x Quantity) |
| Wind Turbine |  |  |  | Rating, in kW AC, of a single WTG |  |  |
| Medium Voltage Transformer |  |  |  | Apparent power rating in kVA at a specific ambient temperature to be defined and high/low voltage ratings |  |  |
| Primary Step- Up Transformer |  |  |  | Apparent power rating in kVA at a specific ambient temperature to be defined and high/low voltage ratings |  |  |

PART II.	PROJECT AND SITE DESCRIPTION.

- Project Description

{SCE Note: Provide a summary of the Project. Seller may provide additional written description of the Project beyond what is summarized in Part II of this Attachment 2}

Site Plan Drawing

{SCE Note: Seller must provide a depiction of the Project, and identify where the Project is located on the Site. Details shall include the Delivery Point, the Interconnection Point (with substation name and voltage), Site boundary, points of ingress and egress, adjacent roads, labels of the Project components, delineation of Seller and SCE equipment, shared facilities, a legend of symbols and acronyms, and an arrow indicating North}

Site Legal Description

{SCE Note: Seller must provide a legal description of the site, including APN number and parcel map}

Site Map

{SCE Note: Seller must provide a minimum of one map each for the following: Site Map 1 shall show the location of the Project within the respective county in which it resides and include major highways and the latitude and longitude of the Project centroid. Site Map 2 shall show the Project location within its immediate area including highways, landmarks, roadways, the site address, latitude(s) and longitude(s) of Project ingress/egress, clear delineation of the Project perimeter/boundary, and interconnection location detail. North arrow is required on both drawings}

PART III.	ELECTRICAL SINGLE LINE DIAGRAM.

{SCE Note: Seller must provide an electrical single line diagram that depicts all the major electrical equipment associated with the Project and the Site (an “over-all” single line diagram), including for the Project, and including inverters, transformers, meters, breakers, etc. Include ratings when possible. This drawing must also show the Interconnection Point, the Delivery Point, auxiliary power, and a legend.

This drawing must include location of the: (1) the CAISO Approved Meter and (2) all Check Meters.

As applicable, differentiation between underground and overhead circuitry and customer versus owner facilities shall be clear. For all electrical drawings, separate drawings depicting both the AC and DC circuits is preferred}

ATTACHMENT 3

Commercial Terms

{SCE Note: Do not modify table headers or formatting}

1.03  Committed Amount.

| Main Committed Amount Table (ID-ATT3-CA) |  |
| --- | --- |
| Element | Entry |
| Expected Contract Capacity (MW) | [include value from selected Offer] |
| Expected AC Nameplate Capacity (MW) | [include value from selected Offer] |
| Expected DC Rating Capacity (kWpdc) {SCE Note: solar only, otherwise delete row} | [include value from selected Offer] |

[1.03(c)  Annual [Degradation] [Production] Factor.] {SCE Note: applicable to Solar and Baseload, delete for Wind. This number should start at 1.00 or 100%}

| Term Year | Annual [Degradation] [Production] Factor |
| --- | --- |
| 1 |  |
| 2 |  |
| 3 |  |
| 4 |  |
| 5 |  |
| 6 |  |
| 7 |  |
| 8 |  |
| 9 |  |
| 10 |  |
| 11 |  |
| 12 |  |
| 13 |  |
| 14 |  |
| 15 |  |
| 16 |  |
| 17 |  |
| 18 |  |
| 19 |  |
| 20 |  |

1.04  Price.

| Price Table (ID-ATT3-PR) |  |
| --- | --- |
| Product Price ($/MWh) | [Dollar amount text] dollars ($[Number]) per MWh [escalated at [Number text] percent ([Number]%) per Term Year] |